## README
Data Center Atlas workbook
Dataset | Data Center Atlas
Updated | 2026-10-13
Observation dates | 2023-12-01 to 2026-10-09
Sites | 395
Projects | 419
Countries | 53
Evidence rows | 2065
Read before using
Each status is the last reported project status as of a dated source (status_as_of), not the status today.
Locators are not building footprints or construction extents; some markers identify only a town or region, not a facility position.
Empty or null values are unknown, never zero.
Coverage is incomplete and varies by country.
Sheets | sites, projects and evidence hold the CSV columns (geometry_json is omitted: use the GeoJSON link in each row), followed by link columns added by the site builder.
Project details | Additional metrics, parties, milestones and power_sources sheets preserve original source scopes. Each source record appears once; an empty project_id identifies a multi-site or unresolved record; source_record_id identifies its original record.
Cells | Empty cells are unknown values, never zero. *_json columns hold JSON text. A cell longer than Excel's limit ends with a truncation note; the CSV files hold the full value.
Licence | Creative Commons Attribution 4.0 International (https://creativecommons.org/licenses/by/4.0/) for Atlas-authored data. Geometries derived from OpenStreetMap: © OpenStreetMap contributors, ODbL-1.0 (https://opendatacommons.org/licenses/odbl/1-0/). Other third-party facts and geometries keep their source terms: see each evidence row and https://kiankyars.github.io/datacenter-atlas/about/attribution/
Cite as | Kyars, K. (2026). Data Center Atlas (2026-10-13) [Data set]. https://kiankyars.github.io/datacenter-atlas/downloads/2026-10-13-research-asia/
Field dictionary | https://kiankyars.github.io/datacenter-atlas/data/dictionary/
Downloads | https://kiankyars.github.io/datacenter-atlas/downloads/2026-10-13-research-asia/
API | https://kiankyars.github.io/datacenter-atlas/api/

## sites
site_id | physical_site_stable_key | name | country | country_iso_a2 | latitude | longitude | geometry_type | geometry_source_entity_kinds_json | geometry_derivations_json | geometry_methods_json | geometry_scope_classes_json | geometry_authority_classes_json | geometry_use_scopes_json | geometry_precision_scopes_json | horizontal_uncertainty_metres | horizontal_uncertainty_unknown_reason | geometry_evidence_ids_json | project_count | project_ids_json | project_stable_keys_json | statuses_json | oldest_status_as_of | newest_status_as_of | verification_posture | independent_imagery_verification | imagery_review_outcomes_json | url | api_url | geojson_url | geometry_licenses
vcc-site-00432e4e9c8e2d91ff76 | imported:semiconductor-atlas:openai-stargate-milam-county | Stargate Milam County (SB Energy campus) | United States | US | 30.7627 | -96.9982 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Milam County centroid from OpenStreetMap Nominatim. Sources name only the county, which Epoch AI places about 70 miles northeast of Austin; no site address was found."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["882a168d-1e56-5d20-99d6-d4e41e2c0cb6"] | 1 | ["316e6c68-21e0-50d1-973e-d4fa5847a99f"] | ["imported:semiconductor-atlas:openai-stargate-milam-county"] | ["under_construction"] | 2026-04-17 | 2026-04-17 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-00432e4e9c8e2d91ff76/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-00432e4e9c8e2d91ff76.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-00432e4e9c8e2d91ff76.geojson | source-terms-not-recorded
vcc-site-004b39e14dadd642b1e8 | curated:microsoft-finland-kirkkonummi-campus | Microsoft Kirkkonummi Datacenter Campus | Finland | FI | 60.1451 | 24.5488 | Point | ["campus"] | ["official_permit_activity_reference_coordinate_transformed"] | ["source_E363900_N6670100_tm35_interpreted_as_EPSG3067_to_EPSG4326"] | ["official_environmental_permit_activity_site_reference_point"] | ["official_source"] | ["campus_locator"] | ["Municipal source-reported reference point for Microsoft's named data-center activity/rock-crushing permit site. Native values are E 363900, N 6670100 labelled tm-35; the explicit EPSG:3067 interpretation is transformed without claiming a building center, boundary, construction footprint or survey accuracy."] |  | The source states no numeric positional accuracy or surveyed reference feature. Its coordinate notation does not justify an accuracy estimate. | ["6096de66-dad6-5326-8155-173cfe6969a4"] | 1 | ["64289119-458d-5fc9-bf51-5af6097220eb"] | ["curated:microsoft-finland-kirkkonummi-campus:building-1"] | ["under_construction"] | 2026-06-26 | 2026-06-26 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-004b39e14dadd642b1e8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-004b39e14dadd642b1e8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-004b39e14dadd642b1e8.geojson | no-open-redistribution-license-asserted
vcc-site-00808116377785b5c125 | curated:verne-mantsala-data-center-campus | Verne Mäntsälä Data Center Campus | Finland | FI | 60.6353 | 25.2862 | Polygon | ["campus"] | ["direct_geometry"] | ["authoritative_site_plan"] | ["official_cadastral_campus_parcel_boundary"] | ["official_source"] | ["official_boundary"] | ["Exact municipal cadastral polygon for property 505-407-7-137, inherited through the explicit project-to-campus link; it is the full campus parcel, not a building or the current 70 MW development footprint."] |  | official source does not state positional accuracy | ["708cee21-4519-5840-a07c-2f1f8398cb87"] | 1 | ["8f8c241d-ee6b-5182-8a76-ebb101a3f4c2"] | ["curated:verne-mantsala-data-center-campus:current-development"] | ["under_construction"] | 2026-06-17 | 2026-06-17 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-00808116377785b5c125/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-00808116377785b5c125.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-00808116377785b5c125.geojson | all-rights-reserved
vcc-site-028ea637886484fbc894 | imported:semiconductor-atlas:vantage-villanueva-de-gallego | Vantage Data Centers Villanueva de Gállego campus | Spain | ES | 41.767 | -0.817 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from the Villanueva de Gállego Wikipedia article. Sources place the site south of the town along the A-23 (Huesca motorway), opposite the San Miguel industrial estate and close to the Universidad San Jorge campus; no parcel boundary is published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["25e8d6e9-275e-55fb-ad03-97523dd3b542"] | 1 | ["a8c0727c-ed59-5641-8856-e4eac08a5cf0"] | ["imported:semiconductor-atlas:vantage-villanueva-de-gallego"] | ["announced"] | 2026-03-20 | 2026-03-20 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-028ea637886484fbc894/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-028ea637886484fbc894.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-028ea637886484fbc894.geojson | source-terms-not-recorded
vcc-site-03a8f52a32b90569e4e1 | curated:china-telecom-cloud-computing-guizhou-information-park | China Telecom Cloud Computing Guizhou Information Park | China | CN | 26.38 | 106.54 | Point | ["campus"] | ["direct_geometry"] | ["literal_reported_campus_coordinates_no_transformation"] | ["institutional_report_approximate_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The SASAC official account names the China Telecom Guizhou Information Park and publishes 26.38 N, 106.54 E to two decimal places. This is an approximate campus reference, not a B5/B6 building, parcel, entrance or work-extent locator. The original datum is not stated; values are retained literally without a claimed CRS conversion."] |  | Coordinates published to 0.01 degree; datum, surveyed reference feature and measured horizontal accuracy are unknown. Rounding alone is roughly kilometre scale, and no precise building position or accuracy radius is inferred. | ["b29dd16b-b07a-5737-9570-ee1a8811fca2"] | 1 | ["be874ef3-dd3e-54dd-be06-f01895ac6992"] | ["curated:china-telecom-cloud-computing-guizhou-information-park:phase-2-1-b5-b6-data-center-build"] | ["completed"] | 2026-09-20 | 2026-09-20 | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-03a8f52a32b90569e4e1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-03a8f52a32b90569e4e1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-03a8f52a32b90569e4e1.geojson | all-rights-reserved
vcc-site-044046b0ede92919a936 | curated:goodman-ams01-amsterdam-data-centre-campus | Goodman AMS01 Amsterdam Data Centre Campus | Netherlands | NL | 52.3794 | 4.7049 | Point | ["campus"] | ["official_notice_published_point_marker"] | ["first_published_RD_point_transformed_to_WGS84_without_centroiding"] | ["official_project_notice_campus_locator"] | ["official_source"] | ["campus_locator"] | ["The provincial notice marker locates the same named entity/address as the certifier's literal AMS01 record. It does not delineate Building A, Building B, a cadastral property or the June 30 active-work extent. One point represents one campus."] |  | The notice gives a location marker but no numeric horizontal-accuracy statement or surveyed reference feature. | ["4791ed5e-b266-5f0f-b86f-d183cc829ba2","fb26fa5c-bb7a-5323-b71e-afa469c7b954"] | 1 | ["f8900f55-087d-5d51-aef2-820402bcbdc2"] | ["curated:goodman-ams01-amsterdam-data-centre-campus:phase-1-current-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-044046b0ede92919a936/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-044046b0ede92919a936.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-044046b0ede92919a936.geojson | no-open-redistribution-license-asserted
vcc-site-04be359939cf11193024 | imported:semiconductor-atlas:microsoft-middenmeer-campus-west | Microsoft Middenmeer Campus West expansion (Agriport Plot B) | Netherlands | NL | 52.783 | 5.0254 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Point of OSM way 1428523639 in the local OpenStreetMap layer, a Microsoft area tagged as a proposed datacenter expansion west of Microsoft's existing Agriport buildings; it is consistent with Microsoft's description of Plot B west of the A7 but is not confirmed by Microsoft."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d781093d-2c20-51bc-a765-09bc25052ccf"] | 1 | ["55df6642-2ef8-5b72-a965-996a28bdfb24"] | ["imported:semiconductor-atlas:microsoft-middenmeer-campus-west"] | ["announced"] | 2026-03-25 | 2026-03-25 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-04be359939cf11193024/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-04be359939cf11193024.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-04be359939cf11193024.geojson | source-terms-not-recorded
vcc-site-04c2489b55d49bcb5ef5 | imported:semiconductor-atlas:aws-fayette-county-ohio | AWS Fayette County data center site | United States | US | 39.56 | -83.45 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Amazon names only the county; coordinates are the Fayette County point from its Wikipedia article (Nominatim was unavailable)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["e5bdd89d-ddf9-528d-869d-0a61c6492cc2"] | 1 | ["b649f6b4-e5be-5d52-9b44-0273c14cbea3"] | ["imported:semiconductor-atlas:aws-fayette-county-ohio"] | ["announced"] | 2024-12-24 | 2024-12-24 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-04c2489b55d49bcb5ef5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-04c2489b55d49bcb5ef5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-04c2489b55d49bcb5ef5.geojson | source-terms-not-recorded
vcc-site-0660c8cc500011957a7b | curated:estructure-cal3-rocky-view-campus | eStruxture CAL-3 Rocky View Campus | Canada | CA | 51.2108 | -113.9147 | Point | ["facility"] | ["coordinates_to_point"] | ["first_party_published_decimal_coordinate_to_point"] | ["first_party_facility_reference_point"] | ["official_source"] | ["project_locator"] | ["First-party CAL-3 datasheet coordinate bound to the named facility. It is a project locator, not a parcel, campus, building, entrance, survey point, centroid, or current-work boundary."] |  | The datasheet supplies coordinate digits but no datum, collection method, reference-feature definition, or bounded numeric horizontal-accuracy value. | ["89aab19e-2eb3-59f5-a3c3-71366d5cb026"] | 1 | ["a225d046-5d72-5a1f-bf4b-ba454f713a49"] | ["curated:estructure-cal3-rocky-view-campus:initial-build"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0660c8cc500011957a7b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0660c8cc500011957a7b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0660c8cc500011957a7b.geojson | all-rights-reserved-fact-extraction-only
vcc-site-078fc4166e995b536458 | imported:semiconductor-atlas:google-waltham-cross-uk | Google Waltham Cross data centre | United Kingdom | GB | 51.6858 | -0.033 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid of Waltham Cross via Nominatim; Google's sources name the town but not the street address."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["99547e51-4312-55b7-bca0-e1e247aee399"] | 1 | ["03b5fd0f-9eaf-5f2b-bd8e-7c11fe6672a9"] | ["imported:semiconductor-atlas:google-waltham-cross-uk"] | ["operational"] | 2025-09-16 | 2025-09-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-078fc4166e995b536458/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-078fc4166e995b536458.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-078fc4166e995b536458.geojson | source-terms-not-recorded
vcc-site-07b3e2197c23d98b282e | imported:semiconductor-atlas:powerhouse-pennsylvania-digital-i-carlisle | Pennsylvania Digital I (PAX-1), Middlesex Township | United States | US | 40.2167 | -77.1164 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia point for Middlesex Township (s4). Local reporting places the site off Country Club Road about five miles northeast of Carlisle; the parcel was not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["0018bbb4-353b-533f-81ca-d19336a4c0f1"] | 1 | ["39dca169-c304-53a7-b2a6-15a9a914e4d1"] | ["imported:semiconductor-atlas:powerhouse-pennsylvania-digital-i-carlisle"] | ["announced"] | 2026-03-05 | 2026-03-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-07b3e2197c23d98b282e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-07b3e2197c23d98b282e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-07b3e2197c23d98b282e.geojson | source-terms-not-recorded
vcc-site-07ef7b0d529815ef1fe5 | curated:capitaland-dc-navi-mumbai-campus | CapitaLand DC Navi Mumbai Campus | India | IN | 19.1758 | 73.0002 | Point | ["campus"] | ["first_party_published_map_pin"] | ["source_attribute_decimal_coordinates_to_point_without_centroiding"] | ["official_operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The dated results table explicitly places Tower 1 and Tower 2 in CapitaLand DC Navi Mumbai; the operator property page names Mumbai 01 in Airoli and provides the campus point. The current point is not a Tower 2 footprint. No building, phase, construction extent or survey accuracy is asserted."] |  | The publisher supplies no numeric horizontal-accuracy statement or surveyed reference feature. | ["77dc8de7-b028-5897-b0d6-072bc8a1c922"] | 1 | ["e62026de-3394-51f7-8823-44ee0da1801c"] | ["curated:capitaland-dc-navi-mumbai-campus:tower-2"] | ["under_construction"] | 2026-07-29 | 2026-07-29 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-07ef7b0d529815ef1fe5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-07ef7b0d529815ef1fe5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-07ef7b0d529815ef1fe5.geojson | all-rights-reserved
vcc-site-0819a764e96ce06f14c6 | imported:semiconductor-atlas:aws-clinton-hinds-county-mississippi | AWS Clinton data center (former Delphi plant) | United States | US | 32.3583 | -90.3556 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Clinton city point from its Wikipedia article (Nominatim was unavailable). One local TV report places the site on Industrial Park Drive but calls it the former Milwaukee Tool factory, which conflicts with the Delphi identification, so no site point is used."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["4e31a439-2221-535f-a651-5f280bc2ed4a"] | 1 | ["2cb7333c-d029-5457-baf2-346f48e7fb26"] | ["imported:semiconductor-atlas:aws-clinton-hinds-county-mississippi"] | ["operational"] | 2026-06-09 | 2026-06-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0819a764e96ce06f14c6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0819a764e96ce06f14c6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0819a764e96ce06f14c6.geojson | source-terms-not-recorded
vcc-site-0834945607ed54e349ce | imported:semiconductor-atlas:bell-ai-fabric-sherwood-saskatchewan | Bell AI Fabric Sherwood campus (Regina area) | Canada | CA | 50.473 | -104.627 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Bell names only the rural municipality. Coordinates are the RM's published reference point (Wikipedia infobox); because the RM surrounds Regina, this point is near the city and is not the campus site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["34f860f9-9746-5f72-9b8f-9cb414f9cb9c"] | 1 | ["0b37ac4d-93f2-559b-a6ec-f5a12938681a"] | ["imported:semiconductor-atlas:bell-ai-fabric-sherwood-saskatchewan"] | ["under_construction"] | 2026-10-01 | 2026-10-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0834945607ed54e349ce/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0834945607ed54e349ce.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0834945607ed54e349ce.geojson | source-terms-not-recorded
vcc-site-08c96f4448334dc081a5 | curated:jera-chiba-thermal-power-station | JERA Chiba Thermal Power Station AI Infrastructure | Japan | JP | 35.5638 | 140.102 | Point | ["campus"] | ["direct_geometry"] | ["operator_selected_map_feature_coordinates"] | ["operator_published_host_campus_map_reference"] | ["compiled_reference"] | ["campus_locator"] | ["Operator-selected host power-station address feature; no AI data-center plot, building footprint or phase boundary is established."] |  | No positional accuracy or AI plot is published. The plant spans about76ha and the DC location within it is unknown. Decimal precision reflects map parameters, not surveyed accuracy. | ["a25bcee2-8a5a-5951-81ba-924dd0c09607"] | 1 | ["02a9ee88-08e5-58fd-b715-488b3ee903a3"] | ["curated:jera-chiba-thermal-power-station:ai-datacenter-campus"] | ["announced"] | 2026-10-01 | 2026-10-01 | authoritative_project_record_plus_scoped_location | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-08c96f4448334dc081a5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-08c96f4448334dc081a5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-08c96f4448334dc081a5.geojson | all-rights-reserved
vcc-site-09a8ea20931b50e7a218 | imported:semiconductor-atlas:huntley-page-arizona | Page, Arizona data center site (Huntley LLC) | United States | US | 36.9142 | -111.5033 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of Page (s6). The city says the land lies on the southwest side of Page near Highway 98, about two miles from Horseshoe Bend, and that the exact building location is undetermined; other reports describe it as next to Horseshoe Bend."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["8f755fe0-608b-580c-a6fb-767c4d8df930"] | 1 | ["bc344b80-1656-5a9a-a788-a5f7cb59131e"] | ["imported:semiconductor-atlas:huntley-page-arizona"] | ["proposed"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-09a8ea20931b50e7a218/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-09a8ea20931b50e7a218.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-09a8ea20931b50e7a218.geojson | source-terms-not-recorded
vcc-site-0a62731022d2820e105f | imported:semiconductor-atlas:wonder-valley-alberta | Wonder Valley AI data centre park (Alberta) | Canada | CA | 54.8119 | -118.6834 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Point taken from the Government of Alberta major projects inventory entry for Phase 1 and rounded; the developer's FAQ places the site in the Greenview Industrial Gateway about 42 km south of Grande Prairie. Parcel boundaries were not published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d43b045c-1fff-5626-9644-8a866d075e46"] | 1 | ["bb1b28fd-610b-5739-b928-e44f21cb6f1b"] | ["imported:semiconductor-atlas:wonder-valley-alberta"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0a62731022d2820e105f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0a62731022d2820e105f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0a62731022d2820e105f.geojson | source-terms-not-recorded
vcc-site-0ac82fd201fa1878b892 | epoch-ai:data-center:ae2c8749-c97f-5512-a0ad-a40ed8df37ce | Applied Digital Polaris Forge 1 Campus | United States | US | 46.0144 | -98.5743 | Point | ["campus"] | ["official_constituent_permit_reference_point"] | ["NDDEQ_PDF_page18_NAD83_EPSG4269_to_EPSG4326_NAD83_to_WGS84_1"] | ["official_constituent_permit_reference_point"] | ["official_source"] | ["campus_locator"] | ["Official reference coordinate for the ELN Building 1 backup-generator plant at the exact street address shared by PF1 campus leases. It locates the campus through a constituent plant, not the still-building project, building center or campus boundary. The permit is not current physical-status evidence. EPSG transformation is a no-op with nominal 4m transformation accuracy; total source positional accuracy is unknown."] |  | No source-specific numeric accuracy is supplied. Coordinate decimals and transformation agreement are not source positional accuracy. | ["dd0153fd-0d77-5e96-9561-d64ddc7b9eec"] | 2 | ["20ee1eea-91bf-52aa-a464-c4a38d436f9e","32b98d7e-1d0f-5c16-af18-3f469f3b662b"] | ["curated:applied-digital-polaris-forge-1:current-expansion","imported:semiconductor-atlas:applied-digital-polaris-forge-1"] | ["partially_operational","under_construction"] | 2026-07-27 | 2026-10-07 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ac82fd201fa1878b892/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ac82fd201fa1878b892.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ac82fd201fa1878b892.geojson | no-open-redistribution-license-asserted
vcc-site-0baa18deeb394aec986b | curated:iron-mountain-madrid-data-center-campus | Iron Mountain Madrid Data Center Campus | Spain | ES | 40.4582 | -3.4985 | Point | ["campus"] | ["official_exact_street_number_address_point"] | ["select_exact_CartoCiudad_portal_result_and_preserve_service_WGS84_coordinates"] | ["official_address_point_campus_locator"] | ["official_source"] | ["campus_locator"] | ["The operator names Calle Mar Egeo 4 for its whole Madrid campus. The selected government result locates that address, not an individual data hall, parcel boundary, active works or a surveyed building point. The two current components count as one physical campus."] |  | The exact returned address point has no published source-specific numeric horizontal accuracy; decimal precision is not accuracy. | ["71e329e6-eaa7-5cff-8740-459fd32d5449","7f15b727-7dba-5482-ab95-8b2660221d71"] | 1 | ["bf8d11a2-72a6-500d-a532-98fb73958c84"] | ["curated:iron-mountain-madrid-data-center-campus:mad-2-mad-3-20mw-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0baa18deeb394aec986b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0baa18deeb394aec986b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0baa18deeb394aec986b.geojson | no-open-redistribution-license-asserted
vcc-site-0bec2abc5fdac2e0fcf6 | curated:goodman-hkg09-kwai-chung-data-centre | Goodman HKG09 Kwai Chung Data Centre | Hong Kong | HK | 22.3679 | 114.1363 | Point | ["campus"] | ["cross_source_overlay"] | ["official_company_exact_address_to_lands_department_location_search_and_official_hk80_wgs84_transform"] | ["official_lands_department_address_building_reference_point"] | ["official_source"] | ["campus_locator"] | ["Official address/building reference point used only to locate the HKG09 campus inherited by the current redevelopment. It is not a parcel, building footprint or centroid, redevelopment extent, construction extent, campus boundary, or survey-accuracy claim."] |  | The Location Search API and transformation API do not publish numeric horizontal accuracy for this selected result; the transformation service warns against precise-point applications. | ["9f4c707b-692b-5d29-b1df-3db4259967cc"] | 1 | ["c04bedc0-51b3-5d4d-996c-1d1e56de96c0"] | ["curated:goodman-hkg09-kwai-chung-data-centre:current-redevelopment"] | ["under_construction"] | 2026-07-15 | 2026-07-15 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0bec2abc5fdac2e0fcf6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0bec2abc5fdac2e0fcf6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0bec2abc5fdac2e0fcf6.geojson | Hong-Kong-DATA.GOV.HK-Terms-of-Use
vcc-site-0ca1d5c08f1eb1cf1cf3 | curated:microsoft-alviso-san-jose-datacenter-campus | Microsoft Alviso San Jose Datacenter Campus | United States | US | 37.4252 | -121.9287 | Point | ["project"] | ["official_address_point"] | ["city_of_san_jose_address_point_cross_identified_by_named_development_record"] | ["official_city_address_point_cross_identified_to_named_project"] | ["official_source"] | ["project_locator"] | ["Official City of San Jose address point for 1657 Alviso-Milpitas Road, cross-identified to Microsoft and CP23-016 by the City's named Major Private Development record. The point locates the named project and shared parent campus only; the separate development polygon is rejected."] |  | The City address record labels the feature Placed on Map and supplies no bounded numeric horizontal-accuracy value; coordinate digits do not establish survey accuracy, containment, an entrance, or a footprint. | ["5b7da16c-3a43-5e42-97ad-816ae894e900"] | 1 | ["1861d9fb-3980-5a16-baa1-c32762e244c1"] | ["curated:microsoft-alviso-san-jose-datacenter-campus:phase-2-greenfield-development"] | ["under_construction"] | 2026-06-10 | 2026-06-10 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ca1d5c08f1eb1cf1cf3/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ca1d5c08f1eb1cf1cf3.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ca1d5c08f1eb1cf1cf3.geojson | city-open-data-disclaimer
vcc-site-0d25d33c7b8c51f70ba3 | imported:semiconductor-atlas:samca-green-it-aragon-luceni | Green IT Aragón data center campus (SAMCA), Luceni | Spain | ES | 41.833 | -1.233 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Luceni municipal centroid from its Wikipedia article. The technical annex places all three data centers in Luceni municipality; associated grid and wind works extend into Rueda de Jalón, Plasencia de Jalón and Pedrola. No cited source gives site coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["117a516b-4901-56d6-8322-ad8efe5b2ddd"] | 1 | ["15360f72-acfa-572f-aac9-eb117ae9fc0d"] | ["imported:semiconductor-atlas:samca-green-it-aragon-luceni"] | ["announced"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0d25d33c7b8c51f70ba3/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0d25d33c7b8c51f70ba3.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0d25d33c7b8c51f70ba3.geojson | source-terms-not-recorded
vcc-site-0ecf05307f91c1e40479 | curated:qscale-q01-levis-campus | QScale Q01 Lévis Campus | Canada | CA | 46.6762 | -71.3251 | Polygon | ["campus"] | ["cross_source_overlay"] | ["openstreetmap_named_addressed_facility_polygon_as_campus_locator"] | ["reviewed_openstreetmap_named_addressed_qscale_facility_building_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped polygon for one named QScale data-centre building at Q01's exact first-party address, used only to locate the Q01 campus. It is not the Building B footprint or centroid, the Q01 campus boundary, a parcel, a construction extent, or a survey-accuracy claim."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | ["8dff3085-994d-5629-b19b-7f2f88c44967"] | 2 | ["a848e771-2e45-55fb-8d43-db0885bb824f","b9f9191a-1f90-551d-a8b9-44e6f8833e96"] | ["curated:qscale-q01-levis-campus:building-b","imported:semiconductor-atlas:qscale-q01-levis"] | ["partially_operational","under_construction"] | 2026-06-04 | 2026-10-09 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ecf05307f91c1e40479/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ecf05307f91c1e40479.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ecf05307f91c1e40479.geojson | ODbL-1.0
vcc-site-0ed3e2f5c48bfda417a3 | curated:borealis-blonduos-data-center-campus | Borealis Blönduós Data Center Campus | Iceland | IS | 65.6473 | -20.243 | Polygon | ["facility"] | ["cross_source_geometry"] | ["openstreetmap_borealis_blonduos_named_building_polygon_as_parent_campus_locator"] | ["reviewed_openstreetmap_borealis_blonduos_named_building_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped polygon for a named Borealis building at Blönduós, used only to locate the parent campus. It is not the 2026 expansion boundary, a complete campus boundary, an official parcel or planning boundary, or a current construction-progress extent. A first-party map link that resolves only to the Blönduós town/place is rejected as site geometry."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | ["b24c0246-2488-55e4-9022-3609124fd8c8"] | 1 | ["adc32529-cea1-5d06-86de-334e63433be6"] | ["curated:borealis-blonduos-data-center-campus:expansion-current-build"] | ["under_construction"] | 2026-06-23 | 2026-06-23 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ed3e2f5c48bfda417a3/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ed3e2f5c48bfda417a3.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0ed3e2f5c48bfda417a3.geojson | ODbL-1.0
vcc-site-0f9ffed73b02dd75c9a5 | curated:cdc-laverton-melbourne-campus | CDC Laverton Melbourne Campus | Australia | AU | -37.8416 | 144.7754 | Polygon | ["facility"] | ["cross_source_geometry"] | ["openstreetmap_cdc_laverton_named_development_polygon_as_parent_campus_locator"] | ["reviewed_openstreetmap_cdc_laverton_named_development_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped named development/address polygon used only to locate the parent Laverton campus. It is not the current-build project boundary, a complete campus boundary, an official parcel or planning boundary, a building footprint, a security fence, or a current construction-progress extent."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | ["e07bd94a-9734-5f78-a7b6-d69e757357c2"] | 1 | ["9cceddca-71bc-52f2-a417-e9fdf0d7faa3"] | ["curated:cdc-laverton-melbourne-campus:current-build"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0f9ffed73b02dd75c9a5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0f9ffed73b02dd75c9a5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0f9ffed73b02dd75c9a5.geojson | ODbL-1.0
vcc-site-0fd145d30136b16a75ed | imported:semiconductor-atlas:fermi-america-hypergrid-amarillo | Fermi America Project Matador campus | United States | US | 35.3116 | -101.5597 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Coordinates of the Pantex Plant from Wikipedia (s5). Fermi says its campus is next to the Pantex complex (s2), in Carson County (s1, s4) and near Amarillo (s3); the campus covers thousands of acres, so the point is only approximate."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f6b4d9a4-f01a-5a71-beb8-621d552bdb95"] | 1 | ["94562977-e3af-5f59-bee1-896ee8db20f6"] | ["imported:semiconductor-atlas:fermi-america-hypergrid-amarillo"] | ["under_construction"] | 2026-09-28 | 2026-09-28 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0fd145d30136b16a75ed/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0fd145d30136b16a75ed.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0fd145d30136b16a75ed.geojson | source-terms-not-recorded
vcc-site-0fd8442bfe3dc0c487e5 | curated:lg-uplus-paju-aidc-campus | LG Uplus Paju AIDC | Korea, Republic of | KR | 37.8141 | 126.7561 | Point | ["campus"] | ["community_named_former_factory_representative_point_bound_to_official_redevelopment_parcel"] | ["preserve_Nominatim_source_lat_lon_for_OSM_way_469691383_and_bind_unique_factory_name_through_municipal_registry_and_LG_Uplus_notice"] | ["community_former_factory_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["The source-supplied representative point of former Heesung Electronics industrial building way469691383 locates the exact subsequently redeveloped Paju parcel1239-1. The operator name comes from the city landing page, not from the PDF. This is a historical physical-site locator only: not the current AIDC footprint, factory-survival assertion, entrance, surveyed point, campus boundary, neighboring LG Display1239 complex or June5 active-work extent."] |  | Neither the OSM feature nor its Nominatim representative point supplies quantitative positional accuracy. Source coordinate digits are not survey precision. | ["362131d4-48db-5185-a5db-a5d237c876db","5cd22b84-8f94-5761-a01b-df911d39ffff"] | 1 | ["fc6dd688-fca0-5a7f-a6e9-54f9116607c5"] | ["curated:lg-uplus-paju-aidc-campus:building-1"] | ["under_construction"] | 2026-06-05 | 2026-06-05 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0fd8442bfe3dc0c487e5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0fd8442bfe3dc0c487e5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-0fd8442bfe3dc0c487e5.geojson | ODbL-1.0
vcc-site-1057cda1149b646f7a24 | imported:semiconductor-atlas:igoudar-dakhla | Igoudar Dakhla green data centre complex | Western Sahara | EH | 23.7081 | -15.9456 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City coordinates from the Dakhla Wikipedia page; no site within Dakhla has been named. Dakhla is in Western Sahara (ISO code EH), a disputed territory administered by Morocco; the sources present the project as a Moroccan national programme."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["56fcfb3f-baa2-5c37-ad58-6c959485a7cb"] | 1 | ["40a718e2-038a-5edf-a495-ba05e3f76560"] | ["imported:semiconductor-atlas:igoudar-dakhla"] | ["announced"] | 2026-04-16 | 2026-04-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1057cda1149b646f7a24/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1057cda1149b646f7a24.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1057cda1149b646f7a24.geojson | source-terms-not-recorded
vcc-site-10c105346f5cad5b0aa5 | curated:ten-brinke-spata-data-center | Ten Brinke Spata Data Center | Greece | GR | 37.9663 | 23.9087 | Point | ["project"] | ["direct_geometry"] | ["authoritative_site_plan"] | ["facility_reference_point"] | ["official_source"] | ["reviewed_site_locator"] | ["First-party project map point, facility-specific, with 50 metre stated horizontal uncertainty."] | 50 |  | ["ad6f843e-6f09-567d-82e6-58ecd9959ff7"] | 1 | ["38033ec9-dbd8-56bb-8a35-0fa91dd284e2"] | ["curated:ten-brinke-spata-data-center:active-construction"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-10c105346f5cad5b0aa5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-10c105346f5cad5b0aa5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-10c105346f5cad5b0aa5.geojson | all-rights-reserved
vcc-site-119a6992bb6bb25cc011 | imported:semiconductor-atlas:cyrusone-bosque-county | CyrusOne Bosque County data center campus (Thad Hill) | United States | US | 31.9 | -97.63 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Coordinates are the Wikipedia point for Bosque County (s5). Sources place the campus next to the Thad Hill Energy Center in Bosque County but give no address; the site was not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["5d8d2d25-a113-5f7c-bc17-ebe03191d0ff"] | 1 | ["79276528-66df-572a-8baf-0afce2bb01e4"] | ["imported:semiconductor-atlas:cyrusone-bosque-county"] | ["under_construction"] | 2025-11-03 | 2025-11-03 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-119a6992bb6bb25cc011/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-119a6992bb6bb25cc011.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-119a6992bb6bb25cc011.geojson | source-terms-not-recorded
vcc-site-1246c2b9750b8b4832d2 | imported:semiconductor-atlas:stack-amazon-resilient-technology-park-shreveport | Amazon and STACK campus at Resilient Technology Park, Shreveport | United States | US | 32.4639 | -93.7944 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Local radio gives 7340 Greenwood Road, and the Shreveport-Bossier Journal places the park off Greenwood Road in west Shreveport next to I-20, but no coordinates are published. The point is the Shreveport city coordinate from its Wikipedia article, not the park."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["4ce23293-83e8-5780-8614-585b94021cd5"] | 1 | ["3641032c-9acd-5840-b94b-beab26a1ce0d"] | ["imported:semiconductor-atlas:stack-amazon-resilient-technology-park-shreveport"] | ["announced"] | 2026-08-27 | 2026-08-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1246c2b9750b8b4832d2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1246c2b9750b8b4832d2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1246c2b9750b8b4832d2.geojson | source-terms-not-recorded
vcc-site-1295b8a3ae3b2543ec97 | curated:cloud4y-marfino-data-center-campus | Cloud4Y DC4Y.1 S33 Marfino Data Center Campus | Russia | RU | 56.0741 | 37.5663 | Point | ["campus"] | ["operator_card_coordinate_pair_axis_reorder_only"] | ["first_party_named_datacenter_card_yandex_placemark"] | ["operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact operator-supplied numeric precision retained; actual positional accuracy unknown. Campus marker only, not construction boundary, main-building footprint, energy-center footprint, entrance, parcel centroid or land extent."] |  | Operator supplies no positional accuracy or survey statement; many decimal places are not measured accuracy. | ["1434c1dc-df1e-5f02-a1b2-371520fc95c5","94835d2a-e5ba-5f12-ae4a-5168c1f3dfdc","9b3dada3-b68b-5658-b9cb-f304c02dadb5","c1518571-545b-5395-a744-3e59ca5114c1"] | 1 | ["cbe9c330-13a3-5d1f-a9ba-c981c31585a7"] | ["curated:cloud4y-marfino-data-center-campus:main-building-current-build"] | ["under_construction"] | 2026-06-01 | 2026-06-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1295b8a3ae3b2543ec97/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1295b8a3ae3b2543ec97.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1295b8a3ae3b2543ec97.geojson | no-open-license-asserted
vcc-site-12d6215837c6451ab8a3 | curated:microsoft-etobicoke-ontario-campus | Microsoft Etobicoke Ontario Datacenter Campus | Canada | CA | 43.7087 | -79.5482 | Point | ["project"] | ["official_municipal_land_address_point"] | ["exact_city_address_point_id_30029368_preserved_without_atlas_centroiding"] | ["official_project_address_land_locator"] | ["official_source"] | ["project_locator"] | ["City OAR Land address point for exact 48 Lowe's Place, independently bound to Microsoft ownership and the Etobicoke datacentre. Not the new building footprint, full campus boundary, entrance, active-work extent or a surveyed building-centre claim."] |  | No numeric positional accuracy published for the selected municipal address point. | ["289b100b-96a4-5c57-9235-a36c407be5f3","3cef948d-9ec8-5287-a23c-f3d70d2a7bdd","7c4cadfb-e968-5939-b44f-f8450b1e9389","c5cf08ec-c05c-54ab-86b1-f9ba72b1e068","e8e31981-940f-534d-846f-a33d96781bf6"] | 1 | ["c4ffa53e-bb43-5af1-9e07-aa5045ea480b"] | ["curated:microsoft-etobicoke-ontario-campus:first-building"] | ["under_construction"] | 2026-08-05 | 2026-08-05 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-12d6215837c6451ab8a3/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-12d6215837c6451ab8a3.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-12d6215837c6451ab8a3.geojson | Open Government Licence - Toronto
vcc-site-133b0abe4851d7ed6df5 | imported:semiconductor-atlas:terawulf-muskie | TeraWulf Muskie Data Campus | United States | US | 38.36 | -82.69 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Local media place the site in EastPark near Ashland and Interstate 64, spanning the Boyd and Greenup county line; TeraWulf's Q2 2026 release describes it as Grayson, Eastern Kentucky. Coordinates are the Boyd County point from its Wikipedia article, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f8fe5488-ecbb-5edb-9c8e-aa35059c9c26"] | 1 | ["7a5658df-f9c8-55e3-8623-b1a0fa40ce1d"] | ["imported:semiconductor-atlas:terawulf-muskie"] | ["announced"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-133b0abe4851d7ed6df5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-133b0abe4851d7ed6df5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-133b0abe4851d7ed6df5.geojson | source-terms-not-recorded
vcc-site-137418ccdcd0272f024b | curated:digital-realty-vienna-vie13-vie16-expansion | Digital Realty VIE13-VIE16 Digital Park Vienna Expansion | Austria | AT | 48.271 | 16.4241 | Point | ["project"] | ["direct_geometry"] | ["first_party_facility_page_next_data_point"] | ["first_party_facility_page_reference_point"] | ["official_source"] | ["project_locator"] | ["The source decimal strings are preserved exactly and parsed without coordinate transformation. Their displayed precision does not imply a surveyed reference feature or horizontal accuracy."] |  | The page does not identify a geodetic datum, surveyed reference feature, collection method, or numeric horizontal accuracy. | ["4bbf6d0c-4fcb-5dd0-9504-4322a80117b8"] | 1 | ["f9e7c64e-3dc3-5d47-a4de-4c72a4284231"] | ["curated:digital-realty-vienna-vie13-vie16-expansion:vie13-phase-1-current-build"] | ["under_construction"] | 2026-06-18 | 2026-06-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-137418ccdcd0272f024b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-137418ccdcd0272f024b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-137418ccdcd0272f024b.geojson | all-rights-reserved
vcc-site-137a78b7abc74703d577 | curated:beale-tulsa-county-project-clydesdale-campus | Google / Beale Tulsa County Project Clydesdale Campus | United States | US | 36.2698 | -95.9109 | Point | ["campus"] | ["representative_point_inside_reconstructed_public_draft_survey_tract"] | ["18_visual_metes_and_bounds_courses_anchored_by_section_corners_EPSG6553_to4326_then_Shapely_representative_point"] | ["public_draft_survey_tract_interior_campus_locator"] | ["official_source"] | ["campus_locator"] | ["One derived point inside the named Project Clydesdale draft survey tract. Official-source classification refers to public planning custody, not survey approval. No registered boundary, individual hall, construction footprint, road junction, offsite benchmark or mailing address is selected."] |  | The draft supplies no site-specific horizontal accuracy. Printed decimals, traverse closure, agreement between anchors and two-metre datum-operation accuracy do not establish locator accuracy. | ["9abda1b5-9d23-59c2-81b7-a930d3ec670f"] | 1 | ["0a4a2c40-bdf2-5f56-aa09-ecfa54431d3c"] | ["curated:beale-tulsa-county-project-clydesdale-campus:current-campus-build"] | ["under_construction"] | 2026-08-19 | 2026-08-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-137a78b7abc74703d577/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-137a78b7abc74703d577.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-137a78b7abc74703d577.geojson | no-open-license-asserted
vcc-site-138d436c47cc25fa668a | curated:amazon-falls-township-innovation-campus | Amazon Falls Township Innovation Campus | United States | US | 40.1555 | -74.75 | Polygon | ["campus"] | ["official_parcel_polygon"] | ["county_service_outSR_4326_rings_to_geojson_without_boundary_inference"] | ["official_tax_parcel_constituent_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Exact county tax parcel 13-051-001-034 for reused building six only. This locates a constituent of the Amazon Falls Township campus, not its full 250-acre development, individual new halls or construction footprint. Display anchor is the coordinate-envelope midpoint used only for rendering; it is not an observed center."] |  | No source provides a numeric horizontal-accuracy guarantee or a surveyed campus reference feature. | ["4f2ffb6c-d4e6-51d6-8105-3deea9fb32e1","5c2bf655-6b70-536a-9e6d-c511c785c64c"] | 1 | ["bdfd522f-2d7e-5d1f-8e00-3c43b462ed27"] | ["curated:amazon-falls-township-innovation-campus:active-buildout"] | ["under_construction"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-138d436c47cc25fa668a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-138d436c47cc25fa668a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-138d436c47cc25fa668a.geojson | no-open-redistribution-license-asserted
vcc-site-14a570a5f1dfb8b45e8d | imported:semiconductor-atlas:brookfield-cambrai | Data4 Cambrai E-Valley campus | France | FR | 50.22 | 3.1765 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Nominatim position of the E-Valley information board on Avenue de France, Épinoy, inside the former BA 103 base; sources identify the base and E-Valley but not the data center parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["65504e98-2e99-5c57-9dfd-9b25a7cb6e8e"] | 1 | ["f0697b74-aa81-5aca-ab5b-95a2591d7b2c"] | ["imported:semiconductor-atlas:brookfield-cambrai"] | ["announced"] | 2026-06-11 | 2026-06-11 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-14a570a5f1dfb8b45e8d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-14a570a5f1dfb8b45e8d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-14a570a5f1dfb8b45e8d.geojson | source-terms-not-recorded
vcc-site-155a753d051b04508b1c | imported:semiconductor-atlas:microsoft-aragon-la-muela | Microsoft La Muela datacenter campus (Aragón) | Spain | ES | 41.6068 | -1.0832 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Nominatim point for the Polígono Industrial Centrovía in La Muela, which sources name as the site area (the campus involves an expansion of the estate); the 146-hectare boundary is not published in the sources."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["aeaecec7-38ef-58cd-888d-4c1a9f97d17c"] | 1 | ["a9ca22ae-d872-5122-a052-e5c9ec410abd"] | ["imported:semiconductor-atlas:microsoft-aragon-la-muela"] | ["announced"] | 2026-09-04 | 2026-09-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-155a753d051b04508b1c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-155a753d051b04508b1c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-155a753d051b04508b1c.geojson | source-terms-not-recorded
vcc-site-1589f325b3b39da5fb19 | curated:microsoft-hebron-oh-datacenter | Microsoft Hebron Datacenter | United States | US | 39.972 | -82.4889 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["1de91fed-9b38-5c47-886d-5fa766be2aa0"] | 1 | ["86bcbcd1-702d-5afa-aeb8-1cb145224b97"] | ["curated:microsoft-hebron-oh-datacenter:initial-site-preparation"] | ["site_preparation"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1589f325b3b39da5fb19/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1589f325b3b39da5fb19.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1589f325b3b39da5fb19.geojson | public-domain-us-government
vcc-site-15afee16348a0ffc414f | curated:google-bermuda-hundred-chesterfield-campus | Google Bermuda Hundred Data Center Campus | United States | US | 37.3463 | -77.3049 | Point | ["campus"] | ["official_service_parcel_centroid"] | ["ArcGIS_returnCentroid_true_outSR_4326_exact_property_query"] | ["official_parcel_reference_point"] | ["official_source"] | ["campus_locator"] | ["Official source-specific constituent-property centroid used only as a campus locator. Not a surveyed point, full campus boundary, building footprint, entrance, active-work extent or construction stage. Source numerical precision is not positional accuracy."] |  | County terms explicitly disclaim numerical positional accuracy and legal/survey use. | ["18e55c05-989b-581b-b412-470a89fff1c3","3908b2d8-3494-5c31-93f5-c5d84f368a20","3935b984-1fc9-538b-aa2e-c2431e85553a","7b52ba23-d027-54d2-9dc8-998a8c792c8e","9751ec41-030f-5351-9f67-7ca95c26e7b1","9f29ad18-9652-5243-9cd5-48eb83fb967f","e527b9c8-58f6-56e3-98d5-1d620a146f92","f1c93b01-9ffe-571c-b4f0-dd7a32d28d79"] | 1 | ["f3cc5dc7-9547-517f-94aa-89e0769f2bf8"] | ["curated:google-bermuda-hundred-chesterfield-campus:current-development"] | ["under_construction"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-15afee16348a0ffc414f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-15afee16348a0ffc414f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-15afee16348a0ffc414f.geojson | CC0-1.0; all-rights-reserved; no-open-document-redistribution-license-asserted
vcc-site-166ec46634755791abc3 | curated:israel-mega-dc-mdcil5-idan-hanegev-site | Mega D.C. MDCIL-5 Idan HaNegev Site | Israel | IL | 31.3743 | 34.7899 | Polygon | ["campus"] | ["approved_plan_land_use_plot_ring_transformed_EPSG2039_to_WGS84"] | ["Xplan_layer4_plot_query_native_ring_PROJ_Israel1993_to_WGS84_2_round7"] | ["approved_statutory_plan_land_use_plot"] | ["official_source"] | ["campus_locator"] | ["Every native plot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. Plot 10 of plan 625-0866855 is bound to the campus by the issuer's own plot references; it is a planning plot, not a surveyed cadastral boundary, building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it."] |  | The planning service states no positional accuracy and disclaims official status; the 0.5 m datum-operation figure is not a plot accuracy. | ["17ee56c4-bb04-50b4-a94b-d1550ac3f2a5","dae2e594-fb54-5b36-b83e-7a330026ca33"] | 1 | ["96d7988b-a1e7-517c-9218-462524058a80"] | ["curated:israel-mega-dc-mdcil5-idan-hanegev-site:phase-a"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-166ec46634755791abc3/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-166ec46634755791abc3.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-166ec46634755791abc3.geojson | no-open-license-asserted
vcc-site-17f7ed745e789e79ad69 | curated:atnorth-ice02-reykjanesbaer-campus | atNorth ICE02 Reykjanesbær Campus | Iceland | IS | 63.9636 | -22.5385 | Polygon | ["campus"] | ["cross_source_overlay"] | ["openstreetmap_named_campus_fence_boundary"] | ["reviewed_openstreetmap_named_campus_fence"] | ["community_mapped"] | ["campus_locator"] | ["The frozen global-open-v3 Polygon is a reviewed named ICE02 campus fence/site locator inherited by the phase-two project through the explicit project_targets relationship. It is not an official, cadastral, or survey boundary; a complete current campus extent; a building footprint; or a Phase 2 footprint."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | ["6aa2c3ec-e7cc-59f0-8cd1-4b6e68a51fef"] | 1 | ["9be0ab88-c727-5dbc-8a12-e2443878b69f"] | ["curated:atnorth-ice02-reykjanesbaer-campus:phase-2-expansion"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-17f7ed745e789e79ad69/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-17f7ed745e789e79ad69.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-17f7ed745e789e79ad69.geojson | ODbL-1.0
vcc-site-18500c4557e6b208669d | imported:semiconductor-atlas:project-blue-tucson | Project Blue | United States | US | 32.2219 | -110.9714 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Tucson. The site is in unincorporated Pima County immediately north of the Pima County Fairgrounds and west of Houghton Road in the Southeast Employment and Logistics Center, southeast of this point; no coordinates were found in a cited source."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["27cd40f2-5183-5f51-a749-737dcb1e93a5"] | 1 | ["d654ea2a-ea8e-564e-a1df-67f35d52ebbc"] | ["imported:semiconductor-atlas:project-blue-tucson"] | ["under_construction"] | 2026-04-24 | 2026-04-24 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-18500c4557e6b208669d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-18500c4557e6b208669d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-18500c4557e6b208669d.geojson | source-terms-not-recorded
vcc-site-18b5f6f9e4309fa610af | imported:semiconductor-atlas:bridge-my06-sedenak | Bridge Data Centres MY06, Sedenak Tech Park | Malaysia | MY | 1.7137 | 103.5248 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources place the campus in Kidex Sedenak, within the Sedenak Technology Valley (Sedenak Tech Park), without an address; the point is the Sedenak coordinate from its Wikipedia article, so it marks the locality rather than the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6b6e6695-a936-5100-990b-004dd1051786"] | 1 | ["eebaf579-8fee-543e-9f06-f7423d642684"] | ["imported:semiconductor-atlas:bridge-my06-sedenak"] | ["operational"] | 2026-09-15 | 2026-09-15 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-18b5f6f9e4309fa610af/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-18b5f6f9e4309fa610af.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-18b5f6f9e4309fa610af.geojson | source-terms-not-recorded
vcc-site-191fa12b770b8f520c6e | curated:edgecore-as02-sterling-virginia-campus | EdgeCore AS02 Sterling Site | United States | US | 38.995 | -77.4461 | Polygon | ["project"] | ["direct_geometry"] | ["official_parcel_polygon"] | ["assessor_linked_project_parcel"] | ["official_source"] | ["project_locator"] | ["Exact geometryPrecision=8 county parcel geometry for MCPI 045465016000, identity-linked through assessor records to the AS02 address; project locator only, not a surveyed data-center or active-work footprint."] |  | Loudoun County disclaims accuracy and supplies no survey-grade horizontal error. | ["dc629454-e376-50b1-aecf-b16ac4408021"] | 1 | ["6b62c459-dc75-5f31-87d4-d6dbf47de8b0"] | ["curated:edgecore-as02-sterling-virginia-campus:as02-data-center"] | ["under_construction"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-191fa12b770b8f520c6e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-191fa12b770b8f520c6e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-191fa12b770b8f520c6e.geojson | Loudoun-County-GIS-disclaimer
vcc-site-1c393b2e71d64f0ffd69 | imported:semiconductor-atlas:google-west-memphis-arkansas | Google West Memphis data center campus | United States | US | 35.1163 | -90.2115 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["OpenStreetMap geometry of the southern end of Bollinger Road in West Memphis; sources place the campus at the south end of Bollinger Road. One source also gives 1500 South Loop Drive, which could not be resolved to a point. The campus parcel itself is not mapped here."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2a51650c-1b90-5cd4-9448-8601d200965e"] | 1 | ["09904943-69d4-51d7-aef7-4ff880e47332"] | ["imported:semiconductor-atlas:google-west-memphis-arkansas"] | ["under_construction"] | 2026-02-26 | 2026-02-26 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1c393b2e71d64f0ffd69/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1c393b2e71d64f0ffd69.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1c393b2e71d64f0ffd69.geojson | source-terms-not-recorded
vcc-site-1e165cace19ab3a9b463 | imported:semiconductor-atlas:microsoft-aragon-zaragoza-puerto-venecia | Microsoft Zaragoza (Puerto Venecia) datacenter campus | Spain | ES | 41.6088 | -0.8872 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Nominatim point for Puerto Venecia (Torrero-La Paz district); sources place the campus next to Puerto Venecia and Parque Venecia, but the parcel boundary is not published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2765ea35-4037-5771-8cab-3cbd7f180977"] | 1 | ["6788c655-d9ed-520c-8012-56d246d29a0c"] | ["imported:semiconductor-atlas:microsoft-aragon-zaragoza-puerto-venecia"] | ["announced"] | 2026-09-04 | 2026-09-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1e165cace19ab3a9b463/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1e165cace19ab3a9b463.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1e165cace19ab3a9b463.geojson | source-terms-not-recorded
vcc-site-1f0a3581ea8ef66ce00b | curated:noris-network-fra1-schwalbach-campus | noris network FRA1 Schwalbach Campus | Germany | DE | 50.1629 | 8.5326 | Point | ["campus"] | ["copy_Overpass_center_for_named_OSM_way_313208490"] | ["copy_Overpass_center_for_named_OSM_way_313208490"] | ["community_mapped_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["Representative center of an explicitly named and operated community-mapped campus enclosure; not a surveyed parcel or building centroid. OSM object identity matches the company release; the street spelling discrepancy is disclosed."] |  | The source provides no survey accuracy or quantitative positional uncertainty; coordinate digits do not establish accuracy. | ["3b796d81-9046-5662-b53e-4a7363bb50f3"] | 1 | ["05033935-bf13-5754-a9af-25c96ea1b473"] | ["curated:noris-network-fra1-schwalbach-campus:current-build"] | ["under_construction"] | 2026-06-10 | 2026-06-10 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1f0a3581ea8ef66ce00b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1f0a3581ea8ef66ce00b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1f0a3581ea8ef66ce00b.geojson | ODbL-1.0
vcc-site-1f215e81ecc04c69b5d6 | curated:hut8-river-bend-ai-data-center-campus | Hut 8 River Bend AI Data Center Campus | United States | US | 30.7279 | -91.2995 | Point | ["campus"] | ["Match direct campus page to the platform's same title and slug; dereference explicit geolocation fields; reproduce the site's six-decimal marker rounding; emit longitude then latitude."] | ["operator_published_mapbox_campus_marker"] | ["operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact operator-rendered named campus marker, not a survey, campus boundary, building centroid, construction footprint, or phase-specific location."] |  | Publisher reports no bounded horizontal positional accuracy; decimal places and deterministic rounding do not establish site accuracy. | ["111e4ef0-d1c4-5b87-8c40-be427705300f","649edbaf-a971-56f7-93c0-ea2569188d14","688470de-c2fd-561a-93c3-5b4b00bcf981","873a0c1d-1e8a-55f6-81ab-db5d75aa832e","ebef4446-a514-5896-8a6d-c9e0109c3eb4"] | 2 | ["3e074273-f5f7-5785-ab10-232a5ebd5c6b","8aa8e9f5-915e-51f6-bc08-463822cf16f9"] | ["curated:hut8-river-bend-ai-data-center-campus:245mw-critical-it-current-build","imported:semiconductor-atlas:hut8-river-bend-louisiana"] | ["under_construction"] | 2026-08-04 | 2026-10-05 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1f215e81ecc04c69b5d6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1f215e81ecc04c69b5d6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-1f215e81ecc04c69b5d6.geojson | IETF-Trust-Legal-Provisions; all-rights-reserved
vcc-site-2088ce1cae4288c3f3a1 | imported:semiconductor-atlas:sify-rabale-navi-mumbai | Sify Rabale data center campus (Mumbai 03), Navi Mumbai | India | IN | 19.1442 | 73.0086 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sify gives the address as Plot R-847, TTC Industrial Area, Rabale, Navi Mumbai, and the prospectus places towers 11 and 12 on Plot R-978 in the same industrial area. The point is the Rabale coordinate from its Wikipedia article (which also gives Thane district), so it marks the neighbourhood rather than the plots."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3ca04bf3-2438-554c-8f7a-ac8c8167e22c"] | 1 | ["c52dcc98-dfd2-5012-8703-5d9e24de51b2"] | ["imported:semiconductor-atlas:sify-rabale-navi-mumbai"] | ["partially_operational"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2088ce1cae4288c3f3a1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2088ce1cae4288c3f3a1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2088ce1cae4288c3f3a1.geojson | source-terms-not-recorded
vcc-site-20a2edd7bbbbe47d7c25 | curated:digital-realty-digital-dulles-campus | Digital Realty Digital Dulles Campus | United States | US | 38.961 | -77.4915 | Point | ["campus"] | ["first_party_published_map_pin"] | ["operator_decimal_coordinate_attributes_to_point_without_centroiding"] | ["official_operator_published_constituent_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Operator IAD44/B7 reference point within the county-identified Digital Dulles campus. It is not asserted to locate the unnamed 96 MW active development or Dulles 9 building; no building footprint or accuracy is inferred."] |  | No source provides a numeric horizontal-accuracy guarantee or a surveyed campus reference feature. | ["e9598e01-b9ef-5d87-a239-9d028a3e30c9"] | 1 | ["f054a923-1869-5cee-aec7-f9673b431f14"] | ["curated:digital-realty-digital-dulles-campus:current-96mw-development"] | ["under_construction"] | 2026-06-29 | 2026-06-29 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-20a2edd7bbbbe47d7c25/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-20a2edd7bbbbe47d7c25.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-20a2edd7bbbbe47d7c25.geojson | no-open-redistribution-license-asserted
vcc-site-210a7753dcf05471886c | imported:semiconductor-atlas:google-kansas-city-north-missouri | Google Kansas City data center campus (Hunt Midwest Business Center) | United States | US | 39.168 | -94.4788 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Approximate point on NE Parvin Road east of Interstate 435, within the Hunt Midwest Business Center that sources name as the site; the business park covers about 2,500 acres, so the data center parcel within it is not pinpointed."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["aea3d2fe-d525-5a26-a903-592f579b298d"] | 1 | ["52e21086-11ad-588d-a8a8-d9525e5e4744"] | ["imported:semiconductor-atlas:google-kansas-city-north-missouri"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-210a7753dcf05471886c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-210a7753dcf05471886c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-210a7753dcf05471886c.geojson | source-terms-not-recorded
vcc-site-2205657258ac3679cfaa | curated:hyperco-loviisa-data-center-campus | Hyperco Loviisa Data Center Campus | Finland | FI | 60.4744 | 26.2681 | Point | ["building"] | ["direct_geometry"] | ["ryhti_official_permit_building_point_as_project_locator"] | ["official_permit_building_reference_point"] | ["official_source"] | ["project_locator"] | ["Ryhti point for permanent building 104259934N cross-identified to the Hyperco permit by permanent permit, property, decision date, and gross floor area. It is a project locator, not a building footprint, parcel, campus, entrance, survey point, or work-at-point claim."] |  | Ryhti supplies no collection method, reference-feature definition, or bounded numeric horizontal-accuracy value for the building point. | ["a1f1c613-7606-5e9d-baf9-31cdb38d34f0"] | 1 | ["d024514a-30a3-514d-b65e-2743133f6800"] | ["curated:hyperco-loviisa-data-center-campus:current-development"] | ["under_construction"] | 2026-07-02 | 2026-07-02 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2205657258ac3679cfaa/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2205657258ac3679cfaa.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2205657258ac3679cfaa.geojson | CC-BY-4.0
vcc-site-23595034ead536d5a4cb | curated:firstcolo-fra7-rosbach-campus | firstcolo FRA7 Rosbach Campus | Germany | DE | 50.2948 | 8.6994 | Point | ["facility"] | ["coordinates_to_point"] | ["first_party_published_dms_coordinate_to_point"] | ["first_party_facility_reference_point"] | ["official_source"] | ["project_locator"] | ["First-party FRA7 factsheet coordinate converted exactly from degrees, minutes, and seconds and bound to the same named facility and street address. It is a facility locator, not a parcel, campus, building, project, entrance, centroid, or current-work boundary."] |  | The factsheet supplies no reference-feature definition, collection method, or numeric horizontal-accuracy statement; decimal digits produced by the DMS conversion do not add precision. | ["706814f6-ce3c-5619-83a7-174fea885db2"] | 1 | ["4afd2551-1442-5f67-a1d9-0d245835088d"] | ["curated:firstcolo-fra7-rosbach-campus:fra7-current-build"] | ["under_construction"] | 2026-06-15 | 2026-06-15 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-23595034ead536d5a4cb/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-23595034ead536d5a4cb.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-23595034ead536d5a4cb.geojson | all-rights-reserved-fact-extraction-only
vcc-site-23e1a428ab99ad167ba5 | curated:digico-syd1-ultimo-campus | DigiCo SYD1 Ultimo Campus | Australia | AU | -33.875 | 151.197 | Point | ["campus"] | ["source_geojson_point_without_coordinate_change"] | ["nsw_planning_portal_named_project_coordinate"] | ["official_project_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact source three-decimal official project point. This is a coarse campus reference, potentially outside building footprints, not a surveyed point, entrance, work area, parcel or boundary. Do not imply 1m accuracy, add zeros or replace it with a more precise third-party pin."] |  | The department publishes no accuracy statement. Decimal resolution is not measured positional accuracy. | ["34abf7af-e181-5f64-a9ec-6701337d4344","70fca129-659c-5b65-be70-00212cae5916","acc81d9e-b4ac-5438-962d-2d1c636ffae2"] | 1 | ["14a67880-da37-5f59-a2cf-2322bbf778d7"] | ["curated:digico-syd1-ultimo-campus:current-site-preparation"] | ["site_preparation"] | 2026-08-19 | 2026-08-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-23e1a428ab99ad167ba5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-23e1a428ab99ad167ba5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-23e1a428ab99ad167ba5.geojson | CC-BY-4.0; CC-BY-4.0-Department-material-scope
vcc-site-23fd4beb18c498caa043 | imported:semiconductor-atlas:tcs-hypervault-hyderabad | TCS HyperVault AI data center campus, Bharat Future City (Hyderabad) | India | IN | 17.3617 | 78.4747 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Hyderabad and place the campus in Bharat Future City on the city's southern outskirts, without a district, address or coordinates; Bharat Future City's Wikipedia article has no coordinates. The point is the Hyderabad city coordinate from Wikipedia, so it marks the named city, and the site lies an unknown distance to its south."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["68467274-a4f9-5243-aa49-c2a638788480"] | 1 | ["0d75be4c-1fff-5854-895c-71aef25eff11"] | ["imported:semiconductor-atlas:tcs-hypervault-hyderabad"] | ["announced"] | 2026-09-09 | 2026-09-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-23fd4beb18c498caa043/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-23fd4beb18c498caa043.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-23fd4beb18c498caa043.geojson | source-terms-not-recorded
vcc-site-249f52c31025c0aa2ef2 | curated:related-openai-oracle-stargate-michigan-saline | The Barn Stargate Data Center Campus | United States | US | 42.1239 | -83.8821 | Polygon | ["campus"] | ["cross_source_overlay"] | ["openstreetmap_named_website_tagged_construction_site_polygon_as_campus_locator"] | ["reviewed_openstreetmap_named_website_tagged_barn_construction_site_polygon"] | ["community_mapped"] | ["campus_locator"] | ["The frozen global-open-v3 Polygon is a contributor-mapped construction-site locator for the named Barn data-center campus, inherited by the current-build project through the explicit v14 project_targets relationship. It is not an official, cadastral, or survey boundary; a verified complete 250-acre campus extent; a building or project footprint; a construction extent; or a source of lifecycle, capacity, energy, operating-status, or imagery claims."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | ["2c1a0857-1368-581b-adfa-96bf72cc9c16"] | 1 | ["7d936c4e-29f2-592f-984b-61f5d6367fc8"] | ["curated:related-openai-oracle-stargate-michigan-saline:current-build"] | ["under_construction"] | 2026-09-28 | 2026-09-28 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["tracked_identity_bound_visible_change_followup_only_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-249f52c31025c0aa2ef2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-249f52c31025c0aa2ef2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-249f52c31025c0aa2ef2.geojson | ODbL-1.0
vcc-site-26279485fb1f7f11e894 | curated:merlin-edged-bilbao-arasur-campus | MERLIN Edged Bilbao-Arasur Campus | Spain | ES | 42.6977 | -2.9092 | Point | ["campus"] | ["operator_published_campus_location_link_literal_coordinate_query"] | ["operator_published_campus_location_link_literal_coordinate_query"] | ["operator_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["A campus locator may point to another constituent of a multi-building campus. It is not asserted to be the footprint or centroid of the selected new building. The named owner asset page provides the Supermanzana 6 campus address and LOCATION link. The captured 302 Location is a literal latitude/longitude search query. Coordinates are copied in reversed order for GeoJSON, without geocoding or selecting a map viewport."] |  | Neither source states quantitative positional accuracy or survey provenance; coordinate digits are not an accuracy estimate. | ["8c9736bc-10fe-5095-8011-14bd5162c919"] | 1 | ["7ac977cb-cbe2-5dfd-b058-f26707f86b6c"] | ["curated:merlin-edged-bilbao-arasur-campus:building-2-current-build"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-26279485fb1f7f11e894/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-26279485fb1f7f11e894.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-26279485fb1f7f11e894.geojson | no-open-license-asserted
vcc-site-265ff643497c82472bb3 | curated:chirisa-chesterfield-campus | Chirisa Chesterfield Campus | United States | US | 37.3562 | -77.3343 | Point | ["campus"] | ["official_service_parcel_centroid"] | ["ArcGIS_returnCentroid_true_outSR_4326_exact_property_query"] | ["official_parcel_reference_point"] | ["official_source"] | ["campus_locator"] | ["Official source-specific constituent-property centroid used only as a campus locator. Not a surveyed point, full campus boundary, building footprint, entrance, active-work extent or construction stage. Source numerical precision is not positional accuracy."] |  | County terms explicitly disclaim numerical positional accuracy and legal/survey use. | ["18e55c05-989b-581b-b412-470a89fff1c3","7b52ba23-d027-54d2-9dc8-998a8c792c8e","7df9c542-8a3d-5c86-815b-d46943c70555","86f45bc6-05ec-50f5-bfee-bdcfcac3b59c","9751ec41-030f-5351-9f67-7ca95c26e7b1","9f29ad18-9652-5243-9cd5-48eb83fb967f","e527b9c8-58f6-56e3-98d5-1d620a146f92","f1c93b01-9ffe-571c-b4f0-dd7a32d28d79"] | 1 | ["0b67b532-d779-5784-bd6d-d7ee124844aa"] | ["curated:chirisa-chesterfield-campus:digital-drive-current-build"] | ["under_construction"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-265ff643497c82472bb3/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-265ff643497c82472bb3.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-265ff643497c82472bb3.geojson | CC0-1.0; all-rights-reserved; no-open-document-redistribution-license-asserted
vcc-site-274ba04f1a143a081314 | curated:cyrusone-fra7-frankfurt-westside-campus | CyrusOne FRA7 Frankfurt Westside Campus | Germany | DE | 50.0934 | 8.5805 | Point | ["project"] | ["official_coordinate_transform"] | ["rp_darmstadt_ff7_l1_etrs89_utm32_coordinate_to_wgs84_point"] | ["official_source_reported_ff7_l1_reference_point"] | ["official_source"] | ["project_locator"] | ["Official-source coordinate for the FF7 L1 permit site/building, used only to locate the current FRA7 development. It is not a building centroid, parcel polygon, two-building campus boundary, current work zone, construction extent, or survey-accuracy claim."] |  | The permit and CRS reference do not state the feature represented by the coordinate, collection method, epoch-specific transform parameters, or horizontal positional accuracy. | ["850336d5-4d8f-5821-ae65-cb195961e7b6"] | 1 | ["58f9a985-bfa8-521c-ab85-132aec6799ed"] | ["curated:cyrusone-fra7-frankfurt-westside-campus:current-multi-building-development"] | ["under_construction"] | 2026-06-12 | 2026-06-12 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-274ba04f1a143a081314/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-274ba04f1a143a081314.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-274ba04f1a143a081314.geojson | rights-status-not-established
vcc-site-27b404b316b5fece1ef1 | imported:semiconductor-atlas:mgx-bpifrance-mistral-nvidia-campus | Campus AI Fouju | France | FR | 48.5864 | 2.7785 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Nominatim centroid of the commune of Fouju; sources name the commune but not a parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a82abc73-6eb4-56a6-896f-91d027b975eb"] | 1 | ["dd65fe26-5f6d-52e8-96b6-8709ca040b13"] | ["imported:semiconductor-atlas:mgx-bpifrance-mistral-nvidia-campus"] | ["under_construction"] | 2026-09-01 | 2026-09-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-27b404b316b5fece1ef1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-27b404b316b5fece1ef1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-27b404b316b5fece1ef1.geojson | source-terms-not-recorded
vcc-site-284562d636d49db446ea | imported:semiconductor-atlas:khazna-ajman | Khazna QAJ1 AI data center (Ajman) | United Arab Emirates | AE | 25.4136 | 55.4456 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin1"] | ["compiled_reference"] | ["admin1_context"] | ["Sources name only Ajman. Coordinates are the Ajman city point from its Wikipedia article and stand in for the emirate; the plot location is not published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2b3603ad-d2a2-504e-9c31-dbbb21a8b08d"] | 1 | ["384a401d-cc7f-52e4-9ae3-218a378995b9"] | ["imported:semiconductor-atlas:khazna-ajman"] | ["under_construction"] | 2025-10-14 | 2025-10-14 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-284562d636d49db446ea/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-284562d636d49db446ea.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-284562d636d49db446ea.geojson | source-terms-not-recorded
vcc-site-2890b11431bd73672216 | imported:semiconductor-atlas:vermaland-la-osa-pinal-county | La Osa Energy Center (Vermaland), Pinal County | United States | US | 32.7636 | -111.6 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of Eloy (s6). Sources place the site south of Eloy along the Greene Canal (s1), off Picacho Highway (s2) and about 12 miles outside the city (s4), so the parcel lies some distance from this point."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["792842fe-d879-503d-950c-3572e6314e9d"] | 1 | ["18844ee0-7ce9-5a0b-9a50-1d9ed0769266"] | ["imported:semiconductor-atlas:vermaland-la-osa-pinal-county"] | ["cancelled"] | 2026-08-26 | 2026-08-26 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2890b11431bd73672216/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2890b11431bd73672216.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2890b11431bd73672216.geojson | source-terms-not-recorded
vcc-site-2972c6d36048ca1770e2 | imported:semiconductor-atlas:meta-talavera-de-la-reina | Meta Talavera de la Reina data center campus | Spain | ES | 39.9583 | -4.8328 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid from the Talavera de la Reina Wikipedia article. Sources place the campus in the second phase of the Torrehierro industrial area, about 12 km from the town centre, but give no coordinates, so the site is not pinpointed."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["043bbd43-bda2-54d9-97f7-697c718363a4"] | 1 | ["1369aebb-7496-56a6-9260-159cd3a37283"] | ["imported:semiconductor-atlas:meta-talavera-de-la-reina"] | ["announced"] | 2026-08-28 | 2026-08-28 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2972c6d36048ca1770e2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2972c6d36048ca1770e2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2972c6d36048ca1770e2.geojson | source-terms-not-recorded
vcc-site-298aaa4c04e0d88160f7 | curated:microsoft-la-porte-indiana-campus | Microsoft La Porte Indiana Campus | United States | US | 41.5796 | -86.6901 | Polygon | ["campus"] | ["exact_official_constituent_parcel_id_match"] | ["Indiana_IGIO_layer0_state_parcel_id_461107326005000058_native_and_output_EPSG4326_no_transform"] | ["official_constituent_parcel_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Exact state-published polygon of constituent parcel 461107326005000058 at 360 E Boyd Boulevard, bound to Microsoft LPO campus by the government-hosted application and embedded county record. The application reports 215.361 acres for this parcel; Microsoft describes approximately 500 acres for the initial campus. This is not the whole campus boundary, a specific LPO building, the current grading area or the proposed eastern expansion. No campus count is inferred from buildings or phases."] |  | No source-specific numerical horizontal positional accuracy is established for this county-supplied parcel geometry. GIS storage tolerance, decimal precision and a government source do not establish surveyed accuracy. | ["740555a3-7826-5874-98c5-fd0e532c3b7b","a2b0611b-2853-50eb-9744-39c6c94b8f69"] | 1 | ["f2b93d1a-7c33-5a9e-be4d-f7d0dadec047"] | ["curated:microsoft-la-porte-indiana-campus:first-phase-current-build"] | ["under_construction"] | 2026-06-18 | 2026-06-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-298aaa4c04e0d88160f7/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-298aaa4c04e0d88160f7.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-298aaa4c04e0d88160f7.geojson | no-open-redistribution-license-asserted
vcc-site-29c7aa69cf49aaa11516 | curated:ascenty-vinhedo-campus | Ascenty Vinhedo Campus | Brazil | BR | -23.0702 | -47.013 | Point | ["campus"] | ["coordinates_to_point"] | ["first_party_published_coordinate"] | ["named_constituent_facility_point"] | ["official_source"] | ["campus_locator"] | ["Exact publisher coordinate for VIN02, used only as a broad Vinhedo campus locator for Vinhedo 3; not Vinhedo 3 parcel, building, or work footprint."] |  | The factsheet does not state coordinate accuracy. | ["2184bacc-e338-5f73-bb78-327e08fc392a"] | 1 | ["2cac8eb7-dff6-50bc-be49-b45f6e353982"] | ["curated:ascenty-vinhedo-campus:vinhedo-3"] | ["under_construction"] | 2026-05-28 | 2026-05-28 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-29c7aa69cf49aaa11516/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-29c7aa69cf49aaa11516.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-29c7aa69cf49aaa11516.geojson | all-rights-reserved-fact-extraction-only
vcc-site-2a7b2edfacb6958b2186 | curated:teraco-ct1-rondebosch-data-centre | Teraco CT1 Data Centre | South Africa | ZA | -33.9712 | 18.4649 | Point | ["campus"] | ["direct_geometry"] | ["first_party_facility_page_displayed_gps_coordinate_to_point"] | ["official_source_reported_facility_reference_point"] | ["official_source"] | ["campus_locator"] | ["The point locates the CT1 facility/campus only. It is not specific to the current expansion and is not a centroid, parcel, building outline, construction extent, or boundary."] |  | The page does not identify datum, reference feature, collection method, or horizontal accuracy; GPS wording supports geographic-point semantics but not survey accuracy. | ["3f9c9345-6060-57f1-af90-8f61f17e2cab"] | 1 | ["59a74e45-2dd2-5204-9c65-5430e8fc3148"] | ["curated:teraco-ct1-rondebosch-data-centre:current-expansion"] | ["under_construction"] | 2026-07-17 | 2026-07-17 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2a7b2edfacb6958b2186/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2a7b2edfacb6958b2186.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2a7b2edfacb6958b2186.geojson | all-rights-reserved
vcc-site-2b9d83de9f69d94f5df1 | imported:semiconductor-atlas:airtrunk-hyd1-chandanvelly | AirTrunk HYD1 Hyderabad | India | IN | 17.2327 | 78.1713 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["AirTrunk names Chandanvelly, Hyderabad, without an address; the point is the Chandanvelly village coordinate from its Wikipedia article, so it marks the village rather than the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["853741ff-31ec-5ba1-b5d2-522cb38c86e5"] | 1 | ["f8a7bd1c-26a2-5b59-8e1b-d657084c4f7c"] | ["imported:semiconductor-atlas:airtrunk-hyd1-chandanvelly"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2b9d83de9f69d94f5df1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2b9d83de9f69d94f5df1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2b9d83de9f69d94f5df1.geojson | source-terms-not-recorded
vcc-site-2c055eade62aa3fef4a9 | curated:dansk-data-center-1-esbjerg-campus | Dansk Data Center 1 Esbjerg Campus | Denmark | DK | 55.4582 | 8.4599 | Point | ["campus"] | ["official_address_feature_to_point"] | ["dar_access_address_point_for_dma_bound_ddc1_site"] | ["official_access_address_point_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Exact current DAR access-address point for Sahara 9, inherited through the DDC1 project_targets relationship. It is not a surveyed project point, entrance, parcel centroid, site boundary, building footprint, or construction extent."] |  | DAR returns accuracy code A but the captured feature supplies no bounded numeric horizontal uncertainty applicable to this point. | ["d9a29ab2-cb25-5e79-a336-da8c0f65241c"] | 1 | ["52d209cc-c8cd-5f8a-8337-cd887187f383"] | ["curated:dansk-data-center-1-esbjerg-campus:ddc1-current-build"] | ["under_construction"] | 2026-08-13 | 2026-08-13 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2c055eade62aa3fef4a9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2c055eade62aa3fef4a9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2c055eade62aa3fef4a9.geojson | CC-BY-4.0
vcc-site-2d8fde06f5151b5ae93b | curated:noris-network-nbg6-nuremberg-south-campus | noris network NBG6 Nürnberg Süd Campus | Germany | DE | 49.41 | 11.1315 | Point | ["campus"] | ["provider_supplied_community_named_BA3_building_centroid_bound_to_operator_project_code_and_campus"] | ["preserve_Nominatim_lat_lon_for_OSM_way_1445218606_match_literal_NBG6_BA3_name_to_operator_code_and_campus_then_corroborate_modular_400_square_metre_units"] | ["community_constituent_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["Exact returned representative point of a community feature named NBG6 BA3. The operator explicitly binds that code to Nürnberg Süd; separate modular-unit identity connects the August work report. Only a locator for the one campus is proposed, not an official parcel, campus boundary, surveyed entrance, active-work extent, quantitative accuracy claim, or independently verified imagery. Adjacent BA1/BA2 share the campus; the office map point is excluded."] |  | Neither selected community response supplies quantified positional accuracy; seven decimal digits do not establish accuracy. | ["6c64af1f-287f-5513-b5aa-839345350a23","9e7bcd9e-1b16-55c5-86ac-b3b91b931a00","a72810fd-923b-5f56-ab03-8c005cc5d8b1","b1dcdbb3-dd62-5d23-9129-baccd2b08f23","b4b28f3b-6f8f-56f1-8da7-0ebd8835d3d5"] | 1 | ["a1390e66-5b95-568b-869b-b9413c56f8ce"] | ["curated:noris-network-nbg6-nuremberg-south-campus:ba3-modular-expansion"] | ["under_construction"] | 2026-08-13 | 2026-08-13 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2d8fde06f5151b5ae93b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2d8fde06f5151b5ae93b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2d8fde06f5151b5ae93b.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-2d9846dc358cfee26779 | curated:bitzero-namsskogan-data-center-campus | Bitzero Namsskogan Data Center Campus | Norway | NO | 64.7143 | 12.8341 | Polygon | ["campus"] | ["cross_source_geometry"] | ["kartverket_official_cadastral_parcel_polygon_as_campus_locator"] | ["official_cadastral_parcel_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Exact reviewed Kartverket cadastral polygon for property 5044-50/44, used only to locate the source-linked Bitzero Namsskogan parent campus and inherited by its current power-infrastructure project. It is not a transformer-foundation location, data-hall or building footprint, current-work extent, verified complete campus boundary, security boundary, or survey-accuracy claim."] |  | Kartverket supplies only the coarse green parcel-accuracy class here, warns that property maps may be incomplete or imprecise, and does not expose boundary-line quality or a numeric horizontal uncertainty in this response. | ["90d3590f-be24-5554-809a-36313784fe51"] | 1 | ["c30aeadf-c2f6-58a5-a8b1-227868f477c1"] | ["curated:bitzero-namsskogan-data-center-campus:2026-power-infrastructure-expansion"] | ["foundations"] | 2026-06-15 | 2026-06-15 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2d9846dc358cfee26779/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2d9846dc358cfee26779.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2d9846dc358cfee26779.geojson | CC-BY-4.0
vcc-site-2f392531ebec4705b0aa | curated:jefferson-lab-newport-news-campus | Jefferson Lab Newport News Campus | United States | US | 37.0984 | -76.4897 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["34a0d6a4-02e3-57e3-8b39-6c7e64363b3a"] | 1 | ["9283d3fe-3789-54c7-abf4-8bb757e29835"] | ["curated:jefferson-lab-newport-news-campus:jldc-building"] | ["under_construction"] | 2026-06-12 | 2026-06-12 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2f392531ebec4705b0aa/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2f392531ebec4705b0aa.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2f392531ebec4705b0aa.geojson | public-domain-us-government
vcc-site-2fb799e38497b94b3ed1 | curated:nscale-kvandal-narvik-ai-data-center-campus | Nscale Kvandal Narvik AI Data Center Campus | Norway | NO | 68.5753 | 17.5801 | Polygon | ["campus"] | ["cross_source_overlay"] | ["kartverket_official_cadastral_parcel_polygon_as_campus_locator"] | ["official_cadastral_parcel_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Exact current Kartverket cadastral polygon for parcel 10/760, used only to locate the Nscale Kvandal campus and inherited by the 25 MW current-build project through the explicit v14 project_targets relationship. The parcel contains both officially mapped data-center buildings and is not the footprint or centroid of Data Center 1, the 25 MW EPC project, Data Center 2, or the complete campus."] |  | The captured WFS publishes accuracy class “Grønt” but no numeric horizontal uncertainty in metres; the bridge does not convert that class into survey accuracy. | ["7960e467-cbd7-52b6-9fe5-c0b3d905f1dd"] | 2 | ["8d1ed9d7-795d-55a8-b8cf-41e51579dd27","97f12a4b-6526-5c76-94b3-6562420ffe99"] | ["curated:nscale-kvandal-narvik-ai-data-center-campus:initial-25mw-epc-current-build","imported:semiconductor-atlas:nscale-kvandal-narvik"] | ["under_construction"] | 2026-07-06 | 2026-09-02 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2fb799e38497b94b3ed1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2fb799e38497b94b3ed1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-2fb799e38497b94b3ed1.geojson | CC-BY-4.0
vcc-site-307be41074d784035ee5 | imported:semiconductor-atlas:microsoft-skelton-grange-leeds | Microsoft Skelton Grange datacentre campus, Leeds | United Kingdom | GB | 53.7758 | -1.4978 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Nominatim point on Skelton Grange Road, Stourton (LS10 1RS), next to the former power station land the sources name; the exact plot boundaries are not published in the sources."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["72dad65d-f126-519a-a2dd-bfbd080c5b9a"] | 1 | ["ca9b7a8f-2f71-5996-8ef1-66d4a2bfe2fa"] | ["imported:semiconductor-atlas:microsoft-skelton-grange-leeds"] | ["announced"] | 2026-04-27 | 2026-04-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-307be41074d784035ee5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-307be41074d784035ee5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-307be41074d784035ee5.geojson | source-terms-not-recorded
vcc-site-30de35a29d7b36fc6ef8 | curated:flexbase-technologiezentrum-laufenburg-campus | FlexBase Technologiezentrum Laufenburg Campus | Switzerland | CH | 47.5536 | 8.0511 | Point | ["campus"] | ["copy_Overpass_center_of_explicitly_named_Technologiezentrum_Laufenburg_way1160708952"] | ["copy_Overpass_center_of_explicitly_named_Technologiezentrum_Laufenburg_way1160708952"] | ["community_mapped_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["Representative center of the named new construction feature. It is not a survey, building centroid, legal boundary, existing-office location or a claim that all mixed-use floor area is data-center space."] |  | Community map metadata does not provide survey accuracy or quantitative positional uncertainty. | ["0348daa4-b3cf-562b-97d3-9a49949647d2"] | 1 | ["c9b6bff7-09a3-599b-9c8c-49243461c0fb"] | ["curated:flexbase-technologiezentrum-laufenburg-campus:new-technology-centre-current-build"] | ["under_construction"] | 2026-06-18 | 2026-06-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-30de35a29d7b36fc6ef8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-30de35a29d7b36fc6ef8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-30de35a29d7b36fc6ef8.geojson | ODbL-1.0
vcc-site-315b5d219b6cb4413a2b | curated:university-edinburgh-acf | University of Edinburgh Advanced Computing Facility | United Kingdom | GB | 55.8557 | -3.1995 | Point | ["campus"] | ["direct_geometry"] | ["bbox_center_of_named_osm_building"] | ["community_mapped_existing_campus_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["Campus locator derived from the bounding-box centre of the existing named ACF building. OSM object address and name agree with the university procurement address. It does not delineate the CR4 extension, construction footprint, parcel or legal campus boundary."] |  | OSM object states no positional accuracy | ["f0213b05-a7d9-5681-98b7-0bd38e6e0c53"] | 1 | ["52b09d3a-44ac-5836-9724-7df5c69687bf"] | ["curated:university-edinburgh-acf:cr4-extension"] | ["shell"] | 2026-09-22 | 2026-09-22 | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-315b5d219b6cb4413a2b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-315b5d219b6cb4413a2b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-315b5d219b6cb4413a2b.geojson | ODbL-1.0
vcc-site-31ed6c5da19a943535f6 | curated:racks-central-johor-ai-campus | Racks Central Johor AI Campus | Malaysia | MY | 1.5324 | 103.9282 | MultiPolygon | ["host_estate"] | ["topological_union_of_two_osm_host_development_way_polygons"] | ["osm_iskandar_halal_park_phase_1_v4_phase_2_v3_union_retained_as_host_estate_context_not_campus_locator"] | ["community_multi_phase_host_development_polygon_context_only"] | ["community_source"] | ["host_estate_context"] | ["Union of the two named Iskandar Halal Park host-development phases as mapped by OpenStreetMap: way 639973556 version 4 (Phase 1; 16 distinct vertices in a closed way of 17 node references; about 39.76 ha) and way 639973557 version 3 (tagged Phase 2, U/C; 19 distinct vertices in a closed way of 20 node references; about 83.55 ha), two disjoint community polygons about 22 m apart totalling about 123.31 ha (WGS84 geodesic, diagnostic). Racks Central places its RCJM campus only in Iskandar Halal Park, 81700 Pasir Gudang, and reports its first Johor land as a five-acre (about 2.02 ha) plot in the park; no reviewed source places RCJM1, Phase A or that plot at any position within, or confirms containment in, either phase polygon. Host-development locality context only: not an RCJM campus, RCJM1 or Phase A locator, parcel, boundary, footprint or work extent. The display anchor is the planar centroid of the two longitude/latitude rings, kept unchanged only because the row schema requires a point; it lies about 3.3 m outside the Phase 2 ring and about 402 m from the Phase 1 ring, inside neither polygon, and is not an RCJM1 position."] |  | RCJM1's position relative to this host-development outline is unknown and no source bounds it; OpenStreetMap states no positional accuracy for either outline. No numeric uncertainty is asserted. | ["491b3b57-f2fb-53b4-ad33-07902a6d2e19","509271d0-17c4-5ef8-a5a2-58c9ccc5a9a2","a005d1f9-e99d-504f-8c0b-c8c1f03a29a4","b7d02532-d340-5ead-b9ab-84b2ca52a197","c9c2d9bd-d6b3-5738-9ca0-78a9c351954f"] | 1 | ["f6d1bce2-6fc7-5fd8-a1fb-55d5fe4cd8e9"] | ["curated:racks-central-johor-ai-campus:rcjm1-first-phase"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_host_estate_context_only | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-31ed6c5da19a943535f6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-31ed6c5da19a943535f6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-31ed6c5da19a943535f6.geojson | CC-BY-SA-2.0; ODbL-1.0; all-rights-reserved
vcc-site-32a95caf9128d7dd56c8 | imported:semiconductor-atlas:qts-fayetteville-georgia | QTS Fayetteville campus | United States | US | 33.4478 | -84.4617 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Fayetteville, Georgia. The campus is at 1435 Highway 54 West, bounded by Highway 54 West, Tyrone Road and Flat Creek Trail; no cited source gives site coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["25e20e63-5e98-5bda-9722-480996fbd354"] | 1 | ["7c43c342-562c-5d46-b793-39a4dd2a8cc0"] | ["imported:semiconductor-atlas:qts-fayetteville-georgia"] | ["partially_operational"] | 2025-11-21 | 2025-11-21 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-32a95caf9128d7dd56c8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-32a95caf9128d7dd56c8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-32a95caf9128d7dd56c8.geojson | source-terms-not-recorded
vcc-site-33110c77390f92dc4432 | curated:meta-richland-parish-data-center | Meta Richland Parish Data Center | United States | US | 32.5289 | -91.6361 | Point | ["campus"] | ["Use the single exact-name community feature, verify its source object geometry, and emit the unchanged service longitude/latitude in GeoJSON order."] | ["nominatim_exact_named_campus_reference_point"] | ["community_named_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["The returned point lies in the northern component of the named three-component campus relation. It represents the overall operator-described campus, not a particular first building, Phase 2 construction, or Laidley/Evest legal parcel. No survey, exact building centroid, active construction footprint or bounded numerical accuracy is claimed."] |  | Community mapper and geocoder provide no bounded horizontal accuracy; coordinate decimal places are not measurement precision. | ["0357dcf6-dd2c-51fe-b107-8c9b253f17ec","5492ab7f-9c74-548f-b15a-a0173d4d9c47","816746dd-9748-5937-8412-65422ee24556","90966722-c08a-559d-abf9-1e0cd87125ac","d5e0a9c8-25a7-56f4-b135-3a8fc17352e0"] | 2 | ["1404f5cd-04ee-57ea-8f73-91992fea0552","803e9da5-cd1e-5849-813c-fe7c5b5f126b"] | ["curated:meta-richland-parish-data-center:current-development","imported:semiconductor-atlas:meta-hyperion-richland-parish"] | ["under_construction"] | 2026-07-14 | 2026-07-16 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-33110c77390f92dc4432/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-33110c77390f92dc4432.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-33110c77390f92dc4432.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-35381f89404ef4c2a035 | imported:semiconductor-atlas:aker-nscale-korgen | Aker Nscale Korgen AI data center | Norway | NO | 66.0766 | 13.8219 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Korgen village centroid from Nominatim; sources say the plot is in a designated area at Korgen, possibly at Nedre Røssåga power station, but do not give a parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["88844eaa-3de7-5991-bf0e-d3ddbfa00b26"] | 1 | ["88c15bf1-8080-55a3-b2cd-dbd795654bf3"] | ["imported:semiconductor-atlas:aker-nscale-korgen"] | ["announced"] | 2025-10-27 | 2025-10-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-35381f89404ef4c2a035/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-35381f89404ef4c2a035.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-35381f89404ef4c2a035.geojson | source-terms-not-recorded
vcc-site-355111878b17009b2503 | curated:nextdc-kl1-kuala-lumpur | NEXTDC KL1 Kuala Lumpur Data Center Campus | Malaysia | MY | 3.0947 | 101.6284 | Point | ["campus"] | ["community_named_building_representative_point"] | ["preserve_Nominatim_way1026603690_lat_lon_and_bind_exact_NEXTDC_KL1_ref_operator_and_street"] | ["community_building_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["Representative point of the explicitly named NEXTDC KL1 data-center building, bound by operator/ref/address/URL tags and official contact address. Campus locator only, not the remaining fit-out hall, surveyed entrance or boundary. The same-named industrial-landuse result is not another campus; the operator's road-only directions destination is excluded."] |  | No feature-specific quantitative positional-accuracy estimate is supplied by the selected point source. Coordinate digits are retained without asserting survey accuracy. | ["679a7d39-e811-5c81-83c5-4ef3caff29c6","b420edee-9de9-5a3f-b6f7-0fe68eddf368"] | 1 | ["95b33a98-a85e-57af-b18d-6811a7fd3b20"] | ["curated:nextdc-kl1-kuala-lumpur:incremental-in-progress-fit-out"] | ["mep_electrical"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-355111878b17009b2503/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-355111878b17009b2503.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-355111878b17009b2503.geojson | ODbL-1.0
vcc-site-36334bc427db6b226db5 | curated:vantage-zrh1-winterthur-campus | Vantage Zurich I (ZRH1) Data Center Campus | Switzerland | CH | 47.5007 | 8.7613 | Point | ["campus"] | ["exact_official_download_record_LV95_easting_northing_to_WGS84_via_official_REFRAME_service"] | ["exact_operator_campus_street_house_number_postal_code_city_to_unique_official_address_directory_record"] | ["official_building_entrance_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["The selected exact official address record locates the shared ZRH1 campus, not the ZRH12 building, active construction footprint, campus boundary or new access entrance. The CSV gives millimetre-formatted coordinates but no quantitative accuracy for this record. Coordinate decimal places and transformation-service precision do not establish survey accuracy."] |  | No quantitative accuracy supplied for individual official address record EGAID 102586517. | ["0818330a-60db-531c-ab23-5ac7a6f225c7","22f02ca2-f634-5d40-8cff-d36809be3432","40248504-0241-53a6-b48b-cebedaf9a313","4ae7bc83-7774-5d6d-b321-f8ff5e764e46","add29c08-84c7-516f-ac75-dffc58438a11","c9b93f36-c38e-59b2-be92-b84c13969efe","db35dc26-765d-50ff-b592-447355a0a667"] | 1 | ["f0e92e2e-e082-5b7f-9486-fd744b5b68e6"] | ["curated:vantage-zrh1-winterthur-campus:zrh12"] | ["under_construction"] | 2026-07-30 | 2026-07-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-36334bc427db6b226db5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-36334bc427db6b226db5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-36334bc427db6b226db5.geojson | no-open-license-asserted; swisstopo-free-geodata-terms-2021-03-01; swisstopo-report-A-public-domain
vcc-site-36fd6f2f441272102aa1 | imported:semiconductor-atlas:scala-tambore-barueri | Scala Data Centers Tamboré Campus | Brazil | BR | -23.4656 | -46.8419 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Releases place the campus in the Tamboré area of Barueri alongside the Rodoanel without a street address; coordinates are the Tamboré reference point (Portuguese Wikipedia), and Tamboré spans Barueri and neighbouring Santana de Parnaíba."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["28743ca1-9778-595d-974c-94ff2c3c980a"] | 1 | ["4ea35229-9824-5086-8441-310876ea8911"] | ["imported:semiconductor-atlas:scala-tambore-barueri"] | ["partially_operational"] | 2025-10-30 | 2025-10-30 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-36fd6f2f441272102aa1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-36fd6f2f441272102aa1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-36fd6f2f441272102aa1.geojson | source-terms-not-recorded
vcc-site-37108b4d9d3683d6451d | imported:semiconductor-atlas:sify-noida-02 | Sify Noida 02 data center campus | India | IN | 28.57 | 77.32 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sify says Noida 02 is within 1 km of Noida 01, whose address is Plot B7, Sector 132, Noida; no address is given for Noida 02 itself. The point is the Noida city coordinate from its Wikipedia article, so it marks the city rather than the site near Sector 132."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["5a5fd34a-45cf-5da0-8871-2e26a40fc5f2"] | 1 | ["d31725a8-2753-5d70-963d-320d4f6fbb61"] | ["imported:semiconductor-atlas:sify-noida-02"] | ["partially_operational"] | 2025-10-16 | 2025-10-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-37108b4d9d3683d6451d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-37108b4d9d3683d6451d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-37108b4d9d3683d6451d.geojson | source-terms-not-recorded
vcc-site-37497f8175db87d92ef8 | curated:goodman-syd01-macquarie-park-data-centre | Goodman SYD01 Artarmon Data Centre | Australia | AU | -33.8184 | 151.19 | Point | ["project"] | ["coordinates_to_point"] | ["nsw_planning_portal_applicant_project_coordinate_to_point"] | ["official_applicant_project_site_reference_point"] | ["official_source"] | ["project_locator"] | ["Applicant-reported State Significant Development project-site coordinate for SSD-66777221, whose project name, applicant, address, and lots bind the SYD01 development. It is a point locator, not any lot, parcel, campus, building, project, or current-work boundary."] |  | The application supplies no datum, reference-feature definition, collection method, or numeric horizontal-accuracy statement. | ["8f3069b1-7b32-5df4-9329-c365ae2a09bb"] | 1 | ["99fa93f5-9f63-5576-b036-2ee8086032a3"] | ["curated:goodman-syd01-macquarie-park-data-centre:current-single-building-development"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-37497f8175db87d92ef8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-37497f8175db87d92ef8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-37497f8175db87d92ef8.geojson | all-rights-reserved-fact-extraction-only
vcc-site-37ddc3b143bf9ea08d1c | curated:cdc-marsden-park-campus | CDC Marsden Park Campus | Australia | AU | -33.7237 | 150.8364 | Polygon | ["facility"] | ["capture_replayed_geometry"] | ["cross_source_identity_bridge_to_live_osm_named_cdc_marsden_park_campus_polygon"] | ["community_mapped_named_cdc_marsden_park_campus_development_polygon"] | ["community_mapped"] | ["campus_locator"] | ["The polygon is a contributor-mapped named development outline and the point is only its deterministic longitude-latitude bounding-box midpoint. Neither is a survey, cadastral, planning, parcel, security, building, phase, or current construction boundary. OSM construction tags are retained solely as source context and never provide the selected project's authoritative lifecycle."] |  | OpenStreetMap supplies no survey accuracy, cadastral authority, planning-boundary authority, or numeric horizontal uncertainty for this way. | ["ce28239d-1c35-5043-9373-97416961a743"] | 1 | ["164033cb-411d-5ffb-ab5d-b04bdecfa1ac"] | ["curated:cdc-marsden-park-campus:early-construction"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-37ddc3b143bf9ea08d1c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-37ddc3b143bf9ea08d1c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-37ddc3b143bf9ea08d1c.geojson | ODbL-1.0
vcc-site-382d4c7030c7ed7c700d | curated:qts-york-county-south-carolina-data-center-campus | QTS York County Data Center Campus | United States | US | 35.0354 | -81.1034 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The exact address is asserted only for the parent QTS York campus. Building 1 remains at its source-explicit York locality, so the point is a campus locator only."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["6600dddb-f2d8-5458-8e71-b43f77cc5e01"] | 1 | ["5b758548-2a2a-5643-9ebb-d8381bbd2c52"] | ["curated:qts-york-county-south-carolina-data-center-campus:initial-phase-building-1"] | ["shell"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-382d4c7030c7ed7c700d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-382d4c7030c7ed7c700d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-382d4c7030c7ed7c700d.geojson | public-domain-us-government
vcc-site-3867ebd8648d7b1a2b65 | curated:equinix-mu4-munich-data-center | Equinix MU4 Munich Data Center | Germany | DE | 48.147 | 11.6825 | Polygon | ["facility"] | ["cross_source_geometry"] | ["openstreetmap_mu4_construction_landuse_polygon_as_parent_campus_locator"] | ["reviewed_openstreetmap_mu4_construction_landuse_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped MU4 construction-landuse polygon, used only to locate the parent MU4 campus. It is not a Phase 3 point or boundary, the complete current campus extent, an official parcel or planning boundary, a building footprint, or a current construction-progress extent."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | ["efe5b5c9-7394-5f0c-951b-051197168c49"] | 1 | ["b284fbeb-8cd9-5448-860d-b4f69bb8bd7a"] | ["curated:equinix-mu4-munich-data-center:phase-3"] | ["shell"] | 2026-07-16 | 2026-07-16 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3867ebd8648d7b1a2b65/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3867ebd8648d7b1a2b65.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3867ebd8648d7b1a2b65.geojson | ODbL-1.0
vcc-site-387901bd13edd6eab35d | imported:semiconductor-atlas:riot-corsicana | Riot Platforms Corsicana facility | United States | US | 32.05 | -96.47 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Riot's 10-K places the facility in Navarro County without naming a town or address. Coordinates are the Navarro County point from its Wikipedia article, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["8d80043d-a444-5148-9284-457130885e28"] | 1 | ["27338e9f-68b5-58be-b981-a8a13c391bd6"] | ["imported:semiconductor-atlas:riot-corsicana"] | ["partially_operational"] | 2026-08-10 | 2026-08-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-387901bd13edd6eab35d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-387901bd13edd6eab35d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-387901bd13edd6eab35d.geojson | source-terms-not-recorded
vcc-site-38f7e55e7e55aaed6c27 | curated:iij-shiroi-data-center-campus | IIJ Shiroi Data Center Campus | Japan | JP | 35.7991 | 140.0996 | Polygon | ["address_area"] | ["cross_source_geometry"] | ["estat_2020_jgd2011_exact_sakuradai_5_chome_polygon_as_campus_address_area_locator"] | ["official_census_small_area_address_area_polygon"] | ["official_source"] | ["campus_locator"] | ["Official e-Stat 2020 census small-area polygon for 桜台五丁目, used only as a broad address-area locator for the named campus. It is not a campus, parcel, cadastral, building, Phase 3, security, construction, or current-work boundary. The reported 55,117.019 square metres is only the selected statistical feature's area, never an IIJ campus, site, parcel, building, Phase 3, or construction area. Statistical small-area boundaries may not match general regional or administrative boundaries."] |  | The e-Stat download does not provide a numeric horizontal positional-accuracy statement for this selected feature. | ["f6d41f05-04ff-5e9b-8be6-164d895d24d6"] | 1 | ["1f33fed8-b0f9-50e2-8fac-56d135325c27"] | ["curated:iij-shiroi-data-center-campus:phase-3-server-building"] | ["under_construction"] | 2026-06-25 | 2026-06-25 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-38f7e55e7e55aaed6c27/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-38f7e55e7e55aaed6c27.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-38f7e55e7e55aaed6c27.geojson | e-stat-terms-compatible-with-CC-BY-4.0
vcc-site-3a91e1c2ee3ef8dbd116 | imported:semiconductor-atlas:terranova-praia-grande | Terranova Praia Grande data center campus (proposed) | Brazil | BR | -24.0061 | -46.4028 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name the city of Praia Grande and say the site is near its submarine cable landing point, without an address. The point is the city coordinate from the Praia Grande Wikipedia article."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f170ffcd-17b7-5b11-99ba-f4f8a5d74ea8"] | 1 | ["3fc18374-cbc2-5a11-9356-ab751ac3820c"] | ["imported:semiconductor-atlas:terranova-praia-grande"] | ["proposed"] | 2026-08-25 | 2026-08-25 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3a91e1c2ee3ef8dbd116/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3a91e1c2ee3ef8dbd116.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3a91e1c2ee3ef8dbd116.geojson | source-terms-not-recorded
vcc-site-3b04bcaab24c7214a619 | imported:semiconductor-atlas:atnorth-salo-fin05 | atNorth FIN05 Salo mega site | Finland | FI | 60.3879 | 23.1249 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Salo without a street address; the coordinates are the Nominatim point for Salo's central district (Salon suuralue)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["e5f7decb-779b-558c-bd40-4179cd817302"] | 1 | ["1f415639-6b0f-5f32-b15e-07984488b5cc"] | ["imported:semiconductor-atlas:atnorth-salo-fin05"] | ["announced"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3b04bcaab24c7214a619/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3b04bcaab24c7214a619.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3b04bcaab24c7214a619.geojson | source-terms-not-recorded
vcc-site-3b5d1fe13cf00d04d3f2 | imported:semiconductor-atlas:data4-escaudain | Data4 Escaudain campus | France | FR | 50.3333 | 3.3438 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Nominatim centroid of the commune of Escaudain; the site is the Parc des Soufflantes (former Usinor plant), which could not be geocoded more precisely."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ac81d24f-1213-55b4-8895-b11b038fa18b"] | 1 | ["f0afff75-0b96-5e18-a8f9-08ac9a4b99ff"] | ["imported:semiconductor-atlas:data4-escaudain"] | ["announced"] | 2026-06-15 | 2026-06-15 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3b5d1fe13cf00d04d3f2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3b5d1fe13cf00d04d3f2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3b5d1fe13cf00d04d3f2.geojson | source-terms-not-recorded
vcc-site-3c1f872aa59b74b065ea | curated:cdc-eastern-creek-campus | CDC Eastern Creek Campus | Australia | AU | -33.8181 | 150.8377 | Point | ["project"] | ["direct_geometry"] | ["authoritative_site_plan"] | ["shared_campus_reference_point"] | ["official_source"] | ["reviewed_site_locator"] | ["Official NSW project-site representative point for the shared Eastern Creek campus; not an EC5 building footprint.","Official NSW project-site representative point for the shared Eastern Creek campus; not an EC6 building footprint."] | 250 |  | ["6e5dc4f7-2b39-5a4a-8dc3-f0e20691527b","a4ae0a31-3e69-5886-ad17-7d2402e15677"] | 2 | ["2e2b9d40-5024-5e6d-bbb2-56a8b16b9c16","5c366d64-4bb5-5c28-ab62-ec20d60fb31a"] | ["curated:cdc-eastern-creek-campus:ec5-current-build","curated:cdc-eastern-creek-campus:ec6-current-build"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3c1f872aa59b74b065ea/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3c1f872aa59b74b065ea.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3c1f872aa59b74b065ea.geojson | no-license-stated-for-compact-factual-extraction
vcc-site-3c5c88d7f501e957c28a | curated:meta-lebanon-indiana-data-center | Meta Lebanon Indiana Data Center Campus | United States | US | 40.0643 | -86.531 | Point | ["campus"] | ["official_exact_permit_record_reference_point"] | ["DNR_DOWUnity_ATS_layer0_folder_id_FW33468_0_native_EPSG3857_server_to_EPSG4326_independently_checked"] | ["official_campus_associated_detention_outfall_permit_reference_locator"] | ["official_source"] | ["campus_locator"] | ["DNR record-reference point for FW-33468-0, an Orla campus-associated detention outfall at Deer Creek. The full DNR notice names the data-center campus at 3602 West State Road32; municipal July6 minutes equate Orla/Domino/Meta at that address. This locates one campus through its permit reference at the creek edge. It is not a data-center building center, construction work extent, surveyed facility point or campus boundary. Original UTM-to-map derivation was not independently verified; September location retrieval does not advance July6 construction."] |  | DNR publishes a permit-record reference point but no site-specific numeric horizontal accuracy. Service coordinate precision and transform agreement are not positional accuracy. | ["0795bcb6-d4ac-58b7-81dc-8f90bf417f20","63f2e542-6955-59a9-ba0e-6819eb82749a","7676427f-a61d-547c-a3f8-d91a734ebccd"] | 1 | ["1f430ea1-a0e6-5a91-b3e7-3f002b331cf6"] | ["curated:meta-lebanon-indiana-data-center:current-development"] | ["under_construction"] | 2026-07-06 | 2026-07-06 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3c5c88d7f501e957c28a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3c5c88d7f501e957c28a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3c5c88d7f501e957c28a.geojson | no-open-redistribution-license-asserted
vcc-site-3cd7dd9c786c855c1820 | osm:way/1383040174 | Microsoft Lévis Charny Data Center | Canada | CA | 46.7079 | -71.2587 | Point | ["campus"] | ["point_on_named_community_polygon"] | ["Shapely_Polygon_representative_point"] | ["named_community_site_locator"] | ["community_source"] | ["campus_locator"] | ["Interior representative point of an explicitly named OSM Microsoft campus polygon. Not official boundary, current work footprint or surveyed position."] |  | OSM mapping accuracy is not quantified; node decimal precision does not establish positional accuracy. | ["3ced538d-64d2-56f9-982d-6e46504192d5","ac662b5d-3d31-52ed-be5a-8b1f6f8d7589","d247e13b-a788-5e5d-83eb-0c2b6b92ed96"] | 1 | ["b3656b35-f3ad-5119-8918-ac5237bf2a7f"] | ["osm:way/1383040174:development-project"] | ["under_construction"] | 2026-06-08 | 2026-06-08 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3cd7dd9c786c855c1820/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3cd7dd9c786c855c1820.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3cd7dd9c786c855c1820.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-3d8ad7e35f76709e9b15 | imported:semiconductor-atlas:airtrunk-jhb2-iskandar-puteri | AirTrunk JHB2 | Malaysia | MY | 1.4523 | 103.6145 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["AirTrunk names Iskandar Puteri without an address; coordinates are the OpenStreetMap Nominatim centroid of Iskandar Puteri."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["09661d28-4b3e-583a-97a6-7e4d2a00a48a"] | 1 | ["ec871425-75fd-5ee1-9a6f-0e901b2f5837"] | ["imported:semiconductor-atlas:airtrunk-jhb2-iskandar-puteri"] | ["announced"] | 2026-07-29 | 2026-07-29 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3d8ad7e35f76709e9b15/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3d8ad7e35f76709e9b15.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3d8ad7e35f76709e9b15.geojson | source-terms-not-recorded
vcc-site-3dedcd29014f493a2abb | curated:riot-rockdale-site | Riot Rockdale Campus | United States | US | 30.5759 | -97.0789 | Point | ["campus"] | ["official_named_address_point"] | ["native_EPSG3857_to_EPSG4326_inverse_Web_Mercator"] | ["official_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["One official state-aggregated site/structure address reference point matched to the exact facility address. Not a campus boundary, parcel, surveyed point, active AMD work footprint, entrance or precise building marker. Decimal places preserve calculation only."] |  | Originating point placement and numeric positional accuracy are unspecified. Projection operation accuracy is also unavailable; no precision inferred. | ["05b0646a-d1a4-519d-8665-d227d9de98de","97d5f7f7-eccb-525f-8b01-7fe9559fc9b6","9e5d4ed7-96b5-5ce4-ac88-93dae1d063e1","a84487b4-936f-58f5-af8b-4990c2fbc3a1","ac66c257-47cc-5d6e-8d64-75d812af8d5c"] | 2 | ["298d7152-0985-535e-a701-60b689a3cd00","b4ff75a2-9d55-54ad-bf27-4c60b096eb0f"] | ["curated:riot-rockdale-site:amd-expansion-phases-3-4","imported:semiconductor-atlas:riot-rockdale"] | ["partially_operational","under_construction"] | 2026-08-10 | 2026-08-10 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3dedcd29014f493a2abb/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3dedcd29014f493a2abb.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3dedcd29014f493a2abb.geojson | no-open-license-asserted
vcc-site-3e65a9f3d78bff82cf77 | curated:qts-eagle-mountain-slc1-data-center-campus | QTS Eagle Mountain SLC1 Data Center Campus | United States | US | 40.2677 | -112.0333 | Point | ["campus"] | ["official_address_point"] | ["official_address_point"] | ["campus_address_point"] | ["official_source"] | ["campus_locator"] | ["Exact county-returned point for 550 E Hyperscale Way, capture method Placed on Map (Calc Parcel); broad SLC1 campus locator, not Building 2 footprint or parcel boundary."] |  | The county says the point was calculated from a parcel and supplies no bounded positional error. | ["646e7f86-8e12-5320-a580-ce00ffedf6ad"] | 1 | ["f166440f-2ab0-57ea-9788-c66d89c8704f"] | ["curated:qts-eagle-mountain-slc1-data-center-campus:building-2"] | ["under_construction"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3e65a9f3d78bff82cf77/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3e65a9f3d78bff82cf77.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-3e65a9f3d78bff82cf77.geojson | county-public-gis-fact-extraction-only
vcc-site-401adc8a0db451b1d581 | imported:semiconductor-atlas:stargate-uae | Stargate UAE / UAE-US AI Campus | United Arab Emirates | AE | 24.3438 | 55.1 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin1"] | ["compiled_reference"] | ["admin1_context"] | ["Sources place the campus in Abu Dhabi without naming a district, and its exact site has not been published. Coordinates are the OpenStreetMap Nominatim centroid of the Abu Dhabi emirate, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["dcc56831-8961-557a-ae3e-0ff3f61cd95d"] | 1 | ["4278fea3-2c31-5512-87d1-d713170569e2"] | ["imported:semiconductor-atlas:stargate-uae"] | ["under_construction"] | 2026-08-13 | 2026-08-13 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-401adc8a0db451b1d581/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-401adc8a0db451b1d581.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-401adc8a0db451b1d581.geojson | source-terms-not-recorded
vcc-site-40f241ba326fd84eebf1 | curated:goodman-par02-paris-data-centre-campus | Goodman PAR02 Paris Data Centre Campus | France | FR | 48.7604 | 2.4472 | Point | ["campus"] | ["official_exact_house_number_geocode"] | ["exact_named_address_feature_to_point_without_centroiding"] | ["official_address_campus_locator"] | ["official_source"] | ["campus_locator"] | ["The exact house-number point locates the reviewed Goodman campus address, not any specific phase, building, campus boundary or observed-work extent. Multiple buildings on this campus remain one physical site."] |  | The service supplies a house-number address point without a numeric horizontal-accuracy statement. Match score is not positional uncertainty. | ["15a46a40-3971-5abd-8e45-f6ccadbb5c48"] | 1 | ["e1aeeee2-575c-5873-a96a-528a6c08b387"] | ["curated:goodman-par02-paris-data-centre-campus:phase-1-current-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-40f241ba326fd84eebf1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-40f241ba326fd84eebf1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-40f241ba326fd84eebf1.geojson | no-open-redistribution-license-asserted
vcc-site-418907144d1bd1426055 | curated:cra-prague-gateway-data-center-campus | CRA Prague Gateway Data Center Campus | Czechia | CZ | 49.9482 | 14.3678 | Point | ["campus"] | ["official_parcel_union_point_on_surface"] | ["cuzk_permit_named_parcel_union_as_campus_locator"] | ["official_parcels_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["A deterministic point on the union of two current official parcel geometries named by the permit. It locates the wider CRA site only and is not an official campus boundary, building or work footprint, entrance, surveyed project point, or horizontal-accuracy claim."] |  | No project-applicable bounded horizontal accuracy was selected from CUZK. | ["956fa5bf-63d8-55e6-80f8-60eeeeca386d"] | 1 | ["acf9eda7-3b44-5e9b-8c40-62783a7e0aa0"] | ["curated:cra-prague-gateway-data-center-campus:current-campus-build"] | ["under_construction"] | 2026-08-20 | 2026-08-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-418907144d1bd1426055/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-418907144d1bd1426055.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-418907144d1bd1426055.geojson | all-rights-reserved
vcc-site-41e0189f5fc22ef9a733 | curated:enka-data-solutions-eds-ist-01-tuzla-data-center | ENKA Data Solutions EDS IST 01 Tuzla Data Center | Türkiye | TR | 40.8352 | 29.3237 | Point | ["project"] | ["direct_geometry"] | ["first_party_facility_page_map_pin_point"] | ["first_party_facility_page_reference_point"] | ["official_source"] | ["project_locator"] | ["The source decimal strings are preserved exactly and parsed without coordinate transformation. Their many decimal places do not imply a surveyed reference feature or centimetre-scale horizontal accuracy."] |  | The page does not identify a geodetic datum, surveyed reference feature, collection method, or numeric horizontal accuracy. | ["959963fd-1d27-5927-a972-8a04fd97727e"] | 1 | ["15e0ef92-6408-5517-b0d4-a6b8707745f4"] | ["curated:enka-data-solutions-eds-ist-01-tuzla-data-center:initial-build"] | ["under_construction"] | 2026-06-12 | 2026-06-12 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-41e0189f5fc22ef9a733/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-41e0189f5fc22ef9a733.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-41e0189f5fc22ef9a733.geojson | all-rights-reserved
vcc-site-424c62f417d6e6ef2c93 | imported:semiconductor-atlas:atnorth-solleftea-swe04 | atNorth SWE04 Sollefteå mega site | Sweden | SE | 63.1785 | 17.0671 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Site is the Hamre property (Hamre 4:87 after subdivision) in Hamre Industrial Park, Långsele; the Långsele village centroid from Nominatim is used because the parcel was not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["5633b2ba-7c68-53a7-aa22-b84d9bb65d02"] | 1 | ["77b8badc-29e2-55ce-b570-5d4387e30505"] | ["imported:semiconductor-atlas:atnorth-solleftea-swe04"] | ["announced"] | 2026-06-16 | 2026-06-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-424c62f417d6e6ef2c93/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-424c62f417d6e6ef2c93.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-424c62f417d6e6ef2c93.geojson | source-terms-not-recorded
vcc-site-42f06f3124352e4af817 | imported:semiconductor-atlas:adaniconnex-hyderabad | AdaniConneX Hyderabad data centre campus | India | IN | 17.3888 | 78.4611 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Hyderabad only. Coordinates are the OpenStreetMap Nominatim centroid of Hyderabad, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["9d576bb9-0637-5135-927f-62427dc5e634"] | 1 | ["9753db27-dba7-5bba-933f-499d9b7ffa72"] | ["imported:semiconductor-atlas:adaniconnex-hyderabad"] | ["partially_operational"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-42f06f3124352e4af817/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-42f06f3124352e4af817.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-42f06f3124352e4af817.geojson | source-terms-not-recorded
vcc-site-4325075080f62b6ecff4 | curated:israel-mega-dc-mdcil1-modiin-site | Mega D.C. MDCIL-1 Modi'in Site | Israel | IL | 31.9168 | 34.9688 | Polygon | ["campus"] | ["approved_plan_land_use_plot_ring_transformed_EPSG2039_to_WGS84"] | ["Xplan_layer4_plot_query_native_ring_PROJ_Israel1993_to_WGS84_2_round7"] | ["approved_statutory_plan_land_use_plot"] | ["official_source"] | ["campus_locator"] | ["Every native plot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. Plot 62 of plan 420-1456037 is bound to the campus by the issuer's own plot references; it is a planning plot, not a surveyed cadastral boundary, building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it."] |  | The planning service states no positional accuracy and disclaims official status; the 0.5 m datum-operation figure is not a plot accuracy. | ["30404c19-2608-5791-98f7-8411cde80c3c","5743d0fa-a65e-5167-a493-d21e6e0f1c59"] | 1 | ["82f20665-aa7b-51d5-b303-ddf63792d77b"] | ["curated:israel-mega-dc-mdcil1-modiin-site:phase-b"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4325075080f62b6ecff4/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4325075080f62b6ecff4.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4325075080f62b6ecff4.geojson | no-open-license-asserted
vcc-site-43a4fd4202a0c1c9518f | imported:semiconductor-atlas:bitdeer-shalersville-portage-county | Bitdeer and Geis Shalersville AI data center campus | United States | US | 41.2456 | -81.2603 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources place the site at the Turnpike Commerce Center just north of the Ohio Turnpike in Shalersville Township, without coordinates. The point is the township coordinate from its Wikipedia article, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["54ab57f7-416c-52ec-8ca1-9b7762480ab9"] | 1 | ["9ed96427-8138-552b-9f88-3b1fbeaa341b"] | ["imported:semiconductor-atlas:bitdeer-shalersville-portage-county"] | ["proposed"] | 2026-10-07 | 2026-10-07 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-43a4fd4202a0c1c9518f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-43a4fd4202a0c1c9518f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-43a4fd4202a0c1c9518f.geojson | source-terms-not-recorded
vcc-site-43bf6c7b8c9e9dfc51d0 | curated:galaxy-helios-data-center-campus | Galaxy Helios Data Center Campus | United States | US | 33.7806 | -100.8671 | Point | ["campus"] | ["official_address_range_geocode"] | ["census_single_exact_address_match_then_explicit_nad83_to_wgs84"] | ["official_address_range_interpolation_constituent_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Government geocoder street-range interpolation for the TCEQ-registered Helios I address. Used for the physical campus only; Phase II's separate 1003 FM 193 address is unresolved in Census. No Phase II footprint, parcel boundary or surveyed accuracy is asserted."] |  | No source provides a numeric horizontal-accuracy guarantee or a surveyed campus reference feature. | ["50b56d5c-226f-57f8-b2b1-9d79212c26eb","69ecb4cd-be02-55fa-b978-732f307eeb00"] | 2 | ["2f422325-bd08-5072-a93f-dde01520f486","c7adcc1a-b5ed-5df0-b28b-572b6d9dbc4b"] | ["curated:galaxy-helios-data-center-campus:phase-2-260mw-critical-it-build","imported:semiconductor-atlas:galaxy-helios"] | ["partially_operational","under_construction"] | 2026-07-06 | 2026-08-12 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-43bf6c7b8c9e9dfc51d0/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-43bf6c7b8c9e9dfc51d0.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-43bf6c7b8c9e9dfc51d0.geojson | no-open-redistribution-license-asserted
vcc-site-450769770dfe5ea908d6 | imported:semiconductor-atlas:powerhouse-big-watt-taylor | Taylor Technology Campus (Big Watt Digital and PowerHouse) | United States | US | 30.5725 | -97.4167 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Bisnow gives the address 3301 Farm to Market Road 112; KUT places the site just outside Taylor's city limits in unincorporated Williamson County, pending annexation. The point is the Taylor city coordinate from its Wikipedia article, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["900327af-48bd-5ddf-a20d-83ef31e1ec24"] | 1 | ["8e72e640-c0e0-5e58-8a76-e53c011dcf92"] | ["imported:semiconductor-atlas:powerhouse-big-watt-taylor"] | ["proposed"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-450769770dfe5ea908d6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-450769770dfe5ea908d6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-450769770dfe5ea908d6.geojson | source-terms-not-recorded
vcc-site-45292d327405c32357bc | curated:flexential-hillsboro-starr-campus | Flexential Hillsboro Starr Campus | United States | US | 45.5565 | -122.9394 | Point | ["campus"] | ["source_community_representative_point"] | ["exact_OSM_way1080170580_Nominatim_representative_lon_lat"] | ["named_community_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["Exact H5-named, operator/address-bound OSM building representative point. Not a surveyed building footprint, campus boundary, construction extent, entrance or whole-campus centre. Neighboring H4/H3 and restricted municipal points unselected."] |  | No source-specific numeric positional accuracy for community geometry/representative point. | ["16df3c45-da29-54dc-8ddd-5db6caea30ac","9a452bd3-9e57-553d-aa8a-322bd1b1d4df","b5f725b6-c011-5875-9eac-4b24ef7aa0ed","f3fccadb-e01f-5545-9b50-2e655093f641"] | 1 | ["ad57807a-f6b6-55f9-b26f-acd194e12880"] | ["curated:flexential-hillsboro-starr-campus:hillsboro-5-current-build"] | ["under_construction"] | 2026-08-18 | 2026-08-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-45292d327405c32357bc/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-45292d327405c32357bc.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-45292d327405c32357bc.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-4551992e6d4d1487d1ab | imported:semiconductor-atlas:bitdeer-clarington-ohio | Bitdeer Clarington data center site | United States | US | 39.7728 | -80.8708 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Bitdeer names only Clarington, Ohio. Coordinates are the village point from its Wikipedia article, which also gives the county; the site itself is not pinpointed."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a2bccfaf-e1b2-5d80-8e08-ff37122f1c29"] | 1 | ["6799aac4-c4f8-5902-b8ae-2fffb6fa893d"] | ["imported:semiconductor-atlas:bitdeer-clarington-ohio"] | ["announced"] | 2026-08-10 | 2026-08-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4551992e6d4d1487d1ab/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4551992e6d4d1487d1ab.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4551992e6d4d1487d1ab.geojson | source-terms-not-recorded
vcc-site-4586aa46386f0cb18dc7 | curated:niger-national-data-center-pk5-niamey | Niger National Data Center PK5 | Niger | NE | 13.5597 | 2.1135 | Point | ["project"] | ["official_dms_coordinate_to_point"] | ["bnee_eies_project_area_coordinate"] | ["official_environmental_assessment_project_point"] | ["official_source"] | ["project_locator"] | ["The point is the EIES-reported coordinate of the project area at the selected Niger Telecom PK5 site. It is not a surveyed entrance, parcel centroid, building footprint, campus boundary, or current-work extent."] |  | The EIES reports DMS precision but no survey method, datum-specific accuracy statement, or bounded horizontal uncertainty. | ["e8b0b9c1-e565-5bea-be8f-a8f5c4eeb6df"] | 1 | ["4f39070f-83dd-557a-a1b0-88408f56c1fb"] | ["curated:niger-national-data-center-pk5-niamey:current-build"] | ["under_construction"] | 2026-06-18 | 2026-06-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4586aa46386f0cb18dc7/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4586aa46386f0cb18dc7.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4586aa46386f0cb18dc7.geojson | all-rights-reserved
vcc-site-4776103546341c240223 | imported:semiconductor-atlas:cyrusone-freestone-county | CyrusOne Freestone County data center campus | United States | US | 31.7183 | -96.1697 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of Fairfield (s3). CyrusOne gives the Freestone Energy Center's Fairfield address (on FM 488) as the reference point and has no address for the data center itself; the site was not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["1d917775-0af3-5219-98e1-39146778e43a"] | 1 | ["a5618437-38a6-5fd0-a340-56ab10f1e97b"] | ["imported:semiconductor-atlas:cyrusone-freestone-county"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4776103546341c240223/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4776103546341c240223.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4776103546341c240223.geojson | source-terms-not-recorded
vcc-site-47f902912a847a235f3d | imported:semiconductor-atlas:eni-khazna-ferrera-erbognone | Eni and Khazna AI data center campus, Ferrera Erbognone | Italy | IT | 45.117 | 8.867 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Municipality centroid from the Ferrera Erbognone Wikipedia article. Sources name the municipality only."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a7222596-74ce-5d03-8348-f324c5280b8d"] | 1 | ["5d11dbb6-e8aa-5602-9c7c-8997b1c620c1"] | ["imported:semiconductor-atlas:eni-khazna-ferrera-erbognone"] | ["announced"] | 2026-08-10 | 2026-08-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-47f902912a847a235f3d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-47f902912a847a235f3d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-47f902912a847a235f3d.geojson | source-terms-not-recorded
vcc-site-487fd7b91c213d078d2d | curated:microsoft-heath-oh-datacenter | Microsoft Heath Datacenter | United States | US | 40.0258 | -82.4803 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["2803efb1-75a9-5146-8bbd-483714ab9841"] | 1 | ["edf978b4-fbe8-5f8a-9fe0-bd1e9f33e1d2"] | ["curated:microsoft-heath-oh-datacenter:initial-site-preparation"] | ["site_preparation"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-487fd7b91c213d078d2d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-487fd7b91c213d078d2d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-487fd7b91c213d078d2d.geojson | public-domain-us-government
vcc-site-4905a5572ec5f3fc6e2d | imported:semiconductor-atlas:meta-montgomery | Meta Montgomery data center | United States | US | 32.3777 | -86.3091 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City point from OpenStreetMap Nominatim; Meta gives no site address."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["26e820ae-0d05-593e-9d5f-794caa26f215"] | 1 | ["c0f8dadf-2c3d-5176-b649-85363c06e1fa"] | ["imported:semiconductor-atlas:meta-montgomery"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4905a5572ec5f3fc6e2d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4905a5572ec5f3fc6e2d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4905a5572ec5f3fc6e2d.geojson | source-terms-not-recorded
vcc-site-492efa6e8a99e32cfb93 | imported:semiconductor-atlas:airtrunk-jhb3-iskandar-puteri | AirTrunk JHB3 Johor Bahru | Malaysia | MY | 1.4222 | 103.65 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["AirTrunk and W.Media name Iskandar Puteri without an address; the point is the Iskandar Puteri coordinate from its Wikipedia article, so it marks the city rather than the campus."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["9a88e6c1-7d4b-5b22-96b2-7c13e495e1a7"] | 1 | ["baa5ddbb-3439-5e4f-a03f-265b844b4460"] | ["imported:semiconductor-atlas:airtrunk-jhb3-iskandar-puteri"] | ["announced"] | 2026-04-30 | 2026-04-30 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-492efa6e8a99e32cfb93/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-492efa6e8a99e32cfb93.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-492efa6e8a99e32cfb93.geojson | source-terms-not-recorded
vcc-site-495790bb0eec99f8d10f | osm:way/1383040176 | Microsoft L’Ancienne-Lorette Data Center | Canada | CA | 46.7919 | -71.3468 | Point | ["campus"] | ["official_address_range_interpolation"] | ["EPSG4617_to_EPSG4326_NAD83CSRS_to_WGS84_2"] | ["official_interpolated_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["Source-matched unsuffixed address record interpolated along a road-address range. Not an entrance, exact building, parcel centroid, or current work footprint. Exact decimal output preserves calculation only."] |  | Official source labels geometry geocoded and supplies no numeric positional accuracy. The 1m datum operation accuracy is not the much less constrained address-interpolation accuracy. | ["1f2cd24b-81fb-5075-a1a7-dc959ca421ba","b492f623-6c24-5c9e-93c9-5ae9e8cc61b6","b78fbb97-deca-58c8-b3a8-233e3a77baf5","f1de17cc-40e9-5de3-8054-8d23d670f770"] | 1 | ["867d91cb-7a17-59db-a92e-4a50a499f54f"] | ["osm:way/1383040176:development-project"] | ["under_construction"] | 2026-06-08 | 2026-06-08 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-495790bb0eec99f8d10f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-495790bb0eec99f8d10f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-495790bb0eec99f8d10f.geojson | CC-BY-4.0; no-open-license-asserted
vcc-site-499a1602728034c6a587 | imported:semiconductor-atlas:mihta-askiy-data-centre-peace-river | Mihta Askiy Data Centre | Canada | CA | 56.3814 | -116.7479 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Point from the Government of Alberta major projects inventory, which notes its map location is not exact; rounded to four decimals. The federal notice places the project about 40 km northeast of Peace River."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["1b01daad-275d-5d85-8065-33576847e484"] | 1 | ["a2de1edb-c874-5d78-902a-e174a5ecd03e"] | ["imported:semiconductor-atlas:mihta-askiy-data-centre-peace-river"] | ["proposed"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-499a1602728034c6a587/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-499a1602728034c6a587.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-499a1602728034c6a587.geojson | source-terms-not-recorded
vcc-site-4a5d5083c6a8b110c612 | imported:semiconductor-atlas:data4-hanau | Data4 Hanau campus | Germany | DE | 50.1 | 8.95 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Centroid of the Großauheim district of Hanau from its Wikipedia article. Data4 places the campus on the former Großauheim military base but no cited source gives coordinates for the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ce89216d-e227-5e79-944a-25d62f4fc66c"] | 1 | ["c53b72b6-ff87-58eb-b74f-7082b159a513"] | ["imported:semiconductor-atlas:data4-hanau"] | ["under_construction"] | 2026-03-11 | 2026-03-11 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4a5d5083c6a8b110c612/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4a5d5083c6a8b110c612.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4a5d5083c6a8b110c612.geojson | source-terms-not-recorded
vcc-site-4ac69f22d359cc462f5b | curated:bitdeer-wenatchee-washington-campus | Bitdeer Wenatchee Washington Campus | United States | US | 47.4139 | -120.2093 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["626c5c59-9386-58ac-9de1-f81bc82d4900"] | 1 | ["484cf452-3a8f-5574-8003-a5b3f693c5d2"] | ["curated:bitdeer-wenatchee-washington-campus:2026-ai-conversion-site-preparation"] | ["site_preparation"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4ac69f22d359cc462f5b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4ac69f22d359cc462f5b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4ac69f22d359cc462f5b.geojson | public-domain-us-government
vcc-site-4b620bcac790d6755738 | imported:semiconductor-atlas:iozera-tetouan | Iozera Tetouan AI data center and hub | Morocco | MA | 35.567 | -5.367 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City coordinates from the Tétouan Wikipedia article; the opened sources name only the city, not a site within it."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["00756bbb-b1cd-54d5-9350-2a11b661673f"] | 1 | ["ee6721e5-5463-5350-9b3d-fe2429103a70"] | ["imported:semiconductor-atlas:iozera-tetouan"] | ["announced"] | 2026-07-09 | 2026-07-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4b620bcac790d6755738/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4b620bcac790d6755738.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4b620bcac790d6755738.geojson | source-terms-not-recorded
vcc-site-4c2cf1101b80a8a4c17e | curated:atnorth-fin04-kouvola-campus | atNorth FIN04 Kouvola Campus | Finland | FI | 60.7834 | 26.7644 | MultiPolygon | ["campus"] | ["official_coordinate_transform"] | ["nls_official_cadastral_multipolygon_as_fin04_shared_campus_locator"] | ["official_cadastral_property_as_shared_campus_locator"] | ["official_source"] | ["campus_locator"] | ["NLS property 286-423-20-1 transformed from EPSG:3067 using pyproj 3.7.2 / PROJ 9.5.1 after the Kouvola permit binds atNorth and Lossitie 26 to that property. Its three disconnected cadastral features are retained as one exact MultiPolygon only as a shared-campus locator, not a Phase 1, campus, building, current-work, or publication-target official boundary."] |  | NLS supplies authoritative source geometry but no bounded numeric horizontal-accuracy value applicable to this transformed publication; transformed digits do not add accuracy. | ["6fa1a931-3b5c-5259-9b15-853187c9ae2a"] | 1 | ["7c7b8437-ca56-55a0-aa36-54155f43760e"] | ["curated:atnorth-fin04-kouvola-campus:phase-1"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4c2cf1101b80a8a4c17e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4c2cf1101b80a8a4c17e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4c2cf1101b80a8a4c17e.geojson | CC-BY-4.0
vcc-site-4c3f2c7b887170cea7c1 | imported:semiconductor-atlas:compass-meridian-mississippi | Compass Datacenters Meridian campus | United States | US | 32.3747 | -88.7042 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Meridian. Compass places the campus in the Meridian I-20/59 Industrial Park; no cited source gives site coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3b11e0f1-1a48-542b-9b5c-c681ae6ed732"] | 1 | ["2b520cfa-8aea-5212-9b60-8ff417ee6578"] | ["imported:semiconductor-atlas:compass-meridian-mississippi"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4c3f2c7b887170cea7c1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4c3f2c7b887170cea7c1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4c3f2c7b887170cea7c1.geojson | source-terms-not-recorded
vcc-site-4cde3223014097681c99 | imported:semiconductor-atlas:k2-zibido-san-giacomo-lacchiarella | K2 hyperscale data center campus, Zibido San Giacomo and Lacchiarella | Italy | IT | 45.317 | 9.133 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Lacchiarella municipal centroid from its Wikipedia article. The campus spans Zibido San Giacomo and Lacchiarella; no cited source gives site coordinates, so the point only marks one of the two municipalities."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["678ee678-24bb-5cee-bce9-0f8e0bd74c28"] | 1 | ["a0ee0f70-6708-5a9c-8b50-a61e93a5e501"] | ["imported:semiconductor-atlas:k2-zibido-san-giacomo-lacchiarella"] | ["announced"] | 2026-08-18 | 2026-08-18 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4cde3223014097681c99/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4cde3223014097681c99.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4cde3223014097681c99.geojson | source-terms-not-recorded
vcc-site-4d39b5b9701e6327b926 | curated:telecom-egypt-rdh2-smart-village-campus | Telecom Egypt RDH2 Smart Village Campus | Egypt | EG | 30.0767 | 31.0218 | Polygon | ["host_estate"] | ["osm_way_nodes_to_polygon"] | ["osm_smart_village_way_545580264_v6_retained_as_host_estate_context_not_campus_locator"] | ["community_host_development_polygon_context_only"] | ["community_source"] | ["host_estate_context"] | ["Entire Smart Village business park in Giza as mapped by OSM way 545580264 version 6: a 12-vertex community polygon (a closed way of 13 node references) of about 382.32 ha (WGS84 geodesic, diagnostic). The selected project evidence places RDH2 only in Smart Village; no reviewed source places RDH2 at any position within, or confirms containment in, this polygon. In the 2026-10-08 OSM snapshot it contains 88 mapped buildings, 38 of them named, among them Vodafone Egypt, Orange Egypt, Microsoft, Oracle, IBM, Huawei, Ericsson, HSBC, the National Telecom Regulatory Authority and the communications ministry, plus a separate Telecom Egypt office building and a TE Data building; none is named or tagged as RDH2 or a data centre. Host-development locality context only: not an RDH2 locator, parcel, boundary, footprint or work extent. The display anchor is the planar centroid of the business park's longitude/latitude ring, kept unchanged only because the row schema requires a point; it is not an RDH2 position."] |  | RDH2's position relative to this host-development outline is unknown and no source bounds it; OpenStreetMap states no positional accuracy for the outline. No numeric uncertainty is asserted. | ["491b3b57-f2fb-53b4-ad33-07902a6d2e19","6b5a280d-e799-5d2a-bbd6-ec92effbe2e0","d222545d-ed52-5967-9482-5e9fff4d291b"] | 1 | ["35c427dc-af95-5011-b3ab-3fa7c90fcb30"] | ["curated:telecom-egypt-rdh2-smart-village-campus:regional-data-hub-2"] | ["commissioning"] | 2026-06-10 | 2026-06-10 | recent_authoritative_physical_observation_plus_host_estate_context_only | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4d39b5b9701e6327b926/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4d39b5b9701e6327b926.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4d39b5b9701e6327b926.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-4ed4b7a2d6d92a9362bb | imported:semiconductor-atlas:meta-tulsa | Meta Tulsa data center | United States | US | 36.1563 | -95.9928 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City point from OpenStreetMap Nominatim; Meta places the site in East Tulsa but names no road or parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["7fec14c3-48ab-51e7-806a-bcca87662826"] | 1 | ["302bc1de-8d94-5ca1-a94e-ceb9facdcc1e"] | ["imported:semiconductor-atlas:meta-tulsa"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4ed4b7a2d6d92a9362bb/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4ed4b7a2d6d92a9362bb.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-4ed4b7a2d6d92a9362bb.geojson | source-terms-not-recorded
vcc-site-50ba6e2d0f69faaff629 | imported:semiconductor-atlas:teton-digital-black-bear-swan-hills | Teton Digital Black Bear power and data centre campus (Swan Hills) | Canada | CA | 54.5325 | -115.5732 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Coordinates of the south end of the power plant project area as stated in the 2024 federal project description (SW and SE quarters of Section 15-64-11-W5M). The data centre land is described only as adjacent Crown land, so its centre may differ."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d5c22c5a-1956-5498-9c09-94a18e16251b"] | 1 | ["b10fbc1b-2689-5864-989c-b36b13abb9ad"] | ["imported:semiconductor-atlas:teton-digital-black-bear-swan-hills"] | ["proposed"] | 2026-09-23 | 2026-09-23 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-50ba6e2d0f69faaff629/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-50ba6e2d0f69faaff629.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-50ba6e2d0f69faaff629.geojson | source-terms-not-recorded
vcc-site-52b1e1c3038357306a39 | curated:adaniconnex-pune-data-center-campus | AdaniConneX Pune Data Center Campus | India | IN | 18.6467 | 73.8073 | Point | ["project"] | ["direct_geometry"] | ["official_project_report_coordinate_to_point"] | ["official_source_reported_project_reference_point"] | ["official_source"] | ["project_locator"] | ["Official source-reported point used only to locate the PNQ04 project. It is not a project centroid, footprint, parcel, building outline, construction extent, campus boundary, or survey-accuracy claim."] |  | The report does not identify the coordinate's datum, reference feature, collection method, or horizontal accuracy. | ["9e5f7eb0-994d-534d-8715-b16378b71787"] | 2 | ["48eb54d5-dd3f-51a3-aeed-1ddce1949763","df5ccb0c-2ab0-56fc-a260-71db9387c492"] | ["curated:adaniconnex-pune-data-center-campus:pnq04-current-build","imported:semiconductor-atlas:adaniconnex-pune"] | ["partially_operational","under_construction"] | 2026-06-01 | 2026-07-29 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-52b1e1c3038357306a39/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-52b1e1c3038357306a39.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-52b1e1c3038357306a39.geojson | all-rights-reserved
vcc-site-5376b585718a989c8dc5 | imported:semiconductor-atlas:beacon-ai-centers-heartland | Beacon AI Centers Heartland campus (Sturgeon County) | Canada | CA | 53.8403 | -113.1922 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["site"] | ["compiled_reference"] | ["project_locator"] | ["Decimal coordinates stated in the federal project description summary, which places the project just north-northeast of Highway 643 and Range Road 223 (NW and SW quarters of Section 15-56-22-W4M)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["444bf1b1-03c1-5c00-8571-522390feeb7b"] | 1 | ["9a4afe64-8789-5cee-8947-61a12f8966a8"] | ["imported:semiconductor-atlas:beacon-ai-centers-heartland"] | ["proposed"] | 2026-03-10 | 2026-03-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5376b585718a989c8dc5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5376b585718a989c8dc5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5376b585718a989c8dc5.geojson | source-terms-not-recorded
vcc-site-53d6b726e740613f2b41 | curated:raiden-infotech-turbhe-midc-data-centre-campus | Raiden Infotech Turbhe MIDC Data Centre Campus | India | IN | 19.0554 | 73.0234 | Polygon | ["campus"] | ["source_KML_project_polygon_XY_preserved"] | ["PARIVESH_CAF226849_2025_active_raiden_kml_Raiden_Plot_Boundary_WGS84_lonlat_no_transform"] | ["proponent_submitted_environmental_project_polygon"] | ["official_source"] | ["campus_locator"] | ["Exact source polygon vertices from the active CAF attachment's named plot boundary. SEIAA's EC site coordinate lies inside it and its geodesic area is within 0.13% of the EC plot area. A government-hosted proponent filing establishes a project-specific campus locator, not cadastral, surveyed or current-work-extent accuracy. The display anchor is the planar shoelace centroid of the source ring in source vertex order, verified inside it; it is not a publisher point, entrance or surveyed location."] |  | Neither the KML, the CAF nor the EC states a positional accuracy, survey method, geodetic realization or control points. Decimal count and government hosting do not establish accuracy. | ["2f076364-097b-50d9-a0fe-8b96fe3d404d","34034aa1-f108-544c-8a94-2dd5f9244826","c624b662-4424-5c24-851f-f5ec06c70a4d"] | 1 | ["118053c0-38ee-5fc1-9c4d-f4875cc3c32e"] | ["curated:raiden-infotech-turbhe-midc-data-centre-campus:ec-531703-current-build"] | ["under_construction"] | 2026-08-03 | 2026-08-03 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-53d6b726e740613f2b41/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-53d6b726e740613f2b41.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-53d6b726e740613f2b41.geojson | no-open-license-asserted
vcc-site-54113ebec20f61dd4a6e | imported:semiconductor-atlas:vantage-kul2-cyberjaya | Vantage Data Centers Cyberjaya II campus (KUL2) | Malaysia | MY | 2.9225 | 101.655 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Vantage places KUL2 next to its KUL1 campus in Cyberjaya without an address. The point is the Cyberjaya coordinate from its Wikipedia article (which also gives the district), so it marks the township rather than the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["89571c26-d4c1-5923-adbf-ee81b0b8b068"] | 1 | ["a31a1552-7be0-58e9-8097-4083d11175dd"] | ["imported:semiconductor-atlas:vantage-kul2-cyberjaya"] | ["under_construction"] | 2024-08-06 | 2024-08-06 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-54113ebec20f61dd4a6e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-54113ebec20f61dd4a6e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-54113ebec20f61dd4a6e.geojson | source-terms-not-recorded
vcc-site-549acc09ba21cef52928 | curated:goodman-hkg10-tsuen-wan-data-centre | Goodman HKG10 Tsuen Wan Data Centre | Hong Kong | HK | 22.3645 | 114.1198 | Polygon | ["campus"] | ["official_lot_boundary_ring_transformed_EPSG2326_to_WGS84"] | ["CSDI_LandsD_lot_layer_query_LotCSUID_463000472_A_native_ring_PROJ_HK1980_to_WGS84_1_round7"] | ["official_land_grant_lot_boundary"] | ["official_source"] | ["campus_locator"] | ["Every native vertex of D.D. 443 Lot 472 S.A is transformed once with the recorded PROJ operation and rounded to seven decimals. The lot is the government-recorded land of the Goodman Texaco Centre, whose conversion is HKG10; it is a land-grant lot section, not a building footprint, data-hall extent or current work extent. The government address point for Goodman Texaco Centre and Goodman's own listing point both fall inside it and are not selected. The display anchor is the planar shoelace centroid of the transformed ring in source vertex order, verified inside it."] |  | The lot layer states no positional tolerance for this boundary; the datum-operation accuracy is not a boundary accuracy. | ["a421efb9-4743-597d-8207-ce31b596dc4f","b033aa39-e393-5f37-9bcf-81840e9b7a59"] | 1 | ["726d6e35-8381-58ae-8dcd-eeb9ae23583a"] | ["curated:goodman-hkg10-tsuen-wan-data-centre:current-redevelopment"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-549acc09ba21cef52928/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-549acc09ba21cef52928.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-549acc09ba21cef52928.geojson | csdi-terms-free-reuse-with-attribution
vcc-site-54d4a697323404ecfc35 | imported:semiconductor-atlas:edgecore-mesa | EdgeCore Mesa data center campus | United States | US | 33.3442 | -111.6196 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Point from the local OpenStreetMap layer (datacenters/layers/osm/features.geojson): a building footprint tagged EdgeCore at South Everton Terrace, Mesa (OSM way 808979618). It marks one existing building, not the centroid of the expanded 84-acre campus. The cited sources name Mesa but give no street address."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3b92e884-db33-5b13-be1e-bcb97a3e4344"] | 1 | ["441174d1-4dab-5b80-bfb2-76062cf675aa"] | ["imported:semiconductor-atlas:edgecore-mesa"] | ["partially_operational"] | 2025-05-21 | 2025-05-21 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-54d4a697323404ecfc35/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-54d4a697323404ecfc35.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-54d4a697323404ecfc35.geojson | source-terms-not-recorded
vcc-site-5565cfa2824c955c2f04 | curated:bulk-n01-vennesla-campus | Bulk N01 Vennesla Campus | Norway | NO | 58.2576 | 7.8921 | Point | ["campus"] | ["source_attribute_decimal_coordinates_to_point_without_centroiding"] | ["first_party_schema_org_geocoordinates_literal_point"] | ["official_operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Campus reference point only, associated by canonical site URL and postal address. The new construction project is on this campus but is not asserted at the exact point. No parcel boundary, work footprint, surveyed entrance or quantified accuracy is claimed."] |  | Publisher supplies no positional accuracy. Decimal precision and supporting map containment do not establish survey accuracy. | ["482e608f-c5a8-5719-b1ac-96373501e140","93cbb7f5-e70d-5fff-ae18-d5c9cc25404d"] | 1 | ["2c3a5bbe-3573-5abe-98dc-8d8312b0a586"] | ["curated:bulk-n01-vennesla-campus:current-new-facility-construction"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5565cfa2824c955c2f04/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5565cfa2824c955c2f04.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5565cfa2824c955c2f04.geojson | no-open-license-asserted
vcc-site-560ea7139f27238b7ea1 | imported:semiconductor-atlas:meta-dekalb-illinois | Meta DeKalb Data Center | United States | US | 41.8894 | -88.7265 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Mean of three building outlines tagged as Meta-operated data centers in the local OpenStreetMap layer (ways 1312792611, 1312792612, 1312792613) on DeKalb's south side, consistent with the cited address on Metaverse Way off I-88. The point is a building centroid average, not a surveyed parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["0ad1d56c-aa25-535d-82b8-275d8a38b87c"] | 1 | ["d3694f4b-3497-5f87-88aa-de8e9449c754"] | ["imported:semiconductor-atlas:meta-dekalb-illinois"] | ["partially_operational"] | 2023-12-01 | 2023-12-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-560ea7139f27238b7ea1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-560ea7139f27238b7ea1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-560ea7139f27238b7ea1.geojson | source-terms-not-recorded
vcc-site-5750ea0ecd6d7c900211 | curated:digital-edge-seoul-bupyeong-campus | Digital Edge Seoul Bupyeong Campus | Korea, Republic of | KR | 37.518 | 126.7109 | Point | ["campus"] | ["cross_source_geometry"] | ["first_party_sel2_specification_point_to_cross_source_shared_sel2_sel3_campus_locator"] | ["official_source_reported_adjacent_facility_point_used_as_shared_campus_locator"] | ["official_source"] | ["campus_locator"] | ["The point is the first-party SEL2 facility coordinate and may be spatially offset from SEL3. It is a shared-campus locator only, not a SEL3 project point, campus centroid, footprint, parcel, building outline, construction extent, or boundary."] |  | The specification does not state datum, reference feature, collection method, or horizontal accuracy. | ["adac0b2c-575b-5ec5-a0d8-bed593fc3c20"] | 1 | ["d2915b77-394c-5202-8c38-cbd3277121c7"] | ["curated:digital-edge-seoul-bupyeong-campus:sel3-phase-2"] | ["under_construction"] | 2026-07-09 | 2026-07-09 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5750ea0ecd6d7c900211/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5750ea0ecd6d7c900211.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5750ea0ecd6d7c900211.geojson | all-rights-reserved
vcc-site-57a103a9de718a95ae14 | curated:stt-jakarta-data-centre-campus | STT Jakarta Data Centre Campus | Indonesia | ID | -6.374 | 107.2011 | Polygon | ["campus"] | ["cross_source_overlay"] | ["openstreetmap_exactly_named_stt_jakarta_1_facility_polygon_as_shared_campus_locator"] | ["reviewed_openstreetmap_stt_jakarta_1_building_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped polygon for STT Jakarta 1, used only as one known-building anchor for the shared campus targeted by STT Jakarta 3. It is not the Jakarta 3 location or footprint, the campus boundary, a parcel, a construction extent, or a survey-accuracy claim.","Contributor-mapped polygon for STT Jakarta 1, used only as one known-building anchor for the shared campus targeted by STT Jakarta 5. It is not the Jakarta 5 location or footprint, the campus boundary, a parcel, a construction extent, or a survey-accuracy claim.","Contributor-mapped polygon for STT Jakarta 1, used only as one known-building anchor for the shared campus targeted by STT Jakarta 6. It is not the Jakarta 6 location or footprint, the campus boundary, a parcel, a construction extent, or a survey-accuracy claim."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral or survey geometry. | ["f16b034b-60d8-5826-841a-1acaa849a930"] | 3 | ["42e50e84-873d-562d-b6d2-945ccf04b0e8","aa93c84a-17d6-5092-bf57-686f7e1ab4a4","e4e51c8d-a98e-50a4-ba16-0795f1f3f63a"] | ["curated:stt-jakarta-data-centre-campus:stt-jakarta-3","curated:stt-jakarta-data-centre-campus:stt-jakarta-5","curated:stt-jakarta-data-centre-campus:stt-jakarta-6"] | ["shell","under_construction"] | 2026-06-10 | 2026-06-10 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-57a103a9de718a95ae14/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-57a103a9de718a95ae14.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-57a103a9de718a95ae14.geojson | ODbL-1.0
vcc-site-5878345369c98c058193 | imported:semiconductor-atlas:google-cedar-rapids-iowa | Google Cedar Rapids data center campus (Big Cedar Industrial Center) | United States | US | 41.9172 | -91.7254 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["OpenStreetMap point for the Big Cedar Industrial Center in Cedar Rapids, which the site owner names as the campus location; the Google parcel within the industrial center is not pinpointed."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["b4f744ea-d41d-5a5a-9bd0-dec70b3ae320"] | 1 | ["27c38b34-579b-5542-b04b-44d6d5747bff"] | ["imported:semiconductor-atlas:google-cedar-rapids-iowa"] | ["under_construction"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5878345369c98c058193/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5878345369c98c058193.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5878345369c98c058193.geojson | source-terms-not-recorded
vcc-site-5973ad6c7ce7afc4f6b6 | curated:green-mountain-undheim-campus | Green Mountain Undheim Campus | Norway | NO | 58.6593 | 5.7941 | Polygon | ["campus"] | ["official_parcel_union"] | ["authoritative_kartverket_cadastral_parcel_union"] | ["official_cadastral_project_site_parcel_union_boundary"] | ["official_source"] | ["official_boundary"] | ["Exact deterministic union of three Kartverket official cadastral parcel polygons explicitly listed as the Green Mountain project address in the approved municipal situation plan and area schedule. It is not a survey-accuracy claim, security fence, building outline, current construction extent, or assertion that every square metre is developed."] |  | Kartverket supplies only a coarse green accuracy class and explicitly does not expose boundary-line type or detailed boundary quality. | ["12f5d89c-ebd5-501c-8f98-62e845710d8c"] | 1 | ["0a075c8d-2733-5aba-b19a-4b53e51fd8f8"] | ["curated:green-mountain-undheim-campus:current-two-building-development"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | ["first_party_contractor_drone_imagery_present_not_independently_verified"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5973ad6c7ce7afc4f6b6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5973ad6c7ce7afc4f6b6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5973ad6c7ce7afc4f6b6.geojson | CC-BY-4.0
vcc-site-5a7d73c964538b72f14d | curated:dayone-kiverio-lahti-unnamed-data-center-campus | DayOne Kiveriö Unnamed Data Center Campus | Finland | FI | 60.9908 | 25.7039 | Point | ["campus"] | ["official_cadastral_referencePoint_transformed_to_WGS84"] | ["exact_permit_parcel_address_join_then_NLS_nationalCadastralReference_filter_and_pyproj_3067_to_4326_always_xy"] | ["official_parcel_reference_point"] | ["official_source"] | ["campus_locator"] | ["Official provider-supplied reference point for the exact permit-bound cadastral parcel, used only to locate one DayOne Kiveriö campus. Not a calculated centroid, survey, entrance, active-work extent, building footprint or asserted complete campus boundary. The parcel and reference point are not reused from the rejected road, wholesaler or service-area coordinates."] |  | No selected source quantifies this reference point's positional accuracy. Transformation-operation accuracy of 1 metre and numeric precision do not establish survey accuracy. | ["55ce3154-fb59-5734-a907-8c210b649346","cdc8d295-dbe5-5ec1-98b5-2393692f2f2c","e9bb34d9-fd43-587a-b6f5-377738f2b091"] | 1 | ["fe92035e-3a00-5a85-b009-34fe9c2c545e"] | ["curated:dayone-kiverio-lahti-unnamed-data-center-campus:unnamed-construction-project"] | ["under_construction"] | 2026-08-11 | 2026-08-11 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5a7d73c964538b72f14d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5a7d73c964538b72f14d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5a7d73c964538b72f14d.geojson | CC-BY-4.0; no-open-license-asserted
vcc-site-5adc03aabe03531ee95f | curated:goodman-par01-paris-data-centre-campus | Goodman PAR01 Paris Data Centre Campus | France | FR | 48.9676 | 2.5694 | Point | ["campus"] | ["official_exact_house_number_geocode"] | ["exact_named_address_feature_to_point_without_centroiding"] | ["official_address_campus_locator"] | ["official_source"] | ["campus_locator"] | ["The exact house-number point locates the reviewed Goodman campus address, not any specific phase, building, campus boundary or observed-work extent. Multiple buildings on this campus remain one physical site."] |  | The service supplies a house-number address point without a numeric horizontal-accuracy statement. Match score is not positional uncertainty. | ["17a1d516-33f6-5108-9c04-806f94890963"] | 1 | ["be6d721d-f632-5c86-a057-78774604bc6c"] | ["curated:goodman-par01-paris-data-centre-campus:phase-1-current-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5adc03aabe03531ee95f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5adc03aabe03531ee95f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5adc03aabe03531ee95f.geojson | no-open-redistribution-license-asserted
vcc-site-5af95dd1d26b0546ea7f | imported:semiconductor-atlas:applied-digital-polaris-forge-3 | Applied Digital Polaris Forge 3 | United States | US | 47.115 | -101.2978 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid of Center from its Wikipedia coordinates (s4). The October 2026 earnings release (s3) names Center, Oliver County; no parcel or address has been found."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["bf899518-100f-5bdf-a35a-f09014cb679f"] | 1 | ["0eb54c2e-ed0f-58e9-85cc-bf616b723139"] | ["imported:semiconductor-atlas:applied-digital-polaris-forge-3"] | ["under_construction"] | 2026-10-07 | 2026-10-07 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5af95dd1d26b0546ea7f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5af95dd1d26b0546ea7f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5af95dd1d26b0546ea7f.geojson | source-terms-not-recorded
vcc-site-5b95b2458a9a5add9fad | imported:semiconductor-atlas:acs-la-puebla-de-alfinden | ACS DC La Puebla data center campus | Spain | ES | 41.634 | -0.748 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid from the La Puebla de Alfindén Wikipedia article. The regional plan describes the plot but no cited source gives coordinates for it."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["183ff3fc-f33e-5695-a1cd-dd7f80c0d4e3"] | 1 | ["f07274ee-deff-5651-b606-da909d7328af"] | ["imported:semiconductor-atlas:acs-la-puebla-de-alfinden"] | ["announced"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5b95b2458a9a5add9fad/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5b95b2458a9a5add9fad.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5b95b2458a9a5add9fad.geojson | source-terms-not-recorded
vcc-site-5b9d2c3d36d5b5f40ab6 | curated:portus-munich-data-center-campus | Portus Munich Data Center Campus | Germany | DE | 48.1585 | 11.7688 | Point | ["campus"] | ["provider_supplied_community_building_centroid_bound_to_exact_certified_constituent_site_address"] | ["preserve_Nominatim_lat_lon_for_OSM_way_571006394_and_match_MUC1_certificate_address_then_explicit_MUC1_MUC2_shared_campus"] | ["community_constituent_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["The source-supplied centroid of the address-tagged Spacenet commercial building locates the MUC1/MUC2 campus through the exact MUC1 certificate address and explicit operator same-campus statement. It is not MUC2's building, active-work footprint, campus boundary, entrance, parcel centroid, verified current building-use assertion or survey-accuracy claim. The conflicting operator structured-data point is excluded. Source digits do not establish accuracy."] |  | Neither OSM way 571006394 nor its Nominatim point gives quantitative positional accuracy. | ["1ec15cfd-6343-5e8d-bdfd-cc9b07fdf514","3e2be26d-bcc7-5313-a9d8-9886d2157402","6bc49137-7fe1-543d-aeaa-883824ff4cdb","9efb7454-992b-5f25-814d-bb8ac1b7c5a9","b205414a-1ead-5049-b1fe-13d21fe5403f"] | 1 | ["9217888a-3e78-5b75-ac86-bd32ef026084"] | ["curated:portus-munich-data-center-campus:muc2"] | ["under_construction"] | 2026-05-28 | 2026-05-28 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5b9d2c3d36d5b5f40ab6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5b9d2c3d36d5b5f40ab6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5b9d2c3d36d5b5f40ab6.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-5c6aac8d35554558a1fc | imported:semiconductor-atlas:qts-eemshaven | QTS Eemshaven data center campus | Netherlands | NL | 53.4375 | 6.8581 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["site"] | ["compiled_reference"] | ["project_locator"] | ["Point for the 'QTS Eemshaven Netherlands Data Center' building (OSM way 455499803, Huibertgatweg) from the local OpenStreetMap layer, matching the address on QTS's campus page. The layer also maps a QTS new build about 350 m to the north-west; the full 18-hectare campus boundary is not published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["404031a4-7ade-5c05-9e6c-4e2242a6d4d2"] | 1 | ["409466ac-1b48-5098-adf6-4f3a2999b5f6"] | ["imported:semiconductor-atlas:qts-eemshaven"] | ["partially_operational"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5c6aac8d35554558a1fc/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5c6aac8d35554558a1fc.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5c6aac8d35554558a1fc.geojson | source-terms-not-recorded
vcc-site-5c75a2f4b8b62cd1f40a | curated:flexential-douglasville-north-river-campus | Flexential Douglasville North River Campus | United States | US | 33.7307 | -84.6112 | Point | ["campus"] | ["source_community_representative_point"] | ["exact_OSM_way1258702591_Nominatim_lon_lat"] | ["named_community_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["Exact D2-named, address-bound community building point used only to locate the North River campus. Not a legal campus boundary, active-work extent, surveyed footprint, entrance or D1 point."] |  | No numeric source-specific accuracy for community geometry or representative-point placement. | ["16df3c45-da29-54dc-8ddd-5db6caea30ac","b5f725b6-c011-5875-9eac-4b24ef7aa0ed","b8f48947-744f-5802-8111-0e8519cafdd1","fa35b333-9224-5eaa-8c0e-2a614d99bdee"] | 1 | ["8c926b8f-0190-533b-aa7e-3223971b9e23"] | ["curated:flexential-douglasville-north-river-campus:douglasville-2-current-build"] | ["under_construction"] | 2026-08-18 | 2026-08-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5c75a2f4b8b62cd1f40a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5c75a2f4b8b62cd1f40a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5c75a2f4b8b62cd1f40a.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-5c9b661562b39e724fe6 | curated:merlin-edged-madrid-getafe-ii-campus | MERLIN Edged Madrid-Getafe II Campus | Spain | ES | 40.3114 | -3.7068 | Point | ["campus"] | ["literal_operator_specification_site_point"] | ["preserve_MAD02_specification_latitude_longitude_bound_to_Fundidores2_and_Getafe2_parent_page"] | ["operator_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact operator-published MAD02 site-coordinate point at Fundidores2. Campus locator only, not an entrance, surveyed boundary, building footprint or active-demolition extent. Distinct from Getafe1 at Fundidores40. The MAD-GETII report code match is explicit analyst identity inference."] |  | Neither selected source supplies quantitative positional accuracy or survey provenance. Decimal digits do not establish accuracy. | ["2bd9d01f-b34d-5ac0-94b8-8dd17c9543cf"] | 1 | ["aa2dc8a4-52d8-5519-b23a-2ff0313db9e3"] | ["curated:merlin-edged-madrid-getafe-ii-campus:mad02-site-preparation"] | ["site_preparation"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5c9b661562b39e724fe6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5c9b661562b39e724fe6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5c9b661562b39e724fe6.geojson | all-rights-reserved
vcc-site-5cc5c2b2cb554d5a3255 | imported:semiconductor-atlas:crusoe-lancium-childress-texas | Crusoe and Lancium Childress AI data center campus | United States | US | 34.4281 | -100.215 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City centroid of Childress from Wikipedia (s3); the announcements name the city and county but give no address for the 270-acre site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["c00fd435-d289-5c04-9091-11d567b1ae79"] | 1 | ["715ba9aa-f36a-5afb-b266-caeb7681b54e"] | ["imported:semiconductor-atlas:crusoe-lancium-childress-texas"] | ["announced"] | 2026-07-15 | 2026-07-15 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5cc5c2b2cb554d5a3255/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5cc5c2b2cb554d5a3255.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5cc5c2b2cb554d5a3255.geojson | source-terms-not-recorded
vcc-site-5da88d035bad0f411f53 | curated:telia-vilnius-data-center | Telia Vilnius Data Center | Lithuania | LT | 54.7823 | 25.1831 | Polygon | ["campus"] | ["osm_way_nodes_to_polygon"] | ["osm_named_telia_construction_area_as_site_campus_locator"] | ["community_named_construction_area_as_campus_locator"] | ["community_source"] | ["campus_locator"] | ["The community way names a Telia data centre and is tagged construction, but it is only a site locator. It is not an official parcel, campus boundary, project footprint, building footprint, or current-work extent; its opening_date tag is not lifecycle evidence."] |  | OpenStreetMap supplies no bounded numeric accuracy for this community construction-area geometry. | ["198c88a9-e654-5181-8c63-320728601fe3"] | 1 | ["1cae5b48-c630-5f16-9fe2-5d77571cafe9"] | ["curated:telia-vilnius-data-center:new-data-center-current-build"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5da88d035bad0f411f53/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5da88d035bad0f411f53.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-5da88d035bad0f411f53.geojson | ODbL-1.0
vcc-site-60428cb258a38898ef68 | imported:semiconductor-atlas:box2bit-epila | Box2Bit Epilon data center campus (Épila) | Spain | ES | 41.6 | -1.283 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from the Épila Wikipedia article. Aragón Digital says the site has two accesses from the A-2 near the bonÀrea development; no parcel boundary is published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["7e303358-ae48-520e-be8a-8ed7407889de"] | 1 | ["46abd4bf-bd8a-5525-9388-c938807fe2f0"] | ["imported:semiconductor-atlas:box2bit-epila"] | ["announced"] | 2026-06-15 | 2026-06-15 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-60428cb258a38898ef68/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-60428cb258a38898ef68.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-60428cb258a38898ef68.geojson | source-terms-not-recorded
vcc-site-60a52daa24c85edeb3a2 | curated:applied-digital-delta-forge-1-alexandria | Applied Digital Delta Forge 1 Campus | United States | US | 31.3826 | -92.6862 | Point | ["campus"] | ["representative_point_of_OSM_named_construction_enclosure"] | ["OSM_way1545345944_v2_WGS84_nodes_in_provider_order_ShAPely_representative_point"] | ["open_mapping_named_construction_enclosure_representative_point"] | ["community_source"] | ["campus_locator"] | ["A point inside the provider-mapped Applied Digital construction-fence enclosure. Not a project centroid, footprint, building, parcel or legal campus boundary; independent authoritative well/address bridge is corroborative only. Source positional accuracy is unknown."] |  | Neither mapping provider nor source record publishes source-specific survey accuracy. Map decimals, local-knowledge notes and coordinate agreement do not establish accuracy. | ["36b66e9e-70fc-5150-850b-6a65e9646e55","ea663d84-8e4a-55d8-bd1e-007e7851f8b3","edcc1730-7319-5627-8ff6-d544abf2db4c"] | 1 | ["b7744ad5-aa48-5977-a70e-3d6a588f468d"] | ["curated:applied-digital-delta-forge-1-alexandria:current-build"] | ["under_construction"] | 2026-07-27 | 2026-07-27 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-60a52daa24c85edeb3a2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-60a52daa24c85edeb3a2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-60a52daa24c85edeb3a2.geojson | ODbL-1.0
vcc-site-60b38ee835b4579aa5f2 | imported:semiconductor-atlas:meta-kansas-city | Meta Kansas City data center | United States | US | 39.1001 | -94.5781 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City point from OpenStreetMap Nominatim; Meta names Kansas City but not the site. Meta's local funding goes to Clay County, Platte County and Kansas City-area groups, but no parcel is published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["09fd54b2-c42d-5a6e-bfe0-9b30a1c87a00"] | 1 | ["3315c754-ca0d-5702-8071-44b22787215a"] | ["imported:semiconductor-atlas:meta-kansas-city"] | ["operational"] | 2025-08-20 | 2025-08-20 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-60b38ee835b4579aa5f2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-60b38ee835b4579aa5f2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-60b38ee835b4579aa5f2.geojson | source-terms-not-recorded
vcc-site-61f9e739f63e5c96092e | curated:cdc-beard-campus | CDC Beard Data Center Campus | Australia | AU | -35.3402 | 149.2092 | Polygon | ["project"] | ["direct_geometry"] | ["act_official_retired_block_polygon_as_be1_historical_project_locator"] | ["official_historical_cadastral_parcel_as_project_locator"] | ["official_source"] | ["project_locator"] | ["ACT Block 24 Section 11 polygon cross-identified to the BE1 DA plan. The source marks the block RETIRED, so the exact polygon is published only as a historical project locator; it is never a current parcel, present legal boundary, campus boundary, project footprint, building footprint, or current-work extent."] |  | The ACT feature supplies no bounded numeric horizontal-accuracy value, and its retired lifecycle makes it unsuitable as a present legal-boundary claim. | ["9677a40a-6a16-59e3-b098-3bf415f47dfd"] | 1 | ["9c34c305-5149-5961-b88f-648da82351f7"] | ["curated:cdc-beard-campus:be1-current-build"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-61f9e739f63e5c96092e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-61f9e739f63e5c96092e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-61f9e739f63e5c96092e.geojson | CC-BY-4.0
vcc-site-62511f2ff7c107b083ea | imported:semiconductor-atlas:blackstone-calatorao | QTS Calatorao data center campus | Spain | ES | 41.5222 | -1.3464 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Nominatim centroid of the municipality of Calatorao; sources place the site on industrial land beside the A-2 about 7 km from the town centre, without a parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["1503cf45-fa45-5d59-a7fc-7ce360a11a88"] | 1 | ["46434a5c-4980-5f79-ac83-000783b60566"] | ["imported:semiconductor-atlas:blackstone-calatorao"] | ["announced"] | 2025-08-27 | 2025-08-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-62511f2ff7c107b083ea/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-62511f2ff7c107b083ea.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-62511f2ff7c107b083ea.geojson | source-terms-not-recorded
vcc-site-627bed0b413c9b712d70 | imported:semiconductor-atlas:ntt-gdc-tokyo-tky12-shiroi | NTT Global Data Centers Tokyo TKY12 campus, Shiroi | Japan | JP | 35.7915 | 140.0563 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["NTT names Shiroi City, Chiba Prefecture, without an address. The point is the Shiroi city coordinate from its Wikipedia article, so it marks the city rather than the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["23498602-d954-533f-bdcc-e9bb8a865749"] | 1 | ["511bfd88-0355-5080-b5ef-5a39ec51dfd8"] | ["imported:semiconductor-atlas:ntt-gdc-tokyo-tky12-shiroi"] | ["announced"] | 2026-04-22 | 2026-04-22 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-627bed0b413c9b712d70/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-627bed0b413c9b712d70.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-627bed0b413c9b712d70.geojson | source-terms-not-recorded
vcc-site-62e42a722eab77bd5345 | imported:semiconductor-atlas:xai-colossus-2-memphis | xAI Colossus 2 (Memphis) | United States | US | 34.998 | -90.0349 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["site"] | ["compiled_reference"] | ["project_locator"] | ["Center of the OpenStreetMap building tagged 'xAI Macrohard Colossus 2' at 5420 Tulane Road, taken from this project's OpenStreetMap data center layer (no geocoder call); Cleanview gives the same address. MLGW describes the facility as on Tulane Road very near the Tennessee-Mississippi line."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["206aff59-d746-56e5-af7e-4ce594a6af30"] | 1 | ["9002afae-5b81-5c8c-a6f9-4504c91e8624"] | ["imported:semiconductor-atlas:xai-colossus-2-memphis"] | ["partially_operational"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-62e42a722eab77bd5345/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-62e42a722eab77bd5345.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-62e42a722eab77bd5345.geojson | source-terms-not-recorded
vcc-site-63cd8442296ed3e4fc36 | imported:semiconductor-atlas:bitdeer-fox-creek | Bitdeer Fox Creek energy and computing facility | Canada | CA | 54.395 | -116.8092 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from the Fox Creek Wikipedia page; Bitdeer places the site about 1.5 km from the town but gives no exact location."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["0ceb23a4-a4de-5d14-8ae4-328ee9bf3212"] | 1 | ["602d4e58-abef-54a7-b8f6-894a714e7174"] | ["imported:semiconductor-atlas:bitdeer-fox-creek"] | ["under_construction"] | 2026-08-10 | 2026-08-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-63cd8442296ed3e4fc36/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-63cd8442296ed3e4fc36.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-63cd8442296ed3e4fc36.geojson | source-terms-not-recorded
vcc-site-63d7eb757cdf71a1ae84 | imported:semiconductor-atlas:airtrunk-kurri-kurri | AirTrunk Kurri Kurri Data Centre | Australia | AU | -32.8167 | 151.4833 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name the former Kurri Kurri smelter site on Hart Road, Loxford, without coordinates; the point is the Kurri Kurri town coordinate from its Wikipedia article, so it marks the neighbouring town rather than the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["7745e0a7-3b94-55f1-b9e7-f4c7b4e8eb78"] | 1 | ["33a0110e-c5fb-58d0-8913-81aef5fdd9d3"] | ["imported:semiconductor-atlas:airtrunk-kurri-kurri"] | ["proposed"] | 2026-09-21 | 2026-09-21 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-63d7eb757cdf71a1ae84/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-63d7eb757cdf71a1ae84.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-63d7eb757cdf71a1ae84.geojson | source-terms-not-recorded
vcc-site-63daf0f8749544e0e6f4 | curated:tecra-ome-takinouecho | TECRA Ome Takinouecho | Japan | JP | 35.7876 | 139.2569 | Point | ["campus"] | ["direct_geometry"] | ["developer_embedded_explicit_dms_target"] | ["developer_selected_parent_parcel_locator"] | ["official_source"] | ["campus_locator"] | ["Developer-selected original campus point decoded from explicit DMS target; not a building-B centroid or legal boundary."] |  | No positional accuracy stated. Locator identifies the parent property; the exact subdivided data-center parcel and building outline are not established numerically. | ["e90c6601-0627-5995-8c17-9efee49ac630"] | 1 | ["510a8216-64d9-5626-992a-3ca10f40fb90"] | ["curated:tecra-ome-takinouecho:building-b"] | ["permitted"] | 2026-09-15 | 2026-09-15 | authoritative_project_record_plus_scoped_location | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-63daf0f8749544e0e6f4/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-63daf0f8749544e0e6f4.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-63daf0f8749544e0e6f4.geojson | all-rights-reserved
vcc-site-64d29806f5007969e3b9 | imported:semiconductor-atlas:xai-macrohardrr-southaven | xAI MACROHARDRR data center (Southaven) | United States | US | 34.9935 | -90.0342 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Center of the OpenStreetMap building tagged 'xAI Macrohardrr' on Stateline Road West, taken from this project's OpenStreetMap data center layer (no geocoder call), about 0.5 km south of the Colossus 2 building. This matches Cleanview's address of 2400 Stateline Road, Southaven, and WREG's description of the warehouse as just south of Colossus 2."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["dbe7d792-d348-5083-ba1b-746c73feceff"] | 1 | ["493361d4-686f-5f75-af07-7f95dcf81323"] | ["imported:semiconductor-atlas:xai-macrohardrr-southaven"] | ["operational"] | 2026-07-31 | 2026-07-31 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-64d29806f5007969e3b9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-64d29806f5007969e3b9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-64d29806f5007969e3b9.geojson | source-terms-not-recorded
vcc-site-6524649236861b8342aa | curated:bitdeer-massillon-ohio-campus | Bitdeer Massillon Ohio Campus | United States | US | 40.7804 | -81.5223 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["fa1a4303-efd0-5426-adb3-2878bca8bb28"] | 1 | ["fb943def-5b5b-5192-8bb9-599e4cf616cc"] | ["curated:bitdeer-massillon-ohio-campus:2026-fire-damaged-buildings-reconstruction"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6524649236861b8342aa/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6524649236861b8342aa.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6524649236861b8342aa.geojson | public-domain-us-government
vcc-site-6547aae0762f92e98a07 | imported:semiconductor-atlas:aws-lake-anna-technology-campus-louisa-county | AWS Lake Anna Technology Campus | United States | US | 38.0606 | -77.7894 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["The campus sits at Kentucky Springs Road (Route 652) and Haley Drive (Route 700), next to the North Anna Power Station. Geocoding was unavailable, so coordinates are the power station's location from its Wikipedia article; the campus lies beside it."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["76cf51ed-92f5-5532-a590-aca54829516f"] | 1 | ["39753efd-ec90-5e1a-a234-8551ba238bda"] | ["imported:semiconductor-atlas:aws-lake-anna-technology-campus-louisa-county"] | ["announced"] | 2026-03-16 | 2026-03-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6547aae0762f92e98a07/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6547aae0762f92e98a07.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6547aae0762f92e98a07.geojson | source-terms-not-recorded
vcc-site-6548266e7ea8549844f6 | imported:semiconductor-atlas:brookfield-strangnas | Brookfield AI center, Strängnäs | Sweden | SE | 59.367 | 17.033 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid from the Strängnäs Wikipedia article. Dagens PS places the site at Gorsingeberget on the outskirts of Strängnäs, but no cited source gives a parcel or coordinates, so the site itself is not pinpointed."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6e8e9bad-0a96-5cfb-98da-f6af9ca3e60d"] | 1 | ["6aa46e28-dd40-513b-8722-f514b6503b02"] | ["imported:semiconductor-atlas:brookfield-strangnas"] | ["announced"] | 2025-06-04 | 2025-06-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6548266e7ea8549844f6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6548266e7ea8549844f6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6548266e7ea8549844f6.geojson | source-terms-not-recorded
vcc-site-65784844ad2a20822ec7 | imported:semiconductor-atlas:google-franklin-township-indianapolis | Google Franklin Township data center proposal (Project Flo) | United States | US | 39.6803 | -86.0275 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Franklin Township coordinates from its Wikipedia page. Sources name the township but give no parcel location, so the site is not pinpointed."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["40118eda-3e71-5638-a2a0-cdcd65a28e83"] | 1 | ["892af381-b656-528b-a9db-61013937174e"] | ["imported:semiconductor-atlas:google-franklin-township-indianapolis"] | ["cancelled"] | 2025-09-22 | 2025-09-22 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-65784844ad2a20822ec7/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-65784844ad2a20822ec7.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-65784844ad2a20822ec7.geojson | source-terms-not-recorded
vcc-site-66e95eb80a122bb2ee32 | imported:semiconductor-atlas:meta-prometheus-new-albany | Meta New Albany data center campus (Prometheus) | United States | US | 40.0812 | -82.8088 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City point from OpenStreetMap Nominatim; the cited sources name New Albany but give no site address for the data center buildings."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f777e6f8-5a41-53c1-85a1-8a093d44e70b"] | 1 | ["edaa7f7d-5025-5f95-9870-3ad12478339c"] | ["imported:semiconductor-atlas:meta-prometheus-new-albany"] | ["partially_operational"] | 2026-09-16 | 2026-09-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-66e95eb80a122bb2ee32/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-66e95eb80a122bb2ee32.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-66e95eb80a122bb2ee32.geojson | source-terms-not-recorded
vcc-site-6727a9539ece2f19ad23 | curated:avaio-taurus-brandon-mississippi-campus | AVAIO Digital Taurus Data Center Campus | United States | US | 32.2593 | -90.0185 | Point | ["project"] | ["coordinates_to_point"] | ["authoritative_site_plan"] | ["first_party_campus_reference_point"] | ["official_source"] | ["reviewed_site_locator"] | ["First-party Taurus campus location point derived exactly from the published latitude and longitude; not the 329-acre boundary, a parcel, building footprint, measured centroid, or phase-one outline."] |  | official source does not state positional accuracy | ["68b10772-f3b4-5152-bffe-23d34c4f8477"] | 1 | ["37e33657-b788-57e6-98f2-b78834cdecda"] | ["curated:avaio-taurus-brandon-mississippi-campus:phase-one-current-campus-build"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["tracked_identity_bound_uncertain_with_unadjudicated_later_stricter_review_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6727a9539ece2f19ad23/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6727a9539ece2f19ad23.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6727a9539ece2f19ad23.geojson | all-rights-reserved
vcc-site-6835cf832163c1403b4e | imported:semiconductor-atlas:aws-project-rainier-new-carlisle | AWS New Carlisle data center campus (Project Rainier) | United States | US | 41.7006 | -86.4964 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources place the campus in the Indiana Enterprise Center near New Carlisle but give no parcel or address; coordinates are the New Carlisle town point from its Wikipedia article (Nominatim was unavailable)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["b24d6eb3-c5c8-574f-ae34-b54e0c7dd6b0"] | 1 | ["a5b2cd4f-b857-573e-82b8-6edc1e776eec"] | ["imported:semiconductor-atlas:aws-project-rainier-new-carlisle"] | ["partially_operational"] | 2026-07-23 | 2026-07-23 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6835cf832163c1403b4e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6835cf832163c1403b4e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6835cf832163c1403b4e.geojson | source-terms-not-recorded
vcc-site-684f1565a0f48756e238 | imported:semiconductor-atlas:core-scientific-hunt-county | Core Scientific Hunt County data center site | United States | US | 33.12 | -96.09 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Core Scientific names Hunt County only. Coordinates are the Hunt County point from its Wikipedia article, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2fce484d-a8d3-5fb3-be18-3cb4c685c302"] | 1 | ["40abc164-3033-5172-b386-52422d1513b9"] | ["imported:semiconductor-atlas:core-scientific-hunt-county"] | ["announced"] | 2026-07-28 | 2026-07-28 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-684f1565a0f48756e238/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-684f1565a0f48756e238.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-684f1565a0f48756e238.geojson | source-terms-not-recorded
vcc-site-68fa7b1f6e39bd438e45 | imported:semiconductor-atlas:cloudhq-gru-paulinia | CloudHQ GRU Campus (Paulínia) | Brazil | BR | -22.7709 | -47.1043 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Coordinates are the point published on CloudHQ's campus page; they were not checked against a parcel boundary."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["5e4b28c3-60ce-52ab-81c0-062eea76a31e"] | 1 | ["8efbf742-c042-5872-9bbe-82d576865125"] | ["imported:semiconductor-atlas:cloudhq-gru-paulinia"] | ["under_construction"] | 2026-04-08 | 2026-04-08 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-68fa7b1f6e39bd438e45/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-68fa7b1f6e39bd438e45.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-68fa7b1f6e39bd438e45.geojson | source-terms-not-recorded
vcc-site-695cedb1c24a33253685 | curated:greenergy-huuru-data-center-campus | Greenergy Hüüru Data Center Campus | Estonia | EE | 59.3861 | 24.562 | Point | ["campus"] | ["representative_point_of_exact_named_OSM_enclosure"] | ["OSM_way_1043819046_full_ordered_nodes_WGS84_Shapely_representative_point"] | ["community_named_enclosure_representative_point"] | ["community_source"] | ["campus_locator"] | ["Interior representative point of exact named community-mapped Greenergy enclosure. Not a surveyed or official boundary, building footprint, entrance, work extent or inferred office locator. The underlying enclosure's name, address, phone and website match the operator data-center page."] |  | No source quantifies positional accuracy. Seven-decimal source coordinates and extra derived decimals are not survey accuracy. | ["20f56b6a-7a02-5d6a-8594-62c37963dc46","77ce34d0-dde3-553d-906b-ca13e7c339fd","892c8445-2e50-5df3-b6a3-cb78285accd2"] | 1 | ["b4349487-1879-5b90-9064-d1b86cb49850"] | ["curated:greenergy-huuru-data-center-campus:data-hall-expansion"] | ["site_preparation"] | 2026-07-30 | 2026-07-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-695cedb1c24a33253685/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-695cedb1c24a33253685.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-695cedb1c24a33253685.geojson | ODbL-1.0; no-open-license-asserted
vcc-site-6a1efb9a8859fd17aa59 | imported:semiconductor-atlas:terawulf-chesapeake-morgantown | TeraWulf Chesapeake Data Campus (Morgantown) | United States | US | 38.3453 | -76.9711 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name the Morgantown Generating Station in Charles County without an address. Coordinates are the Morgantown community point from its Wikipedia article, which notes the plant's smokestacks; they are not the plant site itself."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["973d660a-dde9-5e62-a89b-8cfea760353c"] | 1 | ["eb75ea0d-8dba-56a1-a956-135227b3d6e6"] | ["imported:semiconductor-atlas:terawulf-chesapeake-morgantown"] | ["proposed"] | 2026-08-05 | 2026-08-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6a1efb9a8859fd17aa59/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6a1efb9a8859fd17aa59.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6a1efb9a8859fd17aa59.geojson | source-terms-not-recorded
vcc-site-6afd5a936ac72410543b | imported:semiconductor-atlas:meta-temple-texas | Meta Temple Data Center | United States | US | 31.1056 | -97.4208 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Temple city coordinates from its Wikipedia page. Sources place the site off NW H K Dodgen Loop and Industrial Boulevard but give no parcel coordinates, so the campus itself is not pinpointed."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["24883aba-24d8-587f-b4e2-c84ea6bdd083"] | 1 | ["2fc433ea-05de-5b3a-b4a1-bd9d544f8ae3"] | ["imported:semiconductor-atlas:meta-temple-texas"] | ["operational"] | 2026-07-22 | 2026-07-22 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6afd5a936ac72410543b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6afd5a936ac72410543b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6afd5a936ac72410543b.geojson | source-terms-not-recorded
vcc-site-6bd6515ae5d1dc80cf5a | imported:semiconductor-atlas:azora-tillion-villamayor-de-gallego | Tillion Aragón data center campus (Azora), Villamayor de Gállego | Spain | ES | 41.6856 | -0.77389 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid from the Villamayor de Gállego Wikipedia article. Azora places the site near Villamayor de Gállego, less than 3 km from the transmission substation, but no cited source gives coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["7db7facd-988b-5356-8a99-32564b31071e"] | 1 | ["2a273a46-2f4f-5ccb-9d10-6f2bfeb5e5f5"] | ["imported:semiconductor-atlas:azora-tillion-villamayor-de-gallego"] | ["announced"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6bd6515ae5d1dc80cf5a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6bd6515ae5d1dc80cf5a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6bd6515ae5d1dc80cf5a.geojson | source-terms-not-recorded
vcc-site-6bedc032f2f6fb914715 | curated:cipher-digital-black-pearl-wink-texas-data-center-campus | Cipher Digital Black Pearl Wink Data Center Campus | United States | US | 31.6913 | -103.067 | Point | ["campus"] | ["official_9_1_1_address_point_for_exact_primary_site_address"] | ["TxGIO_StratMap_address_point_query_by_full_addr_and_county_outSR4326_round7"] | ["official_address_point_for_campus_site_address"] | ["official_source"] | ["campus_locator"] | ["The official statewide 9-1-1 address point for the exact site address named by primary identity sources. It locates the campus address, not a data hall, phase, parcel boundary, footprint or current work extent. Source value rounded to seven decimals."] |  | TxGIO states that each authoritative 9-1-1 source applies its own point-placement guideline and policy (rooftop, parcel centroid or street centreline are not fixed) and publishes no positional accuracy for individual points. | ["322acf52-c4b4-5ba6-9083-b2bb02a7ab87","eb0bee76-1393-5d0c-ab38-31f685139b3d"] | 2 | ["ade90a9a-b55b-503e-a8b9-d2f8340a81d6","f595ca9f-e584-5dcb-bf76-38b346f6e4aa"] | ["curated:cipher-digital-black-pearl-wink-texas-data-center-campus:aws-phase-2-site-preparation","imported:semiconductor-atlas:cipher-black-pearl"] | ["partially_operational","under_construction"] | 2026-08-04 | 2026-08-04 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6bedc032f2f6fb914715/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6bedc032f2f6fb914715.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6bedc032f2f6fb914715.geojson | public-use-as-is
vcc-site-6bf2ad82353d1ed7d3c9 | imported:semiconductor-atlas:softbank-sesterce-bosquel | SoftBank-Sesterce Bosquel AI data center | France | FR | 49.7391 | 2.2179 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Nominatim centroid of the commune of Bosquel (Somme); sources name the commune only."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f59be53e-26ee-5e1c-b1ad-7b5ff0f833ed"] | 1 | ["53a18106-0c3f-5249-8717-107230729abc"] | ["imported:semiconductor-atlas:softbank-sesterce-bosquel"] | ["announced"] | 2026-06-01 | 2026-06-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6bf2ad82353d1ed7d3c9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6bf2ad82353d1ed7d3c9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6bf2ad82353d1ed7d3c9.geojson | source-terms-not-recorded
vcc-site-6c4336501258c6139275 | curated:nextdc-m2-melbourne | NEXTDC M2 Melbourne Data Center Campus | Australia | AU | -37.708 | 144.8757 | Point | ["campus"] | ["operator_published_destination_coordinate"] | ["copy_M2_facility_href_destination_not_viewport"] | ["operator_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The M2 facility's own operator-published directions URL supplies the destination at 75 Sharps Road. No Google page or third-party search result is selected. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate."] |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | ["69f903c5-00c1-557f-a61e-d7eaadb9ad04"] | 1 | ["ad5f9b2b-80bf-5580-92f2-0f53473c882d"] | ["curated:nextdc-m2-melbourne:incremental-in-progress-fit-out"] | ["mep_electrical"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6c4336501258c6139275/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6c4336501258c6139275.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6c4336501258c6139275.geojson | all-rights-reserved
vcc-site-6d5b0030886927a4cf46 | curated:envia-tel-datacenter-leipzig-campus | envia TEL Datacenter Campus Leipzig | Germany | DE | 51.3727 | 12.4728 | Point | ["campus"] | ["Nominatim centroid of exact address named OSM building; axis reorder only"] | ["community_named_exact_address_constituent_building_centroid"] | ["constituent_building_point_for_shared_campus"] | ["community_source"] | ["campus_locator"] | ["Literal provider precision retained; constituent building centroid only. Not a fourth-section footprint, official survey, cadastral parcel, whole-campus boundary, headquarters, road or entrance."] |  | Neither OSM object nor Nominatim response supplies positional accuracy. Decimal places and centroid semantics are not accuracy. | ["14226399-1fd3-570b-a457-48adc247ccf4","6377c3c3-0049-5835-abf5-55d51bd7522d","ad832a5d-9162-5c63-a11b-673cbc572545","b66a9bf2-5455-55a9-a30d-3a4ef573bd11","f1de53ed-290d-52d7-aa8f-4aab6e3cbbec"] | 1 | ["898b0895-99d6-545b-8053-79813ae63ffa"] | ["curated:envia-tel-datacenter-leipzig-campus:leipzig-2-fourth-section-current-build"] | ["under_construction"] | 2026-05-27 | 2026-05-27 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6d5b0030886927a4cf46/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6d5b0030886927a4cf46.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6d5b0030886927a4cf46.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-6d5fe2fc2166ad27899f | imported:semiconductor-atlas:powerhouse-95-spotsylvania | PowerHouse 95 data center campus | United States | US | 38.18 | -77.65 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Sources say only that the campus is in Spotsylvania along the I-95 corridor near existing electrical infrastructure. The point is the Spotsylvania County coordinate from its Wikipedia article, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d440612d-86b8-51ec-96fc-7b670f03f886"] | 1 | ["48d82a4f-46ea-5641-a650-b6e147b30ae6"] | ["imported:semiconductor-atlas:powerhouse-95-spotsylvania"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6d5fe2fc2166ad27899f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6d5fe2fc2166ad27899f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6d5fe2fc2166ad27899f.geojson | source-terms-not-recorded
vcc-site-6e1076932d6836b39df9 | imported:semiconductor-atlas:tract-morris-technology-park | Morris Technology Park | United States | US | 41.38 | -88.4244 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Morris. Bisnow places the parcel off Interstate 80 in Morris but gives no address."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["448aa44d-8acb-5a23-ace6-59eb47fbba83"] | 1 | ["8ac449d0-47a8-5735-a32a-d4eb2a6def53"] | ["imported:semiconductor-atlas:tract-morris-technology-park"] | ["announced"] | 2026-01-27 | 2026-01-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6e1076932d6836b39df9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6e1076932d6836b39df9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6e1076932d6836b39df9.geojson | source-terms-not-recorded
vcc-site-6ec62bca94b5d5e1db03 | curated:cdc-brooklyn-melbourne-campus | CDC Brooklyn Melbourne Campus | Australia | AU | -37.8174 | 144.8438 | Point | ["campus"] | ["coordinates_to_point"] | ["official_regulatory_site_coordinate"] | ["addressed_regulatory_site_point"] | ["official_source"] | ["campus_locator"] | ["Exact ACMA-published six-decimal coordinate for a CDC-linked radio site at the named campus address; not a parcel, building, work area, or facility-allocation boundary."] |  | ACMA publishes no bounded positional accuracy for this radio-site coordinate. | ["69b44d85-4d17-5832-aaf7-8c2ba2bcf14f"] | 1 | ["83efe2e8-3b4b-5260-b4ca-d1dbc653b792"] | ["curated:cdc-brooklyn-melbourne-campus:remaining-facilities-current-build"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6ec62bca94b5d5e1db03/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6ec62bca94b5d5e1db03.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6ec62bca94b5d5e1db03.geojson | ACMA-radiocomms-licence-data-terms
vcc-site-6fbf2c20aeb106991c61 | imported:semiconductor-atlas:edgeconnex-kyotanabe-greater-osaka | EdgeConneX Greater Osaka campus (Kagoya Tatara Campus, Kyotanabe) | Japan | JP | 34.8144 | 135.7678 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["The releases name the Kagoya Tatara Campus and place it in Kyotanabe City through a quote from the city's mayor; no address is given. The point and the prefecture come from the Kyotanabe Wikipedia article, so the point marks the city rather than the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["604f97e6-9edd-5e9c-b350-035f4b500542"] | 1 | ["ffbda424-5468-5619-97e8-3a32b0522e79"] | ["imported:semiconductor-atlas:edgeconnex-kyotanabe-greater-osaka"] | ["under_construction"] | 2026-03-18 | 2026-03-18 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6fbf2c20aeb106991c61/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6fbf2c20aeb106991c61.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6fbf2c20aeb106991c61.geojson | source-terms-not-recorded
vcc-site-6fc591eaf0edc175a75c | imported:semiconductor-atlas:softbank-tomakomai | SoftBank Hokkaido Tomakomai AI Data Center | Japan | JP | 42.6341 | 141.6055 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Tomakomai City only; coordinates are the OpenStreetMap Nominatim centroid of the city boundary."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d00b5a09-e567-5c82-9aaf-df71b5f87d92"] | 1 | ["c4cf35bd-5452-551f-8b1c-bb88d2f2b35b"] | ["imported:semiconductor-atlas:softbank-tomakomai"] | ["under_construction"] | 2026-08-04 | 2026-08-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6fc591eaf0edc175a75c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6fc591eaf0edc175a75c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-6fc591eaf0edc175a75c.geojson | source-terms-not-recorded
vcc-site-7067da1bf27989e69807 | curated:iron-mountain-nje-1-new-jersey-data-center | Iron Mountain NJE-1 New Jersey Data Center | United States | US | 40.5299 | -74.3279 | Point | ["campus"] | ["official_address_range_geocode"] | ["census_single_exact_address_match_then_explicit_nad83_to_wgs84"] | ["official_address_range_interpolation_exact_campus_address_locator"] | ["official_source"] | ["campus_locator"] | ["Official Census street-address interpolation for the exact NJE-1 address at 3003 Woodbridge Avenue. The operator identifies NJE-1 at that address and Edison government records corroborate the property and parcel identity. This locates the existing campus containing the selected expansion; it is not the new expansion hall, footprint, parcel boundary or surveyed facility center."] |  | No source-specific numerical horizontal-accuracy guarantee is published for the selected street-range interpolation. | ["44fdf373-1340-5203-82e9-b78513f8f5d5","69ecb4cd-be02-55fa-b978-732f307eeb00"] | 1 | ["0bf81b53-0bf9-551d-807b-16392ea21962"] | ["curated:iron-mountain-nje-1-new-jersey-data-center:expansion-4mw"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7067da1bf27989e69807/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7067da1bf27989e69807.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7067da1bf27989e69807.geojson | no-open-redistribution-license-asserted
vcc-site-72215030ee46f7977c35 | curated:cyrusone-yorkville-technology-campus | CyrusOne Yorkville Technology Campus | United States | US | 41.6772 | -88.4822 | Point | ["campus"] | ["official_parcel_centroid_to_point"] | ["official_parcel_centroid"] | ["largest_identified_owner_parcel_centroid"] | ["official_source"] | ["campus_locator"] | ["Exact county-returned centroid of one 72.52475709-acre C1 YORKVILLE LLC parcel; not the full campus, a building, or active work area."] |  | The county service provides a derived parcel centroid but no survey-grade horizontal accuracy. | ["b5ab4fb4-fff8-580c-8974-9c89f54ed8ec"] | 1 | ["eaea9fff-9fd3-506f-a490-320f64d86dc3"] | ["curated:cyrusone-yorkville-technology-campus:current-site-work"] | ["site_preparation"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-72215030ee46f7977c35/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-72215030ee46f7977c35.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-72215030ee46f7977c35.geojson | county-public-gis-fact-extraction-only
vcc-site-72339650a9d5c93e8286 | imported:semiconductor-atlas:elea-rio-ai-city | Rio AI City (Elea Data Centers) | Brazil | BR | -22.977 | -43.394 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Sources place the project in Rio de Janeiro's Olympic Park area without a parcel; coordinates are the Barra Olympic Park reference point (Wikipedia). Whether the existing RJO1 building sits inside the park was not stated."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["83146c8f-827a-54a2-8269-215420d9378e"] | 1 | ["51f3ec57-401e-5060-9d04-c2dfdfee6b1f"] | ["imported:semiconductor-atlas:elea-rio-ai-city"] | ["partially_operational"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-72339650a9d5c93e8286/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-72339650a9d5c93e8286.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-72339650a9d5c93e8286.geojson | source-terms-not-recorded
vcc-site-725184148f2278feb335 | curated:pure-dc-brent-cross-lon01-campus | Pure DC Brent Cross LON01 Campus | United Kingdom | GB | 51.5706 | -0.23719 | Polygon | ["building"] | ["cross_source_geometry"] | ["openstreetmap_lon01_named_building_polygon_as_parent_campus_locator"] | ["reviewed_openstreetmap_pure_dc_lon01_named_building_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped polygon for one known LON01 building, used only to locate the parent Brent Cross campus. It is not identified as either B2 work zone, the B2 composite-build footprint, a complete campus boundary, an official parcel or planning boundary, or a current construction-progress extent."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | ["ee256a2f-4e9b-5224-a6ce-e4f95c4a11ed"] | 1 | ["0cdff49d-f05c-5993-acd1-d1259fd80165"] | ["curated:pure-dc-brent-cross-lon01-campus:b2-composite-build"] | ["under_construction"] | 2026-05-28 | 2026-05-28 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-725184148f2278feb335/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-725184148f2278feb335.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-725184148f2278feb335.geojson | ODbL-1.0
vcc-site-74a60737ad3cfc9e9a75 | imported:semiconductor-atlas:khazna-dammam | Khazna Data Centers Dammam campus | Saudi Arabia | SA | 26.433 | 50.1 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City coordinates from the Dammam Wikipedia page; Khazna has not published the plot location."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["65049f53-47cc-5d17-ba8b-143900d276d7"] | 1 | ["41ec9844-286f-5128-a8bf-54e1e328301f"] | ["imported:semiconductor-atlas:khazna-dammam"] | ["announced"] | 2025-12-09 | 2025-12-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-74a60737ad3cfc9e9a75/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-74a60737ad3cfc9e9a75.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-74a60737ad3cfc9e9a75.geojson | source-terms-not-recorded
vcc-site-74bd4d30e1805ec36812 | curated:ascenty-sumare-campus | Ascenty Sumaré Campus | Brazil | BR | -22.8123 | -47.2129 | Point | ["campus"] | ["copy_named_SUM01_literal_latitude_longitude_as_parent_campus_locator"] | ["first_party_site_coordinate_with_verified_WGS84_provider_contract"] | ["named_constituent_facility_point"] | ["official_source"] | ["campus_locator"] | ["Publisher point for SUM01 is a broad Sumaré campus locator only. It is not the SUM03 building, entrance, parcel, campus boundary, surveyed centroid or active-work extent."] |  | Publisher gives no numeric horizontal accuracy; decimal digits do not establish accuracy. | ["5317bdcc-4654-5b52-a678-347ffedc551d","803fc201-cc51-5950-bec1-84f1b0cc79d4","8df93779-2a17-51ba-97ba-28cf726b66b8","90f962ca-3e44-5141-beaa-f6485628fc91","b195ad58-b064-50da-a978-6015aee83c72","c83755d8-f1a4-5040-a3c7-485ea057fc53"] | 1 | ["5b52a118-2f46-5f43-b308-a3237e99e065"] | ["curated:ascenty-sumare-campus:sumare-3"] | ["under_construction"] | 2026-05-28 | 2026-05-28 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-74bd4d30e1805ec36812/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-74bd4d30e1805ec36812.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-74bd4d30e1805ec36812.geojson | CC-BY-4.0; all-rights-reserved
vcc-site-755524c9fd6de6eed9f2 | imported:semiconductor-atlas:bitdeer-weathersfield-ohio | Bitdeer Weathersfield (Niles) development site | United States | US | 41.1783 | -80.7578 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Bitdeer names the site Niles and later Weathersfield, Ohio, without an address. The point is the Weathersfield Township coordinate from its Wikipedia article, which lists much of the city of Niles among the township's populated places; it is not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["854437f1-bd50-583c-9b5a-aeb46572a5cf"] | 1 | ["b02620fe-58af-53a3-91fc-855e2454512c"] | ["imported:semiconductor-atlas:bitdeer-weathersfield-ohio"] | ["announced"] | 2026-08-10 | 2026-08-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-755524c9fd6de6eed9f2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-755524c9fd6de6eed9f2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-755524c9fd6de6eed9f2.geojson | source-terms-not-recorded
vcc-site-75fed87a1b38b8cd7280 | curated:maincubes-mainhub-nauen-campus | maincubes mainHub Nauen Campus | Germany | DE | 52.5935 | 12.893 | Point | ["project"] | ["coordinates_to_point"] | ["authoritative_site_plan"] | ["first_party_shared_campus_reference_point"] | ["official_source"] | ["reviewed_site_locator"] | ["First-party BER02/mainHub Nauen location point derived exactly from the published latitude and longitude; not a parcel, building outline, footprint, or measured centroid."] |  | official source does not state positional accuracy | ["1e5b63b2-b334-52e0-94a1-f78d02457964"] | 1 | ["3941c42e-216d-52fa-b0d8-d7555b441a1a"] | ["curated:maincubes-mainhub-nauen-campus:ber02"] | ["under_construction"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["tracked_identity_bound_reject_with_unadjudicated_later_conflict_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-75fed87a1b38b8cd7280/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-75fed87a1b38b8cd7280.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-75fed87a1b38b8cd7280.geojson | all-rights-reserved
vcc-site-76ff9a11d8e0e21c29cb | curated:green-mountain-fra-mainz-campus | Green Mountain FRA-Mainz Campus | Germany | DE | 50.0276 | 8.2406 | Point | ["project"] | ["coordinates_to_point"] | ["energieatlas_named_green_rocks_project_point"] | ["official_government_project_reference_point"] | ["official_source"] | ["project_locator"] | ["Official Energieatlas point for the named Green Rocks project in Mainz, whose card identifies Green Mountain, KMW, Gaßnerallee, and the three-building facility. It is a project locator, not a parcel, campus, building, entrance, survey point, centroid, or current-work boundary."] |  | Energieatlas supplies coordinate digits but no collection method, reference-feature definition, or bounded numeric horizontal-accuracy value. | ["29bdb34b-54f1-5e00-b28e-877efbf2e828"] | 1 | ["4eeb97fa-8e1d-53de-ae86-eebc40e97d6f"] | ["curated:green-mountain-fra-mainz-campus:current-three-building-development"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-76ff9a11d8e0e21c29cb/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-76ff9a11d8e0e21c29cb.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-76ff9a11d8e0e21c29cb.geojson | all-rights-reserved-fact-extraction-only
vcc-site-770ec5f91c36fa41886d | curated:csc-lumi-ai-data-center-renforsin-ranta-kajaani | CSC LUMI-AI Data Center | Finland | FI | 64.232 | 27.6915 | Point | ["campus"] | ["provider_supplied_named_CSC_LUMI_building_centroid_bound_to_official_same_hall_expansion"] | ["copy_Nominatim_lat_lon_for_OSM_way_705545655_then_bind_CSC_LUMI_names_and_Tehdaskatu_15_to_primary_same_hall_campus_identity"] | ["community_constituent_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["Exact provider-returned centroid of the community industrial building named CSC, alt_name LUMI, at Tehdaskatu 15. Primary CSC sources identify its Kajaani data center at that address and the LUMI-AI expansion in the same hall as LUMI/Roihu. This locates one shared physical campus, not the expansion's exact room, parcel, whole-campus boundary, surveyed entrance or active-work extent. No imagery verification is claimed."] |  | No selected source quantifies positional accuracy. Decimal digit count does not establish accuracy. | ["1293fc76-3f6d-560f-9cb3-7ea2a0751450","38ba8adb-7b5d-5a1f-9482-a94654fc485d","3a5551fb-11b1-5245-b4b0-6611bca52342","7cb57482-543c-518d-847c-383a1062dfda","83564720-35f4-5704-a990-e42a65961f0e"] | 1 | ["5bfb4ad8-a8f4-5937-9242-a96f9292c385"] | ["curated:csc-lumi-ai-data-center-renforsin-ranta-kajaani:current-build"] | ["under_construction"] | 2026-08-20 | 2026-08-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-770ec5f91c36fa41886d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-770ec5f91c36fa41886d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-770ec5f91c36fa41886d.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-779f30ba676706e8e5db | curated:core-scientific-pecos-cottonwood-campus | Core Scientific Pecos Cottonwood Campus | United States | US | 31.5342 | -103.8027 | Point | ["campus"] | ["source_community_representative_point"] | ["exact_OSM_relation20669718_Nominatim_representative_lon_lat"] | ["community_constituent_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["Exact named 1851 FM 2119 Core Scientific Pecos constituent locator within the issuer-grouped Cottonwood 1 and 2 campus. Not the new data hall, active construction extent, entrance, surveyed boundary, or an assertion that nearby COT2 is physically contiguous. One conservative campus group, no additional site for either constituent. The existing OSM facility identity is preserved."] |  | Community feature and representative point have no documented site-specific numeric accuracy. | ["0f6a6cde-f89b-55f8-9fec-f74f96737f10","c2435d5e-e945-52cf-9831-eb7bcbda882c","e62d45bd-e00d-5243-b288-16c098bb2b10","e95c68d5-dcea-51c7-a21a-11eaa2bf9140","ed20cf81-ee66-5390-b44b-6faeca5eb769"] | 2 | ["709cd37b-7f3a-5313-b3e2-a18ddc0885ec","8ce04eb2-b1ed-5375-a685-122f79fc2ee6"] | ["curated:core-scientific-pecos-cottonwood-campus:initial-hdc-current-build","imported:semiconductor-atlas:core-scientific-pecos"] | ["announced","under_construction"] | 2026-06-02 | 2026-07-28 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-779f30ba676706e8e5db/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-779f30ba676706e8e5db.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-779f30ba676706e8e5db.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-77fa0d95d9c7ed1b2168 | curated:trg-spring-cypress-campus | TRG Spring Cypress Campus | United States | US | 30.066 | -95.4557 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The brochure places HOU1 and HOU2 on one two-data-center campus. The address point locates that campus and is not an HOU2 building footprint."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["6600dddb-f2d8-5458-8e71-b43f77cc5e01"] | 1 | ["ba5ddf33-10ec-5fb8-b880-98a04df096b8"] | ["curated:trg-spring-cypress-campus:hou2"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-77fa0d95d9c7ed1b2168/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-77fa0d95d9c7ed1b2168.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-77fa0d95d9c7ed1b2168.geojson | public-domain-us-government
vcc-site-780d34f93b2e30c4ae73 | curated:xtx-markets-kajaani-data-center-campus | XTX Markets Kajaani Data Center Campus | Finland | FI | 64.2372 | 27.6554 | Polygon | ["campus"] | ["official_coordinate_transform"] | ["nls_official_cadastral_parcel_polygon_as_campus_locator"] | ["official_cadastral_parcel_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Exact reviewed NLS cadastral polygon for parcel 205-7-4-1, used only to locate the XTX Markets Kajaani parent campus and inherited by the Second Data Center project through the explicit project-to-campus link. It is not the DC2 location or footprint, either data-center building footprint, the current work extent, a verified complete campus boundary, a security boundary, or proof every square metre is developed."] |  | The cadastral feature is authoritative parcel geometry but the reviewed response publishes no numeric survey-accuracy or horizontal-uncertainty value for this feature; transformed digits do not add accuracy. | ["23365ee9-f538-56fe-acec-e41f43182ded"] | 1 | ["fe6f26cf-4be9-51a3-857e-fca7ee21726b"] | ["curated:xtx-markets-kajaani-data-center-campus:second-data-center"] | ["under_construction"] | 2026-06-25 | 2026-06-25 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-780d34f93b2e30c4ae73/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-780d34f93b2e30c4ae73.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-780d34f93b2e30c4ae73.geojson | CC-BY-4.0
vcc-site-78289e1b65e2284a986f | curated:nextdc-m4-melbourne | NEXTDC M4 Melbourne Data Center Campus | Australia | AU | -37.8287 | 144.9115 | Point | ["campus"] | ["exact_official_primary_virtual_address_point"] | ["preserve_Vicmap_PFI214016983_point_response_in_EPSG4326_bound_to_NEXTDC_M4_127_Todd_Road"] | ["official_virtual_address_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Primary virtual address point for 127 Todd Road; source location descriptor PART is retained. The exact operator address and CP172440L government site record bind the campus. Not a surveyed entrance, full campus boundary, built footprint or June30 work extent; not the near-coincident non-primary entrance point."] |  | No feature-specific quantitative positional-accuracy estimate is supplied by the selected point source. Coordinate digits are retained without asserting survey accuracy. | ["21e4e740-9c6e-5115-996c-3aa378a2f590","2ebacc55-15b9-5a33-b96e-3c51676e39c8","a53097c1-06e3-589b-9748-1e9a83879720","a5f4e2d6-95ca-5cc3-be57-aeb381fdf2ab","d023a91d-b0e7-5468-a30f-b28d6db4714c"] | 2 | ["869dffc7-22ea-5f40-8810-13d87c696908","8715738f-39ac-5058-a01a-b62758b49831"] | ["curated:nextdc-m4-melbourne:initial-early-works","imported:semiconductor-atlas:nextdc-m4-port-melbourne"] | ["announced","site_preparation"] | 2026-01-19 | 2026-06-30 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-78289e1b65e2284a986f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-78289e1b65e2284a986f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-78289e1b65e2284a986f.geojson | CC-BY-4.0
vcc-site-782c0112e90a5282be53 | curated:coresite-de3-race-street-campus | CoreSite DE3 Race Street Campus | United States | US | 39.7861 | -104.9628 | Polygon | ["project"] | ["direct_geometry"] | ["authoritative_tax_parcel"] | ["tax_parcel_boundary"] | ["official_source"] | ["official_boundary"] | ["Exact Denver tax-parcel polygon whose returned owner is CoreSite Real Estate DE3 LLC; not a building footprint."] |  | official source does not state positional accuracy | ["58cd4851-129d-59c4-9cb0-4f24070a71a9"] | 1 | ["65e8849e-2ebe-5d58-be63-299cbbcf8d23"] | ["curated:coresite-de3-race-street-campus:de3"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | ["tracked_blind_clear_locally_unsealed_identity_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-782c0112e90a5282be53/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-782c0112e90a5282be53.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-782c0112e90a5282be53.geojson | CC-BY-3.0
vcc-site-78bd59a55f0376662286 | imported:semiconductor-atlas:stt-gdc-fairview-quezon-city | STT Fairview data center campus | Philippines | PH | 14.65 | 121.0475 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["STT's factsheet gives the address as Regalado Avenue, Fairview, Quezon City. The point is the Quezon City coordinate from its Wikipedia article, so it marks the city centre, several kilometres south of the Fairview area; precision is therefore given at city level."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["9adc2e4b-72ef-566e-bf9f-4008c8f42a92"] | 1 | ["b75df57e-ef16-50f9-b1d8-ae13bae596a5"] | ["imported:semiconductor-atlas:stt-gdc-fairview-quezon-city"] | ["under_construction"] | 2026-04-20 | 2026-04-20 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-78bd59a55f0376662286/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-78bd59a55f0376662286.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-78bd59a55f0376662286.geojson | source-terms-not-recorded
vcc-site-78e17687e90595467a13 | curated:colt-frankfurt3-sossenheim-campus | Colt Frankfurt 3 Sossenheim Campus | Germany | DE | 50.1245 | 8.5876 | Polygon | ["building"] | ["cross_source_geometry"] | ["openstreetmap_exactly_named_colt_fra3_building_polygon_as_current_facility_build_locator"] | ["reviewed_openstreetmap_colt_fra3_named_building_polygon"] | ["community_mapped"] | ["project_locator"] | ["Contributor-mapped polygon for the named Colt FRA3 building, used only as a facility/project locator. It is not an official site or parcel boundary, not the complete campus, and not evidence that the entire mapped building equals the current first-phase build or present construction extent."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | ["d0865f65-7e1e-59ab-989c-2d49ec5ce196"] | 1 | ["7352e9b5-ecec-5497-8c62-3e6a8c7bd012"] | ["curated:colt-frankfurt3-sossenheim-campus:frankfurt3-current-facility-build"] | ["under_construction"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-78e17687e90595467a13/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-78e17687e90595467a13.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-78e17687e90595467a13.geojson | ODbL-1.0
vcc-site-7a48afbd332e0560f535 | imported:semiconductor-atlas:ctrls-chandanvelly-hyderabad | CtrlS Chandanvelly AI-ready data center park | India | IN | 17.2327 | 78.1713 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name the Chandanvelly Industrial Park near Hyderabad without an address; the point is the Chandanvelly village coordinate from its Wikipedia article, so it marks the village rather than the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["bf0ce2e0-c7f1-565f-a5ab-18f5a70ff896"] | 1 | ["0d416a87-60ba-5c1d-a419-a94965619724"] | ["imported:semiconductor-atlas:ctrls-chandanvelly-hyderabad"] | ["announced"] | 2025-01-23 | 2025-01-23 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7a48afbd332e0560f535/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7a48afbd332e0560f535.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7a48afbd332e0560f535.geojson | source-terms-not-recorded
vcc-site-7a7046b12f3789bb93a5 | imported:semiconductor-atlas:synapse-olds | Synapse Data Center (Olds) | Canada | CA | 51.7928 | -114.1067 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from the Olds Wikipedia page. The developer places the site in the town's industrial area at the northeast corner of Highways 2A and 27 (SW and NW quarters of Section 4-33-1-W5M)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3bb1bb6d-c4d0-57ac-9eb0-dc81963e6429"] | 1 | ["4a0d8f6f-b848-5650-a479-4f0caee97fa1"] | ["imported:semiconductor-atlas:synapse-olds"] | ["proposed"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7a7046b12f3789bb93a5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7a7046b12f3789bb93a5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7a7046b12f3789bb93a5.geojson | source-terms-not-recorded
vcc-site-7b36022a26fba8770036 | imported:semiconductor-atlas:balico-pittsylvania-county | Balico gas-powered data center campus, Pittsylvania County | United States | US | 36.8256 | -79.3975 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of the town of Chatham (s5). Sources place the land near Chatham (s3, s4) in the county's Banister district (s1) but name no roads; the parcels were not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2b620414-745c-5b05-9ddb-a65fa6fe757a"] | 1 | ["908ba9ce-1e84-567b-926f-8d47d4d2a7ed"] | ["imported:semiconductor-atlas:balico-pittsylvania-county"] | ["cancelled"] | 2025-04-16 | 2025-04-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7b36022a26fba8770036/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7b36022a26fba8770036.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7b36022a26fba8770036.geojson | source-terms-not-recorded
vcc-site-7b3778f58b65d557b1f9 | imported:semiconductor-atlas:google-meitner-energy-center-texas | Google Meitner Energy Center data center (Gray and Roberts counties) | United States | US | 35.5363 | -100.9602 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid of Pampa via Nominatim. The project spans Gray and Roberts counties, and Google's location list includes a Pampa, Texas site in development that matches it; no site address or parcel has been published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["0fa34a95-4233-5fb6-af85-c271b4c81be0"] | 1 | ["db205e2d-f250-5c0b-861e-1c243f7be933"] | ["imported:semiconductor-atlas:google-meitner-energy-center-texas"] | ["under_construction"] | 2026-06-04 | 2026-06-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7b3778f58b65d557b1f9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7b3778f58b65d557b1f9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7b3778f58b65d557b1f9.geojson | source-terms-not-recorded
vcc-site-7b9b287883c887b86116 | imported:semiconductor-atlas:atnorth-haugaland-nor01 | atNorth NOR01 Haugaland mega site | Norway | NO | 59.3154 | 5.4252 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["atNorth names Haugaland Business Park in Tysvær; the business park was geocoded with OpenStreetMap, but the specific plot within it was not identified."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a66d9703-a215-5f0f-affb-7f70b07b491d"] | 1 | ["ce6cee07-15ea-56c9-83d5-c0cdb18aa695"] | ["imported:semiconductor-atlas:atnorth-haugaland-nor01"] | ["announced"] | 2026-06-09 | 2026-06-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7b9b287883c887b86116/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7b9b287883c887b86116.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7b9b287883c887b86116.geojson | source-terms-not-recorded
vcc-site-7cb4c635a0469cf8e507 | imported:semiconductor-atlas:tract-buckeye | Tract Buckeye data center park | United States | US | 33.3706 | -112.5908 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of Buckeye (s5). Local reporting places the park in southwest Buckeye, south of Interstate 10 on Johnson Road near Buckeye Municipal Airport; the parcel was not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["b46f3107-539f-500d-9ea3-bcc373b6e760"] | 1 | ["3f13d78d-ac2f-533b-8e04-01009bd9d17b"] | ["imported:semiconductor-atlas:tract-buckeye"] | ["announced"] | 2026-06-15 | 2026-06-15 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7cb4c635a0469cf8e507/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7cb4c635a0469cf8e507.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7cb4c635a0469cf8e507.geojson | source-terms-not-recorded
vcc-site-7cc1c64f44550b086450 | curated:edged-council-bluffs-data-center-campus | Edged Council Bluffs Data Center Campus | United States | US | 41.275 | -95.7912 | Point | ["project"] | ["official_address_point"] | ["official_address_point"] | ["project_address_point"] | ["official_source"] | ["project_locator"] | ["Exact county address point for the permit-linked 2313 College Road site; not a parcel, building footprint, or current work boundary."] |  | The county address-point layer states no bounded capture accuracy. | ["0fff6073-2536-58db-b16e-b82141605ef5"] | 1 | ["85cb6e56-ec73-5685-82e7-15e4ef96106b"] | ["curated:edged-council-bluffs-data-center-campus:first-data-center"] | ["shell"] | 2026-07-17 | 2026-07-17 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7cc1c64f44550b086450/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7cc1c64f44550b086450.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7cc1c64f44550b086450.geojson | county-open-data-no-explicit-license
vcc-site-7ceb4cfa4ba358ea4547 | imported:semiconductor-atlas:coreweave-kenilworth-new-jersey | CoreWeave Kenilworth NEST 11 AI data center | United States | US | 40.6781 | -74.2881 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Borough centroid from the Wikipedia infobox for Kenilworth (s6), which also gives Union County. Sources place the building at 2000 Galloping Hill Road on the roughly 108-acre NEST campus, but no geocoder was used, so the point is the borough centroid rather than the building."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["e5ef1215-681f-5d68-9a47-e7992ada26ad"] | 1 | ["35995588-0599-5f9b-bc3d-29f9f67ea81b"] | ["imported:semiconductor-atlas:coreweave-kenilworth-new-jersey"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7ceb4cfa4ba358ea4547/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7ceb4cfa4ba358ea4547.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7ceb4cfa4ba358ea4547.geojson | source-terms-not-recorded
vcc-site-7e1b680aa925165fe2ef | curated:alto-sp01-granada-data-center-campus | Alto Infrastructure SP01 Granada Data Center Campus | Spain | ES | 37.0833 | -3.752 | Point | ["project"] | ["direct_geometry"] | ["official_junta_sp01_event_location_link_to_coordinate_point"] | ["official_government_project_event_reference_point"] | ["official_source"] | ["project_locator"] | ["Official project-event locator point used only to locate SP01. The seven-decimal redirect coordinate is preserved as published but is not treated as survey accuracy, parcel geometry, or a project centroid."] |  | Neither the Junta agenda nor linked location redirect states the reference feature, collection method, or numeric horizontal accuracy. | ["dfffb2f5-ca78-5c98-bef7-2b58e7c98238"] | 1 | ["4a934222-f3af-5945-bb46-b98bfaef89b7"] | ["curated:alto-sp01-granada-data-center-campus:phase-1-10mw-critical-it"] | ["under_construction"] | 2026-07-09 | 2026-07-09 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7e1b680aa925165fe2ef/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7e1b680aa925165fe2ef.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7e1b680aa925165fe2ef.geojson | rights-status-not-established
vcc-site-7f644893d8685d1d4b44 | imported:semiconductor-atlas:reliance-jamnagar-ai-data-center | Reliance Jamnagar AI-enabled data centre for Meta | India | IN | 22.4732 | 70.0552 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["The release names Jamnagar, Gujarat only. Coordinates are the OpenStreetMap Nominatim centroid of Jamnagar city, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["12061b36-621f-5896-9816-570fc1e6d37f"] | 1 | ["987638c1-43b0-5075-a91a-f02ac2f007cc"] | ["imported:semiconductor-atlas:reliance-jamnagar-ai-data-center"] | ["announced"] | 2026-06-10 | 2026-06-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7f644893d8685d1d4b44/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7f644893d8685d1d4b44.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-7f644893d8685d1d4b44.geojson | source-terms-not-recorded
vcc-site-80fb287847eab3cd8bf9 | curated:nebius-pajarila-lappeenranta-campus | Nebius Pajarila Lappeenranta Campus | Finland | FI | 61.0559 | 28.2855 | Point | ["campus"] | ["municipal_exact_address_result_transformed_by_same_municipal_service_to_EPSG4326"] | ["municipal_exact_address_result_transformed_by_same_municipal_service_to_EPSG4326"] | ["government_site_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["Municipal point for the exact address printed in Fira's project-bound data-center piling notice. It identifies the first-phase campus parcel at Pajarilanväylä24, not the whole 41ha boundary, a building footprint or a current work-area centroid."] |  | The source provides no survey accuracy or quantitative positional uncertainty; coordinate digits do not establish accuracy. | ["1396cf0e-0de1-5c51-ab78-5e027fd4a6e8","2705a04d-8e88-5b06-9cd5-30fc83cc4328","b2f07aa5-6b86-5975-8eee-c77d11d6aa0a"] | 1 | ["b9ccc1e7-c2da-5822-82bc-b20be7d43dfe"] | ["curated:nebius-pajarila-lappeenranta-campus:first-phase-current-build"] | ["under_construction"] | 2026-08-11 | 2026-08-11 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-80fb287847eab3cd8bf9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-80fb287847eab3cd8bf9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-80fb287847eab3cd8bf9.geojson | no-open-license-asserted
vcc-site-81f27673b0960b9da911 | curated:microsoft-finland-espoo-hepokorpi-campus | Microsoft Espoo Hepokorpi Datacenter Campus | Finland | FI | 60.2378 | 24.6875 | Polygon | ["project"] | ["official_registered_parcel_coordinate_transform"] | ["exact_parcel_49-65-3-1_EPSG3879_to_EPSG4326_with_planar_area_centroid_anchor"] | ["official_registered_parcel_containing_selected_project"] | ["official_source"] | ["project_locator"] | ["Registered parcel 49-65-3-1 contains the selected second building and the first-building project. It is a parcel locator, not a data-center campus boundary or building footprint. The planar area-weighted centroid is a derived display anchor, not an official building-center coordinate; third-building parcel 49-65-2-1 is excluded."] |  | The selected property-unit response states no numeric horizontal accuracy for this parcel geometry. | ["9ba2902e-39d3-51fc-abcb-9a36d3a66d72"] | 1 | ["c1af62b5-b9a2-5c15-a8a4-717e1a65ac05"] | ["curated:microsoft-finland-espoo-hepokorpi-campus:second-building"] | ["under_construction"] | 2026-06-11 | 2026-06-11 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-81f27673b0960b9da911/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-81f27673b0960b9da911.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-81f27673b0960b9da911.geojson | CC-BY-4.0
vcc-site-8345f1f9d37238aa593f | imported:semiconductor-atlas:bridge-chonburi-khlong-tamru | Bridge Data Centres Chonburi hyperscale campus | Thailand | TH | 13.3619 | 100.9792 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Bridge names Khlong Tamru subdistrict in Chonburi Province and W.Media adds Mueang District, without an address; the point is the district coordinate from the Mueang Chonburi district Wikipedia article, so it marks the district rather than the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["cdb912f3-7a04-528a-ae5e-b5fbd9f7823a"] | 1 | ["755ec57c-df00-5ee2-a290-9997607440b4"] | ["imported:semiconductor-atlas:bridge-chonburi-khlong-tamru"] | ["announced"] | 2025-10-21 | 2025-10-21 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8345f1f9d37238aa593f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8345f1f9d37238aa593f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8345f1f9d37238aa593f.geojson | source-terms-not-recorded
vcc-site-837c77c61e73b3c11714 | imported:semiconductor-atlas:xai-colossus-memphis | xAI Colossus 1 (Memphis) | United States | US | 35.0599 | -90.1563 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["site"] | ["compiled_reference"] | ["project_locator"] | ["Center of the OpenStreetMap building tagged 'xAI Colossus' at 3231 Paul R. Lowery Road, taken from this project's OpenStreetMap data center layer (no geocoder call). The address comes from Cleanview and from Memphis Business Journal reporting cited by WMC; MLGW places the facility in the former Electrolux plant in Frank C. Pidgeon Industrial Park. Shelby County is the jurisdiction of the health department that permitted the site's turbines."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f683c140-2c68-543f-bc1a-5b12f7daf9b1"] | 1 | ["d2db6863-886a-5c16-b819-7f2cd95cd87e"] | ["imported:semiconductor-atlas:xai-colossus-memphis"] | ["operational"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-837c77c61e73b3c11714/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-837c77c61e73b3c11714.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-837c77c61e73b3c11714.geojson | source-terms-not-recorded
vcc-site-847f0ddc67e6e40ce38a | curated:applied-digital-polaris-forge-2-harwood | Applied Digital Polaris Forge 2 Campus | United States | US | 46.9669 | -96.8685 | Polygon | ["campus"] | ["official_constituent_tax_parcel"] | ["Cass_GISPIN75000000120020_native_EPSG3857_to_EPSG4326_server_independently_checked"] | ["official_constituent_tax_parcel"] | ["official_source"] | ["campus_locator"] | ["Official corporate tax parcel at the exact NDDEQ data-center-associated generator address; one campus locator, not the complete PF2 campus boundary or the construction footprint of both buildings. WGS84 returned ring independently agrees with native Web Mercator conversion within 1.43e-14 degrees. No parcel survey accuracy is published."] |  | No source-specific numeric accuracy is supplied. Coordinate decimals and transformation agreement are not source positional accuracy. | ["1e7d82eb-791b-578e-b8b8-6c9312497731","6946a0b0-a9de-530f-8cea-5f0477b9bd7c","a15f97b3-ce3d-52af-84d8-d063322cc772","d07a6f63-e9f2-51aa-904c-f6f60205763a"] | 2 | ["12407b2e-a44d-5c8d-aa62-c7b64045e20f","5c691ba6-a630-5ab4-a45d-4d676e3e4d53"] | ["curated:applied-digital-polaris-forge-2-harwood:current-construction","imported:semiconductor-atlas:applied-digital-polaris-forge-2"] | ["under_construction"] | 2026-07-27 | 2026-10-07 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-847f0ddc67e6e40ce38a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-847f0ddc67e6e40ce38a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-847f0ddc67e6e40ce38a.geojson | public-domain-per-Cass-County-item-policy
vcc-site-8511f5b23fe433a2c61f | curated:datar-rellingen-campus | dataR Rellingen Data Center Campus | Germany | DE | 53.635 | 9.8728 | Point | ["campus"] | ["Literal native OSM node point; named latitude/longitude axis order only; independently matched to same Nominatim node"] | ["community_named_exact_address_site_node"] | ["named_site_address_point"] | ["community_source"] | ["campus_locator"] | ["Exact mapped dataR site-address node only; not a current-work footprint, cadastral parcel, campus boundary, building centroid, headquarters substitute, road point or entrance. Decimal precision retained without an accuracy claim."] |  | OSM native node and Nominatim result do not provide positional accuracy or original survey provenance. Seven-decimal storage precision is not feature accuracy. | ["21e72855-0ef7-570f-85cd-49291f6c0f6d","58396c5d-9232-5398-b381-bc3c594518f3","db9400d1-0b3e-5e26-9ac3-e8eec898b1ae","f84b7d28-409b-5088-bf66-9ba5aa67de9a"] | 1 | ["5443b4c1-09dc-5f14-a9a3-ec32c05602fb"] | ["curated:datar-rellingen-campus:current-build"] | ["under_construction"] | 2026-07-17 | 2026-07-17 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8511f5b23fe433a2c61f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8511f5b23fe433a2c61f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8511f5b23fe433a2c61f.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-85b3549bb55293336132 | curated:lancium-clean-campus-abilene-ai-data-center | Lancium Clean Campus Abilene AI Data Center | United States | US | 32.5096 | -99.7748 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The municipal address binds Buildings 5 through 8 and the remaining campus development; the point is not any one of the six remaining building locations."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["6600dddb-f2d8-5458-8e71-b43f77cc5e01"] | 2 | ["632aad8a-8c12-5a02-bd17-1138e6b03b6c","938feeec-a323-56e0-b6ce-2590fe58e623"] | ["curated:lancium-clean-campus-abilene-ai-data-center:remaining-six-building-expansion","imported:semiconductor-atlas:openai-stargate-abilene"] | ["partially_operational","under_construction"] | 2026-06-04 | 2026-10-05 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-85b3549bb55293336132/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-85b3549bb55293336132.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-85b3549bb55293336132.geojson | public-domain-us-government
vcc-site-8626707eb0091306e3b9 | imported:semiconductor-atlas:kio-qro3-queretaro | KIO Data Centers QRO3, Querétaro | Mexico | MX | 20.5664 | -100.2567 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Mexico Business News places QRO3 on KIO's campus in the El Marqués Industrial Park. The point is the existing building tagged 'Centro de datos KIO QRO1 y QRO2' in the local OpenStreetMap layer (datacenters/layers/osm/features.geojson, OSM way 741133962); exactly where QRO3 would sit on or near that campus is not reported."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["13c130cf-a2a7-51db-9d24-6b6aef94d717"] | 1 | ["352e29e6-cabf-5acb-bd20-619157576502"] | ["imported:semiconductor-atlas:kio-qro3-queretaro"] | ["proposed"] | 2026-08-17 | 2026-08-17 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8626707eb0091306e3b9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8626707eb0091306e3b9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8626707eb0091306e3b9.geojson | source-terms-not-recorded
vcc-site-86c96db92481ee74998d | curated:ntt-dallas-data-center-campus | NTT Dallas Data Center Campus | United States | US | 32.9825 | -96.6544 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The current NTT page supplies 2060 Lookout Drive and controls the locator; the Texas TDLR record supplies conflicting 2008 Lookout Drive. Both remain disclosed, and neither point is a TX4 footprint or parcel."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["6600dddb-f2d8-5458-8e71-b43f77cc5e01"] | 1 | ["9ddf0df3-e40c-515f-9468-ed78f063513b"] | ["curated:ntt-dallas-data-center-campus:tx4"] | ["under_construction"] | 2026-05-31 | 2026-05-31 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-86c96db92481ee74998d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-86c96db92481ee74998d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-86c96db92481ee74998d.geojson | public-domain-us-government
vcc-site-885f8423ea04be0404cf | curated:microsoft-san-bovio-italy-datacenter | Microsoft San Bovio Datacenter | Italy | IT | 45.4621 | 9.3106 | Polygon | ["campus"] | ["capture_replayed_geometry"] | ["cross_source_identity_bridge_to_live_osm_former_industrial_site_polygon"] | ["community_mapped_former_industrial_site_polygon"] | ["community_mapped"] | ["campus_locator"] | ["The representative point is a deterministic planar centroid derived with pyproj 3.7.2, PROJ 9.5.1, and Shapely 2.1.2 under the method pinned in geometry_entity; its serialized digits are computational reproducibility, not survey accuracy. The polygon is a community-mapped former industrial-site outline last edited in 2022. It may include land outside the 77,237 m² municipal intervention area and must not be represented as an official campus, project, parcel, planning, construction, or building boundary."] |  | OSM supplies no survey accuracy, cadastral authority, or numeric horizontal uncertainty for this way. | ["13dc86ac-4e90-5c6e-8540-de0c7893690f"] | 1 | ["257f3255-46fe-585e-bdf5-9689b34edbdc"] | ["curated:microsoft-san-bovio-italy-datacenter:initial-development"] | ["site_preparation"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-885f8423ea04be0404cf/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-885f8423ea04be0404cf.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-885f8423ea04be0404cf.geojson | ODbL-1.0
vcc-site-88781eb659e91e68b6e9 | curated:israel-mega-dc-mdcil2-masmiyya-site | Mega D.C. MDCIL-2 Masmiyya Site | Israel | IL | 31.7532 | 34.779 | Polygon | ["campus"] | ["approved_plan_land_use_plot_ring_transformed_EPSG2039_to_WGS84"] | ["Xplan_layer4_plot_query_native_ring_PROJ_Israel1993_to_WGS84_2_round7"] | ["approved_statutory_plan_land_use_plot"] | ["official_source"] | ["campus_locator"] | ["Every native plot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. Plot 200A of plan 632-0649806 is bound to the campus by the issuer's own plot references; it is a planning plot, not a surveyed cadastral boundary, building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it."] |  | The planning service states no positional accuracy and disclaims official status; the 0.5 m datum-operation figure is not a plot accuracy. | ["95d0d9b6-a7af-57ce-8b80-2e2714afe61e","cc9f6953-6149-5d86-b69a-d7c3ad57b7a8"] | 1 | ["e542ef62-912c-5edb-982a-8e463179484b"] | ["curated:israel-mega-dc-mdcil2-masmiyya-site:phase-a"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88781eb659e91e68b6e9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88781eb659e91e68b6e9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88781eb659e91e68b6e9.geojson | no-open-license-asserted
vcc-site-88b1acf055e1ab6200e4 | epoch-ai:data-center:dd4bfd7c-adf8-5312-9a4a-f2728f1fe791 | TeraWulf Lake Mariner Data Campus | United States | US | 43.3489 | -78.6029 | Point | ["project"] | ["official_census_street_address_range_interpolation"] | ["exact_issuer_defined_CB5_address_Census_NAD83_to_WGS84_pyproj_3_8_0"] | ["official_project_street_address_locator"] | ["official_source"] | ["project_locator"] | ["Exact source-bound CB-5 postal-address interpolation along Lake Road. It is not the physical CB-5 building position, entrance, centre, construction footprint, surveyed parcel or campus boundary. No interior-campus position is claimed."] |  | Census provides no site-specific accuracy for the address-range interpolation. | ["05fc7a75-5568-56e7-95cd-90eaeb278a67","4aa18999-3b90-56ae-be13-e899ddb7d886","8d8b2825-0c0b-585b-a596-7bfcdd59da40"] | 2 | ["6b11de63-a6b0-5513-87a1-b77ff3b71bfb","e389cd04-b538-5729-85a5-8e0b18e78002"] | ["epoch-ai:data-center:dd4bfd7c-adf8-5312-9a4a-f2728f1fe791:cb-5-current-build","imported:semiconductor-atlas:terawulf-lake-mariner"] | ["partially_operational","under_construction"] | 2026-08-05 | 2026-08-05 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88b1acf055e1ab6200e4/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88b1acf055e1ab6200e4.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88b1acf055e1ab6200e4.geojson | no-open-redistribution-license-asserted
vcc-site-88d9a98c0d66b0ceae9f | imported:semiconductor-atlas:nightpeak-old-ocean | Old Ocean Data Center (Nightpeak Energy) | United States | US | 29.0797 | -95.7494 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Bisnow, citing county meeting documents, places the 158-acre site outside Sweeny, and the campus is named after Old Ocean, an unincorporated community about 5 miles northwest of Sweeny. The point is Old Ocean's coordinate from its Wikipedia article, not the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f3c72526-743a-54a9-be8a-a843c26bfe76"] | 1 | ["c400f10b-b4a6-5824-987b-3ff8657fb0d3"] | ["imported:semiconductor-atlas:nightpeak-old-ocean"] | ["proposed"] | 2026-03-11 | 2026-03-11 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88d9a98c0d66b0ceae9f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88d9a98c0d66b0ceae9f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88d9a98c0d66b0ceae9f.geojson | source-terms-not-recorded
vcc-site-88fff6786d166668a98f | curated:aligned-conesville-cmh02-campus | Aligned Conesville CMH-02 Data Center Campus | United States | US | 40.1825 | -81.8748 | Point | ["campus"] | ["official_parcel_centroid"] | ["ArcGIS_returnCentroid_EPSG3734_to_EPSG4326_explicit_datum1188_independently_checked"] | ["official_constituent_parcel_reference_point"] | ["official_source"] | ["campus_locator"] | ["County-computed reference point for one exact Aligned-owned constituent parcel, not a whole-campus centroid, boundary, entrance, building or current-work footprint. Computational digits are retained without claiming surveyed positional accuracy."] |  | County records provide no numerical positional-accuracy estimate; transformation-operation accuracy is not source feature accuracy. | ["306ee880-6ae1-5119-8eed-6b728cca33c0","56c665a4-7406-5a2e-b355-211ccf6be6c0","5dd0cf9d-4dc3-52ad-ba7e-fab8d6990799","b492265f-627e-52b8-9b29-61f0993e3870","bb90c0f6-61de-5891-9200-fe549e67775f","d4b5361d-8a09-58ae-b9ee-4cac8a64e855","d9f0d2d4-00db-532c-aaf4-62229f101ec6"] | 1 | ["26ebe837-0ec5-5973-a729-656b1b4ce011"] | ["curated:aligned-conesville-cmh02-campus:current-site-preparation"] | ["site_preparation"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88fff6786d166668a98f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88fff6786d166668a98f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-88fff6786d166668a98f.geojson | no-open-license-asserted
vcc-site-8a182a091b75047cadab | curated:bulk-dk01-esbjerg-campus | Bulk DK01 Esbjerg Campus | Denmark | DK | 55.5092 | 8.4955 | Point | ["campus"] | ["source_attribute_decimal_coordinates_to_point_without_centroiding"] | ["first_party_schema_org_geocoordinates_literal_point"] | ["official_operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Campus reference point only, associated by canonical site URL and postal address. The new construction project is on this campus but is not asserted at the exact point. No parcel boundary, work footprint, surveyed entrance or quantified accuracy is claimed."] |  | Publisher supplies no positional accuracy. Decimal precision and supporting map containment do not establish survey accuracy. | ["482e608f-c5a8-5719-b1ac-96373501e140","8e346666-c072-5c99-9322-d0e3257bdcde"] | 1 | ["d2e988cd-e878-5061-817e-0c1cda87f372"] | ["curated:bulk-dk01-esbjerg-campus:current-new-building-construction"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8a182a091b75047cadab/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8a182a091b75047cadab.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8a182a091b75047cadab.geojson | no-open-license-asserted
vcc-site-8a73ede727ab01225667 | curated:schwarz-digits-luebbenau-campus | Schwarz Digits Lübbenau Campus | Germany | DE | 51.8471 | 13.961 | Point | ["campus"] | ["copy_exact_LGB_address_WKT_point_to_GeoJSON"] | ["exact_operator_street_house_number_postal_code_city_to_official_LGB_address_object"] | ["official_house_number_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["Official Kraftwerkstraße 24 address point only. No exact new data-center hall, active construction footprint, site boundary or surveyed entrance is asserted. LGB metadata permits a parcel point when an address is reserved or has no building. The source supplies no quantitative positional accuracy for this record; decimal places do not establish survey precision."] |  | No numerical positional accuracy or reserved-address classification supplied for this individual government address record. | ["905c48e3-76d6-5aed-8e41-0ca3486f7998","98b82ddb-afbd-541a-a1fb-7e25ee01fc00","e2316504-2b8a-5b2f-a096-b8bff9c8d507"] | 1 | ["8f5c2434-0b2d-547e-ac2c-e25ddeefe1b7"] | ["curated:schwarz-digits-luebbenau-campus:current-build"] | ["under_construction"] | 2026-08-18 | 2026-08-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8a73ede727ab01225667/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8a73ede727ab01225667.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8a73ede727ab01225667.geojson | dl-de/by-2-0
vcc-site-8cdb2274a5a7f5abf1c9 | imported:semiconductor-atlas:nebius-birmingham-alabama | Nebius Birmingham AI factory (Lakeshore Parkway) | United States | US | 33.5175 | -86.8094 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City centroid from the Wikipedia infobox for Birmingham (s3). The report places the site off Lakeshore Parkway without an address, so the point is the city centroid, not the site. Birmingham spans Jefferson and Shelby counties, so no county is given."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["8039fb20-c919-5864-948c-86bd8da72cdd"] | 1 | ["c01f2073-5c23-511c-9d85-80ad9345987a"] | ["imported:semiconductor-atlas:nebius-birmingham-alabama"] | ["proposed"] | 2026-02-10 | 2026-02-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8cdb2274a5a7f5abf1c9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8cdb2274a5a7f5abf1c9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8cdb2274a5a7f5abf1c9.geojson | source-terms-not-recorded
vcc-site-8d354596ddb2508a0eda | imported:semiconductor-atlas:applied-digital-delta-forge-2 | Applied Digital Delta Forge 2 | United States | US | 33.2397 | -87.3278 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Local reports place the campus north of the 17000 block of Brookwood Parkway. No geocoder was used; coordinates are the Brookwood city point from its Wikipedia article."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ab72ef7f-022c-58c6-87fb-9002d3f55b74"] | 1 | ["d2bf7339-8e09-50df-8229-96ad3f8fa358"] | ["imported:semiconductor-atlas:applied-digital-delta-forge-2"] | ["under_construction"] | 2026-10-07 | 2026-10-07 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8d354596ddb2508a0eda/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8d354596ddb2508a0eda.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8d354596ddb2508a0eda.geojson | source-terms-not-recorded
vcc-site-8d8b8d427f99ad4fa5a1 | curated:nextdc-s4-sydney | NEXTDC S4 Sydney Data Center Campus | Australia | AU | -33.8278 | 150.8246 | Point | ["campus"] | ["government_named_project_geojson_point"] | ["preserve_public_Drupal_GeoJSON_feature_for_node68004716_SSD63741210_and_bind_application_Lot305_DP1275011"] | ["government_project_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The portal's named NEXTDC S4 project marker is bound to SSD-63741210 and the application's 16 Johnston Crescent / Lot 305 DP 1275011. Normal JSON floating-point serialization shortens literal tokens without geocoding. The unrelated default map center and rounded application longitude are excluded. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate."] |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | ["07ea32f1-85b6-5285-8219-504b14f65e60","4092b0af-767b-5a50-a717-531361167237"] | 1 | ["3761e59a-fe39-523d-83a6-9fbfa9feec85"] | ["curated:nextdc-s4-sydney:initial-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8d8b8d427f99ad4fa5a1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8d8b8d427f99ad4fa5a1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8d8b8d427f99ad4fa5a1.geojson | CC-BY-4.0-Department-material-scope
vcc-site-8ea405601b72e53a6661 | imported:semiconductor-atlas:terawulf-fluidstack-abernathy | Abernathy HPC campus (TeraWulf and Fluidstack joint venture) | United States | US | 33.8322 | -101.8431 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from Wikipedia; the sources name Abernathy but give no address. The town spans Hale and Lubbock counties, so no county is recorded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["9160242e-d5c4-5428-b55d-9234947b7f01"] | 1 | ["b6f0ed21-2ab2-51e2-971e-4e9512279101"] | ["imported:semiconductor-atlas:terawulf-fluidstack-abernathy"] | ["under_construction"] | 2026-02-27 | 2026-02-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8ea405601b72e53a6661/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8ea405601b72e53a6661.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8ea405601b72e53a6661.geojson | source-terms-not-recorded
vcc-site-8f9f601fd64ed7dfc62c | imported:semiconductor-atlas:humain-dammam | HUMAIN Dammam AI data centre | Saudi Arabia | SA | 26.433 | 50.1 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Dammam only. Coordinates are the Dammam city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["c9f21c02-2182-5b65-8bc0-367b74112020"] | 1 | ["55a2bfbb-45b2-5d51-bc40-4cc74d88ccfd"] | ["imported:semiconductor-atlas:humain-dammam"] | ["under_construction"] | 2025-08-26 | 2025-08-26 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8f9f601fd64ed7dfc62c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8f9f601fd64ed7dfc62c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-8f9f601fd64ed7dfc62c.geojson | source-terms-not-recorded
vcc-site-900b1508d570a2f4253f | curated:procergs-porto-alegre-praca-dos-acorianos-campus | Procergs Porto Alegre Data Center Campus | Brazil | BR | -30.0386 | -51.2308 | Point | ["campus"] | ["provider_supplied_named_Procergs_building_centroid_bound_to_explicit_datacenter_address_and_substation_contract6033"] | ["copy_exact_Nominatim_lat_lon_for_OSM_way112410783_corroborate_canonical_website_short_name_historic_name_and_official_DC_address"] | ["community_constituent_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["Only a locator for the Procergs campus from its named existing headquarters/datacenter constituent. New substation is alongside that same building, not asserted at this exact point. No work-footprint containment, official parcel, exact entrance, surveyed location or quantitative positional accuracy claim. OSM/Nominatim address labels differ from the official address; identity rests on the literal company name, short_name, canonical website and independent datacenter-address record."] |  | Neither OSM nor Nominatim provides a quantified positional accuracy. Decimal digits and point-in-building containment do not establish survey accuracy. | ["22df2f28-4402-57a9-9de9-45919481329d","8a08ee35-6a29-506f-b3f8-411546518be6","a019a821-4ecd-59b8-a01e-ffb7df16a1dd","c3c1222b-f7d8-5ddd-9fb4-b037a442b1b2","e687363e-0a56-5567-a0c7-7503be4dffa6"] | 1 | ["b91d994d-0f59-5ed8-ad74-20e4ba2251f3"] | ["curated:procergs-porto-alegre-praca-dos-acorianos-campus:new-substation-6033"] | ["under_construction"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-900b1508d570a2f4253f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-900b1508d570a2f4253f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-900b1508d570a2f4253f.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-910b8939869a2f993425 | imported:semiconductor-atlas:provident-powerhouse-grand-prairie | PowerHouse Grand Prairie campus (PowerHouse and Provident) | United States | US | 32.5069 | -97.0069 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of Midlothian (s5), the mailing city in the state filing for Building 1 at 881 Miller Road (s4). The developers describe the site as just outside Grand Prairie in northern Ellis County. The street address was not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["8199ea4f-93f5-5f57-b678-e54dc4cd96c5"] | 1 | ["fe8ac418-224e-5ac7-b342-11689bcc613e"] | ["imported:semiconductor-atlas:provident-powerhouse-grand-prairie"] | ["announced"] | 2026-04-02 | 2026-04-02 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-910b8939869a2f993425/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-910b8939869a2f993425.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-910b8939869a2f993425.geojson | source-terms-not-recorded
vcc-site-9110ab1aaf7969ec33fc | curated:data-world-matatirtha-campus | Data World Matatirtha Campus | Nepal | NP | 27.6786 | 85.2365 | Point | ["campus"] | ["source_marker_decimal_coordinates_to_point_without_centroiding"] | ["data_world_named_kathmandu_marker_as_matatirtha_campus_locator"] | ["first_party_facility_map_marker_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["The exact first-party Kathmandu marker is linked to the IFC-named Matatirtha project through Data World, Chandragiri, and singular facility context. It is only a broad campus locator, not an entrance, parcel, surveyed point, boundary, footprint, or work extent."] |  | Data World publishes no marker collection method, represented feature, datum, or bounded horizontal accuracy. | ["6a83e8a4-4c67-5ec1-8979-c49535d7d363"] | 1 | ["36ac2490-7d9c-51f3-96c4-1344481aa4e2"] | ["curated:data-world-matatirtha-campus:core-data-center-current-build"] | ["under_construction"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9110ab1aaf7969ec33fc/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9110ab1aaf7969ec33fc.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9110ab1aaf7969ec33fc.geojson | all-rights-reserved
vcc-site-91ad5264ef3af020a0ed | imported:semiconductor-atlas:microsoft-pecos-texas | Microsoft Pecos datacenter campus | United States | US | 31.4156 | -103.5 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Pecos city coordinates from its Wikipedia page. Sources name Pecos and Reeves County but give no site or acreage."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ebbafd06-419e-5b39-9468-e6032100b037"] | 1 | ["735e570e-2923-5425-a0af-2a13e94f49e3"] | ["imported:semiconductor-atlas:microsoft-pecos-texas"] | ["announced"] | 2026-07-02 | 2026-07-02 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-91ad5264ef3af020a0ed/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-91ad5264ef3af020a0ed.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-91ad5264ef3af020a0ed.geojson | source-terms-not-recorded
vcc-site-9209936dfd95900f78c3 | imported:semiconductor-atlas:cloudhq-queretaro | CloudHQ QRO Campus (Querétaro) | Mexico | MX | 20.6198 | -100.1474 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Coordinates are the point published on CloudHQ's campus page. News reports place the 52-hectare site on the west side of the airport; the published point was not checked against a parcel boundary."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["eb3a316f-cdae-55ad-b88b-08ed42e7c6ed"] | 1 | ["a7a29c6e-70aa-5f7b-b172-d1abe208715e"] | ["imported:semiconductor-atlas:cloudhq-queretaro"] | ["announced"] | 2025-09-30 | 2025-09-30 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9209936dfd95900f78c3/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9209936dfd95900f78c3.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9209936dfd95900f78c3.geojson | source-terms-not-recorded
vcc-site-9369a9dbb7d04a9e1327 | curated:edged-chicago-aurora-campus | Edged Chicago Aurora Data Center Campus | United States | US | 41.807 | -88.241 | Point | ["project"] | ["direct_geometry"] | ["authoritative_address_geocode"] | ["campus_address_point"] | ["official_source"] | ["reviewed_site_locator"] | ["Exact City of Aurora address point for 2835 Bilter Road on the Edged Chicago LLC-owned parcel; not an ORD01-2 footprint."] |  | official source does not state positional accuracy | ["98fcd750-ba33-537e-8669-fe8d1db1a6c6"] | 1 | ["b8399bc6-5c72-5627-a035-4fea208cd287"] | ["curated:edged-chicago-aurora-campus:ord01-2"] | ["shell"] | 2026-06-04 | 2026-06-04 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9369a9dbb7d04a9e1327/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9369a9dbb7d04a9e1327.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9369a9dbb7d04a9e1327.geojson | public-domain
vcc-site-94afbf6dc84e8a88fc00 | imported:semiconductor-atlas:kasi-cloud-lekki | Kasi Cloud LOS campus (Lekki, Lagos) | Nigeria | NG | 6.4934 | 3.7207 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates of Lekki from its Wikipedia article. Capacity Media places the site in the Maiyegun area of Lekki, ThisDay along the Lagos-Calabar coastal highway, and Kasi's website lists the campus in Lekki, Lagos; no exact point is published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6bd0fd8d-5b0f-51c9-a6cd-55c87d0a291b"] | 1 | ["cb66229f-70db-5cfc-95b3-f5a05a3e73bc"] | ["imported:semiconductor-atlas:kasi-cloud-lekki"] | ["partially_operational"] | 2026-05-19 | 2026-05-19 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-94afbf6dc84e8a88fc00/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-94afbf6dc84e8a88fc00.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-94afbf6dc84e8a88fc00.geojson | source-terms-not-recorded
vcc-site-94d1b580090a69685f9f | curated:skygard-osl1-hovinbyen-campus | Skygard OSL1 Hovinbyen Campus | Norway | NO | 59.9294 | 10.8181 | Point | ["campus"] | ["cross_source_overlay"] | ["official_nve_site_address_to_matrikkelen_epsg4326_address_point"] | ["official_matrikkelen_verified_address_representative_point"] | ["official_source"] | ["campus_locator"] | ["Official address representative point used only to locate the OSL1 campus inherited by Phase 2. It is not the Phase 2 location or footprint, a building centroid, parcel, campus boundary, construction extent, or survey-accuracy claim."] |  | The response marks the address point verified but does not publish numeric horizontal accuracy for this record. | ["8d4c81f8-cb29-54f6-b5b4-c6e5f1f6b628"] | 1 | ["5ae9f639-4de6-5ce4-af8d-a40d6f8a3bec"] | ["curated:skygard-osl1-hovinbyen-campus:phase-2"] | ["under_construction"] | 2026-06-16 | 2026-06-16 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-94d1b580090a69685f9f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-94d1b580090a69685f9f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-94d1b580090a69685f9f.geojson | CC-BY-4.0
vcc-site-983cd9eec3d1aaa46e69 | curated:iron-mountain-va-9-northern-virginia-data-center | Iron Mountain VA-9 Northern Virginia Data Center | United States | US | 38.7728 | -77.5429 | Point | ["campus"] | ["official_address_range_geocode"] | ["census_single_exact_address_match_then_explicit_nad83_to_wgs84"] | ["official_address_range_interpolation_constituent_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Official Census street-address interpolation for existing VA-1 at 11680 Hayden Road. First-party documents identify VA-1 and VA-9 as constituents of the same 142-acre Manassas campus. Used solely as a campus locator; not the VA-8/VA-9 building, Phase 1/2 work area, campus centroid, parcel boundary or surveyed accuracy. VA-9's 11530 Elevate Drive address was not matched by Census."] |  | No source-specific numerical horizontal-accuracy guarantee is published for the selected street-range interpolation. | ["375685f2-b4b3-5f21-a1fe-48a1597c9eb2","69ecb4cd-be02-55fa-b978-732f307eeb00"] | 1 | ["d83dc321-220b-5c4c-b5af-ff1f4bc19a5d"] | ["curated:iron-mountain-va-9-northern-virginia-data-center:phase-1"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-983cd9eec3d1aaa46e69/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-983cd9eec3d1aaa46e69.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-983cd9eec3d1aaa46e69.geojson | no-open-redistribution-license-asserted
vcc-site-98db1c10877fca784aba | curated:dc-blox-palm-coast-cls-campus | DC BLOX Palm Coast Cable Landing Station and Colocation Campus | United States | US | 29.4954 | -81.1973 | Point | ["campus"] | ["official_named_address_point"] | ["native_EPSG2881_to_EPSG4326_pyproj_NAD83_HARN_to_WGS84_3"] | ["official_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["Literal municipal address reference point inside the exact approved Lot 7B parcel, transformed from its stored-source NAD83(HARN) Florida East coordinates. Not a parcel centroid, surveyed boundary, entrance, building outline or precise active-work position; digits preserve computational precision only."] |  | The city supplies no numeric positional-accuracy estimate and warns of generalized map error and scale limitations. The one-metre selected transformation-operation accuracy is not source feature accuracy. | ["05cb13bf-4df5-5b3c-8ecc-a2a16b1ced59","103edd8f-a15e-54f0-802f-cd68c47df0ea","29917174-7529-531b-9498-1ccd315ddb92","31cbba68-5623-5192-9250-ed5fa4e62c21","7b7ab8d3-080d-5810-8944-e2eba368fb3a","8a6fde4a-2282-5060-a6f1-a8f6bd64e411","e5855643-474a-5e69-ab89-f951302a58dd","ff5476f6-2554-575f-8400-8451ed8fced6"] | 1 | ["d5b84301-4f54-5958-a0d1-fd2c5a72cc5b"] | ["curated:dc-blox-palm-coast-cls-campus:approved-first-building-current-build"] | ["under_construction"] | 2026-06-19 | 2026-06-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-98db1c10877fca784aba/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-98db1c10877fca784aba.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-98db1c10877fca784aba.geojson | no-open-license-asserted
vcc-site-98db91806e7e60522076 | curated:qts-aurora-den1-campus | QTS Aurora DEN1 Data Center Campus | United States | US | 39.7338 | -104.7124 | Point | ["campus"] | ["official_address_point"] | ["Official_ArcGIS_address_geometry_EPSG2232_to_EPSG4326_explicit_datum1188_independently_checked"] | ["official_constituent_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["City address point for exact DEN1 DC2 constituent at1140 N Gun Club Road. It is not a campus boundary, centroid, entrance, surveyed building location or actual drywall-work footprint; unknown real-world positional accuracy."] |  | The city supplies no numerical source feature accuracy and expressly disclaims accuracy warranties. Coordinate digits and four-metre transformation-operation accuracy are not measured locator accuracy. | ["2d52158b-57ba-559c-8ffa-acde0ff95458","3325e1c3-aaa7-5316-9737-22d7b08edb1a","4b248546-1941-5d72-92f0-0a67da1096e3","7270537c-36c5-56e3-8dc2-e01b4e99cc17","e97c0da9-90a1-580d-9ef4-08102fb2c60c","fc9e68c5-1181-5edc-ae96-5e02ddc90a3a"] | 1 | ["c23fe40c-0685-5cee-8fab-9c08575e6b27"] | ["curated:qts-aurora-den1-campus:dc2-current-fit-out"] | ["under_construction"] | 2026-08-19 | 2026-08-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-98db91806e7e60522076/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-98db91806e7e60522076.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-98db91806e7e60522076.geojson | no-open-license-asserted
vcc-site-990a491f49bc3fcbf938 | imported:semiconductor-atlas:lancium-qts-hall-county-texas | QTS and Lancium Hall County data center campus | United States | US | 34.3939 | -100.8953 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid of Turkey from Wikipedia (s2); the announcement says only that the campus is near Turkey in Hall County."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6c8c178e-7ec1-5458-96d5-446d5fa443fc"] | 1 | ["39eada86-53aa-55d0-ae26-0ff35f9e1207"] | ["imported:semiconductor-atlas:lancium-qts-hall-county-texas"] | ["announced"] | 2026-07-13 | 2026-07-13 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-990a491f49bc3fcbf938/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-990a491f49bc3fcbf938.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-990a491f49bc3fcbf938.geojson | source-terms-not-recorded
vcc-site-99459620c3cd48c8a82f | curated:omnia-pecem-data-center-campus | OMNIA Pecém Data Center Campus | Brazil | BR | -3.6542 | -38.8223 | Point | ["campus"] | ["literal_official_public_project_marker"] | ["SEMACE_named_enterprise_record_lat_lon_under_public_Google_Maps_WGS84_interface_contract"] | ["officially_published_applicant_declared_project_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact point published for named Projeto Data Center Pecém / enterprise127774, not a surveyed agency boundary, parcel centroid, entrance, hall or selected-work footprint. All provided digits retained; underlying survey datum and measurement accuracy unknown."] |  | SEMACE public client warns of distortions arising from applicant registration; no numerical accuracy is stated. WGS84 map-interface semantics and coordinate digits do not establish survey accuracy. | ["49912dcd-7f63-554b-add9-bcc489f2c2a4","663ee31a-cd15-5b05-9341-a4030ee42612","6e15977f-e53d-5f29-8f9a-dddbde4623f6","dfb5624b-015b-5f37-a73e-0fe1e83ee48b","fe73d447-a8fe-584d-8aac-8fa45211919e"] | 2 | ["0fd5e6a4-6421-5a23-b51c-e490e4a79cd9","ebd0b7e7-0ca5-501e-89ff-74f8bf30f59b"] | ["curated:omnia-pecem-data-center-campus:initial-tiktok-bytedance-build","imported:semiconductor-atlas:omnia-data-center-pecem"] | ["announced","under_construction"] | 2026-05-18 | 2026-06-16 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-99459620c3cd48c8a82f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-99459620c3cd48c8a82f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-99459620c3cd48c8a82f.geojson | CC-BY-4.0; no-open-license-asserted
vcc-site-998792d68106140776c0 | imported:semiconductor-atlas:rowan-project-temple | Rowan Project Temple | United States | US | 31.1056 | -97.4208 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Temple, Texas. Bisnow places the 707-acre campus near Bob White Road and Lorraine Avenue, and Rowan places it in east Temple, so the site lies east of this point."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["33a59a67-e62e-5348-8fbb-5fc44302a000"] | 1 | ["4a2a09d1-1ace-5ff8-a80f-89996cda5799"] | ["imported:semiconductor-atlas:rowan-project-temple"] | ["under_construction"] | 2026-05-29 | 2026-05-29 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-998792d68106140776c0/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-998792d68106140776c0.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-998792d68106140776c0.geojson | source-terms-not-recorded
vcc-site-99c848590f717e20510c | curated:nxdata3-bucharest-ring-road-campus | NXDATA-3 Bucharest Ring Road Campus | Romania | RO | 44.5387 | 26.1291 | Point | ["project"] | ["source_published_marker_to_point_without_atlas_centroiding"] | ["inflect_named_nxdata_bucharest_3_location_marker_as_project_locator"] | ["commercial_directory_named_data_center_marker_as_project_locator"] | ["community_source"] | ["project_locator"] | ["Atlas copies the exact page-issued marker and calculates no centroid. Treat it only as a locator for the named NXDATA Bucharest 3 record. It is not an entrance, surveyed point, parcel, building footprint, campus boundary, project footprint, construction extent, or horizontal-accuracy claim. Inflect does not disclose whether its upstream marker was geocoded, manually selected, or otherwise derived."] |  | Inflect publishes no collection method, represented feature, datum, or bounded horizontal accuracy for this marker. | ["b1f159c6-216e-5c92-9a98-9c2e0d27ad3a"] | 1 | ["df2b8f33-9c46-5f6a-9853-b47474606979"] | ["curated:nxdata3-bucharest-ring-road-campus:nxdata3-buh3"] | ["under_construction"] | 2026-06-02 | 2026-06-02 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-99c848590f717e20510c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-99c848590f717e20510c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-99c848590f717e20510c.geojson | all-rights-reserved-fact-extraction-only
vcc-site-99d9ae40e299f5a9f017 | imported:semiconductor-atlas:pdg-jc3-bekasi | Princeton Digital Group JC3 Greater Jakarta | Indonesia | ID | -6.3836 | 107.1911 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["PDG places JC3 in the Greenland International Industrial Center (GIIC), Bekasi Regency, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the GIIC industrial estate."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["701fe2a3-dc28-5cef-81d2-9c7a67259df8"] | 1 | ["c7671f1b-16fb-5d22-b002-93f28cea5585"] | ["imported:semiconductor-atlas:pdg-jc3-bekasi"] | ["under_construction"] | 2026-05-07 | 2026-05-07 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-99d9ae40e299f5a9f017/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-99d9ae40e299f5a9f017.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-99d9ae40e299f5a9f017.geojson | source-terms-not-recorded
vcc-site-9b47e002ec40fe02a2d7 | imported:semiconductor-atlas:aws-richmond-county-north-carolina | AWS Richmond County data center campus | United States | US | 35 | -79.76 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["The opened sources name only Richmond County (the announcement was held in Hamlet); coordinates are the county point from its Wikipedia article (Nominatim was unavailable)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["8e2eac72-0b39-5b36-a8bd-abebd98c3c4c"] | 1 | ["3e853975-e7a4-52ba-bc38-6b3d09bfdaf0"] | ["imported:semiconductor-atlas:aws-richmond-county-north-carolina"] | ["under_construction"] | 2026-09-23 | 2026-09-23 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9b47e002ec40fe02a2d7/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9b47e002ec40fe02a2d7.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9b47e002ec40fe02a2d7.geojson | source-terms-not-recorded
vcc-site-9b86fe87cb674e474940 | curated:microsoft-lyle-creek-conover-data-center | Microsoft Conover Lyle Creek Data Center | United States | US | 35.7311 | -81.2054 | Point | ["project"] | ["coordinates_to_point"] | ["official_permit_project_coordinate"] | ["permit_notice_project_point"] | ["official_source"] | ["project_locator"] | ["Exact USACE-published project coordinate, independently shown inside a current official Catawba parcel; not a parcel boundary, building, or work footprint. The primary capture is an indexed-text extract, not fetched PDF bytes."] |  | USACE gives no bounded positional accuracy and the live legacy PDF body is currently unavailable. | ["64ff0af6-8438-5865-b01f-3d997ee799b2","689228be-5762-5bca-9f0c-c8efd81c2da7"] | 1 | ["eb451867-d1d3-5e41-bce7-d375e861167a"] | ["curated:microsoft-lyle-creek-conover-data-center:current-build"] | ["under_construction"] | 2026-05-31 | 2026-05-31 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9b86fe87cb674e474940/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9b86fe87cb674e474940.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9b86fe87cb674e474940.geojson | US-federal-public-domain; county-public-gis-fact-extraction-only
vcc-site-9b9b5ef71cedda52fd47 | curated:coreweave-chirisa-lancaster-greenfield-road-campus | CoreWeave/Chirisa Lancaster Greenfield Road Campus | United States | US | 40.0487 | -76.2561 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The address identifies the adaptive-reuse property, but the Census point is not the existing shell or Phase 1 footprint."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["6600dddb-f2d8-5458-8e71-b43f77cc5e01"] | 1 | ["b75695b9-38e3-58ec-baf2-039179ab353a"] | ["curated:coreweave-chirisa-lancaster-greenfield-road-campus:phase-1-adaptive-reuse"] | ["under_construction"] | 2026-07-22 | 2026-07-22 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9b9b5ef71cedda52fd47/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9b9b5ef71cedda52fd47.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9b9b5ef71cedda52fd47.geojson | public-domain-us-government
vcc-site-9bb64eeea962a4cadd06 | imported:semiconductor-atlas:deutsche-telekom-nvidia-munich | Deutsche Telekom Industrial AI Cloud, Munich Tucherpark | Germany | DE | 48.1527 | 11.5991 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Nominatim geocode of the street Am Tucherpark in Munich; sources name the Tucherpark complex beside the Eisbach but give no street address."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d6c36486-e845-5998-b33f-0204a765588a"] | 1 | ["54782d37-d21e-5ddf-990b-a578130ac9d0"] | ["imported:semiconductor-atlas:deutsche-telekom-nvidia-munich"] | ["partially_operational"] | 2026-02-04 | 2026-02-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9bb64eeea962a4cadd06/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9bb64eeea962a4cadd06.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9bb64eeea962a4cadd06.geojson | source-terms-not-recorded
vcc-site-9c23979ae731456903ea | imported:semiconductor-atlas:aws-king-george-county-virginia | Amazon Web Services King George County campus (Birchwood site) | United States | US | 38.2614 | -77.3319 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Sealston community coordinates from its Wikipedia page. Sources place the campus at the former Birchwood power plant on State Route 3 in the Sealston area but give no parcel coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["77cb3c3a-e777-5b92-80e3-e42a09b8002f"] | 1 | ["c42e542c-bee8-54bc-9f79-9f03d98979ea"] | ["imported:semiconductor-atlas:aws-king-george-county-virginia"] | ["proposed"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9c23979ae731456903ea/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9c23979ae731456903ea.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9c23979ae731456903ea.geojson | source-terms-not-recorded
vcc-site-9d88c072bfebf964cf3a | imported:semiconductor-atlas:bridge-my07-ulu-tiram | Bridge Data Centres MY07, Ulu Tiram | Malaysia | MY | 1.6 | 103.8203 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Ulu Tiram without an address; the point is the Ulu Tiram coordinate from its Wikipedia article, so it marks the town rather than the campus."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["44239b30-48b7-5964-b6e5-4f77ff0ac125"] | 1 | ["2c24f89f-37e6-5164-a240-e1e3d2fca176"] | ["imported:semiconductor-atlas:bridge-my07-ulu-tiram"] | ["partially_operational"] | 2026-09-02 | 2026-09-02 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9d88c072bfebf964cf3a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9d88c072bfebf964cf3a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9d88c072bfebf964cf3a.geojson | source-terms-not-recorded
vcc-site-9da1382c1df4f319ef97 | imported:semiconductor-atlas:google-armstrong-county-texas | Google Armstrong County data center campus (Crusoe Goodnight) | United States | US | 35.1081 | -101.3627 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town centroid of Claude via Nominatim. Sources place the roughly 1,300-acre site near Claude but give no street address."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ed446beb-064d-5891-bbfb-502f3438c893"] | 1 | ["b7d85afa-fbc0-53d6-b19c-6e00c6639642"] | ["imported:semiconductor-atlas:google-armstrong-county-texas"] | ["under_construction"] | 2026-10-01 | 2026-10-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9da1382c1df4f319ef97/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9da1382c1df4f319ef97.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9da1382c1df4f319ef97.geojson | source-terms-not-recorded
vcc-site-9f7647940a58e048e38f | imported:semiconductor-atlas:crusoe-abilene-microsoft | Crusoe Abilene AI factory campus for Microsoft | United States | US | 32.45 | -99.75 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Crusoe places the campus in Abilene, adjacent to its existing campus, without an address. Coordinates are the Abilene city point from its Wikipedia article; the city spans Taylor and Jones counties, so no county is recorded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2eb43ea9-9af0-573a-80a9-aa67d7210065"] | 1 | ["31ee01b0-a72b-5f4a-bcc1-a13a53732efc"] | ["imported:semiconductor-atlas:crusoe-abilene-microsoft"] | ["under_construction"] | 2026-07-15 | 2026-07-15 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9f7647940a58e048e38f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9f7647940a58e048e38f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-9f7647940a58e048e38f.geojson | source-terms-not-recorded
vcc-site-a1239f397b785f28fd31 | imported:semiconductor-atlas:scala-ai-city-eldorado-do-sul | Scala AI City (Eldorado do Sul) | Brazil | BR | -30.0839 | -51.6158 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Municipal reference point for Eldorado do Sul (Wikipedia infobox); the releases name the municipality but not the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["bb426ea9-cd82-5aec-a66e-9a11374b7be7"] | 1 | ["d461c464-bedc-555a-a582-c6f96a0a2acc"] | ["imported:semiconductor-atlas:scala-ai-city-eldorado-do-sul"] | ["announced"] | 2025-05-14 | 2025-05-14 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a1239f397b785f28fd31/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a1239f397b785f28fd31.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a1239f397b785f28fd31.geojson | source-terms-not-recorded
vcc-site-a15d402305ed80ba8cba | curated:hut8-beacon-point-ai-data-center-campus | Hut 8 Beacon Point AI Data Center Campus | United States | US | 27.8345 | -97.6148 | Point | ["campus"] | ["Match direct campus page to the platform's same title and slug; dereference explicit geolocation fields; reproduce the site's six-decimal marker rounding; emit longitude then latitude."] | ["operator_published_mapbox_campus_marker"] | ["operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact operator-rendered named campus marker, not a survey, campus boundary, building centroid, construction footprint, or phase-specific location."] |  | Publisher reports no bounded horizontal positional accuracy; decimal places and deterministic rounding do not establish site accuracy. | ["111e4ef0-d1c4-5b87-8c40-be427705300f","649edbaf-a971-56f7-93c0-ea2569188d14","68bba6b3-26b0-50d9-929f-570e39728681","873a0c1d-1e8a-55f6-81ab-db5d75aa832e","ebef4446-a514-5896-8a6d-c9e0109c3eb4"] | 2 | ["86c83f59-88b9-5791-bc15-ab6c32f256a7","9563b94b-4d68-5f38-b2b2-ce63346ebbe8"] | ["curated:hut8-beacon-point-ai-data-center-campus:first-phase-352mw-critical-it-lease","imported:semiconductor-atlas:hut8-beacon-point"] | ["under_construction"] | 2026-08-04 | 2026-08-04 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a15d402305ed80ba8cba/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a15d402305ed80ba8cba.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a15d402305ed80ba8cba.geojson | IETF-Trust-Legal-Provisions; all-rights-reserved
vcc-site-a226e4ce3df02dee4be7 | imported:semiconductor-atlas:humain-al-saad-riyadh | HUMAIN Al-Saad hyperscale AI data centre campus | Saudi Arabia | SA | 24.6389 | 46.716 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources place the site in the Al-Saad area of east Riyadh. OpenStreetMap Nominatim did not resolve that district, so coordinates are the Riyadh city centroid from Nominatim."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["db21518c-9ab6-58b0-8572-18a1df09cf7f"] | 1 | ["4f8a32cf-b64b-51b4-8758-368320eb441d"] | ["imported:semiconductor-atlas:humain-al-saad-riyadh"] | ["announced"] | 2026-09-27 | 2026-09-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a226e4ce3df02dee4be7/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a226e4ce3df02dee4be7.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a226e4ce3df02dee4be7.geojson | source-terms-not-recorded
vcc-site-a291a33ca480670cccf1 | imported:semiconductor-atlas:terawulf-lake-hawkeye | TeraWulf Lake Hawkeye data campus | United States | US | 42.5658 | -76.5319 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources place the site at the former Cayuga power plant in the town of Lansing without an address. Coordinates are the town point from the Lansing, New York Wikipedia article, not the plant site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["17da0c46-2546-5d53-b910-108e95100470"] | 1 | ["2e14f098-9798-567b-ae40-a7d552f9be18"] | ["imported:semiconductor-atlas:terawulf-lake-hawkeye"] | ["announced"] | 2026-08-05 | 2026-08-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a291a33ca480670cccf1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a291a33ca480670cccf1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a291a33ca480670cccf1.geojson | source-terms-not-recorded
vcc-site-a2932dfc186e6f2538c8 | imported:semiconductor-atlas:red-admiral-rochfortbridge | Red Admiral data centre campus, Rochfortbridge | Ireland | IE | 53.416 | -7.296 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Rochfortbridge village centroid from its Wikipedia article. The application covers several townlands around Rochfortbridge (Gneevebane, Oldtown, Farthingstown, Castlelost and Kiltotan, and Collinstown), but no cited source gives site coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["8d2bc043-b17a-55ab-9ace-cd8a44ea7a3a"] | 1 | ["48458229-1481-521a-8ee4-edcc2d7408bc"] | ["imported:semiconductor-atlas:red-admiral-rochfortbridge"] | ["proposed"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a2932dfc186e6f2538c8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a2932dfc186e6f2538c8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a2932dfc186e6f2538c8.geojson | source-terms-not-recorded
vcc-site-a393d0e2bc6a6f9efbd5 | imported:semiconductor-atlas:prometheus-hyperscale-evanston | Prometheus Hyperscale Evanston campus | United States | US | 41.2683 | -110.9632 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of Evanston (s5). Local reporting places the site about 12 miles east of Evanston on the south side of Interstate 80, so the campus lies some distance east of this point."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["60251015-30da-5d17-8ff5-4e2de7e27afc"] | 1 | ["74d6b0be-d450-509d-a406-ddfed7ede756"] | ["imported:semiconductor-atlas:prometheus-hyperscale-evanston"] | ["announced"] | 2026-06-22 | 2026-06-22 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a393d0e2bc6a6f9efbd5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a393d0e2bc6a6f9efbd5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a393d0e2bc6a6f9efbd5.geojson | source-terms-not-recorded
vcc-site-a39bc0fe88ed4e44ee52 | imported:semiconductor-atlas:meta-bowling-green | Meta Bowling Green data center | United States | US | 41.4743 | -83.6661 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Township point from OpenStreetMap Nominatim. BG Independent places the adjacent power plant at the northeast corner of Ohio 582 and Mercer Road, but no source gives the data center parcel itself."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["815af14a-2c15-522b-a396-8c38b60d9cf0"] | 1 | ["619c5358-cf99-5e82-a690-4ae5c58f07f1"] | ["imported:semiconductor-atlas:meta-bowling-green"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a39bc0fe88ed4e44ee52/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a39bc0fe88ed4e44ee52.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a39bc0fe88ed4e44ee52.geojson | source-terms-not-recorded
vcc-site-a4bfb4274cc4e48492b6 | imported:semiconductor-atlas:cavour-trino | Cavour Hyperscale Campus (Trino) | Italy | IT | 45.2521 | 8.1939 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Coordinates of the former Galileo Ferraris thermoelectric plant (frazione Leri Cavour, Trino) from its Italian Wikipedia article; the campus boundary has not been published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["b6f06cee-d9d3-5814-9501-bf553666503b"] | 1 | ["b3d41aee-bf24-5299-97dd-2e16bc40012e"] | ["imported:semiconductor-atlas:cavour-trino"] | ["announced"] | 2026-07-27 | 2026-07-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a4bfb4274cc4e48492b6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a4bfb4274cc4e48492b6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a4bfb4274cc4e48492b6.geojson | source-terms-not-recorded
vcc-site-a51d60551e72a6720e31 | imported:semiconductor-atlas:meta-cheyenne | Meta Cheyenne data center | United States | US | 41.14 | -104.8202 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City point from OpenStreetMap Nominatim; Meta names Cheyenne but gives no site or road."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a544ab6b-cf2e-55b9-9593-f91850151e15"] | 1 | ["da9fec8b-b7a1-54cb-afb9-7f534cbab584"] | ["imported:semiconductor-atlas:meta-cheyenne"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a51d60551e72a6720e31/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a51d60551e72a6720e31.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a51d60551e72a6720e31.geojson | source-terms-not-recorded
vcc-site-a54941d2855e5bc71a3b | curated:nextdc-ge1-geelong | NEXTDC GE1 Geelong Data Center Campus | Australia | AU | -38.0561 | 144.3727 | Point | ["campus"] | ["exact_official_primary_virtual_address_point_with_explicit_campus_identity_inference"] | ["preserve_Vicmap_PFI215512998_point_response_in_EPSG4326_for_exact_official_Next_DC_Corio_application_address"] | ["official_virtual_address_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact virtual address point for 148-158 O'Brien's Road, Corio; the government Next DC application supplies Lot6 PS615585P. The GE1 code association comes from matching the operator's named Corio facility and is explicit analyst inference for independent review. Not the rejected Geelong city-center marker, Lovely Banks landbank, surveyed entrance, campus boundary or active-work footprint."] |  | No feature-specific quantitative positional-accuracy estimate is supplied by the selected point source. Coordinate digits are retained without asserting survey accuracy. | ["21e4e740-9c6e-5115-996c-3aa378a2f590","2ebacc55-15b9-5a33-b96e-3c51676e39c8","a5f4e2d6-95ca-5cc3-be57-aeb381fdf2ab","b522ac80-5fe4-592c-b147-223fb992336b","d023a91d-b0e7-5468-a30f-b28d6db4714c"] | 1 | ["e39b5191-4a78-5781-8944-24efaf944aa9"] | ["curated:nextdc-ge1-geelong:incremental-in-progress-fit-out"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a54941d2855e5bc71a3b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a54941d2855e5bc71a3b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a54941d2855e5bc71a3b.geojson | CC-BY-4.0
vcc-site-a55b68896de9ae43657e | imported:semiconductor-atlas:datavolt-oxagon | DataVolt Oxagon AI data centre campus (NEOM) | Saudi Arabia | SA | 27.5679 | 35.546 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Oxagon in NEOM but not a parcel. Coordinates are the OpenStreetMap Nominatim result for Oxagon (a construction land-use area in Duba governorate, Tabuk region)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ec1bd3eb-3559-5ed2-a446-9a875bd7abfe"] | 1 | ["016877e7-a475-5ebe-9219-0ac699cfff53"] | ["imported:semiconductor-atlas:datavolt-oxagon"] | ["under_construction"] | 2026-09-07 | 2026-09-07 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a55b68896de9ae43657e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a55b68896de9ae43657e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a55b68896de9ae43657e.geojson | source-terms-not-recorded
vcc-site-a94efdae4ca44082dd5e | imported:semiconductor-atlas:art-data-centres-ennis | Art Data Centres Ennis campus | Ireland | IE | 52.8463 | -8.9807 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Ennis town centroid from its Wikipedia article. Clare FM places the site beside the Tulla Road on the town's eastern side near M18 junction 13, but no cited source gives coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["80ea5db6-fbbf-5202-8504-3c045fc73ac8"] | 1 | ["917342c6-069b-5678-bf52-e27fcf933a5a"] | ["imported:semiconductor-atlas:art-data-centres-ennis"] | ["announced"] | 2026-03-25 | 2026-03-25 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a94efdae4ca44082dd5e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a94efdae4ca44082dd5e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a94efdae4ca44082dd5e.geojson | source-terms-not-recorded
vcc-site-a9577b8feaea08be317c | wikidata:Q136745002 | Google Data Center, Elmina Business Park | Malaysia | MY | 3.2226 | 101.5197 | Point | ["campus"] | ["community_named_entity_source_point"] | ["literal_Wikidata_P625_Earth_WGS84_coordinate_no_transform"] | ["community_named_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["Exact numeric point from named community entity Q136745002, used only as a first-campus reference locator. Source precision field is 1e-8 degree and the stored decimals are retained; neither is surveyed accuracy. Not an official point, OSM feature, boundary, entrance, parcel centroid, building footprint or observed-work extent."] |  | No positional accuracy or coordinate reference is supplied by the community entity. Its precision parameter describes model resolution only; independent survey accuracy remains unknown. | ["2064a4dc-8fc1-50cb-a098-994f6139abe4","21a7143e-0bd4-5c77-9527-9029d461b655","56e6290e-d33c-5ac2-8023-3be6b6550dd2"] | 1 | ["e56ff51f-930c-5c5b-bc82-7add264e576e"] | ["curated:google-elmina-business-park-data-center:current-campus-build"] | ["under_construction"] | 2026-08-15 | 2026-08-15 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a9577b8feaea08be317c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a9577b8feaea08be317c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a9577b8feaea08be317c.geojson | CC-BY-SA-4.0; CC0-1.0
vcc-site-a982e0093e476f44e98f | curated:capitaland-dc-chennai-ambattur | CapitaLand DC Chennai Ambattur Campus | India | IN | 13.1115 | 80.1603 | Polygon | ["campus"] | ["source_KML_project_polygon_XY_preserved"] | ["PARIVESH_original_CAF128123_2023_active_Project_Site_KML_WGS84_lonlat_no_transform"] | ["proponent_submitted_environmental_project_polygon"] | ["official_source"] | ["campus_locator"] | ["Original source polygon vertices, not the conflicting CAF extent labels or an arithmetic midpoint. Government-hosted proponent filing establishes a project-specific campus locator, not cadastral or surveyed boundary accuracy. Exact source decimal tuples are retained with the evidence. The separate display anchor is the planar centroid of this source polygon, independently verified inside it; it is not a publisher point, entrance, surveyed location or replacement geometry."] |  | Neither the proponent KML nor the public CAF states a positional-accuracy estimate, survey method, geodetic realization or control points. Decimal count and government hosting do not establish survey accuracy. | ["1c75ed75-477d-5d59-9337-803500086218","78987995-0a72-5638-b0ef-a4d6e2f00341","7ab9223a-89b0-539f-af5c-4fb159cad681"] | 1 | ["d852bc01-c8e9-57c4-b469-9ff3ea1d8a5c"] | ["curated:capitaland-dc-chennai-ambattur:current-facility-build"] | ["under_construction"] | 2026-07-29 | 2026-07-29 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a982e0093e476f44e98f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a982e0093e476f44e98f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-a982e0093e476f44e98f.geojson | no-open-license-asserted
vcc-site-aa53021c0d413ab5dd3d | curated:flexential-parker-compark-campus | Flexential Parker Compark Campus | United States | US | 39.5609 | -104.8119 | Point | ["project"] | ["official_census_street_address_range_interpolation"] | ["exact_official_postal_address_Census_NAD83_to_WGS84_pyproj_3_8_0"] | ["official_project_street_address_locator"] | ["official_source"] | ["project_locator"] | ["Census interpolation for exact 15255 Compark Blvd, bound by Town Flexential DEN12 record and county postal alias. Not a campus centre, surveyed point, building footprint, parcel boundary, entrance or active-work extent. No county coordinate selected."] |  | No source-specific numeric horizontal accuracy published for the address-range interpolation. | ["01d2faf8-1fe2-5401-9411-3486a52fa477","03627a5f-061f-575a-8f9f-a0431558c660","55324d0e-6884-5efa-b6a9-a0a7bc5a752f"] | 1 | ["8dbc82d0-1a4d-5d8e-955e-c5e4973ea19e"] | ["curated:flexential-parker-compark-campus:first-data-center"] | ["under_construction"] | 2026-08-18 | 2026-08-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-aa53021c0d413ab5dd3d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-aa53021c0d413ab5dd3d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-aa53021c0d413ab5dd3d.geojson | no-open-redistribution-license-asserted
vcc-site-ab1cba1760d42b280cd1 | imported:semiconductor-atlas:aws-vicksburg-warren-county-mississippi | AWS Vicksburg data center campus | United States | US | 32.3525 | -90.8775 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["No site, parcel or road has been published; coordinates are the Vicksburg city point from its Wikipedia article (Nominatim was unavailable)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6323bbc2-696d-588a-97e0-2b98b39e0897"] | 1 | ["077a5970-0684-5ef0-8320-65efbf78c960"] | ["imported:semiconductor-atlas:aws-vicksburg-warren-county-mississippi"] | ["announced"] | 2026-04-09 | 2026-04-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ab1cba1760d42b280cd1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ab1cba1760d42b280cd1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ab1cba1760d42b280cd1.geojson | source-terms-not-recorded
vcc-site-acf731facf63970bd84b | imported:semiconductor-atlas:nebius-independence-missouri | Nebius Independence AI factory | United States | US | 39.0925 | -94.4139 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City centroid from the Wikipedia infobox for Independence (s3). The groundbreaking release places the roughly 400-acre site in eastern Independence and the project page puts it at Route 78 and Little Blue Parkway, but no geocoder was used, so the point is the city centroid rather than the site. The city spans Jackson and Clay counties, so no county is given."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c"] | 1 | ["c01906b8-f76a-5afe-ae86-ea56184443f3"] | ["imported:semiconductor-atlas:nebius-independence-missouri"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-acf731facf63970bd84b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-acf731facf63970bd84b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-acf731facf63970bd84b.geojson | source-terms-not-recorded
vcc-site-ad58c35abfe93060c2c2 | imported:semiconductor-atlas:datavita-lanarkshire-ai-growth-zone | DataVita Lanarkshire AI Growth Zone campus (Chapelhall) | United Kingdom | GB | 55.835 | -3.9444 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["The UK government places the site in Airdrie; DataVita locates the DV4 expansion at Lancaster Avenue, Chapelhall, next to its existing DV1 and DV3. Coordinates are an approximate point near Lancaster Avenue; individual building plots were not identified."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["63c621be-5d2c-562b-80ca-84dd7a6d2ca5"] | 1 | ["d63cbbf2-d501-5bf8-83d4-befc76c4bb39"] | ["imported:semiconductor-atlas:datavita-lanarkshire-ai-growth-zone"] | ["under_construction"] | 2026-09-02 | 2026-09-02 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ad58c35abfe93060c2c2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ad58c35abfe93060c2c2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ad58c35abfe93060c2c2.geojson | source-terms-not-recorded
vcc-site-ad9a83cc2040a19f7750 | imported:semiconductor-atlas:cipher-barber-lake | Cipher Barber Lake data center | United States | US | 32.3961 | -100.8622 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from Wikipedia; Cipher places the Barber Lake site in Colorado City but gives no address or county."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["51b65782-8eb9-5ff6-8178-9322da57ed43"] | 1 | ["8fc14c03-d70a-5634-81e4-883a2fd6eec9"] | ["imported:semiconductor-atlas:cipher-barber-lake"] | ["under_construction"] | 2026-09-25 | 2026-09-25 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ad9a83cc2040a19f7750/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ad9a83cc2040a19f7750.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ad9a83cc2040a19f7750.geojson | source-terms-not-recorded
vcc-site-af1774a8d4eb3398e76e | imported:semiconductor-atlas:koacc-national-ai-computing-center-haenam | National AI Computing Center, Solaseado (Haenam) | Korea, Republic of | KR | 34.5742 | 126.5975 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Sources place the site in the Solaseado data center park in Sani-myeon, Haenam County, without coordinates; the point is the Haenam County coordinate from its Wikipedia article, so it marks the county, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["4c353195-1c08-58a5-88f0-fc05ceac97af"] | 1 | ["ddaae950-1e47-58e8-b57a-37aeed0eba7a"] | ["imported:semiconductor-atlas:koacc-national-ai-computing-center-haenam"] | ["under_construction"] | 2026-08-03 | 2026-08-03 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-af1774a8d4eb3398e76e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-af1774a8d4eb3398e76e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-af1774a8d4eb3398e76e.geojson | source-terms-not-recorded
vcc-site-af26df3b9a306efc763c | curated:merlin-lisbon-data-center-campus | MERLIN Lisbon Data Center Campus | Portugal | PT | 38.9883 | -8.9637 | Point | ["campus"] | ["operator_published_literal_site_coordinates"] | ["operator_published_literal_site_coordinates"] | ["operator_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The point identifies the campus, not the boundary or centroid of either Phase II building. Positional accuracy and survey provenance are not stated. The Edged Lisbon page prints these literal coordinates directly beneath its Lisbon Campus heading. MERLIN's named Lisbon campus page and its Phase II results disclosures identify the same Castanheira do Ribatejo campus. No redirect resolution is needed for the explicitly printed point."] |  | Neither source states quantitative positional accuracy or survey provenance; coordinate digits are not an accuracy estimate. | ["bad12459-311d-512a-aca2-716918af6b40"] | 1 | ["43ded2e8-5dcf-5174-b553-a4a04aaeebe3"] | ["curated:merlin-lisbon-data-center-campus:phase-2-two-building-development"] | ["under_construction"] | 2026-07-27 | 2026-07-27 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-af26df3b9a306efc763c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-af26df3b9a306efc763c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-af26df3b9a306efc763c.geojson | all-rights-reserved
vcc-site-afb6c00afe427fdacc70 | curated:digital-edge-edge2-jakarta | Digital Edge EDGE2 Jakarta Campus | Indonesia | ID | -6.214 | 106.8351 | Polygon | ["campus"] | ["Exact OSM way1230327255 ordered node ring; display-only anchor is the mean of four unique corners of this parallelogram."] | ["copy_named_community_building_source_nodes_in_way_order_without_digitizing_or_geocoding"] | ["community_mapped_constituent_building_outline"] | ["community_source"] | ["campus_locator"] | ["Source node coordinates retain seven decimal places. The mapped existing EDGE2 building locates one physical campus with phase3 electrical/mechanical construction; it is not an official cadastral or campus boundary, a surveyed footprint or the current work extent. Separate EDGE1, CGK, DGE1 and DGE2 are not merged. The brochure point remains rejected and source-map precision is not measured accuracy."] |  | OSM does not supply a survey method or quantitative positional accuracy for this feature. Numeric precision and agreement with earlier snapshots do not establish accuracy. | ["4371c850-3ed4-546a-9cb0-d238c412defe","60295470-6e35-5151-ae6c-7ff84481ab48","cf259b6f-4018-5021-88f7-3317999d6359"] | 1 | ["c7eebc15-358c-5985-9a48-16f53bdd4726"] | ["curated:digital-edge-edge2-jakarta:phase-3-electrical-mechanical-build"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-afb6c00afe427fdacc70/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-afb6c00afe427fdacc70.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-afb6c00afe427fdacc70.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-b020cba78b5fa2123866 | imported:semiconductor-atlas:dayone-chonburi-tech-park | DayOne Chonburi Tech Park (CTP) data center campus | Thailand | TH | 13.217 | 101.183 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin1"] | ["compiled_reference"] | ["admin1_context"] | ["Sources place the campus in the AMATA City estate in Chonburi province but give no district or address. The point is the province coordinate from the Chonburi province Wikipedia article, so it marks the province, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3ec56c55-c7d6-5540-9496-65bd267bfc8b"] | 1 | ["e934864d-423f-5afa-a9a8-09bd05079ee1"] | ["imported:semiconductor-atlas:dayone-chonburi-tech-park"] | ["under_construction"] | 2026-04-26 | 2026-04-26 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b020cba78b5fa2123866/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b020cba78b5fa2123866.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b020cba78b5fa2123866.geojson | source-terms-not-recorded
vcc-site-b065c16b51237fbb767f | curated:amazon-salem-township-innovation-campus | Amazon Salem Township Innovation Campus | United States | US | 41.084 | -76.1434 | Polygon | ["campus"] | ["cross_source_overlay"] | ["openstreetmap_named_addressed_aws_building_polygon_as_campus_locator"] | ["reviewed_openstreetmap_named_addressed_aws_data_centre_building_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped polygon for one named and addressed Amazon AWS data-centre building, used only to locate the Salem Township innovation campus. It is not an official campus boundary, the complete campus extent, a parcel, the active-buildout footprint or centroid, a construction extent, a current-building count, or a survey-accuracy claim."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | ["13a65a07-1b3a-58a3-9ca7-b98723686f7c"] | 2 | ["c73ac912-e44d-5477-84f5-c5beb4813518","dc6f83d9-dac5-563a-ba7e-ff18e27ba506"] | ["curated:amazon-salem-township-innovation-campus:active-buildout","imported:semiconductor-atlas:aws-salem-township-pennsylvania"] | ["partially_operational","under_construction"] | 2026-07-19 | 2026-10-09 | mixed_review_postures | FALSE | ["not_reviewed","tracked_identity_bound_uncertain_unsuperseded_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b065c16b51237fbb767f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b065c16b51237fbb767f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b065c16b51237fbb767f.geojson | ODbL-1.0
vcc-site-b12dddd73cb490c6bb64 | curated:scala-praia-do-futuro-campus | Scala Praia do Futuro Campus | Brazil | BR | -3.7515 | -38.458 | Polygon | ["project"] | ["direct_geometry"] | ["authoritative_surveyed_project_boundary"] | ["surveyed_project_boundary"] | ["official_source"] | ["official_boundary"] | ["Polygon transformed from the four surveyed project-boundary vertices in the official municipal plan; 5 metre stated uncertainty."] | 5 |  | ["295b555a-ca97-5752-b525-24ab75f62a71"] | 1 | ["b5625b8f-5e00-5fbe-b313-ba7adb980583"] | ["curated:scala-praia-do-futuro-campus:sforpf01"] | ["under_construction"] | 2026-08-04 | 2026-08-04 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | ["tracked_blind_ambiguous_locally_unsealed_identity_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b12dddd73cb490c6bb64/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b12dddd73cb490c6bb64.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b12dddd73cb490c6bb64.geojson | all-rights-reserved
vcc-site-b25b924e3e107c2cbaf1 | curated:atnorth-swe02-stockholm-campus | atNorth SWE02 Stockholm Campus | Sweden | SE | 59.4202 | 17.9191 | Point | ["project"] | ["direct_geometry"] | ["official_stockholm_project_map_epsg3011_point_transformed_to_wgs84"] | ["official_municipal_project_map_reference_point"] | ["official_source"] | ["project_locator"] | ["Official municipal project-page point transformed deterministically from EPSG:3011 to EPSG:4326. Decimal precision and sub-nanometre software roundtrip do not imply source survey accuracy."] |  | The municipal page publishes projected coordinates but no surveyed reference feature, collection method, or numeric horizontal accuracy. | ["ad0c7dc7-a25c-56d6-a190-734216237c6a"] | 1 | ["def7f329-a075-519e-bc4b-8f8126bc1901"] | ["curated:atnorth-swe02-stockholm-campus:current-development"] | ["under_construction"] | 2026-06-09 | 2026-06-09 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b25b924e3e107c2cbaf1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b25b924e3e107c2cbaf1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b25b924e3e107c2cbaf1.geojson | rights-status-not-established
vcc-site-b2ce7bc4242acd906a7b | curated:iron-mountain-lon-3-london-data-center | Iron Mountain LON-3 London Data Center | United Kingdom | GB | 51.5202 | -0.62006 | Point | ["campus"] | ["official_environmental_report_site_grid_reference"] | ["EPSG_27700_to_EPSG_4326_always_xy_with_documented_OSGB36_transform"] | ["official_environmental_report_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The report's National Grid Reference locates the LON3 site at 111 Buckingham Avenue. It is not a parcel, building centre, full Slough campus boundary or observed construction extent. LON1, LON2 and LON3 campus relationships do not create separate site additions."] |  | No source-specific numeric horizontal accuracy is published; transform operation accuracy is not site-locator uncertainty. | ["dc67d965-3723-5231-ac1f-ca26516929b0"] | 1 | ["825dd9ee-ffe9-525e-8d9f-ec8e370d9944"] | ["curated:iron-mountain-lon-3-london-data-center:25mw-build"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b2ce7bc4242acd906a7b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b2ce7bc4242acd906a7b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b2ce7bc4242acd906a7b.geojson | all-rights-reserved
vcc-site-b2e02b9541ac2f2a5b20 | imported:semiconductor-atlas:compass-hoffman-estates | Compass Datacenters Hoffman Estates campus | United States | US | 42.0639 | -88.1469 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Hoffman Estates. The campus occupies the former Sears headquarters site in the village; no cited source gives site coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2099b779-9d76-5a88-a84f-0c239664a1e0"] | 1 | ["a1696719-0fe3-52ce-ad37-43e6d2215f4f"] | ["imported:semiconductor-atlas:compass-hoffman-estates"] | ["under_construction"] | 2026-10-06 | 2026-10-06 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b2e02b9541ac2f2a5b20/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b2e02b9541ac2f2a5b20.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b2e02b9541ac2f2a5b20.geojson | source-terms-not-recorded
vcc-site-b38b02f920b409f27698 | curated:colt-london-hayes-campus | Colt London Hayes Campus | United Kingdom | GB | 51.5096 | -0.39409 | Polygon | ["building"] | ["capture_replayed_geometry"] | ["capture_replayed_openstreetmap_exact_colt_london4_named_building_polygon_as_project_locator"] | ["community_mapped_named_colt_london4_building_polygon"] | ["community_mapped"] | ["project_locator"] | ["Contributor-mapped polygon for the exact named London 4 building, used only to locate the selected facility-build project. It is not an official building footprint, parcel, complete present or future campus boundary, five-building plan, security boundary, or current construction-progress extent."] |  | OpenStreetMap supplies no survey, cadastral, planning-boundary, or numeric horizontal-accuracy statement. | ["c0b3ca09-1341-5395-9301-9f6a2d67cf0c"] | 1 | ["0bac3fe4-c3dd-54ba-a500-e37599191432"] | ["curated:colt-london-hayes-campus:london4-current-facility-build"] | ["under_construction"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b38b02f920b409f27698/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b38b02f920b409f27698.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b38b02f920b409f27698.geojson | ODbL-1.0
vcc-site-b3a2be1a532755abcfa9 | imported:semiconductor-atlas:tbc-partners-cambois | TBC Partners Cambois data centre campus | United Kingdom | GB | 55.1453 | -1.5309 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["The site is on Factory Road, Cambois, beside the A189 just south of the River Wansbeck. Nominatim did not resolve Factory Road, so the Cambois village centroid is used."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["07eeb2a7-7bc4-59bf-953c-00879a92180d"] | 1 | ["81d20134-d073-5e0c-ad1c-7f8a97f2dadb"] | ["imported:semiconductor-atlas:tbc-partners-cambois"] | ["proposed"] | 2026-08-18 | 2026-08-18 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b3a2be1a532755abcfa9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b3a2be1a532755abcfa9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b3a2be1a532755abcfa9.geojson | source-terms-not-recorded
vcc-site-b414ed2a7f2e60f4b886 | curated:stack-bossier-highway-3-technology-park-campus | STACK Bossier Highway 3 Technology Park Campus | United States | US | 32.7556 | -93.7357 | Point | ["campus"] | ["Extract the named smaller Project Site path from the government-published applicant map; interpolate its PDF positions through the four embedded source-CRS controls, explicitly normalize the self-touching ring, take an interior representative point in source projected units, transform without ballpark operations and round the locator to five decimals."] | ["interior_point_of_named_project_map_vector_path_using_embedded_geospatial_pdf_controls"] | ["derived_point_within_named_applicant_project_area"] | ["official_source"] | ["campus_locator"] | ["Five-decimal longitude/latitude locator derived from the specifically named Project Site, not from the larger landholding or viewport. Official source means the government-published applicant submission, not Corps survey certification. This is not a surveyed building, entrance, parcel centroid, campus boundary, verified construction footprint or observed work location. Extra intermediate digits are computational precision; the two-metre datum-operation accuracy is not source positional accuracy."] |  | The applicant drawing provides no quantitative survey or positional-accuracy estimate. Embedded five-decimal geographic controls, vector-page precision, interpolation consistency and datum-operation accuracy do not establish the accuracy of the drawing or derived locator. | ["1839db3d-9273-53fc-8afb-de73b478e26d","2990174e-9cc5-5129-9c06-7fd46477a9b0"] | 1 | ["cbe074bd-68d8-59cb-aaf7-e21fa82b193f"] | ["curated:stack-bossier-highway-3-technology-park-campus:current-campus-build"] | ["under_construction"] | 2026-06-10 | 2026-06-10 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b414ed2a7f2e60f4b886/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b414ed2a7f2e60f4b886.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b414ed2a7f2e60f4b886.geojson | all-rights-reserved; no-open-redistribution-license-asserted-for-applicant-map
vcc-site-b74f3c274a5a8c1e01da | imported:semiconductor-atlas:microsoft-aragon-villamayor-de-gallego | Microsoft Villamayor de Gállego datacenter campus (Aragón) | Spain | ES | 41.6857 | -0.774 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Municipality centroid from Nominatim. Sources place the campus on Villamayor de Gállego land associated with the Polígono Malpica, whose named substation (Malpica) serves it; the parcel itself is not identified."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["e35f6456-545d-588b-96a4-06edc7861eec"] | 1 | ["ec8c635b-93db-5c3c-904e-820b7c4f1233"] | ["imported:semiconductor-atlas:microsoft-aragon-villamayor-de-gallego"] | ["announced"] | 2026-09-04 | 2026-09-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b74f3c274a5a8c1e01da/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b74f3c274a5a8c1e01da.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b74f3c274a5a8c1e01da.geojson | source-terms-not-recorded
vcc-site-b80c969b486b2844a8d9 | imported:semiconductor-atlas:iren-childress | IREN Childress data center campus | United States | US | 34.4281 | -100.215 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City coordinates from Wikipedia; IREN names the site after Childress but publishes no street address or county."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a6ebeceb-ddd9-5507-b6d7-40f1189162b4"] | 1 | ["b74385b8-0724-5b4d-b192-4aa5a1c45885"] | ["imported:semiconductor-atlas:iren-childress"] | ["partially_operational"] | 2026-08-27 | 2026-08-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b80c969b486b2844a8d9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b80c969b486b2844a8d9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b80c969b486b2844a8d9.geojson | source-terms-not-recorded
vcc-site-b83e933ca77e513685ed | imported:semiconductor-atlas:airtrunk-jhb1-johor | AirTrunk JHB1 | Malaysia | MY | 1.5367 | 103.7206 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["AirTrunk places JHB1 in Johor Bahru without an address; coordinates are the OpenStreetMap Nominatim centroid of the Johor Bahru administrative area, which includes Iskandar Puteri."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d520bc9c-46a1-5e00-8e7a-5cc2803873fd"] | 1 | ["abb5573d-8211-5781-be5c-50c8b27d4fe8"] | ["imported:semiconductor-atlas:airtrunk-jhb1-johor"] | ["partially_operational"] | 2024-08-09 | 2024-08-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b83e933ca77e513685ed/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b83e933ca77e513685ed.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b83e933ca77e513685ed.geojson | source-terms-not-recorded
vcc-site-b8522efc1a60fe3072e4 | curated:meta-sturgeon-county-alberta-data-center | Meta Sturgeon County Alberta Data Center | Canada | CA | 53.8181 | -113.1867 | Point | ["project"] | ["official_parcel_union"] | ["official_permit_units_representative_point"] | ["representative_point_of_partial_permit_envelope"] | ["official_source"] | ["project_locator"] | ["Representative point of the deterministic union of 11 official ATS quarter sections named by DP-26-0028; Shapely 2.1.2/GEOS 3.13.1 unary_union followed by representative_point. It is a partial permit-envelope locator, not the full project boundary, parcel survey, building, or work area."] |  | The selected permit units include road allowances and non-quarter cadastral identifiers that are not represented by the 11 queried quarter-section polygons. | ["e049970c-d467-5fc5-9e5c-6660606eb9be"] | 1 | ["d1538d73-e301-5203-9e49-924b20051374"] | ["curated:meta-sturgeon-county-alberta-data-center:current-campus-build"] | ["under_construction"] | 2026-07-08 | 2026-07-08 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b8522efc1a60fe3072e4/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b8522efc1a60fe3072e4.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-b8522efc1a60fe3072e4.geojson | Open-Government-Licence-Alberta
vcc-site-ba5a5fcafa0e68a3bbc8 | imported:semiconductor-atlas:sdaia-hexagon-riyadh | Hexagon Data Center (Riyadh) | Saudi Arabia | SA | 24.633 | 46.717 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City coordinates from the Riyadh Wikipedia page; the sources do not name a district."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6627618c-e97b-5d09-b2b1-ccc30c1d176b"] | 1 | ["912a1942-9e25-5d1f-b3ce-7f39f60ca845"] | ["imported:semiconductor-atlas:sdaia-hexagon-riyadh"] | ["under_construction"] | 2026-05-01 | 2026-05-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ba5a5fcafa0e68a3bbc8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ba5a5fcafa0e68a3bbc8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ba5a5fcafa0e68a3bbc8.geojson | source-terms-not-recorded
vcc-site-bae4ad7e597cccb0da1d | curated:macquarie-ic3-super-west-facility | Macquarie IC3 Super West Facility | Australia | AU | -33.781 | 151.127 | Polygon | ["project"] | ["cross_source_geometry"] | ["openstreetmap_ic3_super_west_full_development_polygon_as_parent_facility_campus_locator"] | ["reviewed_openstreetmap_ic3_super_west_full_development_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped full-development polygon for Intellicentre 3 Super West, used only to locate the parent IC3 Super West facility/campus. It is not specific to the nested Phase 1 fitted-out scope, and it is not an official planning, cadastral, parcel, building, current-construction, or phase boundary."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | ["7b2675bd-76c0-54b0-82d1-3f5d6cb328b2"] | 1 | ["ea4a0cc5-bb09-5a81-b385-38ae79baf22a"] | ["curated:macquarie-ic3-super-west-facility:phase-1-build"] | ["under_construction"] | 2026-07-17 | 2026-07-17 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bae4ad7e597cccb0da1d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bae4ad7e597cccb0da1d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bae4ad7e597cccb0da1d.geojson | ODbL-1.0
vcc-site-bb743c7caad1e739c23e | curated:keppel-genting-lane-data-centre-campus | Keppel Genting Lane Data Centre Campus | Singapore | SG | 1.3254 | 103.8766 | Polygon | ["campus"] | ["Exact OSM way 1560974456 ordered node ring; display anchor is the planar shoelace centroid of that ring."] | ["copy_named_community_campus_source_nodes_in_way_order_without_digitizing_or_geocoding"] | ["community_mapped_named_campus_outline"] | ["community_source"] | ["campus_locator"] | ["Source node coordinates are retained as serialized. The named fenced campus locates the Genting Lane campus containing operating SGP 7 and SGP 8 and the SGP 9 build; it is not an official boundary, surveyed footprint or current work extent."] |  | OSM supplies no survey method or positional accuracy for this feature. | ["491b3b57-f2fb-53b4-ad33-07902a6d2e19","55851feb-fc9d-51f3-ab77-030da1cbf8a2"] | 1 | ["04b22725-af3a-5d12-b2b6-0caf17b0c39e"] | ["curated:keppel-genting-lane-data-centre-campus:keppel-dc-sgp-9-current-build"] | ["under_construction"] | 2026-07-30 | 2026-07-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bb743c7caad1e739c23e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bb743c7caad1e739c23e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bb743c7caad1e739c23e.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-bb97e3ebf82c06ecfb2c | imported:semiconductor-atlas:adaniconnex-navi-mumbai | AdaniConneX Navi Mumbai data centre campus | India | IN | 19.0308 | 73.0199 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["The company names Navi Mumbai only. Coordinates are the OpenStreetMap Nominatim centroid of Navi Mumbai, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["e515e455-3532-5efd-a7b5-516691716bd7"] | 1 | ["96c80c6f-de7a-5e5c-b9b1-fc1bb7c738a6"] | ["imported:semiconductor-atlas:adaniconnex-navi-mumbai"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bb97e3ebf82c06ecfb2c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bb97e3ebf82c06ecfb2c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bb97e3ebf82c06ecfb2c.geojson | source-terms-not-recorded
vcc-site-bdf4718cb174c2faaaf4 | curated:cipher-digital-stingray-andrews-texas-data-center-campus | Cipher Digital Stingray Andrews Data Center Campus | United States | US | 32.3721 | -102.9824 | Point | ["campus"] | ["official_9_1_1_address_point_for_exact_primary_site_address"] | ["TxGIO_StratMap_address_point_query_by_full_addr_and_county_outSR4326_round7"] | ["official_address_point_for_campus_site_address"] | ["official_source"] | ["campus_locator"] | ["The official statewide 9-1-1 address point for the exact site address named by primary identity sources. It locates the campus address, not a data hall, phase, parcel boundary, footprint or current work extent. Source value rounded to seven decimals."] |  | TxGIO states that each authoritative 9-1-1 source applies its own point-placement guideline and policy (rooftop, parcel centroid or street centreline are not fixed) and publishes no positional accuracy for individual points. | ["1cafca44-f42f-5814-982a-730ce77686e5","ed8d464b-61d2-5e36-94ce-a362d05d4bbc"] | 1 | ["fa44cb24-5185-5616-a6a2-3977f190001f"] | ["curated:cipher-digital-stingray-andrews-texas-data-center-campus:current-build"] | ["under_construction"] | 2026-08-04 | 2026-08-04 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bdf4718cb174c2faaaf4/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bdf4718cb174c2faaaf4.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bdf4718cb174c2faaaf4.geojson | public-use-as-is
vcc-site-be615a0bc019c0f6d350 | curated:sabey-sdc-austin-round-rock-campus | Sabey SDC Austin Round Rock Campus | United States | US | 30.4858 | -97.651 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["b4bdfbf2-b320-5186-8978-0076403b94c3"] | 1 | ["ae484949-f575-5553-ad33-bc1f96eab345"] | ["curated:sabey-sdc-austin-round-rock-campus:building-b-current-build"] | ["shell"] | 2026-06-16 | 2026-06-16 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-be615a0bc019c0f6d350/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-be615a0bc019c0f6d350.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-be615a0bc019c0f6d350.geojson | public-domain-us-government
vcc-site-beb10377588af430b5a6 | imported:semiconductor-atlas:meta-gallatin-tennessee | Meta Gallatin Data Center | United States | US | 36.4085 | -86.3716 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Centroid of the area named Gallatin Data Center and tagged as Meta-operated in the local OpenStreetMap layer (way 1213758201); Meta-tagged data center buildings lie within about 500 m of it. Sources name only the city and county."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["dfa60568-7e3e-5a91-b7e4-a8639c511983"] | 1 | ["a203f1e3-768b-5094-b606-9c494490e0a6"] | ["imported:semiconductor-atlas:meta-gallatin-tennessee"] | ["partially_operational"] | 2024-11-15 | 2024-11-15 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-beb10377588af430b5a6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-beb10377588af430b5a6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-beb10377588af430b5a6.geojson | source-terms-not-recorded
vcc-site-bf298971fe1dec3fc0ac | imported:semiconductor-atlas:quantum-frederick | Quantum Frederick data center park | United States | US | 39.4311 | -77.3972 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of the city of Frederick (s5). Baxtel's listing beside the 2021 article (s1) gives a Manor Woods Road, Frederick address for the former Eastalco site, which lies outside the city; the park was not geocoded."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a690b130-039f-5489-af4c-cc5ffc583b78"] | 1 | ["a490f00a-8b75-5547-b0e9-5fb3b6e5f616"] | ["imported:semiconductor-atlas:quantum-frederick"] | ["under_construction"] | 2026-03-12 | 2026-03-12 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bf298971fe1dec3fc0ac/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bf298971fe1dec3fc0ac.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bf298971fe1dec3fc0ac.geojson | source-terms-not-recorded
vcc-site-bf829ea21a9d7386fb5f | imported:semiconductor-atlas:core-scientific-muskogee | Core Scientific Muskogee data center campus | United States | US | 35.7433 | -95.3567 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Core Scientific gives the street address 1525 West 43rd Street South, Muskogee. No geocoder was used, so coordinates are the Muskogee city point from its Wikipedia article, which also names the county."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["cfd03805-4a4b-5df9-9505-c6caaf3d7ca5"] | 1 | ["d87a919b-df32-53fa-bc01-47b7f6f1dce9"] | ["imported:semiconductor-atlas:core-scientific-muskogee"] | ["partially_operational"] | 2026-07-28 | 2026-07-28 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bf829ea21a9d7386fb5f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bf829ea21a9d7386fb5f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bf829ea21a9d7386fb5f.geojson | source-terms-not-recorded
vcc-site-bf97558b9c05a083995c | curated:nextdc-s3-sydney | NEXTDC S3 Sydney Data Center Campus | Australia | AU | -33.8191 | 151.1846 | Point | ["campus"] | ["community_exact_address_named_campus_representative_point"] | ["preserve_Nominatim_way1225879499_lat_lon_and_bind_S3_operator_URL_ref_and_exact_2_Broadcast_Way_address"] | ["community_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["The named S3 community feature includes exact operator, facility URL, ref S3 and 2 Broadcast Way address. Its Sidney spelling is a source label, not a new campus. Adjacent S6 is not separately counted. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate."] |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | ["22eac0e1-71fa-59dd-a6d7-4378a663ab9d","843db8e1-a763-56df-9e6d-d982efb9018c"] | 1 | ["8a5fbd17-48b6-5484-8c37-ce406068bf3e"] | ["curated:nextdc-s3-sydney:incremental-in-progress-fit-out"] | ["mep_electrical"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bf97558b9c05a083995c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bf97558b9c05a083995c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-bf97558b9c05a083995c.geojson | ODbL-1.0
vcc-site-c0945d7c74abf8504604 | curated:microsoft-new-albany-oh-datacenter | Microsoft New Albany Datacenter | United States | US | 40.1038 | -82.7535 | Point | ["campus"] | ["official_address_geocode"] | ["census_public_ar_current_street_range_interpolation"] | ["official_census_address_locator_point"] | ["official_source"] | ["campus_locator"] | ["Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position."] |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | ["35c41e3e-909b-57dd-b9a0-879467ec17cb"] | 1 | ["f8377a0f-dc89-5b7a-8257-25f25cdbac43"] | ["curated:microsoft-new-albany-oh-datacenter:initial-site-preparation"] | ["site_preparation"] | 2026-07-01 | 2026-07-01 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c0945d7c74abf8504604/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c0945d7c74abf8504604.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c0945d7c74abf8504604.geojson | public-domain-us-government
vcc-site-c14008c0552564c11274 | curated:dataone-vineland-ai-data-center-campus | DataOne Vineland Two-Phase AI Data Center Facility | United States | US | 39.4252 | -75.0135 | Polygon | ["campus"] | ["exact_single_public_municipal_parcel_ring_server_projected_with_explicit_epsg1188"] | ["municipal_block_lot_query_native_epsg3424_to_epsg4326"] | ["official_mapped_constituent_parcel_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Only the exact municipal mapped Block 7503 Lot 35.01 parcel is selected to locate the one campus shared by both phases. Not a surveyed cadastral boundary, complete campus boundary, security fence, Phase 2 building footprint or active-work extent. Derived display anchor is not an additional authoritative point. Old Lot 33.01 is not added or inferred merged."] |  | City expressly warns some GIS data use assumptions and estimates and supplies no numerical positional accuracy. Coordinate digits, projection agreement and transformation operation accuracy are not a survey-accuracy estimate. | ["1973e08d-0c30-5b25-a128-58ccfb617a19","62770f24-4458-5e79-8c07-46a66733c64f","66c81dd1-d72c-5dd4-b071-b870a6521026"] | 2 | ["38cbdb58-5ff7-504d-98be-60187be91e02","5ace12f8-658e-5956-9173-d78e625d4df9"] | ["curated:dataone-vineland-ai-data-center-campus:phase-2-expansion-current-build","imported:semiconductor-atlas:nebius-vineland-new-jersey"] | ["under_construction"] | 2026-08-07 | 2026-10-09 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c14008c0552564c11274/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c14008c0552564c11274.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c14008c0552564c11274.geojson | no-open-license-asserted
vcc-site-c1a0f58564147c78c139 | curated:digipowerx-columbiana-ai-data-center-campus | Digi Power X Columbiana AI Data Center Campus | United States | US | 33.1828 | -86.6185 | Point | ["campus"] | ["official_address_geocode"] | ["official_address_geocode"] | ["address_range_geocode"] | ["official_source"] | ["campus_locator"] | ["Exact returned Census coordinate for the project-linked street address; digits are not positional accuracy and the point is not parcel, rooftop, building, or work-area geometry."] |  | Census supplies an address-range geocode without a bounded horizontal error for this match. | ["8e34c085-5ca7-50e1-b460-ac5132c8439a"] | 1 | ["c794c146-24e6-5cb8-8cd9-a12a266bba83"] | ["curated:digipowerx-columbiana-ai-data-center-campus:purpose-built-flagship-vertical-build"] | ["shell"] | 2026-07-07 | 2026-07-07 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c1a0f58564147c78c139/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c1a0f58564147c78c139.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c1a0f58564147c78c139.geojson | US-federal-public-domain
vcc-site-c1a8be222fca1d1646d2 | curated:tecra-ome-shinmachi-9a | OME Data Center04 (Shinmachi9-A) | Japan | JP | 35.7828 | 139.3177 | Point | ["campus"] | ["direct_geometry"] | ["developer_selected_map_feature_coordinates"] | ["developer_selected_parent_parcel_locator"] | ["compiled_reference"] | ["campus_locator"] | ["Developer-selected mapped parent-parcel address point; not the exact subdivided data-center lot or new-building footprint."] |  | No positional accuracy stated. Locator identifies the parent property; the exact subdivided data-center parcel and building outline are not established numerically. | ["75fa711b-93d1-5930-ba55-8a741000f1c7"] | 1 | ["7b86e3a5-3492-5bb1-b47c-2010427939cd"] | ["curated:tecra-ome-shinmachi-9a:building"] | ["under_construction"] | 2026-07-15 | 2026-07-15 | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c1a8be222fca1d1646d2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c1a8be222fca1d1646d2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c1a8be222fca1d1646d2.geojson | all-rights-reserved
vcc-site-c2bcc9c77043eec23331 | imported:semiconductor-atlas:terranova-campinas | Terranova Campinas data centre campus | Brazil | BR | -22.8278 | -47.0797 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates of the Barão Geraldo district from its Wikipedia page; the campus is on the Fazenda Pau D'Alho property within the PIDS innovation zone, whose exact boundary was not located."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["41ac3df9-e6e7-5309-b711-87feefee4cf7"] | 1 | ["f533639a-f574-566d-a780-db81daa4b78c"] | ["imported:semiconductor-atlas:terranova-campinas"] | ["announced"] | 2026-08-26 | 2026-08-26 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c2bcc9c77043eec23331/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c2bcc9c77043eec23331.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c2bcc9c77043eec23331.geojson | source-terms-not-recorded
vcc-site-c2fa5b54c32ada55d1e4 | curated:odata-dc-sp04-osasco-campus | ODATA DC SP04 Osasco Campus | Brazil | BR | -23.4832 | -46.776 | Point | ["campus"] | ["first_party_published_map_pin"] | ["first_party_published_map_pin"] | ["operator_facility_pin"] | ["official_source"] | ["campus_locator"] | ["Operator-embedded terminal place-pin values, not the map viewport center and not a parcel or Phase 2 work footprint; decimal digits are not an accuracy claim."] |  | The embedded Google place pin carries no publisher-stated accuracy. | ["ec98aabb-2dd1-5a20-813a-cb4682042aa2"] | 1 | ["c160d8d5-7572-53c2-8051-cd7990b1f771"] | ["curated:odata-dc-sp04-osasco-campus:phase-2-expansion"] | ["under_construction"] | 2026-06-18 | 2026-06-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c2fa5b54c32ada55d1e4/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c2fa5b54c32ada55d1e4.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c2fa5b54c32ada55d1e4.geojson | all-rights-reserved-fact-extraction-only
vcc-site-c4475d593124b26a70cd | imported:semiconductor-atlas:adaniconnex-noida | AdaniConneX Noida data centre campus | India | IN | 28.57 | 77.32 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Noida only. Coordinates are the Noida city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d9f7e0af-ae46-5af6-9d9a-39f54b5b80fd"] | 1 | ["8c2ed321-ddad-5bb1-ab38-bd5b66bf4f2b"] | ["imported:semiconductor-atlas:adaniconnex-noida"] | ["partially_operational"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c4475d593124b26a70cd/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c4475d593124b26a70cd.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c4475d593124b26a70cd.geojson | source-terms-not-recorded
vcc-site-c48f4a7325dfc30566cd | curated:kao-data-harlow-campus | KAO Data Harlow Campus | United Kingdom | GB | 51.7701 | 0.1305 | Point | ["campus"] | ["coordinates_to_point"] | ["government_hosted_report_coordinate_conversion"] | ["government_report_campus_centre_point"] | ["official_source"] | ["reviewed_site_locator"] | ["Campus-centre point derived deterministically from EPSG:27700 easting 547101 and northing 210080 supplied by the government-hosted KLON-03 site report. It is not a parcel, campus boundary, KLON-03 building centroid or footprint, and the report states no horizontal positional accuracy."] |  | official source does not state positional accuracy | ["b133a4dc-126f-5e44-8841-f770b6fa9ad0"] | 1 | ["7206a400-093d-5c92-b1c5-c4243807de29"] | ["curated:kao-data-harlow-campus:klon-03-building"] | ["under_construction"] | 2026-05-26 | 2026-05-26 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["tracked_identity_bound_uncertain_with_unadjudicated_later_clear_conflict_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c48f4a7325dfc30566cd/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c48f4a7325dfc30566cd.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c48f4a7325dfc30566cd.geojson | all-rights-reserved
vcc-site-c51acbb151880f9815b8 | imported:semiconductor-atlas:aws-hobart-indiana | Amazon Web Services Hobart data center campus | United States | US | 41.5286 | -87.2675 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Hobart city coordinates from its Wikipedia page. The cited sources name the city but give no parcel or street location."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["0eda5c21-7b89-54f5-92a8-531e280f0d17"] | 1 | ["8d08b021-e457-5102-9ef2-33528ad786d1"] | ["imported:semiconductor-atlas:aws-hobart-indiana"] | ["announced"] | 2026-08-25 | 2026-08-25 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c51acbb151880f9815b8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c51acbb151880f9815b8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c51acbb151880f9815b8.geojson | source-terms-not-recorded
vcc-site-c5988379bc974f1f6240 | imported:semiconductor-atlas:microsoft-mount-pleasant-international-drive | Microsoft Mount Pleasant International Drive datacenter campus | United States | US | 42.7112 | -87.9339 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Nominatim point for International Drive in Mount Pleasant, the road the sources name for the campus; the parcel boundary is not published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["20fee728-51c4-598d-b3e8-3cf49887dbe3"] | 1 | ["96848e3f-da64-53c8-be33-bf5c9cd2109a"] | ["imported:semiconductor-atlas:microsoft-mount-pleasant-international-drive"] | ["announced"] | 2026-01-27 | 2026-01-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c5988379bc974f1f6240/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c5988379bc974f1f6240.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c5988379bc974f1f6240.geojson | source-terms-not-recorded
vcc-site-c606ab687ab04588148a | imported:semiconductor-atlas:pdg-jc4-bekasi | Princeton Digital Group JC4 Greater Jakarta | Indonesia | ID | -6.3836 | 107.1911 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["PDG places JC4 in the Greenland International Industrial Center (GIIC), Bekasi Regency, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the GIIC industrial estate and are shared with the nearby JC3 record."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["492bf081-e5dc-5500-97ce-502bfc37c051"] | 1 | ["42ae14a5-797b-5251-a05a-c9a12ddc6603"] | ["imported:semiconductor-atlas:pdg-jc4-bekasi"] | ["under_construction"] | 2026-04-30 | 2026-04-30 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c606ab687ab04588148a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c606ab687ab04588148a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c606ab687ab04588148a.geojson | source-terms-not-recorded
vcc-site-c61c3aef755484b5c52d | curated:green-campus-zrh1-lupfig | Green Campus ZRH1 Lupfig | Switzerland | CH | 47.4464 | 8.2108 | Polygon | ["campus"] | ["cross_source_overlay"] | ["openstreetmap_exactly_addressed_data_center_building_polygon_as_campus_locator"] | ["reviewed_openstreetmap_addressed_green_data_center_building_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped polygon for one data-center building at Green's exact first-party Campus ZRH1 address, used only to locate Campus ZRH1. It is not the DC4 footprint or centroid, the Campus ZRH1 boundary, a parcel, a construction extent, or a survey-accuracy claim."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | ["a488471c-6dc2-593f-92df-db707862cbfc"] | 1 | ["58129708-0b52-5984-afbc-f8f38e085df1"] | ["curated:green-campus-zrh1-lupfig:data-center-4"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c61c3aef755484b5c52d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c61c3aef755484b5c52d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c61c3aef755484b5c52d.geojson | ODbL-1.0
vcc-site-c879bad0c737049a2484 | curated:related-digital-cheyenne-campus | Related Digital Cheyenne Campus | United States | US | 41.1426 | -104.7015 | Point | ["campus"] | ["first_party_published_map_pin"] | ["first_party_published_map_pin"] | ["operator_project_map_point"] | ["official_source"] | ["campus_locator"] | ["Exact first-party Wyoming page coordinate, used only as a broad Cheyenne campus locator; not a parcel, Phase 1 building, or work footprint."] |  | Related Digital states no bounded accuracy for its embedded map coordinate. | ["9249d532-23ae-58da-bcd6-80cf09aaac30"] | 1 | ["31635fdf-a7a6-52c8-91dc-f64e5c7d10d3"] | ["curated:related-digital-cheyenne-campus:phase-1"] | ["under_construction"] | 2026-07-20 | 2026-07-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c879bad0c737049a2484/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c879bad0c737049a2484.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c879bad0c737049a2484.geojson | all-rights-reserved-fact-extraction-only
vcc-site-c9f14a3df329db2670d8 | imported:semiconductor-atlas:microsoft-mount-pleasant-durand-avenue | Microsoft Mount Pleasant Durand Avenue datacenter campus | United States | US | 42.6965 | -87.947 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Approximate point where Durand Avenue meets Hewitt Memorial Drive, the two roads Microsoft names for Phase 3, from Nominatim lookups of each road in Mount Pleasant. The 791-acre parcel boundary is not published in the sources."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["a5fe32e0-fc83-54bf-84bc-075b875d3693"] | 1 | ["7c5eed16-f5f1-515a-b9ee-b7c30754fc10"] | ["imported:semiconductor-atlas:microsoft-mount-pleasant-durand-avenue"] | ["under_construction"] | 2026-07-01 | 2026-07-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c9f14a3df329db2670d8/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c9f14a3df329db2670d8.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-c9f14a3df329db2670d8.geojson | source-terms-not-recorded
vcc-site-ca2269119237054941e1 | curated:colt-villebon-sur-yvette-campus | Colt Villebon-sur-Yvette Campus | France | FR | 48.691 | 2.22 | Polygon | ["project"] | ["direct_geometry"] | ["official_prefecture_and_municipal_project_to_dgfip_cadastral_parcel_polygon"] | ["official_cadastral_project_site_parcel_boundary"] | ["official_source"] | ["official_boundary"] | ["Official cadastral project-site parcel polygon used as the PAR2 project boundary. Its representative point is a deterministic planar centroid of the published WGS84 ring and lies inside the polygon; it is not an official cadastral point or survey-accuracy claim."] |  | The cadastral feature is authoritative parcel geometry but publishes no survey-grade or numeric horizontal-accuracy field for this feature. | ["2157a790-74df-5026-b2b6-58b1bb82519d"] | 1 | ["08d881e7-8a1c-50da-81a5-d2ef49f22a7a"] | ["curated:colt-villebon-sur-yvette-campus:paris2-current-facility-build"] | ["under_construction"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ca2269119237054941e1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ca2269119237054941e1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ca2269119237054941e1.geojson | etalab-2.0
vcc-site-ca4532d5353073b32508 | curated:ezditek-ruh01-pnu-riyadh-data-center | Ezditek RUH01/PNU Riyadh Data Center | Saudi Arabia | SA | 24.867 | 46.714 | Polygon | ["building"] | ["capture_replayed_geometry"] | ["capture_replayed_openstreetmap_exact_ezditek_ruh01_named_building_polygon_as_project_locator"] | ["community_mapped_named_ezditek_ruh01_building_polygon"] | ["community_mapped"] | ["project_locator"] | ["Contributor-mapped building polygon explicitly tagged operator=Ezditek, ref=RUH01, telecom=data_center, used only to locate the selected RUH01 Phase 1 project. It is not an official, cadastral, planning, survey, parcel, security, Phase 1, or current-construction boundary."] |  | OpenStreetMap supplies no survey, cadastral, planning-authority, or numeric horizontal-accuracy statement for this way. | ["b91493e8-2d06-5029-8df8-bfc06d77f418"] | 1 | ["010c4071-5901-54ea-a312-f59d53358a0a"] | ["curated:ezditek-ruh01-pnu-riyadh-data-center:phase-1-current-build"] | ["under_construction"] | 2026-06-18 | 2026-06-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ca4532d5353073b32508/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ca4532d5353073b32508.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ca4532d5353073b32508.geojson | ODbL-1.0
vcc-site-cb8ab0ad35bb603ea3ba | imported:semiconductor-atlas:meta-mesa-arizona | Meta Mesa Data Center | United States | US | 33.4222 | -111.8228 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Mesa city coordinates from its Wikipedia page, not the site. Sources give the street address (3841 S. Ellsworth Road, at the southeast corner of Elliot and Ellsworth Roads), but it was not converted to coordinates because no geocoder was used."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f2e0aa56-e925-51e3-94a6-43ac3a38be1c"] | 1 | ["8d3985c2-7777-5c6b-9a7f-fcab6c9b6a4f"] | ["imported:semiconductor-atlas:meta-mesa-arizona"] | ["partially_operational"] | 2025-01-31 | 2025-01-31 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cb8ab0ad35bb603ea3ba/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cb8ab0ad35bb603ea3ba.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cb8ab0ad35bb603ea3ba.geojson | source-terms-not-recorded
vcc-site-cc86e5f5e64a0438e8c1 | curated:lvrtc-pozitrons-kurzeme-data-center | LVRTC Pozitrons Kurzeme Data Center | Latvia | LV | 56.9356 | 22.0133 | Point | ["project"] | ["direct_geometry"] | ["authoritative_site_plan"] | ["parcel_reference_point"] | ["official_source"] | ["reviewed_site_locator"] | ["Government cadastral reference point for the reported 113,200 square metre project parcel; 300 metre stated uncertainty."] | 300 |  | ["a16dbcad-9b13-557e-9b38-46e3305bcc0e"] | 1 | ["e997ad94-2a62-5c44-90f9-fa27edf77dc2"] | ["curated:lvrtc-pozitrons-kurzeme-data-center:phase-1-current-build"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cc86e5f5e64a0438e8c1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cc86e5f5e64a0438e8c1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cc86e5f5e64a0438e8c1.geojson | CC-BY-4.0
vcc-site-cc8bbdad8c252d9ba4e2 | curated:akashi-astana-data-center-campus | Akashi Astana Data Center Campus | Kazakhstan | KZ | 51.2068 | 71.4577 | Point | ["project"] | ["direct_geometry"] | ["authoritative_site_plan"] | ["same_parcel_infrastructure_reference_point"] | ["official_source"] | ["reviewed_site_locator"] | ["Official site-plan point for a substation within the same data-centre parcel; 500 metre stated uncertainty and not a hall footprint."] | 500 |  | ["ff1fe928-217c-5369-8ab1-5dce1a637677"] | 1 | ["44130f9f-95af-5f19-9fcf-47aabd3a5c8b"] | ["curated:akashi-astana-data-center-campus:phase-1-current-build"] | ["under_construction"] | 2026-07-21 | 2026-07-21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cc8bbdad8c252d9ba4e2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cc8bbdad8c252d9ba4e2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cc8bbdad8c252d9ba4e2.geojson | no-license-stated-for-compact-factual-extraction
vcc-site-cd315d5cbb01f749da8f | imported:semiconductor-atlas:pw-digital-gateway | PW Digital Gateway | United States | US | 38.7947 | -77.6206 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Gainesville, Virginia. WTOP places the roughly 2,000-acre corridor along Pageland Lane near Gainesville, next to Manassas National Battlefield Park; the court describes three adjoining rezoning areas, so the site extends several kilometres from this point."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["aceb4a50-9fe3-5a13-9418-ac919e40d9ba"] | 1 | ["4ac7a0d0-0faf-50c0-bed8-08d54e0bc62b"] | ["imported:semiconductor-atlas:pw-digital-gateway"] | ["cancelled"] | 2026-07-04 | 2026-07-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cd315d5cbb01f749da8f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cd315d5cbb01f749da8f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cd315d5cbb01f749da8f.geojson | source-terms-not-recorded
vcc-site-cd3c4380161bc1c0389f | imported:semiconductor-atlas:wbs-power-baltic-data-center-campus | WBS Power Baltic Data Center Campus, Lublewo | Poland | PL | 54.7597 | 17.9453 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["The press release and Gramwzielone name the site as Lublewo in Choczewo municipality; neither uses the official name Lublewo Lęborskie. Wikipedia lists Lublewo Lęborskie as the only village called Lublewo in Gmina Choczewo (the other similar name is Lublewko), so its village coordinates are used, at locality precision. County is from Wikipedia. No cited source gives site coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["c8683395-ab3c-5394-9f84-9a6b854c57f6"] | 1 | ["4eea4b6a-9f71-5c9f-81bb-ae597972ddd5"] | ["imported:semiconductor-atlas:wbs-power-baltic-data-center-campus"] | ["announced"] | 2026-03-24 | 2026-03-24 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cd3c4380161bc1c0389f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cd3c4380161bc1c0389f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cd3c4380161bc1c0389f.geojson | source-terms-not-recorded
vcc-site-cde9b25f26b96465e0dd | curated:aws-thane-balkum-majiwada-campus | AWS Thane Balkum & Majiwada Data Centre Campus | India | IN | 19.218 | 72.9873 | Polygon | ["campus"] | ["source_KML_project_polygon_XY_preserved"] | ["PARIVESH_CAF157807_2024_active_Amazon_kml_placemark0_WGS84_lonlat_no_transform"] | ["proponent_submitted_environmental_project_polygon"] | ["official_source"] | ["campus_locator"] | ["Exact source polygon vertices from the active CAF attachment, whose extremes equal the EC annexure's site coordinates. A government-hosted proponent filing establishes a project-specific campus locator, not cadastral, surveyed or current-work-extent accuracy. The display anchor is the planar shoelace centroid of the source ring in source vertex order, verified inside it; it is not a publisher point, entrance or surveyed location."] |  | Neither the KML, the CAF nor the EC states a positional accuracy, survey method, geodetic realization or control points. Decimal count and government hosting do not establish accuracy. | ["49f2eb1c-bf1e-5e48-b9d5-e47463fdc97d","74d8adab-09c1-5862-9497-1686fa410e14","9cf9e078-dd02-5712-a0b5-b944ab61bfbd"] | 1 | ["60485ece-bd7e-5f82-9f1b-6e271b8dcf45"] | ["curated:aws-thane-balkum-majiwada-campus:ec-477127-current-build"] | ["under_construction"] | 2026-05-27 | 2026-05-27 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cde9b25f26b96465e0dd/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cde9b25f26b96465e0dd.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-cde9b25f26b96465e0dd.geojson | no-open-license-asserted
vcc-site-ce3b42e4fc2f6b33b8a2 | imported:semiconductor-atlas:ecodatacenter-borlange | EcoDataCenter 2 Borlänge campus | Sweden | SE | 60.4856 | 15.4364 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Borlänge town centroid from its Wikipedia article. EcoDataCenter gives the street address Kvarnsvedsvägen 420 on the former Kvarnsveden mill site, but no cited source gives coordinates for it."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6f693b49-5cf7-51bd-b9ff-56dbbb0dc051"] | 1 | ["304e9b81-f1b5-5a80-8ad5-6f46e12f5a85"] | ["imported:semiconductor-atlas:ecodatacenter-borlange"] | ["under_construction"] | 2026-10-05 | 2026-10-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ce3b42e4fc2f6b33b8a2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ce3b42e4fc2f6b33b8a2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ce3b42e4fc2f6b33b8a2.geojson | source-terms-not-recorded
vcc-site-d00d83a0549fcc042174 | curated:goodman-mad01-madrid-data-centre-campus | Goodman MAD01 Madrid Data Centre Campus | Spain | ES | 40.4441 | -3.5464 | Point | ["campus"] | ["first_party_brochure_published_map_coordinate_query"] | ["resolve_exact_PDF_URI_annotation_and_preserve_published_coordinate_query"] | ["official_operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The exact MAD01 brochure map query locates the campus at C/ Provisional Iveco-Pegaso Cinco 2. No survey, boundary, building footprint or current-work extent is asserted; secured future campus expansion is not another site."] |  | No numeric accuracy or surveyed-feature description accompanies the owner's coordinate query. | ["1e532437-06f5-5fc8-8a2f-9d239405abc1","c874fcec-0c4d-5dec-b277-0c338369d9c7"] | 1 | ["b0be5071-aff0-5470-a041-a0be3cc8385a"] | ["curated:goodman-mad01-madrid-data-centre-campus:current-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d00d83a0549fcc042174/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d00d83a0549fcc042174.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d00d83a0549fcc042174.geojson | all-rights-reserved
vcc-site-d0dffbb1f095b96397b5 | curated:runze-hong-kong-sandy-ridge-data-facility-cluster | Range Hong Kong Sandy Ridge Data Facility Cluster | Hong Kong | HK | 22.5318 | 114.1224 | Polygon | ["campus"] | ["official_lot_boundary_ring_transformed_EPSG2326_to_WGS84"] | ["CSDI_LandsD_lot_layer_query_LotCSUID_145000953_native_ring_PROJ_HK1980_to_WGS84_1_round7"] | ["official_land_grant_lot_boundary"] | ["official_source"] | ["campus_locator"] | ["Every native lot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. The lot is the government-identified site of the data facility cluster; it is a land-grant boundary, not a building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it."] |  | The lot layer states no positional tolerance for this boundary; the datum-operation accuracy is not a boundary accuracy. | ["50580ff2-c627-53a7-ac15-a975a9bd027f","fff150e7-3392-5155-a739-1293b7e66c1a"] | 1 | ["6a3cb870-eb89-5d4b-a486-44eb7d10f8b0"] | ["curated:runze-hong-kong-sandy-ridge-data-facility-cluster:initial-build"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d0dffbb1f095b96397b5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d0dffbb1f095b96397b5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d0dffbb1f095b96397b5.geojson | csdi-terms-free-reuse-with-attribution
vcc-site-d1b09eaeac654b3c56f6 | imported:semiconductor-atlas:herbata-naas | Herbata data centre campus (Naas) | Ireland | IE | 53.217 | -6.663 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from the Naas Wikipedia article. The appeal case lists the townlands of Halverstown, Jigginstown and Newhall, and reports place the site next to the M7 and a business park; no parcel point is published."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["da93ca09-cc13-5f11-81da-e797c36cefe3"] | 1 | ["2a418e82-60a0-52bf-ac57-8e0e3d3eabdb"] | ["imported:semiconductor-atlas:herbata-naas"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d1b09eaeac654b3c56f6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d1b09eaeac654b3c56f6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d1b09eaeac654b3c56f6.geojson | source-terms-not-recorded
vcc-site-d272a722ca415c1be654 | curated:vantage-lighthouse-port-washington-campus | Vantage Lighthouse Port Washington Data Center Campus | United States | US | 43.4307 | -87.8615 | Point | ["project"] | ["coordinates_to_point"] | ["official_project_coordinate"] | ["environmental_review_project_point"] | ["official_source"] | ["project_locator"] | ["Exact sign-and-decimal parsing of the DNR project coordinate; not a parcel, building, or construction footprint."] |  | Wisconsin DNR publishes no bounded accuracy for the project coordinate. | ["40f1c2ae-aacb-5aac-8edd-60e4a405c7fc"] | 1 | ["3b636397-fbb2-5564-a352-fa1382a218b5"] | ["curated:vantage-lighthouse-port-washington-campus:current-campus-build"] | ["under_construction"] | 2026-06-12 | 2026-06-12 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d272a722ca415c1be654/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d272a722ca415c1be654.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d272a722ca415c1be654.geojson | public-government-record-fact-extraction-only
vcc-site-d3117bafca6bdcc5007e | imported:semiconductor-atlas:airtrunk-tok1-inzai | AirTrunk TOK1 Tokyo East | Japan | JP | 35.8323 | 140.1453 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["AirTrunk's TOK1 page places the campus in Inzai's data center hub without an address; coordinates are the OpenStreetMap Nominatim centroid of Inzai City."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["4e36cb9c-336f-526e-bf8a-2fadaa356951"] | 1 | ["3fe8297a-147b-56fe-a5a6-6ae165798506"] | ["imported:semiconductor-atlas:airtrunk-tok1-inzai"] | ["partially_operational"] | 2026-03-10 | 2026-03-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d3117bafca6bdcc5007e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d3117bafca6bdcc5007e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d3117bafca6bdcc5007e.geojson | source-terms-not-recorded
vcc-site-d5d70748e492c5e2278a | curated:cyrusone-aurora-diehl-road-campus | CyrusOne Aurora Diehl Road Campus | United States | US | 41.7981 | -88.2434 | Point | ["campus"] | ["official_census_street_address_range_interpolation"] | ["exact_state_named_campus_address_Census_NAD83_to_WGS84_pyproj_3_8_0"] | ["official_campus_street_address_locator"] | ["official_source"] | ["campus_locator"] | ["Exact source-bound campus address interpolated along Diehl Road. This is not the CHI2 rooftop work site, surveyed building position, campus interior, parcel boundary or construction footprint. The state campus address locates the shared CHI1-CHI3 campus once."] |  | Census supplies no site-specific accuracy for this address-range interpolation. | ["24e8b46a-f7f4-57b5-a278-3a6cd588c244","2f63a682-a415-5963-81ef-ad0f0b71cfdd","f1342044-d585-5e7f-8596-2af4ecf75928"] | 1 | ["cf028790-cea6-555d-a3bb-48e08ff78f3b"] | ["curated:cyrusone-aurora-diehl-road-campus:chi2-sound-mitigation-capital-retrofit"] | ["under_construction"] | 2026-08-20 | 2026-08-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d5d70748e492c5e2278a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d5d70748e492c5e2278a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d5d70748e492c5e2278a.geojson | no-open-license-asserted
vcc-site-d60291ccffe6616c33cc | curated:qts-cedar-rapids-data-center-campus | QTS Cedar Rapids Data Center Campus | United States | US | 41.9073 | -91.7543 | Point | ["campus"] | ["first_party_published_map_pin"] | ["qts_first_party_cdr1_dc1_page_map_pin_as_shared_campus_locator"] | ["first_party_facility_page_point_as_broad_campus_locator"] | ["official_source"] | ["campus_locator"] | ["QTS-published page map pin attached to the CDR1 DC1 address at the shared 6200 76th Avenue SW campus. It is used only as a broad campus locator, not as DC1, DC2, DC3, current-development, sewer-work, building, parcel, or 612-acre campus boundary geometry."] |  | The QTS page publishes coordinate digits but no collection method, reference-feature definition, or bounded numeric horizontal-accuracy value; the map pin is not asserted to fall on any specific building or work extent. | ["7f58e6cc-7e09-55a4-8202-38d31f72d03d"] | 1 | ["ae6f1b86-660b-54e9-bdb0-d29bfeedc551"] | ["curated:qts-cedar-rapids-data-center-campus:current-campus-development"] | ["under_construction"] | 2026-07-15 | 2026-07-15 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d60291ccffe6616c33cc/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d60291ccffe6616c33cc.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d60291ccffe6616c33cc.geojson | all-rights-reserved-fact-extraction-only
vcc-site-d6e7826cfaef008088a0 | curated:aws-walqa-huesca-data-center | AWS Walqa Data Center Campus | Spain | ES | 42.1138 | -0.45644 | Point | ["project"] | ["direct_geometry"] | ["official_aragon_piga_project_report_dms_coordinate_to_point"] | ["official_source_reported_project_reference_point"] | ["official_source"] | ["project_locator"] | ["Official project-report point used only to locate the proposed/current Walqa build. The reported 0.01-arc-second display precision is preserved but is not converted into survey accuracy."] |  | The report prints DMS precision but does not state datum, surveyed reference feature, collection method, or horizontal accuracy. | ["a66352ad-9007-510c-ad30-c88e41cbe37a"] | 1 | ["55f4eb88-750d-5aa5-b4cb-bd5b8e746fe6"] | ["curated:aws-walqa-huesca-data-center:current-build"] | ["under_construction"] | 2026-06-25 | 2026-06-25 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["tracked_blind_reject_locally_unsealed_identity_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d6e7826cfaef008088a0/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d6e7826cfaef008088a0.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d6e7826cfaef008088a0.geojson | rights-status-not-established
vcc-site-d70371ee13abb96e26fb | imported:semiconductor-atlas:vantage-jhb1-sedenak | Vantage Data Centers Johor campus (JHB1), Sedenak Tech Park | Malaysia | MY | 1.7137 | 103.5248 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Sedenak Tech Park in Johor without an address. The point is the Sedenak coordinate from its Wikipedia article (which also gives Kulai District), so it marks the locality rather than the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["9a802eef-12cf-5e0b-a459-c17fab1ce0d9"] | 1 | ["77f10b6a-00c1-5bf7-974e-d4dc4467b35e"] | ["imported:semiconductor-atlas:vantage-jhb1-sedenak"] | ["partially_operational"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d70371ee13abb96e26fb/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d70371ee13abb96e26fb.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d70371ee13abb96e26fb.geojson | source-terms-not-recorded
vcc-site-d7089d81dd52f365db5b | curated:firmus-st-leonards-launceston-campus | Firmus St Leonards Launceston Campus | Australia | AU | -41.4409 | 147.1766 | Point | ["campus"] | ["Literal Nominatim object-centroid lat/lon fields for native OSM way429540795, reordered to longitude/latitude only; no numerical coordinate transform or map-image extraction."] | ["community_named_constituent_building_centroid"] | ["constituent_building_reference_point"] | ["community_source"] | ["campus_locator"] | ["Named Firmus LST01 existing-building reference on the explicitly joined municipal development site. Not a new-hall footprint, demolition extent, complete campus boundary, locality center, headquarters or neighboring substation."] |  | Neither the source object nor Nominatim states positional accuracy or original survey provenance. Decimal precision and WGS84 semantics do not establish accuracy. | ["0ceea970-6b27-5b46-945e-0e9dd038f9e3","1a63393b-38dd-5e83-b13b-1b8e4256c63c","68d8543a-af32-5676-a95a-459a238279e6","da0bd3e7-ecee-5411-a6e6-dcd153d7683c","f6a5780c-e38a-53b2-b296-ce8fcec21a62"] | 1 | ["e8a1add0-19fb-5196-ae75-34353e7d580b"] | ["curated:firmus-st-leonards-launceston-campus:ai-factory-current-build"] | ["under_construction"] | 2026-07-02 | 2026-07-02 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d7089d81dd52f365db5b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d7089d81dd52f365db5b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d7089d81dd52f365db5b.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-d80966c9e0bc776042e6 | imported:semiconductor-atlas:meta-kuna-idaho | Meta Kuna Data Center | United States | US | 43.4903 | -116.3717 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Kuna city coordinates from its Wikipedia page. Sources name the city and county but give no address or parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["793a4b14-609c-5493-8af9-b9186eaa0d5f"] | 1 | ["e375d86c-75a4-53f3-a80e-31aa6f32b616"] | ["imported:semiconductor-atlas:meta-kuna-idaho"] | ["operational"] | 2026-09-03 | 2026-09-03 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d80966c9e0bc776042e6/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d80966c9e0bc776042e6.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d80966c9e0bc776042e6.geojson | source-terms-not-recorded
vcc-site-d9155165962c78be00da | imported:semiconductor-atlas:softbank-sakai | SoftBank Osaka Sakai AI data center | Japan | JP | 34.596 | 135.4333 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["SoftBank names Sharp's Sakai LCD plant in Sakai City; Sharp gives the plant address as 1 Takumi-cho, Sakai-ku. Coordinates are the OpenStreetMap Nominatim centroid of the Takumi-cho neighbourhood, so they approximate the plant complex rather than the exact SoftBank portion (about 60% of the plant land)."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["91c22675-230e-5b67-a4f1-96c461b4eb5b"] | 1 | ["75596cc6-0434-596d-be35-53be39de9c0a"] | ["imported:semiconductor-atlas:softbank-sakai"] | ["under_construction"] | 2026-06-23 | 2026-06-23 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d9155165962c78be00da/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d9155165962c78be00da.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d9155165962c78be00da.geojson | source-terms-not-recorded
vcc-site-d92255df1f2246ac16d5 | imported:semiconductor-atlas:google-stillwater-oklahoma | Google Stillwater data center campus | United States | US | 36.116 | -97.059 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Stillwater city coordinates from its Wikipedia page. Sources place the site at the intersection of Perkins and Richmond Roads but give no parcel coordinates, and no geocoder was used."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["acd64cf6-e494-594b-ab09-08d50e7f3392"] | 1 | ["1b7d1694-1f94-5ac5-a39d-ef81696ed589"] | ["imported:semiconductor-atlas:google-stillwater-oklahoma"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d92255df1f2246ac16d5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d92255df1f2246ac16d5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d92255df1f2246ac16d5.geojson | source-terms-not-recorded
vcc-site-d98cef70ec1688f58e42 | imported:semiconductor-atlas:joliet-technology-center | Joliet Technology Center | United States | US | 41.5297 | -88.0728 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for Joliet. Neither source gives a street address or parcel; the developers' site describes the location only as away from homes and near distribution uses and a racetrack."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["f15c1fc4-df2b-52c9-a0c7-06ff78e68425"] | 1 | ["def89e4b-c93d-5dc8-a955-edd8e51a1058"] | ["imported:semiconductor-atlas:joliet-technology-center"] | ["announced"] | 2026-03-23 | 2026-03-23 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d98cef70ec1688f58e42/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d98cef70ec1688f58e42.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-d98cef70ec1688f58e42.geojson | source-terms-not-recorded
vcc-site-dadea001f97aa8058f7a | imported:semiconductor-atlas:core-scientific-denton | Core Scientific Denton data center (CoreWeave) | United States | US | 33.2164 | -97.1292 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City coordinates from Wikipedia. Core Scientific gives the address 8171 Jim Christal Rd, Denton, TX 76207, but it was not geocoded in this review."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3877ce56-44bc-5417-b82c-46b731aa3cf8"] | 1 | ["c62aed61-a87f-57ab-b1a4-76d1867f73b9"] | ["imported:semiconductor-atlas:core-scientific-denton"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dadea001f97aa8058f7a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dadea001f97aa8058f7a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dadea001f97aa8058f7a.geojson | source-terms-not-recorded
vcc-site-dba81c9003e655831d45 | imported:semiconductor-atlas:virtus-wustermark | VIRTUS Wustermark campus | Germany | DE | 52.5463 | 12.9404 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Nominatim centroid of the municipality of Wustermark; sources name the municipality and the 50Hertz Wustermark substation but give no address."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["8df23ef2-bd9e-5794-9b1e-e8c46ce5a4c5"] | 1 | ["b6d175dc-d92a-56ca-a1a7-85306c9de22a"] | ["imported:semiconductor-atlas:virtus-wustermark"] | ["under_construction"] | 2026-06-01 | 2026-06-01 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dba81c9003e655831d45/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dba81c9003e655831d45.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dba81c9003e655831d45.geojson | source-terms-not-recorded
vcc-site-dbe568d910290db51ead | imported:semiconductor-atlas:terawulf-justified-data-hawesville | TeraWulf Justified Data campus (Hawesville) | United States | US | 37.9011 | -86.7494 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City coordinates from Wikipedia. TeraWulf places the campus at the former Century Aluminum Hawesville facility in Hancock County, whose exact position is not given in the sources."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["30a8faac-6bf4-5f82-80b3-159eed56720e"] | 1 | ["9dbfd718-7b41-58b1-bb46-0138b96aeca8"] | ["imported:semiconductor-atlas:terawulf-justified-data-hawesville"] | ["announced"] | 2026-08-24 | 2026-08-24 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dbe568d910290db51ead/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dbe568d910290db51ead.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dbe568d910290db51ead.geojson | source-terms-not-recorded
vcc-site-dc7beeb061c0e039f4cf | imported:semiconductor-atlas:sify-chennai-02-siruseri | Sify Chennai 02 data center campus, Siruseri | India | IN | 12.835 | 80.2 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Siruseri, Chennai, without an address. The point is the Siruseri coordinate from its Wikipedia article (which also gives the district), so it marks the locality rather than the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ac5b7466-58d3-5166-a4b9-6156d63c66d9"] | 1 | ["9d173225-d19b-5566-ab43-b319b0434236"] | ["imported:semiconductor-atlas:sify-chennai-02-siruseri"] | ["partially_operational"] | 2025-10-16 | 2025-10-16 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dc7beeb061c0e039f4cf/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dc7beeb061c0e039f4cf.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dc7beeb061c0e039f4cf.geojson | source-terms-not-recorded
vcc-site-dd0f231b23c8dd96495b | imported:semiconductor-atlas:nextdc-s7-eastern-creek | NEXTDC S7 Sydney | Australia | AU | -33.8059 | 150.85 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["NEXTDC names the suburb of Eastern Creek, about 45 km west of the Sydney CBD, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the suburb."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["22e3e100-6fac-50ab-ac5c-44d1960cfbf1"] | 1 | ["688df4a2-dc56-5cde-901a-87c87a08137e"] | ["imported:semiconductor-atlas:nextdc-s7-eastern-creek"] | ["announced"] | 2025-12-05 | 2025-12-05 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dd0f231b23c8dd96495b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dd0f231b23c8dd96495b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dd0f231b23c8dd96495b.geojson | source-terms-not-recorded
vcc-site-de7d1b5d61517ef55cfe | curated:databank-red-oak-campus | DataBank Red Oak Campus | United States | US | 32.5382 | -96.7349 | Point | ["campus"] | ["official_named_address_point"] | ["native_EPSG2276_to_EPSG4326_pyproj_NAD83_to_WGS84_1"] | ["official_address_reference_point"] | ["official_source"] | ["campus_locator"] | ["One literal county Site address point at the exact operator-defined DFW10 address, used to locate the single Red Oak campus. Not a surveyed building point, boundary, centroid, entrance or observed work footprint; decimal digits retain computational precision only."] |  | County supplies no numeric positional accuracy for this Site address point. Four-metre transformation operation accuracy is not feature accuracy. | ["03b9ee73-7cf3-53a7-9660-81544f5ee935","0966d5c7-8856-5c81-94e5-503a5bee322d","100ab544-05a4-5194-a4af-64a391377239","4a80f27c-9e26-5cec-be34-785d537de98c","5beeb28d-4f5f-5a65-8ef2-dbc053b1b243","7f7a189c-0a0e-56f1-8a82-c6f28bf85caf","836a5ca6-2fb9-5c2d-b3d9-bb2d346fee94","b639e1e4-9a40-5565-86a8-2b676fabc30a"] | 1 | ["546bf83f-2bb4-5539-b576-6b7100981420"] | ["curated:databank-red-oak-campus:first-phase-current-build"] | ["under_construction"] | 2026-07-26 | 2026-07-26 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-de7d1b5d61517ef55cfe/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-de7d1b5d61517ef55cfe.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-de7d1b5d61517ef55cfe.geojson | no-open-license-asserted
vcc-site-dec24d7a34a6a816e35b | curated:nextdc-m3-melbourne | NEXTDC M3 Melbourne Data Center Campus | Australia | AU | -37.8049 | 144.8638 | Point | ["campus"] | ["community_named_campus_representative_point"] | ["preserve_Nominatim_way1431074202_lat_lon_and_bind_exact_NEXTDC_M3_name_to_operator_West_Footscray_entry"] | ["community_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["OSM way1431074202 is named NEXTDC M3 in West Footscray, matching the operator campus entry at 25 Indwe Street. It has no OSM address tag; the street address is operator evidence, not a synthesized OSM property. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate."] |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | ["53ffc2fa-fde1-50f1-a7b4-9e43d9dcb293","944d20c6-1f9a-503d-857d-951b8336071c"] | 1 | ["c789668b-ecf3-53b2-b23c-44151e199317"] | ["curated:nextdc-m3-melbourne:incremental-in-progress-fit-out"] | ["mep_electrical"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dec24d7a34a6a816e35b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dec24d7a34a6a816e35b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-dec24d7a34a6a816e35b.geojson | ODbL-1.0
vcc-site-deed58b28fabd02848f5 | imported:semiconductor-atlas:microsoft-union-city-georgia | Microsoft Union City data center campus (EdgeConneX) | United States | US | 33.605 | -84.4936 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["The July 2024 regional-impact report gives the street address 4810 Stonewall Tell Road but no coordinates. The point is the Union City coordinate from its Wikipedia article, so it marks the city rather than the parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["d9584c37-4753-57d5-9a45-ab4450dbf7f6"] | 1 | ["561d28db-c1e2-5bbc-bda9-e10cbee90d7d"] | ["imported:semiconductor-atlas:microsoft-union-city-georgia"] | ["under_construction"] | 2026-08-06 | 2026-08-06 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-deed58b28fabd02848f5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-deed58b28fabd02848f5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-deed58b28fabd02848f5.geojson | source-terms-not-recorded
vcc-site-df93318f7935fb88ea53 | curated:prologis-trenton-project-mila-campus | Prologis Trenton Project Mila Campus | United States | US | 39.4562 | -84.4597 | Point | ["campus"] | ["representative_point_inside_transformed_exact_developer_parcel"] | ["county_response_WKT_EPSG3735_to4326_pyproj3_8_0_then_Shapely2_1_2_representative_point"] | ["official_consolidated_parcel_interior_campus_locator"] | ["official_source"] | ["campus_locator"] | ["One point within the exact consolidated parcel R8000060000011 linked by developer filings to Project Mila. It is not a surveyed building position, construction footprint, approved campus boundary or individual hall. The source parcel polygon is not redistributed."] |  | County GIS supplies no site-specific positional accuracy; four-metre datum-operation accuracy is not parcel or locator accuracy. | ["0048b025-5c07-5f60-82f2-78a73d462260","33d8c10b-d2f7-59d5-b1de-bb27cd65ffc4","6a90d412-842e-5aec-ae30-6556a0d4522f"] | 1 | ["d6a6d399-4580-54f8-80de-1dc0854e4699"] | ["curated:prologis-trenton-project-mila-campus:current-campus-build"] | ["under_construction"] | 2026-08-20 | 2026-08-20 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-df93318f7935fb88ea53/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-df93318f7935fb88ea53.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-df93318f7935fb88ea53.geojson | no-open-license-asserted
vcc-site-e2ec9daea00e4e3d9dc1 | imported:semiconductor-atlas:google-fort-wayne-indiana | Google Fort Wayne data center | United States | US | 41.018 | -85.058 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Approximate intersection of East Tillman Road and Adams Center Road, derived from OpenStreetMap geometry for the two roads named by the state announcement; the parcel itself is not mapped."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["3ac3ad9e-8831-5419-8130-9e60d24342e6"] | 1 | ["7c9397d2-971c-5d1e-ad58-210d19777a37"] | ["imported:semiconductor-atlas:google-fort-wayne-indiana"] | ["operational"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e2ec9daea00e4e3d9dc1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e2ec9daea00e4e3d9dc1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e2ec9daea00e4e3d9dc1.geojson | source-terms-not-recorded
vcc-site-e305b394a907f57f2639 | imported:semiconductor-atlas:lambda-kansas-city | Lambda Kansas City AI factory | United States | US | 39.0997 | -94.5783 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City centroid from Wikipedia (s2). The announcement places the facility in the Northland part of Kansas City but gives no address, so the point is not at the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6846ad0f-2ca2-53a2-a083-33bef62ed168"] | 1 | ["a95db60b-fb99-5f16-ad4a-c763e4714041"] | ["imported:semiconductor-atlas:lambda-kansas-city"] | ["announced"] | 2025-10-28 | 2025-10-28 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e305b394a907f57f2639/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e305b394a907f57f2639.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e305b394a907f57f2639.geojson | source-terms-not-recorded
vcc-site-e348a191d95cf61970ae | imported:semiconductor-atlas:google-journey-haskell-county-texas | Google Journey data center campus (Haskell County) | United States | US | 33.1564 | -99.5683 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["OpenStreetMap geometry of Red Creek Road in Haskell County. The abatement exhibit places the 300-acre tract on the west side of Red Creek Road about two miles south of US Highway 380; the registered address is 1362 Red Creek Rd, which could not be resolved to a point."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["dfab1504-d44e-5ef1-b4c7-78e82a32d5b9"] | 1 | ["93e5705d-3c86-524c-8089-0868d13bbd0d"] | ["imported:semiconductor-atlas:google-journey-haskell-county-texas"] | ["under_construction"] | 2026-06-25 | 2026-06-25 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e348a191d95cf61970ae/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e348a191d95cf61970ae.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e348a191d95cf61970ae.geojson | source-terms-not-recorded
vcc-site-e4874e06dbb0a951c91d | curated:pure-dc-ams01-amsterdam-westpoort-campus | Pure DC AMS01 Amsterdam Westpoort Campus | Netherlands | NL | 52.3953 | 4.8346 | Point | ["campus"] | ["official_bag_address_record_to_point"] | ["pdok_bag_tower_1_address_point_as_broad_campus_locator"] | ["official_constituent_address_point_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Plimsollweg 3 is the official BAG address used for one AMS01 constituent permit. It is only a broad campus locator, not a project point, entrance, parcel, complete campus, building footprint, or current-work extent."] |  | BAG/PDOK publishes no bounded numeric horizontal accuracy applicable to this selected address point. | ["2f4528c3-705c-5b59-95c2-1b4a37661ccf"] | 1 | ["a072994f-1b7d-5cc8-98b7-bc79c666c6c3"] | ["curated:pure-dc-ams01-amsterdam-westpoort-campus:data-hall-development"] | ["under_construction"] | 2026-05-27 | 2026-05-27 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e4874e06dbb0a951c91d/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e4874e06dbb0a951c91d.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e4874e06dbb0a951c91d.geojson | Public-Domain-Mark-1.0
vcc-site-e5029d978178bf23ae67 | curated:goodman-lax01-los-angeles-program-anchor | Goodman LAX01 Los Angeles Program Anchor | United States | US | 34.0051 | -118.2181 | Point | ["project"] | ["official_parcel_reference_point"] | ["official_exact_address_match_to_published_center_lat_lon_fields_without_atlas_centroiding"] | ["official_assessor_parcel_reference_point"] | ["official_source"] | ["project_locator"] | ["Current assessor parcel reference point for the exact owner-bound first-facility address at 3094 E Vernon Avenue. This is not the entire 3094/3200 property boundary, a building footprint, current construction extent, or surveyed building-center claim."] |  | The selected county service result supplies no numeric horizontal accuracy for its reference-point fields. | ["37013ce5-a12c-59d4-beb5-6ae9011daed7"] | 1 | ["447b19d9-b89b-59a6-9931-824aa1781fb0"] | ["curated:goodman-lax01-los-angeles-program-anchor:first-site-current-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e5029d978178bf23ae67/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e5029d978178bf23ae67.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e5029d978178bf23ae67.geojson | no-open-redistribution-license-asserted
vcc-site-e5d89f88732b72ed1705 | imported:semiconductor-atlas:atnorth-varde-den02 | atNorth DEN02 Varde mega site | Denmark | DK | 55.8058 | 8.6181 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Local press places the site at Krageris, north and northeast of Ølgod; Krageris was not found in Nominatim, so the Ølgod village centroid is used."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["15245591-7c39-5b0f-ba74-f5156f3bf425"] | 1 | ["297b1705-767f-5434-af46-c08932afceb9"] | ["imported:semiconductor-atlas:atnorth-varde-den02"] | ["announced"] | 2026-08-11 | 2026-08-11 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e5d89f88732b72ed1705/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e5d89f88732b72ed1705.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e5d89f88732b72ed1705.geojson | source-terms-not-recorded
vcc-site-e6669b76221d6e79fd89 | imported:semiconductor-atlas:qts-vimercate | QTS Vimercate data center campus | Italy | IT | 45.617 | 9.367 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Town coordinates from the Vimercate Wikipedia article. Sources place the site on the former IBM area at Velasca, a frazione of Vimercate, near the boundary with Burago; the site is not mapped in the local OpenStreetMap layer."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["e4ddd93d-c079-503a-8fb4-c050901d33db"] | 1 | ["b19d5d3a-c2cc-5cea-9698-fe07ac125c8e"] | ["imported:semiconductor-atlas:qts-vimercate"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e6669b76221d6e79fd89/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e6669b76221d6e79fd89.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e6669b76221d6e79fd89.geojson | source-terms-not-recorded
vcc-site-e6ad7f75be14475fcc3b | imported:semiconductor-atlas:stack-berry-hill-pittsylvania-county | STACK Infrastructure Berry Hill campus, Pittsylvania County | United States | US | 36.82 | -79.4 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Coordinates are the Wikipedia point for Pittsylvania County (s5); precision is county level. Sources place the campus at the Berry Hill megasite in Pittsylvania County but give no address, and the parcel was not geocoded. The staged record used the Danville city centroid, which lies outside the county."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["ded86a8d-470e-5b47-9611-0fdb4ab1f141"] | 1 | ["e9f8645b-ff54-5ebb-8f6c-6c04dbc8d5e2"] | ["imported:semiconductor-atlas:stack-berry-hill-pittsylvania-county"] | ["announced"] | 2026-07-27 | 2026-07-27 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e6ad7f75be14475fcc3b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e6ad7f75be14475fcc3b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e6ad7f75be14475fcc3b.geojson | source-terms-not-recorded
vcc-site-e6b61ca210eeece21cf5 | curated:daou-jukjeon-cdc-campus | Daou Jukjeon CDC Campus | Korea, Republic of | KR | 37.3321 | 127.1324 | Point | ["campus"] | ["source_attribute_decimal_coordinates_to_point_without_centroiding"] | ["first_party_named_maps_javascript_marker"] | ["official_operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact operator-authored six-decimal marker input for the named Jukjeon CDC campus. Decimal precision is not surveyed accuracy; not a boundary, new-building footprint or trade-work location."] |  | Operator provides no positional-accuracy statement. | ["6a4993c0-e63b-5684-a225-fb502d9c3db2","73eb3f1c-f1ed-548b-8697-2721d5e570d0"] | 1 | ["057826b7-3798-5e94-9628-e76e45647c61"] | ["curated:daou-jukjeon-cdc-campus:current-build"] | ["under_construction"] | 2026-08-14 | 2026-08-14 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e6b61ca210eeece21cf5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e6b61ca210eeece21cf5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e6b61ca210eeece21cf5.geojson | CC-BY-4.0; all-rights-reserved
vcc-site-e7cbc915d8b179b3017f | curated:cdc-maddington-perth-campus | CDC Maddington Perth Campus | Australia | AU | -32.0342 | 116.0052 | Polygon | ["campus"] | ["official_coordinate_transform"] | ["official_property_polygon"] | ["one_constituent_campus_lot"] | ["official_source"] | ["campus_locator"] | ["Exact transformed polygon for one of four officially identified Maddington campus lots; not the complete campus, an individual building, or current work area."] |  | The public property service states no survey-grade horizontal accuracy after transformation. | ["04eb4e29-b035-5d4f-b6dc-ababe98ba94e"] | 1 | ["bb8ba3ad-d563-5f84-a543-079a10264640"] | ["curated:cdc-maddington-perth-campus:current-build"] | ["shell"] | 2026-06-25 | 2026-06-25 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e7cbc915d8b179b3017f/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e7cbc915d8b179b3017f.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e7cbc915d8b179b3017f.geojson | rights-status-uncertain-fact-extraction-only
vcc-site-e7f4d963829eac6090a7 | imported:semiconductor-atlas:kenya-olkaria-geothermal-campus | G42 and Microsoft Olkaria geothermal data centre campus | Kenya | KE | -0.88574 | 36.27 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources name Olkaria only. Coordinates are those given for the Olkaria geothermal area on its Wikipedia page, not a data centre parcel."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["e8aa9f30-dd73-5067-824b-efe66a6d7dcd"] | 1 | ["e3e31b3f-d0db-54ad-849f-126a4eae2868"] | ["imported:semiconductor-atlas:kenya-olkaria-geothermal-campus"] | ["announced"] | 2026-08-24 | 2026-08-24 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e7f4d963829eac6090a7/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e7f4d963829eac6090a7.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e7f4d963829eac6090a7.geojson | source-terms-not-recorded
vcc-site-e8f2d5efccb035e9135a | imported:semiconductor-atlas:sk-aws-ulsan-ai-data-center | SK AI Data Center Ulsan | Korea, Republic of | KR | 35.5392 | 129.3119 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin1"] | ["compiled_reference"] | ["admin1_context"] | ["Sources place the site in the Mipo National Industrial Complex in Ulsan without an address, and the complex could not be geocoded; coordinates are the OpenStreetMap Nominatim centroid of Ulsan Metropolitan City."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["c4cbb4ab-c343-5664-82db-472e1cbb7b1a"] | 1 | ["64f6ec20-7a91-530a-85f2-7748b0e320f8"] | ["imported:semiconductor-atlas:sk-aws-ulsan-ai-data-center"] | ["under_construction"] | 2026-09-14 | 2026-09-14 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e8f2d5efccb035e9135a/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e8f2d5efccb035e9135a.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-e8f2d5efccb035e9135a.geojson | source-terms-not-recorded
vcc-site-ebacb890726508925a40 | imported:semiconductor-atlas:ytl-kulai-johor | YTL Green Data Center Park, Kulai | Malaysia | MY | 1.6569 | 103.6059 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Sources place the park in Kulai, Johor, about 30 km from Johor Bahru, without an address; coordinates are the OpenStreetMap Nominatim point for Kulai town."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["afe4b6ea-54ab-594d-ad5e-94b2a01dea6d"] | 1 | ["2d2dbfa9-0685-5532-8d89-80ceeaf07427"] | ["imported:semiconductor-atlas:ytl-kulai-johor"] | ["partially_operational"] | 2026-08-20 | 2026-08-20 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ebacb890726508925a40/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ebacb890726508925a40.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ebacb890726508925a40.geojson | source-terms-not-recorded
vcc-site-ebc20ddd515fd9367ea7 | imported:semiconductor-atlas:edgecore-louisa-county | EdgeCore Louisa County campus | United States | US | 37.99 | -77.96 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Wikipedia coordinates for Louisa County, Virginia. EdgeCore places the campus in the Shannon Hill Regional Business Park, which no cited source locates precisely."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["6857f912-65fa-51fd-8bf5-88f9bde79ed1"] | 1 | ["8560b48f-07cb-54c8-8b8d-163dc196caee"] | ["imported:semiconductor-atlas:edgecore-louisa-county"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ebc20ddd515fd9367ea7/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ebc20ddd515fd9367ea7.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ebc20ddd515fd9367ea7.geojson | source-terms-not-recorded
vcc-site-ece79fca728f9d94dc00 | curated:northc-frankfurt-fra01 | NorthC Frankfurt1 (FRA01) | Germany | DE | 50.0996 | 8.581 | Point | ["campus"] | ["direct_geometry"] | ["official_municipal_address_point_crs_transform"] | ["official_building_address_point"] | ["official_source"] | ["project_locator"] | ["Official municipal building-address point for exact street and house number695. Binds the operator-published project address; does not delineate the new data-centre building, parcel or works boundary."] |  | Address source provides no positional accuracy. Transformation operation accuracy of1m is not site-location uncertainty. | ["8a94810f-0243-582c-b684-10791ec2a193"] | 1 | ["c2ec8d08-3436-5bbc-af4e-4eb553297fe2"] | ["curated:northc-frankfurt-fra01:current-facility-build"] | ["site_preparation"] | 2026-09-18 | 2026-09-18 | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ece79fca728f9d94dc00/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ece79fca728f9d94dc00.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ece79fca728f9d94dc00.geojson | public-record-source-terms
vcc-site-ee33430200d597833ebe | curated:qts-cambois-data-centre-campus | QTS Cambois Data Centre Campus | United Kingdom | GB | 55.1509 | -1.5336 | Point | ["campus"] | ["official_coordinate_transform"] | ["applicant_report_osgb36_national_grid_reference_to_wgs84"] | ["government_hosted_applicant_report_wider_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Government-hosted applicant report's approximate centre for the wider Cambois Campus, transformed once from NGR NZ 29820 84164. It is not the Phase A point, east- or south-side earthworks location, parcel, campus, building, project, or current-work boundary."] |  | The report explicitly calls the NGR an approximate centre and supplies no numeric horizontal-accuracy statement; transformed digits do not add accuracy. | ["a4ff7674-bfdc-5a88-92cd-673e02250b1a"] | 2 | ["2bd78b04-9314-5aa8-ac32-ef30e111bc2e","5b11c034-5a3b-5e5d-bc6a-b7122e21fbec"] | ["curated:qts-cambois-data-centre-campus:2026-earthworks","imported:semiconductor-atlas:qts-cambois-blyth"] | ["civil_works","under_construction"] | 2026-07-01 | 2026-08-06 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ee33430200d597833ebe/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ee33430200d597833ebe.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ee33430200d597833ebe.geojson | all-rights-reserved-fact-extraction-only
vcc-site-ee413666d6aa0f69a386 | curated:hive-yguazu-paraguay-campus | HIVE Yguazú Paraguay Campus | Paraguay | PY | -25.4845 | -55.0114 | Point | ["campus"] | ["official_named_environmental_project_geojson_point"] | ["MADES_SIAM_expId83461_GeoJSON_point_copied_exactly_under_RFC7946_CRS84_contract"] | ["official_environmental_project_reference_point"] | ["official_source"] | ["campus_locator"] | ["One source-supplied point for the named Zunz data-center/substation project, linked to Finca1534/Padrón33. It is not a surveyed point, building footprint, campus boundary, entrance, or separate utility-only site. No arithmetic centroid or imagery-derived coordinate."] |  | MADES gives no source-specific positional-accuracy estimate or point-placement method; decimal digits do not imply survey accuracy. | ["3530db1f-8c5d-541a-bf50-146038fd3aaa","7b54b2a6-dc99-58e3-b816-eb8d3ae4c3d4","8799b8d9-43e5-562f-94de-86e09c8caa87"] | 1 | ["20a32e9d-3c57-520d-aeb8-ad999d43fee3"] | ["curated:hive-yguazu-paraguay-campus:2026-100mw-expansion"] | ["under_construction"] | 2026-08-14 | 2026-08-14 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ee413666d6aa0f69a386/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ee413666d6aa0f69a386.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ee413666d6aa0f69a386.geojson | no-open-license-asserted
vcc-site-ef8be5d9da9f69e72683 | imported:semiconductor-atlas:beacon-ai-centers-indus | Beacon AI Centers Indus campus | Canada | CA | 50.9434 | -113.8072 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["site"] | ["compiled_reference"] | ["project_locator"] | ["Decimal coordinates given in the proponent's initial project description (legal land description in section 11-23-28-W4M, south of Township Road 232), rounded to four decimals."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["314d2a34-7e3f-5faa-8251-c7eda8caadde"] | 1 | ["fbbfee97-55a0-5a4e-b000-282ff02a8a39"] | ["imported:semiconductor-atlas:beacon-ai-centers-indus"] | ["announced"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ef8be5d9da9f69e72683/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ef8be5d9da9f69e72683.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ef8be5d9da9f69e72683.geojson | source-terms-not-recorded
vcc-site-efe797bc04a70a7ce5bb | curated:china-telecom-shaotang-shaoguan | China Telecom Shaotang Campus, Shaoguan | China | CN | 24.7875 | 113.6619 | Point | ["campus"] | ["direct_geometry"] | ["official_eia_geographic_dms_point_transcription"] | ["official_eia_on_campus_substation_locator"] | ["official_source"] | ["campus_locator"] | ["Reported center point of the campus 220kV substation in its northwest corner. Locates the campus through named on-campus support infrastructure; not a data-hall center, parcel centroid, or construction boundary."] |  | No positional accuracy or coordinate datum stated. Numeric precision is source transcription precision, not positional accuracy; offset to individual data halls is unknown. | ["ba904be8-28ae-59dc-9fda-afca852eb5d9"] | 1 | ["bb2a6c51-4439-5bda-aa65-a5f7f9e14e98"] | ["curated:china-telecom-shaotang-shaoguan:announced-campus-development"] | ["announced"] | 2026-09-21 | 2026-09-21 | authoritative_project_record_plus_scoped_location | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-efe797bc04a70a7ce5bb/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-efe797bc04a70a7ce5bb.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-efe797bc04a70a7ce5bb.geojson | all-rights-reserved
vcc-site-f1171e4b8e247993d773 | curated:china-mobile-plateau-big-data-center-haidong | China Mobile Plateau Big Data Center Haidong | China | CN | 36.5097 | 102.0073 | Point | ["project"] | ["official_dms_coordinate_to_point"] | ["haidong_government_eia_project_center_coordinate"] | ["official_environmental_assessment_phase2_stage1_project_point"] | ["official_source"] | ["project_locator"] | ["The point is the official EIA project-center coordinate for Phase 2 Stage 1 and locates the named Phase 2 build. It is not a surveyed entrance, parcel centroid, campus boundary, building footprint, or current-work extent."] |  | The EIA reports a project-center coordinate but no bounded horizontal-accuracy or survey-method statement. | ["e702223c-2730-5dda-90f9-ab59caa40a76"] | 1 | ["e2c7ea58-17cc-594d-8b98-56ca08988c99"] | ["curated:china-mobile-plateau-big-data-center-haidong:phase-2-build"] | ["under_construction"] | 2026-09-02 | 2026-09-02 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f1171e4b8e247993d773/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f1171e4b8e247993d773.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f1171e4b8e247993d773.geojson | all-rights-reserved
vcc-site-f19474c4631ae00b2725 | imported:semiconductor-atlas:iren-kiowa-oklahoma | IREN Kiowa data center campus | United States | US | 34.7228 | -95.9025 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Local reports place the site just south of Kiowa between US 69 and Kiowa Lake Road, with no exact address set. Coordinates are the Kiowa town point from its Wikipedia article, which also gives the county."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["7d65dd59-1f92-5e99-978e-e5dd7a669bcb"] | 1 | ["39b97d53-5af7-55ea-bfc4-6f2f08f32e74"] | ["imported:semiconductor-atlas:iren-kiowa-oklahoma"] | ["proposed"] | 2026-09-08 | 2026-09-08 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f19474c4631ae00b2725/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f19474c4631ae00b2725.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f19474c4631ae00b2725.geojson | source-terms-not-recorded
vcc-site-f20ebb79d86fe03fc732 | curated:iron-mountain-mia-1-miami-data-center | Iron Mountain MIA-1 Miami Data Center | United States | US | 25.8842 | -80.2476 | Point | ["campus"] | ["official_address_range_geocode"] | ["census_single_exact_address_match_then_explicit_nad83_to_wgs84"] | ["official_address_range_interpolation_exact_facility_address_locator"] | ["official_source"] | ["campus_locator"] | ["Official Census street-address interpolation for the exact publisher- and government-bound MIA-1 address at 2925 NW 120th Terrace. Campus/project locator only; not a building centroid, parcel boundary, work extent, survey point or occupancy determination."] |  | No source-specific numerical horizontal-accuracy guarantee is published for the selected street-range interpolation. | ["69ecb4cd-be02-55fa-b978-732f307eeb00","b215f251-e72b-51f5-9363-705226aef274"] | 1 | ["24911fb6-56e2-5357-a224-8cbd977e2234"] | ["curated:iron-mountain-mia-1-miami-data-center:build"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f20ebb79d86fe03fc732/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f20ebb79d86fe03fc732.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f20ebb79d86fe03fc732.geojson | no-open-redistribution-license-asserted
vcc-site-f3c14c6227b2ae418664 | imported:semiconductor-atlas:openai-stargate-shackelford-county | Vantage Frontier campus (Stargate Shackelford County) | United States | US | 32.7089 | -99.3308 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Shackelford County centroid from OpenStreetMap Nominatim. Texas TDLR filings give a site address on Private Road 1604 with an Abilene mailing address in Shackelford County, but the road was not found in OpenStreetMap. Epoch AI places the campus just across the county line from the Abilene site, so the true site is likely west of this point."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["c23b8163-4dfb-5179-bdc2-bf2c0f07c255"] | 1 | ["126f2c37-cadc-5f20-9e3c-e544d70b5c37"] | ["imported:semiconductor-atlas:openai-stargate-shackelford-county"] | ["under_construction"] | 2026-09-08 | 2026-09-08 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f3c14c6227b2ae418664/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f3c14c6227b2ae418664.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f3c14c6227b2ae418664.geojson | source-terms-not-recorded
vcc-site-f42f9f22874b1766554e | curated:digital-edge-cgk-campus-bekasi | Digital Edge CGK Campus | Indonesia | ID | -6.3868 | 107.1871 | Polygon | ["host_estate"] | ["osm_way_nodes_to_polygon"] | ["osm_giic_way_568349989_v13_retained_as_host_estate_context_not_campus_locator"] | ["community_host_estate_polygon_context_only"] | ["community_source"] | ["host_estate_context"] | ["Entire Greenland International Industrial Center (GIIC) host estate as mapped by OSM way 568349989 version 13: a 458-vertex community polygon (a closed way of 459 node references) of about 2,113.63 ha (WGS84 geodesic, diagnostic). Digital Edge places CGK Campus only in the GIIC Industrial Estate; no reviewed source places CGK or CGK1 at any position within, or confirms containment in, this polygon. It also wholly contains the selected STT Jakarta Data Centre Campus geometry and, in the 2026-10-08 OSM snapshot, named data-centre buildings of AWS (ref CGK Sukamahi), Princeton Digital (JC3), Microsoft (JKT05, JKT11) and Digital Hyperspace. Host-estate locality context only: not a CGK or CGK1 locator, parcel, boundary, footprint or work extent. The display anchor is the planar centroid of the estate's longitude/latitude ring, kept unchanged only because the row schema requires a point; it is not a CGK position."] |  | CGK's position relative to this host-estate outline is unknown and no source bounds it; OpenStreetMap states no positional accuracy for the outline. No numeric uncertainty is asserted. | ["491b3b57-f2fb-53b4-ad33-07902a6d2e19","60324cce-b743-571c-ace0-813e7ae281bc","7133f023-619a-5656-a041-7f9af60abb61"] | 1 | ["b2e4945f-3d75-5d9b-b2bb-d65deb74c405"] | ["curated:digital-edge-cgk-campus-bekasi:cgk1"] | ["shell"] | 2026-06-08 | 2026-06-08 | recent_authoritative_physical_observation_plus_host_estate_context_only | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f42f9f22874b1766554e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f42f9f22874b1766554e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f42f9f22874b1766554e.geojson | CC-BY-SA-2.0; ODbL-1.0
vcc-site-f49882717c93278a3c62 | imported:semiconductor-atlas:homer-city-redevelopment | Homer City Energy Campus | United States | US | 40.5108 | -79.1936 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["approximate_site"] | ["compiled_reference"] | ["approximate_site_locator"] | ["Coordinates of the former Homer City Generating Station from Wikipedia (s6), which places it in Center Township near the borough of Homer City; the campus is built on the former station site, which covers a large area, so the point is approximate."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["78e4189f-fca3-5ade-9969-696d30129b77"] | 1 | ["7d6333d2-26e6-548c-979a-324c7113281b"] | ["imported:semiconductor-atlas:homer-city-redevelopment"] | ["under_construction"] | 2026-09-04 | 2026-09-04 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f49882717c93278a3c62/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f49882717c93278a3c62.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f49882717c93278a3c62.geojson | source-terms-not-recorded
vcc-site-f5c004356599de3efed9 | curated:nxtra-eko-atlantic-lagos-data-center | Nxtra Eko Atlantic Lagos Data Center Campus | Nigeria | NG | 6.4175 | 3.4214 | Point | ["campus"] | ["copy_literal_operator_LOS1_latitude_longitude_to_GeoJSON_longitude_latitude"] | ["copy_literal_operator_LOS1_latitude_longitude_to_GeoJSON_longitude_latitude"] | ["operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Operator-authored point tied to the named Lagos Eko Atlantic LOS1 campus. It is not a campus boundary, footprint, entrance or surveyed work-area center. Source digits are preserved."] |  | The operator provides no positional accuracy or survey metadata. Numeric precision does not establish accuracy. | ["a7227b84-a250-530e-bee8-51edf1231237","ac60e560-f381-5e36-ad8b-444ecc49cb2d"] | 1 | ["9fe862f6-ace2-5f5d-9c90-486fa4622982"] | ["curated:nxtra-eko-atlantic-lagos-data-center:current-facility-build"] | ["under_construction"] | 2026-07-23 | 2026-07-23 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f5c004356599de3efed9/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f5c004356599de3efed9.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f5c004356599de3efed9.geojson | CC-BY-4.0; all-rights-reserved
vcc-site-f616a1fa427698a3ecec | curated:dvz-schwerin-luebecker-strasse-campus | DVZ Schwerin Lübecker Straße Campus | Germany | DE | 53.647 | 11.3811 | Point | ["campus"] | ["copy_Overpass_center_for_named_DVZ_data_center_campus_way1545965488"] | ["copy_Overpass_center_for_named_DVZ_data_center_campus_way1545965488"] | ["community_mapped_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["A representative point for the entire named DVZ campus. The operator's plot description and TED exact-address clause bind the new building to this campus. The point is not claimed to locate the new building footprint or its active work extent; individual office centers are not selected."] |  | No source states survey accuracy or quantitative positional uncertainty. | ["123278b3-cec1-5c38-b035-facda8b70f25"] | 1 | ["c1016e49-7b45-52ff-8938-0bd01e78a7ad"] | ["curated:dvz-schwerin-luebecker-strasse-campus:new-modular-data-center-current-build"] | ["under_construction"] | 2026-07-31 | 2026-07-31 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f616a1fa427698a3ecec/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f616a1fa427698a3ecec.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f616a1fa427698a3ecec.geojson | ODbL-1.0
vcc-site-f65d3c659a862ad07679 | curated:oracle-project-jupiter-dona-ana-campus | Oracle Project Jupiter Doña Ana County AI Data Center Campus | United States | US | 31.8183 | -106.6653 | Polygon | ["facility"] | ["cross_source_geometry"] | ["frozen_openstreetmap_exact_project_jupiter_named_development_polygon_as_parent_campus_locator"] | ["reviewed_openstreetmap_named_project_jupiter_development_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped Project Jupiter development polygon used only to locate the parent campus. It is not an official parcel, legal campus boundary, project footprint, building outline, security boundary, or current construction-progress extent."] |  | OpenStreetMap supplies no survey, cadastral, planning-boundary, or numeric horizontal-accuracy statement. | ["0cad69d1-3151-5073-af8e-73f8401bf2cb"] | 1 | ["6f0acd88-cd04-5f3f-915c-48a71fd51f39"] | ["curated:oracle-project-jupiter-dona-ana-campus:current-campus-build"] | ["under_construction"] | 2026-09-14 | 2026-09-14 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f65d3c659a862ad07679/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f65d3c659a862ad07679.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f65d3c659a862ad07679.geojson | ODbL-1.0
vcc-site-f671a7ae44bca4e0f1f1 | curated:leitwerk-baden-cloud-lahr-campus | LEITWERK BADEN CLOUD Lahr Data Center Campus | Germany | DE | 48.3623 | 7.817 | Point | ["campus"] | ["official_INSPIRE_address_position_for_exact_operator_stated_site_address"] | ["LGL_BW_INSPIRE_AD_Address_DEBWhx01000s9CqQ_native_EPSG25832_to_WGS84_via_ETRS89_to_WGS84_1_round7"] | ["official_address_point_for_campus_site_address"] | ["official_source"] | ["campus_locator"] | ["Baden-Württemberg's official address position for Einsteinallee 14, the exact site address that the operator's own pages give for the Lahr data centre. It locates the addressed campus, not a data hall, phase, parcel boundary, footprint or current work extent. Native millimetre-serialized UTM coordinates were transformed once and rounded to seven decimals."] |  | The service publishes the position's placement intent (building) and method (by administrator) but no positional accuracy for individual points. The 1 m figure is the ETRS89 to WGS 84 operation's accuracy, not the point's accuracy. | ["05ae0c36-233c-5df1-a141-9576a0cb36ba","194b0923-7bbf-5769-b6ec-24d034caa47e","2f78833c-a01d-51fb-9395-3b52350e1505","3954fec5-a497-5881-b6df-94f7331ccb47","6e99cda8-409e-576a-bba9-524318b5121d","988e5b50-461f-56e3-9254-779362733688","c34338c5-2204-533c-b661-f79dc3605770","dba81a59-b894-51b7-bf27-a419276dea17","dd8ce815-c747-5b42-b7d7-fd4a10d74ff2"] | 1 | ["5e0d1954-690d-51cb-816a-88cec595f51a"] | ["curated:leitwerk-baden-cloud-lahr-campus:current-build"] | ["under_construction"] | 2026-06-19 | 2026-06-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f671a7ae44bca4e0f1f1/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f671a7ae44bca4e0f1f1.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f671a7ae44bca4e0f1f1.geojson | dl-de/by-2-0; no-open-license-asserted
vcc-site-f6a2889114e99d84b372 | imported:semiconductor-atlas:crusoe-tallgrass-cheyenne | Crusoe and Tallgrass AI data center campus near Cheyenne (Project Jade) | United States | US | 41.2737 | -104.7268 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["admin2"] | ["compiled_reference"] | ["admin2_context"] | ["Laramie County centroid from OpenStreetMap Nominatim. The announcement says only southeast Wyoming near Tallgrass's CO2 sequestration hub; analyst Cleanview places the project in Laramie County outside Cheyenne. No address or parcel was found."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["96e1e9b5-df0a-50d4-ab97-2b6ffff786ce"] | 1 | ["7a05f519-bf3a-5423-bd7f-fcb8e1cd6c0f"] | ["imported:semiconductor-atlas:crusoe-tallgrass-cheyenne"] | ["announced"] | 2025-07-24 | 2025-07-24 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f6a2889114e99d84b372/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f6a2889114e99d84b372.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f6a2889114e99d84b372.geojson | source-terms-not-recorded
vcc-site-f711d13af70d9b633456 | curated:meta-el-paso-texas-data-center | Meta El Paso Data Center | United States | US | 31.994 | -106.3632 | Point | ["campus"] | ["Use the single exact-name community feature, verify its source object geometry, and emit the unchanged service longitude/latitude in GeoJSON order."] | ["nominatim_exact_named_campus_reference_point"] | ["community_named_campus_reference_point"] | ["community_source"] | ["campus_locator"] | ["Source way explicitly says boundary very approximate. The returned point is only a broad campus locator consistent with the municipal north-of-Stan-Roberts, west-of-US54 description; neither the rectangle nor its slightly cross-state northern edge is selected as a legal boundary. No survey, exact building centroid, active construction footprint or bounded numerical accuracy is claimed."] |  | Community mapper and geocoder provide no bounded horizontal accuracy; coordinate decimal places are not measurement precision. | ["047b4c1b-72aa-5de6-b677-d5ba01d3a2a3","52580d24-8309-5295-99e6-7364f705bf1c","5492ab7f-9c74-548f-b15a-a0173d4d9c47","816746dd-9748-5937-8412-65422ee24556","90966722-c08a-559d-abf9-1e0cd87125ac"] | 1 | ["337ace90-652d-52fe-a856-fe9b04b5966f"] | ["curated:meta-el-paso-texas-data-center:current-development"] | ["under_construction"] | 2026-07-28 | 2026-07-28 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f711d13af70d9b633456/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f711d13af70d9b633456.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f711d13af70d9b633456.geojson | CC-BY-SA-2.0; ODbL-1.0; no-open-license-asserted
vcc-site-f72817dc402c9746aa98 | curated:datagrid-makarewa-ai-factory | Datagrid Makarewa AI Data Centre Campus | New Zealand | NZ | -46.3369 | 168.3875 | Polygon | ["campus"] | ["official_primary_parcel_union"] | ["linz_title_matched_primary_parcels_deterministic_union"] | ["official_cadastral_union_as_core_campus_locator"] | ["official_source"] | ["campus_locator"] | ["Current LINZ cadastral union for the four exact title-matched parcels making up about 49.2 hectares. It is not an asserted official project boundary, work extent, building footprint, as-built survey, or the full six-parcel consent property."] |  | LINZ publishes broad nominal urban and rural ranges but no bounded project-specific horizontal accuracy for this dissolved four-parcel locator. | ["e7f25be7-7451-526c-b584-30468a12afe5"] | 1 | ["c71872a1-fc95-5d5b-8ee8-6b5082e974df"] | ["curated:datagrid-makarewa-ai-factory:initial-horizontal-works"] | ["under_construction"] | 2026-08-18 | 2026-08-18 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f72817dc402c9746aa98/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f72817dc402c9746aa98.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f72817dc402c9746aa98.geojson | CC-BY-4.0
vcc-site-f764d5138ed8928c53bc | curated:capitaland-dc-itph-hyderabad | CapitaLand DC ITPH Hyderabad Campus | India | IN | 17.4353 | 78.3841 | Point | ["campus"] | ["first_party_published_map_pin"] | ["source_attribute_decimal_coordinates_to_point_without_centroiding"] | ["official_operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The dated results table names CapitaLand DC ITPH. The operator Hyderabad 01 property page explicitly places the data centre within International Tech Park Hyderabad at Madhapur. Its point locates that shared park/campus, not a surveyed data-centre building. No building, phase, construction extent or survey accuracy is asserted."] |  | The publisher supplies no numeric horizontal-accuracy statement or surveyed reference feature. | ["786fc8a6-df78-5a81-91bd-ab8f60443243"] | 1 | ["ea847e06-abc6-5935-ad21-a3c0adbec711"] | ["curated:capitaland-dc-itph-hyderabad:current-facility-build"] | ["under_construction"] | 2026-07-29 | 2026-07-29 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f764d5138ed8928c53bc/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f764d5138ed8928c53bc.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f764d5138ed8928c53bc.geojson | all-rights-reserved
vcc-site-f7c2acac6f50afd8adde | imported:semiconductor-atlas:powerhouse-poe-louisville-camp-ground-road | PowerHouse Louisville hyperscale campus (Camp Ground Road) | United States | US | 38.2561 | -85.7514 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Local sources place the campus on Camp Ground Road in southern or southwest Louisville without coordinates. The point is the Louisville city coordinate from its Wikipedia article, not the site."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["371c4d8b-d919-5614-9c6c-2d8b2976c0af"] | 1 | ["dd87fe4b-fdb0-5c4e-a906-70fda834e424"] | ["imported:semiconductor-atlas:powerhouse-poe-louisville-camp-ground-road"] | ["under_construction"] | 2026-08-13 | 2026-08-13 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f7c2acac6f50afd8adde/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f7c2acac6f50afd8adde.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f7c2acac6f50afd8adde.geojson | source-terms-not-recorded
vcc-site-f806b9a83ed45bed3268 | curated:digital-realty-330-east-cermak-chicago | Digital Realty 330 E. Cermak Site | United States | US | 41.8532 | -87.6195 | Polygon | ["building"] | ["cross_source_geometry"] | ["openstreetmap_exact_330_east_cermak_address_existing_building_polygon_as_current_facility_build_locator"] | ["reviewed_openstreetmap_330_east_cermak_existing_building_polygon"] | ["community_mapped"] | ["project_locator"] | ["Contributor-mapped polygon for the existing American Book Company Building at 330 East Cermak Road, used only to locate the Digital Realty current facility-build project. It is not the project boundary, current construction extent, parcel, official footprint, complete site, or proof that every part of the existing building is within the current build."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped building geometry is not cadastral, planning-authority, survey, or current-construction geometry. | ["b2a12b58-767d-5517-9d63-a5d6fc6e9426"] | 1 | ["01baa3bb-ea56-5f41-8c67-82dd84f87d51"] | ["curated:digital-realty-330-east-cermak-chicago:current-facility-build"] | ["under_construction"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f806b9a83ed45bed3268/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f806b9a83ed45bed3268.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f806b9a83ed45bed3268.geojson | ODbL-1.0
vcc-site-f8df65a48b8288eac8cb | imported:semiconductor-atlas:airtrunk-jhb4-iskandar-puteri | AirTrunk JHB4 Johor Bahru | Malaysia | MY | 1.4222 | 103.65 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["AirTrunk and W.Media name Iskandar Puteri without an address; the point is the Iskandar Puteri coordinate from its Wikipedia article, so it marks the city rather than the campus."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["c8b886b2-f389-5c16-8c04-57ce8610a2aa"] | 1 | ["db7fc7c1-cc03-5473-80b8-31b36c8224d5"] | ["imported:semiconductor-atlas:airtrunk-jhb4-iskandar-puteri"] | ["announced"] | 2026-04-30 | 2026-04-30 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f8df65a48b8288eac8cb/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f8df65a48b8288eac8cb.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f8df65a48b8288eac8cb.geojson | source-terms-not-recorded
vcc-site-f95670603a10a1f6f24b | curated:goodman-fra02-frankfurt-data-centre-campus | Goodman FRA02 Frankfurt Data Centre Campus | Germany | DE | 50.0427 | 8.6855 | Point | ["campus"] | ["first_party_brochure_published_map_link_target"] | ["resolve_official_PDF_hyperlink_and_select_marker_coordinates_without_geocoding_or_centroiding"] | ["official_operator_published_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Goodman's FRA II brochure links this campus point at Rathenaustrasse 31; the city identifies the same Rathenaustrasse project as FRA02. The point is not a specific building, phase, substation, parcel boundary, campus footprint or June 30 active-work extent. Two campus buildings remain one physical site."] |  | Neither Goodman nor the linked marker supplies a numeric horizontal-accuracy statement or identifies a surveyed reference feature. | ["aaab4a40-99dd-50ee-a496-a7d7c2e44fe7","f84e5176-a3af-53b3-88ad-f29294ea2b3d"] | 1 | ["4f86e285-bcf1-537b-b31e-8af7b27ed556"] | ["curated:goodman-fra02-frankfurt-data-centre-campus:phase-1-current-development"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f95670603a10a1f6f24b/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f95670603a10a1f6f24b.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f95670603a10a1f6f24b.geojson | all-rights-reserved
vcc-site-f9661fed6650ccc21ce2 | curated:ai-tech-tomakomai-kashiwabara | AI Tech Tomakomai Kashiwabara Data Center Campus | Japan | JP | 42.6952 | 141.7662 | Polygon | ["campus"] | ["association_converted_official_cadastral_reference_polygon"] | ["retain_CRS84_AIGID_MOJ_2026_feature29260_Kashiwabara32_17_polygon_and_derive_planar_display_centroid"] | ["community_conversion_of_named_cadastral_parcel_containing_selected_project"] | ["community_source"] | ["campus_locator"] | ["The company names the same cadastral parcel as its data-center site. The association-converted polygon is retained as a reference parcel, not promoted to an official campus boundary, surveyed building footprint, active Phase I work extent or substation boundary. The centroid is only a derived display anchor. The same-number four other-city-district parcels and the Tokyo corporate office are excluded."] |  | The source classifies this as graphically measured map data and provides no numeric parcel-specific horizontal uncertainty. CRS84 coordinates are retained, without claiming survey precision or exact datum-realization accuracy. | ["043916cc-e7ce-5a3d-a8a7-d3dc7bd28038","17a317b4-d4a3-5fc0-b852-09cdfaf3de99","1c0a3b0c-6e89-5bf2-aaca-bed6426d2b2f","bb068d33-84b8-51c6-bf12-3a96045eddd7","de4550fe-a477-5719-879b-41a2628fc130"] | 1 | ["100cf064-1cae-5dba-a4d9-6c4ae35152ec"] | ["curated:ai-tech-tomakomai-kashiwabara:phase1-foundations"] | ["under_construction"] | 2026-06-19 | 2026-06-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f9661fed6650ccc21ce2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f9661fed6650ccc21ce2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f9661fed6650ccc21ce2.geojson | CC-BY-version-unspecified; underlying MOJ-map-data-custom-terms-2023-01-23; MOJ-map-data-custom-terms-2023-01-23
vcc-site-f98926ffb5ad45066954 | curated:digital-realty-fra20-frankfurt | Digital Realty Digital Park Fechenheim Campus | Germany | DE | 50.1259 | 8.7528 | Point | ["campus"] | ["literal_operator_facility_latitude_longitude_reordered_without_numeric_transform"] | ["first_party_named_constituent_facility_marker_with_static_frontend_and_wgs84_contract"] | ["official_operator_published_constituent_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["FRA20 constituent facility marker at Hugo-Junkers-Strasse 5a, used solely to locate the physical Digital Park Fechenheim campus shared with UW04. Not the UW04 building, its entrance/address, a transformer position, cadastral parcel, campus boundary, active work extent or quantified survey location."] |  | Operator publishes no positional accuracy; six decimal places and a documented datum do not establish survey accuracy. | ["1deeba50-c61e-5703-a5eb-a4b870f9a9ea","5df585a4-222b-5dbd-9e0f-3abef084dbdd","b5ab3aa2-b2f0-520f-a60a-debc9a6c6a1b","de30d8ff-1dd6-500b-b538-0704dd5ae94e","e3dc329e-f986-5f88-a671-fcfae64ead54","ef0201ca-7de5-55f6-bf43-747baf258e07","efec83a1-a199-5bd0-a4d9-66ee81370b4b"] | 1 | ["b0588082-53ae-577a-b989-667b8f9f171d"] | ["curated:digital-realty-fra20-frankfurt:uw04-substation-current-build"] | ["under_construction"] | 2026-07-02 | 2026-07-02 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f98926ffb5ad45066954/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f98926ffb5ad45066954.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-f98926ffb5ad45066954.geojson | CC-BY-4.0; no-open-license-asserted
vcc-site-faa101d551da0c45f1c5 | curated:iron-mountain-amsterdam-data-center-campus | Iron Mountain Amsterdam Data Center Campus | Netherlands | NL | 52.3917 | 4.6647 | Point | ["campus"] | ["official_notice_source_point"] | ["EPSG_28992_to_EPSG_4326_always_xy_with_documented_Amersfoort_transform"] | ["official_permit_notice_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["The provincial notice point locates the campus at J.W. Lucasweg 35, Haarlem, not the selected expansion building's footprint. Linking the owner's AMS-2 10 MW description to the SEC AMS-1 Phase 4 row is an analyst identity inference from the same campus, 10 MW scope and Q2 2027 schedule, not an explicit issuer renaming statement. The separate 20 MW held-development row is excluded. Existing and future campus buildings count once."] |  | No source-specific numeric horizontal accuracy is published; transform operation accuracy is not site-locator uncertainty. | ["4791ed5e-b266-5f0f-b86f-d183cc829ba2","583562f6-1d06-596e-81cc-289524fe0c00"] | 1 | ["e3f1fc38-bc59-5373-803f-d5c86d817096"] | ["curated:iron-mountain-amsterdam-data-center-campus:ams-2-10mw-expansion"] | ["under_construction"] | 2026-06-30 | 2026-06-30 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-faa101d551da0c45f1c5/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-faa101d551da0c45f1c5.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-faa101d551da0c45f1c5.geojson | no-open-redistribution-license-asserted
vcc-site-fbb0a56d0fdb8284922c | curated:ntt-frankfurt-1-campus | NTT Frankfurt 1 Data Center Campus | Germany | DE | 50.1293 | 8.602 | Polygon | ["facility"] | ["cross_source_geometry"] | ["openstreetmap_named_ntt_global_data_centers_campus_polygon_with_exact_contained_address_objects_as_parent_campus_locator"] | ["reviewed_openstreetmap_named_ntt_global_data_centers_campus_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped named NTT campus polygon used only to locate the parent Frankfurt 1 campus. It is not the 7.3MW expansion point or footprint, a complete current or legal campus extent, an official parcel, cadastral, planning, or survey boundary, a building footprint, or a current construction-progress extent."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry and address objects are not cadastral, planning-authority, or survey geometry. | ["eb188ade-b0ff-5b98-bbd4-83cee821ca4b"] | 1 | ["b3b98301-a692-5790-88e7-656d77e8fb69"] | ["curated:ntt-frankfurt-1-campus:7-3mw-expansion"] | ["under_construction"] | 2026-07-19 | 2026-07-19 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fbb0a56d0fdb8284922c/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fbb0a56d0fdb8284922c.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fbb0a56d0fdb8284922c.geojson | ODbL-1.0
vcc-site-fcc06643c640f5d8cce2 | curated:microsoft-mount-pleasant-datacenter-campus | Microsoft Mount Pleasant Datacenter Campus | United States | US | 42.6765 | -87.9103 | Polygon | ["campus"] | ["cross_source_overlay"] | ["openstreetmap_named_construction_area_polygon_as_campus_locator"] | ["reviewed_openstreetmap_named_microsoft_fairwater_phase_2_construction_area_polygon"] | ["community_mapped"] | ["campus_locator"] | ["Contributor-mapped polygon for a named Microsoft Fairwater Phase 2 construction area, used only to locate the Mount Pleasant datacenter campus. It is not an official campus boundary, the complete campus extent, a parcel, a building footprint, the official second-facility footprint, a construction-progress extent, or a survey-accuracy claim."] |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | ["ab38ac59-f17b-5f63-b060-392d2bebd078"] | 2 | ["0f5f4fcc-53c4-53d0-9795-2a387d195364","ccb7fe0e-f94d-58ca-8d36-695a9cd48d56"] | ["curated:microsoft-mount-pleasant-datacenter-campus:second-facility","imported:semiconductor-atlas:microsoft-fairwater-mount-pleasant"] | ["partially_operational","under_construction"] | 2026-06-23 | 2026-06-23 | mixed_review_postures | FALSE | ["not_reviewed","tracked_identity_bound_uncertain_unsuperseded_no_construction_claim"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fcc06643c640f5d8cce2/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fcc06643c640f5d8cce2.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fcc06643c640f5d8cce2.geojson | ODbL-1.0
vcc-site-fcd641148c4f61598efc | imported:semiconductor-atlas:project-sail-coweta-county | Project Sail (Prologis data center campus, Coweta County) | United States | US | 33.376 | -84.788 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Coordinates are the Wikipedia centroid of Sargent (s5). The river group's fact sheet (s1) places the site in rural Sargent about 7 miles northwest of Newnan, with Wahoo Creek crossing the property; no parcel coordinates were found."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["2866b764-c7b1-5435-8585-2f4a496a00f3"] | 1 | ["4a2847d7-f84f-5f89-a4c2-ee832e1f6cad"] | ["imported:semiconductor-atlas:project-sail-coweta-county"] | ["announced"] | 2026-04-09 | 2026-04-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fcd641148c4f61598efc/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fcd641148c4f61598efc.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fcd641148c4f61598efc.geojson | source-terms-not-recorded
vcc-site-fcfc181b3d5d02fb0a65 | imported:semiconductor-atlas:meta-beaver-dam | Meta Beaver Dam data center | United States | US | 43.4578 | -88.8373 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["City point from OpenStreetMap Nominatim; Meta names the city but no site or road."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["38a97c43-cfaf-5c4e-8a2a-12611c839cbd"] | 1 | ["eaaa4486-a9d9-5cf1-b196-d03c258f8dc1"] | ["imported:semiconductor-atlas:meta-beaver-dam"] | ["under_construction"] | 2026-10-09 | 2026-10-09 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fcfc181b3d5d02fb0a65/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fcfc181b3d5d02fb0a65.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fcfc181b3d5d02fb0a65.geojson | source-terms-not-recorded
vcc-site-fdb92bb99c36b43e6162 | epoch-ai:data-center:1fb39208-53bc-5714-80d2-881a5c944551 | Start Campus Sines Data Campus | Portugal | PT | 37.9384 | -8.8055 | Point | ["campus"] | ["official_georeferenced_drawing_shared_area_centroid_transformed_to_crs84"] | ["apa_sin02_06_shared_multi_phase_area_centroid_as_campus_locator"] | ["official_shared_multi_phase_area_centroid_as_campus_locator"] | ["official_source"] | ["campus_locator"] | ["The point is an approximate centroid of the official shared SIN02-06 multi-phase area. It is not the SIN02 facility, an entrance, survey point, parcel, campus boundary, project footprint, building footprint, or current-work point or extent."] | 25 |  | ["26d88bed-8fc2-5e71-8683-68d3b9bb1ee3"] | 2 | ["3a54ff50-0fd6-5767-86f2-c6818a515bb2","94c0f50d-843b-57cd-bfcd-4bd3b7b9d9f0"] | ["curated:start-campus-sines-data-campus:sin02-current-facility-build","imported:semiconductor-atlas:start-campus-sines"] | ["partially_operational","under_construction"] | 2026-06-23 | 2026-08-03 | mixed_review_postures | FALSE | ["not_reviewed","not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fdb92bb99c36b43e6162/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fdb92bb99c36b43e6162.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fdb92bb99c36b43e6162.geojson | rights-status-uncertain-fact-extraction-only
vcc-site-fe662eaf021a8dc4f203 | curated:monarch-compute-campus-point-pleasant-west-virginia | Monarch Compute Campus Point Pleasant | United States | US | 38.9169 | -82.1111 | Point | ["campus"] | ["exact_official_registration_geometry"] | ["WVDEP_WVR113311_native3857_to_source4326_independently_checked"] | ["official_constituent_campus_reference_point"] | ["official_source"] | ["campus_locator"] | ["Exact official Power Generation Pad South registration point, associated by explicit integrated-campus identity plus analyst reconciliation. Not a data-center hall, entrance, construction footprint, campus centroid, surveyed location or1100/2250-acre boundary."] |  | No source numerical positional accuracy or point-placement method. | ["561599d5-1050-50f3-842f-9112db1fca3f","6b75b539-7052-581e-8917-705f59bcc673","7df45990-aacd-5519-86c7-0f3d4a2bee4a","f4de824e-a9b1-581b-b83f-152393af714f","f7352fdb-963a-5f76-bed8-d0d1fe72fb85"] | 1 | ["762397cd-ffc7-55c2-936e-af38cb8d4d0c"] | ["curated:monarch-compute-campus-point-pleasant-west-virginia:current-site-preparation"] | ["under_construction"] | 2026-07-14 | 2026-07-14 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fe662eaf021a8dc4f203/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fe662eaf021a8dc4f203.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fe662eaf021a8dc4f203.geojson | no-open-license-asserted
vcc-site-fe9285f72381fc346e86 | curated:ast-janciems-dispatcher-control-data-center | AST Jāņciems Dispatcher Control and Data Centre | Latvia | LV | 56.9331 | 24.1815 | Point | ["project"] | ["direct_geometry"] | ["authoritative_address_geocode"] | ["facility_address_point"] | ["official_source"] | ["reviewed_site_locator"] | ["Current Latvian State Land Service address-register point, facility-specific, with 20 metre stated uncertainty."] | 20 |  | ["458f3a8b-8978-5fa6-a7f9-35d2f1801375"] | 1 | ["98e47ac5-8576-53f7-ab71-9f3d683b5ec5"] | ["curated:ast-janciems-dispatcher-control-data-center:fit-out-after-building-completion"] | ["shell"] | 2026-06-27 | 2026-06-27 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | ["not_reviewed_for_core_preview"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fe9285f72381fc346e86/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fe9285f72381fc346e86.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-fe9285f72381fc346e86.geojson | CC-BY-4.0
vcc-site-ff3fe91dbbe9f9beaf9e | imported:semiconductor-atlas:natelli-new-hill-digital-campus | New Hill Digital Campus | United States | US | 35.6811 | -78.9356 | Point | ["project"] | ["imported_reference_point"] | ["imported_reference_point"] | ["locality"] | ["compiled_reference"] | ["locality_context"] | ["Wikipedia coordinates for the New Hill community. WRAL places the site on Shearon Harris Road beside the Shearon Harris nuclear plant, a few kilometres south of this point; no cited source gives site coordinates."] |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ["b65b4f7b-10e1-58b6-ae22-7f723d348388"] | 1 | ["03207f8c-1d9d-577f-9d8c-af881144fb86"] | ["imported:semiconductor-atlas:natelli-new-hill-digital-campus"] | ["cancelled"] | 2026-03-10 | 2026-03-10 | imported_source_record | FALSE | ["not_reviewed"] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ff3fe91dbbe9f9beaf9e/ | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ff3fe91dbbe9f9beaf9e.json | https://kiankyars.github.io/datacenter-atlas/api/v1/sites/vcc-site-ff3fe91dbbe9f9beaf9e.geojson | source-terms-not-recorded

## projects
project_id | project_stable_key | site_id | physical_site_stable_key | name | country | country_iso_a2 | latitude | longitude | geometry_type | geometry_source_entity_kind | geometry_derivation | geometry_method | geometry_scope_class | geometry_authority_class | geometry_use_scope | geometry_precision_scope | horizontal_uncertainty_metres | horizontal_uncertainty_unknown_reason | geometry_evidence_id | last_observed_physical_status | status_as_of | status_age_days_at_review | status_method | status_evidence_id | verification_posture | independent_imagery_verification | imagery_review_outcome | development_type | development_type_unknown_reason | operating_model | operating_model_unknown_reason | operating_model_evidence_id | workloads_json | workload_unknown_reason | role_claims_json | power_observations_json | power_unknown_reason | annual_energy_observations_json | annual_energy_unknown_reason | efficiency_observations_json | efficiency_unknown_reason | owner | operator | users | tenants | customers | status_source_url | geometry_source_url | project_details_json | url | api_url
010c4071-5901-54ea-a312-f59d53358a0a | curated:ezditek-ruh01-pnu-riyadh-data-center:phase-1-current-build | vcc-site-ca4532d5353073b32508 | curated:ezditek-ruh01-pnu-riyadh-data-center | Ezditek RUH01 Phase 1 Current Build | Saudi Arabia | SA | 24.867 | 46.714 | Polygon | building | capture_replayed_geometry | capture_replayed_openstreetmap_exact_ezditek_ruh01_named_building_polygon_as_project_locator | community_mapped_named_ezditek_ruh01_building_polygon | community_mapped | project_locator | Contributor-mapped building polygon explicitly tagged operator=Ezditek, ref=RUH01, telecom=data_center, used only to locate the selected RUH01 Phase 1 project. It is not an official, cadastral, planning, survey, parcel, security, Phase 1, or current-construction boundary. |  | OpenStreetMap supplies no survey, cadastral, planning-authority, or numeric horizontal-accuracy statement for this way. | b91493e8-2d06-5029-8df8-bfc06d77f418 | under_construction | 2026-06-18 | 117 | authoritative_physical_status_update | f7185801-68f1-568d-ac6f-602eb4be0e8b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.13 geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/embed/feed/update/urn:li:activity:7473316883811930112 | https://api.openstreetmap.org/api/0.6/way/1544103564/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ca4532d5353073b32508/#project-010c4071-5901-54ea-a312-f59d53358a0a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/010c4071-5901-54ea-a312-f59d53358a0a.json
016877e7-a475-5ebe-9219-0ac699cfff53 | imported:semiconductor-atlas:datavolt-oxagon | vcc-site-a55b68896de9ae43657e | imported:semiconductor-atlas:datavolt-oxagon | DataVolt Oxagon AI data centre campus (NEOM) | Saudi Arabia | SA | 27.5679 | 35.546 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Oxagon in NEOM but not a parcel. Coordinates are the OpenStreetMap Nominatim result for Oxagon (a construction land-use area in Duba governorate, Tabuk region). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ec1bd3eb-3559-5ed2-a446-9a875bd7abfe | under_construction | 2026-09-07 | 36 | imported_documented_status | 020ae58c-6caf-51af-ba92-3ec539c5f030 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ec1bd3eb-3559-5ed2-a446-9a875bd7abfe","notes":"Develops the campus under its 2025 agreement with NEOM and will also operate it.","party":"DataVolt","relationship_scope":"unknown","role":"developer","source_record_id":"datavolt-oxagon"},{"evidence_id":"ee849430-43e1-5e54-8bb7-b5babdc94773","notes":"Develops the campus under its 2025 agreement with NEOM and will also operate it.","party":"DataVolt","relationship_scope":"unknown","role":"developer","source_record_id":"datavolt-oxagon"},{"evidence_id":"ec1bd3eb-3559-5ed2-a446-9a875bd7abfe","notes":null,"party":"DataVolt","relationship_scope":"unknown","role":"operator","source_record_id":"datavolt-oxagon"},{"evidence_id":"ee849430-43e1-5e54-8bb7-b5babdc94773","notes":null,"party":"DataVolt","relationship_scope":"unknown","role":"operator","source_record_id":"datavolt-oxagon"},{"evidence_id":"ec1bd3eb-3559-5ed2-a446-9a875bd7abfe","notes":"Committed an initial USD 5 billion for the first phase.","party":"DataVolt","relationship_scope":"unknown","role":"investor","source_record_id":"datavolt-oxagon"},{"evidence_id":"020ae58c-6caf-51af-ba92-3ec539c5f030","notes":"Co-develops the first 100 MW block with DataVolt and contributes its AI technology stack; advised by Hogan Lovells Cadwalader on the first phase.","party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"datavolt-oxagon"},{"evidence_id":"ee849430-43e1-5e54-8bb7-b5babdc94773","notes":"Co-develops the first 100 MW block with DataVolt and contributes its AI technology stack; advised by Hogan Lovells Cadwalader on the first phase.","party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"datavolt-oxagon"},{"evidence_id":"54d49199-3c96-5d2e-ad5a-1b50b9a7dec2","notes":"Co-develops the first 100 MW block with DataVolt and contributes its AI technology stack; advised by Hogan Lovells Cadwalader on the first phase.","party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"datavolt-oxagon"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | DataVolt |  |  |  | https://www.neom.com/en-us/newsroom/HUMAIN-and-DataVolt-to-develop-AI-data-center-in-NEOM | https://www.neom.com/en-us/newsroom/datavolt-signs-agreement-with-neom | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve DataVolt Oxagon AI data centre campus (NEOM) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"datavolt-oxagon"},"record":{"aliases":["NEOM net-zero AI factory campus","Oxagon AI data center campus"],"id":"datavolt-oxagon","last_reviewed":"2026-10-09","location":{"admin1":"Tabuk Province","country":"SA","lat":27.5679,"locality":"Oxagon, NEOM","lon":35.546,"note":"Sources name Oxagon in NEOM but not a parcel. Coordinates are the OpenStreetMap Nominatim result for Oxagon (a construction land-use area in Duba governorate, Tabuk region).","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-31","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":1500},{"applies_to":"phase","as_of":"2026-08-31","basis":"planned","metric":"power_capacity","phase_label":"First phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3","s5"],"unit":"MW","value":360},{"applies_to":"phase","as_of":"2026-09-07","basis":"under_construction","metric":"power_capacity","phase_label":"Initial HUMAIN-DataVolt block","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3","s4"],"unit":"MW","value":100},{"applies_to":"phase","as_of":"2025-02-10","basis":"announced","metric":"investment","note":"Initial DataVolt investment announced to fund the first phase, before the first phase was sized at 360 MW.","phase_label":"First phase","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":5000000000},{"applies_to":"phase","as_of":"2026-09-07","basis":"reported","metric":"investment","note":"Cost of the initial 100 MW facility as reported by Semafor; the article does not attribute the figure to DataVolt.","phase_label":"Initial HUMAIN-DataVolt block","qualifier":"approximately","source_ids":["s4"],"unit":"USD","value":1000000000}],"milestones":[{"date":"2025-02-10","event":"announced","kind":"actual","note":"DataVolt and NEOM signed the campus agreement, including a land lease at Oxagon.","source_ids":["s1"]},{"date":"2026-08-31","event":"construction_started","kind":"actual","note":"Groundbreaking announced at LEAP for the 360 MW first phase, starting with the 100 MW block.","source_ids":["s2","s3"]},{"date":"2028","event":"first_operational","kind":"planned","note":"Ready-for-service target for the first 100 MW. Semafor reported in September 2026 that DataVolt plans to finish the first 100 MW facility within 13 months, which would be earlier than 2028.","source_ids":["s1","s2","s3","s4","s5"]}],"name":"DataVolt Oxagon AI data centre campus (NEOM)","notes":"Customer plans differ by source: DataVolt's release says the campus will serve international and domestic customers, while its chief executive told Semafor all capacity would be sold abroad. The August 2026 company releases disclose no investment figure for the 100 MW block; the only figure is Semafor's own estimate. DataVolt's chief executive also said project financing for the first facility was close to being secured.","parties":[{"name":"DataVolt","note":"Develops the campus under its 2025 agreement with NEOM and will also operate it.","role":"developer","source_ids":["s1","s3"]},{"name":"DataVolt","role":"operator","source_ids":["s1","s3"]},{"name":"DataVolt","note":"Committed an initial USD 5 billion for the first phase.","role":"investor","source_ids":["s1"]},{"name":"HUMAIN","note":"Co-develops the first 100 MW block with DataVolt and contributes its AI technology stack; advised by Hogan Lovells Cadwalader on the first phase.","role":"developer","source_ids":["s2","s3","s5"]}],"power_sources":[{"description":"The 2025 agreement says the campus is to run on renewable energy and operate at net zero, and the 2026 releases say it will integrate renewable sources; Oxagon is promoted as offering cost-competitive renewables and green hydrogen, but no specific supply has been named.","source_ids":["s1","s2","s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-02-10","publisher":"NEOM","title":"DataVolt signs agreement with NEOM to design and develop the region's first truly sustainable, net-zero AI factory campus in Oxagon","type":"company","url":"https://www.neom.com/en-us/newsroom/datavolt-signs-agreement-with-neom"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-31","publisher":"NEOM","title":"HUMAIN partners with DataVolt to jointly develop 100MW of a 360MW AI data center project in NEOM","type":"company","url":"https://www.neom.com/en-us/newsroom/HUMAIN-and-DataVolt-to-develop-AI-data-center-in-NEOM"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-31","publisher":"DataVolt","title":"HUMAIN Partners with DataVolt to Jointly Develop 100MW of a 360MW AI Data Center Project in NEOM","type":"company","url":"https://data-volt.com/media/breaking-news/humain-partners-datavolt-develop-100mw-of-a-360mw-ai-datacenter-in-neom/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260907210848/https://www.semafor.com/article/09/07/2026/saudi-arabian-data-center-firm-races-to-export-compute-from-neom","id":"s4","published":"2026-09-07","publisher":"Semafor","title":"Saudi Arabian data center firm races to export compute from NEOM","type":"news","url":"https://www.semafor.com/article/09/07/2026/saudi-arabian-data-center-firm-races-to-export-compute-from-neom"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-07","publisher":"Hogan Lovells Cadwalader","title":"Hogan Lovells Cadwalader advises HUMAIN on AI data center development in Saudi Arabia","type":"other","url":"https://hlc.com/en/news/hogan-lovells-cadwalader-advises-humain-on-ai-data-center-development-in-saudi-arabia"}],"status":"under_construction","status_as_of":"2026-09-07","status_source_ids":["s2","s3","s4"],"summary":"Saudi developer DataVolt plans a 1.5 GW AI data centre campus at Oxagon, NEOM's industrial city on the Red Sea coast, on land leased from Oxagon. Under the February 2025 agreement DataVolt committed an initial USD 5 billion to the first phase, which is meant to run on renewable power. In August 2026 DataVolt and HUMAIN broke ground on a jointly developed 100 MW block within a 360 MW first phase, with the first 100 MW expected in service in 2028. Semafor reported in September 2026 that the initial facility would cost about USD 1 billion, and DataVolt's chief executive said the compute would be sold to customers abroad.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"ec1bd3eb-3559-5ed2-a446-9a875bd7abfe","s2":"020ae58c-6caf-51af-ba92-3ec539c5f030","s3":"ee849430-43e1-5e54-8bb7-b5babdc94773","s4":"28c33ea5-e84c-5d84-aa08-9603a4d56df3","s5":"54d49199-3c96-5d2e-ad5a-1b50b9a7dec2"},"source_file":"datacenters/projects/datavolt-oxagon.json","source_record_id":"datavolt-oxagon","source_record_sha256":"55133dd6d75ca52eb0ee78922496756fb284d18ccf52ac00be1955a870a6a561","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"79f79d176b9e284611718789a59964c7f458094219717cf28126b09478697cda"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a55b68896de9ae43657e/#project-016877e7-a475-5ebe-9219-0ac699cfff53 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/016877e7-a475-5ebe-9219-0ac699cfff53.json
01baa3bb-ea56-5f41-8c67-82dd84f87d51 | curated:digital-realty-330-east-cermak-chicago:current-facility-build | vcc-site-f806b9a83ed45bed3268 | curated:digital-realty-330-east-cermak-chicago | Digital Realty 330 E. Cermak Current Facility Build | United States | US | 41.8532 | -87.6195 | Polygon | building | cross_source_geometry | openstreetmap_exact_330_east_cermak_address_existing_building_polygon_as_current_facility_build_locator | reviewed_openstreetmap_330_east_cermak_existing_building_polygon | community_mapped | project_locator | Contributor-mapped polygon for the existing American Book Company Building at 330 East Cermak Road, used only to locate the Digital Realty current facility-build project. It is not the project boundary, current construction extent, parcel, official footprint, complete site, or proof that every part of the existing building is within the current build. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped building geometry is not cadastral, planning-authority, survey, or current-construction geometry. | b2a12b58-767d-5517-9d63-a5d6fc6e9426 | under_construction | 2026-07-19 | 86 | authoritative_physical_status_update | 9f47299f-1ce7-579f-b0b8-1bd454faabd5 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.digitalrealty.com/about/projects/digital-cermak | https://www.openstreetmap.org/way/210537873 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f806b9a83ed45bed3268/#project-01baa3bb-ea56-5f41-8c67-82dd84f87d51 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/01baa3bb-ea56-5f41-8c67-82dd84f87d51.json
02a9ee88-08e5-58fd-b715-488b3ee903a3 | curated:jera-chiba-thermal-power-station:ai-datacenter-campus | vcc-site-08c96f4448334dc081a5 | curated:jera-chiba-thermal-power-station | JERA / RHAELM Chiba AI Data Center Infrastructure | Japan | JP | 35.5638 | 140.102 | Point | campus | direct_geometry | operator_selected_map_feature_coordinates | operator_published_host_campus_map_reference | compiled_reference | campus_locator | Operator-selected host power-station address feature; no AI data-center plot, building footprint or phase boundary is established. |  | No positional accuracy or AI plot is published. The plant spans about76ha and the DC location within it is unknown. Decimal precision reflects map parameters, not surveyed accuracy. | a25bcee2-8a5a-5951-81ba-924dd0c09607 | announced | 2026-10-01 | 12 | authoritative_project_announcement | 306c783a-a273-51e4-a2c2-9c40e2912596 | authoritative_project_record_plus_scoped_location | FALSE | not_reviewed | unknown | not established by selected evidence | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.jera.co.jp/news/information/20261001_2535 | https://maps.google.com/?cid=8004290950342727219 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-08c96f4448334dc081a5/#project-02a9ee88-08e5-58fd-b715-488b3ee903a3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/02a9ee88-08e5-58fd-b715-488b3ee903a3.json
03207f8c-1d9d-577f-9d8c-af881144fb86 | imported:semiconductor-atlas:natelli-new-hill-digital-campus | vcc-site-ff3fe91dbbe9f9beaf9e | imported:semiconductor-atlas:natelli-new-hill-digital-campus | New Hill Digital Campus | United States | US | 35.6811 | -78.9356 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for the New Hill community. WRAL places the site on Shearon Harris Road beside the Shearon Harris nuclear plant, a few kilometres south of this point; no cited source gives site coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | b65b4f7b-10e1-58b6-ae22-7f723d348388 | cancelled | 2026-03-10 | 217 | imported_documented_status | 3b847726-3c79-5d0b-8e80-70c0498fd745 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3b847726-3c79-5d0b-8e80-70c0498fd745","notes":null,"party":"Natelli Investments","relationship_scope":"unknown","role":"developer","source_record_id":"natelli-new-hill-digital-campus"},{"evidence_id":"b65b4f7b-10e1-58b6-ae22-7f723d348388","notes":null,"party":"Natelli Investments","relationship_scope":"unknown","role":"developer","source_record_id":"natelli-new-hill-digital-campus"},{"evidence_id":"b15455cd-25b4-5e61-b70c-33d0359a295f","notes":null,"party":"Natelli Investments","relationship_scope":"unknown","role":"developer","source_record_id":"natelli-new-hill-digital-campus"},{"evidence_id":"b65b4f7b-10e1-58b6-ae22-7f723d348388","notes":"Annexation and rezoning authority for the site.","party":"Town of Apex","relationship_scope":"unknown","role":"government","source_record_id":"natelli-new-hill-digital-campus"},{"evidence_id":"3b847726-3c79-5d0b-8e80-70c0498fd745","notes":"Annexation and rezoning authority for the site.","party":"Town of Apex","relationship_scope":"unknown","role":"government","source_record_id":"natelli-new-hill-digital-campus"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.bisnow.com/news/raleigh-durham/data-center/massive-raleigh-area-data-center-scrapped-133584 | https://www.wral.com/news/local/natelli-withdraws-apex-data-center-project-shearon-harris-march-2026/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve New Hill Digital Campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"natelli-new-hill-digital-campus"},"record":{"aliases":["Apex data center (Natelli Investments)"],"id":"natelli-new-hill-digital-campus","last_reviewed":"2026-10-09","location":{"admin1":"North Carolina","admin2":"Wake County","country":"US","lat":35.6811,"locality":"New Hill","lon":-78.9356,"note":"Wikipedia coordinates for the New Hill community. WRAL places the site on Shearon Harris Road beside the Shearon Harris nuclear plant, a few kilometres south of this point; no cited source gives site coordinates.","precision":"locality","source_ids":["s2","s1"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-10","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2026-03-10","basis":"planned","metric":"land_area","note":"A WRAL photo caption gives 190 acres.","qualifier":"approximately","source_ids":["s1","s2"],"unit":"acres","value":189}],"milestones":[{"date":"2025-09","event":"announced","kind":"actual","note":"Bisnow, writing in March 2026, says the developer first proposed the project in September and requested rezoning last fall, which places it in 2025. WRAL reports residents were already pushing back in August, so the proposal may have been known earlier.","source_ids":["s1"]},{"date":"2026-03-05","event":"cancelled","kind":"actual","note":"Natelli withdrew its annexation and rezoning applications on 5 March, per WRAL; ABC11 reports the company's announcement on 7 March.","source_ids":["s2","s1","s3"]}],"name":"New Hill Digital Campus","notes":"Recorded as cancelled because the developer withdrew its applications and the coverage describes the project as scrapped; Natelli said it could decide on a further course of action if Apex later adopts a zoning amendment allowing data centers.","parties":[{"name":"Natelli Investments","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Town of Apex","note":"Annexation and rezoning authority for the site.","role":"government","source_ids":["s2","s1"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-03-10","publisher":"Bisnow","title":"Apex Data Center Scrapped","type":"trade_press","url":"https://www.bisnow.com/news/raleigh-durham/data-center/massive-raleigh-area-data-center-scrapped-133584"},{"accessed":"2026-10-09","id":"s2","published":"2026-03-05","publisher":"WRAL","title":"Residents near proposed Apex data center relieved project is scrapped, says more work needed","type":"news","url":"https://www.wral.com/news/local/natelli-withdraws-apex-data-center-project-shearon-harris-march-2026/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001014120/https://abc11.com/post/data-center-developer-pulls-back-apex-now/18685708/","id":"s3","published":"2026-03-07","publisher":"ABC11 (WTVD)","title":"Data center developer pulls back from Apex for now","type":"news","url":"https://abc11.com/post/data-center-developer-pulls-back-apex-now/18685708/"}],"status":"cancelled","status_as_of":"2026-03-10","status_source_ids":["s1","s2","s3"],"summary":"Maryland developer Natelli Investments proposed a 250 MW data center campus on about 189 acres of former farmland on Shearon Harris Road in the New Hill community of Wake County, North Carolina, next to Duke Energy's Shearon Harris nuclear plant. The project needed annexation into and rezoning by the Town of Apex and drew organized local opposition in 2025. In March 2026 Natelli withdrew its annexation and rezoning applications, saying it would consider next steps only if Apex amended its zoning rules to allow data centers, while town leaders weighed a one-year moratorium."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3b847726-3c79-5d0b-8e80-70c0498fd745","s2":"b65b4f7b-10e1-58b6-ae22-7f723d348388","s3":"b15455cd-25b4-5e61-b70c-33d0359a295f"},"source_file":"datacenters/projects/natelli-new-hill-digital-campus.json","source_record_id":"natelli-new-hill-digital-campus","source_record_sha256":"ce0a61a3c0650b4f20901871383b33a499a2f44ec25ff5f8d350a43483c5f70c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"334fcb46e99a2440902633f2788d2445a18859a2d38dd97a94c3b9b36d81d1ad"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ff3fe91dbbe9f9beaf9e/#project-03207f8c-1d9d-577f-9d8c-af881144fb86 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/03207f8c-1d9d-577f-9d8c-af881144fb86.json
03b5fd0f-9eaf-5f2b-bd8e-7c11fe6672a9 | imported:semiconductor-atlas:google-waltham-cross-uk | vcc-site-078fc4166e995b536458 | imported:semiconductor-atlas:google-waltham-cross-uk | Google Waltham Cross data centre | United Kingdom | GB | 51.6858 | -0.033 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid of Waltham Cross via Nominatim; Google's sources name the town but not the street address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 99547e51-4312-55b7-bca0-e1e247aee399 | operational | 2025-09-16 | 392 | imported_documented_status | 66c2d67a-88e5-59e1-beb4-fab7c41ca004 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"99547e51-4312-55b7-bca0-e1e247aee399","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-waltham-cross-uk"},{"evidence_id":"66c2d67a-88e5-59e1-beb4-fab7c41ca004","notes":null,"party":"Google","relationship_scope":"unknown","role":"operator","source_record_id":"google-waltham-cross-uk"},{"evidence_id":"cf31b0e6-7294-594b-a8ab-3088110ec041","notes":null,"party":"Google","relationship_scope":"unknown","role":"operator","source_record_id":"google-waltham-cross-uk"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Google |  |  |  | https://blog.google/around-the-globe/google-europe/united-kingdom/waltham-cross-data-centre/ | https://blog.google/around-the-globe/google-europe/united-kingdom/google-1-billion-investment-in-a-new-uk-data-centre/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Google Waltham Cross data centre as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"google-waltham-cross-uk"},"record":{"aliases":[],"id":"google-waltham-cross-uk","last_reviewed":"2026-10-09","location":{"admin1":"England","admin2":"Hertfordshire","country":"GB","lat":51.6858,"locality":"Waltham Cross","lon":-0.033,"note":"Town centroid of Waltham Cross via Nominatim; Google's sources name the town but not the street address.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2024-01-18","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2024-01-18","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":33}],"milestones":[{"date":"2024-01-18","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-09-16","event":"first_operational","kind":"actual","note":"Opening by the Chancellor reported in Google's post of this date.","source_ids":["s2","s3"]}],"name":"Google Waltham Cross data centre","notes":"The GBP 5 billion figure announced at the opening is a two-year UK-wide programme covering capital spending, R&D and engineering, including Google DeepMind research, so it is not recorded as a campus investment. Google's location page says the facility uses air cooling that limits water use to domestic needs.","parties":[{"name":"Google","role":"developer","source_ids":["s1"]},{"name":"Google","role":"operator","source_ids":["s2","s3"]}],"power_sources":[{"description":"Google's 2022 offshore wind PPA with ENGIE for the Moray West farm in Scotland, adding 100 MW to the grid, covers its UK operations rather than this site alone.","source_ids":["s1"],"type":"wind"},{"description":"Shell manages Google's UK carbon-free energy portfolio and is to deploy battery technology that stores surplus clean energy for the grid; the arrangement is UK-wide, not specific to this site.","source_ids":["s2"],"type":"battery_storage"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-01-18","publisher":"Google","title":"Our $1 billion investment in a new UK data centre","type":"company","url":"https://blog.google/around-the-globe/google-europe/united-kingdom/google-1-billion-investment-in-a-new-uk-data-centre/"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-16","publisher":"Google","title":"Our new Waltham Cross data center is part of our two-year, £5 billion investment to help power the UK's AI economy","type":"company","url":"https://blog.google/around-the-globe/google-europe/united-kingdom/waltham-cross-data-centre/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260920080314/https://datacenters.google/locations/waltham-cross/","id":"s3","published":null,"publisher":"Google","title":"Waltham Cross, United Kingdom - Google Data Center Location","type":"company","url":"https://datacenters.google/locations/waltham-cross/"}],"status":"operational","status_as_of":"2025-09-16","status_source_ids":["s2","s3"],"summary":"Google data centre on a 33-acre site in Waltham Cross, Hertfordshire, England. Google announced a $1 billion investment in the new facility in January 2024, describing air-based cooling with provision for off-site heat recovery to nearby homes and businesses. Chancellor Rachel Reeves opened the data centre in September 2025, when Google also announced a two-year GBP 5 billion UK investment covering capital spending, R&D and engineering. Google says the site supports AI services, Google Cloud, Search and Maps. Power capacity has not been disclosed.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"99547e51-4312-55b7-bca0-e1e247aee399","s2":"66c2d67a-88e5-59e1-beb4-fab7c41ca004","s3":"cf31b0e6-7294-594b-a8ab-3088110ec041"},"source_file":"datacenters/projects/google-waltham-cross-uk.json","source_record_id":"google-waltham-cross-uk","source_record_sha256":"47e318f4b8230e9ed27a809ada7e790775570bdec16dd09d07b91c2a09e52201","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5e6dc9f27aa333dc00c400fa71bf41ef507f208a3899f03cff1e944e4c43d1c8"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-078fc4166e995b536458/#project-03b5fd0f-9eaf-5f2b-bd8e-7c11fe6672a9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/03b5fd0f-9eaf-5f2b-bd8e-7c11fe6672a9.json
04b22725-af3a-5d12-b2b6-0caf17b0c39e | curated:keppel-genting-lane-data-centre-campus:keppel-dc-sgp-9-current-build | vcc-site-bb743c7caad1e739c23e | curated:keppel-genting-lane-data-centre-campus | Keppel DC SGP 9 Current Build | Singapore | SG | 1.3254 | 103.8766 | Polygon | campus | Exact OSM way 1560974456 ordered node ring; display anchor is the planar shoelace centroid of that ring. | copy_named_community_campus_source_nodes_in_way_order_without_digitizing_or_geocoding | community_mapped_named_campus_outline | community_source | campus_locator | Source node coordinates are retained as serialized. The named fenced campus locates the Genting Lane campus containing operating SGP 7 and SGP 8 and the SGP 9 build; it is not an official boundary, surveyed footprint or current work extent. |  | OSM supplies no survey method or positional accuracy for this feature. | 55851feb-fc9d-51f3-ab77-030da1cbf8a2 | under_construction | 2026-07-30 | 75 | authoritative_physical_status_update | f5b6d780-e4e6-5028-bb4b-719b8953891d | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.keppel.com/file/media/media-releases-sgx/2026/07-july/30-july-kcl/2-keppel-ltd-1h2026-presentation-slides.pdf | https://www.openstreetmap.org/api/0.6/way/1560974456/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bb743c7caad1e739c23e/#project-04b22725-af3a-5d12-b2b6-0caf17b0c39e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/04b22725-af3a-5d12-b2b6-0caf17b0c39e.json
05033935-bf13-5754-a9af-25c96ea1b473 | curated:noris-network-fra1-schwalbach-campus:current-build | vcc-site-1f0a3581ea8ef66ce00b | curated:noris-network-fra1-schwalbach-campus | noris network FRA1 Schwalbach Current Build | Germany | DE | 50.1629 | 8.5326 | Point | campus | copy_Overpass_center_for_named_OSM_way_313208490 | copy_Overpass_center_for_named_OSM_way_313208490 | community_mapped_campus_reference_point | community_source | campus_locator | Representative center of an explicitly named and operated community-mapped campus enclosure; not a surveyed parcel or building centroid. OSM object identity matches the company release; the street spelling discrepancy is disclosed. |  | The source provides no survey accuracy or quantitative positional uncertainty; coordinate digits do not establish accuracy. | 3b796d81-9046-5662-b53e-4a7363bb50f3 | under_construction | 2026-06-10 | 125 | authoritative_physical_status_update | 7af69c5c-2f00-5ead-ab9e-66b67a60b797 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://datacenter-group.com/de/news-stories/artikel/grundstein-fuer-neues-rechenzentrum-gelegt/ | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bway%28313208490%29%3Bout%20meta%20center%3B | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1f0a3581ea8ef66ce00b/#project-05033935-bf13-5754-a9af-25c96ea1b473 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/05033935-bf13-5754-a9af-25c96ea1b473.json
057826b7-3798-5e94-9628-e76e45647c61 | curated:daou-jukjeon-cdc-campus:current-build | vcc-site-e6b61ca210eeece21cf5 | curated:daou-jukjeon-cdc-campus | Daou Jukjeon CDC Current Build | Korea, Republic of | KR | 37.3321 | 127.1324 | Point | campus | source_attribute_decimal_coordinates_to_point_without_centroiding | first_party_named_maps_javascript_marker | official_operator_published_campus_reference_point | official_source | campus_locator | Exact operator-authored six-decimal marker input for the named Jukjeon CDC campus. Decimal precision is not surveyed accuracy; not a boundary, new-building footprint or trade-work location. |  | Operator provides no positional-accuracy statement. | 73eb3f1c-f1ed-548b-8697-2721d5e570d0 | under_construction | 2026-08-14 | 60 | authoritative_physical_status_update | e07d06a3-b838-5a16-8b64-06a457c77a5a | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.daou.co.kr/images/sub/ir/data_down/Daoutech_quarter_half_2026.pdf | https://www.daouidc.com/infra/cdc.do | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e6b61ca210eeece21cf5/#project-057826b7-3798-5e94-9628-e76e45647c61 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/057826b7-3798-5e94-9628-e76e45647c61.json
077a5970-0684-5ef0-8320-65efbf78c960 | imported:semiconductor-atlas:aws-vicksburg-warren-county-mississippi | vcc-site-ab1cba1760d42b280cd1 | imported:semiconductor-atlas:aws-vicksburg-warren-county-mississippi | AWS Vicksburg data center campus | United States | US | 32.3525 | -90.8775 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | No site, parcel or road has been published; coordinates are the Vicksburg city point from its Wikipedia article (Nominatim was unavailable). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6323bbc2-696d-588a-97e0-2b98b39e0897 | announced | 2026-04-09 | 187 | imported_documented_status | 6323bbc2-696d-588a-97e0-2b98b39e0897 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6323bbc2-696d-588a-97e0-2b98b39e0897","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-vicksburg-warren-county-mississippi"},{"evidence_id":"c99117ac-74eb-5f84-b895-202ac7ae59fa","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-vicksburg-warren-county-mississippi"},{"evidence_id":"6323bbc2-696d-588a-97e0-2b98b39e0897","notes":null,"party":"Entergy Mississippi","relationship_scope":"unknown","role":"utility","source_record_id":"aws-vicksburg-warren-county-mississippi"},{"evidence_id":"a87ef6ff-6a94-5cf9-849a-2bad55454961","notes":null,"party":"Entergy Mississippi","relationship_scope":"unknown","role":"utility","source_record_id":"aws-vicksburg-warren-county-mississippi"},{"evidence_id":"6323bbc2-696d-588a-97e0-2b98b39e0897","notes":"The county is contributing to the project; state incentives passed for the Madison County campuses also apply.","party":"Warren County","relationship_scope":"unknown","role":"government","source_record_id":"aws-vicksburg-warren-county-mississippi"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://governorreeves.ms.gov/governor-tate-reeves-announces-amazon-plans-to-invest-3-billion-in-vicksburg/ | https://governorreeves.ms.gov/governor-tate-reeves-announces-amazon-plans-to-invest-3-billion-in-vicksburg/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AWS Vicksburg data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"aws-vicksburg-warren-county-mississippi"},"record":{"aliases":["AWS Warren County data center campus"],"id":"aws-vicksburg-warren-county-mississippi","last_reviewed":"2026-10-09","location":{"admin1":"Mississippi","admin2":"Warren County","country":"US","lat":32.3525,"locality":"Vicksburg","lon":-90.8775,"note":"No site, parcel or road has been published; coordinates are the Vicksburg city point from its Wikipedia article (Nominatim was unavailable).","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-20","basis":"announced","metric":"investment","qualifier":"at_least","source_ids":["s1","s4"],"unit":"USD","value":3000000000},{"applies_to":"campus","as_of":"2025-11-20","basis":"planned","metric":"jobs_permanent","note":"Officials also project more than 300 additional positions in the wider county.","qualifier":"at_least","source_ids":["s1","s2","s3"],"unit":"count","value":200}],"milestones":[{"date":"2025-11-20","event":"announced","kind":"actual","source_ids":["s1","s3"]},{"date":"2026","event":"construction_started","kind":"planned","note":"Target year given at announcement; no source opened confirms that work has begun.","source_ids":["s1","s2"]}],"name":"AWS Vicksburg data center campus","notes":"The Vicksburg mayor described a five-to-seven-year build-out at the November 2025 announcement (Mississippi Public Broadcasting). The governor's release gives $3 billion while Amazon says at least $3 billion.","parties":[{"name":"Amazon Web Services","role":"developer","source_ids":["s1","s4"]},{"name":"Entergy Mississippi","role":"utility","source_ids":["s1","s2"]},{"name":"Warren County","note":"The county is contributing to the project; state incentives passed for the Madison County campuses also apply.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Entergy Mississippi committed to the campus's long-term power needs and is building a roughly $1.2 billion gas-fired station at the retired Baxter Wilson plant site to serve this and other industrial load.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260909125457/https://governorreeves.ms.gov/governor-tate-reeves-announces-amazon-plans-to-invest-3-billion-in-vicksburg/","id":"s1","published":"2025-11-20","publisher":"Office of Governor Tate Reeves","title":"Governor Tate Reeves announces Amazon plans to invest $3 billion in Vicksburg","type":"government","url":"https://governorreeves.ms.gov/governor-tate-reeves-announces-amazon-plans-to-invest-3-billion-in-vicksburg/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260831160715/https://www.mpbonline.org/blogs/news/amazon-web-services-to-build-3-billion-data-center-in-warren-county-expanding-tech-footprint-in-mi/","id":"s2","published":"2025-11-21","publisher":"Mississippi Public Broadcasting","title":"Amazon to build $3 billion data center in Warren County, expanding tech footprint in Mississippi","type":"news","url":"https://www.mpbonline.org/blogs/news/amazon-web-services-to-build-3-billion-data-center-in-warren-county-expanding-tech-footprint-in-mi/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260928223038/https://www.mississippifreepress.org/amazon-to-build-3b-ai-data-center-in-vicksburg-as-gov-reeves-proclaims-arrival-of-the-digital-delta/","id":"s3","published":"2025-11-20","publisher":"Mississippi Free Press","title":"Amazon to Build $3B AI Data Center in Vicksburg, as Gov. Reeves Proclaims Arrival of the 'Digital Delta'","type":"news","url":"https://www.mississippifreepress.org/amazon-to-build-3b-ai-data-center-in-vicksburg-as-gov-reeves-proclaims-arrival-of-the-digital-delta/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Amazon","title":"Amazon plans to invest at least $3 billion in Warren County, Mississippi, for next-generation data center campus","type":"company","url":"https://www.aboutamazon.com/md/news/company-news/amazon-3-billion-mississippi-data-center-investment"},{"accessed":"2026-10-09","id":"s5","published":"2026-04-09","publisher":"Office of Governor Tate Reeves","title":"Amazon continues Mississippi expansion, announcing plans to invest a total of $25 billion across the Magnolia State","type":"government","url":"https://governorreeves.ms.gov/amazon-continues-mississippi-expansion-announcing-plans-to-invest-a-total-of-25-billion-across-the-magnolia-state/"}],"status":"announced","status_as_of":"2026-04-09","status_source_ids":["s1","s5"],"summary":"Amazon announced in November 2025 that it would spend at least $3 billion on a new data center campus in Vicksburg, Warren County, with at least 200 full-time jobs. Officials said construction would start in 2026 and the local mayor expected a five-to-seven-year build-out. Amazon said the campus will support AI and cloud computing. Entergy Mississippi agreed to meet its long-term power needs and is building a gas plant at the former Baxter Wilson site to serve the campus and other industrial projects. The April 2026 statewide update still listed it as planned.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6323bbc2-696d-588a-97e0-2b98b39e0897","s2":"a87ef6ff-6a94-5cf9-849a-2bad55454961","s3":"1bf3f4be-636b-5f44-88bd-072d6d3a526f","s4":"c99117ac-74eb-5f84-b895-202ac7ae59fa","s5":"bbc73677-89d2-5fad-b604-8f53763caf9e"},"source_file":"datacenters/projects/aws-vicksburg-warren-county-mississippi.json","source_record_id":"aws-vicksburg-warren-county-mississippi","source_record_sha256":"e1ddd3d99fd07c52d39a039e17ead8347cc72830b536cfe7e1b763cbc216a041","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"6949c11c8bd0d18cf3e974952a3984290ab3afa7d024b48705c446ff2c41ee1e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ab1cba1760d42b280cd1/#project-077a5970-0684-5ef0-8320-65efbf78c960 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/077a5970-0684-5ef0-8320-65efbf78c960.json
08d881e7-8a1c-50da-81a5-d2ef49f22a7a | curated:colt-villebon-sur-yvette-campus:paris2-current-facility-build | vcc-site-ca2269119237054941e1 | curated:colt-villebon-sur-yvette-campus | Colt Paris 2 Current Facility Build | France | FR | 48.691 | 2.22 | Polygon | project | direct_geometry | official_prefecture_and_municipal_project_to_dgfip_cadastral_parcel_polygon | official_cadastral_project_site_parcel_boundary | official_source | official_boundary | Official cadastral project-site parcel polygon used as the PAR2 project boundary. Its representative point is a deterministic planar centroid of the published WGS84 ring and lies inside the polygon; it is not an official cadastral point or survey-accuracy claim. |  | The cadastral feature is authoritative parcel geometry but publishes no survey-grade or numeric horizontal-accuracy field for this feature. | 2157a790-74df-5026-b2b6-58b1bb82519d | under_construction | 2026-07-19 | 86 | authoritative_physical_status_update | 0bb1b8a1-24a2-5e40-818e-29621e6017d1 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-19","base":39.6,"confidence":0.99,"evidence_id":"90f6acac-7fe4-57e4-b8cd-f9b6acdf6c66","high":39.6,"low":39.6,"method":"reported","metric":"critical_it_mw","notes":"Planned critical-IT capacity for Paris 2 when fully developed, using the official report's exact 39.6 MW figure rather than the location page's rounded 40 MW. This is not current load, 120 MW three-facility contracted power, gross facility power, grid draw, generation, measured energy consumption, or proof of completion or operation.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.coltdatacentres.net/en-GB/our-locations/data-centre-locations-europe/paris-2 | https://cadastre.data.gouv.fr/data/etalab-cadastre/latest/geojson/communes/91/91661/cadastre-91661-parcelles.json.gz | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ca2269119237054941e1/#project-08d881e7-8a1c-50da-81a5-d2ef49f22a7a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/08d881e7-8a1c-50da-81a5-d2ef49f22a7a.json
09904943-69d4-51d7-aef7-4ff880e47332 | imported:semiconductor-atlas:google-west-memphis-arkansas | vcc-site-1c393b2e71d64f0ffd69 | imported:semiconductor-atlas:google-west-memphis-arkansas | Google West Memphis data center campus | United States | US | 35.1163 | -90.2115 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | OpenStreetMap geometry of the southern end of Bollinger Road in West Memphis; sources place the campus at the south end of Bollinger Road. One source also gives 1500 South Loop Drive, which could not be resolved to a point. The campus parcel itself is not mapped here. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2a51650c-1b90-5cd4-9448-8601d200965e | under_construction | 2026-02-26 | 229 | imported_documented_status | 877db821-3ff2-5bd8-bf86-006e488fe927 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"b4f0d50f-dfc9-5004-940d-d54886b6b774","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"a46c8e42-bb2b-580d-b430-45b8dfcced04","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"2a51650c-1b90-5cd4-9448-8601d200965e","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"2a51650c-1b90-5cd4-9448-8601d200965e","notes":"Named as the developer of record in local filings. Before Google confirmed the project in September 2025, reports described Groot as widely believed to be backed by Google.","party":"Groot LLC","relationship_scope":"unknown","role":"developer","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"235d8722-38d3-5f6d-849c-675e6c0dea42","notes":"Named as the developer of record in local filings. Before Google confirmed the project in September 2025, reports described Groot as widely believed to be backed by Google.","party":"Groot LLC","relationship_scope":"unknown","role":"developer","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"a46c8e42-bb2b-580d-b430-45b8dfcced04","notes":"Holds the power contract with Google for the project and partnered with Google on the announcement. Trade press notes that West Memphis Utilities, not Entergy Arkansas, is the local utility serving the city.","party":"Entergy Arkansas","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"a677e0f7-2a3e-5eeb-a004-6a7e355f22b7","notes":"Holds the power contract with Google for the project and partnered with Google on the announcement. Trade press notes that West Memphis Utilities, not Entergy Arkansas, is the local utility serving the city.","party":"Entergy Arkansas","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"2a51650c-1b90-5cd4-9448-8601d200965e","notes":"Holds the power contract with Google for the project and partnered with Google on the announcement. Trade press notes that West Memphis Utilities, not Entergy Arkansas, is the local utility serving the city.","party":"Entergy Arkansas","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"235d8722-38d3-5f6d-849c-675e6c0dea42","notes":"Reported in May 2025 as a lead contractor based on site signage.","party":"Turner Construction","relationship_scope":"unknown","role":"builder","source_record_id":"google-west-memphis-arkansas"},{"evidence_id":"235d8722-38d3-5f6d-849c-675e6c0dea42","notes":"Reported in May 2025 as a lead contractor based on site signage.","party":"Yates Construction","relationship_scope":"unknown","role":"builder","source_record_id":"google-west-memphis-arkansas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.actionnews5.com/2026/02/26/google-hiring-new-west-memphis-data-center/ | https://dailymemphian.com/section/businessreal-estate/article/54862/google-west-memphis-data-center-entergy-arkansas-groot | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Google West Memphis data center campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"google-west-memphis-arkansas"},"record":{"aliases":["Groot LLC West Memphis data center"],"id":"google-west-memphis-arkansas","last_reviewed":"2026-10-09","location":{"admin1":"Arkansas","admin2":"Crittenden County","country":"US","lat":35.1163,"locality":"West Memphis","lon":-90.2115,"note":"OpenStreetMap geometry of the southern end of Bollinger Road in West Memphis; sources place the campus at the south end of Bollinger Road. One source also gives 1500 South Loop Drive, which could not be resolved to a point. The campus parcel itself is not mapped here.","precision":"approximate_site","source_ids":["s4","s6","s7"]},"metrics":[{"applies_to":"campus","as_of":"2025-05-30","basis":"reported","metric":"investment","note":"Proposed campus cost reported before Google confirmed its involvement; it differs from the other reported figures.","qualifier":"exact","source_ids":["s5"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2025-09-05","basis":"reported","metric":"investment","note":"Local reporting described the data center as a $1 billion project at the time Google confirmed it; no phase breakdown or source for the figure was given, and it differs from the $10 billion reported earlier.","qualifier":"exact","source_ids":["s4"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2025-09-05","basis":"planned","metric":"floor_area","note":"Size given for the data center in local reporting at the time Google confirmed it; no phase breakdown was given.","qualifier":"exact","source_ids":["s4"],"unit":"sq_ft","value":900000},{"applies_to":"campus","as_of":"2026-02-26","basis":"reported","metric":"land_area","note":"Sources differ on the property size: about 1,000, 1,100, 1,178 and almost 1,200 acres have all been reported.","qualifier":"approximately","source_ids":["s3","s6"],"unit":"acres","value":1100},{"applies_to":"campus","as_of":"2025-05-30","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s5"],"unit":"acres","value":1178},{"applies_to":"campus","as_of":"2025-10-02","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s2"],"unit":"acres","value":1000},{"applies_to":"campus","as_of":"2026-09-02","basis":"reported","metric":"land_area","note":"Described as almost 1,200 acres.","qualifier":"approximately","source_ids":["s7"],"unit":"acres","value":1200},{"applies_to":"campus","as_of":"2026-09-02","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s5","s7"],"unit":"count","value":5},{"applies_to":"campus","as_of":"2026-02-26","basis":"planned","metric":"jobs_permanent","note":"Reported as about 300 positions expected, with Google hiring electrical engineers and facilities technicians.","qualifier":"approximately","source_ids":["s6"],"unit":"count","value":300}],"milestones":[{"date":"2024-12","event":"other","kind":"actual","note":"Groot LLC submitted site plans to the US Army Corps of Engineers Memphis office for water-mitigation review.","source_ids":["s4"]},{"date":"2025-09-05","event":"other","kind":"actual","note":"Google and Entergy Arkansas confirmed the project in a joint statement.","source_ids":["s4"]},{"date":"2025-10-02","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2025-10","event":"construction_started","kind":"actual","note":"Reported schedule of 18 to 24 months to complete.","source_ids":["s6"]},{"date":"2026-09-02","event":"other","kind":"actual","note":"Released records showed Google paying Entergy $526 million upfront toward a $1.6 billion solar project tied to the data center, with the remainder recovered from ratepayers; a federal judge declined Entergy's request to force newspapers to remove stories on the deal.","source_ids":["s7"]}],"name":"Google West Memphis data center campus","notes":"Google's $4 billion figure is an Arkansas-wide commitment through 2027 that includes the West Memphis data center along with other cloud and AI infrastructure and local programs, so it is not recorded as a campus investment, although some news reports describe it as the cost of the West Memphis project. Reported campus cost and size figures conflict and are kept as separate statements.","parties":[{"name":"Google","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Groot LLC","note":"Named as the developer of record in local filings. Before Google confirmed the project in September 2025, reports described Groot as widely believed to be backed by Google.","role":"developer","source_ids":["s4","s5"]},{"name":"Entergy Arkansas","note":"Holds the power contract with Google for the project and partnered with Google on the announcement. Trade press notes that West Memphis Utilities, not Entergy Arkansas, is the local utility serving the city.","role":"power_supplier","source_ids":["s2","s3","s4"]},{"name":"Turner Construction","note":"Reported in May 2025 as a lead contractor based on site signage.","role":"builder","source_ids":["s5"]},{"name":"Yates Construction","note":"Reported in May 2025 as a lead contractor based on site signage.","role":"builder","source_ids":["s5"]}],"power_sources":[{"description":"Entergy Arkansas is to supply power under its contract with Google, using solar and existing generation; earlier reports said Entergy was considering a 500/230 kV substation. Google says it will cover the facility's energy costs and reduce its workload during peak demand.","source_ids":["s2","s3"],"type":"grid"},{"description":"The Google-Entergy contract includes investment in Cypress Solar, a 600 MW solar facility near Pine Bluff in Jefferson County; unlike Google's earlier solar PPAs, the money supports construction directly.","source_ids":["s1","s3"],"type":"solar"},{"description":"The Cypress Solar project includes a 350 MW battery energy storage facility to be built by Entergy Arkansas.","source_ids":["s3"],"type":"battery_storage"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-10-02","publisher":"Google","title":"Google announces new $4 billion investment in Arkansas","type":"company","url":"https://blog.google/inside-google/company-announcements/google-american-innovation-arkansas/"},{"accessed":"2026-10-09","id":"s2","published":"2025-10-02","publisher":"Talk Business & Politics","title":"Google announces plan to build $4 billion data center in West Memphis","type":"news","url":"https://talkbusiness.net/2025/10/google-announces-plan-to-build-4-billion-data-center-in-west-memphis/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260412122631/https://www.powermag.com/entergy-will-power-4-billion-google-data-center-in-arkansas/","id":"s3","published":"2025-10-03","publisher":"POWER Magazine","title":"Entergy Will Power $4-Billion Google Data Center in Arkansas","type":"trade_press","url":"https://www.powermag.com/entergy-will-power-4-billion-google-data-center-in-arkansas/"},{"accessed":"2026-10-09","id":"s4","published":"2025-09-05","publisher":"The Daily Memphian","title":"Google confirms West Memphis data center","type":"news","url":"https://dailymemphian.com/section/businessreal-estate/article/54862/google-west-memphis-data-center-entergy-arkansas-groot"},{"accessed":"2026-10-09","id":"s5","published":"2025-05-30","publisher":"Construction Briefing","title":"Google linked to US$10bn data centre campus in US","type":"trade_press","url":"https://www.constructionbriefing.com/news/google-linked-to-us10bn-data-centre-campus-in-us/8062290.article"},{"accessed":"2026-10-09","id":"s6","published":"2026-02-26","publisher":"Action News 5 (WMC)","title":"Google hiring for new West Memphis data center","type":"news","url":"https://www.actionnews5.com/2026/02/26/google-hiring-new-west-memphis-data-center/"},{"accessed":"2026-10-09","id":"s7","published":"2026-09-02","publisher":"Action News 5 (WMC)","title":"Docs reveal plans for $6 utility rate hike to help fund Google's data center project in West Memphis","type":"news","url":"https://www.actionnews5.com/2026/09/02/docs-reveal-plans-6-utility-rate-hike-help-fund-googles-data-center-project-west-memphis/"}],"status":"under_construction","status_as_of":"2026-02-26","status_source_ids":["s6"],"summary":"Google's first Arkansas data center campus, under construction at the south end of Bollinger Road in West Memphis, Crittenden County, on a property reported at 1,000 to 1,200 acres. Google announced it in October 2025 as part of a $4 billion Arkansas commitment running through 2027. The developer of record, Groot LLC, filed plans with the US Army Corps of Engineers in late 2024; earlier reporting described a proposed $10 billion campus with five data center buildings and a substation. Construction began in October 2025 on an 18-24 month schedule. Entergy Arkansas is supplying power under a contract with Google, which is paying part of the cost of a new Entergy solar and storage project.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"b4f0d50f-dfc9-5004-940d-d54886b6b774","s2":"a46c8e42-bb2b-580d-b430-45b8dfcced04","s3":"a677e0f7-2a3e-5eeb-a004-6a7e355f22b7","s4":"2a51650c-1b90-5cd4-9448-8601d200965e","s5":"235d8722-38d3-5f6d-849c-675e6c0dea42","s6":"877db821-3ff2-5bd8-bf86-006e488fe927","s7":"d6ae77f3-2838-50ee-a056-a35bbe4db7a7"},"source_file":"datacenters/projects/google-west-memphis-arkansas.json","source_record_id":"google-west-memphis-arkansas","source_record_sha256":"affe666039075290c2511ab766a40b580f546f594dfcdc4b58bfb59341573b09","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1218050e330271598a27a21bc7c628a27a7dcccaa69ae6d90d6e4d09b2adbf90"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1c393b2e71d64f0ffd69/#project-09904943-69d4-51d7-aef7-4ff880e47332 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/09904943-69d4-51d7-aef7-4ff880e47332.json
0a075c8d-2733-5aba-b19a-4b53e51fd8f8 | curated:green-mountain-undheim-campus:current-two-building-development | vcc-site-5973ad6c7ce7afc4f6b6 | curated:green-mountain-undheim-campus | Green Mountain Undheim Current Two-Building Development | Norway | NO | 58.6593 | 5.7941 | Polygon | campus | official_parcel_union | authoritative_kartverket_cadastral_parcel_union | official_cadastral_project_site_parcel_union_boundary | official_source | official_boundary | Exact deterministic union of three Kartverket official cadastral parcel polygons explicitly listed as the Green Mountain project address in the approved municipal situation plan and area schedule. It is not a survey-accuracy claim, security fence, building outline, current construction extent, or assertion that every square metre is developed. |  | Kartverket supplies only a coarse green accuracy class and explicitly does not expose boundary-line type or detailed boundary quality. | 12f5d89c-ebd5-501c-8f98-62e845710d8c | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | 78af4a56-8fe9-5552-b965-4704ae219a8c | recent_authoritative_physical_observation_plus_official_boundary | FALSE | first_party_contractor_drone_imagery_present_not_independently_verified | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-20","base":80.0,"confidence":0.99,"evidence_id":"78af4a56-8fe9-5552-b965-4704ae219a8c","high":80.0,"low":80.0,"method":"reported","metric":"critical_it_mw","notes":"Planned IT capacity for the complete current two-building development. It is not current load, grid capacity, generation, measured energy, or additive to the 100 MW gross-facility observation.","stage":"planned","target_date":null,"unit":"MW"},{"as_of_date":"2026-07-20","base":100.0,"confidence":0.99,"evidence_id":"78af4a56-8fe9-5552-b965-4704ae219a8c","high":100.0,"low":100.0,"method":"reported","metric":"gross_facility_mw","notes":"Planned total effect capacity for the complete current two-building development, treated as gross facility demand. It is not IT load, grid capacity, generation, measured energy, or additive to the 80 MW critical-IT observation.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://info.greenmountain.no/datasenter-pa-undheim/ | https://api.kartverket.no/eiendom/v1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5973ad6c7ce7afc4f6b6/#project-0a075c8d-2733-5aba-b19a-4b53e51fd8f8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0a075c8d-2733-5aba-b19a-4b53e51fd8f8.json
0a4a2c40-bdf2-5f56-aa09-ecfa54431d3c | curated:beale-tulsa-county-project-clydesdale-campus:current-campus-build | vcc-site-137a78b7abc74703d577 | curated:beale-tulsa-county-project-clydesdale-campus | Google / Beale Tulsa County Project Clydesdale Campus Construction | United States | US | 36.2698 | -95.9109 | Point | campus | representative_point_inside_reconstructed_public_draft_survey_tract | 18_visual_metes_and_bounds_courses_anchored_by_section_corners_EPSG6553_to4326_then_Shapely_representative_point | public_draft_survey_tract_interior_campus_locator | official_source | campus_locator | One derived point inside the named Project Clydesdale draft survey tract. Official-source classification refers to public planning custody, not survey approval. No registered boundary, individual hall, construction footprint, road junction, offsite benchmark or mailing address is selected. |  | The draft supplies no site-specific horizontal accuracy. Printed decimals, traverse closure, agreement between anchors and two-metre datum-operation accuracy do not establish locator accuracy. | 9abda1b5-9d23-59c2-81b7-a930d3ec670f | under_construction | 2026-08-19 | 55 | authoritative_physical_status_update | fc217a36-275a-5ef8-b4fe-3d0b2898abfb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"bdf01d48-8749-52a5-b32c-d10ab31c4ba0","notes":"Also funds the new on-site electrical substation.","party":"Beale Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"fa504205-50fd-5637-88a5-bb3ab52520f5","notes":"Also funds the new on-site electrical substation.","party":"Beale Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"15e1fc03-9d97-5c6a-8ea4-ac692cba90af","notes":"Also funds the new on-site electrical substation.","party":"Beale Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"6ecf1809-362a-559a-abff-792fe3a2050d","notes":"Also funds the new on-site electrical substation.","party":"Beale Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"15e1fc03-9d97-5c6a-8ea4-ac692cba90af","notes":"ConstructConnect reported that Google will operate the campus, following the 19 August 2026 announcement; other coverage presents the campus as joining Google's data center network without naming an operator.","party":"Google","relationship_scope":"unknown","role":"operator","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"b639af84-80b6-5a63-9a59-d1171f547450","notes":null,"party":"Public Service Company of Oklahoma","relationship_scope":"unknown","role":"utility","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"15e1fc03-9d97-5c6a-8ea4-ac692cba90af","notes":null,"party":"Public Service Company of Oklahoma","relationship_scope":"unknown","role":"utility","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"6ecf1809-362a-559a-abff-792fe3a2050d","notes":null,"party":"Public Service Company of Oklahoma","relationship_scope":"unknown","role":"utility","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"bdf01d48-8749-52a5-b32c-d10ab31c4ba0","notes":"Approved the project's economic development plan and tax incentives in September 2025; the Tulsa Flyer reports the vote was unanimous.","party":"Tulsa County Board of Commissioners","relationship_scope":"unknown","role":"government","source_record_id":"google-owasso-project-clydesdale"},{"evidence_id":"fa504205-50fd-5637-88a5-bb3ab52520f5","notes":"Approved the project's economic development plan and tax incentives in September 2025; the Tulsa Flyer reports the vote was unanimous.","party":"Tulsa County Board of Commissioners","relationship_scope":"unknown","role":"government","source_record_id":"google-owasso-project-clydesdale"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected |  | Google |  |  |  | https://bealeinfra.com/google-and-beale-infrastructure-building-new-data-center-campus-in-tulsa-county/ | https://tulsaplanning.org/tmapc/agendas/exhibits/Accelerated%20Release%20of%20Permits%20-%20Staff%20Report%20v03.pdf | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Project Clydesdale alias, Beale developer, Google operator and Tulsa County west-of-Owasso location identify the same campus development. Source town centroid is not the campus.","source_record_id":"google-owasso-project-clydesdale","target_project_stable_key":"curated:beale-tulsa-county-project-clydesdale-campus:current-campus-build"},"record":{"aliases":["Project Clydesdale"],"id":"google-owasso-project-clydesdale","last_reviewed":"2026-10-09","location":{"admin1":"Oklahoma","admin2":"Tulsa County","country":"US","lat":36.2878,"locality":"Owasso","lon":-95.8311,"note":"Sources place the campus in unincorporated Tulsa County just west of Owasso, on land bounded by East 76th Street North, East 86th Street North, North Yale Avenue and North Sheridan Road. No coordinates are published, so the point is the Owasso town coordinate from its Wikipedia article and marks the neighbouring town, not the parcel.","precision":"locality","source_ids":["s1","s2","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2025-10-30","basis":"announced","metric":"investment","note":"Beale's planned investment as announced at groundbreaking. ConstructConnect (August 2026) describes the USD 1 billion as backing the initial phase rather than the full build-out; no total for all phases was found.","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2026-08-21","basis":"reported","metric":"land_area","note":"Groundbreaking coverage by the Tulsa Flyer rounded this to about 500 acres.","qualifier":"exact","source_ids":["s2","s3","s4","s5"],"unit":"acres","value":506},{"applies_to":"phase","as_of":"2025-11-12","basis":"planned","metric":"floor_area","phase_label":"Each phase (at least one, with up to three more possible)","qualifier":"approximately","source_ids":["s2"],"unit":"sq_ft","value":200000},{"applies_to":"phase","as_of":"2026-08-21","basis":"planned","metric":"jobs_permanent","note":"Technical jobs that ConstructConnect ties to the five-year build-out of the initial phase.","phase_label":"Initial phase","qualifier":"up_to","source_ids":["s2","s4"],"unit":"count","value":100}],"milestones":[{"date":"2025-09","event":"other","kind":"actual","note":"Tulsa County commissioners approved the economic development plan and tax incentives.","source_ids":["s1","s2"]},{"date":"2025-10-30","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony attended by state and local officials.","source_ids":["s1","s4"]},{"date":"2026-08-19","event":"other","kind":"actual","note":"Google and Beale announced the campus as part of Google's data center network; ConstructConnect identified Google as the operator.","source_ids":["s4","s5"]}],"name":"Project Clydesdale data center campus (Google, Tulsa County)","notes":"No megawatt figure for this campus was found. Google's statewide figures (a USD 9 billion Oklahoma commitment announced in 2025, more than USD 15 billion invested in Oklahoma since 2011, and power agreements supporting more than 2.5 GW) are not campus figures. A Tulsa County commissioner said the campus would yield about USD 2 million a year in local tax revenue once running. The project also funds about 1.5 miles of new water lines for Washington County Rural Water District No. 3. The Tulsa Flyer describes the intended use as cloud storage.","parties":[{"name":"Beale Infrastructure","note":"Also funds the new on-site electrical substation.","role":"developer","source_ids":["s1","s2","s4","s5"]},{"name":"Google","note":"ConstructConnect reported that Google will operate the campus, following the 19 August 2026 announcement; other coverage presents the campus as joining Google's data center network without naming an operator.","role":"operator","source_ids":["s4"]},{"name":"Public Service Company of Oklahoma","role":"utility","source_ids":["s3","s4","s5"]},{"name":"Tulsa County Board of Commissioners","note":"Approved the project's economic development plan and tax incentives in September 2025; the Tulsa Flyer reports the vote was unanimous.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"Supplied by Public Service Company of Oklahoma through a new on-site substation paid for by Beale; the project is also described as improving the utility's regional transmission and distribution reliability.","source_ids":["s3","s4","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-10-30","publisher":"Tulsa Flyer","title":"Developers break ground on $1B data center near Tulsa","type":"news","url":"https://tulsaflyer.org/2025/10/30/government/post/developers-break-ground-on-1b-data-center-near-tulsa/"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-12","publisher":"Construction Equipment Guide","title":"Beale Breaks Ground On Project Clydesdale Data Campus","type":"trade_press","url":"https://www.constructionequipmentguide.com/beale-breaks-ground-on-project-clydesdale-data-campus/69597"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-20","publisher":"News 9","title":"Google begins construction on 506-acre data center campus in Tulsa County","type":"news","url":"https://www.news9.com/data-centers-in-oklahoma/google-data-center-campus-tulsa-county-oklahoma"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-21","publisher":"ConstructConnect","title":"Google ID'd as Operator of Tulsa Area Data Center","type":"trade_press","url":"https://news.constructconnect.com/google-idd-as-operator-of-tulsa-area-data-center"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-01","publisher":"Construction Equipment Guide","title":"Google, Beale Infrastructure Announce Okla. Data Center","type":"trade_press","url":"https://www.constructionequipmentguide.com/google-beale-infrastructure-announce-okla-data-center/72160"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Owasso, Oklahoma","type":"other","url":"https://en.wikipedia.org/wiki/Owasso,_Oklahoma"}],"status":"under_construction","status_as_of":"2026-09-01","status_source_ids":["s3","s4","s5"],"summary":"Beale Infrastructure is building a 506-acre data center campus in unincorporated Tulsa County, Oklahoma, just west of Owasso near Cherokee Industrial Park. Tulsa County commissioners approved the economic development plan and tax incentives in September 2025, and ground was broken on 30 October 2025 for what was billed as a USD 1 billion project. Plans call for at least one phase of about 200,000 sq ft, with up to three more possible, and construction expected to take at least five years. In August 2026 Google was identified as the operator of the campus, which Public Service Company of Oklahoma will power through a new Beale-funded on-site substation.","workloads":["cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"bdf01d48-8749-52a5-b32c-d10ab31c4ba0","s2":"fa504205-50fd-5637-88a5-bb3ab52520f5","s3":"b639af84-80b6-5a63-9a59-d1171f547450","s4":"15e1fc03-9d97-5c6a-8ea4-ac692cba90af","s5":"6ecf1809-362a-559a-abff-792fe3a2050d","s6":"2777bf28-902c-5287-9929-cee958f099b3"},"source_file":"datacenters/projects/google-owasso-project-clydesdale.json","source_record_id":"google-owasso-project-clydesdale","source_record_sha256":"a97c56693be5922a0e0efe7d6461c0d87a07a5d861231215bf2d8e48f2ff4ef6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"e154f3ad7667aea5efc74f50a11b3f6d107811a595c49c3f51636b211857d773"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-137a78b7abc74703d577/#project-0a4a2c40-bdf2-5f56-aa09-ecfa54431d3c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0a4a2c40-bdf2-5f56-aa09-ecfa54431d3c.json
0b37ac4d-93f2-559b-a6ec-f5a12938681a | imported:semiconductor-atlas:bell-ai-fabric-sherwood-saskatchewan | vcc-site-0834945607ed54e349ce | imported:semiconductor-atlas:bell-ai-fabric-sherwood-saskatchewan | Bell AI Fabric Sherwood campus (Regina area) | Canada | CA | 50.473 | -104.627 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Bell names only the rural municipality. Coordinates are the RM's published reference point (Wikipedia infobox); because the RM surrounds Regina, this point is near the city and is not the campus site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 34f860f9-9746-5f72-9b8f-9cb414f9cb9c | under_construction | 2026-10-01 | 12 | imported_documented_status | 34f860f9-9746-5f72-9b8f-9cb414f9cb9c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2c88a108-743f-55a6-98df-271b27933fdd","notes":"Develops the campus under its Bell AI Fabric program.","party":"Bell Canada","relationship_scope":"unknown","role":"developer","source_record_id":"bell-ai-fabric-sherwood-saskatchewan"},{"evidence_id":"34f860f9-9746-5f72-9b8f-9cb414f9cb9c","notes":"Develops the campus under its Bell AI Fabric program.","party":"Bell Canada","relationship_scope":"unknown","role":"developer","source_record_id":"bell-ai-fabric-sherwood-saskatchewan"},{"evidence_id":"2c88a108-743f-55a6-98df-271b27933fdd","notes":"Signed a non-binding memorandum with Bell and says it approved the expansion under its Data Centre Framework.","party":"Government of Saskatchewan","relationship_scope":"unknown","role":"government","source_record_id":"bell-ai-fabric-sherwood-saskatchewan"},{"evidence_id":"34f860f9-9746-5f72-9b8f-9cb414f9cb9c","notes":"Signed a non-binding memorandum with Bell and says it approved the expansion under its Data Centre Framework.","party":"Government of Saskatchewan","relationship_scope":"unknown","role":"government","source_record_id":"bell-ai-fabric-sherwood-saskatchewan"},{"evidence_id":"7e971879-548c-51e7-8f04-85af309e090e","notes":"Signed a non-binding memorandum with Bell and says it approved the expansion under its Data Centre Framework.","party":"Government of Saskatchewan","relationship_scope":"unknown","role":"government","source_record_id":"bell-ai-fabric-sherwood-saskatchewan"},{"evidence_id":"34f860f9-9746-5f72-9b8f-9cb414f9cb9c","notes":"Building the high-voltage substation that connects the campus to the provincial grid.","party":"Dynamo Electric","relationship_scope":"unknown","role":"builder","source_record_id":"bell-ai-fabric-sherwood-saskatchewan"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-provides-construction-update-in-saskatchewan-announces-1-million-mental-health-commitment | https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-provides-construction-update-in-saskatchewan-announces-1-million-mental-health-commitment | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bell AI Fabric Sherwood campus (Regina area) as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"bell-ai-fabric-sherwood-saskatchewan"},"record":{"aliases":["Bell AI Fabric Saskatchewan"],"id":"bell-ai-fabric-sherwood-saskatchewan","last_reviewed":"2026-10-09","location":{"admin1":"Saskatchewan","admin2":"Rural Municipality of Sherwood No. 159","country":"CA","lat":50.473,"locality":"Regina area","lon":-104.627,"note":"Bell names only the rural municipality. Coordinates are the RM's published reference point (Wikipedia infobox); because the RM surrounds Regina, this point is near the city and is not the campus site.","precision":"admin2","source_ids":["s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-01","basis":"under_construction","metric":"power_capacity","note":"Bell describes this campus as the first phase of a potential 1.2 GW hub; the additional up to 900 MW under the September 2026 memorandum is not tied to a named site.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2026-10-01","basis":"under_construction","metric":"buildings","phase_label":"First phase","qualifier":"exact","source_ids":["s2"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2026-10-01","basis":"reported","metric":"jobs_construction","note":"Workers on site at the time of the update.","qualifier":"more_than","source_ids":["s2"],"unit":"count","value":500}],"milestones":[{"date":"2026-09-14","event":"expansion_announced","kind":"actual","note":"Non-binding memorandum with the Government of Saskatchewan for phased development of up to 900 MW of additional capacity, which the province says it approved under its Data Centre Framework; contingent on customers, agreements and approvals.","source_ids":["s1","s3"]},{"date":"2027-H1","event":"first_operational","kind":"planned","note":"First data hall expected to begin operating.","source_ids":["s2"]}],"name":"Bell AI Fabric Sherwood campus (Regina area)","notes":"Bell says total capital investment across its Saskatchewan presence, including data centre infrastructure, customer compute and power generation, could exceed 50 billion dollars if fully realized; this is province-wide and not recorded as a campus metric.","parties":[{"name":"Bell Canada","note":"Develops the campus under its Bell AI Fabric program.","role":"developer","source_ids":["s1","s2"]},{"name":"Government of Saskatchewan","note":"Signed a non-binding memorandum with Bell and says it approved the expansion under its Data Centre Framework.","role":"government","source_ids":["s1","s2","s3"]},{"name":"Dynamo Electric","note":"Building the high-voltage substation that connects the campus to the provincial grid.","role":"builder","source_ids":["s2"]}],"power_sources":[{"description":"The province says the original 300 MW comes from the provincial grid; a new high-voltage substation will connect the campus.","source_ids":["s2","s3"],"type":"grid"},{"description":"Expansion of up to 900 MW would use Bell-arranged generation under the province's bring-your-own-power approach; Bell describes it as partner-developed natural gas generation. Siting relative to the campus was not stated.","source_ids":["s1","s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-09-14","publisher":"BCE Inc.","title":"Bell AI Fabric to expand nation-building project in Saskatchewan with up to 900 MW of additional power","type":"company","url":"https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-to-expand-nation-building-project-in-saskatchewan-with-up-to-900-mw-of-additional-power"},{"accessed":"2026-10-09","id":"s2","published":"2026-10-01","publisher":"BCE Inc.","title":"Bell AI Fabric provides construction update in Saskatchewan, announces $1 million mental health commitment","type":"company","url":"https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-provides-construction-update-in-saskatchewan-announces-1-million-mental-health-commitment"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-14","publisher":"Government of Saskatchewan","title":"Single Largest Private Sector Capital Investment in History of Canada Through Bell AI's Saskatchewan Expansion","type":"government","url":"https://www.saskatchewan.ca/government/news-and-media/2026/september/14/single-largest-private-sector-capital-investment-in-history-of-canada-through-bell-ais-saskatchewan"}],"status":"under_construction","status_as_of":"2026-10-01","status_source_ids":["s2"],"summary":"Bell Canada is building a 300 MW Bell AI Fabric data centre campus in the Rural Municipality of Sherwood, which surrounds Regina, Saskatchewan. In October 2026 Bell reported structural steel rising on all four first-phase buildings, more than 500 workers on site and the first data hall on track to operate in the first half of 2027. In September 2026 Bell and the Government of Saskatchewan signed a non-binding memorandum for up to 900 MW more, which would make the Sherwood campus the first phase of a potential 1.2 GW provincial AI hub.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2c88a108-743f-55a6-98df-271b27933fdd","s2":"34f860f9-9746-5f72-9b8f-9cb414f9cb9c","s3":"7e971879-548c-51e7-8f04-85af309e090e"},"source_file":"datacenters/projects/bell-ai-fabric-sherwood-saskatchewan.json","source_record_id":"bell-ai-fabric-sherwood-saskatchewan","source_record_sha256":"16c96149f34f8e8f77b8c0c17353148d280b27c5336b316bd6a5419437e7acef","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b9459e91be9778e53640bf83151969fff7795be0edbd0d71666ce677c12c8b71"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0834945607ed54e349ce/#project-0b37ac4d-93f2-559b-a6ec-f5a12938681a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0b37ac4d-93f2-559b-a6ec-f5a12938681a.json
0b67b532-d779-5784-bd6d-d7ee124844aa | curated:chirisa-chesterfield-campus:digital-drive-current-build | vcc-site-265ff643497c82472bb3 | curated:chirisa-chesterfield-campus | Chirisa Chesterfield Digital Drive Current Build | United States | US | 37.3562 | -77.3343 | Point | campus | official_service_parcel_centroid | ArcGIS_returnCentroid_true_outSR_4326_exact_property_query | official_parcel_reference_point | official_source | campus_locator | Official source-specific constituent-property centroid used only as a campus locator. Not a surveyed point, full campus boundary, building footprint, entrance, active-work extent or construction stage. Source numerical precision is not positional accuracy. |  | County terms explicitly disclaim numerical positional accuracy and legal/survey use. | 86f45bc6-05ec-50f5-bfee-bdcfcac3b59c | under_construction | 2026-07-01 | 104 | authoritative_physical_status_update | 4c158d0b-011c-5409-971b-60ce87d4f972 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.chesterfield.gov/5989/Data-Centers | https://services3.arcgis.com/TsynfzBSE6sXfoLq/ArcGIS/rest/services/Cadastral_ProdA/FeatureServer/3/query | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-265ff643497c82472bb3/#project-0b67b532-d779-5784-bd6d-d7ee124844aa | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0b67b532-d779-5784-bd6d-d7ee124844aa.json
0bac3fe4-c3dd-54ba-a500-e37599191432 | curated:colt-london-hayes-campus:london4-current-facility-build | vcc-site-b38b02f920b409f27698 | curated:colt-london-hayes-campus | Colt London 4 Current Facility Build | United Kingdom | GB | 51.5096 | -0.39409 | Polygon | building | capture_replayed_geometry | capture_replayed_openstreetmap_exact_colt_london4_named_building_polygon_as_project_locator | community_mapped_named_colt_london4_building_polygon | community_mapped | project_locator | Contributor-mapped polygon for the exact named London 4 building, used only to locate the selected facility-build project. It is not an official building footprint, parcel, complete present or future campus boundary, five-building plan, security boundary, or current construction-progress extent. |  | OpenStreetMap supplies no survey, cadastral, planning-boundary, or numeric horizontal-accuracy statement. | c0b3ca09-1341-5395-9301-9f6a2d67cf0c | under_construction | 2026-07-19 | 86 | authoritative_physical_status_update | 465b57e0-58b6-56aa-8b00-728b9cc9c201 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-19","base":31.0,"confidence":0.99,"evidence_id":"6e4b0bfe-23de-5439-9dc0-3688a382a285","high":31.0,"low":31.0,"method":"reported","metric":"critical_it_mw","notes":"Planned critical-IT capacity for the London 4 facility only. The source says 31 MW of IT power will be delivered upon completion; this is not current load, gross facility power, grid draw, generation, measured energy consumption, or capacity for the future five-building campus.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.coltdatacentres.net/en-GB/our-locations/data-centre-locations-europe/london-4/timeline | https://www.openstreetmap.org/way/1495920404 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b38b02f920b409f27698/#project-0bac3fe4-c3dd-54ba-a500-e37599191432 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0bac3fe4-c3dd-54ba-a500-e37599191432.json
0bf81b53-0bf9-551d-807b-16392ea21962 | curated:iron-mountain-nje-1-new-jersey-data-center:expansion-4mw | vcc-site-7067da1bf27989e69807 | curated:iron-mountain-nje-1-new-jersey-data-center | Iron Mountain NJE-1 Expansion | United States | US | 40.5299 | -74.3279 | Point | campus | official_address_range_geocode | census_single_exact_address_match_then_explicit_nad83_to_wgs84 | official_address_range_interpolation_exact_campus_address_locator | official_source | campus_locator | Official Census street-address interpolation for the exact NJE-1 address at 3003 Woodbridge Avenue. The operator identifies NJE-1 at that address and Edison government records corroborate the property and parcel identity. This locates the existing campus containing the selected expansion; it is not the new expansion hall, footprint, parcel boundary or surveyed facility center. |  | No source-specific numerical horizontal-accuracy guarantee is published for the selected street-range interpolation. | 44fdf373-1340-5203-82e9-b78513f8f5d5 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 57a8e965-42f2-5089-b1a1-0d3297d572c3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1020569/000102056926000068/q22026srpfinal.htm | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=3003%20Woodbridge%20Ave%20Edison%20NJ%2008837&benchmark=Public_AR_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7067da1bf27989e69807/#project-0bf81b53-0bf9-551d-807b-16392ea21962 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0bf81b53-0bf9-551d-807b-16392ea21962.json
0cdff49d-f05c-5993-acd1-d1259fd80165 | curated:pure-dc-brent-cross-lon01-campus:b2-composite-build | vcc-site-725184148f2278feb335 | curated:pure-dc-brent-cross-lon01-campus | Pure DC Brent Cross LON01 B2 Composite Build | United Kingdom | GB | 51.5706 | -0.23719 | Polygon | building | cross_source_geometry | openstreetmap_lon01_named_building_polygon_as_parent_campus_locator | reviewed_openstreetmap_pure_dc_lon01_named_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for one known LON01 building, used only to locate the parent Brent Cross campus. It is not identified as either B2 work zone, the B2 composite-build footprint, a complete campus boundary, an official parcel or planning boundary, or a current construction-progress extent. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | ee256a2f-4e9b-5224-a6ce-e4f95c4a11ed | under_construction | 2026-05-28 | 138 | authoritative_physical_status_update | a9d0173c-a00c-5936-b2d2-493a61fc0d53 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://puredc.com/2026/05/28/pure-dc-appoints-glencar-for-next-phase-of-its-90mw-brent-cross-campus-build-out | https://www.openstreetmap.org/way/38246899 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-725184148f2278feb335/#project-0cdff49d-f05c-5993-acd1-d1259fd80165 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0cdff49d-f05c-5993-acd1-d1259fd80165.json
0d416a87-60ba-5c1d-a419-a94965619724 | imported:semiconductor-atlas:ctrls-chandanvelly-hyderabad | vcc-site-7a48afbd332e0560f535 | imported:semiconductor-atlas:ctrls-chandanvelly-hyderabad | CtrlS Chandanvelly AI-ready data center park | India | IN | 17.2327 | 78.1713 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name the Chandanvelly Industrial Park near Hyderabad without an address; the point is the Chandanvelly village coordinate from its Wikipedia article, so it marks the village rather than the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | bf0ce2e0-c7f1-565f-a5ab-18f5a70ff896 | announced | 2025-01-23 | 628 | imported_documented_status | bf0ce2e0-c7f1-565f-a5ab-18f5a70ff896 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"bf0ce2e0-c7f1-565f-a5ab-18f5a70ff896","notes":null,"party":"CtrlS Datacenters Ltd","relationship_scope":"unknown","role":"developer","source_record_id":"ctrls-chandanvelly-hyderabad"},{"evidence_id":"a470afb0-c3b6-589e-bdcf-24534f789f2e","notes":null,"party":"CtrlS Datacenters Ltd","relationship_scope":"unknown","role":"developer","source_record_id":"ctrls-chandanvelly-hyderabad"},{"evidence_id":"5176efe4-1348-522b-add5-9b2a98a0fe3d","notes":null,"party":"CtrlS Datacenters Ltd","relationship_scope":"unknown","role":"developer","source_record_id":"ctrls-chandanvelly-hyderabad"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://w.media/ctrls-to-build-new-ai-ready-dc-park-near-hyderabad/ | https://w.media/ctrls-to-build-new-ai-ready-dc-park-near-hyderabad/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve CtrlS Chandanvelly AI-ready data center park as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"ctrls-chandanvelly-hyderabad","source_relations":[{"reason":"Distinct AirTrunk HYD1 and CtrlS campus announcements share only the Chandanvelly locality locator.","relationship":"separate_named_developments","source_id":"airtrunk-hyd1-chandanvelly"}]},"record":{"aliases":["CtrlS Hyderabad datacenter park"],"id":"ctrls-chandanvelly-hyderabad","last_reviewed":"2026-10-09","location":{"admin1":"Telangana","country":"IN","lat":17.2327,"locality":"Chandanvelly","lon":78.1713,"note":"Sources name the Chandanvelly Industrial Park near Hyderabad without an address; the point is the Chandanvelly village coordinate from its Wikipedia article, so it marks the village rather than the parcel.","precision":"locality","source_ids":["s1","s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-01-22","basis":"planned","metric":"power_capacity","note":"Potential IT load at full development.","power_scope":"it_load","qualifier":"more_than","source_ids":["s1","s3"],"unit":"MW","value":600},{"applies_to":"phase","as_of":"2025-01-22","basis":"contracted","metric":"power_capacity","note":"Power capacity CtrlS said was sanctioned for the first phase.","phase_label":"Phase 1","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2025-01-22","basis":"planned","metric":"power_capacity","note":"Expandable rating of the planned dedicated gas-insulated substation.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s1","s3"],"unit":"MW","value":900},{"applies_to":"campus","as_of":"2025-01-22","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1","s3"],"unit":"acres","value":40}],"milestones":[{"date":"2025-01-21","event":"announced","kind":"actual","source_ids":["s1","s3"]}],"name":"CtrlS Chandanvelly AI-ready data center park","notes":"Two days after the announcement, CtrlS signed an MoU with the Telangana government at the World Economic Forum in Davos for more than Rs 10,000 crore of investment in a cluster of AI-ready data centers in the state; the coverage does not tie that amount to Chandanvelly, so it is not recorded as a site investment. No 2025 or 2026 construction or status update was found; status reflects the January 2025 announcement. Wikipedia is cited only for the village coordinate.","parties":[{"name":"CtrlS Datacenters Ltd","role":"developer","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"Dedicated gas-insulated substation expandable to 900 MW, with 250 MW sanctioned for phase 1.","source_ids":["s1","s3"],"type":"grid"},{"description":"Solar module facades planned on the western and southern elevations of the buildings.","source_ids":["s1"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250723233847/https://w.media/ctrls-to-build-new-ai-ready-dc-park-near-hyderabad/","id":"s1","published":"2025-01-22","publisher":"W.Media","title":"CtrlS to build new AI-ready DC park near Hyderabad","type":"trade_press","url":"https://w.media/ctrls-to-build-new-ai-ready-dc-park-near-hyderabad/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260829031127/https://w.media/ctrls-signs-mou-with-telangana-govt-to-invest-rs-10000-crores-into-ai-dc-cluster/","id":"s2","published":"2025-01-23","publisher":"W.Media","title":"CtrlS signs MoU with Telangana gov't: To invest Rs 10,000 crores into AI DC cluster","type":"trade_press","url":"https://w.media/ctrls-signs-mou-with-telangana-govt-to-invest-rs-10000-crores-into-ai-dc-cluster/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260416111839/https://apacnewsnetwork.com/2025/01/ctrls-to-establish-new-datacentre-park-near-hyderabad-to-enhance-companys-it-capabilities/","id":"s3","published":"2025-01-21","publisher":"APAC News Network","title":"CtrlS to establish new datacentre park near Hyderabad to enhance company's IT capabilities","type":"news","url":"https://apacnewsnetwork.com/2025/01/ctrls-to-establish-new-datacentre-park-near-hyderabad-to-enhance-companys-it-capabilities"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Chandanvelly","type":"other","url":"https://en.wikipedia.org/wiki/Chandanvelly"}],"status":"announced","status_as_of":"2025-01-23","status_source_ids":["s1","s2","s3"],"summary":"CtrlS Datacenters announced in January 2025 a 40-acre data center park at the planned Chandanvelly Industrial Park near Hyderabad, Telangana, designed for more than 600 MW of IT load at full build. CtrlS said 250 MW of power had been sanctioned for the first phase, served by a dedicated gas-insulated substation expandable to 900 MW, with buildings designed for up to 135 kW per rack and immersion cooling up to 300 kW per rack. No construction update was found.","workloads":["ai_unspecified","colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"bf0ce2e0-c7f1-565f-a5ab-18f5a70ff896","s2":"a470afb0-c3b6-589e-bdcf-24534f789f2e","s3":"5176efe4-1348-522b-add5-9b2a98a0fe3d","s4":"a22e40d8-827d-5577-8c94-3751b3d8ba02"},"source_file":"datacenters/projects/ctrls-chandanvelly-hyderabad.json","source_record_id":"ctrls-chandanvelly-hyderabad","source_record_sha256":"7dd01d7be3753fcb156107c7dc695342e69642ef510f51568f1d467a05d2d340","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a0d9b7273ed148ab2ef4c769a6636861cd032a95a13290a6ac885bc1cd293278"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7a48afbd332e0560f535/#project-0d416a87-60ba-5c1d-a419-a94965619724 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0d416a87-60ba-5c1d-a419-a94965619724.json
0d75be4c-1fff-5854-895c-71aef25eff11 | imported:semiconductor-atlas:tcs-hypervault-hyderabad | vcc-site-23fd4beb18c498caa043 | imported:semiconductor-atlas:tcs-hypervault-hyderabad | TCS HyperVault AI data center campus, Bharat Future City (Hyderabad) | India | IN | 17.3617 | 78.4747 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Hyderabad and place the campus in Bharat Future City on the city's southern outskirts, without a district, address or coordinates; Bharat Future City's Wikipedia article has no coordinates. The point is the Hyderabad city coordinate from Wikipedia, so it marks the named city, and the site lies an unknown distance to its south. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 68467274-a4f9-5243-aa49-c2a638788480 | announced | 2026-09-09 | 34 | imported_documented_status | 68467274-a4f9-5243-aa49-c2a638788480 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"68467274-a4f9-5243-aa49-c2a638788480","notes":"Subsidiary of Tata Consultancy Services.","party":"HyperVault AI Data Center Limited","relationship_scope":"unknown","role":"developer","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"3b23c6b7-ae38-589a-bc7f-c53ddade961d","notes":"Subsidiary of Tata Consultancy Services.","party":"HyperVault AI Data Center Limited","relationship_scope":"unknown","role":"developer","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"482ec04b-4106-572f-8f58-56bc4c621d4e","notes":"Subsidiary of Tata Consultancy Services.","party":"HyperVault AI Data Center Limited","relationship_scope":"unknown","role":"developer","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"68467274-a4f9-5243-aa49-c2a638788480","notes":"Parent of HyperVault; keeps board control under the TPG deal.","party":"Tata Consultancy Services","relationship_scope":"unknown","role":"investor","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"3b23c6b7-ae38-589a-bc7f-c53ddade961d","notes":"Parent of HyperVault; keeps board control under the TPG deal.","party":"Tata Consultancy Services","relationship_scope":"unknown","role":"investor","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"68467274-a4f9-5243-aa49-c2a638788480","notes":"Agreed in November 2025 to invest up to Rs 8,820 crore in HyperVault for a 27.5 to 49 percent stake; this is an investment in the company, not specifically in this site.","party":"TPG","relationship_scope":"unknown","role":"investor","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"3b23c6b7-ae38-589a-bc7f-c53ddade961d","notes":"Agreed in November 2025 to invest up to Rs 8,820 crore in HyperVault for a 27.5 to 49 percent stake; this is an investment in the company, not specifically in this site.","party":"TPG","relationship_scope":"unknown","role":"investor","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"482ec04b-4106-572f-8f58-56bc4c621d4e","notes":"Agreed in November 2025 to invest up to Rs 8,820 crore in HyperVault for a 27.5 to 49 percent stake; this is an investment in the company, not specifically in this site.","party":"TPG","relationship_scope":"unknown","role":"investor","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"adc18193-865a-5686-a376-7ce0530392b8","notes":"Agreed in November 2025 to invest up to Rs 8,820 crore in HyperVault for a 27.5 to 49 percent stake; this is an investment in the company, not specifically in this site.","party":"TPG","relationship_scope":"unknown","role":"investor","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"68467274-a4f9-5243-aa49-c2a638788480","notes":"The chief minister announced the project and assured HyperVault of the required sanctions.","party":"Government of Telangana","relationship_scope":"unknown","role":"government","source_record_id":"tcs-hypervault-hyderabad"},{"evidence_id":"3b23c6b7-ae38-589a-bc7f-c53ddade961d","notes":"The chief minister announced the project and assured HyperVault of the required sanctions.","party":"Government of Telangana","relationship_scope":"unknown","role":"government","source_record_id":"tcs-hypervault-hyderabad"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://thearabianpost.com/tcs-commits-₹700-billion-to-hyderabad-ai-campus/ | https://thearabianpost.com/tcs-commits-₹700-billion-to-hyderabad-ai-campus/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve TCS HyperVault AI data center campus, Bharat Future City (Hyderabad) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"tcs-hypervault-hyderabad"},"record":{"aliases":["HyperVault Hyderabad","HyperVault Bharat Future City"],"id":"tcs-hypervault-hyderabad","last_reviewed":"2026-10-09","location":{"admin1":"Telangana","country":"IN","lat":17.3617,"locality":"Hyderabad (Bharat Future City)","lon":78.4747,"note":"Sources name Hyderabad and place the campus in Bharat Future City on the city's southern outskirts, without a district, address or coordinates; Bharat Future City's Wikipedia article has no coordinates. The point is the Hyderabad city coordinate from Wikipedia, so it marks the named city, and the site lies an unknown distance to its south.","precision":"locality","source_ids":["s1","s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-09-05","basis":"planned","metric":"power_capacity","note":"Sources say up to 1 GW without stating IT or facility power; build-out will be phased to demand.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-09-05","basis":"announced","metric":"investment","note":"Rs 70,000 crore expected from HyperVault and its partners for development and operation over several years.","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"INR","value":700000000000},{"applies_to":"campus","as_of":"2026-09-05","basis":"reported","metric":"land_area","note":"Described as land HyperVault has secured; the sources do not say whether it was bought or allotted.","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"acres","value":264}],"milestones":[{"date":"2026-09-05","event":"announced","kind":"actual","source_ids":["s1","s2","s3"]},{"date":"2028-06-02","event":"first_operational","kind":"planned","note":"Opening date requested by Telangana's chief minister, tied to the state's formation day; not stated as a company target.","source_ids":["s2"]}],"name":"TCS HyperVault AI data center campus, Bharat Future City (Hyderabad)","notes":"StartupFeed says HyperVault disclosed the plan in a regulatory filing but does not name the exchange; the filing itself is not cited, so the record relies on news coverage. Telangana's chief minister estimated about 7,000 jobs without saying whether they are direct or permanent, so no job metric is recorded. W.Media reports that OpenAI was announced in February 2026 as HyperVault's first customer at 100 MW, but no source ties OpenAI to this site. HyperVault's land in Anakapalli and in Bopkhel, Pune, are separate projects. Wikipedia is cited only for the city coordinate.","parties":[{"name":"HyperVault AI Data Center Limited","note":"Subsidiary of Tata Consultancy Services.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Tata Consultancy Services","note":"Parent of HyperVault; keeps board control under the TPG deal.","role":"investor","source_ids":["s1","s2"]},{"name":"TPG","note":"Agreed in November 2025 to invest up to Rs 8,820 crore in HyperVault for a 27.5 to 49 percent stake; this is an investment in the company, not specifically in this site.","role":"investor","source_ids":["s1","s2","s3","s5"]},{"name":"Government of Telangana","note":"The chief minister announced the project and assured HyperVault of the required sanctions.","role":"government","source_ids":["s1","s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260906092732/https://thearabianpost.com/tcs-commits-%e2%82%b9700-billion-to-hyderabad-ai-campus/","id":"s1","published":"2026-09-05","publisher":"The Arabian Post","title":"TCS commits ₹700 billion to Hyderabad AI campus","type":"news","url":"https://thearabianpost.com/tcs-commits-₹700-billion-to-hyderabad-ai-campus/"},{"accessed":"2026-10-09","id":"s2","published":"2026-09-09","publisher":"StartupFeed","title":"TCS HyperVault to Build Rs 70,000 Cr AI Data Centre in Hyderabad","type":"news","url":"https://startupfeed.in/?p=11607"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-05","publisher":"Sahi","title":"TCS HyperVault to set up ₹70,000 crore AI data center in Telangana","type":"news","url":"https://www.sahi.com/news/tcs-hypervault-to-set-up-70-000-crore-ai-data-center-in-telangana-2185-PE1_COR"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Hyderabad","type":"other","url":"https://en.wikipedia.org/wiki/Hyderabad"},{"accessed":"2026-10-09","id":"s5","published":"2026-07-21","publisher":"W.Media","title":"TCS adds Anakapalli and Pune sites to fuel its data center push","type":"trade_press","url":"https://w.media/tcs-adds-anakapalli-and-pune-sites-to-fuel-its-data-center-push/"}],"status":"announced","status_as_of":"2026-09-09","status_source_ids":["s1","s2","s3"],"summary":"HyperVault AI Data Center Limited, the data center subsidiary of Tata Consultancy Services, announced on 5 September 2026 that it had secured 264 acres in Hyderabad, Telangana, for an AI campus of up to 1 GW, with HyperVault and its partners expected to invest up to Rs 70,000 crore over the build-out. The site is in Bharat Future City on Hyderabad's southern outskirts. Construction will be phased to customer demand, and Telangana's chief minister asked for the campus to open by 2 June 2028. TPG agreed in November 2025 to take a 27.5 to 49 percent stake in HyperVault.","workloads":["ai_training","ai_inference"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"68467274-a4f9-5243-aa49-c2a638788480","s2":"3b23c6b7-ae38-589a-bc7f-c53ddade961d","s3":"482ec04b-4106-572f-8f58-56bc4c621d4e","s4":"bfe42f31-b6e0-563e-b4dd-957271914fbc","s5":"adc18193-865a-5686-a376-7ce0530392b8"},"source_file":"datacenters/projects/tcs-hypervault-hyderabad.json","source_record_id":"tcs-hypervault-hyderabad","source_record_sha256":"7ab430f2d4c7241fbcba9a1d98ff235e0e05dbfb82b29311d12b2af980637444","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"cc82971333d2d52d504e8812317c8a7e9bbcbcc25371cfacf3567ff4f9b6b0a2"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-23fd4beb18c498caa043/#project-0d75be4c-1fff-5854-895c-71aef25eff11 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0d75be4c-1fff-5854-895c-71aef25eff11.json
0eb54c2e-ed0f-58e9-85cc-bf616b723139 | imported:semiconductor-atlas:applied-digital-polaris-forge-3 | vcc-site-5af95dd1d26b0546ea7f | imported:semiconductor-atlas:applied-digital-polaris-forge-3 | Applied Digital Polaris Forge 3 | United States | US | 47.115 | -101.2978 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid of Center from its Wikipedia coordinates (s4). The October 2026 earnings release (s3) names Center, Oliver County; no parcel or address has been found. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | bf899518-100f-5bdf-a35a-f09014cb679f | under_construction | 2026-10-07 | 6 | imported_documented_status | bf899518-100f-5bdf-a35a-f09014cb679f | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"382c3879-d33c-54d1-bdaf-beabe809b5ab","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-polaris-forge-3"},{"evidence_id":"f7e21ccf-b5ac-5fcb-859a-73f9804397da","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-polaris-forge-3"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year | https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Applied Digital Polaris Forge 3 as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"applied-digital-polaris-forge-3"},"record":{"aliases":["Polaris Forge 3 AI Factory Campus"],"id":"applied-digital-polaris-forge-3","last_reviewed":"2026-10-09","location":{"admin1":"North Dakota","admin2":"Oliver County","country":"US","lat":47.115,"locality":"Center","lon":-101.2978,"note":"Town centroid of Center from its Wikipedia coordinates (s4). The October 2026 earnings release (s3) names Center, Oliver County; no parcel or address has been found.","precision":"locality","source_ids":["s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-20","basis":"contracted","metric":"power_capacity","note":"Critical IT load leased to an unnamed US high investment-grade hyperscaler for 15 years, about 7.5 billion US dollars of base-term contracted revenue.","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-05-20","basis":"planned","metric":"power_capacity","note":"Grid-connected utility power supporting the campus.","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":430}],"milestones":[{"date":"2026-05-20","event":"announced","kind":"actual","note":"Lease announcement; the location was described only as a northern state.","source_ids":["s1"]},{"date":"2027-08","event":"first_operational","kind":"planned","note":"May 2026 target; the July 2026 results release says initial operations are expected during calendar 2027.","source_ids":["s1","s2"]}],"name":"Applied Digital Polaris Forge 3","parties":[{"name":"Applied Digital","role":"developer","source_ids":["s1","s3"]}],"power_sources":[{"description":"About 430 MW of grid-connected utility power; the utility is not named in the cited sources.","source_ids":["s1"],"type":"grid"}],"related_ids":["applied-digital-polaris-forge-1","applied-digital-polaris-forge-2"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260921025500/https://ir.applieddigital.com/news-events/press-releases/detail/152/applied-digital-reaches-significant-milestone-surpassing-1","id":"s1","published":"2026-05-20","publisher":"Applied Digital","title":"Applied Digital Reaches Significant Milestone, Surpassing 1 GW of Contracted Capacity with U.S. Based High Investment-Grade Hyperscaler Lease at Fourth Campus, Polaris Forge 3","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/152/applied-digital-reaches-significant-milestone-surpassing-1"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-27","publisher":"Applied Digital","title":"Applied Digital Reports Fiscal Fourth Quarter and Full Year 2026 Results","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year"},{"accessed":"2026-10-09","id":"s3","published":"2026-10-07","publisher":"U.S. Securities and Exchange Commission (Applied Digital filing)","title":"Applied Digital Reports Fiscal First Quarter 2027 Results (Form 8-K exhibit)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001144879/000114487926000057/apldq127earningsrelease.htm"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Center, North Dakota","type":"other","url":"https://en.wikipedia.org/wiki/Center,_North_Dakota"}],"status":"under_construction","status_as_of":"2026-10-07","status_source_ids":["s2","s3"],"summary":"Applied Digital's fourth AI factory campus, in Center, Oliver County, North Dakota. In May 2026 the company announced a 15-year take-or-pay lease with an unnamed US high investment-grade hyperscaler for 300 MW of critical IT load, supported by about 430 MW of grid-connected utility power, worth about 7.5 billion US dollars over the base term. The May release withheld the state; the company's October 2026 earnings release names Center, North Dakota. The campus is under construction, with initial operations targeted for 2027.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"382c3879-d33c-54d1-bdaf-beabe809b5ab","s2":"bf899518-100f-5bdf-a35a-f09014cb679f","s3":"f7e21ccf-b5ac-5fcb-859a-73f9804397da","s4":"2aa9849b-9467-53dd-ba43-e1fdbb2e2641"},"source_file":"datacenters/projects/applied-digital-polaris-forge-3.json","source_record_id":"applied-digital-polaris-forge-3","source_record_sha256":"bf8ae2da16a9750a0827601c845afcadcb3388756142390227e81be26b2fc1a2","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"765b34903aa389a6b11907ae3e16f2574c29e545b9fa29cb2d211a3518e4b8ae"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5af95dd1d26b0546ea7f/#project-0eb54c2e-ed0f-58e9-85cc-bf616b723139 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0eb54c2e-ed0f-58e9-85cc-bf616b723139.json
0f5f4fcc-53c4-53d0-9795-2a387d195364 | imported:semiconductor-atlas:microsoft-fairwater-mount-pleasant | vcc-site-fcc06643c640f5d8cce2 | curated:microsoft-mount-pleasant-datacenter-campus | Microsoft Fairwater AI datacenter, Mount Pleasant | United States | US | 42.6761 | -87.9001 | Point | project | imported_reference_point | imported_reference_point | site | compiled_reference | project_locator | Microsoft's construction page headings place Phase 1 at 'KR & 90' and Phase 2 at 'KR & H' (County Road KR with 90th Street and County Road H); Spectrum News says the site was originally slated for Foxconn. Coordinates are the OpenStreetMap feature named Microsoft Fairwater AI Datacenter (via Nominatim); OSM maps Phase 2 slightly further west at about 42.6780, -87.9076. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 604ef349-560c-5894-a96e-77a93538191a | partially_operational | 2026-06-23 | 112 | imported_documented_status | 91a23fd6-39c0-5dc9-b974-9d851cf2eadb | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"604ef349-560c-5894-a96e-77a93538191a","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"6011eac0-e690-530d-81a5-b6fdc14787c9","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"91a23fd6-39c0-5dc9-b974-9d851cf2eadb","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"02397198-c326-5ccf-af85-e38655c99fab","notes":"Epoch AI lists Microsoft as owner.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"91a23fd6-39c0-5dc9-b974-9d851cf2eadb","notes":"Microsoft reports about 550 full-time employees on site at the completed first facility.","party":"Microsoft","relationship_scope":"unknown","role":"operator","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"584bd73a-2990-55d2-a244-4a012f62f39c","notes":"Named on Microsoft's construction update page for foundation work from November 2023 and as the Phase 2 contractor from November 2025.","party":"Walsh Construction","relationship_scope":"unknown","role":"builder","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"584bd73a-2990-55d2-a244-4a012f62f39c","notes":"Named on Microsoft's construction update page in September and October 2024 as a main contractor working along County Road KR and County Road H.","party":"Kiewit","relationship_scope":"unknown","role":"builder","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"6011eac0-e690-530d-81a5-b6fdc14787c9","notes":"Microsoft cites a partnership with We Energies, and its February 2024 construction update said We Energies would soon start building a substation on the western part of the parcel.","party":"We Energies","relationship_scope":"unknown","role":"utility","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"584bd73a-2990-55d2-a244-4a012f62f39c","notes":"Microsoft cites a partnership with We Energies, and its February 2024 construction update said We Energies would soon start building a substation on the western part of the parcel.","party":"We Energies","relationship_scope":"unknown","role":"utility","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"604ef349-560c-5894-a96e-77a93538191a","notes":"Partner on a 250 MW Wisconsin solar project announced alongside the campus; a renewable matching arrangement rather than a stated direct feed to the site.","party":"National Grid Renewables","relationship_scope":"unknown","role":"power_supplier","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"f0262e63-d476-501f-90e8-8fba23716ac3","notes":"Microsoft describes the cluster as built on NVIDIA GB200 servers with Blackwell GPUs.","party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"f0262e63-d476-501f-90e8-8fba23716ac3","notes":"Reported, not confirmed: Microsoft says its AI datacenters power OpenAI, and Epoch AI lists OpenAI as a likely user of this site.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"microsoft-fairwater-mount-pleasant"},{"evidence_id":"02397198-c326-5ccf-af85-e38655c99fab","notes":"Reported, not confirmed: Microsoft says its AI datacenters power OpenAI, and Epoch AI lists OpenAI as a likely user of this site.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"microsoft-fairwater-mount-pleasant"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Microsoft | Microsoft |  | OpenAI |  | https://news.microsoft.com/source/2026/06/23/microsoft-completes-construction-on-first-datacenter-facility-in-mount-pleasant-wisconsin/ | https://news.microsoft.com/source/2024/05/08/microsoft-announces-3-3-billion-investment-in-wisconsin-to-spur-artificial-intelligence-innovation-and-economic-growth/ | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["source_site_point_not_surveyed_boundary","campus_and_phase_scopes_must_remain_separate"],"rationale":"Source explicitly covers completed phase 1 plus adjacent phase 2 at County Road KR; existing record is specifically the second facility. Durand Avenue and International Drive are separate later locations and remain separate records.","source_record_id":"microsoft-fairwater-mount-pleasant","source_relations":[{"reason":"County Road KR phases 1/2 and Durand/Hewitt Memorial Phase 3 occupy separately described development parcels.","relationship":"separate_campus_parcels","source_id":"microsoft-mount-pleasant-durand-avenue"},{"reason":"County Road KR phases 1/2 and International Drive six-building campus occupy separately described development parcels.","relationship":"separate_campus_parcels","source_id":"microsoft-mount-pleasant-international-drive"}],"target_physical_site_stable_key":"curated:microsoft-mount-pleasant-datacenter-campus"},"record":{"aliases":["Fairwater","Fairwater 1","Microsoft Mount Pleasant datacenter campus"],"id":"microsoft-fairwater-mount-pleasant","last_reviewed":"2026-10-09","location":{"admin1":"Wisconsin","admin2":"Racine County","country":"US","lat":42.6761,"locality":"Mount Pleasant","lon":-87.9001,"note":"Microsoft's construction page headings place Phase 1 at 'KR & 90' and Phase 2 at 'KR & H' (County Road KR with 90th Street and County Road H); Spectrum News says the site was originally slated for Foxconn. Coordinates are the OpenStreetMap feature named Microsoft Fairwater AI Datacenter (via Nominatim); OSM maps Phase 2 slightly further west at about 42.6780, -87.9076.","precision":"site","source_ids":["s1","s4","s5","s6"]},"metrics":[{"applies_to":"phase","as_of":"2024-05-08","basis":"announced","metric":"investment","note":"Announced in May 2024 for spending through the end of 2026; Microsoft later called it the initial investment pledge, with the second datacenter funded separately.","phase_label":"First datacenter (Phase 1)","qualifier":"exact","source_ids":["s1","s2"],"unit":"USD","value":3300000000},{"applies_to":"phase","as_of":"2025-09-18","basis":"announced","metric":"investment","note":"Additional spend over three years on a second datacenter of similar size and scale.","phase_label":"Second datacenter (Phase 2)","qualifier":"exact","source_ids":["s2","s9"],"unit":"USD","value":4000000000},{"applies_to":"campus","as_of":"2025-09-18","basis":"announced","metric":"investment","note":"Microsoft framed this as its total Wisconsin datacenter investment once the second datacenter is included.","qualifier":"more_than","source_ids":["s2"],"unit":"USD","value":7000000000},{"applies_to":"phase","as_of":"2026-05-15","basis":"operational","metric":"power_capacity","note":"Epoch AI modeled estimate of current IT power (timeline entries of April and May 2026), not a company figure. Microsoft has not published a megawatt figure for the site.","phase_label":"First facility (Epoch AI Building 1)","power_scope":"it_load","qualifier":"approximately","source_ids":["s8"],"unit":"MW","value":369},{"applies_to":"phase","as_of":"2025-09-18","basis":"reported","metric":"land_area","phase_label":"First datacenter (Phase 1)","qualifier":"exact","source_ids":["s3","s9"],"unit":"acres","value":315},{"applies_to":"phase","as_of":"2025-09-18","basis":"under_construction","metric":"buildings","phase_label":"First datacenter (Phase 1)","qualifier":"exact","source_ids":["s3","s9"],"unit":"count","value":3},{"applies_to":"phase","as_of":"2025-09-18","basis":"under_construction","metric":"floor_area","note":"Combined floor area under roof of the three Phase 1 buildings.","phase_label":"First datacenter (Phase 1)","qualifier":"exact","source_ids":["s3","s9"],"unit":"sq_ft","value":1200000},{"applies_to":"phase","as_of":"2026-06-23","basis":"reported","metric":"jobs_permanent","phase_label":"First datacenter (Phase 1)","qualifier":"approximately","source_ids":["s4","s6"],"unit":"count","value":550},{"applies_to":"campus","as_of":"2026-06-23","basis":"planned","metric":"jobs_permanent","note":"Expected once the second facility is fully operational.","qualifier":"approximately","source_ids":["s2","s4"],"unit":"count","value":800},{"applies_to":"phase","as_of":"2026-06-23","basis":"reported","metric":"jobs_construction","note":"Workers over the two-year build of the first facility; Microsoft's release says nearly 10,000.","phase_label":"First datacenter (Phase 1)","qualifier":"approximately","source_ids":["s4","s6"],"unit":"count","value":10000}],"milestones":[{"date":"2023-07","event":"construction_started","kind":"actual","note":"Epoch AI dates the start of land clearing to 14 July 2023; Microsoft's update page reported permits received and grading planned from July 2023, with Walsh starting foundation work in November 2023.","source_ids":["s5","s8"]},{"date":"2024-05-08","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024-12","event":"paused","kind":"actual","note":"The Associated Press reported that in late December 2024 Microsoft disclosed it was pausing later phases of a large Wisconsin datacenter project.","source_ids":["s7"]},{"date":"2025-09-18","event":"expansion_announced","kind":"actual","note":"Second datacenter of similar size announced with an additional USD 4 billion.","source_ids":["s2","s9"]},{"date":"2025-11-01","event":"construction_started","kind":"actual","note":"Start of Phase 2 work by Walsh Construction at KR and County Road H.","source_ids":["s5"]},{"date":"2026-04","event":"first_operational","kind":"actual","note":"Microsoft says equipment came online with startup activities in April 2026; Epoch AI lists Building 1 as operational on 16 April 2026. Microsoft declared the first facility fully operational on 2026-06-23.","source_ids":["s4","s8"]},{"date":"2028","event":"other","kind":"planned","note":"Scheduled completion of the second facility (Phase 2); Microsoft's construction page says early 2028.","source_ids":["s4","s5","s6"]}],"name":"Microsoft Fairwater AI datacenter, Mount Pleasant","notes":"Phase 1 and the adjacent Phase 2 are kept in one record because Microsoft describes them as adjacent facilities on one site; the later Durand Avenue and International Drive campuses approved in January 2026 have their own records. Epoch AI's projected figures for this site also fold in a 9-building plan (its Buildings 3-11), so they are not recorded here. The construction page carries month-dated entries only.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Microsoft","note":"Epoch AI lists Microsoft as owner.","role":"owner","source_ids":["s8"]},{"name":"Microsoft","note":"Microsoft reports about 550 full-time employees on site at the completed first facility.","role":"operator","source_ids":["s4"]},{"name":"Walsh Construction","note":"Named on Microsoft's construction update page for foundation work from November 2023 and as the Phase 2 contractor from November 2025.","role":"builder","source_ids":["s5"]},{"name":"Kiewit","note":"Named on Microsoft's construction update page in September and October 2024 as a main contractor working along County Road KR and County Road H.","role":"builder","source_ids":["s5"]},{"name":"We Energies","note":"Microsoft cites a partnership with We Energies, and its February 2024 construction update said We Energies would soon start building a substation on the western part of the parcel.","role":"utility","source_ids":["s2","s5"]},{"name":"National Grid Renewables","note":"Partner on a 250 MW Wisconsin solar project announced alongside the campus; a renewable matching arrangement rather than a stated direct feed to the site.","role":"power_supplier","source_ids":["s1"]},{"name":"NVIDIA","note":"Microsoft describes the cluster as built on NVIDIA GB200 servers with Blackwell GPUs.","role":"hardware_supplier","source_ids":["s3"]},{"name":"OpenAI","note":"Reported, not confirmed: Microsoft says its AI datacenters power OpenAI, and Epoch AI lists OpenAI as a likely user of this site.","role":"tenant","source_ids":["s3","s8"]}],"power_sources":[{"description":"Grid supply via We Energies; Microsoft said in February 2024 that We Energies would soon start a substation on the western part of the parcel.","source_ids":["s5"],"type":"grid"},{"description":"Microsoft is matching the site with renewable contracts, including a 250 MW solar project in Portage County, Wisconsin, developed with National Grid Renewables and expected to operate in 2027.","source_ids":["s1","s2"],"type":"solar"}],"related_ids":["microsoft-mount-pleasant-durand-avenue","microsoft-mount-pleasant-international-drive","microsoft-fairwater-atlanta"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-05-08","publisher":"Microsoft","title":"Microsoft announces $3.3 billion investment in Wisconsin to spur artificial intelligence innovation and economic growth","type":"company","url":"https://news.microsoft.com/source/2024/05/08/microsoft-announces-3-3-billion-investment-in-wisconsin-to-spur-artificial-intelligence-innovation-and-economic-growth/"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-18","publisher":"Microsoft On the Issues","title":"Made in Wisconsin: The world's most powerful AI datacenter","type":"company","url":"https://blogs.microsoft.com/on-the-issues/2025/09/18/made-in-wisconsin-the-worlds-most-powerful-ai-datacenter/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260907010407/https://blogs.microsoft.com/blog/2025/09/18/inside-the-worlds-most-powerful-ai-datacenter/","id":"s3","published":"2025-09-18","publisher":"Official Microsoft Blog","title":"Inside the world's most powerful AI datacenter","type":"company","url":"https://blogs.microsoft.com/blog/2025/09/18/inside-the-worlds-most-powerful-ai-datacenter/"},{"accessed":"2026-10-09","id":"s4","published":"2026-06-23","publisher":"Microsoft","title":"Microsoft completes construction on first datacenter facility in Mount Pleasant, Wisconsin","type":"company","url":"https://news.microsoft.com/source/2026/06/23/microsoft-completes-construction-on-first-datacenter-facility-in-mount-pleasant-wisconsin/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260911205220/https://local.microsoft.com/blog/mount-pleasant-datacenter-project-update/","id":"s5","published":"2026-07","publisher":"Microsoft Local","title":"Mount Pleasant datacenter project update","type":"company","url":"https://local.microsoft.com/blog/mount-pleasant-datacenter-project-update/"},{"accessed":"2026-10-09","id":"s6","published":"2026-06-23","publisher":"Spectrum News 1","title":"Construction complete for first data center facility in Mount Pleasant","type":"news","url":"https://spectrumnews1.com/wi/milwaukee/news/2026/06/23/construction-data-center-facility-microsoft-mount-pleasant-.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250410023315/https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/","id":"s7","published":"2025-04-09","publisher":"Associated Press (via News4JAX)","title":"Microsoft says it's 'slowing or pausing' some AI data center projects, including $1B plan for Ohio","type":"news","url":"https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/"},{"accessed":"2026-10-09","id":"s8","published":"2026-10-05","publisher":"Epoch AI","title":"Microsoft Fairwater Wisconsin","type":"analyst","url":"https://epoch.ai/data/ai-data-centers/directory/microsoft-fairwater-wisconsin"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251026120044/https://w.media/microsoft-unveils-its-largest-ai-data-center-yet-to-spend-us-7-billion-on-wisconsin-facility/","id":"s9","published":"2025-09-22","publisher":"W.Media","title":"Microsoft unveils its largest AI data center yet; to spend US$ 7 billion on Wisconsin facility","type":"trade_press","url":"https://w.media/microsoft-unveils-its-largest-ai-data-center-yet-to-spend-us-7-billion-on-wisconsin-facility/"}],"status":"partially_operational","status_as_of":"2026-06-23","status_source_ids":["s4","s6"],"summary":"Microsoft AI supercomputing campus in Mount Pleasant, Wisconsin, on land originally slated for Foxconn. The first facility (Phase 1, near County Road KR and 90th Street) has three buildings with about 1.2 million sq ft on 315 acres; equipment came online in April 2026 and Microsoft declared it fully operational on 23 June 2026. A second facility of similar scale (Phase 2), immediately adjacent near KR and County Road H, has been under construction since November 2025 with completion scheduled for 2028. Microsoft pledged USD 3.3 billion for the first facility and USD 4 billion more for the second, and calls the site Fairwater.","workloads":["ai_training","ai_inference"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"604ef349-560c-5894-a96e-77a93538191a","s2":"6011eac0-e690-530d-81a5-b6fdc14787c9","s3":"f0262e63-d476-501f-90e8-8fba23716ac3","s4":"91a23fd6-39c0-5dc9-b974-9d851cf2eadb","s5":"584bd73a-2990-55d2-a244-4a012f62f39c","s6":"587ca249-1a3a-59eb-bf77-5afe16dc5ba7","s7":"ef4e5c49-f052-51e2-9745-4bdbf162e940","s8":"02397198-c326-5ccf-af85-e38655c99fab","s9":"3672a27a-eb15-5769-a38d-02c8f32d4991"},"source_file":"datacenters/projects/microsoft-fairwater-mount-pleasant.json","source_record_id":"microsoft-fairwater-mount-pleasant","source_record_sha256":"24656e656bf4cdff0af525c80e7f73c6f32adc9cbc3eecf6bacf0ff2abf770fa","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"ea9e84e4dd1d4c42e8dbd631f1f0f88952818db18088dae02c7f40ab2563e660"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fcc06643c640f5d8cce2/#project-0f5f4fcc-53c4-53d0-9795-2a387d195364 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0f5f4fcc-53c4-53d0-9795-2a387d195364.json
0fd5e6a4-6421-5a23-b51c-e490e4a79cd9 | curated:omnia-pecem-data-center-campus:initial-tiktok-bytedance-build | vcc-site-99459620c3cd48c8a82f | curated:omnia-pecem-data-center-campus | OMNIA Pecém Initial Data Center Construction | Brazil | BR | -3.6542 | -38.8223 | Point | campus | literal_official_public_project_marker | SEMACE_named_enterprise_record_lat_lon_under_public_Google_Maps_WGS84_interface_contract | officially_published_applicant_declared_project_reference_point | official_source | campus_locator | Exact point published for named Projeto Data Center Pecém / enterprise127774, not a surveyed agency boundary, parcel centroid, entrance, hall or selected-work footprint. All provided digits retained; underlying survey datum and measurement accuracy unknown. |  | SEMACE public client warns of distortions arising from applicant registration; no numerical accuracy is stated. WGS84 map-interface semantics and coordinate digits do not establish survey accuracy. | 6e15977f-e53d-5f29-8f9a-dddbde4623f6 | under_construction | 2026-06-16 | 119 | authoritative_physical_status_update | c23039eb-7928-5f8d-9518-505e5d26008a | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.complexodopecem.com.br/no-ceara-iniciadas-obras-do-terminal-logistico-que-ligara-o-porto-do-pecem-a-transnordestina/ | https://servicos.semace.ce.gov.br/SemaceMobileWS/webService/consultaProcesso/processos | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-99459620c3cd48c8a82f/#project-0fd5e6a4-6421-5a23-b51c-e490e4a79cd9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/0fd5e6a4-6421-5a23-b51c-e490e4a79cd9.json
100cf064-1cae-5dba-a4d9-6c4ae35152ec | curated:ai-tech-tomakomai-kashiwabara:phase1-foundations | vcc-site-f9661fed6650ccc21ce2 | curated:ai-tech-tomakomai-kashiwabara | AI Tech Tomakomai Phase I Foundation Works | Japan | JP | 42.6952 | 141.7662 | Polygon | campus | association_converted_official_cadastral_reference_polygon | retain_CRS84_AIGID_MOJ_2026_feature29260_Kashiwabara32_17_polygon_and_derive_planar_display_centroid | community_conversion_of_named_cadastral_parcel_containing_selected_project | community_source | campus_locator | The company names the same cadastral parcel as its data-center site. The association-converted polygon is retained as a reference parcel, not promoted to an official campus boundary, surveyed building footprint, active Phase I work extent or substation boundary. The centroid is only a derived display anchor. The same-number four other-city-district parcels and the Tokyo corporate office are excluded. |  | The source classifies this as graphically measured map data and provides no numeric parcel-specific horizontal uncertainty. CRS84 coordinates are retained, without claiming survey precision or exact datum-realization accuracy. | 17a317b4-d4a3-5fc0-b852-09cdfaf3de99 | under_construction | 2026-06-19 | 116 | authoritative_physical_status_update | 6f691578-9fb0-5ad7-a934-536f5acab3a5 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.ef-hd.com/wp-content/uploads/2026/06/2026061901_1ef.pdf | https://gsic-opendata.s3.ap-northeast-1.amazonaws.com/aigid/aigid-moj/2026/01/aigid-moj-01213/01213_%E8%8B%AB%E5%B0%8F%E7%89%A7%E5%B8%82_%E5%85%AC%E5%85%B1%E5%BA%A7%E6%A8%9912%E7%B3%BB_%E7%AD%86R_2026.geojson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f9661fed6650ccc21ce2/#project-100cf064-1cae-5dba-a4d9-6c4ae35152ec | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/100cf064-1cae-5dba-a4d9-6c4ae35152ec.json
118053c0-38ee-5fc1-9c4d-f4875cc3c32e | curated:raiden-infotech-turbhe-midc-data-centre-campus:ec-531703-current-build | vcc-site-53d6b726e740613f2b41 | curated:raiden-infotech-turbhe-midc-data-centre-campus | Raiden Infotech Turbhe MIDC Data Centre EC 531703 Current Build | India | IN | 19.0554 | 73.0234 | Polygon | campus | source_KML_project_polygon_XY_preserved | PARIVESH_CAF226849_2025_active_raiden_kml_Raiden_Plot_Boundary_WGS84_lonlat_no_transform | proponent_submitted_environmental_project_polygon | official_source | campus_locator | Exact source polygon vertices from the active CAF attachment's named plot boundary. SEIAA's EC site coordinate lies inside it and its geodesic area is within 0.13% of the EC plot area. A government-hosted proponent filing establishes a project-specific campus locator, not cadastral, surveyed or current-work-extent accuracy. The display anchor is the planar shoelace centroid of the source ring in source vertex order, verified inside it; it is not a publisher point, entrance or surveyed location. |  | Neither the KML, the CAF nor the EC states a positional accuracy, survey method, geodetic realization or control points. Decimal count and government hosting do not establish accuracy. | 34034aa1-f108-544c-8a94-2dd5f9244826 | under_construction | 2026-08-03 | 71 | authoritative_physical_status_update | 284323d5-84bc-54e0-94fc-3d8edeafda75 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=1544616&refId=1237477223&refType=COMPLIANCE&uuid=448f19a4-30c8-4bdd-8381-d845615e1f8d&version=1.1 | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=40829&refId=123711148&refType=caf&uuid=82bd367c-609c-46be-ab68-0d537b8e1d8e&version=1.0 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-53d6b726e740613f2b41/#project-118053c0-38ee-5fc1-9c4d-f4875cc3c32e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/118053c0-38ee-5fc1-9c4d-f4875cc3c32e.json
12407b2e-a44d-5c8d-aa62-c7b64045e20f | curated:applied-digital-polaris-forge-2-harwood:current-construction | vcc-site-847f0ddc67e6e40ce38a | curated:applied-digital-polaris-forge-2-harwood | Polaris Forge 2 Current Construction | United States | US | 46.9669 | -96.8685 | Polygon | campus | official_constituent_tax_parcel | Cass_GISPIN75000000120020_native_EPSG3857_to_EPSG4326_server_independently_checked | official_constituent_tax_parcel | official_source | campus_locator | Official corporate tax parcel at the exact NDDEQ data-center-associated generator address; one campus locator, not the complete PF2 campus boundary or the construction footprint of both buildings. WGS84 returned ring independently agrees with native Web Mercator conversion within 1.43e-14 degrees. No parcel survey accuracy is published. |  | No source-specific numeric accuracy is supplied. Coordinate decimals and transformation agreement are not source positional accuracy. | 1e7d82eb-791b-578e-b8b8-6c9312497731 | under_construction | 2026-07-27 | 78 | authoritative_physical_status_update | 8407e7ee-8aad-57dc-a470-545c98e883eb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year | https://gisweb.casscountynd.gov/arcgis/rest/services/OpenData/OpenData/FeatureServer/7/query?where=GISPIN%3D%2775000000120020%27&outFields=OBJECTID,GISPIN,DASHPIN,Name,PropertyAddress,ACRES,Section,LandCity,LandSt,LandZip&returnGeometry=true&outSR=4326&f=pjson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-847f0ddc67e6e40ce38a/#project-12407b2e-a44d-5c8d-aa62-c7b64045e20f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/12407b2e-a44d-5c8d-aa62-c7b64045e20f.json
126f2c37-cadc-5f20-9e3c-e544d70b5c37 | imported:semiconductor-atlas:openai-stargate-shackelford-county | vcc-site-f3c14c6227b2ae418664 | imported:semiconductor-atlas:openai-stargate-shackelford-county | Vantage Frontier campus (Stargate Shackelford County) | United States | US | 32.7089 | -99.3308 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Shackelford County centroid from OpenStreetMap Nominatim. Texas TDLR filings give a site address on Private Road 1604 with an Abilene mailing address in Shackelford County, but the road was not found in OpenStreetMap. Epoch AI places the campus just across the county line from the Abilene site, so the true site is likely west of this point. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | c23b8163-4dfb-5179-bdc2-bf2c0f07c255 | under_construction | 2026-09-08 | 35 | authoritative_physical_status_update | 552c0872-7358-5078-8f5f-d56f0832b2ba | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c23b8163-4dfb-5179-bdc2-bf2c0f07c255","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"04a7d918-5856-59fd-bbaf-8712a56bbc52","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"6dc4768f-ff85-5410-aa54-51246dfee8a3","notes":"TDLR filings list building-level Vantage LLCs (for example Vantage Data Centers TX301, LLC) as owners.","party":"Vantage Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"1a242c9b-8fb0-5db5-a662-bf137da65f36","notes":"TDLR filings list building-level Vantage LLCs (for example Vantage Data Centers TX301, LLC) as owners.","party":"Vantage Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"15cc2b08-69b2-5325-9550-89f870c78575","notes":"Grouped with the Stargate sites being developed by Oracle; analysts Cleanview and Epoch AI, not company disclosures, name Oracle as cloud operator and owner of the AI hardware. TDLR filings show no tenant assigned.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"04a7d918-5856-59fd-bbaf-8712a56bbc52","notes":"Grouped with the Stargate sites being developed by Oracle; analysts Cleanview and Epoch AI, not company disclosures, name Oracle as cloud operator and owner of the AI hardware. TDLR filings show no tenant assigned.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"e9309672-7fde-51a5-8306-f9e1aec7ed06","notes":"Grouped with the Stargate sites being developed by Oracle; analysts Cleanview and Epoch AI, not company disclosures, name Oracle as cloud operator and owner of the AI hardware. TDLR filings show no tenant assigned.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"15cc2b08-69b2-5325-9550-89f870c78575","notes":"End user through Oracle under the Stargate program.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"e9309672-7fde-51a5-8306-f9e1aec7ed06","notes":"End user through Oracle under the Stargate program.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-shackelford-county"},{"evidence_id":"e9309672-7fde-51a5-8306-f9e1aec7ed06","notes":"Analyst Cleanview, citing an Oracle fact sheet, describes VoltaGrid as developer and operator of the on-site gas microgrid; not confirmed in a company source opened here.","party":"VoltaGrid","relationship_scope":"unknown","role":"power_supplier","source_record_id":"openai-stargate-shackelford-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Vantage Data Centers |  |  | OpenAI; Oracle |  | https://www.oracle.com/data-centers/ | https://rebusinessonline.com/vantage-data-centers-to-invest-25b-for-mega-campus-in-shackleford-county-texas/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Vantage Frontier campus (Stargate Shackelford County) as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"openai-stargate-shackelford-county"},"record":{"aliases":["Frontier","Project Frontier","Stargate Frontier","Vantage DC Abilene - TX3"],"id":"openai-stargate-shackelford-county","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Shackelford County","country":"US","lat":32.7089,"lon":-99.3308,"note":"Shackelford County centroid from OpenStreetMap Nominatim. Texas TDLR filings give a site address on Private Road 1604 with an Abilene mailing address in Shackelford County, but the road was not found in OpenStreetMap. Epoch AI places the campus just across the county line from the Abilene site, so the true site is likely west of this point.","precision":"admin2","source_ids":["s1","s4","s5","s8"]},"metrics":[{"applies_to":"campus","as_of":"2025-08-19","basis":"planned","metric":"power_capacity","note":"Trade press gives 1.4 GW and Vantage's locations page lists 1,400 MW total, without saying whether this is IT or facility power.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s6"],"unit":"MW","value":1400},{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"power_capacity","note":"Analyst characterization, not a company disclosure: Cleanview calls 1.4 GW critical IT capacity and Epoch AI says Vantage reports it as IT power, while Vantage's own locations page labels the figure total.","power_scope":"it_load","qualifier":"exact","source_ids":["s7","s8"],"unit":"MW","value":1400},{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"power_capacity","note":"Analyst estimate, not a company disclosure: Epoch AI's projection of total facility power, derived from the reported IT load.","power_scope":"facility","qualifier":"approximately","source_ids":["s8"],"unit":"MW","value":2000},{"applies_to":"campus","as_of":"2026-04","basis":"permitted","metric":"power_capacity","note":"Analyst report, not a company disclosure: gross capacity of the planned Jenbacher engine fleet per a state air permit filing summarized by Cleanview.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s7"],"unit":"MW","value":2580},{"applies_to":"campus","as_of":"2025-08-19","basis":"announced","metric":"investment","note":"Reported as $25 billion in August 2025; later trade coverage describes it as more than $25 billion.","qualifier":"approximately","source_ids":["s1","s3"],"unit":"USD","value":25000000000},{"applies_to":"phase","as_of":"2026-06-29","basis":"reported","metric":"investment","phase_label":"Building TX301 (TDLR estimated cost)","qualifier":"exact","source_ids":["s4"],"unit":"USD","value":950000000},{"applies_to":"phase","as_of":"2026-06-30","basis":"reported","metric":"investment","phase_label":"Building TX310 (TDLR estimated cost)","qualifier":"exact","source_ids":["s5"],"unit":"USD","value":945000000},{"applies_to":"campus","as_of":"2025-08-19","basis":"planned","metric":"land_area","qualifier":"approximately","source_ids":["s1","s3"],"unit":"acres","value":1200},{"applies_to":"campus","as_of":"2025-08-19","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s3"],"unit":"count","value":10},{"applies_to":"campus","as_of":"2025-08-19","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s1","s3"],"unit":"sq_ft","value":3700000}],"milestones":[{"date":"2025-08-19","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-09-23","event":"other","kind":"actual","note":"Named as one of three new Stargate sites under the OpenAI and Oracle agreement.","source_ids":["s2"]},{"date":"2025","event":"construction_started","kind":"actual","note":"August 2025 trade coverage said construction had already begun; analyst Cleanview dates land clearing to September 2025 and a groundbreaking to December 2025, when trade press also reported Vantage had broken ground.","source_ids":["s1","s3","s7"]},{"date":"2026-H2","event":"first_operational","kind":"planned","note":"Target for the first building to be delivered and enter service.","source_ids":["s1","s3"]},{"date":"2027-08-11","event":"other","kind":"planned","note":"Completion date listed in the TDLR registration for building TX301, later than the company's second-half 2026 target for the first building.","source_ids":["s4"]},{"date":"2028","event":"fully_operational","kind":"planned","note":"Trade press reports a 2028 completion; analyst Epoch AI separately projects Q4 2028.","source_ids":["s3","s8"]}],"name":"Vantage Frontier campus (Stargate Shackelford County)","notes":"TDLR registrations list planned start and completion dates per building and do not by themselves confirm progress, so status rests on April 2026 analyst imagery reviews: Cleanview reported vertical construction on five buildings and Epoch AI reported roofing on the first. These are analyst assessments, not company disclosures. No source found confirms the first building has been delivered as of October 2026.","parties":[{"name":"Vantage Data Centers","role":"developer","source_ids":["s1","s3"]},{"name":"Vantage Data Centers","note":"TDLR filings list building-level Vantage LLCs (for example Vantage Data Centers TX301, LLC) as owners.","role":"owner","source_ids":["s4","s5"]},{"name":"Oracle","note":"Grouped with the Stargate sites being developed by Oracle; analysts Cleanview and Epoch AI, not company disclosures, name Oracle as cloud operator and owner of the AI hardware. TDLR filings show no tenant assigned.","role":"tenant","source_ids":["s2","s3","s7"]},{"name":"OpenAI","note":"End user through Oracle under the Stargate program.","role":"tenant","source_ids":["s2","s7"]},{"name":"VoltaGrid","note":"Analyst Cleanview, citing an Oracle fact sheet, describes VoltaGrid as developer and operator of the on-site gas microgrid; not confirmed in a company source opened here.","role":"power_supplier","source_ids":["s7"]}],"power_sources":[{"description":"Off-grid, behind-the-meter gas microgrid of Jenbacher reciprocating engines in ten power blocks, developed and operated by VoltaGrid, with no public plans to connect to the grid, per analysts Cleanview and Epoch AI.","source_ids":["s7","s8"],"type":"natural_gas_onsite"},{"description":"Diesel engines provide black-start capability for the microgrid, according to the air permit filing summarized by analyst Cleanview.","source_ids":["s7"],"type":"diesel_backup"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250819163658/https://rebusinessonline.com/vantage-data-centers-to-invest-25b-for-mega-campus-in-shackleford-county-texas/","id":"s1","published":"2025-08-19","publisher":"REBusinessOnline","title":"Vantage Data Centers to Invest $25B for Mega-Campus in Shackelford County, Texas","type":"trade_press","url":"https://rebusinessonline.com/vantage-data-centers-to-invest-25b-for-mega-campus-in-shackleford-county-texas/"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-24","publisher":"SoftBank Group Corp.","title":"OpenAI, Oracle, and SoftBank expand Stargate with five new AI data center sites","type":"company","url":"https://group.softbank/en/news/press/20250924"},{"accessed":"2026-10-09","id":"s3","published":"2025-12-16","publisher":"W.Media","title":"Vantage Data Centers breaks ground on data center campus in Texas","type":"trade_press","url":"https://w.media/vantage-data-centers-breaks-ground-on-data-center-campus-in-texas/"},{"accessed":"2026-10-09","id":"s4","published":"2026-06-29","publisher":"Texas Department of Licensing and Regulation","title":"TABS2026024068: Vantage DC Abilene - TX3 - Project Frontier, building TX301","type":"regulatory_filing","url":"https://www.tdlr.texas.gov/TABS/Search/Print/TABS2026024068"},{"accessed":"2026-10-09","id":"s5","published":"2026-06-30","publisher":"Texas Department of Licensing and Regulation","title":"TABS2026024112: Vantage DC Abilene - TX3 - Project Frontier, building TX310","type":"regulatory_filing","url":"https://www.tdlr.texas.gov/TABS/Search/Project/TABS2026024112"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Vantage Data Centers","title":"Data Center Locations - North America","type":"company","url":"https://vantage-dc.com/data-center-locations/north-america/"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Cleanview","title":"Behind-the-meter data centers: Stargate Frontier","type":"analyst","url":"https://cleanview.co/reports/behind-the-meter-data-centers/full-report/stargate-frontier"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260517184326/https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand","id":"s8","published":"2026-04-17","publisher":"Epoch AI","title":"OpenAI Stargate: where the US sites stand","type":"analyst","url":"https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand"}],"status":"under_construction","status_as_of":"2026-04-17","status_source_ids":["s7","s8"],"summary":"Vantage Data Centers is building Frontier, a 1,200-acre campus of ten single-story data centers in Shackelford County, Texas, near Abilene. It is planned at 1.4 GW and roughly $25 billion. In September 2025 it was named one of the new Stargate sites under the OpenAI and Oracle agreement. Analysts report power will come from an off-grid natural gas microgrid built and run by VoltaGrid. A groundbreaking was reported in December 2025, and state building registrations filed in mid-2026 list building start dates in 2026 and completions in 2027. Vantage targeted the first building for the second half of 2026, and trade press reports campus completion in 2028.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c23b8163-4dfb-5179-bdc2-bf2c0f07c255","s2":"15cc2b08-69b2-5325-9550-89f870c78575","s3":"04a7d918-5856-59fd-bbaf-8712a56bbc52","s4":"6dc4768f-ff85-5410-aa54-51246dfee8a3","s5":"1a242c9b-8fb0-5db5-a662-bf137da65f36","s6":"f76b051f-9299-5ab3-a61a-26b6e295144f","s7":"e9309672-7fde-51a5-8306-f9e1aec7ed06","s8":"7015a68d-e811-542d-97ca-5630698f9bef"},"source_file":"datacenters/projects/openai-stargate-shackelford-county.json","source_record_id":"openai-stargate-shackelford-county","source_record_sha256":"d7f00a3af4692eb8b87a8fe8ff934e44ef3d783701c67872ad62cb1f21703743","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"130c9be9748b683d69c292d35b59ff95cfc5d1d56c2efa537f540f59faefa4c9"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f3c14c6227b2ae418664/#project-126f2c37-cadc-5f20-9e3c-e544d70b5c37 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/126f2c37-cadc-5f20-9e3c-e544d70b5c37.json
1369aebb-7496-56a6-9260-159cd3a37283 | imported:semiconductor-atlas:meta-talavera-de-la-reina | vcc-site-2972c6d36048ca1770e2 | imported:semiconductor-atlas:meta-talavera-de-la-reina | Meta Talavera de la Reina data center campus | Spain | ES | 39.9583 | -4.8328 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid from the Talavera de la Reina Wikipedia article. Sources place the campus in the second phase of the Torrehierro industrial area, about 12 km from the town centre, but give no coordinates, so the site is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 043bbd43-bda2-54d9-97f7-697c718363a4 | announced | 2026-08-28 | 46 | imported_documented_status | 043bbd43-bda2-54d9-97f7-697c718363a4 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"043bbd43-bda2-54d9-97f7-697c718363a4","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"4edaf2d9-050a-59ab-920f-d5d83426a7f4","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"043bbd43-bda2-54d9-97f7-697c718363a4","notes":"Bought the land and is described as building its own data center.","party":"Meta Platforms","relationship_scope":"unknown","role":"owner","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"4edaf2d9-050a-59ab-920f-d5d83426a7f4","notes":"Bought the land and is described as building its own data center.","party":"Meta Platforms","relationship_scope":"unknown","role":"owner","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"4edaf2d9-050a-59ab-920f-d5d83426a7f4","notes":"State land agency that sold the Torrehierro land to Meta.","party":"Sepes (Entidad Pública Empresarial de Suelo)","relationship_scope":"unknown","role":"government","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"043bbd43-bda2-54d9-97f7-697c718363a4","notes":"Regional government that approved the project as a plan of singular interest and authorised the reparcelling.","party":"Junta de Comunidades de Castilla-La Mancha","relationship_scope":"unknown","role":"government","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"1861a22f-c317-598a-bf68-77573715e3d0","notes":"Regional government that approved the project as a plan of singular interest and authorised the reparcelling.","party":"Junta de Comunidades de Castilla-La Mancha","relationship_scope":"unknown","role":"government","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"043bbd43-bda2-54d9-97f7-697c718363a4","notes":"Will process the building licences.","party":"Talavera de la Reina City Council","relationship_scope":"unknown","role":"government","source_record_id":"meta-talavera-de-la-reina"},{"evidence_id":"1861a22f-c317-598a-bf68-77573715e3d0","notes":"Will process the building licences.","party":"Talavera de la Reina City Council","relationship_scope":"unknown","role":"government","source_record_id":"meta-talavera-de-la-reina"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Meta Platforms |  |  |  |  | https://www.iagua.es/noticias/redaccion-iagua/meta-ultima-en-talavera-un-centro-de-datos-de-1-000-me-que-se-abastecera-de-agua-del-tajo-por-la-red-municipal | https://www.iagua.es/noticias/redaccion-iagua/meta-ultima-en-talavera-un-centro-de-datos-de-1-000-me-que-se-abastecera-de-agua-del-tajo-por-la-red-municipal | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Talavera de la Reina data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-talavera-de-la-reina"},"record":{"aliases":["Meta Torrehierro data center"],"id":"meta-talavera-de-la-reina","last_reviewed":"2026-10-09","location":{"admin1":"Castilla-La Mancha","admin2":"Toledo","country":"ES","lat":39.95833,"locality":"Talavera de la Reina","lon":-4.83278,"note":"Town centroid from the Talavera de la Reina Wikipedia article. Sources place the campus in the second phase of the Torrehierro industrial area, about 12 km from the town centre, but give no coordinates, so the site is not pinpointed.","precision":"locality","source_ids":["s1","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2022","basis":"reported","metric":"investment","note":"Figure from Meta's 2022 announcement as relayed by iAgua; a local opposition leader cited nearly EUR 1 billion in July 2026.","qualifier":"approximately","source_ids":["s1","s2"],"unit":"EUR","value":1000000000},{"applies_to":"campus","as_of":"2026-08-28","basis":"reported","metric":"investment","note":"Estimate in the environmental documentation, of which EUR 685 million is for construction; the mayor cited more than EUR 750 million in July 2026.","qualifier":"approximately","source_ids":["s1","s3"],"unit":"EUR","value":750000000},{"applies_to":"campus","as_of":"2024-12-19","basis":"acquired","metric":"land_area","note":"Bought from Sepes for EUR 20.6 million. iAgua gives 191 hectares in total, of which about 102 hectares are buildable and 50 to 60 hectares are set aside for a river park.","qualifier":"approximately","source_ids":["s3","s1"],"unit":"hectares","value":190},{"applies_to":"campus","as_of":"2024-12-19","basis":"planned","metric":"buildings","note":"Two data center buildings plus administration, logistics and security buildings.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":5},{"applies_to":"campus","as_of":"2026-08-28","basis":"planned","metric":"jobs_permanent","note":"Direct jobs once operating.","qualifier":"approximately","source_ids":["s1","s3"],"unit":"count","value":250},{"applies_to":"campus","as_of":"2024-12-19","basis":"planned","metric":"jobs_construction","qualifier":"more_than","source_ids":["s3"],"unit":"count","value":1000}],"milestones":[{"date":"2022","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024-12-19","event":"site_acquired","kind":"actual","note":"Sale of about 190 hectares by Sepes for EUR 20.6 million signed on 19 December 2024.","source_ids":["s3"]},{"date":"2025-10","event":"other","kind":"actual","note":"The regional government approved the Proyecto de Singular Interés for the data center in late October 2025.","source_ids":["s2"]},{"date":"2026-08","event":"zoning_approved","kind":"actual","note":"Approval of the land reparcelling. In late July 2026 Meta filed its definitive reparcelling proposal and the regional president said it would be authorised within days; by 28 August 2026 iAgua reported the reparcelling approved, allowing building permit applications. The exact approval date was not given.","source_ids":["s1","s2"]},{"date":"2027","event":"construction_started","kind":"planned","note":"In December 2024 works were expected to start in 2027 and last about ten years; starts planned for late 2023 and then 2025 slipped. Later coverage describes four phases through 2036.","source_ids":["s3","s1"]}],"name":"Meta Talavera de la Reina data center campus","notes":"No MW capacity for the campus was found in the sources opened. Investment figures differ: about EUR 1 billion in Meta's 2022 announcement versus EUR 750 million in the environmental documentation. Water figures also differ: the regional government cites about 0.2 cubic hectometres a year, while the environmental approval gives about 504,500 cubic metres a year for the whole site, mostly landscaping, and about 40,600 cubic metres for the data center itself after the move to dry-air cooling.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s3"]},{"name":"Meta Platforms","note":"Bought the land and is described as building its own data center.","role":"owner","source_ids":["s1","s3"]},{"name":"Sepes (Entidad Pública Empresarial de Suelo)","note":"State land agency that sold the Torrehierro land to Meta.","role":"government","source_ids":["s3"]},{"name":"Junta de Comunidades de Castilla-La Mancha","note":"Regional government that approved the project as a plan of singular interest and authorised the reparcelling.","role":"government","source_ids":["s1","s2"]},{"name":"Talavera de la Reina City Council","note":"Will process the building licences.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"Meta has committed to running the campus on 100% renewable energy; the supply arrangement is not described.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-08-28","publisher":"iAgua","title":"Meta ultima en Talavera un centro de datos de 1.000 M€ que se abastecerá de agua del Tajo por la red municipal","type":"trade_press","url":"https://www.iagua.es/noticias/redaccion-iagua/meta-ultima-en-talavera-un-centro-de-datos-de-1-000-me-que-se-abastecera-de-agua-del-tajo-por-la-red-municipal"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-30","publisher":"elDiario.es","title":"Page anuncia la llegada “definitiva” del centro de datos de Meta a Talavera de la Reina","type":"news","url":"https://www.eldiario.es/castilla-la-mancha/provincias/toledo/page-anuncia-llegada-definitiva-centro-datos-meta-talavera-reina_1_13416975.amp.html"},{"accessed":"2026-10-09","id":"s3","published":"2024-12-19","publisher":"El Español (El Digital Castilla-La Mancha)","title":"Meta compra por 20,6 millones el suelo industrial para construir su macrocentro de datos en Talavera de la Reina","type":"news","url":"https://www.elespanol.com/eldigitalcastillalamancha/region/20241219/meta-compra-millones-suelo-industrial-construir-macrocentro-datos-talavera-reina/909909319_0.amp.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260922235227/https://en.wikipedia.org/wiki/Talavera_de_la_Reina","id":"s4","published":null,"publisher":"Wikipedia","title":"Talavera de la Reina","type":"other","url":"https://en.wikipedia.org/wiki/Talavera_de_la_Reina"}],"status":"announced","status_as_of":"2026-08-28","status_source_ids":["s1","s2"],"summary":"Planned Meta data center campus in the Torrehierro industrial area of Talavera de la Reina, Toledo, which would be Meta's first large owned data center in Spain. Meta's 2022 announcement put the investment at about EUR 1 billion; environmental documents later estimated EUR 750 million. Meta bought about 190 hectares from the state land agency Sepes in December 2024. After repeated delays, the regional government approved it as a project of singular interest in October 2025 and authorised the land reparcelling in summer 2026, letting Meta seek building permits. A switch to dry-air cooling cut planned water use. Construction had not been reported as started.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"043bbd43-bda2-54d9-97f7-697c718363a4","s2":"1861a22f-c317-598a-bf68-77573715e3d0","s3":"4edaf2d9-050a-59ab-920f-d5d83426a7f4","s4":"fbcd7b7b-2a73-578b-8c34-09f25b0f4092"},"source_file":"datacenters/projects/meta-talavera-de-la-reina.json","source_record_id":"meta-talavera-de-la-reina","source_record_sha256":"d9ae0a11c63a4d533b2e1fb63d37634e7e84f2e088f00911d1e92b36506c02f5","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"e6e2fdb7e7e6e29fc768be8d0b31773855f532f5b9085086dccaf83ef9b17461"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2972c6d36048ca1770e2/#project-1369aebb-7496-56a6-9260-159cd3a37283 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1369aebb-7496-56a6-9260-159cd3a37283.json
1404f5cd-04ee-57ea-8f73-91992fea0552 | curated:meta-richland-parish-data-center:current-development | vcc-site-33110c77390f92dc4432 | curated:meta-richland-parish-data-center | Meta Richland Parish Current Development | United States | US | 32.5289 | -91.6361 | Point | campus | Use the single exact-name community feature, verify its source object geometry, and emit the unchanged service longitude/latitude in GeoJSON order. | nominatim_exact_named_campus_reference_point | community_named_campus_reference_point | community_source | campus_locator | The returned point lies in the northern component of the named three-component campus relation. It represents the overall operator-described campus, not a particular first building, Phase 2 construction, or Laidley/Evest legal parcel. No survey, exact building centroid, active construction footprint or bounded numerical accuracy is claimed. |  | Community mapper and geocoder provide no bounded horizontal accuracy; coordinate decimal places are not measurement precision. | 0357dcf6-dd2c-51fe-b107-8c9b253f17ec | under_construction | 2026-07-16 | 89 | authoritative_physical_status_update | 3e31f188-1822-59b3-a3ae-ffd7f298725c | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.turnerconstruction.com/insights/expanded-meta-data-center-creates-more-jobs-and-opportunity-in-richland-parish-louisiana | https://nominatim.openstreetmap.org/search?q=Meta%20Richland%20Parish&countrycodes=us&format=jsonv2&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-33110c77390f92dc4432/#project-1404f5cd-04ee-57ea-8f73-91992fea0552 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1404f5cd-04ee-57ea-8f73-91992fea0552.json
14a67880-da37-5f59-a2cf-2322bbf778d7 | curated:digico-syd1-ultimo-campus:current-site-preparation | vcc-site-23e1a428ab99ad167ba5 | curated:digico-syd1-ultimo-campus | DigiCo SYD1 Ultimo Expansion Early Works | Australia | AU | -33.875 | 151.197 | Point | campus | source_geojson_point_without_coordinate_change | nsw_planning_portal_named_project_coordinate | official_project_campus_reference_point | official_source | campus_locator | Exact source three-decimal official project point. This is a coarse campus reference, potentially outside building footprints, not a surveyed point, entrance, work area, parcel or boundary. Do not imply 1m accuracy, add zeros or replace it with a more precise third-party pin. |  | The department publishes no accuracy statement. Decimal resolution is not measured positional accuracy. | acc81d9e-b4ac-5438-962d-2d1c636ffae2 | site_preparation | 2026-08-19 | 55 | authoritative_physical_status_update | 997b12c3-2ee6-5a01-b406-c79cbe4b41ef | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://earningsapi.io/transcripts/shape-australia-corporation-limited_sha_earnings_call_transcript_2026-08-19 | https://www.planningportal.nsw.gov.au/major-projects/projects/digico-syd1-data-centre-expansion?page=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-23e1a428ab99ad167ba5/#project-14a67880-da37-5f59-a2cf-2322bbf778d7 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/14a67880-da37-5f59-a2cf-2322bbf778d7.json
15360f72-acfa-572f-aac9-eb117ae9fc0d | imported:semiconductor-atlas:samca-green-it-aragon-luceni | vcc-site-0d25d33c7b8c51f70ba3 | imported:semiconductor-atlas:samca-green-it-aragon-luceni | Green IT Aragón data center campus (SAMCA), Luceni | Spain | ES | 41.833 | -1.233 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Luceni municipal centroid from its Wikipedia article. The technical annex places all three data centers in Luceni municipality; associated grid and wind works extend into Rueda de Jalón, Plasencia de Jalón and Pedrola. No cited source gives site coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 117a516b-4901-56d6-8322-ad8efe5b2ddd | announced | 2026-10-05 | 8 | imported_documented_status | f33cd16f-df63-59f5-b2d9-9a1cc750757d | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"117a516b-4901-56d6-8322-ad8efe5b2ddd","notes":"Promotes the plan with its subsidiaries Data Center Ribera Alta del Ebro S.L. and Molinos del Ebro S.A.","party":"SAMCA (Sociedad Anónima Minera Catalano-Aragonesa)","relationship_scope":"unknown","role":"developer","source_record_id":"samca-green-it-aragon-luceni"},{"evidence_id":"fe21b4f6-0c6a-585f-bedd-54f3cb9fcc6e","notes":"Promotes the plan with its subsidiaries Data Center Ribera Alta del Ebro S.L. and Molinos del Ebro S.A.","party":"SAMCA (Sociedad Anónima Minera Catalano-Aragonesa)","relationship_scope":"unknown","role":"developer","source_record_id":"samca-green-it-aragon-luceni"},{"evidence_id":"f33cd16f-df63-59f5-b2d9-9a1cc750757d","notes":"Promotes the plan with its subsidiaries Data Center Ribera Alta del Ebro S.L. and Molinos del Ebro S.A.","party":"SAMCA (Sociedad Anónima Minera Catalano-Aragonesa)","relationship_scope":"unknown","role":"developer","source_record_id":"samca-green-it-aragon-luceni"},{"evidence_id":"b63ade20-aecd-5d9a-a43f-895a6c242fea","notes":"Its nearby wind farms, to be renewed and expanded, are to supply renewable power through direct underground lines under a self-consumption arrangement.","party":"SAMCA (Sociedad Anónima Minera Catalano-Aragonesa)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"samca-green-it-aragon-luceni"},{"evidence_id":"fe21b4f6-0c6a-585f-bedd-54f3cb9fcc6e","notes":"Its nearby wind farms, to be renewed and expanded, are to supply renewable power through direct underground lines under a self-consumption arrangement.","party":"SAMCA (Sociedad Anónima Minera Catalano-Aragonesa)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"samca-green-it-aragon-luceni"},{"evidence_id":"fe21b4f6-0c6a-585f-bedd-54f3cb9fcc6e","notes":"Granted grid access permits for the phased capacity.","party":"Red Eléctrica","relationship_scope":"unknown","role":"utility","source_record_id":"samca-green-it-aragon-luceni"},{"evidence_id":"117a516b-4901-56d6-8322-ad8efe5b2ddd","notes":"Declared the project of general interest and gave the regional plan initial approval.","party":"Government of Aragon","relationship_scope":"unknown","role":"government","source_record_id":"samca-green-it-aragon-luceni"},{"evidence_id":"fe21b4f6-0c6a-585f-bedd-54f3cb9fcc6e","notes":"Declared the project of general interest and gave the regional plan initial approval.","party":"Government of Aragon","relationship_scope":"unknown","role":"government","source_record_id":"samca-green-it-aragon-luceni"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html | https://www.aragon.es/-/piga-green-it | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Green IT Aragón data center campus (SAMCA), Luceni as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"samca-green-it-aragon-luceni"},"record":{"aliases":["Green IT Aragón","PIGA Green It Aragón"],"id":"samca-green-it-aragon-luceni","last_reviewed":"2026-10-09","location":{"admin1":"Aragon","admin2":"Zaragoza","country":"ES","lat":41.833,"locality":"Luceni","lon":-1.233,"note":"Luceni municipal centroid from its Wikipedia article. The technical annex places all three data centers in Luceni municipality; associated grid and wind works extend into Rueda de Jalón, Plasencia de Jalón and Pedrola. No cited source gives site coordinates.","precision":"locality","source_ids":["s1","s2","s6"]},"metrics":[{"applies_to":"campus","as_of":"2025-04-28","basis":"planned","metric":"power_capacity","note":"Final-phase capacity under the Red Eléctrica permits described at announcement.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2025-04-28","basis":"permitted","metric":"power_capacity","note":"A second phase could rise to 181 MW.","phase_label":"Phase 1","power_scope":"grid_connection","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":131},{"applies_to":"phase","as_of":"2025-11","basis":"planned","metric":"power_capacity","phase_label":"Each of three identical data center buildings","power_scope":"it_load","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":72},{"applies_to":"phase","as_of":"2025-11","basis":"planned","metric":"power_capacity","note":"Maximum active power each data center would draw from the transmission grid.","phase_label":"Each of three identical data center buildings","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s2"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2025-04-28","basis":"announced","metric":"investment","note":"Includes the renewable generation; El Español says the figure rose from EUR 2,000 million when the renewable supply was added.","qualifier":"exact","source_ids":["s3","s4"],"unit":"EUR","value":2627000000},{"applies_to":"campus","as_of":"2025-11","basis":"planned","metric":"buildings","note":"Named Ribera Alta del Ebro, Ribera Alta del Ebro II and Atalaya del Ebro in the plan documents.","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2025-04-28","basis":"planned","metric":"jobs_construction","note":"Direct and indirect jobs during construction, per the regional government.","qualifier":"up_to","source_ids":["s3"],"unit":"count","value":2300},{"applies_to":"campus","as_of":"2025-04-28","basis":"planned","metric":"jobs_permanent","note":"Direct and indirect jobs during operation, per the regional government.","qualifier":"up_to","source_ids":["s3"],"unit":"count","value":320}],"milestones":[{"date":"2025-04-28","event":"announced","kind":"actual","source_ids":["s3"]},{"date":"2025-04-28","event":"other","kind":"actual","note":"Declared an investment of general interest for Aragon; published in the regional gazette on 26 May 2025.","source_ids":["s1","s3"]},{"date":"2025-11-21","event":"other","kind":"actual","note":"Regional plan filed for processing.","source_ids":["s1"]},{"date":"2025-12-23","event":"other","kind":"actual","note":"Initial approval of the Plan de Interés General de Aragón, after a redrawing of its boundary on 10 December 2025; public information followed.","source_ids":["s1","s5"]},{"date":"2027","event":"construction_started","kind":"planned","note":"In March 2026 construction was planned during 2026; in October 2026 urbanisation was expected by late 2026 or during 2027.","source_ids":["s4","s5"]},{"date":"2028","event":"first_operational","kind":"planned","note":"First phase targeted for 2028; the announcement put start-up and operation between 2026 and 2030.","source_ids":["s5","s3"]}],"name":"Green IT Aragón data center campus (SAMCA), Luceni","notes":"The regional plan page shows a last-updated date of 7 July 2026, used as its published date; the water annex is dated November 2025 on its cover. Per-building figures are recorded separately and not summed. The water annex estimates total campus water use below 460,000 cubic metres a year, mostly for optional evaporative support to air-cooled chillers. No final approval of the regional plan had been reported by early October 2026.","parties":[{"name":"SAMCA (Sociedad Anónima Minera Catalano-Aragonesa)","note":"Promotes the plan with its subsidiaries Data Center Ribera Alta del Ebro S.L. and Molinos del Ebro S.A.","role":"developer","source_ids":["s1","s3","s4"]},{"name":"SAMCA (Sociedad Anónima Minera Catalano-Aragonesa)","note":"Its nearby wind farms, to be renewed and expanded, are to supply renewable power through direct underground lines under a self-consumption arrangement.","role":"power_supplier","source_ids":["s2","s3"]},{"name":"Red Eléctrica","note":"Granted grid access permits for the phased capacity.","role":"utility","source_ids":["s3"]},{"name":"Government of Aragon","note":"Declared the project of general interest and gave the regional plan initial approval.","role":"government","source_ids":["s1","s3"]}],"power_sources":[{"description":"Connections to the transmission grid through 220 kV underground lines from the Jalón PRE, Bayo and Camporroyo substations to a new Ribera Alta del Ebro substation.","source_ids":["s1","s2"],"type":"grid"},{"description":"SAMCA's wind farms in Luceni, Pedrola, Plasencia de Jalón and Rueda de Jalón are to be renewed and expanded to supply the campus through direct underground lines under self-consumption with surplus export.","source_ids":["s2","s3"],"type":"wind"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-07-07","publisher":"Gobierno de Aragón","title":"Plan de Interés General de Aragón Green It Aragón","type":"government","url":"https://www.aragon.es/-/piga-green-it"},{"accessed":"2026-10-09","id":"s2","published":"2025-11","publisher":"Gobierno de Aragón (plan documentation filed by the promoter)","title":"Memoria técnica sobre el consumo de agua del Plan Green IT Aragón (Vol. IV, anexo 18)","type":"regulatory_filing","url":"https://www.aragon.es/documents/d/guest/vol_iv_anx_18_memoria_consumo_agua-1"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260324073925/https://www.eldiario.es/aragon/economia/tres-centros-datos-aragon-samca-anuncia-inversion-2-627-millones-luceni_1_12252656.html","id":"s3","published":"2025-04-28","publisher":"elDiario.es","title":"Otros tres centros de datos en Aragón: Samca anuncia una inversión de 2.627 millones en Luceni","type":"news","url":"https://www.eldiario.es/aragon/economia/tres-centros-datos-aragon-samca-anuncia-inversion-2-627-millones-luceni_1_12252656.html"},{"accessed":"2026-10-09","id":"s4","published":"2026-10-05","publisher":"El Español","title":"Cerca de 6.000 millones invertidos en centros de datos en Aragón esperan en la rampa de salida para las obras","type":"news","url":"https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260527095310/https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html","id":"s5","published":"2026-03-22","publisher":"El Español","title":"Aragón se convierte en la capital de los datos y la nube: el calendario de Amazon, Microsoft y todos los proyectos","type":"news","url":"https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251220030537/https://en.wikipedia.org/wiki/Luceni","id":"s6","published":null,"publisher":"Wikipedia","title":"Luceni","type":"other","url":"https://en.wikipedia.org/wiki/Luceni"}],"status":"announced","status_as_of":"2026-10-05","status_source_ids":["s4","s1"],"summary":"Three-building data center campus planned by the SAMCA group in Luceni, Zaragoza province, paired with renewing and expanding SAMCA's nearby wind farms to supply it. Announced in April 2025 at EUR 2,627 million including the renewable generation. Red Eléctrica has permitted 131 MW for a first phase, which could rise to 181 MW and finally 300 MW. A technical annex describes three identical buildings of 72 MW of IT load, each drawing up to 100 MW from the grid. The regional plan received initial approval in December 2025; in October 2026 site works were expected by late 2026 or in 2027, with the first phase targeted for 2028.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"117a516b-4901-56d6-8322-ad8efe5b2ddd","s2":"b63ade20-aecd-5d9a-a43f-895a6c242fea","s3":"fe21b4f6-0c6a-585f-bedd-54f3cb9fcc6e","s4":"f33cd16f-df63-59f5-b2d9-9a1cc750757d","s5":"fc08af92-398d-50ce-afde-80ee90c94499","s6":"91f9e654-990f-5e6e-b77a-7058226f9609"},"source_file":"datacenters/projects/samca-green-it-aragon-luceni.json","source_record_id":"samca-green-it-aragon-luceni","source_record_sha256":"e8260b20d552deefda45a4ad13f6c0fb3681dc3da63f5e6e3901bc4240b50619","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0e19da99a19f19463b4d36af07c32e4b0861da3cfe5def7c3086482d0dda5a48"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0d25d33c7b8c51f70ba3/#project-15360f72-acfa-572f-aac9-eb117ae9fc0d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/15360f72-acfa-572f-aac9-eb117ae9fc0d.json
15e0ef92-6408-5517-b0d4-a6b8707745f4 | curated:enka-data-solutions-eds-ist-01-tuzla-data-center:initial-build | vcc-site-41e0189f5fc22ef9a733 | curated:enka-data-solutions-eds-ist-01-tuzla-data-center | EDS IST 01 Tuzla Initial Build | Türkiye | TR | 40.8352 | 29.3237 | Point | project | direct_geometry | first_party_facility_page_map_pin_point | first_party_facility_page_reference_point | official_source | project_locator | The source decimal strings are preserved exactly and parsed without coordinate transformation. Their many decimal places do not imply a surveyed reference feature or centimetre-scale horizontal accuracy. |  | The page does not identify a geodetic datum, surveyed reference feature, collection method, or numeric horizontal accuracy. | 959963fd-1d27-5927-a972-8a04fd97727e | under_construction | 2026-06-12 | 123 | authoritative_physical_status_update | 6b7130b5-f5f5-50c8-9689-6b8e348e0015 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-06-12","base":11.0,"confidence":0.99,"evidence_id":"a63792de-87ff-5a78-8a99-e53260b301f1","high":11.0,"low":11.0,"method":"reported","metric":"critical_it_mw","notes":"Project-page IT-load design value only; not current load, gross demand, generation, annual energy, consumption, or PUE.","stage":"design","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.linkedin.com/embed/feed/update/urn:li:activity:7471178062345297920 | https://enkadatasolutions.com/locations/eds-ist-01-tuzla/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-41e0189f5fc22ef9a733/#project-15e0ef92-6408-5517-b0d4-a6b8707745f4 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/15e0ef92-6408-5517-b0d4-a6b8707745f4.json
164033cb-411d-5ffb-ab5d-b04bdecfa1ac | curated:cdc-marsden-park-campus:early-construction | vcc-site-37ddc3b143bf9ea08d1c | curated:cdc-marsden-park-campus | CDC Marsden Park Early Construction | Australia | AU | -33.7237 | 150.8364 | Polygon | facility | capture_replayed_geometry | cross_source_identity_bridge_to_live_osm_named_cdc_marsden_park_campus_polygon | community_mapped_named_cdc_marsden_park_campus_development_polygon | community_mapped | campus_locator | The polygon is a contributor-mapped named development outline and the point is only its deterministic longitude-latitude bounding-box midpoint. Neither is a survey, cadastral, planning, parcel, security, building, phase, or current construction boundary. OSM construction tags are retained solely as source context and never provide the selected project's authoritative lifecycle. |  | OpenStreetMap supplies no survey accuracy, cadastral authority, planning-boundary authority, or numeric horizontal uncertainty for this way. | ce28239d-1c35-5043-9373-97416961a743 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | 56fa3df3-1fe1-50af-80c1-0e2f0f14d610 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"56fa3df3-1fe1-50af-80c1-0e2f0f14d610","party":"CDC Data Centres","relationship_scope":"intended","role":"operator"},{"evidence_id":"242c3019-1f53-551c-a0be-de57b4e4352f","notes":null,"party":"CDC Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"cdc-marsden-park"},{"evidence_id":"adb5e95d-1036-53e3-9d9d-f9b7dd8a942c","notes":null,"party":"CDC Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"cdc-marsden-park"},{"evidence_id":"b578a483-e755-5e2a-a654-0366ac5903ae","notes":null,"party":"CDC Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"cdc-marsden-park"},{"evidence_id":"242c3019-1f53-551c-a0be-de57b4e4352f","notes":null,"party":"CDC Data Centres","relationship_scope":"unknown","role":"owner","source_record_id":"cdc-marsden-park"},{"evidence_id":"242c3019-1f53-551c-a0be-de57b4e4352f","notes":null,"party":"CDC Data Centres","relationship_scope":"unknown","role":"operator","source_record_id":"cdc-marsden-park"},{"evidence_id":"feafa66c-aec7-5021-8dbd-502ace1e0b82","notes":"Assessed and approved the campus as state significant development.","party":"NSW Department of Planning","relationship_scope":"unknown","role":"government","source_record_id":"cdc-marsden-park"},{"evidence_id":"adb5e95d-1036-53e3-9d9d-f9b7dd8a942c","notes":"Assessed and approved the campus as state significant development.","party":"NSW Department of Planning","relationship_scope":"unknown","role":"government","source_record_id":"cdc-marsden-park"}] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | CDC Data Centres | CDC Data Centres |  |  |  | https://cdc.com.au/locations/sydney/ | https://api.openstreetmap.org/api/0.6/way/1336972876/full.json | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same CDC six-building Marsden Park development and early-construction scope. The source suburb centroid does not replace the reviewed campus locator.","source_record_id":"cdc-marsden-park","target_project_stable_key":"curated:cdc-marsden-park-campus:early-construction"},"record":{"aliases":["Marsden Park Data Centre","SSD-70889211"],"id":"cdc-marsden-park","last_reviewed":"2026-10-09","location":{"admin1":"New South Wales","admin2":"City of Blacktown","country":"AU","lat":-33.6892,"locality":"Marsden Park","lon":150.8028,"note":"Sources name the Marsden Park Industrial Precinct without a street address; the point is the Marsden Park suburb coordinate from its Wikipedia article, so it marks the suburb rather than the site.","precision":"locality","source_ids":["s1","s2","s3","s6"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-27","basis":"permitted","metric":"power_capacity","note":"CDC calls this total ICT capacity; the planning portal describes it as power consumption of the data centre. W.Media reports the campus can scale toward 1 GW.","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":504},{"applies_to":"campus","as_of":"2025-11-27","basis":"permitted","metric":"power_capacity","note":"Rating of the on-site substation: 720 MW on the planning portal and 720 MVA in CDC's release.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":720},{"applies_to":"campus","as_of":"2025-11-28","basis":"reported","metric":"investment","note":"Figure given in coverage of the approval; CDC's own release gives no amount.","qualifier":"exact","source_ids":["s3","s4"],"unit":"AUD","value":3100000000},{"applies_to":"campus","as_of":"2025-11-27","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2024-10-25","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":20.1},{"applies_to":"campus","as_of":"2025-12-04","basis":"planned","metric":"jobs_construction","note":"Figure reported by Information Age; CDC's release instead cites more than 10,000 jobs over the life of construction.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":200},{"applies_to":"campus","as_of":"2025-12-04","basis":"planned","metric":"jobs_permanent","qualifier":"exact","source_ids":["s4"],"unit":"count","value":265}],"milestones":[{"date":"2024-10-25","event":"construction_started","kind":"actual","note":"Ceremonial sod-turning, with minor earthworks and site preparation already under way.","source_ids":["s1"]},{"date":"2025-11-27","event":"permit_approved","kind":"actual","note":"Approved as state significant development SSD-70889211; Blacktown City Council had objected on engineering and planning grounds.","source_ids":["s2","s3"]}],"name":"CDC Data Centres Marsden Park campus","notes":"Status rests on CDC's undated Sydney locations page, which described Marsden Park as in the early stages of construction when accessed on 2026-10-09, so status_as_of is the access date. An earlier DatacenterDynamics report on the filing gave a lower investment figure, but that page could not be opened. Wikipedia is cited only for the suburb coordinate.","parties":[{"name":"CDC Data Centres","role":"developer","source_ids":["s1","s3","s4"]},{"name":"CDC Data Centres","role":"owner","source_ids":["s1"]},{"name":"CDC Data Centres","role":"operator","source_ids":["s1"]},{"name":"NSW Department of Planning","note":"Assessed and approved the campus as state significant development.","role":"government","source_ids":["s2","s3"]}],"power_sources":[{"description":"Dedicated on-site substation of about 720 MVA.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-10-25","publisher":"CDC Data Centres","title":"CDC Data Centres Breaks Ground on New State-of-the-Art Data Centre Development in Marsden Park Industrial Precinct","type":"company","url":"https://cdc.com/resources/news/cdc-data-centres-breaks-ground-on-new-state-of-the-art-data-centre-development-in-marsden-park-industrial-precinct/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260723073408/https://www.planningportal.nsw.gov.au/major-projects/projects/marsden-park-data-centre","id":"s2","published":null,"publisher":"NSW Planning Portal","title":"Marsden Park Data Centre (SSD-70889211)","type":"government","url":"https://www.planningportal.nsw.gov.au/major-projects/projects/marsden-park-data-centre"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-28","publisher":"W.Media","title":"NSW govt approves CDC's 504 MW campus in Sydney","type":"trade_press","url":"https://w.media/nsw-govt-approves-cdcs-504-mw-campus-in-sydney/"},{"accessed":"2026-10-09","id":"s4","published":"2025-12-04","publisher":"Startup Daily (Information Age)","title":"NSW gives the nod to a $3 billion CDC data centre in Western Sydney","type":"news","url":"https://www.startupdaily.net/?p=131381"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"CDC Data Centres","title":"Sydney and regional NSW locations","type":"company","url":"https://cdc.com/locations/sydney-and-regional-nsw/"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Marsden Park, New South Wales","type":"other","url":"https://en.wikipedia.org/wiki/Marsden_Park,_New_South_Wales"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s5"],"summary":"CDC Data Centres is building a campus of six four-storey data center buildings on about 20 hectares in the Marsden Park Industrial Precinct in Sydney's north-west, within the City of Blacktown. CDC turned the first sod in October 2024 and plans 504 MW of ICT capacity, scalable toward 1 GW, with a dedicated substation of about 720 MVA. The NSW government approved it as state significant development on 27 November 2025 despite objections from Blacktown City Council; press coverage put the investment at A$3.1 billion. CDC describes the campus as in the early stages of construction.","workloads":["cloud","hpc","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"242c3019-1f53-551c-a0be-de57b4e4352f","s2":"feafa66c-aec7-5021-8dbd-502ace1e0b82","s3":"adb5e95d-1036-53e3-9d9d-f9b7dd8a942c","s4":"b578a483-e755-5e2a-a654-0366ac5903ae","s5":"b011830f-6376-5eb1-9399-1bb70b7f8d81","s6":"b51b6802-aaa4-5be4-91fc-72d370f76b85"},"source_file":"datacenters/projects/cdc-marsden-park.json","source_record_id":"cdc-marsden-park","source_record_sha256":"7f5328a6e8a50cf869cf98075451fd843a9f85bd3c5f6c8f2ec96b1a664b20b4","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"9dd6eb6e5ee39f6394d44a010c9191d933d4d79390405618aacb0ddebb7f150f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-37ddc3b143bf9ea08d1c/#project-164033cb-411d-5ffb-ab5d-b04bdecfa1ac | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/164033cb-411d-5ffb-ab5d-b04bdecfa1ac.json
1861d9fb-3980-5a16-baa1-c32762e244c1 | curated:microsoft-alviso-san-jose-datacenter-campus:phase-2-greenfield-development | vcc-site-0ca1d5c08f1eb1cf1cf3 | curated:microsoft-alviso-san-jose-datacenter-campus | Microsoft Alviso Phase 2 Greenfield Development | United States | US | 37.4252 | -121.9287 | Point | project | official_address_point | city_of_san_jose_address_point_cross_identified_by_named_development_record | official_city_address_point_cross_identified_to_named_project | official_source | project_locator | Official City of San Jose address point for 1657 Alviso-Milpitas Road, cross-identified to Microsoft and CP23-016 by the City's named Major Private Development record. The point locates the named project and shared parent campus only; the separate development polygon is rejected. |  | The City address record labels the feature Placed on Map and supplies no bounded numeric horizontal-accuracy value; coordinate digits do not establish survey accuracy, containment, an entrance, or a footprint. | 5b7da16c-3a43-5e42-97ad-816ae894e900 | under_construction | 2026-06-10 | 125 | authoritative_construction_start | 508e32e2-ef98-5db2-b6b1-50103f924aaf | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.hitt.com/news-hub/hitt-breaks-ground-microsoft-alviso-datacenter/ | https://geo.sanjoseca.gov/server/rest/services/OPN/OPN_OpenDataService/MapServer/36 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ca1d5c08f1eb1cf1cf3/#project-1861d9fb-3980-5a16-baa1-c32762e244c1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1861d9fb-3980-5a16-baa1-c32762e244c1.json
18844ee0-7ce9-5a0b-9a50-1d9ed0769266 | imported:semiconductor-atlas:vermaland-la-osa-pinal-county | vcc-site-2890b11431bd73672216 | imported:semiconductor-atlas:vermaland-la-osa-pinal-county | La Osa Energy Center (Vermaland), Pinal County | United States | US | 32.7636 | -111.6 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of Eloy (s6). Sources place the site south of Eloy along the Greene Canal (s1), off Picacho Highway (s2) and about 12 miles outside the city (s4), so the parcel lies some distance from this point. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 792842fe-d879-503d-950c-3572e6314e9d | cancelled | 2026-08-26 | 48 | imported_documented_status | 18d75187-fb81-5222-af61-f0ad9e97c3fb | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"792842fe-d879-503d-950c-3572e6314e9d","notes":"Phoenix-based land developer; no data center company was officially tied to the project.","party":"Vermaland","relationship_scope":"unknown","role":"developer","source_record_id":"vermaland-la-osa-pinal-county"},{"evidence_id":"e68caa68-4391-5e17-8496-8e5de35a7236","notes":"Phoenix-based land developer; no data center company was officially tied to the project.","party":"Vermaland","relationship_scope":"unknown","role":"developer","source_record_id":"vermaland-la-osa-pinal-county"},{"evidence_id":"fd5c023b-9857-5497-a4ac-e0a976769197","notes":"Phoenix-based land developer; no data center company was officially tied to the project.","party":"Vermaland","relationship_scope":"unknown","role":"developer","source_record_id":"vermaland-la-osa-pinal-county"},{"evidence_id":"f552ffca-f0d2-589c-b93a-8652c54b0180","notes":"Phoenix-based land developer; no data center company was officially tied to the project.","party":"Vermaland","relationship_scope":"unknown","role":"developer","source_record_id":"vermaland-la-osa-pinal-county"},{"evidence_id":"18d75187-fb81-5222-af61-f0ad9e97c3fb","notes":"Phoenix-based land developer; no data center company was officially tied to the project.","party":"Vermaland","relationship_scope":"unknown","role":"developer","source_record_id":"vermaland-la-osa-pinal-county"},{"evidence_id":"fd5c023b-9857-5497-a4ac-e0a976769197","notes":"Rejected the rezoning and site plan by a 4-1 vote.","party":"Pinal County Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"vermaland-la-osa-pinal-county"},{"evidence_id":"18d75187-fb81-5222-af61-f0ad9e97c3fb","notes":"Rejected the rezoning and site plan by a 4-1 vote.","party":"Pinal County Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"vermaland-la-osa-pinal-county"},{"evidence_id":"f552ffca-f0d2-589c-b93a-8652c54b0180","notes":"Reported as planning to serve the project and named as the body that would enforce Vermaland's pledge to pay the full cost of generating and delivering its energy.","party":"Central Arizona Irrigation and Drainage District","relationship_scope":"unknown","role":"utility","source_record_id":"vermaland-la-osa-pinal-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.kjzz.org/politics/2026-08-26/pinal-county-rejects-massive-la-osa-data-center-residents-want-more-rules-for-future-projects | https://baxtel.com/news/vermaland-plans-33bn-data-center-in-arizona | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve La Osa Energy Center (Vermaland), Pinal County as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"vermaland-la-osa-pinal-county"},"record":{"aliases":["La Osa","La Osa Project","La Osa data center"],"id":"vermaland-la-osa-pinal-county","last_reviewed":"2026-10-09","location":{"admin1":"Arizona","admin2":"Pinal County","country":"US","lat":32.7636,"locality":"Eloy","lon":-111.6,"note":"Coordinates are the Wikipedia centroid of Eloy (s6). Sources place the site south of Eloy along the Greene Canal (s1), off Picacho Highway (s2) and about 12 miles outside the city (s4), so the parcel lies some distance from this point.","precision":"locality","source_ids":["s1","s2","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-21","basis":"planned","metric":"power_capacity","note":"Original plan before the May 2026 scale-back.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2"],"unit":"MW","value":3000},{"applies_to":"campus","as_of":"2026-08-26","basis":"planned","metric":"power_capacity","note":"Demand cap in the scaled-back proposal that the county rejected.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s3","s4","s5"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-08-26","basis":"planned","metric":"power_capacity","note":"On-site gas plant in the final proposal; the developer said it had secured the gas supply and turbines, and proposed meeting the other 500 MW from nearby solar or the Palo Verde nuclear plant.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s5"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-04-21","basis":"reported","metric":"investment","note":"Estimated cost of the original 3 GW plan; no figure was reported for the scaled-back version.","qualifier":"up_to","source_ids":["s1","s2"],"unit":"USD","value":33000000000},{"applies_to":"campus","as_of":"2026-05-28","basis":"reported","metric":"land_area","note":"KJZZ's August 2026 preview describes the rezoning as covering more than 3,000 acres, about one-third of which would have stayed open space; an April 2026 report gives 3,000 acres.","qualifier":"approximately","source_ids":["s1","s3","s4"],"unit":"acres","value":3300},{"applies_to":"campus","as_of":"2026-05-28","basis":"planned","metric":"buildings","note":"Original plan.","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":59},{"applies_to":"campus","as_of":"2026-08-26","basis":"planned","metric":"buildings","note":"Final, scaled-back proposal.","qualifier":"up_to","source_ids":["s3","s4","s5"],"unit":"count","value":11}],"milestones":[{"date":"2025-07","event":"announced","kind":"actual","note":"Baxtel's August 2025 report relays azcentral (Arizona Republic) coverage dated 30 July 2025; the rezoning application had been filed about four months earlier.","source_ids":["s1"]},{"date":"2025-07-17","event":"other","kind":"actual","note":"County planning and zoning commission held a non-voting informational session.","source_ids":["s1"]},{"date":"2026-05","event":"other","kind":"actual","note":"At a supervisors' hearing the developer offered to shrink the project by about 80% and won a continuance to August.","source_ids":["s3"]},{"date":"2026-08-26","event":"cancelled","kind":"actual","note":"Board of Supervisors voted 4-1 to reject the rezoning and site plan requests.","source_ids":["s5"]}],"name":"La Osa Energy Center (Vermaland), Pinal County","notes":"Recorded as cancelled because the county rejected the rezoning the project needed; no developer statement on an appeal or a new application was found. Before the board vote, the county planning and zoning commission had voted 7-2 in favour of the rezoning, per an April 2026 report. The water cap, noise studies and energy cost commitments were offered by Vermaland, not imposed by the county.","parties":[{"name":"Vermaland","note":"Phoenix-based land developer; no data center company was officially tied to the project.","role":"developer","source_ids":["s1","s2","s3","s4","s5"]},{"name":"Pinal County Board of Supervisors","note":"Rejected the rezoning and site plan by a 4-1 vote.","role":"government","source_ids":["s3","s5"]},{"name":"Central Arizona Irrigation and Drainage District","note":"Reported as planning to serve the project and named as the body that would enforce Vermaland's pledge to pay the full cost of generating and delivering its energy.","role":"utility","source_ids":["s4"]}],"power_sources":[{"description":"Two on-site gas-fired plants in the original plan; a single 500 MW gas plant in the final proposal.","source_ids":["s2","s5"],"type":"natural_gas_onsite"},{"description":"Utility-scale battery storage, which the developer offered to decommission if unused for 24 months.","source_ids":["s2","s4","s5"],"type":"battery_storage"},{"description":"The 2025 plan relied on upgrading Western Area Power Administration transmission lines; the final plan proposed sourcing half the 1 GW load from nearby solar or Palo Verde power.","source_ids":["s1","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-08-04","publisher":"Baxtel","title":"Vermaland Plans $33bn Data Center in Arizona","type":"trade_press","url":"https://baxtel.com/news/vermaland-plans-33bn-data-center-in-arizona"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-21","publisher":"Construction Reporter","title":"Massive Proposed Southern Arizona Data Center Business Park Moving Forward","type":"trade_press","url":"https://constructionreporter.com/massive-proposed-southern-arizona-data-center-business-park-moving-forward/"},{"accessed":"2026-10-09","id":"s3","published":"2026-05-28","publisher":"KJZZ","title":"Largest proposed data center in Arizona to be scaled back 80% after opposition","type":"news","url":"https://www.kjzz.org/fronteras-desk/2026-05-28/largest-proposed-data-center-in-arizona-to-be-scaled-back-80-after-opposition"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-25","publisher":"KJZZ","title":"Pinal County will vote on La Osa, which could become one of Arizona's largest data center projects","type":"news","url":"https://www.kjzz.org/politics/2026-08-25/pinal-county-will-vote-on-la-osa-which-could-become-one-of-arizonas-largest-data-center-projects"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260908162746/https://www.kjzz.org/politics/2026-08-26/pinal-county-rejects-massive-la-osa-data-center-residents-want-more-rules-for-future-projects","id":"s5","published":"2026-08-26","publisher":"KJZZ","title":"Pinal County rejects massive La Osa data center. Residents want more rules for future projects","type":"news","url":"https://www.kjzz.org/politics/2026-08-26/pinal-county-rejects-massive-la-osa-data-center-residents-want-more-rules-for-future-projects"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260713151042/https://en.wikipedia.org/wiki/Eloy,_Arizona","id":"s6","published":null,"publisher":"Wikipedia","title":"Eloy, Arizona","type":"other","url":"https://en.wikipedia.org/wiki/Eloy,_Arizona"}],"status":"cancelled","status_as_of":"2026-08-26","status_source_ids":["s5"],"summary":"Proposed AI data center and energy campus on more than 3,000 acres of rural land outside Eloy in Pinal County, Arizona, from land developer Vermaland. First reported in mid-2025 as a USD 33 billion plan for up to 3 GW, it called for nearly 60 data center buildings with on-site gas plants and battery storage. After strong local opposition, Vermaland offered in May 2026 to cut it by about 80% to 11 buildings and 1 GW of demand; the final proposal included a 500 MW gas plant, batteries and a 600 acre-foot annual freshwater cap. On 26 August 2026 the Pinal County Board of Supervisors rejected the rezoning and site plan 4-1.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"792842fe-d879-503d-950c-3572e6314e9d","s2":"e68caa68-4391-5e17-8496-8e5de35a7236","s3":"fd5c023b-9857-5497-a4ac-e0a976769197","s4":"f552ffca-f0d2-589c-b93a-8652c54b0180","s5":"18d75187-fb81-5222-af61-f0ad9e97c3fb","s6":"8887b60b-b336-5bc2-9ef7-176d5b307b28"},"source_file":"datacenters/projects/vermaland-la-osa-pinal-county.json","source_record_id":"vermaland-la-osa-pinal-county","source_record_sha256":"5fb12121ee713957a5e0413a435f1746010f7893d018b06a01b1c498a8d8f9b6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"ae70b28f7d056bde8ee79fdd5af396a435be31e1fb371df47be0e98399367463"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2890b11431bd73672216/#project-18844ee0-7ce9-5a0b-9a50-1d9ed0769266 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/18844ee0-7ce9-5a0b-9a50-1d9ed0769266.json
1b7d1694-1f94-5ac5-a39d-ef81696ed589 | imported:semiconductor-atlas:google-stillwater-oklahoma | vcc-site-d92255df1f2246ac16d5 | imported:semiconductor-atlas:google-stillwater-oklahoma | Google Stillwater data center campus | United States | US | 36.116 | -97.059 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Stillwater city coordinates from its Wikipedia page. Sources place the site at the intersection of Perkins and Richmond Roads but give no parcel coordinates, and no geocoder was used. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | acd64cf6-e494-594b-ab09-08d50e7f3392 | announced | 2026-10-09 | 4 | imported_documented_status | 84a06e7d-fd45-57f7-8046-11fd2a7b47bc | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"acd64cf6-e494-594b-ab09-08d50e7f3392","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-stillwater-oklahoma"},{"evidence_id":"732dfda4-ac7d-586c-baab-708a24898add","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-stillwater-oklahoma"},{"evidence_id":"e02beec7-6c88-5f0d-b613-b81fcedce639","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-stillwater-oklahoma"},{"evidence_id":"acd64cf6-e494-594b-ab09-08d50e7f3392","notes":"Acquired the land in 2025.","party":"Google","relationship_scope":"unknown","role":"owner","source_record_id":"google-stillwater-oklahoma"},{"evidence_id":"e02beec7-6c88-5f0d-b613-b81fcedce639","notes":"Acquired the land in 2025.","party":"Google","relationship_scope":"unknown","role":"owner","source_record_id":"google-stillwater-oklahoma"},{"evidence_id":"acd64cf6-e494-594b-ab09-08d50e7f3392","notes":"Announced Google as the buyer; Google is to make payments in lieu of property taxes to the city rather than paying the taxes initially.","party":"City of Stillwater","relationship_scope":"unknown","role":"government","source_record_id":"google-stillwater-oklahoma"},{"evidence_id":"732dfda4-ac7d-586c-baab-708a24898add","notes":"Announced Google as the buyer; Google is to make payments in lieu of property taxes to the city rather than paying the taxes initially.","party":"City of Stillwater","relationship_scope":"unknown","role":"government","source_record_id":"google-stillwater-oklahoma"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Google |  |  |  |  | https://baxtel.com/data-center/google-stillwater-id4 | https://stillwaterok.gov/CivicAlerts.asp?AID=332 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Google Stillwater data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"google-stillwater-oklahoma"},"record":{"aliases":[],"id":"google-stillwater-oklahoma","last_reviewed":"2026-10-09","location":{"admin1":"Oklahoma","admin2":"Payne County","country":"US","lat":36.116,"locality":"Stillwater","lon":-97.059,"note":"Coordinates are the Stillwater city coordinates from its Wikipedia page. Sources place the site at the intersection of Perkins and Richmond Roads but give no parcel coordinates, and no geocoder was used.","precision":"locality","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-03-13","basis":"reported","metric":"investment","note":"Potential total for the full campus, which the mayor described as a 25-year project.","qualifier":"up_to","source_ids":["s2"],"unit":"USD","value":3000000000}],"milestones":[{"date":"2025-03","event":"site_acquired","kind":"actual","note":"The city announced on 12 March 2025 that Google had acquired the land; the transaction date itself is not given.","source_ids":["s1","s3"]},{"date":"2025-03-12","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Construction of the first phase was expected to be finished as early as 2027.","source_ids":["s2"]}],"name":"Google Stillwater data center campus","notes":"No dated 2026 report on construction could be opened; the status relies on Baxtel's undated third-party listing (accessed 2026-10-09), which shows the campus as planned. That listing also describes a USD 3 billion campus of up to six data centers on about 400 acres of state-owned land north of the former Armstrong facility; because this differs from the city's account of land Google acquired at Perkins and Richmond Roads, those site figures are not recorded. The USD 3 billion figure is a ceiling for the full build-out, not a committed first-phase cost.","parties":[{"name":"Google","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Google","note":"Acquired the land in 2025.","role":"owner","source_ids":["s1","s3"]},{"name":"City of Stillwater","note":"Announced Google as the buyer; Google is to make payments in lieu of property taxes to the city rather than paying the taxes initially.","role":"government","source_ids":["s1","s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-03-12","publisher":"City of Stillwater","title":"Google has Acquired Land in Stillwater","type":"government","url":"https://stillwaterok.gov/CivicAlerts.asp?AID=332"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260315181744/https://www.kgou.org/science-technology-and-environment/2025-03-13/google-will-operate-massive-data-center-development-in-stillwater","id":"s2","published":"2025-03-13","publisher":"KGOU (Oklahoma Public Media Exchange)","title":"Google will operate massive data center development in Stillwater","type":"news","url":"https://www.kgou.org/science-technology-and-environment/2025-03-13/google-will-operate-massive-data-center-development-in-stillwater"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260123142405/https://www.tradeandindustrydev.com/region/oklahoma/news/ok-google-acquires-land-stillwater-development-34278","id":"s3","published":"2025-03-18","publisher":"Trade and Industry Development","title":"OK: Google Acquires Land in Stillwater for Development of Data Center Campus","type":"trade_press","url":"https://www.tradeandindustrydev.com/region/oklahoma/news/ok-google-acquires-land-stillwater-development-34278"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Baxtel","title":"Google: Stillwater ID4 Data Center","type":"other","url":"https://baxtel.com/data-center/google-stillwater-id4"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Stillwater, Oklahoma","type":"other","url":"https://en.wikipedia.org/wiki/Stillwater,_Oklahoma"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s4"],"summary":"Planned Google data center campus on land Google acquired at the intersection of Perkins and Richmond Roads in Stillwater, Oklahoma, disclosed by the city in March 2025 after county economic development officials had kept the buyer's identity confidential. Local reporting describes a project of up to USD 3 billion that the mayor called a 25-year plan, with first-phase construction expected to finish as early as 2027 and Google initially making payments in lieu of property taxes. Tracker Baxtel lists the campus as planned.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"acd64cf6-e494-594b-ab09-08d50e7f3392","s2":"732dfda4-ac7d-586c-baab-708a24898add","s3":"e02beec7-6c88-5f0d-b613-b81fcedce639","s4":"84a06e7d-fd45-57f7-8046-11fd2a7b47bc","s5":"d5cb82ef-e8a6-5bc6-92b4-6db56b6676d1"},"source_file":"datacenters/projects/google-stillwater-oklahoma.json","source_record_id":"google-stillwater-oklahoma","source_record_sha256":"a3d3a99caeeae73d486ddaabcccc22fe746038d5a23fb7a11e30539f1f081c6a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"35a7d2fc395b8a80c638ffc3a1982197916f1db32f23f9e35208a9c7dd149d1f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d92255df1f2246ac16d5/#project-1b7d1694-1f94-5ac5-a39d-ef81696ed589 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1b7d1694-1f94-5ac5-a39d-ef81696ed589.json
1cae5b48-c630-5f16-9fe2-5d77571cafe9 | curated:telia-vilnius-data-center:new-data-center-current-build | vcc-site-5da88d035bad0f411f53 | curated:telia-vilnius-data-center | Telia New Vilnius Data Center | Lithuania | LT | 54.7823 | 25.1831 | Polygon | campus | osm_way_nodes_to_polygon | osm_named_telia_construction_area_as_site_campus_locator | community_named_construction_area_as_campus_locator | community_source | campus_locator | The community way names a Telia data centre and is tagged construction, but it is only a site locator. It is not an official parcel, campus boundary, project footprint, building footprint, or current-work extent; its opening_date tag is not lifecycle evidence. |  | OpenStreetMap supplies no bounded numeric accuracy for this community construction-area geometry. | 198c88a9-e654-5181-8c63-320728601fe3 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | a40975a4-9388-5f76-8e67-73e0e96ca8e8 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.16 country-diversity batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nasdaqbaltic.com/market/upload/reports/tel1/2026_q2_en.pdf | https://api.openstreetmap.org/api/0.6/way/1485385261/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5da88d035bad0f411f53/#project-1cae5b48-c630-5f16-9fe2-5d77571cafe9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1cae5b48-c630-5f16-9fe2-5d77571cafe9.json
1f33fed8-b0f9-50e2-8fac-56d135325c27 | curated:iij-shiroi-data-center-campus:phase-3-server-building | vcc-site-38f7e55e7e55aaed6c27 | curated:iij-shiroi-data-center-campus | IIJ Shiroi DCC Phase 3 Server Building | Japan | JP | 35.7991 | 140.0996 | Polygon | address_area | cross_source_geometry | estat_2020_jgd2011_exact_sakuradai_5_chome_polygon_as_campus_address_area_locator | official_census_small_area_address_area_polygon | official_source | campus_locator | Official e-Stat 2020 census small-area polygon for 桜台五丁目, used only as a broad address-area locator for the named campus. It is not a campus, parcel, cadastral, building, Phase 3, security, construction, or current-work boundary. The reported 55,117.019 square metres is only the selected statistical feature's area, never an IIJ campus, site, parcel, building, Phase 3, or construction area. Statistical small-area boundaries may not match general regional or administrative boundaries. |  | The e-Stat download does not provide a numeric horizontal positional-accuracy statement for this selected feature. | f6d41f05-04ff-5e9b-8be6-164d895d24d6 | under_construction | 2026-06-25 | 110 | authoritative_physical_status_update | 4bd37265-9c6e-556b-8899-8015ffc11cae | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2025-05-08","base":10.0,"confidence":0.99,"evidence_id":"35d502eb-803a-5c40-8dc1-f0825babb831","high":10.0,"low":10.0,"method":"reported","metric":"grid_connection_mw","notes":"Source-reported 10 MW planned maximum incoming or received power capacity for the Phase 3 building. The optional 25 MW expandability ceiling is metadata only and is not a second installed, contracted, current, or additive value; neither figure is IT load, gross demand, generation, measured energy, or converted from MVA.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.iij.ad.jp/en/ir/policy/risk/ | https://www.e-stat.go.jp/gis/statmap-search/data?dlserveyId=A002005212020&code=12232&coordSys=1&format=shape&downloadType=5&datum=2011 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-38f7e55e7e55aaed6c27/#project-1f33fed8-b0f9-50e2-8fac-56d135325c27 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1f33fed8-b0f9-50e2-8fac-56d135325c27.json
1f415639-6b0f-5f32-b15e-07984488b5cc | imported:semiconductor-atlas:atnorth-salo-fin05 | vcc-site-3b04bcaab24c7214a619 | imported:semiconductor-atlas:atnorth-salo-fin05 | atNorth FIN05 Salo mega site | Finland | FI | 60.3879 | 23.1249 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Salo without a street address; the coordinates are the Nominatim point for Salo's central district (Salon suuralue). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | e5f7decb-779b-558c-bd40-4179cd817302 | announced | 2026-10-05 | 8 | imported_documented_status | e5f7decb-779b-558c-bd40-4179cd817302 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e5f7decb-779b-558c-bd40-4179cd817302","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-salo-fin05"},{"evidence_id":"f5557b8c-3b16-53fe-83a2-d62b9ca6850b","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-salo-fin05"},{"evidence_id":"e5f7decb-779b-558c-bd40-4179cd817302","notes":"Transmission grid operator; the site will connect through a Fingrid substation.","party":"Fingrid","relationship_scope":"unknown","role":"utility","source_record_id":"atnorth-salo-fin05"},{"evidence_id":"e5f7decb-779b-558c-bd40-4179cd817302","notes":"Municipality that worked with atNorth and site developer Regant Oy to prepare the site.","party":"City of Salo","relationship_scope":"unknown","role":"government","source_record_id":"atnorth-salo-fin05"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.atnorth.com/news/atnorth-to-develop-new-data-center-in-salo-finland/ | https://www.atnorth.com/news/atnorth-to-develop-new-data-center-in-salo-finland/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve atNorth FIN05 Salo mega site as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"atnorth-salo-fin05"},"record":{"aliases":["FIN05","Salo mega site"],"id":"atnorth-salo-fin05","last_reviewed":"2026-10-09","location":{"admin1":"Southwest Finland","admin2":"Salo","country":"FI","lat":60.3879,"locality":"Salo","lon":23.1249,"note":"Sources name Salo without a street address; the coordinates are the Nominatim point for Salo's central district (Salon suuralue).","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Site page gives 230 MW of gross power; the press release describes a path to up to 230 MW without stating scope.","power_scope":"facility","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":230},{"applies_to":"campus","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","power_scope":"it_load","qualifier":"up_to","source_ids":["s2"],"unit":"MW","value":160},{"applies_to":"phase","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Press release figure; the site page lists the first phase as 60 MW of IT capacity, so the two may be different scopes.","phase_label":"First phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":75},{"applies_to":"phase","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","phase_label":"First phase","power_scope":"it_load","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":60},{"applies_to":"campus","as_of":"2026-10-05","basis":"announced","metric":"investment","note":"atNorth's own investment, excluding customer-owned servers and their installation, which the company says could represent a further investment estimated at up to EUR 10bn.","qualifier":"approximately","source_ids":["s1"],"unit":"EUR","value":2000000000},{"applies_to":"campus","as_of":"2026-10-05","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1","s2"],"unit":"hectares","value":28.6}],"milestones":[{"date":"2026-10-05","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2028-Q3","event":"other","kind":"planned","note":"Power availability planned for the 60 MW IT first phase.","source_ids":["s2"]}],"name":"atNorth FIN05 Salo mega site","parties":[{"name":"atNorth","role":"developer","source_ids":["s1","s2"]},{"name":"Fingrid","note":"Transmission grid operator; the site will connect through a Fingrid substation.","role":"utility","source_ids":["s1"]},{"name":"City of Salo","note":"Municipality that worked with atNorth and site developer Regant Oy to prepare the site.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Connection to Fingrid's transmission grid via a substation; first-phase power described as secured, with long-term PPAs with local suppliers planned and generation sources not named.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-10-05","publisher":"atNorth","title":"atNorth to develop new data center in Salo, Finland","type":"company","url":"https://www.atnorth.com/news/atnorth-to-develop-new-data-center-in-salo-finland/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"atNorth","title":"Salo mega site (FIN05)","type":"company","url":"https://www.atnorth.com/nordic-data-centers/finland-data-centers/salo-fin05/"}],"status":"announced","status_as_of":"2026-10-05","status_source_ids":["s1"],"summary":"atNorth announced on 5 October 2026 a data center campus, FIN05, on a 28.6-hectare development-ready site in Salo, southwest Finland, with about EUR 2bn of its own investment; customer-owned servers could add a further investment estimated at up to EUR 10bn. The press release describes a 75 MW first phase with secured power and a path to up to 230 MW, while the site page lists 230 MW of gross power, up to 160 MW of IT capacity and a 60 MW IT first phase with power planned for Q3 2028. The site will connect to Fingrid's transmission grid through a substation, and atNorth plans long-term power purchase agreements with local suppliers.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e5f7decb-779b-558c-bd40-4179cd817302","s2":"f5557b8c-3b16-53fe-83a2-d62b9ca6850b"},"source_file":"datacenters/projects/atnorth-salo-fin05.json","source_record_id":"atnorth-salo-fin05","source_record_sha256":"1da215e6bedfd374871bdfba6be0096bbe36769d6d2c5e7eb23f92cc42504d9d","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b232b45c60aab63fc845fadadb304a28ccbf6e63d347d5c42ff3837fb50d61a7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3b04bcaab24c7214a619/#project-1f415639-6b0f-5f32-b15e-07984488b5cc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1f415639-6b0f-5f32-b15e-07984488b5cc.json
1f430ea1-a0e6-5a91-b3e7-3f002b331cf6 | curated:meta-lebanon-indiana-data-center:current-development | vcc-site-3c5c88d7f501e957c28a | curated:meta-lebanon-indiana-data-center | Meta Lebanon Indiana Current Development | United States | US | 40.0643 | -86.531 | Point | campus | official_exact_permit_record_reference_point | DNR_DOWUnity_ATS_layer0_folder_id_FW33468_0_native_EPSG3857_server_to_EPSG4326_independently_checked | official_campus_associated_detention_outfall_permit_reference_locator | official_source | campus_locator | DNR record-reference point for FW-33468-0, an Orla campus-associated detention outfall at Deer Creek. The full DNR notice names the data-center campus at 3602 West State Road32; municipal July6 minutes equate Orla/Domino/Meta at that address. This locates one campus through its permit reference at the creek edge. It is not a data-center building center, construction work extent, surveyed facility point or campus boundary. Original UTM-to-map derivation was not independently verified; September location retrieval does not advance July6 construction. |  | DNR publishes a permit-record reference point but no site-specific numeric horizontal accuracy. Service coordinate precision and transform agreement are not positional accuracy. | 7676427f-a61d-547c-a3f8-d91a734ebccd | under_construction | 2026-07-06 | 99 | authoritative_physical_status_update | 2c1ca24e-7649-5551-85f5-511271e7c8c4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"82a40887-843c-59ab-9bc1-f3a9c5ca32e2","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"34de5b68-3131-58d5-b992-614a9da691b0","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"34de5b68-3131-58d5-b992-614a9da691b0","notes":"Named among Meta's partners on a page that refers readers to the project's general contractors for construction information.","party":"Mortenson","relationship_scope":"unknown","role":"builder","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"34de5b68-3131-58d5-b992-614a9da691b0","notes":"Named among Meta's partners on a page that refers readers to the project's general contractors for construction information.","party":"Turner Construction Company","relationship_scope":"unknown","role":"builder","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"34de5b68-3131-58d5-b992-614a9da691b0","notes":"Named among Meta's partners on a page that refers readers to the project's general contractors for construction information.","party":"Faith Technologies","relationship_scope":"unknown","role":"builder","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"34de5b68-3131-58d5-b992-614a9da691b0","notes":"Named by Meta as an energy-planning partner; Meta says it pays the full cost of the energy used.","party":"Wabash Valley Power Alliance","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"7d5fa98c-95e0-54e7-8025-77c293438f83","notes":"Named by Meta as an energy-planning partner; Meta says it pays the full cost of the energy used.","party":"Wabash Valley Power Alliance","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"34de5b68-3131-58d5-b992-614a9da691b0","notes":"Named by Meta as an energy-planning partner.","party":"Boone Power","relationship_scope":"unknown","role":"utility","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"7d5fa98c-95e0-54e7-8025-77c293438f83","notes":"Named by Meta as an energy-planning partner.","party":"Boone Power","relationship_scope":"unknown","role":"utility","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"ec4c2359-182b-561d-9cda-b158797bcbc2","notes":"Water utility that said it plans to supply the site.","party":"Citizens Energy Group","relationship_scope":"unknown","role":"utility","source_record_id":"meta-lebanon-indiana"},{"evidence_id":"82a40887-843c-59ab-9bc1-f3a9c5ca32e2","notes":"Committed a performance-based 35-year data center sales tax exemption that requires at least USD 1 billion of investment within six years and can be extended to as many as 50 years with further investment.","party":"Indiana Economic Development Corporation","relationship_scope":"unknown","role":"government","source_record_id":"meta-lebanon-indiana"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://lebanon.in.gov/wp-content/uploads/2026/01/07.06.2026-Board-of-Zoning-Appeals-Mtg-Minutes.pdf | https://gisdata.in.gov/server/rest/services/Hosted/DOWUnity_ATS_Records_PROD/FeatureServer/0/query?where=folder_id%3D%27FW-33468-0%27&outFields=*&f=pjson&returnGeometry=true&outSR=4326 | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same Meta LEAP district Lebanon campus with February 2026 groundbreaking and phased current development. No competing Meta Lebanon site is present in the release.","source_record_id":"meta-lebanon-indiana","target_project_stable_key":"curated:meta-lebanon-indiana-data-center:current-development"},"record":{"aliases":["Lebanon Data Center"],"id":"meta-lebanon-indiana","last_reviewed":"2026-10-09","location":{"admin1":"Indiana","country":"US","lat":40.0484,"locality":"Lebanon","lon":-86.4692,"note":"City point from OpenStreetMap Nominatim; sources place the campus in Lebanon's LEAP district but give no parcel or address.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-02-11","basis":"announced","metric":"investment","note":"To be invested across up to six phases.","qualifier":"more_than","source_ids":["s1","s2","s5"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2026-02-11","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1","s4"],"unit":"acres","value":1500},{"applies_to":"campus","as_of":"2026-02-11","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s2"],"unit":"sq_ft","value":4000000},{"applies_to":"campus","as_of":"2026-02-11","basis":"planned","metric":"buildings","note":"Ten data center buildings plus buildings for logistics and warehousing, network and administrative support.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":13},{"applies_to":"campus","as_of":"2026-02-11","basis":"planned","metric":"jobs_construction","note":"Meta's announcement post says about 4,000 at peak.","qualifier":"more_than","source_ids":["s1","s5"],"unit":"count","value":4000},{"applies_to":"campus","as_of":"2026-02-11","basis":"planned","metric":"jobs_permanent","note":"Meta's announcement post says more than 300; its fact sheet gives 300.","qualifier":"approximately","source_ids":["s1","s5"],"unit":"count","value":300}],"milestones":[{"date":"2026-02-11","event":"announced","kind":"actual","note":"Meta described it as its second data center in Indiana.","source_ids":["s1","s2"]},{"date":"2026-02-11","event":"construction_started","kind":"actual","note":"Groundbreaking attended by Gov. Mike Braun and Meta executives.","source_ids":["s1","s3"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Reported expectation of operations in 2027 or early 2028.","source_ids":["s4"]}],"name":"Meta Lebanon data center campus","notes":"Meta's fact sheet PDF (s5) shows no publication date; its embedded file creation date is 2026-09-02.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Mortenson","note":"Named among Meta's partners on a page that refers readers to the project's general contractors for construction information.","role":"builder","source_ids":["s2"]},{"name":"Turner Construction Company","note":"Named among Meta's partners on a page that refers readers to the project's general contractors for construction information.","role":"builder","source_ids":["s2"]},{"name":"Faith Technologies","note":"Named among Meta's partners on a page that refers readers to the project's general contractors for construction information.","role":"builder","source_ids":["s2"]},{"name":"Wabash Valley Power Alliance","note":"Named by Meta as an energy-planning partner; Meta says it pays the full cost of the energy used.","role":"power_supplier","source_ids":["s2","s5"]},{"name":"Boone Power","note":"Named by Meta as an energy-planning partner.","role":"utility","source_ids":["s2","s5"]},{"name":"Citizens Energy Group","note":"Water utility that said it plans to supply the site.","role":"utility","source_ids":["s4"]},{"name":"Indiana Economic Development Corporation","note":"Committed a performance-based 35-year data center sales tax exemption that requires at least USD 1 billion of investment within six years and can be extended to as many as 50 years with further investment.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Meta says it planned its energy needs with Wabash Valley Power Alliance and Boone Power and will pay the full cost of its energy, including any upgrades needed to power the site.","source_ids":["s2","s4","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-02-11","publisher":"Indiana Economic Development Corporation","title":"Gov. Braun Breaks Ground on $10B Meta Data Center Campus at LEAP District","type":"government","url":"https://iedc.in.gov/events/news/details/2026/02/11/gov.-braun-breaks-ground-on-10b-meta-data-center-campus-at-leap-district"},{"accessed":"2026-10-09","id":"s2","published":"2026-02-11","publisher":"Meta Platforms","title":"Hello, Lebanon!","type":"company","url":"https://datacenters.atmeta.com/2026/02/hello-lebanon/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260307115356/https://www.wrtv.com/news/local-news/meta-breaks-ground-on-10b-data-center-campus-in-lebanon","id":"s3","published":"2026-02-11","publisher":"WRTV","title":"Meta breaks ground on $10B data center campus in Lebanon","type":"news","url":"https://www.wrtv.com/news/local-news/meta-breaks-ground-on-10b-data-center-campus-in-lebanon"},{"accessed":"2026-10-09","id":"s4","published":"2026-02-12","publisher":"Indianapolis Star (via Yahoo News)","title":"Meta pledges responsible water, energy use at $10B Lebanon data center","type":"news","url":"https://www.yahoo.com/news/articles/meta-pledges-responsible-water-energy-101838480.html"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Meta Platforms","title":"Meta Lebanon Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Lebanon-Data-Center.pdf"}],"status":"under_construction","status_as_of":"2026-02-11","status_source_ids":["s1","s3"],"summary":"Meta campus of more than USD 10 billion in the LEAP Innovation and Research District in Lebanon, Indiana, Meta's second data center in the state. The state describes a 1,500-acre site with 13 buildings, 10 of them data centers, built in up to six phases; Meta gives a campus size of roughly 4 million square feet. Ground was broken on 11 February 2026, and local reporting expected operations in 2027 or early 2028. Meta planned its power needs with Wabash Valley Power Alliance and Boone Power, and Citizens Energy Group has said it plans to supply water. Indiana granted a performance-based 35-year sales tax exemption tied to at least USD 1 billion of investment in the first six years.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"82a40887-843c-59ab-9bc1-f3a9c5ca32e2","s2":"34de5b68-3131-58d5-b992-614a9da691b0","s3":"a1063bb6-1f0c-5a00-9540-8d454084b6e4","s4":"ec4c2359-182b-561d-9cda-b158797bcbc2","s5":"7d5fa98c-95e0-54e7-8025-77c293438f83"},"source_file":"datacenters/projects/meta-lebanon-indiana.json","source_record_id":"meta-lebanon-indiana","source_record_sha256":"03e9051a50c26f3cef0e0f42bff8b4b98654c271a046060ae67fac417f04952b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8938b741ef6e72dec099f0f8279e5e719ceca9e359833888c3908cbc207b172e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3c5c88d7f501e957c28a/#project-1f430ea1-a0e6-5a91-b3e7-3f002b331cf6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/1f430ea1-a0e6-5a91-b3e7-3f002b331cf6.json
20a32e9d-3c57-520d-aeb8-ad999d43fee3 | curated:hive-yguazu-paraguay-campus:2026-100mw-expansion | vcc-site-ee413666d6aa0f69a386 | curated:hive-yguazu-paraguay-campus | HIVE Yguazú 2026 Campus Electrical-Infrastructure Expansion | Paraguay | PY | -25.4845 | -55.0114 | Point | campus | official_named_environmental_project_geojson_point | MADES_SIAM_expId83461_GeoJSON_point_copied_exactly_under_RFC7946_CRS84_contract | official_environmental_project_reference_point | official_source | campus_locator | One source-supplied point for the named Zunz data-center/substation project, linked to Finca1534/Padrón33. It is not a surveyed point, building footprint, campus boundary, entrance, or separate utility-only site. No arithmetic centroid or imagery-derived coordinate. |  | MADES gives no source-specific positional-accuracy estimate or point-placement method; decimal digits do not imply survey accuracy. | 3530db1f-8c5d-541a-bf50-146038fd3aaa | under_construction | 2026-08-14 | 60 | authoritative_physical_status_update | 167e54b8-a831-5dd8-8bb7-c78931101544 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.hivedigitaltechnologies.com/static/hivesite/filings/000106299326004434/form10q.htm | https://apps.mades.gov.py/siam/poligono-siam?expediente=6240&gestion=2026&punto=true | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ee413666d6aa0f69a386/#project-20a32e9d-3c57-520d-aeb8-ad999d43fee3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/20a32e9d-3c57-520d-aeb8-ad999d43fee3.json
20ee1eea-91bf-52aa-a464-c4a38d436f9e | curated:applied-digital-polaris-forge-1:current-expansion | vcc-site-0ac82fd201fa1878b892 | epoch-ai:data-center:ae2c8749-c97f-5512-a0ad-a40ed8df37ce | Polaris Forge 1 Current Expansion | United States | US | 46.0144 | -98.5743 | Point | campus | official_constituent_permit_reference_point | NDDEQ_PDF_page18_NAD83_EPSG4269_to_EPSG4326_NAD83_to_WGS84_1 | official_constituent_permit_reference_point | official_source | campus_locator | Official reference coordinate for the ELN Building 1 backup-generator plant at the exact street address shared by PF1 campus leases. It locates the campus through a constituent plant, not the still-building project, building center or campus boundary. The permit is not current physical-status evidence. EPSG transformation is a no-op with nominal 4m transformation accuracy; total source positional accuracy is unknown. |  | No source-specific numeric accuracy is supplied. Coordinate decimals and transformation agreement are not source positional accuracy. | dd0153fd-0d77-5e96-9561-d64ddc7b9eec | under_construction | 2026-07-27 | 78 | authoritative_physical_status_update | 4ff2d650-43ba-552e-b12b-690706c23b58 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year | https://ceris.deq.nd.gov/ext/ncore/downloadfile/6356745512656156278 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ac82fd201fa1878b892/#project-20ee1eea-91bf-52aa-a464-c4a38d436f9e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/20ee1eea-91bf-52aa-a464-c4a38d436f9e.json
24911fb6-56e2-5357-a224-8cbd977e2234 | curated:iron-mountain-mia-1-miami-data-center:build | vcc-site-f20ebb79d86fe03fc732 | curated:iron-mountain-mia-1-miami-data-center | Iron Mountain MIA-1 Build | United States | US | 25.8842 | -80.2476 | Point | campus | official_address_range_geocode | census_single_exact_address_match_then_explicit_nad83_to_wgs84 | official_address_range_interpolation_exact_facility_address_locator | official_source | campus_locator | Official Census street-address interpolation for the exact publisher- and government-bound MIA-1 address at 2925 NW 120th Terrace. Campus/project locator only; not a building centroid, parcel boundary, work extent, survey point or occupancy determination. |  | No source-specific numerical horizontal-accuracy guarantee is published for the selected street-range interpolation. | b215f251-e72b-51f5-9363-705226aef274 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 57a8e965-42f2-5089-b1a1-0d3297d572c3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1020569/000102056926000068/q22026srpfinal.htm | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=2925%20NW%20120th%20Terrace%20Miami%20FL%2033167&benchmark=Public_AR_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f20ebb79d86fe03fc732/#project-24911fb6-56e2-5357-a224-8cbd977e2234 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/24911fb6-56e2-5357-a224-8cbd977e2234.json
257f3255-46fe-585e-bdf5-9689b34edbdc | curated:microsoft-san-bovio-italy-datacenter:initial-development | vcc-site-885f8423ea04be0404cf | curated:microsoft-san-bovio-italy-datacenter | Microsoft San Bovio Initial Development | Italy | IT | 45.4621 | 9.3106 | Polygon | campus | capture_replayed_geometry | cross_source_identity_bridge_to_live_osm_former_industrial_site_polygon | community_mapped_former_industrial_site_polygon | community_mapped | campus_locator | The representative point is a deterministic planar centroid derived with pyproj 3.7.2, PROJ 9.5.1, and Shapely 2.1.2 under the method pinned in geometry_entity; its serialized digits are computational reproducibility, not survey accuracy. The polygon is a community-mapped former industrial-site outline last edited in 2022. It may include land outside the 77,237 m² municipal intervention area and must not be represented as an official campus, project, parcel, planning, construction, or building boundary. |  | OSM supplies no survey accuracy, cadastral authority, or numeric horizontal uncertainty for this way. | 13dc86ac-4e90-5c6e-8540-de0c7893690f | site_preparation | 2026-07-01 | 104 | authoritative_physical_status_update | 3e9e4354-55cc-5daf-84a6-66acd2f67fe4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://local.microsoft.com/blog/san-bovio-datacenter-construction-update/ | https://api.openstreetmap.org/api/0.6/way/554352050/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-885f8423ea04be0404cf/#project-257f3255-46fe-585e-bdf5-9689b34edbdc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/257f3255-46fe-585e-bdf5-9689b34edbdc.json
26ebe837-0ec5-5973-a729-656b1b4ce011 | curated:aligned-conesville-cmh02-campus:current-site-preparation | vcc-site-88fff6786d166668a98f | curated:aligned-conesville-cmh02-campus | Aligned Conesville Current Site Preparation | United States | US | 40.1825 | -81.8748 | Point | campus | official_parcel_centroid | ArcGIS_returnCentroid_EPSG3734_to_EPSG4326_explicit_datum1188_independently_checked | official_constituent_parcel_reference_point | official_source | campus_locator | County-computed reference point for one exact Aligned-owned constituent parcel, not a whole-campus centroid, boundary, entrance, building or current-work footprint. Computational digits are retained without claiming surveyed positional accuracy. |  | County records provide no numerical positional-accuracy estimate; transformation-operation accuracy is not source feature accuracy. | 56c665a4-7406-5a2e-b355-211ccf6be6c0 | site_preparation | 2026-07-01 | 104 | authoritative_physical_status_update | be69399f-bc8f-54f2-b2c6-2d4af67000df | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ccucoal.com/ccu_projects/aligned-data-pad-project/ | https://services5.arcgis.com/zhyAQE7C1EXFJ6bG/ArcGIS/rest/services/Parcels_View/FeatureServer/0/query?objectIds=27692&outFields=OBJECTID,PIN,ONAME,ONAME2&returnGeometry=false&returnCentroid=true&outSR=4326&datumTransformation=1188&f=pjson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88fff6786d166668a98f/#project-26ebe837-0ec5-5973-a729-656b1b4ce011 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/26ebe837-0ec5-5973-a729-656b1b4ce011.json
27338e9f-68b5-58be-b981-a8a13c391bd6 | imported:semiconductor-atlas:riot-corsicana | vcc-site-387901bd13edd6eab35d | imported:semiconductor-atlas:riot-corsicana | Riot Platforms Corsicana facility | United States | US | 32.05 | -96.47 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Riot's 10-K places the facility in Navarro County without naming a town or address. Coordinates are the Navarro County point from its Wikipedia article, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 8d80043d-a444-5148-9284-457130885e28 | partially_operational | 2026-08-10 | 64 | imported_documented_status | 2fda39d7-1494-5a7f-9b17-10910c94ee51 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8d80043d-a444-5148-9284-457130885e28","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"riot-corsicana"},{"evidence_id":"b859f06c-bf9a-507b-931e-ff0555dbe242","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"riot-corsicana"},{"evidence_id":"8d80043d-a444-5148-9284-457130885e28","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"riot-corsicana"},{"evidence_id":"2ec0a78b-0ec9-5148-8f48-34c62e140fb9","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"riot-corsicana"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Riot Platforms |  |  |  | https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810x8k.htm | https://www.sec.gov/Archives/edgar/data/1167419/000110465926022322/riot-20251231x10k.htm | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Riot Platforms Corsicana facility as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"riot-corsicana"},"record":{"aliases":["Corsicana Facility","Riot Corsicana"],"id":"riot-corsicana","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Navarro County","country":"US","lat":32.05,"lon":-96.47,"note":"Riot's 10-K places the facility in Navarro County without naming a town or address. Coordinates are the Navarro County point from its Wikipedia article, not the site.","precision":"admin2","source_ids":["s1","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-10","basis":"planned","metric":"power_capacity","note":"Riot's expected total developed capacity at completion, now described as available for high-density compute; Riot does not say whether this is IT or facility load.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1","s4","s5"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-08-10","basis":"operational","metric":"power_capacity","note":"Developed capacity currently equipped for bitcoin mining.","phase_label":"Phase I (immersion-cooled bitcoin mining)","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1","s5"],"unit":"MW","value":400}],"milestones":[{"date":"2022","event":"construction_started","kind":"actual","note":"Riot began developing the Corsicana Facility in 2022 to expand bitcoin mining.","source_ids":["s1"]},{"date":"2024","event":"first_operational","kind":"actual","note":"Construction of the 400 MW Phase I mining build was completed during 2024.","source_ids":["s1"]},{"date":"2026-01-16","event":"other","kind":"actual","note":"Riot said it was working to convert all available power capacity at Corsicana, as at Rockdale, for data center use.","source_ids":["s2"]},{"date":"2026-08-10","event":"other","kind":"actual","note":"Riot disclosed a non-binding letter of intent with a single, unnamed tenant for a proposed lease of the full site and said it aims to convert it into an executed lease.","source_ids":["s3","s4"]}],"name":"Riot Platforms Corsicana facility","notes":"Status reflects the operating 400 MW mining phase; the AI/HPC conversion rests on a non-binding letter of intent and could change. Riot's 2025 10-K says it has completed a basis of design for its standard data center build to support the initial data center phase at Corsicana. The January 2026 release puts Riot's fully approved data center power portfolio at about 1.7 GW across Rockdale and Corsicana combined.","parties":[{"name":"Riot Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Riot Platforms","role":"operator","source_ids":["s1","s5"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260825192136/https://www.sec.gov/Archives/edgar/data/1167419/000110465926022322/riot-20251231x10k.htm","id":"s1","published":"2026-03-02","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms, Inc. annual report on Form 10-K for fiscal year 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926022322/riot-20251231x10k.htm"},{"accessed":"2026-10-09","id":"s2","published":"2026-01-16","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot announces fee simple acquisition of land and first data center lease with AMD at the Rockdale Site (Form 8-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926004551/riot-20260116xex99d1.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-10","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms Form 8-K: second quarter 2026 results and Corsicana letter of intent","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810x8k.htm"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-10","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms Q2 2026 earnings deck (Form 8-K, Exhibit 99.2)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810xex99d2.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261005041727/https://www.sec.gov/Archives/edgar/data/1167419/000110465926093448/riot-20260630x10q.htm","id":"s5","published":"2026-08-10","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms, Inc. quarterly report on Form 10-Q for the period ended June 30, 2026","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926093448/riot-20260630x10q.htm"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Navarro County, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Navarro_County,_Texas"}],"status":"partially_operational","status_as_of":"2026-08-10","status_source_ids":["s3","s4","s5"],"summary":"Riot Platforms campus in Navarro County, Texas, begun in 2022 to expand bitcoin mining; its 400 MW first phase of immersion-cooled mining infrastructure was completed in 2024 and still serves mining. Riot now plans to make the site's expected total of about 1 GW of developed capacity available for high-density compute: in January 2026 it said it would convert available Corsicana power for data center use, its 2025 annual report described a first data center phase at Corsicana, and in August 2026 it disclosed a non-binding letter of intent with a single tenant for the full site. The sources opened report no signed lease.","workloads":["crypto_mining","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8d80043d-a444-5148-9284-457130885e28","s2":"b859f06c-bf9a-507b-931e-ff0555dbe242","s3":"2fda39d7-1494-5a7f-9b17-10910c94ee51","s4":"84fe937f-8626-5e7f-842b-3885b2f65582","s5":"2ec0a78b-0ec9-5148-8f48-34c62e140fb9","s6":"b69d09d4-c178-5cba-8f60-872733c565de"},"source_file":"datacenters/projects/riot-corsicana.json","source_record_id":"riot-corsicana","source_record_sha256":"fd7de4e5a6744fb57de2a86a81e2ee5777f7ea63817e188b66af01f7259fc006","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"e9ca626950f6f54d42883240cce4b491a37594b6b30cc132b3eefbe58ef540a6"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-387901bd13edd6eab35d/#project-27338e9f-68b5-58be-b981-a8a13c391bd6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/27338e9f-68b5-58be-b981-a8a13c391bd6.json
27c38b34-579b-5542-b04b-44d6d5747bff | imported:semiconductor-atlas:google-cedar-rapids-iowa | vcc-site-5878345369c98c058193 | imported:semiconductor-atlas:google-cedar-rapids-iowa | Google Cedar Rapids data center campus (Big Cedar Industrial Center) | United States | US | 41.9172 | -91.7254 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | OpenStreetMap point for the Big Cedar Industrial Center in Cedar Rapids, which the site owner names as the campus location; the Google parcel within the industrial center is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | b4f744ea-d41d-5a5a-9bd0-dec70b3ae320 | under_construction | 2026-10-05 | 8 | imported_documented_status | 1e2a7ea7-9439-5415-810a-75656b9f2b31 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"cef79f8b-49b2-5c2a-909b-cd54205fe425","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-cedar-rapids-iowa"},{"evidence_id":"b4f744ea-d41d-5a5a-9bd0-dec70b3ae320","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-cedar-rapids-iowa"},{"evidence_id":"d1cbb3b9-c349-539d-8a45-f1ac7f2ce720","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-cedar-rapids-iowa"},{"evidence_id":"1e2a7ea7-9439-5415-810a-75656b9f2b31","notes":null,"party":"Google","relationship_scope":"unknown","role":"owner","source_record_id":"google-cedar-rapids-iowa"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Google |  |  |  |  | https://epoch.ai/data/ai-data-centers/directory/google-cedar-rapids | https://www.alliantenergy.com/news/news-center/2025/06/060425-googlebigcedarannouncement | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Google Cedar Rapids data center campus (Big Cedar Industrial Center) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"google-cedar-rapids-iowa"},"record":{"aliases":[],"id":"google-cedar-rapids-iowa","last_reviewed":"2026-10-09","location":{"admin1":"Iowa","admin2":"Linn County","country":"US","lat":41.9172,"locality":"Cedar Rapids","lon":-91.7254,"note":"OpenStreetMap point for the Big Cedar Industrial Center in Cedar Rapids, which the site owner names as the campus location; the Google parcel within the industrial center is not pinpointed.","precision":"approximate_site","source_ids":["s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Analyst projection of IT power for three buildings by Q2 2027, derived from satellite imagery, permits and equipment counts; Google has not published a capacity figure.","power_scope":"it_load","qualifier":"approximately","source_ids":["s4"],"unit":"MW","value":261},{"applies_to":"phase","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Analyst projection for the first building, which the analyst expects online around the end of 2026.","phase_label":"Building 1","power_scope":"it_load","qualifier":"approximately","source_ids":["s4"],"unit":"MW","value":87},{"applies_to":"campus","as_of":"2026-10-05","basis":"reported","metric":"investment","note":"Analyst projection of total capital cost by Q2 2027; the page does not say what the figure includes and it is not a company-announced figure.","qualifier":"approximately","source_ids":["s4"],"unit":"USD","value":9900000000},{"applies_to":"campus","as_of":"2025-06-06","basis":"planned","metric":"buildings","note":"A first building plus four more planned in later phases.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":5},{"applies_to":"campus","as_of":"2025-06-06","basis":"planned","metric":"jobs_construction","qualifier":"more_than","source_ids":["s3"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2025-06-06","basis":"planned","metric":"jobs_permanent","note":"Operational employees expected once the campus runs.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":100}],"milestones":[{"date":"2024-06-14","event":"construction_started","kind":"actual","note":"Date land clearing began, per analyst review of satellite imagery.","source_ids":["s4"]},{"date":"2025-05-30","event":"announced","kind":"actual","note":"Google confirmed the Cedar Rapids campus with its $7 billion Iowa investment announcement.","source_ids":["s1","s2"]},{"date":"2026","event":"first_operational","kind":"planned","note":"Trade press reported first-building completion expected in 2026; the analyst projection puts Building 1 online around the end of 2026.","source_ids":["s3","s4"]}],"name":"Google Cedar Rapids data center campus (Big Cedar Industrial Center)","notes":"The $7 billion figure is an Iowa-wide two-year commitment shared with the Council Bluffs expansion and is not recorded as a campus investment. Power and cost figures here are Epoch AI estimates (projections from satellite imagery, permits and grid data), not company figures, and should be replaced if Google or regulators publish figures. Status rests on the analyst page, last updated 2026-10-05.","parties":[{"name":"Google","role":"developer","source_ids":["s1","s2","s5"]},{"name":"Google","role":"owner","source_ids":["s4"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-05-30","publisher":"Google","title":"How Google is driving a new era of American innovation in Iowa","type":"company","url":"https://blog.google/feed/new-7-billion-investment-iowa/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007051134/https://www.alliantenergy.com/news/news-center/2025/06/060425-googlebigcedarannouncement","id":"s2","published":null,"publisher":"Alliant Energy","title":"Google Announces Data Center Project at Big Cedar Industrial Center","type":"utility","url":"https://www.alliantenergy.com/news/news-center/2025/06/060425-googlebigcedarannouncement"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260613145840/https://news.constructconnect.com/google-doubles-down-on-iowa-with-7-billion-data-center-investment","id":"s3","published":"2025-06-06","publisher":"ConstructConnect","title":"Google Doubles Down on Iowa with $7 Billion Data Center Investment","type":"trade_press","url":"https://news.constructconnect.com/google-doubles-down-on-iowa-with-7-billion-data-center-investment"},{"accessed":"2026-10-09","id":"s4","published":"2026-10-05","publisher":"Epoch AI","title":"Google Cedar Rapids ¦ AI data centers","type":"analyst","url":"https://epoch.ai/data/ai-data-centers/directory/google-cedar-rapids"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260918215012/https://datacenters.google/locations/iowa/","id":"s5","published":null,"publisher":"Google","title":"Iowa - Google Data Center Location","type":"company","url":"https://datacenters.google/locations/iowa/"}],"status":"under_construction","status_as_of":"2026-10-05","status_source_ids":["s4"],"summary":"Google's second Iowa data center campus, under construction at Alliant Energy's Big Cedar Industrial Center in Cedar Rapids, Linn County, where QTS has also announced a data center. Google confirmed the campus in May 2025 alongside a $7 billion two-year Iowa investment that also funds expansion in Council Bluffs; Google has not said how much goes to Cedar Rapids. Trade reporting said the first building would be finished in 2026, with four more planned and over 1,200 construction workers. Epoch AI, using satellite imagery and permit data, projects three buildings with about 261 MW of IT power and a capital cost near $9.9 billion by Q2 2027; these are analyst projections, not company figures.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"cef79f8b-49b2-5c2a-909b-cd54205fe425","s2":"b4f744ea-d41d-5a5a-9bd0-dec70b3ae320","s3":"6f7cb6d6-acfb-5717-af14-8069c0badaf2","s4":"1e2a7ea7-9439-5415-810a-75656b9f2b31","s5":"d1cbb3b9-c349-539d-8a45-f1ac7f2ce720"},"source_file":"datacenters/projects/google-cedar-rapids-iowa.json","source_record_id":"google-cedar-rapids-iowa","source_record_sha256":"df53e48c7006c49a303c8441490dbef432e4f568bd62589405eab64482984a16","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"c55c97d359b260455d387067bb433e03a369ead4131b9e2ab51887de398ec2b6"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5878345369c98c058193/#project-27c38b34-579b-5542-b04b-44d6d5747bff | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/27c38b34-579b-5542-b04b-44d6d5747bff.json
297b1705-767f-5434-af46-c08932afceb9 | imported:semiconductor-atlas:atnorth-varde-den02 | vcc-site-e5d89f88732b72ed1705 | imported:semiconductor-atlas:atnorth-varde-den02 | atNorth DEN02 Varde mega site | Denmark | DK | 55.8058 | 8.6181 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Local press places the site at Krageris, north and northeast of Ølgod; Krageris was not found in Nominatim, so the Ølgod village centroid is used. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 15245591-7c39-5b0f-ba74-f5156f3bf425 | announced | 2026-08-11 | 63 | imported_documented_status | 68c6b482-d3f7-585e-8771-2f062f91d288 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"68c6b482-d3f7-585e-8771-2f062f91d288","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-varde-den02"},{"evidence_id":"d1cb7946-2e5c-5ec8-b9df-b5b26c667b7c","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-varde-den02"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.atnorth.com/nordic-data-centers/denmark-data-centers/varde-mega-site/ | https://www.atnorth.com/in-the-news/atnorths-data-center-to-supply-district-heating/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve atNorth DEN02 Varde mega site as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"atnorth-varde-den02"},"record":{"aliases":["DEN02","Varde mega site","atNorth Ølgod"],"id":"atnorth-varde-den02","last_reviewed":"2026-10-09","location":{"admin1":"Region of Southern Denmark","admin2":"Varde Municipality","country":"DK","lat":55.8058,"locality":"Ølgod","lon":8.6181,"note":"Local press places the site at Krageris, north and northeast of Ølgod; Krageris was not found in Nominatim, so the Ølgod village centroid is used.","precision":"locality","source_ids":["s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"power_capacity","note":"Campus power capacity on atNorth's undated site page, which also cites scalability potential for several hundred additional MW.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"phase","as_of":"2026","basis":"planned","metric":"power_capacity","phase_label":"Initial capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2025-11-13","basis":"planned","metric":"power_capacity","note":"November 2025 local press described the planned data center at about 250 MW, matching atNorth's initial-capacity figure rather than its 500 MW campus figure.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s2"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2025-11-20","basis":"reported","metric":"investment","note":"Local press figure for the total budget, which includes about 40 hectares of greenhouses by Wa3rm, not only the data center.","qualifier":"approximately","source_ids":["s3"],"unit":"DKK","value":37000000000},{"applies_to":"campus","as_of":"2026","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":171},{"applies_to":"campus","as_of":"2025-11-13","basis":"reported","metric":"land_area","note":"Site size given in the November 13 local press article.","qualifier":"exact","source_ids":["s2"],"unit":"hectares","value":174},{"applies_to":"campus","as_of":"2025-11-20","basis":"reported","metric":"land_area","note":"Total project area including about 40 hectares of greenhouses, per the November 20 local press article.","qualifier":"exact","source_ids":["s3"],"unit":"hectares","value":175},{"applies_to":"campus","as_of":"2025-11-20","basis":"planned","metric":"floor_area","qualifier":"exact","source_ids":["s3"],"unit":"sq_m","value":250000},{"applies_to":"campus","as_of":"2025-11-20","basis":"planned","metric":"jobs_permanent","note":"Expected data center employees only; the greenhouses are expected to employ 400 more.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":100}],"milestones":[{"date":"2025-11-20","event":"other","kind":"actual","note":"Reported to be in the planning phase, with the proposed location still requiring approval by the authorities.","source_ids":["s3"]},{"date":"2025-11-13","event":"other","kind":"actual","note":"Plan reported for Ølgod Tekniske Værker to take the data center's surplus heat into the local district heating network via a pipeline of about 3.5 km; atNorth describes a letter of intent.","source_ids":["s1","s2"]},{"date":"2026-08-11","event":"other","kind":"actual","note":"atNorth named Selected Group to use surplus heat from DEN02 for greenhouses, whose first phase is expected in Q3 2028.","source_ids":["s4"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Stage 1 (data center and two greenhouses) expected to start operating at the end of 2027.","source_ids":["s3"]},{"date":"2029","event":"other","kind":"planned","note":"Stage 2 expected to be operational in 2029.","source_ids":["s3"]}],"name":"atNorth DEN02 Varde mega site","parties":[{"name":"atNorth","role":"developer","source_ids":["s1","s3"]}],"power_sources":[{"description":"Local press reports 60 to 200 chimneys, each 25 metres high, for backup power systems; atNorth says generators are backup only with fuel for at least 48 hours.","source_ids":["s1","s3"],"type":"diesel_backup"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"atNorth","title":"Varde mega site (DEN02)","type":"company","url":"https://www.atnorth.com/nordic-data-centers/denmark-data-centers/varde-mega-site/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260608151158/https://www.atnorth.com/in-the-news/atnorths-data-center-to-supply-district-heating/","id":"s2","published":"2025-11-13","publisher":"JydskeVestkysten (republished by atNorth)","title":"atNorth data center to supply district heating","type":"news","url":"https://www.atnorth.com/in-the-news/atnorths-data-center-to-supply-district-heating/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260510115327/https://www.atnorth.com/in-the-news/local-firms-prepare-for-major-project-in-varde/","id":"s3","published":"2025-11-20","publisher":"JydskeVestkysten (republished by atNorth)","title":"Local firms prepare for major project in Varde","type":"news","url":"https://www.atnorth.com/in-the-news/local-firms-prepare-for-major-project-in-varde/"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-11","publisher":"atNorth","title":"Selected Group will utilize surplus heat from atNorth's DEN02 data center","type":"company","url":"https://www.atnorth.com/news/selected-group-will-utilize-surplus-heat-from-atnorths-den02-data-center/"}],"status":"announced","status_as_of":"2026-08-11","status_source_ids":["s1","s4"],"summary":"atNorth plans its second Danish campus, DEN02, on a greenfield site of about 171-175 hectares at Krageris north of Ølgod in Varde Municipality, western Denmark. The company lists 500 MW of campus power with an initial 250 MW. Local press in November 2025 put the budget for the data center together with about 40 hectares of greenhouses to be developed by Wa3rm at about DKK 37bn, with a first stage due to start operating at the end of 2027 and a second stage in 2029, while the location still needed approval. Surplus heat is to feed Ølgod's district heating, and in August 2026 atNorth named Selected Group to use it for greenhouses next to the campus.","workloads":["colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"68c6b482-d3f7-585e-8771-2f062f91d288","s2":"15245591-7c39-5b0f-ba74-f5156f3bf425","s3":"d1cb7946-2e5c-5ec8-b9df-b5b26c667b7c","s4":"8000095e-7920-5069-9213-db27c10625d3"},"source_file":"datacenters/projects/atnorth-varde-den02.json","source_record_id":"atnorth-varde-den02","source_record_sha256":"2e602936e413676100564b4bf9d804be7256f23bd1dc65bd77af500406096f07","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4b7bf069a7c1e0b13db06d04a550709ccba9f7849ec8c0fdbf87ed931c04d47a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e5d89f88732b72ed1705/#project-297b1705-767f-5434-af46-c08932afceb9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/297b1705-767f-5434-af46-c08932afceb9.json
298d7152-0985-535e-a701-60b689a3cd00 | imported:semiconductor-atlas:riot-rockdale | vcc-site-3dedcd29014f493a2abb | curated:riot-rockdale-site | Riot Platforms Rockdale data center campus | United States | US | 30.6547 | -97.0075 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Filings place the facility in Rockdale, Milam County, without an address. Coordinates are the Rockdale city point from its Wikipedia article. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 095b495d-4219-576d-a976-579e7afcc8be | partially_operational | 2026-08-10 | 64 | imported_documented_status | c04af054-74d8-51f0-ab22-4caef34bfe14 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"095b495d-4219-576d-a976-579e7afcc8be","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"riot-rockdale"},{"evidence_id":"c04af054-74d8-51f0-ab22-4caef34bfe14","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"riot-rockdale"},{"evidence_id":"095b495d-4219-576d-a976-579e7afcc8be","notes":"Bought the roughly 200-acre site in fee simple in January 2026 after operating it under a long-term ground lease.","party":"Riot Platforms","relationship_scope":"unknown","role":"owner","source_record_id":"riot-rockdale"},{"evidence_id":"9a00d1f7-8302-5e85-9d98-1fc69fe21058","notes":"Bought the roughly 200-acre site in fee simple in January 2026 after operating it under a long-term ground lease.","party":"Riot Platforms","relationship_scope":"unknown","role":"owner","source_record_id":"riot-rockdale"},{"evidence_id":"9a00d1f7-8302-5e85-9d98-1fc69fe21058","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"riot-rockdale"},{"evidence_id":"acf9d6bc-e2fc-53ff-b31e-aa7b9bf133ea","notes":null,"party":"Riot Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"riot-rockdale"},{"evidence_id":"095b495d-4219-576d-a976-579e7afcc8be","notes":"First data center tenant: an initial 25 MW of critical IT load on a 10-year term, expanded to 50 MW, with further options and a right of first refusal.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"riot-rockdale"},{"evidence_id":"c04af054-74d8-51f0-ab22-4caef34bfe14","notes":"First data center tenant: an initial 25 MW of critical IT load on a 10-year term, expanded to 50 MW, with further options and a right of first refusal.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"riot-rockdale"},{"evidence_id":"d1a3b38d-af6f-5a5b-8136-93595ee7c920","notes":"First data center tenant: an initial 25 MW of critical IT load on a 10-year term, expanded to 50 MW, with further options and a right of first refusal.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"riot-rockdale"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Riot Platforms | Riot Platforms |  | AMD |  | https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810xex99d1.htm | https://www.sec.gov/Archives/edgar/data/1167419/000110465926004551/riot-20260116xex99d1.htm | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Riot Rockdale mining-to-AI campus. Source spans operating AMD capacity and a separate 191 MW frontier-lab lease; existing record selects AMD expansion phases 3 and 4. Do not combine the tenants or capacity scopes.","source_record_id":"riot-rockdale","target_physical_site_stable_key":"curated:riot-rockdale-site"},"record":{"aliases":["Rockdale Facility","Rockdale Site"],"id":"riot-rockdale","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Milam County","country":"US","lat":30.6547,"locality":"Rockdale","lon":-97.0075,"note":"Filings place the facility in Rockdale, Milam County, without an address. Coordinates are the Rockdale city point from its Wikipedia article.","precision":"locality","source_ids":["s1","s2","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-10","basis":"operational","metric":"power_capacity","note":"Existing grid interconnection, described as fully approved in the August 2026 release; Riot intends to convert the full 700 MW gross for data center tenants, and the 10-Q says the site currently serves both bitcoin mining and data center leasing.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2","s3","s5"],"unit":"MW","value":700},{"applies_to":"phase","as_of":"2026-08-10","basis":"contracted","metric":"power_capacity","note":"Build-to-suit Tier 3 data center; 96 MW expected December 2027 and full capacity by June 2028.","phase_label":"Frontier AI lab lease (96 MW then 95 MW)","power_scope":"it_load","qualifier":"exact","source_ids":["s3","s4","s5"],"unit":"MW","value":191},{"applies_to":"phase","as_of":"2026-08-10","basis":"contracted","metric":"power_capacity","note":"Initial 25 MW commissioned; a further 25 MW under construction in two steps, 10 MW in November 2026 and 15 MW in May 2027.","phase_label":"AMD lease (phases 1-4)","power_scope":"it_load","qualifier":"exact","source_ids":["s3","s4"],"unit":"MW","value":50},{"applies_to":"phase","as_of":"2026-08-10","basis":"operational","metric":"power_capacity","note":"Retrofit deployment planned in phases from January to May 2026 and reported commissioned in May 2026.","phase_label":"AMD initial deployment","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s3","s4"],"unit":"MW","value":25},{"applies_to":"campus","as_of":"2026-08-10","basis":"planned","metric":"power_capacity","note":"Riot's total potential IT capacity at Rockdale: the 191 MW lab lease, 50 MW contracted by AMD and 150 MW of potential AMD expansion.","power_scope":"it_load","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":391},{"applies_to":"campus","as_of":"2026-01-16","basis":"reported","metric":"investment","note":"Purchase price of the 200-acre site, paid by selling about 1,080 bitcoin.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":96000000},{"applies_to":"phase","as_of":"2026-01-16","basis":"announced","metric":"investment","note":"Retrofit capital expenditure for the initial AMD deployment, about USD 3.6 million per MW.","phase_label":"AMD initial 25 MW retrofit","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":89800000},{"applies_to":"phase","as_of":"2026-08-10","basis":"announced","metric":"investment","note":"Expected capital expenditure for the lab buildout in Riot's Q2 2026 earnings deck, consistent with its illustrative USD 11 to 12 million per IT MW; Riot expects USD 1.7 to 2.1 billion of it to be debt financed.","phase_label":"Frontier AI lab build-to-suit (191 MW IT)","qualifier":"range","source_ids":["s4"],"unit":"USD","value":2100000000,"value_high":2300000000},{"applies_to":"campus","as_of":"2026-01-16","basis":"acquired","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2"],"unit":"acres","value":200}],"milestones":[{"date":"2026-01-16","event":"site_acquired","kind":"actual","note":"Riot completed the fee simple purchase of the land under the facility for USD 96.0 million.","source_ids":["s1"]},{"date":"2026-01-16","event":"announced","kind":"actual","note":"First data center lease signed with AMD, and Riot said it would convert the full 700 MW for data center use.","source_ids":["s1"]},{"date":"2026-05","event":"other","kind":"actual","note":"Initial 25 MW for AMD fully commissioned and delivered.","source_ids":["s3","s4"]},{"date":"2026-08-10","event":"expansion_announced","kind":"actual","note":"20-year lease for 191 MW of critical IT load signed with an unnamed frontier AI lab, backed by a USD 573 million interim facility from Morgan Stanley.","source_ids":["s3","s5"]},{"date":"2027-12","event":"other","kind":"planned","note":"Expected delivery of the first 96 MW for the frontier AI lab.","source_ids":["s3","s5"]},{"date":"2028-06","event":"fully_operational","kind":"planned","note":"Expected full deployment of the 191 MW lab lease; AMD's 50 MW is due to be fully deployed by May 2027.","source_ids":["s3","s5"]}],"name":"Riot Platforms Rockdale data center campus","notes":"Riot does not name the frontier AI lab; it is not listed as a party. The lab lease carries two five-year extensions that would lift potential contract revenue to about USD 16.1 billion, and a USD 573 million Morgan Stanley interim facility funds early development. The facility still serves bitcoin mining alongside the data center leases, per the Q2 2026 10-Q.","parties":[{"name":"Riot Platforms","role":"developer","source_ids":["s1","s3"]},{"name":"Riot Platforms","note":"Bought the roughly 200-acre site in fee simple in January 2026 after operating it under a long-term ground lease.","role":"owner","source_ids":["s1","s2"]},{"name":"Riot Platforms","role":"operator","source_ids":["s2","s5"]},{"name":"AMD","note":"First data center tenant: an initial 25 MW of critical IT load on a 10-year term, expanded to 50 MW, with further options and a right of first refusal.","role":"tenant","source_ids":["s1","s3","s4"]}],"power_sources":[{"description":"Existing 700 MW grid interconnection, with dedicated water supply and fiber, reused for the data center leases.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-16","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot announces fee simple acquisition of land and first data center lease with AMD at the Rockdale Site (Form 8-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926004551/riot-20260116xex99d1.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260825192136/https://www.sec.gov/Archives/edgar/data/1167419/000110465926022322/riot-20251231x10k.htm","id":"s2","published":"2026-03-02","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms, Inc. annual report on Form 10-K for fiscal year 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926022322/riot-20251231x10k.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-10","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms reports second quarter 2026 financial results and strategic highlights (Form 8-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810xex99d1.htm"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-10","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms Q2 2026 earnings deck (Form 8-K, Exhibit 99.2)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810xex99d2.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261005041727/https://www.sec.gov/Archives/edgar/data/1167419/000110465926093448/riot-20260630x10q.htm","id":"s5","published":"2026-08-10","publisher":"Riot Platforms, Inc. via SEC EDGAR","title":"Riot Platforms, Inc. quarterly report on Form 10-Q for the period ended June 30, 2026","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1167419/000110465926093448/riot-20260630x10q.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260514082456/https://en.wikipedia.org/wiki/Rockdale,_Texas","id":"s6","published":null,"publisher":"Wikipedia","title":"Rockdale, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Rockdale,_Texas"}],"status":"partially_operational","status_as_of":"2026-08-10","status_source_ids":["s3","s4"],"summary":"Riot Platforms bitcoin mining facility on about 200 acres in Rockdale, Milam County, Texas, with a 700 MW grid interconnection, being converted for AI data center tenants. In January 2026 Riot bought the land it had leased and signed AMD for 25 MW of critical IT load, later expanded to 50 MW; the first 25 MW was commissioned in May 2026. In August 2026 Riot signed a 20-year, build-to-suit lease with an unnamed frontier AI lab for 191 MW of critical IT load worth about USD 9.1 billion, with 96 MW due in December 2027 and the rest by June 2028, and put expected capital spending on that build at USD 2.1 to 2.3 billion.","workloads":["ai_unspecified","crypto_mining"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"095b495d-4219-576d-a976-579e7afcc8be","s2":"9a00d1f7-8302-5e85-9d98-1fc69fe21058","s3":"c04af054-74d8-51f0-ab22-4caef34bfe14","s4":"d1a3b38d-af6f-5a5b-8136-93595ee7c920","s5":"acf9d6bc-e2fc-53ff-b31e-aa7b9bf133ea","s6":"e400c870-924f-5fe8-87ea-064041b029d2"},"source_file":"datacenters/projects/riot-rockdale.json","source_record_id":"riot-rockdale","source_record_sha256":"f94008953bdaca0278e91a5f93b52917878d68e759e2df3a39593ff1e55cb0e8","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"83ee46c3aeab921f2adb3ba21fb99add87cfd4743e9a3f06748fa76b26923754"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3dedcd29014f493a2abb/#project-298d7152-0985-535e-a701-60b689a3cd00 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/298d7152-0985-535e-a701-60b689a3cd00.json
2a273a46-2f4f-5ccb-9d10-6f2bfeb5e5f5 | imported:semiconductor-atlas:azora-tillion-villamayor-de-gallego | vcc-site-6bd6515ae5d1dc80cf5a | imported:semiconductor-atlas:azora-tillion-villamayor-de-gallego | Tillion Aragón data center campus (Azora), Villamayor de Gállego | Spain | ES | 41.6856 | -0.77389 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid from the Villamayor de Gállego Wikipedia article. Azora places the site near Villamayor de Gállego, less than 3 km from the transmission substation, but no cited source gives coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 7db7facd-988b-5356-8a99-32564b31071e | announced | 2026-10-05 | 8 | imported_documented_status | 2435d594-4bb5-5062-9ac2-4564e08dc119 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"7db7facd-988b-5356-8a99-32564b31071e","notes":"Develops the campus through its subsidiary Tillion Data Centres.","party":"Azora","relationship_scope":"unknown","role":"developer","source_record_id":"azora-tillion-villamayor-de-gallego"},{"evidence_id":"2435d594-4bb5-5062-9ac2-4564e08dc119","notes":"Develops the campus through its subsidiary Tillion Data Centres.","party":"Azora","relationship_scope":"unknown","role":"developer","source_record_id":"azora-tillion-villamayor-de-gallego"},{"evidence_id":"0acf5c00-bb2a-5bb7-b417-ea36a5bb07d2","notes":"Promoter of the regional plan; formerly named Maquina Solar, S.L.","party":"Tillion Aragón, S.L.","relationship_scope":"unknown","role":"developer","source_record_id":"azora-tillion-villamayor-de-gallego"},{"evidence_id":"7db7facd-988b-5356-8a99-32564b31071e","notes":"Transmission operator that approved the initial 150 MW grid connection; the plan includes a 400 kV connection to its Peñaflor substation.","party":"Red Eléctrica","relationship_scope":"unknown","role":"utility","source_record_id":"azora-tillion-villamayor-de-gallego"},{"evidence_id":"0acf5c00-bb2a-5bb7-b417-ea36a5bb07d2","notes":"Transmission operator that approved the initial 150 MW grid connection; the plan includes a 400 kV connection to its Peñaflor substation.","party":"Red Eléctrica","relationship_scope":"unknown","role":"utility","source_record_id":"azora-tillion-villamayor-de-gallego"},{"evidence_id":"0acf5c00-bb2a-5bb7-b417-ea36a5bb07d2","notes":"Declared the project of general interest and is processing its Plan de Interés General de Aragón.","party":"Government of Aragon","relationship_scope":"unknown","role":"government","source_record_id":"azora-tillion-villamayor-de-gallego"},{"evidence_id":"2435d594-4bb5-5062-9ac2-4564e08dc119","notes":"Declared the project of general interest and is processing its Plan de Interés General de Aragón.","party":"Government of Aragon","relationship_scope":"unknown","role":"government","source_record_id":"azora-tillion-villamayor-de-gallego"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html | https://azora.com/en/blog/azora-to-invest-e2-billion-in-zaragoza-data-centre/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Tillion Aragón data center campus (Azora), Villamayor de Gállego as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"azora-tillion-villamayor-de-gallego","source_relations":[{"reason":"Distinct Azora/Tillion and Microsoft projects; shared Villamayor municipality point is not a parcel or alias.","relationship":"separate_named_developments","source_id":"microsoft-aragon-villamayor-de-gallego"}]},"record":{"aliases":["Tillion Aragón","PIGA Tillion Aragón"],"id":"azora-tillion-villamayor-de-gallego","last_reviewed":"2026-10-09","location":{"admin1":"Aragon","admin2":"Zaragoza","country":"ES","lat":41.68556,"locality":"Villamayor de Gállego","lon":-0.77389,"note":"Town centroid from the Villamayor de Gállego Wikipedia article. Azora places the site near Villamayor de Gállego, less than 3 km from the transmission substation, but no cited source gives coordinates.","precision":"locality","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-03-13","basis":"planned","metric":"power_capacity","note":"Expansion ceiling after the first phase; scope not stated.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2025-03-13","basis":"planned","metric":"power_capacity","phase_label":"Phase 1","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"phase","as_of":"2025-03-13","basis":"permitted","metric":"power_capacity","note":"Red Eléctrica approved the initial 150 MW grid connection in 2024.","phase_label":"Phase 1","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"phase","as_of":"2025-03-13","basis":"announced","metric":"investment","note":"Also the figure recorded in the initial declaration of general interest.","phase_label":"Phase 1","qualifier":"exact","source_ids":["s1","s3"],"unit":"EUR","value":1100000000},{"applies_to":"campus","as_of":"2025-03-13","basis":"announced","metric":"investment","note":"Azora's investment at 300 MW, headlined as up to EUR 2 billion. Azora said end users would add about EUR 5 billion of computing equipment.","qualifier":"up_to","source_ids":["s1"],"unit":"EUR","value":1950000000},{"applies_to":"campus","as_of":"2026-10-05","basis":"reported","metric":"investment","note":"El Español reports that the investment rose from EUR 1,100 million in the initial declaration of general interest to EUR 2,359.9 million; it does not say whether this covers a phase or the whole campus.","qualifier":"exact","source_ids":["s3"],"unit":"EUR","value":2359900000},{"applies_to":"campus","as_of":"2026-07-07","basis":"planned","metric":"buildings","note":"The plan documents include basic building projects for four data center buildings.","qualifier":"exact","source_ids":["s2"],"unit":"count","value":4}],"milestones":[{"date":"2025-03-13","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-03-13","event":"other","kind":"actual","note":"The Government of Aragon declared the project of general interest (DIGA); published in the regional gazette on 3 April 2025.","source_ids":["s2","s1"]},{"date":"2026-02-21","event":"other","kind":"actual","note":"Tillion Aragón filed the Plan de Interés General de Aragón for initial approval.","source_ids":["s2"]},{"date":"2026-07","event":"other","kind":"actual","note":"El Español reported the regional plan approved in July; the regional page lists an initial-approval order dated 24 June and no final approval. Public information on the plan and its environmental documents followed.","source_ids":["s3","s2"]},{"date":"2027","event":"construction_started","kind":"planned","note":"Azora targeted a 2026 start; in 2026 El Español expected urbanisation works between late 2026 and 2027.","source_ids":["s3","s4","s1"]}],"name":"Tillion Aragón data center campus (Azora), Villamayor de Gállego","notes":"The regional plan page shows a last-updated date of 7 July 2026, used as its published date. The date of the initial-approval order is ambiguous on that page (shown as 24 June with a 2025 order code, before the February 2026 filing), so the approval milestone follows El Español's July report. Microsoft separately plans a campus in the same municipality (microsoft-aragon-villamayor-de-gallego); this is a different project.","parties":[{"name":"Azora","note":"Develops the campus through its subsidiary Tillion Data Centres.","role":"developer","source_ids":["s1","s3"]},{"name":"Tillion Aragón, S.L.","note":"Promoter of the regional plan; formerly named Maquina Solar, S.L.","role":"developer","source_ids":["s2"]},{"name":"Red Eléctrica","note":"Transmission operator that approved the initial 150 MW grid connection; the plan includes a 400 kV connection to its Peñaflor substation.","role":"utility","source_ids":["s1","s2"]},{"name":"Government of Aragon","note":"Declared the project of general interest and is processing its Plan de Interés General de Aragón.","role":"government","source_ids":["s2","s3"]}],"power_sources":[{"description":"Planned 400 kV connection to Red Eléctrica's Peñaflor substation with 66 kV lines and on-site substations.","source_ids":["s2","s1"],"type":"grid"},{"description":"Azora says the campus will run fully on renewable energy through self-consumption or long-term power purchase agreements; El Español reported a plot added to the plan for power supply.","source_ids":["s1","s4"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260314023442/https://www.azora.com/en/blog/azora-to-invest-e2-billion-in-zaragoza-data-centre/","id":"s1","published":"2025-03-13","publisher":"Azora","title":"Azora to invest €2 billion in Zaragoza data centre","type":"company","url":"https://azora.com/en/blog/azora-to-invest-e2-billion-in-zaragoza-data-centre/"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-07","publisher":"Gobierno de Aragón","title":"Plan de Interés General de Aragón Tillion Aragón","type":"government","url":"https://www.aragon.es/-/piga-tillion-aragon"},{"accessed":"2026-10-09","id":"s3","published":"2026-10-05","publisher":"El Español","title":"Cerca de 6.000 millones invertidos en centros de datos en Aragón esperan en la rampa de salida para las obras","type":"news","url":"https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260527095310/https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html","id":"s4","published":"2026-03-22","publisher":"El Español","title":"Aragón se convierte en la capital de los datos y la nube: el calendario de Amazon, Microsoft y todos los proyectos","type":"news","url":"https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003063049/https://en.wikipedia.org/wiki/Villamayor_de_G%C3%A1llego","id":"s5","published":null,"publisher":"Wikipedia","title":"Villamayor de Gállego","type":"other","url":"https://en.wikipedia.org/wiki/Villamayor_de_G%C3%A1llego"}],"status":"announced","status_as_of":"2026-10-05","status_source_ids":["s3","s2"],"summary":"Data center campus planned by Azora, through its Tillion Data Centres business and the project company Tillion Aragón, near Villamayor de Gállego outside Zaragoza. Announced in March 2025 at 150 MW expandable to 300 MW, with EUR 1.1 billion for the first phase and up to about EUR 2 billion in total. Red Eléctrica approved the first 150 MW grid connection in 2024. The regional plan covers four data center buildings and a 400 kV link to the Peñaflor substation. In October 2026 El Español reported the investment had risen to about EUR 2.36 billion, with site works expected from late 2026 or in 2027.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"7db7facd-988b-5356-8a99-32564b31071e","s2":"0acf5c00-bb2a-5bb7-b417-ea36a5bb07d2","s3":"2435d594-4bb5-5062-9ac2-4564e08dc119","s4":"59663da0-d1e1-5f72-a8a8-01d88194d17f","s5":"c8171581-979a-55ee-8d33-80ca7dc08f58"},"source_file":"datacenters/projects/azora-tillion-villamayor-de-gallego.json","source_record_id":"azora-tillion-villamayor-de-gallego","source_record_sha256":"d1aa0d3a5fca4ebf39c3e2a7b90748b3b6d7ece4bb0331301d392f040c29ec3a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7672ac9acef3f6c9df3185493ac1a59755652cde94ebcd069bdc3e0e107ea297"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6bd6515ae5d1dc80cf5a/#project-2a273a46-2f4f-5ccb-9d10-6f2bfeb5e5f5 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2a273a46-2f4f-5ccb-9d10-6f2bfeb5e5f5.json
2a418e82-60a0-52bf-ac57-8e0e3d3eabdb | imported:semiconductor-atlas:herbata-naas | vcc-site-d1b09eaeac654b3c56f6 | imported:semiconductor-atlas:herbata-naas | Herbata data centre campus (Naas) | Ireland | IE | 53.217 | -6.663 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from the Naas Wikipedia article. The appeal case lists the townlands of Halverstown, Jigginstown and Newhall, and reports place the site next to the M7 and a business park; no parcel point is published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | da93ca09-cc13-5f11-81da-e797c36cefe3 | announced | 2026-10-09 | 4 | imported_documented_status | da93ca09-cc13-5f11-81da-e797c36cefe3 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8d74818e-9a60-52d6-a095-8253180dfddb","notes":"The Kildare Nationalist says the plans were lodged by a co-owner of the forklift maker Combilift.","party":"Herbata Ltd","relationship_scope":"unknown","role":"developer","source_record_id":"herbata-naas"},{"evidence_id":"da93ca09-cc13-5f11-81da-e797c36cefe3","notes":"The Kildare Nationalist says the plans were lodged by a co-owner of the forklift maker Combilift.","party":"Herbata Ltd","relationship_scope":"unknown","role":"developer","source_record_id":"herbata-naas"},{"evidence_id":"0cd7c212-77b6-569f-9b56-0f107bec6d3c","notes":"The Kildare Nationalist says the plans were lodged by a co-owner of the forklift maker Combilift.","party":"Herbata Ltd","relationship_scope":"unknown","role":"developer","source_record_id":"herbata-naas"},{"evidence_id":"8d74818e-9a60-52d6-a095-8253180dfddb","notes":"Granted planning permission (reference 2460787 per the appeals board case page) in August 2025; the Irish Times says dozens of conditions were attached, many on energy use.","party":"Kildare County Council","relationship_scope":"unknown","role":"government","source_record_id":"herbata-naas"},{"evidence_id":"4081304f-ec88-5900-b577-1bd2bb35fedd","notes":"Granted planning permission (reference 2460787 per the appeals board case page) in August 2025; the Irish Times says dozens of conditions were attached, many on energy use.","party":"Kildare County Council","relationship_scope":"unknown","role":"government","source_record_id":"herbata-naas"},{"evidence_id":"da93ca09-cc13-5f11-81da-e797c36cefe3","notes":"Granted planning permission (reference 2460787 per the appeals board case page) in August 2025; the Irish Times says dozens of conditions were attached, many on energy use.","party":"Kildare County Council","relationship_scope":"unknown","role":"government","source_record_id":"herbata-naas"},{"evidence_id":"0cd7c212-77b6-569f-9b56-0f107bec6d3c","notes":"Granted planning permission (reference 2460787 per the appeals board case page) in August 2025; the Irish Times says dozens of conditions were attached, many on energy use.","party":"Kildare County Council","relationship_scope":"unknown","role":"government","source_record_id":"herbata-naas"},{"evidence_id":"8d74818e-9a60-52d6-a095-8253180dfddb","notes":"Planning appeals board handling case PL09.323677.","party":"An Coimisiún Pleanála","relationship_scope":"unknown","role":"government","source_record_id":"herbata-naas"},{"evidence_id":"da93ca09-cc13-5f11-81da-e797c36cefe3","notes":"Planning appeals board handling case PL09.323677.","party":"An Coimisiún Pleanála","relationship_scope":"unknown","role":"government","source_record_id":"herbata-naas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.pleanala.ie/en-ie/case/323677 | https://www.pleanala.ie/en-ie/case/323677 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Herbata data centre campus (Naas) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"herbata-naas"},"record":{"aliases":["Herbata Data Centre"],"id":"herbata-naas","last_reviewed":"2026-10-09","location":{"admin1":"Kildare","country":"IE","lat":53.217,"locality":"Naas","lon":-6.663,"note":"Town coordinates from the Naas Wikipedia article. The appeal case lists the townlands of Halverstown, Jigginstown and Newhall, and reports place the site next to the M7 and a business park; no parcel point is published.","precision":"locality","source_ids":["s4","s5","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-09-04","basis":"reported","metric":"investment","qualifier":"exact","source_ids":["s1","s5"],"unit":"EUR","value":3000000000},{"applies_to":"campus","as_of":"2025-09-09","basis":"planned","metric":"power_capacity","note":"Six data halls of 30 MW each at completion.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":180},{"applies_to":"campus","as_of":"2025-09-25","basis":"planned","metric":"power_capacity","note":"Continuous electricity demand cited by the appellants, who say it would roughly triple metered demand in County Kildare; not a developer figure.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":240},{"applies_to":"campus","as_of":"2025-09-25","basis":"planned","metric":"buildings","note":"Large two-storey data hall buildings.","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":6}],"milestones":[{"date":"2025-08","event":"permit_approved","kind":"actual","note":"Kildare County Council granted permission with conditions, many relating to energy use according to the Irish Times; the grant was then appealed.","source_ids":["s1","s5"]},{"date":"2025-09-16","event":"other","kind":"actual","note":"Appeals lodged with An Coimisiún Pleanála by An Taisce, by Friends of the Irish Environment and Friends of the Earth Ireland, and by Herbata against conditions on hedgerows, bats and watercourses.","source_ids":["s1","s3","s4"]},{"date":"2026-01-28","event":"other","kind":"planned","note":"Decision due date shown on the appeals board case page; the Irish Times (September 2026) said a ruling was expected by January, without giving a year.","source_ids":["s4"]}],"name":"Herbata data centre campus (Naas)","notes":"Status is announced because the permission is not in force while appeals are pending. The undated appeals board case page showed no decision when read on 2026-10-09, though its 28 January 2026 due date had passed, so status_as_of is that access date. Industrial Info gives US$3 billion where Irish reports give EUR 3 billion, likely the same figure with a different currency label; it is not recorded as a separate metric. Industrial Info quotes Herbata's chief executive saying a redesign cut lifetime emissions from about 28 to 4.5 million tonnes of CO2. The Irish Times notes a separate Microsoft campus planned near Jigginstown, which is not part of this record.","parties":[{"name":"Herbata Ltd","note":"The Kildare Nationalist says the plans were lodged by a co-owner of the forklift maker Combilift.","role":"developer","source_ids":["s1","s4","s5"]},{"name":"Kildare County Council","note":"Granted planning permission (reference 2460787 per the appeals board case page) in August 2025; the Irish Times says dozens of conditions were attached, many on energy use.","role":"government","source_ids":["s1","s2","s4","s5"]},{"name":"An Coimisiún Pleanála","note":"Planning appeals board handling case PL09.323677.","role":"government","source_ids":["s1","s4"]}],"power_sources":[{"description":"On-site gas turbines and gas engines to supply about half of demand; appellants dispute the emissions estimates and the planned later move to hydrogen.","source_ids":["s1","s2","s3"],"type":"natural_gas_onsite"},{"description":"Battery energy storage systems on site.","source_ids":["s2"],"type":"battery_storage"},{"description":"About 1.5 MW of rooftop solar from some 3,000 panels.","source_ids":["s2"],"type":"solar"},{"description":"Renewable power purchase agreements for about half of demand; Herbata says the campus will not draw electricity from the national grid.","source_ids":["s2","s5"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-09-25","publisher":"Kildare Nationalist","title":"Plans for €3bn data centre campus stalled","type":"news","url":"https://www.kildare-nationalist.ie/news/plans-for-3bn-data-centre-campus-stalled_arid-72032.html"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-09","publisher":"Industrial Info Resources","title":"Green Light for US$3 Billion Data Campus in Kildare","type":"trade_press","url":"https://www.industrialinfo.com/news/article/green-light-for-us3-billion-data-campus-in-kildare--345564"},{"accessed":"2026-10-09","id":"s3","published":"2025-09-25","publisher":"Friends of the Earth Ireland","title":"Campaigners appeal Herbata Data Centre decision in Naas","type":"other","url":"https://www.friendsoftheearth.ie/news/campaigners-appeal-herbata-data-centre-decision-in-naas/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"An Coimisiún Pleanála","title":"Case reference PL09.323677","type":"regulatory_filing","url":"https://www.pleanala.ie/en-ie/case/323677"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260926000805/https://www.irishtimes.com/ireland/2026/09/04/naas-has-a-message-for-the-bond-villains-we-dont-want-your-data-centres/","id":"s5","published":"2026-09-04","publisher":"The Irish Times","title":"'We just don't want them': Hundreds gather in a Kildare town over data centre plans","type":"news","url":"https://www.irishtimes.com/ireland/2026/09/04/naas-has-a-message-for-the-bond-villains-we-dont-want-your-data-centres/"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Naas","type":"other","url":"https://en.wikipedia.org/wiki/Naas"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s4","s5"],"summary":"Proposed EUR 3 billion data centre campus by Herbata Ltd beside the M7 motorway at Naas, County Kildare, Ireland, in the townlands of Halverstown, Jigginstown and Newhall. The plan has six data halls of 30 MW each, 180 MW in total, and would not draw from the national grid: half its power would come from renewable purchase agreements and the rest from on-site gas turbines, gas engines and batteries. Kildare County Council granted permission in August 2025. An Taisce and two environmental groups appealed, as did Herbata over some conditions; in September 2026 the appeals still awaited a decision by An Coimisiún Pleanála.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8d74818e-9a60-52d6-a095-8253180dfddb","s2":"4081304f-ec88-5900-b577-1bd2bb35fedd","s3":"0a7a2121-3c55-5126-b58b-7cadf9f45d72","s4":"da93ca09-cc13-5f11-81da-e797c36cefe3","s5":"0cd7c212-77b6-569f-9b56-0f107bec6d3c","s6":"fe7d5cea-c0f4-5f0d-a208-52f7de824fa1"},"source_file":"datacenters/projects/herbata-naas.json","source_record_id":"herbata-naas","source_record_sha256":"29b656bc7d083a6924175ee16b7bfaa8b3a4ca4c4859a471e7907432dc262ac6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"73ff476080154154700912d847ba718a795f983505a7b6347ee8a344a6cc4570"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d1b09eaeac654b3c56f6/#project-2a418e82-60a0-52bf-ac57-8e0e3d3eabdb | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2a418e82-60a0-52bf-ac57-8e0e3d3eabdb.json
2b520cfa-8aea-5212-9b60-8ff417ee6578 | imported:semiconductor-atlas:compass-meridian-mississippi | vcc-site-4c3f2c7b887170cea7c1 | imported:semiconductor-atlas:compass-meridian-mississippi | Compass Datacenters Meridian campus | United States | US | 32.3747 | -88.7042 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Meridian. Compass places the campus in the Meridian I-20/59 Industrial Park; no cited source gives site coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3b11e0f1-1a48-542b-9b5c-c681ae6ed732 | under_construction | 2026-10-09 | 4 | imported_documented_status | a9095004-9c5e-5929-a366-d8ece83e55c5 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3b11e0f1-1a48-542b-9b5c-c681ae6ed732","notes":null,"party":"Compass Datacenters","relationship_scope":"unknown","role":"developer","source_record_id":"compass-meridian-mississippi"},{"evidence_id":"a9095004-9c5e-5929-a366-d8ece83e55c5","notes":null,"party":"Compass Datacenters","relationship_scope":"unknown","role":"developer","source_record_id":"compass-meridian-mississippi"},{"evidence_id":"3b11e0f1-1a48-542b-9b5c-c681ae6ed732","notes":"Supplying power and invested in a substation for the industrial park.","party":"Mississippi Power","relationship_scope":"unknown","role":"utility","source_record_id":"compass-meridian-mississippi"},{"evidence_id":"3b11e0f1-1a48-542b-9b5c-c681ae6ed732","notes":"Assisting with site preparation and certifying Compass for state data center tax exemptions.","party":"Mississippi Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"compass-meridian-mississippi"},{"evidence_id":"3b11e0f1-1a48-542b-9b5c-c681ae6ed732","notes":"Obtained a state site grant for the industrial park.","party":"Lauderdale County","relationship_scope":"unknown","role":"government","source_record_id":"compass-meridian-mississippi"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.compassdatacenters.com/data-center-markets/ | https://www.compassdatacenters.com/news/compass-10b-investment-lauderdale-county-mississippi/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Compass Datacenters Meridian campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"compass-meridian-mississippi"},"record":{"aliases":["Compass Lauderdale County campus"],"id":"compass-meridian-mississippi","last_reviewed":"2026-10-09","location":{"admin1":"Mississippi","admin2":"Lauderdale County","country":"US","lat":32.3747,"locality":"Meridian","lon":-88.7042,"note":"Wikipedia coordinates for Meridian. Compass places the campus in the Meridian I-20/59 Industrial Park; no cited source gives site coordinates.","precision":"locality","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2025-01-09","basis":"announced","metric":"investment","note":"Value at full fit-out, including future tenants' IT equipment.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2025-01-09","basis":"planned","metric":"power_capacity","note":"Power that Mississippi Power will supply to the facility, per the announcement.","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Figure on Compass's undated markets page as viewed on the access date; it is lower than the roughly 500 MW in the announcement and the page does not say which measure it uses.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":320},{"applies_to":"campus","as_of":"2025-01-09","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1"],"unit":"count","value":8}],"milestones":[{"date":"2025-01-09","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025","event":"construction_started","kind":"actual","source_ids":["s2"]}],"name":"Compass Datacenters Meridian campus","notes":"Status rests on Compass's undated markets page, viewed on 2026-10-09, which says the Meridian site broke ground in 2025; no dated construction update was found.","parties":[{"name":"Compass Datacenters","role":"developer","source_ids":["s1","s2"]},{"name":"Mississippi Power","note":"Supplying power and invested in a substation for the industrial park.","role":"utility","source_ids":["s1"]},{"name":"Mississippi Development Authority","note":"Assisting with site preparation and certifying Compass for state data center tax exemptions.","role":"government","source_ids":["s1"]},{"name":"Lauderdale County","note":"Obtained a state site grant for the industrial park.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Supply from Mississippi Power, which also invested in a substation serving the industrial park.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260908030331/https://www.compassdatacenters.com/news/compass-10b-investment-lauderdale-county-mississippi/","id":"s1","published":"2025-01-09","publisher":"Compass Datacenters","title":"Compass project generates $10 billion investment in Lauderdale County","type":"company","url":"https://www.compassdatacenters.com/news/compass-10b-investment-lauderdale-county-mississippi/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Compass Datacenters","title":"Data Center Markets - Compass Datacenters","type":"company","url":"https://www.compassdatacenters.com/data-center-markets/"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s2"],"summary":"Compass Datacenters is developing a single-tenant hyperscale campus of eight data centers in the Meridian I-20/59 Industrial Park in Meridian, Lauderdale County, Mississippi. Announced in January 2025 with Governor Tate Reeves, the project is valued at USD 10 billion at full fit-out including tenant IT equipment and is to be built over about eight years. Mississippi Power will supply about 500 MW and invested in a substation for the park, while the state granted tax exemptions and site support. Compass's market page now describes Meridian as a 320 MW site that broke ground in 2025."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3b11e0f1-1a48-542b-9b5c-c681ae6ed732","s2":"a9095004-9c5e-5929-a366-d8ece83e55c5"},"source_file":"datacenters/projects/compass-meridian-mississippi.json","source_record_id":"compass-meridian-mississippi","source_record_sha256":"a18df3f46fbdb7b6bbbba380d6ce88046afae5e7f7409b3cc456fe2a94fdb4c6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8a912593f9baab1d2ffa6c2d31b0051dfe27418b9f4236cdf8a31320ca63e2f2"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4c3f2c7b887170cea7c1/#project-2b520cfa-8aea-5212-9b60-8ff417ee6578 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2b520cfa-8aea-5212-9b60-8ff417ee6578.json
2bd78b04-9314-5aa8-ac32-ef30e111bc2e | imported:semiconductor-atlas:qts-cambois-blyth | vcc-site-ee33430200d597833ebe | curated:qts-cambois-data-centre-campus | QTS Cambois Data Centre Campus | United Kingdom | GB | 55.1453 | -1.5309 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the campus on the former Blyth Power Station site at Cambois. Nominatim did not return the power station site, so the Cambois village centroid is used. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | bd226832-56cd-5e1a-9507-a7e23cdf6777 | under_construction | 2026-08-06 | 68 | imported_documented_status | bd226832-56cd-5e1a-9507-a7e23cdf6777 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"bf9d3cb2-85aa-5ed1-b796-452102f90a21","notes":null,"party":"QTS","relationship_scope":"unknown","role":"developer","source_record_id":"qts-cambois-blyth"},{"evidence_id":"be702df2-d081-5b90-b9cd-f7293c1d6427","notes":null,"party":"QTS","relationship_scope":"unknown","role":"developer","source_record_id":"qts-cambois-blyth"},{"evidence_id":"bd226832-56cd-5e1a-9507-a7e23cdf6777","notes":null,"party":"QTS","relationship_scope":"unknown","role":"developer","source_record_id":"qts-cambois-blyth"},{"evidence_id":"bd226832-56cd-5e1a-9507-a7e23cdf6777","notes":null,"party":"QTS","relationship_scope":"unknown","role":"operator","source_record_id":"qts-cambois-blyth"},{"evidence_id":"bf9d3cb2-85aa-5ed1-b796-452102f90a21","notes":"Owner of QTS; the UK government credited Blackstone funds with a projected GBP 10bn investment in the campus.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"qts-cambois-blyth"},{"evidence_id":"16c9db8a-3405-5535-8a99-032f92fc323e","notes":"Owner of QTS; the UK government credited Blackstone funds with a projected GBP 10bn investment in the campus.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"qts-cambois-blyth"},{"evidence_id":"bd226832-56cd-5e1a-9507-a7e23cdf6777","notes":"Blackstone-owned entity described as financing the project.","party":"Renaissance Land","relationship_scope":"unknown","role":"investor","source_record_id":"qts-cambois-blyth"},{"evidence_id":"aacb5e2e-7b84-5bb4-82a5-6899ad1f0080","notes":"Ground improvement and piling subcontractor for data centres one and two.","party":"Keller","relationship_scope":"unknown","role":"builder","source_record_id":"qts-cambois-blyth"},{"evidence_id":"bf9d3cb2-85aa-5ed1-b796-452102f90a21","notes":"Planning authority.","party":"Northumberland County Council","relationship_scope":"unknown","role":"government","source_record_id":"qts-cambois-blyth"},{"evidence_id":"4ab43094-1e98-5c84-b6f1-65d54de480d3","notes":"Planning authority.","party":"Northumberland County Council","relationship_scope":"unknown","role":"government","source_record_id":"qts-cambois-blyth"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | QTS |  |  |  | https://www.placenortheast.co.uk/qts-doubles-down-as-openai-pauses-north-east-data-centre-ambitions/ | https://www.placenortheast.co.uk/qts-doubles-down-as-openai-pauses-north-east-data-centre-ambitions/ | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same QTS former Blyth Power Station campus. Source covers ten-building campus with initial two-building works; existing record selects 2026 earthworks. TBC Partners Factory Road proposal is explicitly nearby and separate.","source_record_id":"qts-cambois-blyth","source_relations":[{"reason":"TBC proposal on Factory Road is explicitly described as near the QTS former power-station campus; identical Cambois centroid is administrative only.","relationship":"separate_nearby_campuses","source_id":"tbc-partners-cambois"}],"target_physical_site_stable_key":"curated:qts-cambois-data-centre-campus"},"record":{"aliases":["Project Wind","Blackstone Northumberland data centre","QTS Cambois"],"id":"qts-cambois-blyth","last_reviewed":"2026-10-09","location":{"admin1":"England","admin2":"Northumberland","country":"GB","lat":55.1453,"locality":"Cambois","lon":-1.5309,"note":"Sources place the campus on the former Blyth Power Station site at Cambois. Nominatim did not return the power station site, so the Cambois village centroid is used.","precision":"locality","source_ids":["s6","s8"]},"metrics":[{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"power_capacity","note":"Architect Corgan lists 720 MW, with each of ten buildings providing 72 MW of IT capacity. Data Centre Review also reports about 720 MW across ten facilities if fully built, without stating scope; W.Media's description of phase one as two 720 MW facilities conflicts with both and is not recorded.","power_scope":"it_load","qualifier":"exact","source_ids":["s5"],"unit":"MW","value":720},{"applies_to":"campus","as_of":"2025-03-05","basis":"announced","metric":"investment","note":"Some sources give GBP 10bn without 'up to'; the UK government describes it as projected investment by Blackstone funds.","qualifier":"up_to","source_ids":["s1","s2","s3","s7"],"unit":"GBP","value":10000000000},{"applies_to":"campus","as_of":"2025-03-05","basis":"planned","metric":"floor_area","qualifier":"up_to","source_ids":["s1","s2","s5"],"unit":"sq_m","value":540000},{"applies_to":"campus","as_of":"2026","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s5"],"unit":"hectares","value":100},{"applies_to":"campus","as_of":"2026-08-06","basis":"reported","metric":"land_area","note":"Keller's description of the site; differs slightly from Corgan's 100 hectares.","qualifier":"more_than","source_ids":["s8"],"unit":"acres","value":133},{"applies_to":"campus","as_of":"2026-08-06","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s5","s8"],"unit":"count","value":10},{"applies_to":"phase","as_of":"2026-08-06","basis":"under_construction","metric":"buildings","note":"Reserved matters approved in December 2025 for the first two buildings; ground improvement for data centres one and two under way in August 2026.","phase_label":"Phase one","qualifier":"exact","source_ids":["s6","s8"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2025-08-27","basis":"planned","metric":"jobs_construction","note":"Described as construction jobs over several years; the March 2025 report gave more than 1,000.","qualifier":"exact","source_ids":["s2"],"unit":"count","value":1200}],"milestones":[{"date":"2025-03","event":"zoning_approved","kind":"actual","note":"Northumberland County Council approved the planning application for the campus.","source_ids":["s1"]},{"date":"2025-08","event":"permit_approved","kind":"actual","note":"Approval reported for preparatory works such as a site compound, vegetation clearance and earthworks.","source_ids":["s2"]},{"date":"2025-09-16","event":"other","kind":"actual","note":"UK government release quoted Blackstone saying its Northumberland campus had been designated an AI Growth Zone.","source_ids":["s3"]},{"date":"2025-10","event":"construction_started","kind":"actual","note":"Trade press reports that construction began in October 2025, after the August approval.","source_ids":["s4"]},{"date":"2025-12-02","event":"zoning_approved","kind":"actual","note":"Council approval of reserved matters for phase one, covering the first two buildings.","source_ids":["s4","s6"]},{"date":"2026-08","event":"other","kind":"actual","note":"Ground improvement with vibro stone columns and CFA piles for data centres one and two was under way, due to finish later in August 2026.","source_ids":["s8"]},{"date":"2028","event":"first_operational","kind":"planned","note":"Corgan says phase one is projected to open in early 2028.","source_ids":["s5"]},{"date":"2035","event":"fully_operational","kind":"planned","note":"Campus completion and tenant onboarding expected by 2035.","source_ids":["s5"]}],"name":"QTS Cambois Data Centre Campus","parties":[{"name":"QTS","role":"developer","source_ids":["s1","s2","s6"]},{"name":"QTS","role":"operator","source_ids":["s6"]},{"name":"Blackstone","note":"Owner of QTS; the UK government credited Blackstone funds with a projected GBP 10bn investment in the campus.","role":"investor","source_ids":["s1","s3"]},{"name":"Renaissance Land","note":"Blackstone-owned entity described as financing the project.","role":"investor","source_ids":["s6"]},{"name":"Keller","note":"Ground improvement and piling subcontractor for data centres one and two.","role":"builder","source_ids":["s8"]},{"name":"Northumberland County Council","note":"Planning authority.","role":"government","source_ids":["s1","s4"]}],"power_sources":[],"related_ids":["tbc-partners-cambois"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250724125702/https://www.uktech.news/big-data/northumberland-council-approves-plans-for-10bn-data-centre-20250305","id":"s1","published":"2025-03-05","publisher":"UKTN","title":"Northumberland Council approves plans for £10bn data centre","type":"news","url":"https://www.uktech.news/big-data/northumberland-council-approves-plans-for-10bn-data-centre-20250305"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260309001235/https://www.acenet.co.uk/news/infrastructure-intelligence/new-milestone-reached-on-10bn-data-centre-project/","id":"s2","published":"2025-08-27","publisher":"ACE Infrastructure Intelligence","title":"New milestone reached on £10bn data centre project","type":"trade_press","url":"https://www.acenet.co.uk/news/infrastructure-intelligence/new-milestone-reached-on-10bn-data-centre-project/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003180409/https://www.gov.uk/government/news/us-uk-pact-will-boost-advances-in-drug-discovery-create-tens-of-thousands-of-jobs-and-transform-lives","id":"s3","published":"2025-09-16","publisher":"UK Government","title":"US-UK pact will boost advances in drug discovery, create tens of thousands of jobs and transform lives","type":"government","url":"https://www.gov.uk/government/news/us-uk-pact-will-boost-advances-in-drug-discovery-create-tens-of-thousands-of-jobs-and-transform-lives"},{"accessed":"2026-10-09","id":"s4","published":"2025-12-09","publisher":"W.Media","title":"QTS gained approval for data center project in Northumbria","type":"trade_press","url":"https://w.media/qts-gained-approval-for-data-center-project-in-northumbria/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Corgan","title":"QTS Data Center Campus Cambois","type":"company","url":"https://www.corgan.com/projects/qts-data-center-campus-cambois"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260521014552/https://www.placenortheast.co.uk/qts-doubles-down-as-openai-pauses-north-east-data-centre-ambitions/","id":"s6","published":"2026-04-13","publisher":"Place North East","title":"QTS doubles down as OpenAI pauses North East data centre ambitions","type":"news","url":"https://www.placenortheast.co.uk/qts-doubles-down-as-openai-pauses-north-east-data-centre-ambitions/"},{"accessed":"2026-10-09","id":"s7","published":"2026-04-14","publisher":"Data Centre Review","title":"QTS reaffirms commitment to North East AI Growth Zone","type":"trade_press","url":"https://datacentrereview.com/2026/04/qts-reaffirms-commitment-to-north-east-ai-growth-zone/"},{"accessed":"2026-10-09","id":"s8","published":"2026-08-06","publisher":"Keller","title":"Keller lays foundations for huge data centre","type":"company","url":"https://www.keller.co.uk/news/keller-lays-foundations-huge-data-centre"}],"status":"under_construction","status_as_of":"2026-08-06","status_source_ids":["s6","s8"],"summary":"QTS, the Blackstone-owned data centre company, is building its first UK campus on the former Blyth Power Station site at Cambois, Northumberland, with up to GBP 10bn of investment. Plans cover ten three-storey buildings and up to 540,000 square metres, with the architect citing 720 MW of IT capacity. Northumberland County Council approved the scheme in March 2025 and phase-one reserved matters for the first two buildings in December 2025. Work on site began in October 2025, and ground improvement for the first two data centres was under way in August 2026. The site sits in the UK's North East AI Growth Zone.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"bf9d3cb2-85aa-5ed1-b796-452102f90a21","s2":"be702df2-d081-5b90-b9cd-f7293c1d6427","s3":"16c9db8a-3405-5535-8a99-032f92fc323e","s4":"4ab43094-1e98-5c84-b6f1-65d54de480d3","s5":"32ac4772-10ce-539c-88d9-4d419bff74ef","s6":"bd226832-56cd-5e1a-9507-a7e23cdf6777","s7":"7ae4db6e-53eb-5962-afbc-9bc4bf691a04","s8":"aacb5e2e-7b84-5bb4-82a5-6899ad1f0080"},"source_file":"datacenters/projects/qts-cambois-blyth.json","source_record_id":"qts-cambois-blyth","source_record_sha256":"0b723f64ffa9d6efd917b3e9c656e1369d367d1a946f7568d998ed9ce8cd7927","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"102e9f9c4b02ce10721d3e1dbe44c28f322f748aa97e3b9459eece88dc34d64c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ee33430200d597833ebe/#project-2bd78b04-9314-5aa8-ac32-ef30e111bc2e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2bd78b04-9314-5aa8-ac32-ef30e111bc2e.json
2c24f89f-37e6-5164-a240-e1e3d2fca176 | imported:semiconductor-atlas:bridge-my07-ulu-tiram | vcc-site-9d88c072bfebf964cf3a | imported:semiconductor-atlas:bridge-my07-ulu-tiram | Bridge Data Centres MY07, Ulu Tiram | Malaysia | MY | 1.6 | 103.8203 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Ulu Tiram without an address; the point is the Ulu Tiram coordinate from its Wikipedia article, so it marks the town rather than the campus. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 44239b30-48b7-5964-b6e5-4f77ff0ac125 | partially_operational | 2026-09-02 | 41 | imported_documented_status | 7b6f5862-19eb-59cd-ac99-93063dae403f | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"44239b30-48b7-5964-b6e5-4f77ff0ac125","notes":"Bain Capital-backed hyperscale data center platform.","party":"Bridge Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-my07-ulu-tiram"},{"evidence_id":"a1de69ea-ac9e-5654-b6b5-7281f944b13e","notes":"Bain Capital-backed hyperscale data center platform.","party":"Bridge Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-my07-ulu-tiram"},{"evidence_id":"7b6f5862-19eb-59cd-ac99-93063dae403f","notes":null,"party":"Bridge Data Centres","relationship_scope":"unknown","role":"operator","source_record_id":"bridge-my07-ulu-tiram"},{"evidence_id":"44239b30-48b7-5964-b6e5-4f77ff0ac125","notes":"Signed the MY07 electricity supply agreement; its subsidiary TNB Renewables drove the deal.","party":"Tenaga Nasional Berhad","relationship_scope":"unknown","role":"utility","source_record_id":"bridge-my07-ulu-tiram"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Bridge Data Centres |  |  |  | https://www.bridgedatacentres.com/building-malaysias-digital-future/ | https://equalocean.com/news/2025010221264-bridge-data-centres-tnb-sign-my07-400mw-agreement-green-energy-partnership | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bridge Data Centres MY07, Ulu Tiram as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"bridge-my07-ulu-tiram"},"record":{"aliases":["BDC MY07","Dragonfly MY07"],"id":"bridge-my07-ulu-tiram","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Johor Bahru District","country":"MY","lat":1.6,"locality":"Ulu Tiram","lon":103.8203,"note":"Sources name Ulu Tiram without an address; the point is the Ulu Tiram coordinate from its Wikipedia article, so it marks the town rather than the campus.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-01-02","basis":"contracted","metric":"power_capacity","note":"Electricity secured under the TNB supply agreement, per the article headline and the Baxtel listing; the article body does not restate the figure.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s4"],"unit":"MW","value":400},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total IT capacity listed for MY07 on Bridge's undated Malaysia locations page; the page does not say how much is built.","power_scope":"it_load","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":374},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s2"],"unit":"count","value":8},{"applies_to":"campus","as_of":"2026-09-02","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":65}],"milestones":[{"date":"2025-01-02","event":"other","kind":"actual","note":"Electricity supply agreement with TNB signed, including head of terms for a bilateral energy supply contract under the corporate renewable energy supply scheme; TNB called it its fastest supply agreement delivery.","source_ids":["s1"]}],"name":"Bridge Data Centres MY07, Ulu Tiram","notes":"Status is partially_operational because Bridge's September 2026 staff profile describes MY07 running mission-critical operations that customers depend on, with a 120-plus operations team and around-the-clock cooling water supply, but gives no go-live date or share of the listed 374 MW and eight buildings in service; the undated Baxtel directory listing still shows the site as under construction with 2027 as its planned year. Cooling water comes from a campus treatment plant that recycles treated effluent from Indah Water Konsortium, per Bridge. Bridge's separate Plentong land purchase and the Southville City plan are different projects. Wikipedia is cited only for the town coordinate.","parties":[{"name":"Bridge Data Centres","note":"Bain Capital-backed hyperscale data center platform.","role":"developer","source_ids":["s1","s2"]},{"name":"Bridge Data Centres","role":"operator","source_ids":["s3"]},{"name":"Tenaga Nasional Berhad","note":"Signed the MY07 electricity supply agreement; its subsidiary TNB Renewables drove the deal.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Supply from Tenaga Nasional through a 275 kV intake, under an electricity supply agreement reported at 400 MW.","source_ids":["s1","s2"],"type":"grid"},{"description":"Head of terms for a bilateral renewable energy supply contract under TNB's Corporate Renewable Energy Supply Scheme, for which Bridge was the first partner; the generation technology is not stated.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-01-02","publisher":"EqualOcean","title":"Bridge Data Centres, TNB Sign MY07 400MW Agreement and Green Energy Partnership","type":"news","url":"https://equalocean.com/news/2025010221264-bridge-data-centres-tnb-sign-my07-400mw-agreement-green-energy-partnership"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260609083542/https://www.bridgedatacentres.com/locations/malaysia/","id":"s2","published":null,"publisher":"Bridge Data Centres","title":"Malaysia locations","type":"company","url":"https://www.bridgedatacentres.com/locations/malaysia/"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-02","publisher":"Bridge Data Centres","title":"Building Malaysia's Digital Future","type":"company","url":"https://www.bridgedatacentres.com/building-malaysias-digital-future/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260214062302/https://baxtel.com/data-center/bridge-johor-my07","id":"s4","published":null,"publisher":"Baxtel","title":"Bridge: Johor MY07","type":"other","url":"https://baxtel.com/data-center/bridge-johor-my07"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Ulu Tiram","type":"other","url":"https://en.wikipedia.org/wiki/Ulu_Tiram"}],"status":"partially_operational","status_as_of":"2026-09-02","status_source_ids":["s3"],"summary":"Bridge Data Centres' MY07 is a 65-acre hyperscale campus in Ulu Tiram, Johor Bahru District. In January 2025, while it was under construction, Bridge signed an electricity supply agreement with Tenaga Nasional for the site, reported at 400 MW, and became the first partner in TNB's corporate renewable energy supply scheme. Bridge lists MY07 at 374 MW of IT capacity across eight buildings. A September 2026 Bridge article describes a campus operations team of more than 120 keeping customer-facing services running, with cooling water recycled from treated effluent rather than drawn from potable supply.","workloads":["colocation","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"44239b30-48b7-5964-b6e5-4f77ff0ac125","s2":"a1de69ea-ac9e-5654-b6b5-7281f944b13e","s3":"7b6f5862-19eb-59cd-ac99-93063dae403f","s4":"4d42ad3b-64db-5c9a-81a1-03d0fa3e652e","s5":"2d648f1e-7c80-5940-a12f-d4773dea2219"},"source_file":"datacenters/projects/bridge-my07-ulu-tiram.json","source_record_id":"bridge-my07-ulu-tiram","source_record_sha256":"fda31697d9ade5ca3619d910cdecda07562b9dd09cef4c65a48d67a3aa1b507c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1cb93221f01bff0430124f313930a046c9a4d8ccc8a17ae9743d98f8c33a300c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9d88c072bfebf964cf3a/#project-2c24f89f-37e6-5164-a240-e1e3d2fca176 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2c24f89f-37e6-5164-a240-e1e3d2fca176.json
2c3a5bbe-3573-5abe-98dc-8d8312b0a586 | curated:bulk-n01-vennesla-campus:current-new-facility-construction | vcc-site-5565cfa2824c955c2f04 | curated:bulk-n01-vennesla-campus | Bulk N01 Current New Facility Construction | Norway | NO | 58.2576 | 7.8921 | Point | campus | source_attribute_decimal_coordinates_to_point_without_centroiding | first_party_schema_org_geocoordinates_literal_point | official_operator_published_campus_reference_point | official_source | campus_locator | Campus reference point only, associated by canonical site URL and postal address. The new construction project is on this campus but is not asserted at the exact point. No parcel boundary, work footprint, surveyed entrance or quantified accuracy is claimed. |  | Publisher supplies no positional accuracy. Decimal precision and supporting map containment do not establish survey accuracy. | 93cbb7f5-e70d-5fff-ae18-d5c9cc25404d | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 48f4cf2e-4c8a-5291-920f-62ea8f8e1761 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://bulkinfrastructure.com/uploads/Financial-report/Quarterly-Report/Bulk-Infrastructure-Group-Financial-statements-Q2-2026.pdf | https://bulkinfrastructure.com/data-centers/locations/n01 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5565cfa2824c955c2f04/#project-2c3a5bbe-3573-5abe-98dc-8d8312b0a586 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2c3a5bbe-3573-5abe-98dc-8d8312b0a586.json
2cac8eb7-dff6-50bc-be49-b45f6e353982 | curated:ascenty-vinhedo-campus:vinhedo-3 | vcc-site-29c7aa69cf49aaa11516 | curated:ascenty-vinhedo-campus | Ascenty Vinhedo 3 | Brazil | BR | -23.0702 | -47.013 | Point | campus | coordinates_to_point | first_party_published_coordinate | named_constituent_facility_point | official_source | campus_locator | Exact publisher coordinate for VIN02, used only as a broad Vinhedo campus locator for Vinhedo 3; not Vinhedo 3 parcel, building, or work footprint. |  | The factsheet does not state coordinate accuracy. | 2184bacc-e338-5f73-bb78-327e08fc392a | under_construction | 2026-05-28 | 138 | authoritative_physical_status_update | 2b138f72-e7f8-560c-8f63-0cbe196b245e | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ascenty.com/en/blog/news-ascenty-en/ascenty-ai-contracts/ | https://ascenty.com/wp-content/uploads/2025/02/EN-Campus-Vinhedo_compressed.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-29c7aa69cf49aaa11516/#project-2cac8eb7-dff6-50bc-be49-b45f6e353982 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2cac8eb7-dff6-50bc-be49-b45f6e353982.json
2cb7333c-d029-5457-baf2-346f48e7fb26 | imported:semiconductor-atlas:aws-clinton-hinds-county-mississippi | vcc-site-0819a764e96ce06f14c6 | imported:semiconductor-atlas:aws-clinton-hinds-county-mississippi | AWS Clinton data center (former Delphi plant) | United States | US | 32.3583 | -90.3556 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Clinton city point from its Wikipedia article (Nominatim was unavailable). One local TV report places the site on Industrial Park Drive but calls it the former Milwaukee Tool factory, which conflicts with the Delphi identification, so no site point is used. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 4e31a439-2221-535f-a651-5f280bc2ed4a | operational | 2026-06-09 | 126 | imported_documented_status | 9daafbcd-4faf-5a9a-879d-aaf347f8bf2c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"4e31a439-2221-535f-a651-5f280bc2ed4a","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-clinton-hinds-county-mississippi"},{"evidence_id":"6f34ad16-895c-5061-9608-572c75e97acc","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-clinton-hinds-county-mississippi"},{"evidence_id":"4e31a439-2221-535f-a651-5f280bc2ed4a","notes":"Co-hosted the June 2026 ribbon-cutting; the governor's release lists Hinds County and the City of Clinton among those assisting the project.","party":"Hinds County Economic Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"aws-clinton-hinds-county-mississippi"},{"evidence_id":"9daafbcd-4faf-5a9a-879d-aaf347f8bf2c","notes":"Co-hosted the June 2026 ribbon-cutting; the governor's release lists Hinds County and the City of Clinton among those assisting the project.","party":"Hinds County Economic Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"aws-clinton-hinds-county-mississippi"},{"evidence_id":"4e31a439-2221-535f-a651-5f280bc2ed4a","notes":null,"party":"City of Clinton","relationship_scope":"unknown","role":"government","source_record_id":"aws-clinton-hinds-county-mississippi"},{"evidence_id":"9daafbcd-4faf-5a9a-879d-aaf347f8bf2c","notes":null,"party":"City of Clinton","relationship_scope":"unknown","role":"government","source_record_id":"aws-clinton-hinds-county-mississippi"},{"evidence_id":"4e31a439-2221-535f-a651-5f280bc2ed4a","notes":"Named for its commitment to Amazon's long-term Mississippi power needs; the release does not single out this site.","party":"Entergy Mississippi","relationship_scope":"unknown","role":"utility","source_record_id":"aws-clinton-hinds-county-mississippi"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.aboutamazon.com/news/aws/amazon-data-centers-locations-news | https://governorreeves.ms.gov/amazon-continues-mississippi-expansion-announcing-plans-to-invest-a-total-of-25-billion-across-the-magnolia-state/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AWS Clinton data center (former Delphi plant) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"aws-clinton-hinds-county-mississippi"},"record":{"aliases":["AWS Hinds County data center"],"id":"aws-clinton-hinds-county-mississippi","last_reviewed":"2026-10-09","location":{"admin1":"Mississippi","admin2":"Hinds County","country":"US","lat":32.3583,"locality":"Clinton","lon":-90.3556,"note":"Coordinates are the Clinton city point from its Wikipedia article (Nominatim was unavailable). One local TV report places the site on Industrial Park Drive but calls it the former Milwaukee Tool factory, which conflicts with the Delphi identification, so no site point is used.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-09","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2026-06-09","basis":"planned","metric":"jobs_permanent","qualifier":"at_least","source_ids":["s1","s4"],"unit":"count","value":100}],"milestones":[{"date":"2026-04-09","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2026-06-09","event":"other","kind":"actual","note":"Ribbon-cutting held to celebrate the investment and jobs; Amazon's post describes the plant as fully retrofitted into a functioning data center but gives no in-service date.","source_ids":["s4"]}],"name":"AWS Clinton data center (former Delphi plant)","notes":"Site identity conflict: the governor's release and Amazon describe the building as the former Delphi plant, while an April 2026 local TV report calls it the former Milwaukee Tool factory on Industrial Park Drive. Status: Amazon's June 2026 post says the plant was fully retrofitted into a functioning data center, but the same post frames the ribbon-cutting as celebrating the investment and job creation and gives no in-service date or operating capacity, so the operational status rests on that one statement.","parties":[{"name":"Amazon Web Services","role":"developer","source_ids":["s1","s3"]},{"name":"Hinds County Economic Development Authority","note":"Co-hosted the June 2026 ribbon-cutting; the governor's release lists Hinds County and the City of Clinton among those assisting the project.","role":"government","source_ids":["s1","s4"]},{"name":"City of Clinton","role":"government","source_ids":["s1","s4"]},{"name":"Entergy Mississippi","note":"Named for its commitment to Amazon's long-term Mississippi power needs; the release does not single out this site.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"The Clinton mayor said day-to-day power will come from the grid, with backup generators on site; the city amended its noise ordinance in October 2025 so such generators can run uninterrupted during emergencies.","source_ids":["s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-04-09","publisher":"Office of Governor Tate Reeves","title":"Amazon continues Mississippi expansion, announcing plans to invest a total of $25 billion across the Magnolia State","type":"government","url":"https://governorreeves.ms.gov/amazon-continues-mississippi-expansion-announcing-plans-to-invest-a-total-of-25-billion-across-the-magnolia-state/"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-09","publisher":"WLOX","title":"'2,000 new jobs right here in Mississippi': Gov. Reeves $12B more in investments from AWS","type":"news","url":"https://www.wlox.com/2026/04/09/gov-reeves-local-leaders-announce-amazons-plans-invest-25-billion-across-mississippi/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Amazon","title":"Amazon plans to invest $25 billion in Mississippi data centers, create 2,000 jobs","type":"company","url":"https://www.aboutamazon.com/news/company-news/amazon-25-billion-mississippi-data-centers"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Amazon","title":"Amazon data center communities: Here's what's happening near data centers across the US","type":"company","url":"https://www.aboutamazon.com/news/aws/amazon-data-centers-locations-news"},{"accessed":"2026-10-09","id":"s5","published":"2026-04-10","publisher":"Mississippi Free Press","title":"Amazon Is Expanding Data Centers in Central Mississippi, Governor Announces","type":"news","url":"https://www.mississippifreepress.org/amazon-is-expanding-data-centers-in-central-mississippi-governor-announces/"}],"status":"operational","status_as_of":"2026-06-09","status_source_ids":["s4"],"summary":"Amazon is converting the former Delphi Packard plant in Clinton, Hinds County, into a data center. The governor announced the $1 billion project in April 2026 with about 100 jobs; Amazon says the plant closed in 2009 and then sat empty for years. At a June 2026 ribbon-cutting held to mark the investment, Amazon said this was its first full retrofit of an existing industrial building into a functioning data center, but it gave no in-service date or capacity. AWS says the site will use no water, and the mayor says day-to-day power will come from the grid."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"4e31a439-2221-535f-a651-5f280bc2ed4a","s2":"689f9c56-0c83-5353-bc56-815f686aec86","s3":"6f34ad16-895c-5061-9608-572c75e97acc","s4":"9daafbcd-4faf-5a9a-879d-aaf347f8bf2c","s5":"84d27eb6-3914-5ffc-9c97-db899da76603"},"source_file":"datacenters/projects/aws-clinton-hinds-county-mississippi.json","source_record_id":"aws-clinton-hinds-county-mississippi","source_record_sha256":"8eb46d8108a32ed34e39b0128dbf80b172ace9308707bb8095296f6aeeac0bb3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"197d305dbb364c7d07b35ffedf1a982ef5ce5ce6f55bd1ad9f80480fb7a264b7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0819a764e96ce06f14c6/#project-2cb7333c-d029-5457-baf2-346f48e7fb26 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2cb7333c-d029-5457-baf2-346f48e7fb26.json
2d2dbfa9-0685-5532-8d89-80ceeaf07427 | imported:semiconductor-atlas:ytl-kulai-johor | vcc-site-ebacb890726508925a40 | imported:semiconductor-atlas:ytl-kulai-johor | YTL Green Data Center Park, Kulai | Malaysia | MY | 1.6569 | 103.6059 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the park in Kulai, Johor, about 30 km from Johor Bahru, without an address; coordinates are the OpenStreetMap Nominatim point for Kulai town. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | afe4b6ea-54ab-594d-ad5e-94b2a01dea6d | partially_operational | 2026-08-20 | 54 | imported_documented_status | b87076e6-422a-54dd-ac3e-47d05f758a83 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"afe4b6ea-54ab-594d-ad5e-94b2a01dea6d","notes":null,"party":"YTL Power International Berhad","relationship_scope":"unknown","role":"developer","source_record_id":"ytl-kulai-johor"},{"evidence_id":"8f72e488-1715-59d5-8ee8-8841ba33c302","notes":null,"party":"YTL Power International Berhad","relationship_scope":"unknown","role":"developer","source_record_id":"ytl-kulai-johor"},{"evidence_id":"88551c95-090e-5107-992d-d05476e11fca","notes":null,"party":"YTL Power International Berhad","relationship_scope":"unknown","role":"developer","source_record_id":"ytl-kulai-johor"},{"evidence_id":"eae72e16-699e-5f85-b086-6c2f78c52f2e","notes":null,"party":"YTL Power International Berhad","relationship_scope":"unknown","role":"developer","source_record_id":"ytl-kulai-johor"},{"evidence_id":"afe4b6ea-54ab-594d-ad5e-94b2a01dea6d","notes":"Wholly owned YTL Power subsidiary described as the initiator of the park.","party":"YTL Data Center Holdings Pte. Ltd.","relationship_scope":"unknown","role":"developer","source_record_id":"ytl-kulai-johor"},{"evidence_id":"afe4b6ea-54ab-594d-ad5e-94b2a01dea6d","notes":"Signed a 2022 partnership to co-develop 168 MW across eight facilities at the park; later status of this arrangement was not found.","party":"GDS Holdings Limited","relationship_scope":"unknown","role":"developer","source_record_id":"ytl-kulai-johor"},{"evidence_id":"8f72e488-1715-59d5-8ee8-8841ba33c302","notes":"YTL's telecom subsidiary, named as owner and manager of the Nvidia-based AI infrastructure rather than of the whole park.","party":"YTL Communications Sdn Bhd","relationship_scope":"unknown","role":"operator","source_record_id":"ytl-kulai-johor"},{"evidence_id":"8f72e488-1715-59d5-8ee8-8841ba33c302","notes":"H100 GPUs were named in 2023; the AI data center reported operational in 2025 uses liquid-cooled GB200 NVL72 systems.","party":"Nvidia","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"ytl-kulai-johor"},{"evidence_id":"b87076e6-422a-54dd-ac3e-47d05f758a83","notes":"H100 GPUs were named in 2023; the AI data center reported operational in 2025 uses liquid-cooled GB200 NVL72 systems.","party":"Nvidia","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"ytl-kulai-johor"},{"evidence_id":"88551c95-090e-5107-992d-d05476e11fca","notes":"H100 GPUs were named in 2023; the AI data center reported operational in 2025 uses liquid-cooled GB200 NVL72 systems.","party":"Nvidia","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"ytl-kulai-johor"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | YTL Communications Sdn Bhd |  |  |  | https://api.edgeprop.my/content/1914263/ytl-power-completes-first-nvidia-powered-ai-data-centre-johor-ytl-ai-cloud-now-operational | https://www.sec.gov/Archives/edgar/data/1526125/000110465922062648/tm2215932d2_ex99-1.htm | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve YTL Green Data Center Park, Kulai as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"ytl-kulai-johor"},"record":{"aliases":["YTL Green Data Center Park","YTL AI Cloud Johor"],"id":"ytl-kulai-johor","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Kulai District","country":"MY","lat":1.6569,"locality":"Kulai","lon":103.6059,"note":"Sources place the park in Kulai, Johor, about 30 km from Johor Bahru, without an address; coordinates are the OpenStreetMap Nominatim point for Kulai town.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2023-12-08","basis":"planned","metric":"power_capacity","note":"Original description of the park as a 500 MW campus matched by an equivalent amount of on-site solar.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":500},{"applies_to":"phase","as_of":"2022-05-19","basis":"planned","metric":"power_capacity","phase_label":"GDS co-development (eight facilities)","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":168},{"applies_to":"campus","as_of":"2025-10-31","basis":"planned","metric":"power_capacity","note":"The Edge/EdgeProp refer to a 600 MW park; W.Media instead attaches 600 MW to backup grid supply, so the basis of this figure is unclear.","power_scope":"unspecified","qualifier":"exact","source_ids":["s3","s5"],"unit":"MW","value":600},{"applies_to":"campus","as_of":"2026-08-20","basis":"planned","metric":"power_capacity","note":"Planned increase of the Kulai park ceiling from 600 MW to 1,000 MW.","power_scope":"unspecified","qualifier":"exact","source_ids":["s5"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2025-11-03","basis":"under_construction","metric":"power_capacity","note":"YTL's managing director described 300 MW as being built and commissioned on the site.","power_scope":"unspecified","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-10-31","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s3","s4"],"unit":"acres","value":1640}],"milestones":[{"date":"2022-05","event":"other","kind":"actual","note":"GDS disclosed a recently signed partnership with YTL Power to co-develop data center capacity at the park, with the first phase expected in service in 2024.","source_ids":["s1"]},{"date":"2023-12-08","event":"other","kind":"actual","note":"YTL and Nvidia announced an AI infrastructure collaboration to be hosted at the park, with a first phase targeted for mid-2024.","source_ids":["s2"]},{"date":"2025-10-31","event":"other","kind":"actual","note":"YTL announced its Nvidia GB200-based AI data center at the park was complete and operational, with global hyperscalers among its customers.","source_ids":["s3","s4"]},{"date":"2026-08","event":"expansion_announced","kind":"actual","note":"Reported plan to raise the park's planned capacity from 600 MW to 1,000 MW.","source_ids":["s5"]}],"name":"YTL Green Data Center Park, Kulai","parties":[{"name":"YTL Power International Berhad","role":"developer","source_ids":["s1","s2","s4","s5"]},{"name":"YTL Data Center Holdings Pte. Ltd.","note":"Wholly owned YTL Power subsidiary described as the initiator of the park.","role":"developer","source_ids":["s1"]},{"name":"GDS Holdings Limited","note":"Signed a 2022 partnership to co-develop 168 MW across eight facilities at the park; later status of this arrangement was not found.","role":"developer","source_ids":["s1"]},{"name":"YTL Communications Sdn Bhd","note":"YTL's telecom subsidiary, named as owner and manager of the Nvidia-based AI infrastructure rather than of the whole park.","role":"operator","source_ids":["s2"]},{"name":"Nvidia","note":"H100 GPUs were named in 2023; the AI data center reported operational in 2025 uses liquid-cooled GB200 NVL72 systems.","role":"hardware_supplier","source_ids":["s2","s3","s4"]}],"power_sources":[{"description":"A solar plant of about 500 MW supplies the park; earlier plans paired data center capacity with an equal amount of on-site solar.","source_ids":["s1","s2","s3","s4"],"type":"solar"},{"description":"About 600 MW of backup supply from the national grid, per W.Media.","source_ids":["s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2022-05-19","publisher":"GDS Holdings Limited (SEC Form 6-K exhibit)","title":"GDS Holdings Limited Reports First Quarter 2022 Results","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1526125/000110465922062648/tm2215932d2_ex99-1.htm"},{"accessed":"2026-10-09","id":"s2","published":"2023-12-08","publisher":"YTL Power International Berhad","title":"YTL to Advance AI Development in Malaysia in Collaboration with NVIDIA","type":"company","url":"https://www.ytlpowerinternational.com/press-releases/ytl-to-advance-ai-development-in-malaysia-in-collaboration-with-nvidia/"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-31","publisher":"EdgeProp Malaysia (The Edge)","title":"YTL Power completes first Nvidia-powered AI data centre in Johor, YTL AI Cloud now operational","type":"news","url":"https://api.edgeprop.my/content/1914263/ytl-power-completes-first-nvidia-powered-ai-data-centre-johor-ytl-ai-cloud-now-operational"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260928115216/https://w.media/ytl-power-completes-nvidia-powered-ai-data-centre-in-johor/","id":"s4","published":"2025-11-03","publisher":"W.Media","title":"YTL Power completes Nvidia-powered AI data centre in Johor","type":"trade_press","url":"https://w.media/ytl-power-completes-nvidia-powered-ai-data-centre-in-johor/"},{"accessed":"2026-10-09","id":"s5","published":"2026-08-20","publisher":"EdgeProp Malaysia (The Edge)","title":"YTL Power to develop new gigawatt data centre campus in Johor","type":"news","url":"https://www.edgeprop.my/content/1917178/ytl-power-develop-new-gigawatt-data-centre-campus-johor"}],"status":"partially_operational","status_as_of":"2026-08-20","status_source_ids":["s3","s4","s5"],"summary":"YTL Power International is developing a large data center park in Kulai, Johor, paired with a solar plant of about 500 MW and backup supply from the national grid. The park was first described as a 500 MW campus; GDS agreed in 2022 to co-develop part of it, and YTL announced an AI infrastructure collaboration with Nvidia in December 2023. YTL said in late 2025 that an Nvidia GB200-based AI data center at the park was operational, with about 300 MW being built and commissioned. In August 2026 it was reported to be bringing capacity online progressively and planning to raise the park's ceiling from 600 MW to 1,000 MW.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"afe4b6ea-54ab-594d-ad5e-94b2a01dea6d","s2":"8f72e488-1715-59d5-8ee8-8841ba33c302","s3":"b87076e6-422a-54dd-ac3e-47d05f758a83","s4":"88551c95-090e-5107-992d-d05476e11fca","s5":"eae72e16-699e-5f85-b086-6c2f78c52f2e"},"source_file":"datacenters/projects/ytl-kulai-johor.json","source_record_id":"ytl-kulai-johor","source_record_sha256":"d2031468d637ccc17fcde6bd8ddbd8883b6d9bf2d63bbba0e1b88191bd48b375","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"143f9a74590e5c248f1f6a1d7693813daba34dd5514d624d001912588729e7bb"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ebacb890726508925a40/#project-2d2dbfa9-0685-5532-8d89-80ceeaf07427 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2d2dbfa9-0685-5532-8d89-80ceeaf07427.json
2e14f098-9798-567b-ae40-a7d552f9be18 | imported:semiconductor-atlas:terawulf-lake-hawkeye | vcc-site-a291a33ca480670cccf1 | imported:semiconductor-atlas:terawulf-lake-hawkeye | TeraWulf Lake Hawkeye data campus | United States | US | 42.5658 | -76.5319 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the site at the former Cayuga power plant in the town of Lansing without an address. Coordinates are the town point from the Lansing, New York Wikipedia article, not the plant site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 17da0c46-2546-5d53-b910-108e95100470 | announced | 2026-08-05 | 69 | imported_documented_status | 1da49023-dd86-5890-ad4c-a83551c3d516 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"17da0c46-2546-5d53-b910-108e95100470","notes":"Holds an 80-year ground lease with reciprocal purchase and sale options from year 50.","party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-lake-hawkeye"},{"evidence_id":"954edfd5-2e62-5421-8f63-efa62dc170e8","notes":"Holds an 80-year ground lease with reciprocal purchase and sale options from year 50.","party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-lake-hawkeye"},{"evidence_id":"1da49023-dd86-5890-ad4c-a83551c3d516","notes":"Holds an 80-year ground lease with reciprocal purchase and sale options from year 50.","party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-lake-hawkeye"},{"evidence_id":"17da0c46-2546-5d53-b910-108e95100470","notes":"Lessor under the 80-year ground lease; TeraWulf discloses that the Cayuga site is owned by its chief executive.","party":"Cayuga Operating Company","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-lake-hawkeye"},{"evidence_id":"c184bc2e-a22e-55c5-b8a4-1ef00ccce2b2","notes":"County legislators passed a resolution in January 2026 asking state regulators for a more thorough review of the project.","party":"Tompkins County","relationship_scope":"unknown","role":"government","source_record_id":"terawulf-lake-hawkeye"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Cayuga Operating Company |  |  |  |  | https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results | https://investors.terawulf.com/news-events/press-releases/detail/113 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve TeraWulf Lake Hawkeye data campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"terawulf-lake-hawkeye"},"record":{"aliases":["Cayuga site","Lake Hawkeye"],"id":"terawulf-lake-hawkeye","last_reviewed":"2026-10-09","location":{"admin1":"New York","admin2":"Tompkins County","country":"US","lat":42.5658,"locality":"Lansing","lon":-76.5319,"note":"Sources place the site at the former Cayuga power plant in the town of Lansing without an address. Coordinates are the town point from the Lansing, New York Wikipedia article, not the plant site.","precision":"locality","source_ids":["s1","s4","s5","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-05","basis":"planned","metric":"power_capacity","note":"The lease grants exclusive rights to develop up to 400 MW; the August 2026 release gives about 400 MW gross, subject to permitting and site development.","power_scope":"facility","qualifier":"approximately","source_ids":["s1","s3"],"unit":"MW","value":400},{"applies_to":"campus","as_of":"2026-08-05","basis":"planned","metric":"power_capacity","power_scope":"it_load","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":320},{"applies_to":"phase","as_of":"2026-05-08","basis":"planned","metric":"power_capacity","note":"Power available in Phase I, expanding to 300 MW in Phase II, per the Q1 2026 release. In August 2025 TeraWulf had expected 138 MW ready for service in the second half of 2026.","phase_label":"Phase I","power_scope":"unspecified","qualifier":"approximately","source_ids":["s2"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2025-08-14","basis":"reported","metric":"land_area","note":"Leased, not owned: an 80-year ground lease on part of a former coal-fired power plant site.","qualifier":"approximately","source_ids":["s1","s2"],"unit":"acres","value":183}],"milestones":[{"date":"2025-08-14","event":"announced","kind":"actual","note":"TeraWulf announced the long-term ground lease at the Cayuga site for high-performance computing.","source_ids":["s1"]},{"date":"2026-05-08","event":"other","kind":"actual","note":"TeraWulf reported the project in site plan review.","source_ids":["s2"]},{"date":"2026-07-14","event":"other","kind":"actual","note":"A New York executive order paused discretionary permits for certain AI data centers for up to a year; TeraWulf said the project was still in early planning and operations would fall after the pause.","source_ids":["s5"]},{"date":"2029","event":"first_operational","kind":"planned","note":"TeraWulf does not expect operations until about 2029; its August 2025 target had been the second half of 2026.","source_ids":["s3"]}],"name":"TeraWulf Lake Hawkeye data campus","notes":"Capacity figures shifted across TeraWulf releases: 138 MW for 2026 (August 2025), about 150 MW then 300 MW in two phases (May 2026), and about 400 MW gross and 320 MW IT longer term (August 2026). Local reporting says TeraWulf has pledged not to use lake water for cooling but has applied to renew a water withdrawal permit. WBNG dates the original lease rights to 2019, while TeraWulf announced the ground lease in August 2025.","parties":[{"name":"TeraWulf","note":"Holds an 80-year ground lease with reciprocal purchase and sale options from year 50.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Cayuga Operating Company","note":"Lessor under the 80-year ground lease; TeraWulf discloses that the Cayuga site is owned by its chief executive.","role":"owner","source_ids":["s1"]},{"name":"Tompkins County","note":"County legislators passed a resolution in January 2026 asking state regulators for a more thorough review of the project.","role":"government","source_ids":["s4"]}],"power_sources":[{"description":"TeraWulf said in August 2025 that a solar installation of about 67 MW was planned, without saying where.","source_ids":["s1"],"type":"solar"},{"description":"An 800 MWh battery storage system was in advanced development on adjacent parcels, per TeraWulf in August 2025.","source_ids":["s1"],"type":"battery_storage"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-08-14","publisher":"TeraWulf","title":"TeraWulf secures long-term ground lease at Cayuga site to expand high-performance computing infrastructure","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/113"},{"accessed":"2026-10-09","id":"s2","published":"2026-05-08","publisher":"TeraWulf","title":"TeraWulf reports first quarter 2026 results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/140/terawulf-reports-first-quarter-2026-results"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004051013/https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results","id":"s3","published":"2026-08-05","publisher":"TeraWulf","title":"TeraWulf reports second quarter 2026 results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","id":"s4","published":"2026-01-28","publisher":"WBNG","title":"Tompkins County residents oppose AI data center on Cayuga Lake","type":"news","url":"https://www.wbng.com/2026/01/28/tompkins-county-residents-oppose-ai-data-center-cayuga-lake/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260723232153/https://www.fingerlakes1.com/2026/07/22/whats-next-for-lansing-data-center-after-state-moratorium/","id":"s5","published":"2026-07-22","publisher":"FingerLakes1.com","title":"What's next for Lansing data center after state moratorium?","type":"news","url":"https://www.fingerlakes1.com/2026/07/22/whats-next-for-lansing-data-center-after-state-moratorium/"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Lansing, New York","type":"other","url":"https://en.wikipedia.org/wiki/Lansing,_New_York"}],"status":"announced","status_as_of":"2026-08-05","status_source_ids":["s3"],"summary":"TeraWulf plan to redevelop about 183 leased acres of the former coal-fired Cayuga power plant site on Cayuga Lake in Lansing, Tompkins County, New York, into a high-performance computing campus. Its 80-year ground lease, announced in August 2025, gives exclusive rights to develop up to 400 MW, and TeraWulf first expected 138 MW online in late 2026. That timeline slipped: the project was in town site plan review in May 2026, faced county and resident opposition, and by August 2026 TeraWulf called it a longer-term redevelopment of about 400 MW gross, 320 MW of critical IT load, with operations not expected before about 2029.","workloads":["hpc","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"17da0c46-2546-5d53-b910-108e95100470","s2":"954edfd5-2e62-5421-8f63-efa62dc170e8","s3":"1da49023-dd86-5890-ad4c-a83551c3d516","s4":"c184bc2e-a22e-55c5-b8a4-1ef00ccce2b2","s5":"f65190ca-29b1-598f-b4ba-c1bfc9118a00","s6":"f2678935-72c7-5885-ad37-162446882f5c"},"source_file":"datacenters/projects/terawulf-lake-hawkeye.json","source_record_id":"terawulf-lake-hawkeye","source_record_sha256":"d8d535edbd465f66e5e0963a5691de97b492f14002691ea654db6ada9c90efd8","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d49e03a278f72f749e6b38962c4bb8520e70e53b97dc38fbe371d4ed37598bab"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a291a33ca480670cccf1/#project-2e14f098-9798-567b-ae40-a7d552f9be18 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2e14f098-9798-567b-ae40-a7d552f9be18.json
2e2b9d40-5024-5e6d-bbb2-56a8b16b9c16 | curated:cdc-eastern-creek-campus:ec5-current-build | vcc-site-3c1f872aa59b74b065ea | curated:cdc-eastern-creek-campus | CDC Eastern Creek EC5 Current Build | Australia | AU | -33.8181 | 150.8377 | Point | project | direct_geometry | authoritative_site_plan | shared_campus_reference_point | official_source | reviewed_site_locator | Official NSW project-site representative point for the shared Eastern Creek campus; not an EC5 building footprint. | 250 |  | a4ae0a31-3e69-5886-ad17-7d2402e15677 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | 1d6cc958-8ca3-5a8c-ab4b-a07cf5a45b32 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://cdc.com.au/locations/sydney/ | https://www.planningportal.nsw.gov.au/major-projects/projects/roberts-road-data-centre | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3c1f872aa59b74b065ea/#project-2e2b9d40-5024-5e6d-bbb2-56a8b16b9c16 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2e2b9d40-5024-5e6d-bbb2-56a8b16b9c16.json
2f422325-bd08-5072-a93f-dde01520f486 | curated:galaxy-helios-data-center-campus:phase-2-260mw-critical-it-build | vcc-site-43bf6c7b8c9e9dfc51d0 | curated:galaxy-helios-data-center-campus | Galaxy Helios Phase II 260 MW Critical IT Build | United States | US | 33.7806 | -100.8671 | Point | campus | official_address_range_geocode | census_single_exact_address_match_then_explicit_nad83_to_wgs84 | official_address_range_interpolation_constituent_campus_locator | official_source | campus_locator | Government geocoder street-range interpolation for the TCEQ-registered Helios I address. Used for the physical campus only; Phase II's separate 1003 FM 193 address is unresolved in Census. No Phase II footprint, parcel boundary or surveyed accuracy is asserted. |  | No source provides a numeric horizontal-accuracy guarantee or a surveyed campus reference feature. | 50b56d5c-226f-57f8-b2b1-9d79212c26eb | under_construction | 2026-07-06 | 99 | authoritative_physical_status_update | 8c104356-5de7-5156-9a00-2996e59f07af | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.galaxy.com/newsroom/galaxy-completes-phase-i-of-its-helios-data-center-campus | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=984%20County%20Road%20112%20Afton%20TX%2079220&benchmark=Public_AR_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-43bf6c7b8c9e9dfc51d0/#project-2f422325-bd08-5072-a93f-dde01520f486 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2f422325-bd08-5072-a93f-dde01520f486.json
2fc433ea-05de-5b3a-b4a1-bd9d544f8ae3 | imported:semiconductor-atlas:meta-temple-texas | vcc-site-6afd5a936ac72410543b | imported:semiconductor-atlas:meta-temple-texas | Meta Temple Data Center | United States | US | 31.1056 | -97.4208 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Temple city coordinates from its Wikipedia page. Sources place the site off NW H K Dodgen Loop and Industrial Boulevard but give no parcel coordinates, so the campus itself is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 24883aba-24d8-587f-b4e2-c84ea6bdd083 | operational | 2026-07-22 | 83 | imported_documented_status | 65c3e60d-9cf7-54bb-bedb-19a9c9c78ced | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"0f8bcc15-68a6-5c0c-93be-7c34bddd54a5","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-temple-texas"},{"evidence_id":"24883aba-24d8-587f-b4e2-c84ea6bdd083","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-temple-texas"},{"evidence_id":"65c3e60d-9cf7-54bb-bedb-19a9c9c78ced","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"meta-temple-texas"},{"evidence_id":"24883aba-24d8-587f-b4e2-c84ea6bdd083","notes":"Issued the announcement and, with the City of Temple, granted a partial 10-year property tax abatement.","party":"Temple Economic Development Corporation","relationship_scope":"unknown","role":"government","source_record_id":"meta-temple-texas"},{"evidence_id":"f26f0414-587b-51f2-beb3-cf03973d87ab","notes":"Issued the announcement and, with the City of Temple, granted a partial 10-year property tax abatement.","party":"Temple Economic Development Corporation","relationship_scope":"unknown","role":"government","source_record_id":"meta-temple-texas"},{"evidence_id":"0f8bcc15-68a6-5c0c-93be-7c34bddd54a5","notes":"Granted a partial property tax abatement; Meta says it pays the full cost of the city's water and wastewater service to the site.","party":"City of Temple","relationship_scope":"unknown","role":"government","source_record_id":"meta-temple-texas"},{"evidence_id":"f26f0414-587b-51f2-beb3-cf03973d87ab","notes":"Granted a partial property tax abatement; Meta says it pays the full cost of the city's water and wastewater service to the site.","party":"City of Temple","relationship_scope":"unknown","role":"government","source_record_id":"meta-temple-texas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Meta Platforms |  |  |  | https://www.kwtx.com/2026/07/22/meta-goes-live-temple-with-12-billion-ai-data-center/ | https://www.kwtx.com/2022/03/31/facebook-parent-company-invest-800-million-central-texas/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Temple Data Center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-temple-texas","source_relations":[{"reason":"Meta operating Temple campus and Rowan Project Temple are separately named developments; both use the Temple city point.","relationship":"separate_named_developments","source_id":"rowan-project-temple"}]},"record":{"aliases":["Temple Data Center"],"id":"meta-temple-texas","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Bell County","country":"US","lat":31.1056,"locality":"Temple","lon":-97.4208,"note":"Coordinates are the Temple city coordinates from its Wikipedia page. Sources place the site off NW H K Dodgen Loop and Industrial Boulevard but give no parcel coordinates, so the campus itself is not pinpointed.","precision":"locality","source_ids":["s2","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2022-03-31","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s2","s3"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2026-07-22","basis":"announced","metric":"investment","note":"Meta's fact sheet gives USD 1.2 billion; KWTX describes the investment as more than USD 1.2 billion once completed.","qualifier":"exact","source_ids":["s1","s4"],"unit":"USD","value":1200000000},{"applies_to":"campus","as_of":"2022-03-31","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":393},{"applies_to":"campus","as_of":"2022-03-31","basis":"planned","metric":"floor_area","note":"Original 2022 plan.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"sq_ft","value":900000},{"applies_to":"campus","as_of":"2026-07-22","basis":"operational","metric":"floor_area","note":"Size of the facility as opened in July 2026.","qualifier":"more_than","source_ids":["s4"],"unit":"sq_ft","value":760000},{"applies_to":"campus","as_of":"2026-07-22","basis":"operational","metric":"buildings","note":"KWTX describes the opened facility as two buildings; it does not say whether both are already in service.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2026-07-22","basis":"reported","metric":"jobs_construction","note":"Skilled trade workers on site at peak construction; Meta's fact sheet gives 1,200, KWTX more than 1,200, and a 2022 trade report about 1,250 over two years.","qualifier":"more_than","source_ids":["s1","s2","s3","s4"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2026-07-22","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s1","s2","s4"],"unit":"count","value":100}],"milestones":[{"date":"2022-03-31","event":"announced","kind":"actual","source_ids":["s2"]},{"date":"2022","event":"construction_started","kind":"actual","note":"Work was expected to begin in spring 2022.","source_ids":["s1","s2","s4"]},{"date":"2023","event":"other","kind":"actual","note":"Construction restarted after the project was redesigned.","source_ids":["s4"]},{"date":"2026-07","event":"first_operational","kind":"actual","note":"KWTX reported the facility open and operational in July 2026; a 2022 trade report had expected completion in 2024.","source_ids":["s3","s4"]}],"name":"Meta Temple Data Center","notes":"KWTX reported the opening in July 2026 without saying whether both buildings are in service. Meta's fact sheet (s1) shows no publication date; its embedded file creation date is 2026-09-02. The investment figure rose from USD 800 million at announcement to USD 1.2 billion; sources do not explain the increase beyond the redesign.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Meta Platforms","role":"operator","source_ids":["s4"]},{"name":"Temple Economic Development Corporation","note":"Issued the announcement and, with the City of Temple, granted a partial 10-year property tax abatement.","role":"government","source_ids":["s2","s3"]},{"name":"City of Temple","note":"Granted a partial property tax abatement; Meta says it pays the full cost of the city's water and wastewater service to the site.","role":"government","source_ids":["s1","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Meta Platforms","title":"Meta Temple Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Metas-Temple-Data-Center.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250721232912/https://www.kwtx.com/2022/03/31/facebook-parent-company-invest-800-million-central-texas/","id":"s2","published":"2022-03-31","publisher":"KWTX","title":"Facebook parent company to invest $800 million in Central Texas","type":"news","url":"https://www.kwtx.com/2022/03/31/facebook-parent-company-invest-800-million-central-texas/"},{"accessed":"2026-10-09","id":"s3","published":"2022-04-07","publisher":"Daily Commercial News (ConstructConnect)","title":"Meta's data centre in Temple is part of Texas' growth trend","type":"trade_press","url":"https://canada.constructconnect.com/?p=261660"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-22","publisher":"KWTX","title":"Meta goes live in Temple with $1.2 billion AI data center","type":"news","url":"https://www.kwtx.com/2026/07/22/meta-goes-live-temple-with-12-billion-ai-data-center/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001014904/https://en.wikipedia.org/wiki/Temple,_Texas","id":"s5","published":null,"publisher":"Wikipedia","title":"Temple, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Temple,_Texas"}],"status":"operational","status_as_of":"2026-07-22","status_source_ids":["s4"],"summary":"Meta data center on a 393-acre site off NW H K Dodgen Loop and Industrial Boulevard in Temple, Texas. Announced in March 2022 as a USD 800 million, roughly 900,000 sq ft hyperscale campus expected to be finished in 2024, it broke ground in 2022, was redesigned with construction restarting in 2023, and opened in July 2026 as an AI data center of two buildings and more than 760,000 sq ft. Meta now gives its investment as USD 1.2 billion. Meta describes it as its second data center in Texas.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"0f8bcc15-68a6-5c0c-93be-7c34bddd54a5","s2":"24883aba-24d8-587f-b4e2-c84ea6bdd083","s3":"f26f0414-587b-51f2-beb3-cf03973d87ab","s4":"65c3e60d-9cf7-54bb-bedb-19a9c9c78ced","s5":"a4b8253b-de34-5e32-8ce6-f3b354576cb6"},"source_file":"datacenters/projects/meta-temple-texas.json","source_record_id":"meta-temple-texas","source_record_sha256":"6558a5072429b8e64f5a5654423c0025443d77b5adf5c9f2228113f65f8fef5c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"57beadebfbaafe4e0a2fe464360d3ea773f0de86d0280307faf5062160b1f8eb"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6afd5a936ac72410543b/#project-2fc433ea-05de-5b3a-b4a1-bd9d544f8ae3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/2fc433ea-05de-5b3a-b4a1-bd9d544f8ae3.json
302bc1de-8d94-5ca1-a94e-ceb9facdcc1e | imported:semiconductor-atlas:meta-tulsa | vcc-site-4ed4b7a2d6d92a9362bb | imported:semiconductor-atlas:meta-tulsa | Meta Tulsa data center | United States | US | 36.1563 | -95.9928 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City point from OpenStreetMap Nominatim; Meta places the site in East Tulsa but names no road or parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 7fec14c3-48ab-51e7-806a-bcca87662826 | under_construction | 2026-10-09 | 4 | imported_documented_status | 64e32c45-abc9-5556-8554-1db2b4058d48 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"7fec14c3-48ab-51e7-806a-bcca87662826","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-tulsa"},{"evidence_id":"64e32c45-abc9-5556-8554-1db2b4058d48","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-tulsa"},{"evidence_id":"7fec14c3-48ab-51e7-806a-bcca87662826","notes":"The project website says Fortis Construction is building the campus for Meta.","party":"Fortis Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-tulsa"},{"evidence_id":"2945aeae-a31b-575f-84f0-0f296eb15f29","notes":"The project website says Fortis Construction is building the campus for Meta.","party":"Fortis Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-tulsa"},{"evidence_id":"7fec14c3-48ab-51e7-806a-bcca87662826","notes":"Named in Meta's fact sheet as its energy-planning partner.","party":"Public Service Company of Oklahoma","relationship_scope":"unknown","role":"utility","source_record_id":"meta-tulsa"},{"evidence_id":"64e32c45-abc9-5556-8554-1db2b4058d48","notes":"Named in Meta's fact sheet as its energy-planning partner.","party":"Public Service Company of Oklahoma","relationship_scope":"unknown","role":"utility","source_record_id":"meta-tulsa"},{"evidence_id":"64e32c45-abc9-5556-8554-1db2b4058d48","notes":"Water and wastewater provider; Meta says it pays the full cost of service.","party":"Tulsa Metropolitan Utility Authority","relationship_scope":"unknown","role":"utility","source_record_id":"meta-tulsa"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Tulsa-Data-Center.pdf | https://datacenters.atmeta.com/2026/04/hello-tulsa/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Tulsa data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-tulsa"},"record":{"aliases":["Tulsa Data Center"],"id":"meta-tulsa","last_reviewed":"2026-10-09","location":{"admin1":"Oklahoma","country":"US","lat":36.1563,"locality":"Tulsa","lon":-95.9928,"note":"City point from OpenStreetMap Nominatim; Meta places the site in East Tulsa but names no road or parcel.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-21","basis":"announced","metric":"investment","note":"Meta also said it is investing more than USD 25 million in local road and water infrastructure.","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"From the undated project website, read 2026-10-09.","qualifier":"approximately","source_ids":["s4"],"unit":"sq_ft","value":2000000},{"applies_to":"campus","as_of":"2026-04-21","basis":"planned","metric":"jobs_construction","note":"Meta's location list gives 1,000 without a qualifier.","qualifier":"more_than","source_ids":["s1","s2","s4"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2026-04-21","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s1","s2"],"unit":"count","value":100}],"milestones":[{"date":"2026-04-21","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2026","event":"construction_started","kind":"actual","note":"Meta's location list gives 2026 as the groundbreaking year.","source_ids":["s3"]}],"name":"Meta Tulsa data center","notes":"The status rests on two undated Meta pages: the U.S. location list, which gives 2026 as the groundbreaking year, and the fact sheet, which describes the data center in the future tense. status_as_of is therefore the date both were read (2026-10-09). The fact sheet PDF shows no publication date; its embedded file creation date is 2026-09-02.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Fortis Construction","note":"The project website says Fortis Construction is building the campus for Meta.","role":"builder","source_ids":["s1","s4"]},{"name":"Public Service Company of Oklahoma","note":"Named in Meta's fact sheet as its energy-planning partner.","role":"utility","source_ids":["s1","s2"]},{"name":"Tulsa Metropolitan Utility Authority","note":"Water and wastewater provider; Meta says it pays the full cost of service.","role":"utility","source_ids":["s2"]}],"power_sources":[{"description":"Meta says it will plan its energy needs with Public Service Company of Oklahoma, pay the full cost of the energy used and match it with clean energy. It cited more than 1,500 MW of new clean energy under contract in Oklahoma in April 2026, and its fact sheet lists five Oklahoma projects totaling 1,273 MW.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-04-21","publisher":"Meta Platforms","title":"Hello, Tulsa!","type":"company","url":"https://datacenters.atmeta.com/2026/04/hello-tulsa/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Meta Platforms","title":"Meta Tulsa Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Tulsa-Data-Center.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007122559/https://datacenters.atmeta.com/us-locations/","id":"s3","published":null,"publisher":"Meta Platforms","title":"United States - Meta Data Centers","type":"company","url":"https://datacenters.atmeta.com/us-locations/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Tulsa Data Center project website","title":"Tulsa Data Center","type":"company","url":"https://tulsaokdatacenter.com/"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s2","s3"],"summary":"Meta AI data center in East Tulsa, Oklahoma, announced in April 2026 as an investment of more than USD 1 billion. Fortis Construction is building a campus of roughly 2 million square feet for Meta, and Meta's location list gives 2026 as the groundbreaking year. Meta names Public Service Company of Oklahoma as its energy-planning partner and reports five Oklahoma clean energy projects totaling 1,273 MW. Meta has not published a power capacity or opening date for the site.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"7fec14c3-48ab-51e7-806a-bcca87662826","s2":"64e32c45-abc9-5556-8554-1db2b4058d48","s3":"caeaf8cf-eb58-5a25-b265-f3137b564476","s4":"2945aeae-a31b-575f-84f0-0f296eb15f29"},"source_file":"datacenters/projects/meta-tulsa.json","source_record_id":"meta-tulsa","source_record_sha256":"1133f6138b97e58b44c5175d758532514cfa710f665fe1387b3ac86f5d43bc21","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"21982c96a5436f7a01f4e5c426091cf6da72f941fd0b0c811a85ee25ab307f9e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4ed4b7a2d6d92a9362bb/#project-302bc1de-8d94-5ca1-a94e-ceb9facdcc1e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/302bc1de-8d94-5ca1-a94e-ceb9facdcc1e.json
304e9b81-f1b5-5a80-8ad5-6f46e12f5a85 | imported:semiconductor-atlas:ecodatacenter-borlange | vcc-site-ce3b42e4fc2f6b33b8a2 | imported:semiconductor-atlas:ecodatacenter-borlange | EcoDataCenter 2 Borlänge campus | Sweden | SE | 60.4856 | 15.4364 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Borlänge town centroid from its Wikipedia article. EcoDataCenter gives the street address Kvarnsvedsvägen 420 on the former Kvarnsveden mill site, but no cited source gives coordinates for it. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6f693b49-5cf7-51bd-b9ff-56dbbb0dc051 | under_construction | 2026-10-05 | 8 | imported_documented_status | 0479f072-9b63-51b5-bdf7-80d627d47394 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6f693b49-5cf7-51bd-b9ff-56dbbb0dc051","notes":null,"party":"EcoDataCenter","relationship_scope":"unknown","role":"developer","source_record_id":"ecodatacenter-borlange"},{"evidence_id":"2ce6c8b6-53a4-51a5-b633-c84753eb096e","notes":null,"party":"EcoDataCenter","relationship_scope":"unknown","role":"developer","source_record_id":"ecodatacenter-borlange"},{"evidence_id":"e4f2337e-5880-50a7-aa30-ffb72cde7856","notes":"Tech Insider describes EcoDataCenter as the operating partner that builds and runs the facility.","party":"EcoDataCenter","relationship_scope":"unknown","role":"operator","source_record_id":"ecodatacenter-borlange"},{"evidence_id":"593ef2ff-09d5-5e4e-a01d-a5752abf1f75","notes":"Announced a partnership with EcoDataCenter in February 2026 to build a dedicated AI data center at the Borlänge site. Analyst Epoch AI lists Mistral as owner and user of the AI chips; EcoDataCenter's campus page does not name tenants.","party":"Mistral AI","relationship_scope":"unknown","role":"tenant","source_record_id":"ecodatacenter-borlange"},{"evidence_id":"e4f2337e-5880-50a7-aa30-ffb72cde7856","notes":"Announced a partnership with EcoDataCenter in February 2026 to build a dedicated AI data center at the Borlänge site. Analyst Epoch AI lists Mistral as owner and user of the AI chips; EcoDataCenter's campus page does not name tenants.","party":"Mistral AI","relationship_scope":"unknown","role":"tenant","source_record_id":"ecodatacenter-borlange"},{"evidence_id":"0479f072-9b63-51b5-bdf7-80d627d47394","notes":"Announced a partnership with EcoDataCenter in February 2026 to build a dedicated AI data center at the Borlänge site. Analyst Epoch AI lists Mistral as owner and user of the AI chips; EcoDataCenter's campus page does not name tenants.","party":"Mistral AI","relationship_scope":"unknown","role":"tenant","source_record_id":"ecodatacenter-borlange"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | EcoDataCenter |  | Mistral AI |  | https://epoch.ai/data/ai-data-centers/directory/ecodatacenter-2 | https://ecodatacenter.tech/data-center/ecodatacenter2 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve EcoDataCenter 2 Borlänge campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"ecodatacenter-borlange"},"record":{"aliases":["EcoDataCenter 2","EcoDataCenter Borlänge mega campus"],"id":"ecodatacenter-borlange","last_reviewed":"2026-10-09","location":{"admin1":"Dalarna County","admin2":"Borlänge Municipality","country":"SE","lat":60.48556,"locality":"Borlänge","lon":15.43639,"note":"Borlänge town centroid from its Wikipedia article. EcoDataCenter gives the street address Kvarnsvedsvägen 420 on the former Kvarnsveden mill site, but no cited source gives coordinates for it.","precision":"locality","source_ids":["s1","s2","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total available power on EcoDataCenter's undated campus page, read on the access date.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":600},{"applies_to":"campus","as_of":"2024-09-06","basis":"planned","metric":"power_capacity","note":"Rating of the campus when first announced; later superseded by the up to 600 MW figure.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":240},{"applies_to":"phase","as_of":"2026-10-05","basis":"under_construction","metric":"power_capacity","note":"Analyst estimate, not a company disclosure: Epoch AI projects about 24 MW of IT power by mid-2027 and 48 MW by mid-2028 from the four buildings it sees under construction.","phase_label":"Buildings 1-4 (Epoch AI projection to mid-2028)","power_scope":"it_load","qualifier":"approximately","source_ids":["s5"],"unit":"MW","value":48},{"applies_to":"campus","as_of":"2026-02-18","basis":"reported","metric":"investment","note":"Mistral AI's reported long-term investment with EcoDataCenter for a dedicated AI data center in Borlänge.","qualifier":"approximately","source_ids":["s4"],"unit":"EUR","value":1200000000},{"applies_to":"campus","as_of":"2026-08-27","basis":"reported","metric":"investment","note":"W.Media's value for the same Mistral AI partnership, stated in US dollars.","qualifier":"approximately","source_ids":["s3"],"unit":"USD","value":1400000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"EcoDataCenter says the plot on the former Kvarnsveden paper mill site spans over 200,000 square metres.","qualifier":"more_than","source_ids":["s1"],"unit":"hectares","value":20},{"applies_to":"campus","as_of":"2026-10-05","basis":"under_construction","metric":"buildings","note":"Analyst observation from satellite imagery, not a company figure: in August 2026 buildings 1 and 2 were roofed with equipment going in, and buildings 3 and 4 had foundations.","qualifier":"exact","source_ids":["s5"],"unit":"count","value":4}],"milestones":[{"date":"2024-09-06","event":"announced","kind":"actual","note":"EcoDataCenter said it had acquired parts of the former paper mill and planned a 240 MW campus.","source_ids":["s2"]},{"date":"2025-09","event":"construction_started","kind":"actual","source_ids":["s1","s5"]},{"date":"2026-02-18","event":"other","kind":"actual","note":"Mistral AI and EcoDataCenter announced their partnership for a dedicated AI data center at the site.","source_ids":["s4","s3"]},{"date":"2027","event":"first_operational","kind":"planned","note":"EcoDataCenter targets completion of the first phase by mid-2027. Analyst Epoch AI projects buildings 1 and 2 operating by mid-2027 and buildings 3 and 4 by mid-2028; Tech Insider noted that long lead times for Nvidia accelerators could push the start of operations into 2028.","source_ids":["s1","s4","s5"]}],"name":"EcoDataCenter 2 Borlänge campus","notes":"EcoDataCenter's campus page is undated, so figures taken from it carry the access date. EcoDataCenter's page does not disclose MW for the Mistral deployment; Tech Insider cites analyst estimates of 75 to 150 MW, which are not recorded, and Epoch AI figures are analyst estimates. W.Media reports Borlänge and Falun together will offer more than 500 MW once complete in 2027. A separate 150 MW EcoDataCenter site in Smedjebacken municipality, south of Borlänge, is a different project.","parties":[{"name":"EcoDataCenter","role":"developer","source_ids":["s1","s2"]},{"name":"EcoDataCenter","note":"Tech Insider describes EcoDataCenter as the operating partner that builds and runs the facility.","role":"operator","source_ids":["s4"]},{"name":"Mistral AI","note":"Announced a partnership with EcoDataCenter in February 2026 to build a dedicated AI data center at the Borlänge site. Analyst Epoch AI lists Mistral as owner and user of the AI chips; EcoDataCenter's campus page does not name tenants.","role":"tenant","source_ids":["s3","s4","s5"]}],"power_sources":[{"description":"EcoDataCenter says the campus uses fully renewable electricity from local hydropower and wind.","source_ids":["s1"],"type":"hydro"},{"description":"Local wind power is part of the renewable supply EcoDataCenter cites.","source_ids":["s1"],"type":"wind"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260610065455/https://ecodatacenter.tech/data-center/ecodatacenter2","id":"s1","published":null,"publisher":"EcoDataCenter","title":"EcoDataCenter 2 - Borlänge","type":"company","url":"https://ecodatacenter.tech/data-center/ecodatacenter2"},{"accessed":"2026-10-09","id":"s2","published":"2024-09-06","publisher":"Data Centre Review","title":"EcoDataCenter announces plans for mega campus in Sweden","type":"trade_press","url":"https://datacentrereview.com/?p=81016"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-27","publisher":"W.Media","title":"EcoDataCenter secures land for third Swedish data center campus","type":"trade_press","url":"https://w.media/ecodatacenter-secures-land-for-third-swedish-data-center-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006155524/https://tech-insider.org/sv/mistral-ai-1-2-miljarder-sverige-ecodatacenter-borlange-2026/","id":"s4","published":"2026-04-24","publisher":"Tech Insider","title":"Mistral AI satsar €1,2 mdr i Sverige med EcoDataCenter [2026]","type":"trade_press","url":"https://tech-insider.org/sv/mistral-ai-1-2-miljarder-sverige-ecodatacenter-borlange-2026/"},{"accessed":"2026-10-09","id":"s5","published":"2026-10-05","publisher":"Epoch AI","title":"EcoDataCenter 2 (AI data center directory)","type":"analyst","url":"https://epoch.ai/data/ai-data-centers/directory/ecodatacenter-2"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Borlänge","type":"other","url":"https://en.wikipedia.org/wiki/Borl%C3%A4nge"}],"status":"under_construction","status_as_of":"2026-10-05","status_source_ids":["s5","s3"],"summary":"EcoDataCenter campus on part of the former Kvarnsveden paper mill in Borlänge, Dalarna, near its existing Falun site. Announced in September 2024 as a 240 MW plan, it is now marketed with up to 600 MW of available power on about 20 hectares. Construction began in September 2025 and the first phase is targeted for mid-2027. In February 2026 Mistral AI announced a partnership and investment, reported at EUR 1.2 billion, for a dedicated AI data center at the site. Analyst Epoch AI saw four buildings under way in August 2026 imagery and projects modest initial IT power.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6f693b49-5cf7-51bd-b9ff-56dbbb0dc051","s2":"2ce6c8b6-53a4-51a5-b633-c84753eb096e","s3":"593ef2ff-09d5-5e4e-a01d-a5752abf1f75","s4":"e4f2337e-5880-50a7-aa30-ffb72cde7856","s5":"0479f072-9b63-51b5-bdf7-80d627d47394","s6":"ee340999-07b2-5ec9-8640-e096177ee4bb"},"source_file":"datacenters/projects/ecodatacenter-borlange.json","source_record_id":"ecodatacenter-borlange","source_record_sha256":"553c6701161532f38f3aefda2f0854ee4f3382deb968866b9e6120abf75060c7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"22f4efdb0cc62fabb4a17b46633dd24c700e80231d5308739e5d58dfd457c8c3"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ce3b42e4fc2f6b33b8a2/#project-304e9b81-f1b5-5a80-8ad5-6f46e12f5a85 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/304e9b81-f1b5-5a80-8ad5-6f46e12f5a85.json
31635fdf-a7a6-52c8-91dc-f64e5c7d10d3 | curated:related-digital-cheyenne-campus:phase-1 | vcc-site-c879bad0c737049a2484 | curated:related-digital-cheyenne-campus | Related Digital Cheyenne Phase 1 | United States | US | 41.1426 | -104.7015 | Point | campus | first_party_published_map_pin | first_party_published_map_pin | operator_project_map_point | official_source | campus_locator | Exact first-party Wyoming page coordinate, used only as a broad Cheyenne campus locator; not a parcel, Phase 1 building, or work footprint. |  | Related Digital states no bounded accuracy for its embedded map coordinate. | 9249d532-23ae-58da-bcd6-80cf09aaac30 | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | e5706273-3ece-59fe-9473-861294daece9 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.related-digital.com/wyoming | https://www.related-digital.com/wyoming | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c879bad0c737049a2484/#project-31635fdf-a7a6-52c8-91dc-f64e5c7d10d3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/31635fdf-a7a6-52c8-91dc-f64e5c7d10d3.json
316e6c68-21e0-50d1-973e-d4fa5847a99f | imported:semiconductor-atlas:openai-stargate-milam-county | vcc-site-00432e4e9c8e2d91ff76 | imported:semiconductor-atlas:openai-stargate-milam-county | Stargate Milam County (SB Energy campus) | United States | US | 30.7627 | -96.9982 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Milam County centroid from OpenStreetMap Nominatim. Sources name only the county, which Epoch AI places about 70 miles northeast of Austin; no site address was found. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 882a168d-1e56-5d20-99d6-d4e41e2c0cb6 | under_construction | 2026-04-17 | 179 | imported_documented_status | 9a99f24e-7b16-5f5e-bd04-b8657f2c12fd | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"882a168d-1e56-5d20-99d6-d4e41e2c0cb6","notes":"Develops the site in partnership with OpenAI. Analyst Epoch AI, not a company disclosure, lists SoftBank as owner of the AI hardware.","party":"SoftBank Group","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-milam-county"},{"evidence_id":"9a99f24e-7b16-5f5e-bd04-b8657f2c12fd","notes":"Develops the site in partnership with OpenAI. Analyst Epoch AI, not a company disclosure, lists SoftBank as owner of the AI hardware.","party":"SoftBank Group","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-milam-county"},{"evidence_id":"882a168d-1e56-5d20-99d6-d4e41e2c0cb6","notes":"Named with SoftBank as partner for the two SoftBank Stargate sites.","party":"OpenAI","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-milam-county"},{"evidence_id":"b07d5317-dc82-5a78-a600-6e96efd36f0d","notes":"Analyst Epoch AI, not a company disclosure, says the SoftBank subsidiary is building and operating the site.","party":"SB Energy","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-milam-county"},{"evidence_id":"882a168d-1e56-5d20-99d6-d4e41e2c0cb6","notes":"Provides the powered infrastructure; Epoch AI (analyst) reports it plans new generation and storage for most of the campus load.","party":"SB Energy","relationship_scope":"unknown","role":"power_supplier","source_record_id":"openai-stargate-milam-county"},{"evidence_id":"9a99f24e-7b16-5f5e-bd04-b8657f2c12fd","notes":"Provides the powered infrastructure; Epoch AI (analyst) reports it plans new generation and storage for most of the campus load.","party":"SB Energy","relationship_scope":"unknown","role":"power_supplier","source_record_id":"openai-stargate-milam-county"},{"evidence_id":"b07d5317-dc82-5a78-a600-6e96efd36f0d","notes":"Provides the powered infrastructure; Epoch AI (analyst) reports it plans new generation and storage for most of the campus load.","party":"SB Energy","relationship_scope":"unknown","role":"power_supplier","source_record_id":"openai-stargate-milam-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.datacenterknowledge.com/data-center-site-selection/openai-expands-stargate-with-five-new-data-center-sites-across-us | https://group.softbank/en/news/press/20250924 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Stargate Milam County (SB Energy campus) as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"openai-stargate-milam-county"},"record":{"aliases":["Stargate Milam County"],"id":"openai-stargate-milam-county","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Milam County","country":"US","lat":30.7627,"lon":-96.9982,"note":"Milam County centroid from OpenStreetMap Nominatim. Sources name only the county, which Epoch AI places about 70 miles northeast of Austin; no site address was found.","precision":"admin2","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"power_capacity","note":"Analyst estimate, not a company disclosure: Epoch AI's projection of total facility power. SoftBank only gave 1.5 GW as the combined scale for this site and Lordstown, Ohio.","power_scope":"facility","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":1200}],"milestones":[{"date":"2025-09-23","event":"announced","kind":"actual","note":"Announced with Lordstown, Ohio as the two SoftBank Stargate sites, together able to scale to 1.5 GW over about 18 months.","source_ids":["s1","s2"]},{"date":"2025-09","event":"construction_started","kind":"actual","note":"SoftBank said at the announcement that it was breaking ground; analyst Epoch AI separately dates the start to Q3 2025.","source_ids":["s2","s3"]},{"date":"2026-10","event":"other","kind":"planned","note":"Analyst Epoch AI, not a company disclosure, cites regulatory filings indicating the first building would be delivered to the tenant by October 2026; delivery is not full operation.","source_ids":["s3"]},{"date":"2028-Q4","event":"fully_operational","kind":"planned","note":"Analyst estimate by Epoch AI, not a company date.","source_ids":["s3"]}],"name":"Stargate Milam County (SB Energy campus)","notes":"No 2026 company or local news source on this site was opened in this review; the newest status evidence is analyst Epoch AI's April 2026 imagery review, which is an analyst assessment rather than a company disclosure.","parties":[{"name":"SoftBank Group","note":"Develops the site in partnership with OpenAI. Analyst Epoch AI, not a company disclosure, lists SoftBank as owner of the AI hardware.","role":"developer","source_ids":["s1","s2"]},{"name":"OpenAI","note":"Named with SoftBank as partner for the two SoftBank Stargate sites.","role":"developer","source_ids":["s1"]},{"name":"SB Energy","note":"Analyst Epoch AI, not a company disclosure, says the SoftBank subsidiary is building and operating the site.","role":"developer","source_ids":["s3"]},{"name":"SB Energy","note":"Provides the powered infrastructure; Epoch AI (analyst) reports it plans new generation and storage for most of the campus load.","role":"power_supplier","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"SB Energy provides the powered infrastructure; analyst Epoch AI reports it plans to fund and build new generation and storage to supply most of the campus's power, with the generation type not disclosed.","source_ids":["s1","s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-09-24","publisher":"SoftBank Group Corp.","title":"OpenAI, Oracle, and SoftBank expand Stargate with five new AI data center sites","type":"company","url":"https://group.softbank/en/news/press/20250924"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260313130748/https://www.datacenterknowledge.com/data-center-site-selection/openai-expands-stargate-with-five-new-data-center-sites-across-us","id":"s2","published":"2025-09-24","publisher":"Data Center Knowledge (Bloomberg)","title":"OpenAI Expands Stargate With Five New Data Center Sites Across US","type":"trade_press","url":"https://www.datacenterknowledge.com/data-center-site-selection/openai-expands-stargate-with-five-new-data-center-sites-across-us"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260517184326/https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand","id":"s3","published":"2026-04-17","publisher":"Epoch AI","title":"OpenAI Stargate: where the US sites stand","type":"analyst","url":"https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand"}],"status":"under_construction","status_as_of":"2026-04-17","status_source_ids":["s2","s3"],"summary":"A fast-build Stargate AI campus in Milam County, Texas, about 70 miles northeast of Austin, developed by SoftBank in partnership with OpenAI, with SoftBank's SB Energy providing the powered infrastructure. It was announced in September 2025 as one of two SoftBank sites that together could scale to 1.5 GW within about 18 months, and SoftBank said then that it was breaking ground. Analyst Epoch AI projects about 1.2 GW for this site, saw steel framing and roofing on the first building in March 2026 imagery, and cites state filings pointing to delivery of that building by October 2026. SB Energy plans to fund and build new generation and storage for most of the campus power.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"882a168d-1e56-5d20-99d6-d4e41e2c0cb6","s2":"9a99f24e-7b16-5f5e-bd04-b8657f2c12fd","s3":"b07d5317-dc82-5a78-a600-6e96efd36f0d"},"source_file":"datacenters/projects/openai-stargate-milam-county.json","source_record_id":"openai-stargate-milam-county","source_record_sha256":"428c501cba6420222f62903244ca71171f145296ff2030582bd6bf575dffbca5","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"366e8c246622e5cb54e849a3461f6fdb15b03e69913acf0f37329bb5088f5e8b"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-00432e4e9c8e2d91ff76/#project-316e6c68-21e0-50d1-973e-d4fa5847a99f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/316e6c68-21e0-50d1-973e-d4fa5847a99f.json
31ee01b0-a72b-5f4a-bcc1-a13a53732efc | imported:semiconductor-atlas:crusoe-abilene-microsoft | vcc-site-9f7647940a58e048e38f | imported:semiconductor-atlas:crusoe-abilene-microsoft | Crusoe Abilene AI factory campus for Microsoft | United States | US | 32.45 | -99.75 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Crusoe places the campus in Abilene, adjacent to its existing campus, without an address. Coordinates are the Abilene city point from its Wikipedia article; the city spans Taylor and Jones counties, so no county is recorded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2eb43ea9-9af0-573a-80a9-aa67d7210065 | under_construction | 2026-07-15 | 90 | imported_documented_status | f5738e1b-fb4e-5562-9bd9-a3c076403ff8 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2eb43ea9-9af0-573a-80a9-aa67d7210065","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"crusoe-abilene-microsoft"},{"evidence_id":"f5738e1b-fb4e-5562-9bd9-a3c076403ff8","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"crusoe-abilene-microsoft"},{"evidence_id":"4a5bed5e-113e-5ad3-9602-75113749a4dd","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"crusoe-abilene-microsoft"},{"evidence_id":"2eb43ea9-9af0-573a-80a9-aa67d7210065","notes":"Crusoe says the campus will support large-scale AI workloads for Microsoft; lease terms were not disclosed.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"crusoe-abilene-microsoft"},{"evidence_id":"36e3d518-b1a0-5bb8-891e-8e2031731430","notes":"Crusoe says the campus will support large-scale AI workloads for Microsoft; lease terms were not disclosed.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"crusoe-abilene-microsoft"},{"evidence_id":"f5738e1b-fb4e-5562-9bd9-a3c076403ff8","notes":"Crusoe describes the land as adjacent Lancium-owned land.","party":"Lancium","relationship_scope":"unknown","role":"owner","source_record_id":"crusoe-abilene-microsoft"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Lancium |  |  | Microsoft |  | https://www.crusoe.ai/resources/newsroom/crusoe-and-lancium-announce-1-gigawatt-ai-data-center-campus-in-childress-texas | https://www.crusoe.ai/resources/newsroom/crusoe-announces-new-900-mw-ai-factory-campus-in-abilene-texas-to-support-microsoft-ai-infrastructure | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Crusoe Abilene AI factory campus for Microsoft as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"crusoe-abilene-microsoft","source_relations":[{"reason":"Source explicitly describes Microsoft campus as second and adjacent to original Oracle/OpenAI campus; distinct building programs and tenants.","relationship":"separate_adjacent_campuses","source_id":"openai-stargate-abilene"}]},"record":{"aliases":["Crusoe Abilene second campus","Abilene 900 MW campus"],"id":"crusoe-abilene-microsoft","last_reviewed":"2026-10-09","location":{"admin1":"Texas","country":"US","lat":32.45,"locality":"Abilene","lon":-99.75,"note":"Crusoe places the campus in Abilene, adjacent to its existing campus, without an address. Coordinates are the Abilene city point from its Wikipedia article; the city spans Taylor and Jones counties, so no county is recorded.","precision":"locality","source_ids":["s1","s3","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-15","basis":"planned","metric":"power_capacity","note":"Crusoe's headline size for the new site; it does not say whether this is IT or facility power.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":900},{"applies_to":"phase","as_of":"2026-03-27","basis":"planned","metric":"power_capacity","note":"Each of the two buildings is designed to deliver 336 MW of critical IT load; the first is due to be energized in mid-2027.","phase_label":"Building 1","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":336},{"applies_to":"phase","as_of":"2026-03-27","basis":"planned","metric":"power_capacity","phase_label":"Building 2","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":336},{"applies_to":"campus","as_of":"2026-03-27","basis":"planned","metric":"power_capacity","note":"Behind-the-meter on-site power plant; Crusoe did not disclose the generation technology or fuel.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":900},{"applies_to":"campus","as_of":"2026-03-27","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":2}],"milestones":[{"date":"2026-03-27","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2026-03","event":"construction_started","kind":"actual","note":"Land clearing and site preparation were under way when the campus was announced.","source_ids":["s1","s2"]},{"date":"2027","event":"first_operational","kind":"planned","note":"First building expected to be energized in mid-2027.","source_ids":["s1","s2"]}],"name":"Crusoe Abilene AI factory campus for Microsoft","notes":"This is a separate build from the eight-building Stargate Abilene campus (openai-stargate-abilene); Crusoe gives about 2.1 GW for its two Abilene campuses combined. The Register reports that Oracle and OpenAI had planned to lease this expansion before negotiations and financing fell through, and that Meta had been expected to take it before Microsoft; these are press reports, not company statements, and are not recorded as parties. In September 2026 Crusoe said it had two campuses under development in Abilene but gave no new status detail for this one.","parties":[{"name":"Crusoe","role":"developer","source_ids":["s1","s3","s4"]},{"name":"Microsoft","note":"Crusoe says the campus will support large-scale AI workloads for Microsoft; lease terms were not disclosed.","role":"tenant","source_ids":["s1","s2"]},{"name":"Lancium","note":"Crusoe describes the land as adjacent Lancium-owned land.","role":"owner","source_ids":["s3"]}],"power_sources":[{"description":"A 900 MW behind-the-meter on-site power plant that Crusoe says supports grid resilience; Crusoe has not said what fuel or technology it uses.","source_ids":["s1","s2"],"type":"other"},{"description":"Medium-voltage battery energy storage paired with the on-site plant.","source_ids":["s1"],"type":"battery_storage"}],"related_ids":["openai-stargate-abilene"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261002002842/https://www.crusoe.ai/resources/newsroom/crusoe-announces-new-900-mw-ai-factory-campus-in-abilene-texas-to-support-microsoft-ai-infrastructure","id":"s1","published":"2026-03-27","publisher":"Crusoe","title":"Crusoe announces new 900 MW AI factory campus in Abilene, Texas to support Microsoft AI infrastructure","type":"company","url":"https://www.crusoe.ai/resources/newsroom/crusoe-announces-new-900-mw-ai-factory-campus-in-abilene-texas-to-support-microsoft-ai-infrastructure"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260418202620/https://www.theregister.com/2026/03/27/microsoft_ai_crusoe/","id":"s2","published":"2026-03-27","publisher":"The Register","title":"Microsoft takes up residence next to OpenAI, Oracle at Crusoe's 900 MW Texas datacenter expansion","type":"news","url":"https://www.theregister.com/2026/03/27/microsoft_ai_crusoe/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260928222354/https://www.crusoe.ai/resources/newsroom/crusoe-and-lancium-announce-1-gigawatt-ai-data-center-campus-in-childress-texas","id":"s3","published":"2026-07-15","publisher":"Crusoe","title":"Crusoe and Lancium announce 1.0 gigawatt AI data center campus in Childress, Texas","type":"company","url":"https://www.crusoe.ai/resources/newsroom/crusoe-and-lancium-announce-1-gigawatt-ai-data-center-campus-in-childress-texas"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-28","publisher":"Crusoe","title":"Crusoe developing data center campus in Armstrong County, Texas","type":"company","url":"https://www.crusoe.ai/resources/newsroom/crusoe-developing-data-center-campus-in-armstrong-county-texas"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Abilene, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Abilene,_Texas"}],"status":"under_construction","status_as_of":"2026-07-15","status_source_ids":["s3"],"summary":"Crusoe's second AI campus in Abilene, Texas, on Lancium-owned land adjacent to its first Abilene campus, announced in March 2026 to support large-scale AI workloads for Microsoft. The 900 MW site has two buildings, each designed for 336 MW of critical IT load, a 900 MW behind-the-meter on-site power plant paired with medium-voltage battery storage, and closed-loop, non-evaporative liquid cooling. Land clearing and site preparation were under way at announcement, Crusoe said in July 2026 that it was building the campus, and the first building is expected to be energized in mid-2027.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2eb43ea9-9af0-573a-80a9-aa67d7210065","s2":"36e3d518-b1a0-5bb8-891e-8e2031731430","s3":"f5738e1b-fb4e-5562-9bd9-a3c076403ff8","s4":"4a5bed5e-113e-5ad3-9602-75113749a4dd","s5":"3984266e-da0e-556b-b18b-5db9ee87f1d6"},"source_file":"datacenters/projects/crusoe-abilene-microsoft.json","source_record_id":"crusoe-abilene-microsoft","source_record_sha256":"b34d49d30f04664484e776e86777c3772a827321f238830f24821bcdc168ab5c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5bcb1d90b7891d23c03ca1ae3e3c95f57da435b4fbcf1af917fa37ff33dedeb4"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9f7647940a58e048e38f/#project-31ee01b0-a72b-5f4a-bcc1-a13a53732efc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/31ee01b0-a72b-5f4a-bcc1-a13a53732efc.json
32b98d7e-1d0f-5c16-af18-3f469f3b662b | imported:semiconductor-atlas:applied-digital-polaris-forge-1 | vcc-site-0ac82fd201fa1878b892 | epoch-ai:data-center:ae2c8749-c97f-5512-a0ad-a40ed8df37ce | Applied Digital Polaris Forge 1 | United States | US | 46.0042 | -98.5253 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid of Ellendale from its Wikipedia coordinates (s9), which also places the town in Dickey County; the company sources name the town but give no street address or parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | c443e1eb-bd36-5107-b264-4395e37f3645 | partially_operational | 2026-10-07 | 6 | imported_documented_status | 97790984-acdf-5857-bfa3-8344a62c86fb | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c443e1eb-bd36-5107-b264-4395e37f3645","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-polaris-forge-1"},{"evidence_id":"649cd638-4a5e-5f90-869a-a4073d36bd36","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-polaris-forge-1"},{"evidence_id":"c443e1eb-bd36-5107-b264-4395e37f3645","notes":"Two leases for 250 MW of critical IT load were announced in June 2025 with an option on a further 150 MW; by October 2025 the company described the full 400 MW of critical IT load as leased to CoreWeave.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"applied-digital-polaris-forge-1"},{"evidence_id":"4d7878ea-08ad-5e3c-9a3e-d4a669b53548","notes":"Two leases for 250 MW of critical IT load were announced in June 2025 with an option on a further 150 MW; by October 2025 the company described the full 400 MW of critical IT load as leased to CoreWeave.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"applied-digital-polaris-forge-1"},{"evidence_id":"1f3f4582-48b8-5490-9d67-31ac283d00c1","notes":"Two leases for 250 MW of critical IT load were announced in June 2025 with an option on a further 150 MW; by October 2025 the company described the full 400 MW of critical IT load as leased to CoreWeave.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"applied-digital-polaris-forge-1"},{"evidence_id":"649cd638-4a5e-5f90-869a-a4073d36bd36","notes":"Two leases for 250 MW of critical IT load were announced in June 2025 with an option on a further 150 MW; by October 2025 the company described the full 400 MW of critical IT load as leased to CoreWeave.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"applied-digital-polaris-forge-1"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | CoreWeave |  | https://ir.applieddigital.com/news-events/press-releases/detail/161/applied-digital-brings-an-additional-75-mw-of-ai | https://ir.applieddigital.com/news-events/press-releases/detail/123/applied-digital-announces-250mw-ai-data-center-lease-with | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Ellendale campus, confirmed by shared issuer results source. Source includes operating ELN buildings and planned total campus; existing record selects the remaining construction expansion.","source_record_id":"applied-digital-polaris-forge-1","target_physical_site_stable_key":"epoch-ai:data-center:ae2c8749-c97f-5512-a0ad-a40ed8df37ce"},"record":{"aliases":["Polaris Forge 1 AI Factory Campus","Applied Digital Ellendale AI campus"],"id":"applied-digital-polaris-forge-1","last_reviewed":"2026-10-09","location":{"admin1":"North Dakota","admin2":"Dickey County","country":"US","lat":46.0042,"locality":"Ellendale","lon":-98.5253,"note":"Town centroid of Ellendale from its Wikipedia coordinates (s9), which also places the town in Dickey County; the company sources name the town but give no street address or parcel.","precision":"locality","source_ids":["s1","s6","s7","s9"]},"metrics":[{"applies_to":"campus","as_of":"2025-10-27","basis":"contracted","metric":"power_capacity","note":"Critical IT load fully leased to CoreWeave at full buildout.","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s3","s6"],"unit":"MW","value":400},{"applies_to":"campus","as_of":"2026-10-01","basis":"operational","metric":"power_capacity","note":"Critical IT load operating across two buildings and 10 data halls after the second 75 MW phase of Building 2.","power_scope":"it_load","qualifier":"exact","source_ids":["s6","s7"],"unit":"MW","value":250},{"applies_to":"phase","as_of":"2025-11-24","basis":"operational","metric":"power_capacity","phase_label":"Building 1","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":100},{"applies_to":"phase","as_of":"2026-10-01","basis":"operational","metric":"power_capacity","phase_label":"Building 2","power_scope":"it_load","qualifier":"exact","source_ids":["s6","s7"],"unit":"MW","value":150},{"applies_to":"phase","as_of":"2026-10-07","basis":"under_construction","metric":"power_capacity","note":"The May 2026 bridge-loan release and the October 2026 results call this the third AI data center at the campus, while the June 2026 notes release calls it the fourth building (ELN-04); the notes were to repay the bridge loan, so both refer to the same building.","phase_label":"Third HPC building (ELN-04)","power_scope":"it_load","qualifier":"exact","source_ids":["s4","s5","s7"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2025-06-02","basis":"planned","metric":"power_capacity","note":"Long-term design ambition for the campus; the same release says more than 1 GW of power was in various stages of load study.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2025-11-24","basis":"planned","metric":"buildings","note":"Number of buildings contracted to CoreWeave at the time of the release.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":3}],"milestones":[{"date":"2025-06-02","event":"other","kind":"actual","note":"Two leases with CoreWeave for 250 MW of critical IT load announced, with an option on 150 MW more; the release already described the second building as under construction.","source_ids":["s1"]},{"date":"2025-10-27","event":"first_operational","kind":"actual","note":"First 50 MW phase of Building 1 reached ready for service.","source_ids":["s2"]},{"date":"2025-11-24","event":"other","kind":"actual","note":"Second 50 MW phase brought Building 1 to its full 100 MW.","source_ids":["s3"]},{"date":"2026-05-04","event":"other","kind":"actual","note":"Closing of a 300 million US dollar bridge facility to fund construction of the third AI building.","source_ids":["s4"]},{"date":"2026-07","event":"other","kind":"actual","note":"First 75 MW phase of Building 2 reached ready for service; company materials give June 30 and July 1, 2026 for this step.","source_ids":["s7","s8"]},{"date":"2026-10-01","event":"other","kind":"actual","note":"Second 75 MW phase completed Building 2, bringing the campus to 250 MW operating.","source_ids":["s6","s7"]},{"date":"2027","event":"other","kind":"planned","note":"Target year given in June 2025 for the third 150 MW building to be ready for service.","source_ids":["s1"]}],"name":"Applied Digital Polaris Forge 1","parties":[{"name":"Applied Digital","role":"developer","source_ids":["s1","s7"]},{"name":"CoreWeave","note":"Two leases for 250 MW of critical IT load were announced in June 2025 with an option on a further 150 MW; by October 2025 the company described the full 400 MW of critical IT load as leased to CoreWeave.","role":"tenant","source_ids":["s1","s2","s3","s7"]}],"power_sources":[],"related_ids":["applied-digital-polaris-forge-2","applied-digital-polaris-forge-3"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001152010/https://ir.applieddigital.com/news-events/press-releases/detail/123/applied-digital-announces-250mw-ai-data-center-lease-with","id":"s1","published":"2025-06-02","publisher":"Applied Digital","title":"Applied Digital Announces 250MW AI Data Center Lease With CoreWeave in North Dakota","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/123/applied-digital-announces-250mw-ai-data-center-lease-with"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260828124810/https://ir.applieddigital.com/news-events/press-releases/detail/133/applied-digital-achieves-ready-for-service-for-phase-1-at","id":"s2","published":"2025-10-27","publisher":"Applied Digital","title":"Applied Digital Achieves Ready for Service for Phase 1 at Polaris Forge 1 Building 1 for CoreWeave","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/133/applied-digital-achieves-ready-for-service-for-phase-1-at"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260921080658/https://ir.applieddigital.com/news-events/press-releases/detail/137/applied-digital-completes-phase-ii-ready-for-service-at","id":"s3","published":"2025-11-24","publisher":"Applied Digital","title":"Applied Digital Completes Phase II Ready for Service at Polaris Forge 1, Fully Energizing First 100 MW Building","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/137/applied-digital-completes-phase-ii-ready-for-service-at"},{"accessed":"2026-10-09","id":"s4","published":"2026-05-04","publisher":"Applied Digital","title":"Applied Digital Announces $300 Million Senior Secured Bridge Facility","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/150/applied-digital-announces-300-million-senior-secured"},{"accessed":"2026-10-09","id":"s5","published":"2026-06-09","publisher":"Applied Digital","title":"Applied Digital Announces Pricing of $1.59 Billion of Senior Secured Notes to fund the Fourth Building at Polaris Forge 1","type":"company","url":"https://ir.applieddigital.com/_assets/_f6377ac165e571402492e7df82cea1ee/appliedblockchaininc/news/2026-06-09_Applied_Digital_Announces_Pricing_of_1_59_Billion__156.pdf"},{"accessed":"2026-10-09","id":"s6","published":"2026-10-02","publisher":"Applied Digital","title":"Applied Digital Brings an Additional 75 MW of AI Infrastructure Online at Polaris Forge 1","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/161/applied-digital-brings-an-additional-75-mw-of-ai"},{"accessed":"2026-10-09","id":"s7","published":"2026-10-07","publisher":"U.S. Securities and Exchange Commission (Applied Digital filing)","title":"Applied Digital Reports Fiscal First Quarter 2027 Results (Form 8-K exhibit)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001144879/000114487926000057/apldq127earningsrelease.htm"},{"accessed":"2026-10-09","id":"s8","published":"2026-07-27","publisher":"Applied Digital","title":"Applied Digital Reports Fiscal Fourth Quarter and Full Year 2026 Results","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260908075941/https://en.wikipedia.org/wiki/Ellendale,_North_Dakota","id":"s9","published":null,"publisher":"Wikipedia","title":"Ellendale, North Dakota","type":"other","url":"https://en.wikipedia.org/wiki/Ellendale,_North_Dakota"}],"status":"partially_operational","status_as_of":"2026-10-07","status_source_ids":["s6","s7"],"summary":"Applied Digital's AI data center campus in Ellendale, North Dakota, leased entirely to CoreWeave under roughly 15-year leases covering 400 MW of critical IT load. The first 100 MW building came online in two 50 MW phases in October and November 2025, and the 150 MW second building came online in two 75 MW phases by October 2026, for 250 MW operating. A third 150 MW building (ELN-04) is under construction, financed through a bridge loan later refinanced with senior secured notes in June 2026.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c443e1eb-bd36-5107-b264-4395e37f3645","s2":"4d7878ea-08ad-5e3c-9a3e-d4a669b53548","s3":"1f3f4582-48b8-5490-9d67-31ac283d00c1","s4":"a3384878-ae23-5aef-84bd-f2472cf5b12a","s5":"04bdf086-bc27-5e07-917a-c52bd1c94e28","s6":"97790984-acdf-5857-bfa3-8344a62c86fb","s7":"649cd638-4a5e-5f90-869a-a4073d36bd36","s8":"b07d55c8-538f-5452-a26d-a30b83d496fe","s9":"af0cfb66-8fa7-5e8f-bb40-2276b74bf0b9"},"source_file":"datacenters/projects/applied-digital-polaris-forge-1.json","source_record_id":"applied-digital-polaris-forge-1","source_record_sha256":"02039c7978eb5ad0982cb959c5731f70118c004f1fe48428a14ffb1b20797de1","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"60c9d000b3220b2cc23d8ae0919df487da9838af251bd0a6dc5435df2b7b159e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ac82fd201fa1878b892/#project-32b98d7e-1d0f-5c16-af18-3f469f3b662b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/32b98d7e-1d0f-5c16-af18-3f469f3b662b.json
3315c754-ca0d-5702-8071-44b22787215a | imported:semiconductor-atlas:meta-kansas-city | vcc-site-60b38ee835b4579aa5f2 | imported:semiconductor-atlas:meta-kansas-city | Meta Kansas City data center | United States | US | 39.1001 | -94.5781 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City point from OpenStreetMap Nominatim; Meta names Kansas City but not the site. Meta's local funding goes to Clay County, Platte County and Kansas City-area groups, but no parcel is published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 09fd54b2-c42d-5a6e-bfe0-9b30a1c87a00 | operational | 2025-08-20 | 419 | imported_documented_status | f72feec7-9b57-5dae-b7d6-d86c7690cb58 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"09fd54b2-c42d-5a6e-bfe0-9b30a1c87a00","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-kansas-city"},{"evidence_id":"f72feec7-9b57-5dae-b7d6-d86c7690cb58","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-kansas-city"},{"evidence_id":"09fd54b2-c42d-5a6e-bfe0-9b30a1c87a00","notes":"Meta calls Evergy its utility partner.","party":"Evergy","relationship_scope":"unknown","role":"utility","source_record_id":"meta-kansas-city"},{"evidence_id":"28e75c9f-ba0c-5a0e-adab-3460af89efcc","notes":"Meta calls Evergy its utility partner.","party":"Evergy","relationship_scope":"unknown","role":"utility","source_record_id":"meta-kansas-city"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://datacenters.atmeta.com/2025/08/kansas-city-we-are-online/ | https://datacenters.atmeta.com/2022/03/hello-kansas-city/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Kansas City data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-kansas-city","source_relations":[{"reason":"Separate Lambda AI factory and Meta campus; coordinates are the same Kansas City civic location, not facility evidence.","relationship":"separate_named_developments","source_id":"lambda-kansas-city"}]},"record":{"aliases":["Kansas City Data Center"],"id":"meta-kansas-city","last_reviewed":"2026-10-09","location":{"admin1":"Missouri","country":"US","lat":39.1001,"locality":"Kansas City","lon":-94.5781,"note":"City point from OpenStreetMap Nominatim; Meta names Kansas City but not the site. Meta's local funding goes to Clay County, Platte County and Kansas City-area groups, but no parcel is published.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2022-03-24","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2025-08-20","basis":"announced","metric":"investment","note":"Stated as Meta's investment in the state of Missouri.","qualifier":"more_than","source_ids":["s2"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"From Meta's undated fact sheet, read 2026-10-09; labeled as data center investment in Missouri.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":1200000000},{"applies_to":"campus","as_of":"2022-03-24","basis":"planned","metric":"jobs_construction","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":1300},{"applies_to":"campus","as_of":"2025-08-20","basis":"reported","metric":"jobs_construction","note":"Meta describes this as the average number of skilled trade workers on site at peak construction.","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":1500},{"applies_to":"campus","as_of":"2025-08-20","basis":"planned","metric":"jobs_permanent","note":"Meta's 2022 announcement gave about 100.","qualifier":"more_than","source_ids":["s2","s3"],"unit":"count","value":100}],"milestones":[{"date":"2022-03-24","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2022","event":"construction_started","kind":"actual","source_ids":["s2","s3"]},{"date":"2025-08","event":"first_operational","kind":"actual","note":"Meta announced on 2025-08-20 that the data center was serving traffic; no earlier go-live date is given.","source_ids":["s2"]}],"name":"Meta Kansas City data center","notes":"Meta's fact sheet PDF (s3) shows no publication date; its embedded file creation date is 2026-09-02. Figures taken only from it carry the date it was read (2026-10-09).","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Evergy","note":"Meta calls Evergy its utility partner.","role":"utility","source_ids":["s1","s3"]}],"power_sources":[{"description":"Served by Evergy. Meta says it worked with Evergy on a market-based tariff that lets customers contract for new renewable energy, pays the full cost of its energy, and reports three Missouri projects adding 599 MW of clean energy.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260616183749/https://datacenters.atmeta.com/2022/03/hello-kansas-city/","id":"s1","published":"2022-03-24","publisher":"Meta Platforms","title":"Hello, Kansas City!","type":"company","url":"https://datacenters.atmeta.com/2022/03/hello-kansas-city/"},{"accessed":"2026-10-09","id":"s2","published":"2025-08-20","publisher":"Meta Platforms","title":"Kansas City, we are online!","type":"company","url":"https://datacenters.atmeta.com/2025/08/kansas-city-we-are-online/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Meta Platforms","title":"Meta Kansas City Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Metas-Kansas-City-Data-Center.pdf"}],"status":"operational","status_as_of":"2025-08-20","status_source_ids":["s2"],"summary":"Meta data center in Kansas City, Missouri, announced in March 2022 as an investment of more than USD 800 million and reported to be serving traffic in August 2025. Meta later put its Missouri investment at more than USD 1 billion and, in its fact sheet, USD 1.2 billion. Construction began in 2022, with an average of 1,500 skilled trade workers on site at peak. Evergy is the utility; Meta says it worked with Evergy on a tariff that lets customers contract for new renewable energy, and it reports three Missouri clean energy projects totaling 599 MW. No power capacity for the data center itself has been published.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"09fd54b2-c42d-5a6e-bfe0-9b30a1c87a00","s2":"f72feec7-9b57-5dae-b7d6-d86c7690cb58","s3":"28e75c9f-ba0c-5a0e-adab-3460af89efcc"},"source_file":"datacenters/projects/meta-kansas-city.json","source_record_id":"meta-kansas-city","source_record_sha256":"d5a16739885c6faee38a87b2fcc8bd21b6a278e697cf56b52e86e13524ae7479","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"90783635a2e19f4cfe10614b875a4690b0e8996639338f412d62ff279250bd0c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-60b38ee835b4579aa5f2/#project-3315c754-ca0d-5702-8071-44b22787215a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3315c754-ca0d-5702-8071-44b22787215a.json
337ace90-652d-52fe-a856-fe9b04b5966f | curated:meta-el-paso-texas-data-center:current-development | vcc-site-f711d13af70d9b633456 | curated:meta-el-paso-texas-data-center | Meta El Paso Current Development | United States | US | 31.994 | -106.3632 | Point | campus | Use the single exact-name community feature, verify its source object geometry, and emit the unchanged service longitude/latitude in GeoJSON order. | nominatim_exact_named_campus_reference_point | community_named_campus_reference_point | community_source | campus_locator | Source way explicitly says boundary very approximate. The returned point is only a broad campus locator consistent with the municipal north-of-Stan-Roberts, west-of-US54 description; neither the rectangle nor its slightly cross-state northern edge is selected as a legal boundary. No survey, exact building centroid, active construction footprint or bounded numerical accuracy is claimed. |  | Community mapper and geocoder provide no bounded horizontal accuracy; coordinate decimal places are not measurement precision. | 047b4c1b-72aa-5de6-b677-d5ba01d3a2a3 | under_construction | 2026-07-28 | 77 | authoritative_physical_status_update | 91268425-6f28-5804-9df4-bb26221064a1 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"2dae533a-a76f-54ec-a85e-7612134d111e","notes":"Provides construction management, administrative and property management services to the joint venture.","party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-el-paso"},{"evidence_id":"f02e15fa-a1b3-5612-a6ea-a0456570b944","notes":"Provides construction management, administrative and property management services to the joint venture.","party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-el-paso"},{"evidence_id":"f02e15fa-a1b3-5612-a6ea-a0456570b944","notes":"Retains a 20% stake in the joint venture.","party":"Meta Platforms","relationship_scope":"unknown","role":"owner","source_record_id":"meta-el-paso"},{"evidence_id":"f02e15fa-a1b3-5612-a6ea-a0456570b944","notes":"Initial sole occupant, with leases of a four-year initial term and four extension options for a potential 20-year term.","party":"Meta Platforms","relationship_scope":"unknown","role":"tenant","source_record_id":"meta-el-paso"},{"evidence_id":"f02e15fa-a1b3-5612-a6ea-a0456570b944","notes":"Funds managed by BlackRock hold 80% of the joint venture announced in July 2026.","party":"BlackRock (managed funds)","relationship_scope":"unknown","role":"owner","source_record_id":"meta-el-paso"},{"evidence_id":"6cab89c8-10b6-54f8-b9dc-9ddceb81655c","notes":null,"party":"El Paso Electric","relationship_scope":"unknown","role":"utility","source_record_id":"meta-el-paso"},{"evidence_id":"bd81d46b-e092-55c1-a90b-56ca6fc9d904","notes":null,"party":"El Paso Electric","relationship_scope":"unknown","role":"utility","source_record_id":"meta-el-paso"},{"evidence_id":"14234414-a555-5760-9bf2-fb50561e5fc2","notes":"Approved tax abatement and economic development agreements for the project.","party":"City of El Paso","relationship_scope":"unknown","role":"government","source_record_id":"meta-el-paso"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | BlackRock (managed funds); Meta Platforms |  |  | Meta Platforms |  | https://about.fb.com/news/2026/07/meta-announces-new-venture-with-blackrock-to-develop-data-center-in-el-paso/ | https://nominatim.openstreetmap.org/search?q=Meta%20El%20Paso&countrycodes=us&format=jsonv2&polygon_geojson=1 | [{"identity_decision":{"decision":"exact_project","flags":["approximate_locator_not_boundary"],"rationale":"Same Meta northeast El Paso campus development, operator and 2028 delivery program. Retain all sourced campus capacity definitions without assigning them to an individual building.","source_record_id":"meta-el-paso","target_project_stable_key":"curated:meta-el-paso-texas-data-center:current-development"},"record":{"aliases":["El Paso Data Center","Wurldwide Data Center"],"id":"meta-el-paso","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"El Paso County","country":"US","lat":31.9868,"locality":"El Paso","lon":-106.426,"note":"Sources place the campus in northeast El Paso off Stan Roberts Sr. Avenue and US 54. Coordinates are a Nominatim point on Stan Roberts Sr. Avenue near that junction, not the parcel centroid.","precision":"approximate_site","source_ids":["s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-07","basis":"planned","metric":"power_capacity","note":"Meta first said the site could scale to 1 GW; later reporting and the joint venture release describe 1 GW of compute capacity. IT versus facility scope is not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s3","s5"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-09-24","basis":"planned","metric":"power_capacity","note":"El Paso Electric's proposed McCloud gas plant on an adjacent site, still awaiting a Public Utility Commission of Texas decision.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s2","s6"],"unit":"MW","value":366},{"applies_to":"campus","as_of":"2025-10-15","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1500000000},{"applies_to":"campus","as_of":"2026-03-30","basis":"reported","metric":"investment","note":"Reported as Meta's planned spending after the increase from USD 1.5 billion.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2026-07","basis":"announced","metric":"investment","note":"Meta's own investment commitment.","qualifier":"more_than","source_ids":["s5","s7"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2026-07","basis":"reported","metric":"investment","note":"Total development cost of the Meta and BlackRock joint venture for buildings and long-lived power, cooling and connectivity infrastructure.","qualifier":"approximately","source_ids":["s5"],"unit":"USD","value":14000000000},{"applies_to":"campus","as_of":"2026-01-20","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s2"],"unit":"acres","value":1000},{"applies_to":"phase","as_of":"2025-10-15","basis":"planned","metric":"jobs_construction","note":"Peak construction workforce for the initial phase.","phase_label":"Initial phase","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":1800},{"applies_to":"campus","as_of":"2026-07","basis":"planned","metric":"jobs_construction","note":"Peak construction workforce; the July 2026 release said more than 2,300 workers were already on site.","qualifier":"more_than","source_ids":["s3","s5","s7"],"unit":"count","value":4000},{"applies_to":"campus","as_of":"2025-10-15","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":100},{"applies_to":"campus","as_of":"2026-07","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s3","s5","s7"],"unit":"count","value":300}],"milestones":[{"date":"2025-10-15","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-H2","event":"construction_started","kind":"actual","note":"Reported as breaking ground in late 2025.","source_ids":["s3"]},{"date":"2026-03","event":"expansion_announced","kind":"actual","note":"Reported on 2026-03-30: Meta's planned investment raised from USD 1.5 billion to USD 10 billion.","source_ids":["s3"]},{"date":"2026-07","event":"other","kind":"actual","note":"Joint venture with BlackRock-managed funds announced to develop and own the campus.","source_ids":["s5"]},{"date":"2026-09","event":"other","kind":"actual","note":"Administrative law judges proposed that the Public Utility Commission of Texas approve the McCloud gas plant only if ratepayers do not bear its capital and operating costs; no commission vote had been scheduled.","source_ids":["s6"]},{"date":"2028","event":"first_operational","kind":"planned","note":"Capacity is expected to begin coming online in 2028.","source_ids":["s3","s5"]}],"name":"Meta El Paso data center campus","notes":"Meta's joint venture release (s5) displays both 27 and 28 July 2026, so only the month is recorded. Meta's fact sheet PDF (s7) shows no publication date; its embedded file creation date is 2026-09-01.","parties":[{"name":"Meta Platforms","note":"Provides construction management, administrative and property management services to the joint venture.","role":"developer","source_ids":["s1","s5"]},{"name":"Meta Platforms","note":"Retains a 20% stake in the joint venture.","role":"owner","source_ids":["s5"]},{"name":"Meta Platforms","note":"Initial sole occupant, with leases of a four-year initial term and four extension options for a potential 20-year term.","role":"tenant","source_ids":["s5"]},{"name":"BlackRock (managed funds)","note":"Funds managed by BlackRock hold 80% of the joint venture announced in July 2026.","role":"owner","source_ids":["s5"]},{"name":"El Paso Electric","role":"utility","source_ids":["s2","s7"]},{"name":"City of El Paso","note":"Approved tax abatement and economic development agreements for the project.","role":"government","source_ids":["s4"]}],"power_sources":[{"description":"Meta says it planned its energy needs with El Paso Electric and pays the full cost of the energy and infrastructure needed to serve the data center.","source_ids":["s7"],"type":"grid"},{"description":"El Paso Electric proposed the 366 MW McCloud plant on about 31 acres next to the campus, made up of 813 modular 450 kW gas generators supplied by Enchanted Rock; it would serve only Meta for its first five years. Reported cost estimates differ (USD 473 million in January 2026, USD 499 million in September 2026), and a state utility commission vote was still pending in late September 2026.","source_ids":["s2","s6"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251113051159/https://www.fox26houston.com/news/meta-ai-data-center-texas-el-paso","id":"s1","published":"2025-10-15","publisher":"FOX 26 Houston","title":"Meta to spend $1.5 billion on AI data center in Texas","type":"news","url":"https://www.fox26houston.com/news/meta-ai-data-center-texas-el-paso"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260418042719/https://constructionreporter.com/el-paso-electric-announces-plans-for-366-megawatt-electric-plant-to-support-meta-data-center/","id":"s2","published":"2026-01-20","publisher":"Construction Reporter","title":"El Paso Electric Announces Plans for 366 Megawatt Electric Plant to Support Meta Data Center","type":"trade_press","url":"https://constructionreporter.com/el-paso-electric-announces-plans-for-366-megawatt-electric-plant-to-support-meta-data-center/"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-30","publisher":"Silicon UK","title":"Meta Ramps Spending On El Paso Data Centre To $10bn","type":"trade_press","url":"https://www.silicon.co.uk/cloud/datacenter/meta-data-centre-el-paso-629273"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260731200901/https://kfoxtv.com/news/local/el-paso-leaders-get-update-on-meta-data-center-project-city-cites-enforceable-agreements","id":"s4","published":"2026-04-13","publisher":"KFOX14","title":"El Paso leaders get update on Meta data center project, city cites enforceable agreements","type":"news","url":"https://kfoxtv.com/news/local/el-paso-leaders-get-update-on-meta-data-center-project-city-cites-enforceable-agreements"},{"accessed":"2026-10-09","id":"s5","published":"2026-07","publisher":"Meta Platforms","title":"Meta Announces New Strategic Venture With BlackRock to Develop Data Center in El Paso","type":"company","url":"https://about.fb.com/news/2026/07/meta-announces-new-venture-with-blackrock-to-develop-data-center-in-el-paso/"},{"accessed":"2026-10-09","id":"s6","published":"2026-09-24","publisher":"Inside Climate News","title":"Texas Electric Utility Only Considered Gas to Power $10 Billion Meta Data Center","type":"news","url":"https://insideclimatenews.org/news/24092026/el-paso-electric-only-considered-gas-to-power-meta-data-center/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260923214153/https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-El-Paso-Data-Center.pdf","id":"s7","published":null,"publisher":"Meta Platforms","title":"Meta El Paso Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-El-Paso-Data-Center.pdf"}],"status":"under_construction","status_as_of":"2026-09-24","status_source_ids":["s5","s6"],"summary":"AI-oriented Meta campus on roughly 1,000 acres in northeast El Paso, Texas, off Stan Roberts Sr. Avenue near US 54. Announced in October 2025 as a USD 1.5 billion project able to scale to 1 GW, it rose to USD 10 billion or more of Meta investment in 2026. In July 2026 Meta placed it in a joint venture 80% owned by BlackRock-managed funds, with a total development cost of about USD 14 billion and capacity due to start coming online in 2028. El Paso Electric has proposed a 366 MW modular gas plant beside the campus; in September 2026 state judges recommended approving it only if ratepayers do not bear its costs.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2dae533a-a76f-54ec-a85e-7612134d111e","s2":"6cab89c8-10b6-54f8-b9dc-9ddceb81655c","s3":"4ccfc743-791a-5bde-b126-4f3afa2e32a5","s4":"14234414-a555-5760-9bf2-fb50561e5fc2","s5":"f02e15fa-a1b3-5612-a6ea-a0456570b944","s6":"4e69cd79-35ff-5c6c-82ac-1ead549dc29d","s7":"bd81d46b-e092-55c1-a90b-56ca6fc9d904"},"source_file":"datacenters/projects/meta-el-paso.json","source_record_id":"meta-el-paso","source_record_sha256":"be1879b543b0ada955c7ab4a7ecebeb6d0d63a8bc5b4b2467644b09395dfd1dc","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0894098cfa0f72755af68c6960065e94ba5d2ec92d995958cb1cf4ed4adc1a9e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f711d13af70d9b633456/#project-337ace90-652d-52fe-a856-fe9b04b5966f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/337ace90-652d-52fe-a856-fe9b04b5966f.json
33a0110e-c5fb-58d0-8913-81aef5fdd9d3 | imported:semiconductor-atlas:airtrunk-kurri-kurri | vcc-site-63d7eb757cdf71a1ae84 | imported:semiconductor-atlas:airtrunk-kurri-kurri | AirTrunk Kurri Kurri Data Centre | Australia | AU | -32.8167 | 151.4833 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name the former Kurri Kurri smelter site on Hart Road, Loxford, without coordinates; the point is the Kurri Kurri town coordinate from its Wikipedia article, so it marks the neighbouring town rather than the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 7745e0a7-3b94-55f1-b9e7-f4c7b4e8eb78 | proposed | 2026-09-21 | 22 | imported_documented_status | baa735f1-e94d-5d9a-be5f-1288d2a7bc70 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"7745e0a7-3b94-55f1-b9e7-f4c7b4e8eb78","notes":"Proponent. Newcastle Weekly's July 2026 coverage of the scoping report named planning consultancy ADW Johnson as lodging it, without naming the developer.","party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-kurri-kurri"},{"evidence_id":"951668c9-10ec-5382-a236-06d6f8abf0cb","notes":"Proponent. Newcastle Weekly's July 2026 coverage of the scoping report named planning consultancy ADW Johnson as lodging it, without naming the developer.","party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-kurri-kurri"},{"evidence_id":"98de44e5-bfeb-52d9-925e-03905b2c2058","notes":"Proponent. Newcastle Weekly's July 2026 coverage of the scoping report named planning consultancy ADW Johnson as lodging it, without naming the developer.","party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-kurri-kurri"},{"evidence_id":"98de44e5-bfeb-52d9-925e-03905b2c2058","notes":"The Newcastle Herald reports the site is on land owned by the McCloy Group.","party":"McCloy Group","relationship_scope":"unknown","role":"owner","source_record_id":"airtrunk-kurri-kurri"},{"evidence_id":"baa735f1-e94d-5d9a-be5f-1288d2a7bc70","notes":"Assessing the project as state significant development; issued the assessment requirements.","party":"NSW Department of Planning, Housing and Infrastructure","relationship_scope":"unknown","role":"government","source_record_id":"airtrunk-kurri-kurri"},{"evidence_id":"cf3afe70-0bf2-5998-b5b7-9dfc68f060b4","notes":"Assessing the project as state significant development; issued the assessment requirements.","party":"NSW Department of Planning, Housing and Infrastructure","relationship_scope":"unknown","role":"government","source_record_id":"airtrunk-kurri-kurri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | McCloy Group |  |  |  |  | https://www.planningportal.nsw.gov.au/major-projects/projects/kurri-kurri-data-centre | https://airtrunk.com/kurri-kurri/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AirTrunk Kurri Kurri Data Centre as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"airtrunk-kurri-kurri"},"record":{"aliases":["Kurri Kurri Data Centre","SSD-128819490"],"id":"airtrunk-kurri-kurri","last_reviewed":"2026-10-09","location":{"admin1":"New South Wales","admin2":"City of Cessnock","country":"AU","lat":-32.8167,"locality":"Loxford (Kurri Kurri)","lon":151.4833,"note":"Sources name the former Kurri Kurri smelter site on Hart Road, Loxford, without coordinates; the point is the Kurri Kurri town coordinate from its Wikipedia article, so it marks the neighbouring town rather than the site.","precision":"locality","source_ids":["s1","s2","s3","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-15","basis":"planned","metric":"power_capacity","note":"The NSW planning portal describes 540 MW as total power consumption of the data center.","power_scope":"facility","qualifier":"exact","source_ids":["s2","s3","s4"],"unit":"MW","value":540},{"applies_to":"campus","as_of":"2026-09-21","basis":"reported","metric":"investment","note":"Figure reported by W.Media; AirTrunk's project page gives only community infrastructure commitments.","qualifier":"approximately","source_ids":["s3"],"unit":"AUD","value":3700000000},{"applies_to":"campus","as_of":"2026-09-21","basis":"planned","metric":"floor_area","note":"Two-storey building about 16.8 m high; Newcastle Weekly describes this as gross floor area.","qualifier":"approximately","source_ids":["s1","s3","s4"],"unit":"sq_m","value":44220},{"applies_to":"campus","as_of":"2026-09-21","basis":"planned","metric":"jobs_permanent","note":"AirTrunk's figure of ongoing local jobs, about 250 on site and more than 100 off site. The July 2026 scoping report coverage gave 250 ongoing jobs.","qualifier":"more_than","source_ids":["s1","s3"],"unit":"count","value":350},{"applies_to":"campus","as_of":"2026-07-15","basis":"planned","metric":"jobs_construction","note":"Figure from coverage of the scoping report; AirTrunk later spoke of several thousand construction jobs.","qualifier":"approximately","source_ids":["s4"],"unit":"count","value":500}],"milestones":[{"date":"2026-07","event":"other","kind":"actual","note":"Scoping report lodged and the planning department issued the Secretary's Environmental Assessment Requirements, as reported by mid-July 2026.","source_ids":["s4"]},{"date":"2026-09","event":"other","kind":"actual","note":"AirTrunk said it lodged the environmental impact statement; the portal still showed the Prepare EIS stage and public exhibition had not started.","source_ids":["s3"]},{"date":"2028","event":"first_operational","kind":"planned","note":"Opening year given in Newcastle Herald reporting on AirTrunk's energy plans; Newcastle Weekly reported that construction would take about 14 months.","source_ids":["s4","s5"]}],"name":"AirTrunk Kurri Kurri Data Centre","notes":"Not approved: the project awaits public exhibition and determination. A Newcastle Herald opinion column speculated about a possible tenant; no end user has been confirmed, so none is recorded. Wikipedia is cited only for the town coordinate.","parties":[{"name":"AirTrunk","note":"Proponent. Newcastle Weekly's July 2026 coverage of the scoping report named planning consultancy ADW Johnson as lodging it, without naming the developer.","role":"developer","source_ids":["s1","s3","s5"]},{"name":"McCloy Group","note":"The Newcastle Herald reports the site is on land owned by the McCloy Group.","role":"owner","source_ids":["s5"]},{"name":"NSW Department of Planning, Housing and Infrastructure","note":"Assessing the project as state significant development; issued the assessment requirements.","role":"government","source_ids":["s2","s4"]}],"power_sources":[{"description":"Connection to a 132 kV line, with AirTrunk funding the connection and a new on-site substation.","source_ids":["s1","s3"],"type":"grid"},{"description":"Renewable supply under negotiation with three suppliers in the Hunter Renewable Energy Zone, with about 70 to 75 percent clean energy expected at opening and 90 to 100 percent targeted by 2030; AirTrunk was also in talks with Snowy Hydro about firmed capacity from the nearby gas-fired Kurri peaking plant.","source_ids":["s5"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"AirTrunk","title":"Kurri Kurri Data Centre","type":"company","url":"https://airtrunk.com/kurri-kurri/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"NSW Planning Portal","title":"Kurri Kurri Data Centre (SSD-128819490)","type":"government","url":"https://www.planningportal.nsw.gov.au/major-projects/projects/kurri-kurri-data-centre"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-21","publisher":"W.Media","title":"AirTrunk proposes AUD 3.7bn NSW data centre with AUD 37m community offer","type":"trade_press","url":"https://w.media/?p=43650"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-15","publisher":"Newcastle Weekly","title":"540MW AI data centre planned for Kurri Kurri","type":"news","url":"https://newcastleweekly.com.au/540mw-ai-data-centre-planned-for-kurri-kurri/"},{"accessed":"2026-10-09","id":"s5","published":"2026-08-13","publisher":"Newcastle Herald","title":"Kurri data centre energy whale needs its own power supply","type":"news","url":"https://www.newcastleherald.com.au/story/9328857/kurri-data-centre-energy-whale-needs-its-own-power-supply/"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Kurri Kurri","type":"other","url":"https://en.wikipedia.org/wiki/Kurri_Kurri"}],"status":"proposed","status_as_of":"2026-09-21","status_source_ids":["s2","s3"],"summary":"AirTrunk proposes a 540 MW data center on the former Hydro Aluminium smelter site on Hart Road, Loxford, near Kurri Kurri in the Hunter region of New South Wales. It is being assessed as state significant development; the NSW planning department issued assessment requirements by July 2026 and AirTrunk said it lodged an environmental impact statement in September 2026. Plans show a two-storey building of about 44,220 square metres with air-based cooling and a 132 kV grid connection with a new substation. Coverage puts the investment at about A$3.7 billion, and AirTrunk told local press it targets opening in 2028.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"7745e0a7-3b94-55f1-b9e7-f4c7b4e8eb78","s2":"baa735f1-e94d-5d9a-be5f-1288d2a7bc70","s3":"951668c9-10ec-5382-a236-06d6f8abf0cb","s4":"cf3afe70-0bf2-5998-b5b7-9dfc68f060b4","s5":"98de44e5-bfeb-52d9-925e-03905b2c2058","s6":"d49522c6-9d9d-5a26-988b-282a3d2fe205"},"source_file":"datacenters/projects/airtrunk-kurri-kurri.json","source_record_id":"airtrunk-kurri-kurri","source_record_sha256":"98d520605685f0f77ee56bdea85284a1e856996edbede4d55331e26716aa03ec","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8744c8432a1ec7ae76b18ea57f26cb38f3af00f679b2e71aa89d74bbbf2da60b"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-63d7eb757cdf71a1ae84/#project-33a0110e-c5fb-58d0-8913-81aef5fdd9d3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/33a0110e-c5fb-58d0-8913-81aef5fdd9d3.json
352e29e6-cabf-5acb-bd20-619157576502 | imported:semiconductor-atlas:kio-qro3-queretaro | vcc-site-8626707eb0091306e3b9 | imported:semiconductor-atlas:kio-qro3-queretaro | KIO Data Centers QRO3, Querétaro | Mexico | MX | 20.5664 | -100.2567 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Mexico Business News places QRO3 on KIO's campus in the El Marqués Industrial Park. The point is the existing building tagged 'Centro de datos KIO QRO1 y QRO2' in the local OpenStreetMap layer (datacenters/layers/osm/features.geojson, OSM way 741133962); exactly where QRO3 would sit on or near that campus is not reported. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 13c130cf-a2a7-51db-9d24-6b6aef94d717 | proposed | 2026-08-17 | 57 | imported_documented_status | 13c130cf-a2a7-51db-9d24-6b6aef94d717 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"13c130cf-a2a7-51db-9d24-6b6aef94d717","notes":null,"party":"KIO Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"kio-qro3-queretaro"},{"evidence_id":"da270c34-f1f4-57e3-8854-a7b8de2545bd","notes":null,"party":"KIO Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"kio-qro3-queretaro"},{"evidence_id":"49bc04f5-03f8-5050-8989-33c858f7891a","notes":null,"party":"KIO Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"kio-qro3-queretaro"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://mexicobusiness.news/trade-and-investment/news/kio-plans-us13-billion-data-center-queretaro | https://mexicobusiness.news/trade-and-investment/news/kio-plans-us13-billion-data-center-queretaro | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve KIO Data Centers QRO3, Querétaro as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"kio-qro3-queretaro"},"record":{"aliases":["QRO3"],"id":"kio-qro3-queretaro","last_reviewed":"2026-10-09","location":{"admin1":"Querétaro","country":"MX","lat":20.56636,"locality":"El Marqués Industrial Park","lon":-100.256724,"note":"Mexico Business News places QRO3 on KIO's campus in the El Marqués Industrial Park. The point is the existing building tagged 'Centro de datos KIO QRO1 y QRO2' in the local OpenStreetMap layer (datacenters/layers/osm/features.geojson, OSM way 741133962); exactly where QRO3 would sit on or near that campus is not reported.","precision":"approximate_site","source_ids":["s1"]},"metrics":[{"applies_to":"phase","as_of":"2026-08-17","basis":"planned","metric":"power_capacity","note":"Sources do not say whether this is IT or facility capacity; W.Media and Mexico Industry present it as conditional on the project going ahead.","phase_label":"QRO3","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"MW","value":100},{"applies_to":"phase","as_of":"2026-08-17","basis":"reported","metric":"investment","note":"Potential investment through 2030 that KIO was described as evaluating rather than committing. Mexico Business News (s1) gives about USD 1.3 billion and does not mention 2030.","phase_label":"QRO3","qualifier":"up_to","source_ids":["s2","s3"],"unit":"USD","value":1300000000}],"milestones":[{"date":"2026-08","event":"other","kind":"actual","note":"KIO presented QRO3 as a project under consideration, alongside an event at which the Economy Ministry gave KIO the Hecho en México designation. Recorded as a proposal rather than a formal announcement.","source_ids":["s1","s2","s3"]}],"name":"KIO Data Centers QRO3, Querétaro","notes":"Status is 'proposed': W.Media says KIO is considering the expansion, and Mexico Industry says KIO is evaluating the investment. Mexico Business News calls the event an announcement, but no opened source reports a formal commitment, and KIO's own release was not opened. The estimate of more than 8,100 direct and indirect jobs is tied to QRO3 by Mexico Business News but to KIO's wider 2030 strategy by Mexico Industry, so it is not a metric. W.Media says KIO's existing QRO2 building in Querétaro is a 12 MW Tier III facility; it is not part of QRO3. W.Media notes grid capacity is a constraint in Querétaro; no power arrangement for QRO3 has been reported.","parties":[{"name":"KIO Data Centers","role":"developer","source_ids":["s1","s2","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-08-14","publisher":"Mexico Business News","title":"KIO Plans US$1.3 Billion Data Center in Queretaro","type":"trade_press","url":"https://mexicobusiness.news/trade-and-investment/news/kio-plans-us13-billion-data-center-queretaro"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-14","publisher":"W.Media","title":"KIO Data Centers considering 100 MW expansion in Mexico","type":"trade_press","url":"https://w.media/kio-data-centers-considering-100-mw-expansion-in-mexico/"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-17","publisher":"Mexico Industry","title":"KIO Data Centers supera los 900 millones de dólares invertidos; proyecta expansión hacia 2030","type":"trade_press","url":"https://mexicoindustry.com/noticia/kio-data-centers-supera-los-900-millones-de-dolares-invertidos-proyecta-expansion-hacia-2030"}],"status":"proposed","status_as_of":"2026-08-17","status_source_ids":["s1","s2","s3"],"summary":"QRO3 is a proposed next phase of KIO Data Centers' technology campus in the El Marqués Industrial Park in Querétaro, Mexico. In August 2026, around an event at which Mexico's Economy Ministry gave KIO the Hecho en México designation, KIO outlined QRO3 as an expansion of about 100 MW that would be its largest data center, with an investment of up to USD 1.3 billion through 2030. Two of the three trade reports describe the investment as under evaluation or dependent on the project going ahead, and no construction schedule has been disclosed. KIO linked the plan to demand for cloud and AI services.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"13c130cf-a2a7-51db-9d24-6b6aef94d717","s2":"da270c34-f1f4-57e3-8854-a7b8de2545bd","s3":"49bc04f5-03f8-5050-8989-33c858f7891a"},"source_file":"datacenters/projects/kio-qro3-queretaro.json","source_record_id":"kio-qro3-queretaro","source_record_sha256":"3fcbdddd0394a4007cbb1d1f2f5f6b03be006d2c4278b477af1a718d233745c9","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"db1d0876190d32b57c15af331c157c0063aa181630c7fe763819a57447fb0fa7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8626707eb0091306e3b9/#project-352e29e6-cabf-5acb-bd20-619157576502 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/352e29e6-cabf-5acb-bd20-619157576502.json
35995588-0599-5f9b-bc3d-29f9f67ea81b | imported:semiconductor-atlas:coreweave-kenilworth-new-jersey | vcc-site-7ceb4cfa4ba358ea4547 | imported:semiconductor-atlas:coreweave-kenilworth-new-jersey | CoreWeave Kenilworth NEST 11 AI data center | United States | US | 40.6781 | -74.2881 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Borough centroid from the Wikipedia infobox for Kenilworth (s6), which also gives Union County. Sources place the building at 2000 Galloping Hill Road on the roughly 108-acre NEST campus, but no geocoder was used, so the point is the borough centroid rather than the building. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | e5ef1215-681f-5d68-9a47-e7992ada26ad | under_construction | 2026-10-09 | 4 | imported_documented_status | 6a554c10-c6b3-5529-be5d-0076b51966ff | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e5ef1215-681f-5d68-9a47-e7992ada26ad","notes":null,"party":"CoreWeave","relationship_scope":"unknown","role":"developer","source_record_id":"coreweave-kenilworth-new-jersey"},{"evidence_id":"982063f5-f73a-5cb1-bd5e-47041f610219","notes":null,"party":"CoreWeave","relationship_scope":"unknown","role":"developer","source_record_id":"coreweave-kenilworth-new-jersey"},{"evidence_id":"982063f5-f73a-5cb1-bd5e-47041f610219","notes":"Bought the building and 27 adjacent acres in August 2025 after first leasing it from a venture of Onyx Equities and Machine Investment Group.","party":"CoreWeave","relationship_scope":"unknown","role":"owner","source_record_id":"coreweave-kenilworth-new-jersey"},{"evidence_id":"e5ef1215-681f-5d68-9a47-e7992ada26ad","notes":"Said in 2024 it would begin preparing local electrical infrastructure for the facility.","party":"PSE&G","relationship_scope":"unknown","role":"utility","source_record_id":"coreweave-kenilworth-new-jersey"},{"evidence_id":"982063f5-f73a-5cb1-bd5e-47041f610219","notes":"Approved a 250 million US dollar tax credit under the Next New Jersey Program - AI on November 12, 2025.","party":"New Jersey Economic Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"coreweave-kenilworth-new-jersey"},{"evidence_id":"70d3aa71-d897-56ec-96b6-d478c50957f4","notes":"Approved a 250 million US dollar tax credit under the Next New Jersey Program - AI on November 12, 2025.","party":"New Jersey Economic Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"coreweave-kenilworth-new-jersey"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | CoreWeave |  |  |  |  | https://www.coreweave.com/ai-data-center-development/kenilworth-new-jersey | https://re-nj.com/ai-startup-coreweave-to-build-1-billion-data-center-at-onyxs-nest-campus-in-kenilworth/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve CoreWeave Kenilworth NEST 11 AI data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"coreweave-kenilworth-new-jersey"},"record":{"aliases":["Kenilworth NEST 11","CoreWeave Kenilworth AI Data Center"],"id":"coreweave-kenilworth-new-jersey","last_reviewed":"2026-10-09","location":{"admin1":"New Jersey","admin2":"Union County","country":"US","lat":40.6781,"locality":"Kenilworth","lon":-74.2881,"note":"Borough centroid from the Wikipedia infobox for Kenilworth (s6), which also gives Union County. Sources place the building at 2000 Galloping Hill Road on the roughly 108-acre NEST campus, but no geocoder was used, so the point is the borough centroid rather than the building.","precision":"locality","source_ids":["s1","s2","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2024-10-24","basis":"announced","metric":"investment","note":"Figure the article's headline gives for the data center at the lease announcement; the body says the conversion is part of a planned 1.2 billion US dollar CoreWeave investment without giving a site breakdown.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2025-11-25","basis":"incentive_agreement","metric":"investment","note":"Project cost cited by the state EDA with the tax credit award; reported as nearly 1.8 billion US dollars.","qualifier":"approximately","source_ids":["s2"],"unit":"USD","value":1760000000},{"applies_to":"campus","as_of":"2025-11-25","basis":"planned","metric":"power_capacity","note":"Figure reported with the EDA award; conflicts with the 40 MW on CoreWeave's own site page.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Planned load listed on CoreWeave's undated NEST 11 page, accessed on this date; the sources do not explain the gap with the 250 MW figure.","power_scope":"unspecified","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":40},{"applies_to":"campus","as_of":"2025-11-25","basis":"under_construction","metric":"floor_area","note":"Retrofit of the existing 284,500 sq ft 11 NEST building plus 108,100 sq ft of new construction.","qualifier":"exact","source_ids":["s2"],"unit":"sq_ft","value":392600},{"applies_to":"campus","as_of":"2024-10-24","basis":"planned","metric":"floor_area","note":"Size of the existing lab and manufacturing building as described at the 2024 lease announcement.","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":280000},{"applies_to":"campus","as_of":"2025-11-25","basis":"acquired","metric":"land_area","note":"Adjacent acreage bought with the building.","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":27},{"applies_to":"campus","as_of":"2025-11-25","basis":"planned","metric":"jobs_permanent","note":"Jobs committed under the state tax credit; CoreWeave's page says more than 140.","qualifier":"exact","source_ids":["s2"],"unit":"count","value":143},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_construction","note":"Union construction and skilled trade jobs cited on CoreWeave's undated site page, accessed on this date.","qualifier":"more_than","source_ids":["s4"],"unit":"count","value":1500}],"milestones":[{"date":"2024-10-24","event":"announced","kind":"actual","note":"Long-term lease of the building and conversion plan announced.","source_ids":["s1"]},{"date":"2025-08","event":"site_acquired","kind":"actual","note":"Purchase of the building and 27 adjacent acres for 322 million US dollars.","source_ids":["s2"]},{"date":"2025-09","event":"construction_started","kind":"actual","note":"Mid-September 2025, according to the EDA.","source_ids":["s2"]},{"date":"2025-11-12","event":"other","kind":"actual","note":"EDA approved a five-year, 250 million US dollar tax credit, the first award under the Next New Jersey Program - AI.","source_ids":["s2","s3"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Operations expected in early 2027.","source_ids":["s2"]}],"name":"CoreWeave Kenilworth NEST 11 AI data center","notes":"CoreWeave's Kenilworth page is undated; status_as_of is the date it was accessed, when it still described the facility as being built. Capacity figures conflict: trade press reported 250 MW with the state tax credit award, while CoreWeave's page lists a planned 40 MW load for NEST 11.","parties":[{"name":"CoreWeave","role":"developer","source_ids":["s1","s2"]},{"name":"CoreWeave","note":"Bought the building and 27 adjacent acres in August 2025 after first leasing it from a venture of Onyx Equities and Machine Investment Group.","role":"owner","source_ids":["s2"]},{"name":"PSE&G","note":"Said in 2024 it would begin preparing local electrical infrastructure for the facility.","role":"utility","source_ids":["s1"]},{"name":"New Jersey Economic Development Authority","note":"Approved a 250 million US dollar tax credit under the Next New Jersey Program - AI on November 12, 2025.","role":"government","source_ids":["s2","s3"]}],"power_sources":[{"description":"Utility supply prepared by PSE&G; CoreWeave says it is funding about 150 million US dollars of new substation and electrical infrastructure.","source_ids":["s1","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-10-24","publisher":"Real Estate NJ","title":"A.I. cloud startup CoreWeave to build $1 billion data center at Onyx's NEST campus in Kenilworth","type":"trade_press","url":"https://re-nj.com/ai-startup-coreweave-to-build-1-billion-data-center-at-onyxs-nest-campus-in-kenilworth/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260828124916/https://re-nj.com/coreweave-begins-1-8-billion-data-center-project-in-kenilworth-landing-first-award-under-new-eda-tax-credit-program/","id":"s2","published":"2025-11-25","publisher":"Real Estate NJ","title":"CoreWeave begins $1.8 billion data center project in Kenilworth, landing first award under new EDA tax credit program","type":"trade_press","url":"https://re-nj.com/coreweave-begins-1-8-billion-data-center-project-in-kenilworth-landing-first-award-under-new-eda-tax-credit-program/"},{"accessed":"2026-10-09","id":"s3","published":"2026-08","publisher":"New Jersey Economic Development Authority","title":"Next NJ Program - AI approvals table","type":"government","url":"https://www.njeda.gov/wp-content/uploads/2026/08/NextNJAI-1.pdf"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"CoreWeave","title":"Kenilworth, NJ AI Data Center","type":"company","url":"https://www.coreweave.com/ai-data-center-development/kenilworth-new-jersey"},{"accessed":"2026-10-09","id":"s5","published":"2026-05-14","publisher":"ABC7 New York","title":"Community rallies against construction of giant data center in small NJ town","type":"news","url":"https://abc7ny.com/post/community-rallies-giant-data-center-being-built-kenilworth-new-jersey/19053270/"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Kenilworth, New Jersey","type":"other","url":"https://en.wikipedia.org/wiki/Kenilworth,_New_Jersey"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s4","s5"],"summary":"CoreWeave is converting a 1982 pharmaceutical research building (11 NEST) on the former Merck campus, now the Northeast Science and Technology Center on Galloping Hill Road in Kenilworth, New Jersey, into an AI data center. It leased the building in October 2024, bought it with 27 adjacent acres for 322 million US dollars in August 2025, and started construction in September 2025. In November 2025 the state EDA approved a 250 million US dollar tax credit for the roughly 1.76 billion US dollar project, reported at 250 MW. CoreWeave's own site page lists 40 MW of planned load. Opening is targeted for early 2027 amid growing local opposition.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e5ef1215-681f-5d68-9a47-e7992ada26ad","s2":"982063f5-f73a-5cb1-bd5e-47041f610219","s3":"70d3aa71-d897-56ec-96b6-d478c50957f4","s4":"6a554c10-c6b3-5529-be5d-0076b51966ff","s5":"5458a5ab-8e38-51b4-a6fe-d450ec5054f1","s6":"e2804eda-dcea-5a55-b880-2ea9c8236852"},"source_file":"datacenters/projects/coreweave-kenilworth-new-jersey.json","source_record_id":"coreweave-kenilworth-new-jersey","source_record_sha256":"104b146b92b2f23f15d3b5d80e82e4c6713b45256e9af367a33b752028dec87f","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b7429ba09a0b37d2d037486979baf5b75d8dba97e709effd93ad4ed9e649b99a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7ceb4cfa4ba358ea4547/#project-35995588-0599-5f9b-bc3d-29f9f67ea81b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/35995588-0599-5f9b-bc3d-29f9f67ea81b.json
35c427dc-af95-5011-b3ab-3fa7c90fcb30 | curated:telecom-egypt-rdh2-smart-village-campus:regional-data-hub-2 | vcc-site-4d39b5b9701e6327b926 | curated:telecom-egypt-rdh2-smart-village-campus | Telecom Egypt Regional Data Hub 2 | Egypt | EG | 30.0767 | 31.0218 | Polygon | host_estate | osm_way_nodes_to_polygon | osm_smart_village_way_545580264_v6_retained_as_host_estate_context_not_campus_locator | community_host_development_polygon_context_only | community_source | host_estate_context | Entire Smart Village business park in Giza as mapped by OSM way 545580264 version 6: a 12-vertex community polygon (a closed way of 13 node references) of about 382.32 ha (WGS84 geodesic, diagnostic). The selected project evidence places RDH2 only in Smart Village; no reviewed source places RDH2 at any position within, or confirms containment in, this polygon. In the 2026-10-08 OSM snapshot it contains 88 mapped buildings, 38 of them named, among them Vodafone Egypt, Orange Egypt, Microsoft, Oracle, IBM, Huawei, Ericsson, HSBC, the National Telecom Regulatory Authority and the communications ministry, plus a separate Telecom Egypt office building and a TE Data building; none is named or tagged as RDH2 or a data centre. Host-development locality context only: not an RDH2 locator, parcel, boundary, footprint or work extent. The display anchor is the planar centroid of the business park's longitude/latitude ring, kept unchanged only because the row schema requires a point; it is not an RDH2 position. |  | RDH2's position relative to this host-development outline is unknown and no source bounds it; OpenStreetMap states no positional accuracy for the outline. No numeric uncertainty is asserted. | d222545d-ed52-5967-9482-5e9fff4d291b | commissioning | 2026-06-10 | 125 | authoritative_physical_status_update | 40643f27-70ef-5a86-9901-863476f5ddf1 | recent_authoritative_physical_observation_plus_host_estate_context_only | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.16 country-diversity batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/embed/feed/update/urn:li:activity:7470418236245942286 | https://api.openstreetmap.org/api/0.6/way/545580264/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4d39b5b9701e6327b926/#project-35c427dc-af95-5011-b3ab-3fa7c90fcb30 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/35c427dc-af95-5011-b3ab-3fa7c90fcb30.json
3641032c-9acd-5840-b94b-beab26a1ce0d | imported:semiconductor-atlas:stack-amazon-resilient-technology-park-shreveport | vcc-site-1246c2b9750b8b4832d2 | imported:semiconductor-atlas:stack-amazon-resilient-technology-park-shreveport | Amazon and STACK campus at Resilient Technology Park, Shreveport | United States | US | 32.4639 | -93.7944 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Local radio gives 7340 Greenwood Road, and the Shreveport-Bossier Journal places the park off Greenwood Road in west Shreveport next to I-20, but no coordinates are published. The point is the Shreveport city coordinate from its Wikipedia article, not the park. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 4ce23293-83e8-5780-8614-585b94021cd5 | announced | 2026-08-27 | 47 | imported_documented_status | 63cd9953-79b9-56b3-8e07-90af3632c8ee | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"4ce23293-83e8-5780-8614-585b94021cd5","notes":"Leads construction and development of Amazon's northwest Louisiana campuses.","party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"c78c0803-2faa-53f5-9156-6ba20741fd5c","notes":"Leads construction and development of Amazon's northwest Louisiana campuses.","party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"63cd9953-79b9-56b3-8e07-90af3632c8ee","notes":"Leads construction and development of Amazon's northwest Louisiana campuses.","party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"0348bc9b-365d-5081-95c5-5c40abc26114","notes":"Leads construction and development of Amazon's northwest Louisiana campuses.","party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"9aba53a5-4916-5aab-8b2e-b131c9c4b9ef","notes":"Leads construction and development of Amazon's northwest Louisiana campuses.","party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"63cd9953-79b9-56b3-8e07-90af3632c8ee","notes":null,"party":"STACK Infrastructure","relationship_scope":"unknown","role":"owner","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"0348bc9b-365d-5081-95c5-5c40abc26114","notes":null,"party":"STACK Infrastructure","relationship_scope":"unknown","role":"owner","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"9aba53a5-4916-5aab-8b2e-b131c9c4b9ef","notes":null,"party":"STACK Infrastructure","relationship_scope":"unknown","role":"owner","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"4ce23293-83e8-5780-8614-585b94021cd5","notes":"The Shreveport-Bossier Journal says STACK will lease the campuses to Amazon; KSLA calls Amazon the customer and end user, and local radio names AWS as the primary tenant or operator.","party":"Amazon (Amazon Web Services)","relationship_scope":"unknown","role":"tenant","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"c78c0803-2faa-53f5-9156-6ba20741fd5c","notes":"The Shreveport-Bossier Journal says STACK will lease the campuses to Amazon; KSLA calls Amazon the customer and end user, and local radio names AWS as the primary tenant or operator.","party":"Amazon (Amazon Web Services)","relationship_scope":"unknown","role":"tenant","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"9aba53a5-4916-5aab-8b2e-b131c9c4b9ef","notes":"The Shreveport-Bossier Journal says STACK will lease the campuses to Amazon; KSLA calls Amazon the customer and end user, and local radio names AWS as the primary tenant or operator.","party":"Amazon (Amazon Web Services)","relationship_scope":"unknown","role":"tenant","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"63cd9953-79b9-56b3-8e07-90af3632c8ee","notes":"The USD 6 billion is presented by the state as Amazon's planned investment; Amazon also funds grid and water upgrades.","party":"Amazon","relationship_scope":"unknown","role":"investor","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"e93584c4-ead8-54ab-b2bc-ea78b3a65e7a","notes":null,"party":"Southwestern Electric Power Company (SWEPCO)","relationship_scope":"unknown","role":"utility","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"63cd9953-79b9-56b3-8e07-90af3632c8ee","notes":null,"party":"Southwestern Electric Power Company (SWEPCO)","relationship_scope":"unknown","role":"utility","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"9aba53a5-4916-5aab-8b2e-b131c9c4b9ef","notes":null,"party":"Southwestern Electric Power Company (SWEPCO)","relationship_scope":"unknown","role":"utility","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},{"evidence_id":"c78c0803-2faa-53f5-9156-6ba20741fd5c","notes":"Approved the development after the Shreveport Metropolitan Planning Commission had initially blocked it; residents' January 2026 suit seeks judicial review of that decision.","party":"Shreveport City Council","relationship_scope":"unknown","role":"government","source_record_id":"stack-amazon-resilient-technology-park-shreveport"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | STACK Infrastructure |  |  | Amazon (Amazon Web Services) |  | https://www.opportunitylouisiana.gov/news/amazon-grows-northwest-louisiana-planned-investment-to-18-billion-with-new-shreveport-campus | https://710keel.com/northwest-louisiana-data-centers/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Amazon and STACK campus at Resilient Technology Park, Shreveport as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"stack-amazon-resilient-technology-park-shreveport"},"record":{"aliases":["Resilient Technology Park","Resilient Tech Park","7340 Greenwood Road"],"id":"stack-amazon-resilient-technology-park-shreveport","last_reviewed":"2026-10-09","location":{"admin1":"Louisiana","admin2":"Caddo Parish","country":"US","lat":32.4639,"locality":"Shreveport","lon":-93.7944,"note":"Local radio gives 7340 Greenwood Road, and the Shreveport-Bossier Journal places the park off Greenwood Road in west Shreveport next to I-20, but no coordinates are published. The point is the Shreveport city coordinate from its Wikipedia article, not the park.","precision":"locality","source_ids":["s1","s3","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-18","basis":"announced","metric":"investment","note":"Investment announced by the state for the third northwest Louisiana campus at Resilient Technology Park, on top of the USD 12 billion announced in February for other campuses.","qualifier":"exact","source_ids":["s4","s5"],"unit":"USD","value":6000000000},{"applies_to":"campus","as_of":"2026-02-23","basis":"reported","metric":"investment","note":"Local radio coverage of the February announcement described the Greenwood Road site as a USD 10 billion AI data center. This conflicts with the state's later USD 6 billion figure and with KSLA and the Shreveport-Bossier Journal, which said this site was not part of the February announcement; it is kept for transparency.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2026-08-27","basis":"reported","metric":"land_area","note":"Size of Resilient Technology Park as a whole.","qualifier":"exact","source_ids":["s3","s5"],"unit":"acres","value":313},{"applies_to":"campus","as_of":"2026-02-23","basis":"planned","metric":"land_area","note":"Area covered by the campus site plan as reported in February 2026, before the 14% footprint reduction reported in August.","qualifier":"more_than","source_ids":["s1"],"unit":"acres","value":250},{"applies_to":"campus","as_of":"2026-02-23","basis":"planned","metric":"buildings","note":"Two-story buildings in the February 2026 site plan.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":7},{"applies_to":"campus","as_of":"2026-02-23","basis":"planned","metric":"floor_area","note":"Reported as nearly 3 million sq ft.","qualifier":"approximately","source_ids":["s1"],"unit":"sq_ft","value":3000000},{"applies_to":"campus","as_of":"2026-08-18","basis":"planned","metric":"jobs_permanent","note":"Direct new jobs attributed to the third campus; the state estimates 499 more indirect jobs.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":210}],"milestones":[{"date":"2026-01","event":"other","kind":"actual","note":"The mayor of Mooringsport and two Caddo Parish residents sued the city seeking judicial review of the City Council's approval; a district court hearing was set for 20 April 2026.","source_ids":["s3"]},{"date":"2026-02-23","event":"other","kind":"actual","note":"Amazon's USD 12 billion northwest Louisiana plan was announced. Local radio listed the Greenwood Road site among its campuses, while KSLA and the Shreveport-Bossier Journal said this site was left out of the USD 12 billion because of the pending litigation.","source_ids":["s1","s3","s7"]},{"date":"2026-08-18","event":"announced","kind":"actual","note":"The state announced a USD 6 billion third campus at Resilient Technology Park; trade press reported that the development footprint had been cut by 14% to keep more green space and buffers.","source_ids":["s4","s5"]}],"name":"Amazon and STACK campus at Resilient Technology Park, Shreveport","notes":"Covers only the Resilient Technology Park campus. Amazon's February 2026 USD 12 billion plan covers STACK campuses north of Blanchard on State Line Road (Caddo Parish) and north of Benton near LA 3 (Bossier Parish), with no site-level figures found. Program-wide figures (up to USD 400 million for water, up to 2,250 construction jobs, up to 750 direct jobs) are not campus figures. No megawatt figure was found. The outcome of the April 2026 court hearing could not be confirmed from an independent openable source, so it is not recorded. Sources do not say whether the USD 6 billion replaces the earlier USD 10 billion radio description of this site. IREI's article is partly paywalled.","parties":[{"name":"STACK Infrastructure","note":"Leads construction and development of Amazon's northwest Louisiana campuses.","role":"developer","source_ids":["s1","s3","s4","s5","s7"]},{"name":"STACK Infrastructure","role":"owner","source_ids":["s4","s5","s7"]},{"name":"Amazon (Amazon Web Services)","note":"The Shreveport-Bossier Journal says STACK will lease the campuses to Amazon; KSLA calls Amazon the customer and end user, and local radio names AWS as the primary tenant or operator.","role":"tenant","source_ids":["s1","s3","s7"]},{"name":"Amazon","note":"The USD 6 billion is presented by the state as Amazon's planned investment; Amazon also funds grid and water upgrades.","role":"investor","source_ids":["s4"]},{"name":"Southwestern Electric Power Company (SWEPCO)","role":"utility","source_ids":["s2","s4","s7"]},{"name":"Shreveport City Council","note":"Approved the development after the Shreveport Metropolitan Planning Commission had initially blocked it; residents' January 2026 suit seeks judicial review of that decision.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"Served by SWEPCO, with Amazon funding new energy infrastructure and grid upgrades so costs are not passed to existing ratepayers.","source_ids":["s2","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-02-23","publisher":"News Radio 710 KEEL","title":"Historic $12 Billion Dollar Investment in Shreveport by Amazon for New Data Centers","type":"news","url":"https://710keel.com/northwest-louisiana-data-centers/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260225172233/https://www.wafb.com/2026/02/23/more-data-centers-reportedly-coming-northwest-louisiana-major-announcement-coming-monday/","id":"s2","published":"2026-02-23","publisher":"WAFB (KSLA report)","title":"Amazon building $12 billion data center in Caddo & Bossier parishes, Gov. Landry announces","type":"news","url":"https://www.wafb.com/2026/02/23/more-data-centers-reportedly-coming-northwest-louisiana-major-announcement-coming-monday/"},{"accessed":"2026-10-09","id":"s3","published":"2026-04-09","publisher":"Shreveport-Bossier Journal","title":"Court hearing set April 20 in challenge to Shreveport Amazon data center","type":"news","url":"https://shreveportbossierjournal.com/2026/04/09/court-hearing-set-april-20-in-challenge-to-shreveport-amazon-data-center/"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-18","publisher":"Louisiana Economic Development","title":"Amazon Grows Northwest Louisiana Planned Investment to $18 Billion With New Shreveport Campus","type":"government","url":"https://www.opportunitylouisiana.gov/news/amazon-grows-northwest-louisiana-planned-investment-to-18-billion-with-new-shreveport-campus"},{"accessed":"2026-10-09","id":"s5","published":"2026-08-27","publisher":"Institutional Real Estate, Inc.","title":"Amazon earmarks $6b for third data center campus in northwest Louisiana","type":"trade_press","url":"https://irei.com/news/amazon-earmarks-6b-for-third-data-center-campus-in-northwest-louisiana/"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Shreveport, Louisiana","type":"other","url":"https://en.wikipedia.org/wiki/Shreveport,_Louisiana"},{"accessed":"2026-10-09","id":"s7","published":"2026-02-24","publisher":"KSLA News 12","title":"Campuses for newly announced Amazon data center spanning Bossier & Caddo parishes confirmed","type":"news","url":"https://www.ksla.com/2026/02/24/campuses-newly-announced-amazon-data-center-spanning-bossier-caddo-parishes-confirmed/"}],"status":"announced","status_as_of":"2026-08-27","status_source_ids":["s4","s5"],"summary":"Data center campus that STACK Infrastructure is to develop, own and lease to Amazon at the 313-acre Resilient Technology Park off Greenwood Road in west Shreveport, Louisiana, next to Interstate 20. The City Council approved it after the planning commission had blocked it, and residents sued in January 2026 seeking judicial review. In February 2026 local radio described a USD 10 billion site plan of seven two-story buildings and nearly 3 million sq ft, though other outlets said the site was left out of Amazon's USD 12 billion regional announcement because of the lawsuit. In August 2026 the state announced USD 6 billion for this third campus, raising Amazon's regional plan to USD 18 billion.","workloads":["cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"4ce23293-83e8-5780-8614-585b94021cd5","s2":"e93584c4-ead8-54ab-b2bc-ea78b3a65e7a","s3":"c78c0803-2faa-53f5-9156-6ba20741fd5c","s4":"63cd9953-79b9-56b3-8e07-90af3632c8ee","s5":"0348bc9b-365d-5081-95c5-5c40abc26114","s6":"b38fe933-0ac6-5423-b0df-b3415fe78d9f","s7":"9aba53a5-4916-5aab-8b2e-b131c9c4b9ef"},"source_file":"datacenters/projects/stack-amazon-resilient-technology-park-shreveport.json","source_record_id":"stack-amazon-resilient-technology-park-shreveport","source_record_sha256":"2237bb64e77771c65a9e25a502b027659ad4492ebb5afaf66d9e21861ce63b15","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a2d6a938a1e16b4c50604538a755ac96f45ce557bc73550adfa1a84017fe45c8"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1246c2b9750b8b4832d2/#project-3641032c-9acd-5840-b94b-beab26a1ce0d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3641032c-9acd-5840-b94b-beab26a1ce0d.json
36ac2490-7d9c-51f3-96c4-1344481aa4e2 | curated:data-world-matatirtha-campus:core-data-center-current-build | vcc-site-9110ab1aaf7969ec33fc | curated:data-world-matatirtha-campus | Data World Matatirtha Core Data Center Current Build | Nepal | NP | 27.6786 | 85.2365 | Point | campus | source_marker_decimal_coordinates_to_point_without_centroiding | data_world_named_kathmandu_marker_as_matatirtha_campus_locator | first_party_facility_map_marker_as_campus_locator | official_source | campus_locator | The exact first-party Kathmandu marker is linked to the IFC-named Matatirtha project through Data World, Chandragiri, and singular facility context. It is only a broad campus locator, not an entrance, parcel, surveyed point, boundary, footprint, or work extent. |  | Data World publishes no marker collection method, represented feature, datum, or bounded horizontal accuracy. | 6a83e8a4-4c67-5ec1-8979-c49535d7d363 | under_construction | 2026-07-01 | 104 | authoritative_physical_status_update | 784f2bc1-8e76-5a75-9b37-7c64d793d955 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ifc.shorthandstories.com/watts-and-zeros-powering-nepals-digital-future/embed.js | https://dataworld.com.np/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9110ab1aaf7969ec33fc/#project-36ac2490-7d9c-51f3-96c4-1344481aa4e2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/36ac2490-7d9c-51f3-96c4-1344481aa4e2.json
3761e59a-fe39-523d-83a6-9fbfa9feec85 | curated:nextdc-s4-sydney:initial-development | vcc-site-8d8b8d427f99ad4fa5a1 | curated:nextdc-s4-sydney | NEXTDC S4 Initial Development | Australia | AU | -33.8278 | 150.8246 | Point | campus | government_named_project_geojson_point | preserve_public_Drupal_GeoJSON_feature_for_node68004716_SSD63741210_and_bind_application_Lot305_DP1275011 | government_project_campus_reference_point | official_source | campus_locator | The portal's named NEXTDC S4 project marker is bound to SSD-63741210 and the application's 16 Johnston Crescent / Lot 305 DP 1275011. Normal JSON floating-point serialization shortens literal tokens without geocoding. The unrelated default map center and rounded application longitude are excluded. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate. |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | 07ea32f1-85b6-5285-8219-504b14f65e60 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 43bd6a30-6bac-5500-afd1-74b0e425d6b0 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nextdc.com/hubfs/Financial%20Reports/FY26/FY26%20Results%20Announcement.pdf | https://www.planningportal.nsw.gov.au/major-projects/projects/nextdc-s4-data-centre-horsley-park | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8d8b8d427f99ad4fa5a1/#project-3761e59a-fe39-523d-83a6-9fbfa9feec85 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3761e59a-fe39-523d-83a6-9fbfa9feec85.json
37e33657-b788-57e6-98f2-b78834cdecda | curated:avaio-taurus-brandon-mississippi-campus:phase-one-current-campus-build | vcc-site-6727a9539ece2f19ad23 | curated:avaio-taurus-brandon-mississippi-campus | AVAIO Digital Taurus Phase One Current Campus Build | United States | US | 32.2593 | -90.0185 | Point | project | coordinates_to_point | authoritative_site_plan | first_party_campus_reference_point | official_source | reviewed_site_locator | First-party Taurus campus location point derived exactly from the published latitude and longitude; not the 329-acre boundary, a parcel, building footprint, measured centroid, or phase-one outline. |  | official source does not state positional accuracy | 68b10772-f3b4-5152-bffe-23d34c4f8477 | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | 68b10772-f3b4-5152-bffe-23d34c4f8477 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | tracked_identity_bound_uncertain_with_unadjudicated_later_stricter_review_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [{"as_of_date":"2025-09-10","confidence":0.98,"deployment_scope":"intended","evidence_id":"1f776e1f-3f79-53d1-880c-e90b0fd8b958","method":"company_disclosure","workload":"mixed"}] |  | [{"evidence_id":"68b10772-f3b4-5152-bffe-23d34c4f8477","party":"AVAIO Digital Partners","relationship_scope":"intended","role":"operator"}] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | AVAIO Digital Partners |  |  |  | https://www.avaiodigital.com/developments/brandon-mississippi | https://www.avaiodigital.com/developments/brandon-mississippi | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6727a9539ece2f19ad23/#project-37e33657-b788-57e6-98f2-b78834cdecda | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/37e33657-b788-57e6-98f2-b78834cdecda.json
38033ec9-dbd8-56bb-8a35-0fa91dd284e2 | curated:ten-brinke-spata-data-center:active-construction | vcc-site-10c105346f5cad5b0aa5 | curated:ten-brinke-spata-data-center | Ten Brinke Spata Data Center Active Construction | Greece | GR | 37.9663 | 23.9087 | Point | project | direct_geometry | authoritative_site_plan | facility_reference_point | official_source | reviewed_site_locator | First-party project map point, facility-specific, with 50 metre stated horizontal uncertainty. | 50 |  | ad6f843e-6f09-567d-82e6-58ecd9959ff7 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | 0319c9a2-0161-5f88-ad38-3fd3aa0e3ea3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.tenbrinke.com/en/projects/current-projects/current-projects-details/data-center-spata-26-1052-gr.html | https://www.tenbrinke.com/en/projects/current-projects/current-projects-details/data-center-spata-26-1052-gr.html | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-10c105346f5cad5b0aa5/#project-38033ec9-dbd8-56bb-8a35-0fa91dd284e2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/38033ec9-dbd8-56bb-8a35-0fa91dd284e2.json
384a401d-cc7f-52e4-9ae3-218a378995b9 | imported:semiconductor-atlas:khazna-ajman | vcc-site-284562d636d49db446ea | imported:semiconductor-atlas:khazna-ajman | Khazna QAJ1 AI data center (Ajman) | United Arab Emirates | AE | 25.4136 | 55.4456 | Point | project | imported_reference_point | imported_reference_point | admin1 | compiled_reference | admin1_context | Sources name only Ajman. Coordinates are the Ajman city point from its Wikipedia article and stand in for the emirate; the plot location is not published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2b3603ad-d2a2-504e-9c31-dbbb21a8b08d | under_construction | 2025-10-14 | 364 | imported_documented_status | 036fc2ba-eaa4-573c-90ba-1d7351a1e086 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2b3603ad-d2a2-504e-9c31-dbbb21a8b08d","notes":null,"party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"khazna-ajman"},{"evidence_id":"4440e777-1b1f-5526-890a-8c1220440cdc","notes":null,"party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"khazna-ajman"},{"evidence_id":"76af208f-eb33-50a8-a0fc-a9461c0bce8d","notes":null,"party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"khazna-ajman"},{"evidence_id":"1f1fdaa4-75e0-53d1-9e81-65fdbc1c09bb","notes":null,"party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"khazna-ajman"},{"evidence_id":"4440e777-1b1f-5526-890a-8c1220440cdc","notes":null,"party":"Laing O'Rourke","relationship_scope":"unknown","role":"builder","source_record_id":"khazna-ajman"},{"evidence_id":"2b3603ad-d2a2-504e-9c31-dbbb21a8b08d","notes":null,"party":"Etihad Water and Electricity","relationship_scope":"unknown","role":"utility","source_record_id":"khazna-ajman"},{"evidence_id":"4440e777-1b1f-5526-890a-8c1220440cdc","notes":null,"party":"Etihad Water and Electricity","relationship_scope":"unknown","role":"utility","source_record_id":"khazna-ajman"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://guest.meed.com/?p=12676 | https://w.media/khazna-announces-construction-of-100-mw-ai-optimised-data-center-in-ajman/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Khazna QAJ1 AI data center (Ajman) as an independent source record; its admin1 locator does not itself establish a surveyed physical site.","source_record_id":"khazna-ajman"},"record":{"aliases":["QAJ1","QAJ01"],"id":"khazna-ajman","last_reviewed":"2026-10-09","location":{"admin1":"Ajman","country":"AE","lat":25.41361,"lon":55.44556,"note":"Sources name only Ajman. Coordinates are the Ajman city point from its Wikipedia article and stand in for the emirate; the plot location is not published.","precision":"admin1","source_ids":["s1","s2","s7"]},"metrics":[{"applies_to":"campus","as_of":"2024-10-18","basis":"under_construction","metric":"power_capacity","note":"Reported as 20 data halls of 5 MW each; these reports do not state the scope.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2026-02-25","basis":"planned","metric":"power_capacity","note":"The Uptime Institute release describes 100 MW of total IT load, with 5 MW of IT capacity in each of 20 halls.","power_scope":"it_load","qualifier":"exact","source_ids":["s6"],"unit":"MW","value":100}],"milestones":[{"date":"2024-10","event":"announced","kind":"actual","note":"Announced by Khazna in a LinkedIn post reported on 15 October 2024.","source_ids":["s1"]},{"date":"2024-10","event":"construction_started","kind":"actual","note":"Laing O'Rourke started construction; completion was then expected within 15 months.","source_ids":["s2"]},{"date":"2025-04","event":"other","kind":"actual","note":"Khazna said the steel structures were complete.","source_ids":["s3"]},{"date":"2026-12","event":"first_operational","kind":"planned","note":"Initial phase target as of April 2025, a delay from an earlier 3Q 2025 completion date.","source_ids":["s3","s4"]},{"date":"2026-02","event":"other","kind":"actual","note":"Uptime Institute Tier III Certification of Design Documents awarded; the design certification does not cover a built facility.","source_ids":["s6"]}],"name":"Khazna QAJ1 AI data center (Ajman)","notes":"Status rests on Khazna saying in October 2025 that it was developing hyperscale facilities in Ajman and on MEED's April 2025 report of completed steel structures; the February 2026 certification release speaks of performance once the facility is constructed, and no later construction or opening report was found. MEED reported in October 2024 a multibillion-dirham cost with no exact figure, and a project area of 100,000 square metres without saying whether that is floor or land area, so neither is recorded as a metric.","parties":[{"name":"Khazna Data Centers","role":"developer","source_ids":["s1","s2","s5","s6"]},{"name":"Laing O'Rourke","role":"builder","source_ids":["s2"]},{"name":"Etihad Water and Electricity","role":"utility","source_ids":["s1","s2"]}],"power_sources":[{"description":"Electricity primarily from Etihad Water and Electricity.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250724204654/https://w.media/khazna-announces-construction-of-100-mw-ai-optimised-data-center-in-ajman/","id":"s1","published":"2024-10-15","publisher":"W.Media","title":"Khazna announces construction of 100 MW AI optimised Data Center in Ajman","type":"trade_press","url":"https://w.media/khazna-announces-construction-of-100-mw-ai-optimised-data-center-in-ajman/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260116201938/https://www.meed.com/construction-begins-on-khazna-data-centre-in-ajman","id":"s2","published":"2024-10-18","publisher":"MEED","title":"Construction begins on Khazna data centre in Ajman","type":"trade_press","url":"https://www.meed.com/construction-begins-on-khazna-data-centre-in-ajman"},{"accessed":"2026-10-09","id":"s3","published":"2025-04-22","publisher":"MEED","title":"Khazna breaks ground on new UAE data centre projects","type":"trade_press","url":"https://guest.meed.com/?p=12676"},{"accessed":"2026-10-09","id":"s4","published":"2025-04-22","publisher":"Enterprise AM","title":"Khazna to boost UAE data center infrastructure with 60 MW projects","type":"news","url":"https://enterpriseam.com/logistics/2025/04/22/khazna-to-boost-uae-data-center-infrastructure-with-60-mw-projects/"},{"accessed":"2026-10-09","id":"s5","published":"2025-10-14","publisher":"Khazna Data Centers","title":"Khazna Data Centers to Add Over 1GW Hyperscale Capacity Across Multiple Countries By 2030","type":"company","url":"https://khaznadatacenters.com/press-release/khazna-data-centers-to-add-over-1gw-hyperscale-capacity-across-multiple-countries-by-2030/"},{"accessed":"2026-10-09","id":"s6","published":"2026-02-25","publisher":"ITWeb Africa (Uptime Institute release via Business Wire)","title":"Khazna Awarded Uptime Tier III Certification of Design Documents for Ajman, UAE Facility, Largest in Company's Portfolio","type":"trade_press","url":"https://itweb.africa/article/khazna-awarded-uptime-tier-iii-certification-of-design-documents-for-ajman-uae-facility-largest-in-companys-portfolio/lLn147mQVWz7J6Aa"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003225448/https://en.wikipedia.org/wiki/Ajman","id":"s7","published":null,"publisher":"Wikipedia","title":"Ajman","type":"other","url":"https://en.wikipedia.org/wiki/Ajman"}],"status":"under_construction","status_as_of":"2025-10-14","status_source_ids":["s3","s5"],"summary":"AI-optimised, liquid-cooled data center being built by Khazna Data Centers in Ajman, United Arab Emirates, with 20 data halls of 5 MW each for 100 MW of IT load, the largest facility in Khazna's portfolio. Construction by Laing O'Rourke began in October 2024 with a 15-month target, and power is to come from Etihad Water and Electricity. By April 2025 the steel structure was complete and the first phase was rescheduled to December 2026 from an earlier 3Q 2025 date. In February 2026 the Uptime Institute awarded the design documents Tier III certification.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2b3603ad-d2a2-504e-9c31-dbbb21a8b08d","s2":"4440e777-1b1f-5526-890a-8c1220440cdc","s3":"036fc2ba-eaa4-573c-90ba-1d7351a1e086","s4":"49cff3f4-9082-5a03-8d9c-6327d280b872","s5":"76af208f-eb33-50a8-a0fc-a9461c0bce8d","s6":"1f1fdaa4-75e0-53d1-9e81-65fdbc1c09bb","s7":"fd4e54bf-8530-5b2c-8da9-3f8a94b25622"},"source_file":"datacenters/projects/khazna-ajman.json","source_record_id":"khazna-ajman","source_record_sha256":"92a643d476e98c5addb8185cc1322ba283996fcbede435884f9449965f68ea71","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"82d8630757274ce07e8fde11a9a428eac9be985349014b73dfb8a8b2ec206b6d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-284562d636d49db446ea/#project-384a401d-cc7f-52e4-9ae3-218a378995b9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/384a401d-cc7f-52e4-9ae3-218a378995b9.json
38cbdb58-5ff7-504d-98be-60187be91e02 | imported:semiconductor-atlas:nebius-vineland-new-jersey | vcc-site-c14008c0552564c11274 | curated:dataone-vineland-ai-data-center-campus | Nebius Vineland AI factory | United States | US | 39.465 | -75.0064 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City centroid from the Wikipedia infobox for Vineland (s7), which also gives Cumberland County. No street address or parcel appears in the cited sources. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | badbf4d8-58c5-5a0a-8aed-34f40b82bea7 | under_construction | 2026-10-09 | 4 | imported_documented_status | db0dcf87-402f-57c7-9f2c-f4887e94bf40 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","notes":"Described as the AI factory designer and builder under a build-to-suit arrangement.","party":"DataOne","relationship_scope":"unknown","role":"developer","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"49d2d717-97a3-577b-ab1e-89c6542ceba8","notes":"Described as the AI factory designer and builder under a build-to-suit arrangement.","party":"DataOne","relationship_scope":"unknown","role":"developer","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","notes":null,"party":"DataOne","relationship_scope":"unknown","role":"owner","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"49d2d717-97a3-577b-ab1e-89c6542ceba8","notes":null,"party":"DataOne","relationship_scope":"unknown","role":"owner","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","notes":null,"party":"DataOne","relationship_scope":"unknown","role":"operator","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"49d2d717-97a3-577b-ab1e-89c6542ceba8","notes":null,"party":"DataOne","relationship_scope":"unknown","role":"operator","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"badbf4d8-58c5-5a0a-8aed-34f40b82bea7","notes":"Owns and operates the servers and GPUs.","party":"Nebius","relationship_scope":"unknown","role":"tenant","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","notes":"Owns and operates the servers and GPUs.","party":"Nebius","relationship_scope":"unknown","role":"tenant","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"49d2d717-97a3-577b-ab1e-89c6542ceba8","notes":"Owns and operates the servers and GPUs.","party":"Nebius","relationship_scope":"unknown","role":"tenant","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","notes":"Vineland-based construction partner.","party":"Northeast Precast","relationship_scope":"unknown","role":"builder","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"49d2d717-97a3-577b-ab1e-89c6542ceba8","notes":"Vineland-based construction partner.","party":"Northeast Precast","relationship_scope":"unknown","role":"builder","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","notes":"Supplier of the on-site fuel cells.","party":"Bloom Energy","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"49d2d717-97a3-577b-ab1e-89c6542ceba8","notes":"Supplier of the on-site fuel cells.","party":"Bloom Energy","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"badbf4d8-58c5-5a0a-8aed-34f40b82bea7","notes":"End customer buying dedicated GPU capacity from Nebius delivered from the Vineland site, rather than a direct lessee of the building.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"e0003a81-fb7d-55a4-9993-c9cbc77bf744","notes":"End customer buying dedicated GPU capacity from Nebius delivered from the Vineland site, rather than a direct lessee of the building.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"nebius-vineland-new-jersey"},{"evidence_id":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","notes":"City Council and mayor approved a five-year payment-in-lieu-of-taxes ordinance in January 2026.","party":"City of Vineland","relationship_scope":"unknown","role":"government","source_record_id":"nebius-vineland-new-jersey"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | DataOne | DataOne |  | Microsoft; Nebius |  | https://nebius.com/vinelandnj | https://nebius.com/newsroom/nebius-announces-multi-billion-dollar-agreement-with-microsoft-for-ai-infrastructure | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same DataOne-owned Vineland campus with Nebius as tenant; canonical evidence includes the exact Nebius project page. Source is campus-wide while existing record selects Phase 2 expansion. A tenant label is not a separate physical site.","source_record_id":"nebius-vineland-new-jersey","target_physical_site_stable_key":"curated:dataone-vineland-ai-data-center-campus"},"record":{"aliases":["Nebius x Vineland"],"id":"nebius-vineland-new-jersey","last_reviewed":"2026-10-09","location":{"admin1":"New Jersey","admin2":"Cumberland County","country":"US","lat":39.465,"locality":"Vineland","lon":-75.0064,"note":"City centroid from the Wikipedia infobox for Vineland (s7), which also gives Cumberland County. No street address or parcel appears in the cited sources.","precision":"locality","source_ids":["s1","s3","s4","s7"]},"metrics":[{"applies_to":"campus","as_of":"2025-05-02","basis":"planned","metric":"power_capacity","note":"The filing describes the New Jersey site as a phased development scalable up to this amount; it gives no figure for the initial phase.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s5"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-07-10","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s3","s4"],"unit":"count","value":200},{"applies_to":"campus","as_of":"2026-07-10","basis":"planned","metric":"jobs_construction","qualifier":"approximately","source_ids":["s3","s4"],"unit":"count","value":1000}],"milestones":[{"date":"2025-H1","event":"construction_started","kind":"actual","note":"The May 2025 filing says construction of the build-to-suit facility began in early 2025.","source_ids":["s5"]},{"date":"2025-09-08","event":"other","kind":"actual","note":"Nebius signed a five-year agreement to provide Microsoft dedicated GPU capacity from the new Vineland data center, about 17.4 billion US dollars through 2031 and up to about 19.4 billion with options.","source_ids":["s1","s2"]},{"date":"2026-01","event":"other","kind":"actual","note":"Vineland approved a five-year payment-in-lieu-of-taxes ordinance for the project.","source_ids":["s3"]},{"date":"2026-08-12","event":"other","kind":"actual","note":"Nebius reported it had delivered all capacity tranches under the Microsoft contract; the letter does not name the site.","source_ids":["s6"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Nebius says the AI factory is expected to be operational by 2027.","source_ids":["s3"]}],"name":"Nebius Vineland AI factory","notes":"The Vineland project page is undated; status_as_of is the date it was accessed, when it said construction was ongoing. Microsoft buys GPU capacity from Nebius rather than leasing the building.","parties":[{"name":"DataOne","note":"Described as the AI factory designer and builder under a build-to-suit arrangement.","role":"developer","source_ids":["s3","s4"]},{"name":"DataOne","role":"owner","source_ids":["s3","s4"]},{"name":"DataOne","role":"operator","source_ids":["s3","s4"]},{"name":"Nebius","note":"Owns and operates the servers and GPUs.","role":"tenant","source_ids":["s1","s3","s4"]},{"name":"Northeast Precast","note":"Vineland-based construction partner.","role":"builder","source_ids":["s3","s4"]},{"name":"Bloom Energy","note":"Supplier of the on-site fuel cells.","role":"hardware_supplier","source_ids":["s3","s4"]},{"name":"Microsoft","note":"End customer buying dedicated GPU capacity from Nebius delivered from the Vineland site, rather than a direct lessee of the building.","role":"tenant","source_ids":["s1","s2"]},{"name":"City of Vineland","note":"City Council and mayor approved a five-year payment-in-lieu-of-taxes ordinance in January 2026.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"On-site Bloom Energy fuel cells described as off-grid generation, with Nebius saying it will bring and pay for its own power.","source_ids":["s3","s4"],"type":"fuel_cell"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261005120903/https://nebius.com/newsroom/nebius-announces-multi-billion-dollar-agreement-with-microsoft-for-ai-infrastructure","id":"s1","published":"2025-09-08","publisher":"Nebius","title":"Nebius announces multi-billion dollar agreement with Microsoft for AI infrastructure","type":"company","url":"https://nebius.com/newsroom/nebius-announces-multi-billion-dollar-agreement-with-microsoft-for-ai-infrastructure"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-08","publisher":"U.S. Securities and Exchange Commission (Nebius Group filing)","title":"Nebius Group N.V. Form 6-K filed September 8, 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1513845/000110465925088312/tm2525580d1_6k.htm"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Nebius","title":"Nebius in Vineland, NJ project page","type":"company","url":"https://nebius.com/vinelandnj"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-10","publisher":"Nebius","title":"Nebius x Vineland, NJ fact sheet","type":"company","url":"https://assets.nebius.com/assets/729154ac-8d55-459f-9dd6-8f85a40da15b/NEW%20Vineland%20NJ%20Fact%20Sheet_7.10.26.pdf?cache-buster=2026-07-10T18:45:11.445Z"},{"accessed":"2026-10-09","id":"s5","published":"2025-05-02","publisher":"U.S. Securities and Exchange Commission (Nebius Group filing)","title":"Nebius Group N.V. Form F-3ASR registration statement","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1513845/000110465925044092/tm2513807-3_f3asr.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260919171250/https://assets.nebius.com/assets/a6ecfd85-a6cb-4967-8ef7-9a25bd261f9c/SHLQ226.pdf?cache-buster=2026-08-12T11%3A54%3A46.695Z","id":"s6","published":"2026-08-12","publisher":"Nebius","title":"Nebius Q2 2026 letter to shareholders","type":"company","url":"https://assets.nebius.com/assets/a6ecfd85-a6cb-4967-8ef7-9a25bd261f9c/SHLQ226.pdf?cache-buster=2026-08-12T11:54:46.695Z"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260928153206/https://en.wikipedia.org/wiki/Vineland,_New_Jersey","id":"s7","published":null,"publisher":"Wikipedia","title":"Vineland, New Jersey","type":"other","url":"https://en.wikipedia.org/wiki/Vineland,_New_Jersey"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s3"],"summary":"AI data center in Vineland, New Jersey, designed, built, owned and operated by DataOne with Nebius as tenant owning the servers and GPUs, and Vineland-based Northeast Precast as builder. A May 2025 Nebius filing describes a phased development scalable up to 300 MW, with construction begun in early 2025. Nebius named the site in its September 2025 agreement to supply Microsoft with dedicated GPU capacity, valued at about 17.4 billion US dollars through 2031. Power is to come from on-site, off-grid Bloom Energy fuel cells. Nebius's project page says construction is ongoing and the AI factory is expected to be operational by 2027.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"badbf4d8-58c5-5a0a-8aed-34f40b82bea7","s2":"e0003a81-fb7d-55a4-9993-c9cbc77bf744","s3":"db0dcf87-402f-57c7-9f2c-f4887e94bf40","s4":"49d2d717-97a3-577b-ab1e-89c6542ceba8","s5":"40dcc768-46e9-5dd2-9514-46d2416e45a5","s6":"4892dbe4-e7ac-5cba-b418-66274a6d7f65","s7":"9a0aae02-55de-506d-84ac-b25c46be8a0e"},"source_file":"datacenters/projects/nebius-vineland-new-jersey.json","source_record_id":"nebius-vineland-new-jersey","source_record_sha256":"9de90d4f57f1b60eda7280b503f5eb642922782c115b708a8a16e6867e535800","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"df44ac009bdf86a5fb958e27f7860e8b4dc55f2e03f7644c90ff1552c2941dae"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c14008c0552564c11274/#project-38cbdb58-5ff7-504d-98be-60187be91e02 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/38cbdb58-5ff7-504d-98be-60187be91e02.json
3941c42e-216d-52fa-b0d8-d7555b441a1a | curated:maincubes-mainhub-nauen-campus:ber02 | vcc-site-75fed87a1b38b8cd7280 | curated:maincubes-mainhub-nauen-campus | maincubes BER02 | Germany | DE | 52.5935 | 12.893 | Point | project | coordinates_to_point | authoritative_site_plan | first_party_shared_campus_reference_point | official_source | reviewed_site_locator | First-party BER02/mainHub Nauen location point derived exactly from the published latitude and longitude; not a parcel, building outline, footprint, or measured centroid. |  | official source does not state positional accuracy | 1e5b63b2-b334-52e0-94a1-f78d02457964 | under_construction | 2026-07-19 | 86 | authoritative_physical_status_update | 28e90c7d-c059-5cbb-a53d-9d6a9913e7f3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | tracked_identity_bound_reject_with_unadjudicated_later_conflict_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.maincubes.com/en/data-centers/berlin-cloud-ai-provider-campus-ber02/ | https://www.maincubes.com/wp-content/uploads/2026/02/maincubes_factsheet_ber02_en.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-75fed87a1b38b8cd7280/#project-3941c42e-216d-52fa-b0d8-d7555b441a1a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3941c42e-216d-52fa-b0d8-d7555b441a1a.json
39753efd-ec90-5e1a-a234-8551ba238bda | imported:semiconductor-atlas:aws-lake-anna-technology-campus-louisa-county | vcc-site-6547aae0762f92e98a07 | imported:semiconductor-atlas:aws-lake-anna-technology-campus-louisa-county | AWS Lake Anna Technology Campus | United States | US | 38.0606 | -77.7894 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | The campus sits at Kentucky Springs Road (Route 652) and Haley Drive (Route 700), next to the North Anna Power Station. Geocoding was unavailable, so coordinates are the power station's location from its Wikipedia article; the campus lies beside it. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 76cf51ed-92f5-5532-a590-aca54829516f | announced | 2026-03-16 | 211 | imported_documented_status | a367bcc2-6a47-56df-a505-d752975b8b9a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"68e3c87e-cbea-55ba-92ea-46f89859adff","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"76cf51ed-92f5-5532-a590-aca54829516f","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"a367bcc2-6a47-56df-a505-d752975b8b9a","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"76cf51ed-92f5-5532-a590-aca54829516f","notes":"General contractor; Shirley Construction was named for rough grading.","party":"Clark Construction","relationship_scope":"unknown","role":"builder","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"68e3c87e-cbea-55ba-92ea-46f89859adff","notes":"County says it will provide electric service; it owns one of the two planned substations.","party":"Rappahannock Electric Cooperative","relationship_scope":"unknown","role":"utility","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"76cf51ed-92f5-5532-a590-aca54829516f","notes":"County says it will provide electric service; it owns one of the two planned substations.","party":"Rappahannock Electric Cooperative","relationship_scope":"unknown","role":"utility","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"fb003dd8-cd46-589e-b3d6-6cebedce41e6","notes":"County says it will provide electric service; it owns one of the two planned substations.","party":"Rappahannock Electric Cooperative","relationship_scope":"unknown","role":"utility","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"76cf51ed-92f5-5532-a590-aca54829516f","notes":"Owns the other planned 300 MW substation serving the site.","party":"Dominion Energy","relationship_scope":"unknown","role":"utility","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"68e3c87e-cbea-55ba-92ea-46f89859adff","notes":"Performance agreement with tax rebates funded from new AWS revenue; the state offered a grant fund and sales and use tax waivers.","party":"Louisa County","relationship_scope":"unknown","role":"government","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},{"evidence_id":"fb003dd8-cd46-589e-b3d6-6cebedce41e6","notes":"Performance agreement with tax rebates funded from new AWS revenue; the state offered a grant fund and sales and use tax waivers.","party":"Louisa County","relationship_scope":"unknown","role":"government","source_record_id":"aws-lake-anna-technology-campus-louisa-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.aboutamazon.com/news/aws/amazon-data-centers-locations-news | https://lakeannalife.com/amazon-planning-to-commence-work-at-lake-anna-technology-campus/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve AWS Lake Anna Technology Campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"aws-lake-anna-technology-campus-louisa-county"},"record":{"aliases":["LATC","REB Investments site"],"id":"aws-lake-anna-technology-campus-louisa-county","last_reviewed":"2026-10-09","location":{"admin1":"Virginia","admin2":"Louisa County","country":"US","lat":38.0606,"lon":-77.7894,"note":"The campus sits at Kentucky Springs Road (Route 652) and Haley Drive (Route 700), next to the North Anna Power Station. Geocoding was unavailable, so coordinates are the power station's location from its Wikipedia article; the campus lies beside it.","precision":"approximate_site","source_ids":["s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2024","basis":"planned","metric":"power_capacity","note":"Described as data center capacity; two substations of 300 MW each are planned to serve the site.","power_scope":"unspecified","qualifier":"at_least","source_ids":["s2"],"unit":"MW","value":420},{"applies_to":"campus","as_of":"2024","basis":"planned","metric":"land_area","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":153},{"applies_to":"campus","as_of":"2024","basis":"planned","metric":"buildings","note":"Standard data centers; plans also include two smaller specialty data centers and an administration building.","qualifier":"exact","source_ids":["s2"],"unit":"count","value":7},{"applies_to":"campus","as_of":"2024","basis":"planned","metric":"floor_area","note":"Combined area of the seven standard data centers.","qualifier":"approximately","source_ids":["s2"],"unit":"sq_ft","value":1700000}],"milestones":[{"date":"2023-08-30","event":"announced","kind":"actual","note":"AWS announced $11 billion for two Louisa County campuses by 2040, part of a $35 billion Virginia plan from January 2023.","source_ids":["s1"]}],"name":"AWS Lake Anna Technology Campus","notes":"Amazon's $11 billion Louisa County figure covers this campus and the North Creek Technology Campus together and is not split by campus, so it is not recorded as a campus metric. The county FAQ projects a 15-year build-out and cooling with raw water from Northeast Creek Reservoir. Status stays announced because no opened source confirms construction start: an undated (about mid-2024) local report described issued land-disturbance and stormwater permits and a pending Army Corps permit, and Amazon's March 2026 update discussed a discharge permit without stating build progress. That report also quoted a county estimate that a first data center might come online in late 2025 or early 2026.","parties":[{"name":"Amazon Web Services","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Clark Construction","note":"General contractor; Shirley Construction was named for rough grading.","role":"builder","source_ids":["s2"]},{"name":"Rappahannock Electric Cooperative","note":"County says it will provide electric service; it owns one of the two planned substations.","role":"utility","source_ids":["s1","s2","s3"]},{"name":"Dominion Energy","note":"Owns the other planned 300 MW substation serving the site.","role":"utility","source_ids":["s2"]},{"name":"Louisa County","note":"Performance agreement with tax rebates funded from new AWS revenue; the state offered a grant fund and sales and use tax waivers.","role":"government","source_ids":["s1","s3"]}],"power_sources":[{"description":"Two planned substations of 300 MW each, one owned by Dominion Energy and one by Rappahannock Electric Cooperative; grid upgrades are to be paid by the utilities and/or AWS.","source_ids":["s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2023-08-30","publisher":"Louisa County, Virginia","title":"Amazon Web Services announces plan to invest $11 billion in Louisa County by 2040","type":"government","url":"https://www.louisacounty.gov/CivicAlerts.aspx?AID=363&ARC=2233"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260311162525/https://lakeannalife.com/amazon-planning-to-commence-work-at-lake-anna-technology-campus/","id":"s2","published":null,"publisher":"Lake Anna Life (Engage Louisa)","title":"Contractors Meet To Discuss Construction Plan At Lake Anna Technology Campus","type":"news","url":"https://lakeannalife.com/amazon-planning-to-commence-work-at-lake-anna-technology-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260913155609/https://www.louisacounty.gov/m/faq?cat=40","id":"s3","published":null,"publisher":"Louisa County, Virginia","title":"Community Update/Press FAQs: AWS","type":"government","url":"https://www.louisacounty.gov/m/faq?cat=40"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Amazon","title":"Amazon data center communities: Here's what's happening near data centers across the US","type":"company","url":"https://www.aboutamazon.com/news/aws/amazon-data-centers-locations-news"}],"status":"announced","status_as_of":"2026-03-16","status_source_ids":["s4"],"summary":"One of two Amazon Web Services campuses in Louisa County's Technology Overlay District, part of an $11 billion AWS plan for the county by 2040 announced in August 2023. The 153-acre campus at Kentucky Springs Road and Haley Drive, next to the North Anna nuclear station, is planned for seven standard data centers (about 1.7 million sq ft), two smaller specialty data centers and an administration building, with at least 420 MW of capacity fed by two 300 MW substations. Local reporting described permits issued and contractors preparing to break ground. Amazon in 2026 described a cooling water discharge permit for the site."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"68e3c87e-cbea-55ba-92ea-46f89859adff","s2":"76cf51ed-92f5-5532-a590-aca54829516f","s3":"fb003dd8-cd46-589e-b3d6-6cebedce41e6","s4":"a367bcc2-6a47-56df-a505-d752975b8b9a"},"source_file":"datacenters/projects/aws-lake-anna-technology-campus-louisa-county.json","source_record_id":"aws-lake-anna-technology-campus-louisa-county","source_record_sha256":"544ad2083a00f197c6a00c25992f53ad4da5fd78457ba2a1481287e287445c7a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"edf751299048511326a12a3de25e631fd2958e0919d7c2d236a39862ab624d49"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6547aae0762f92e98a07/#project-39753efd-ec90-5e1a-a234-8551ba238bda | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/39753efd-ec90-5e1a-a234-8551ba238bda.json
39b97d53-5af7-55ea-bfc4-6f2f08f32e74 | imported:semiconductor-atlas:iren-kiowa-oklahoma | vcc-site-f19474c4631ae00b2725 | imported:semiconductor-atlas:iren-kiowa-oklahoma | IREN Kiowa data center campus | United States | US | 34.7228 | -95.9025 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Local reports place the site just south of Kiowa between US 69 and Kiowa Lake Road, with no exact address set. Coordinates are the Kiowa town point from its Wikipedia article, which also gives the county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 7d65dd59-1f92-5e99-978e-e5dd7a669bcb | proposed | 2026-09-08 | 35 | imported_documented_status | 0e2edc42-b2dd-5f2e-be91-bbb3e5a2abad | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c17732e4-c073-50b6-8b87-20e3913f6b60","notes":null,"party":"IREN","relationship_scope":"unknown","role":"developer","source_record_id":"iren-kiowa-oklahoma"},{"evidence_id":"7d65dd59-1f92-5e99-978e-e5dd7a669bcb","notes":null,"party":"IREN","relationship_scope":"unknown","role":"developer","source_record_id":"iren-kiowa-oklahoma"},{"evidence_id":"ab274494-33ad-5e07-96d5-d86275bc0bb5","notes":null,"party":"IREN","relationship_scope":"unknown","role":"developer","source_record_id":"iren-kiowa-oklahoma"},{"evidence_id":"7d65dd59-1f92-5e99-978e-e5dd7a669bcb","notes":"Local reporting names PSO as the grid supplier; IREN's 10-K says the utility serving the Kiowa project has proposed a large-load rate subject to Oklahoma Corporation Commission review.","party":"Public Service Company of Oklahoma","relationship_scope":"unknown","role":"utility","source_record_id":"iren-kiowa-oklahoma"},{"evidence_id":"0e2edc42-b2dd-5f2e-be91-bbb3e5a2abad","notes":"Local reporting names PSO as the grid supplier; IREN's 10-K says the utility serving the Kiowa project has proposed a large-load rate subject to Oklahoma Corporation Commission review.","party":"Public Service Company of Oklahoma","relationship_scope":"unknown","role":"utility","source_record_id":"iren-kiowa-oklahoma"},{"evidence_id":"0e2edc42-b2dd-5f2e-be91-bbb3e5a2abad","notes":"County commissioners are weighing a tax increment district and economic development plan for the project.","party":"Pittsburg County","relationship_scope":"unknown","role":"government","source_record_id":"iren-kiowa-oklahoma"},{"evidence_id":"e6cf4807-41b7-518a-82cf-4cfd94a1eade","notes":"County commissioners are weighing a tax increment district and economic development plan for the project.","party":"Pittsburg County","relationship_scope":"unknown","role":"government","source_record_id":"iren-kiowa-oklahoma"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.newson6.com/data-centers-in-oklahoma/what-to-know-kiowa-data-center-planned-for-pittsburg-county | https://www.sec.gov/Archives/edgar/data/1878848/000187884826000052/iren-20260630.htm | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve IREN Kiowa data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"iren-kiowa-oklahoma"},"record":{"aliases":["Project Emerald","Kiowa Data Center","Emerald Data Center"],"id":"iren-kiowa-oklahoma","last_reviewed":"2026-10-09","location":{"admin1":"Oklahoma","admin2":"Pittsburg County","country":"US","lat":34.7228,"locality":"Kiowa","lon":-95.9025,"note":"Local reports place the site just south of Kiowa between US 69 and Kiowa Lake Road, with no exact address set. Coordinates are the Kiowa town point from its Wikipedia article, which also gives the county.","precision":"locality","source_ids":["s2","s4","s5","s7"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-27","basis":"planned","metric":"power_capacity","note":"IREN's 10-K lists 1,600 MW of total planned gross power capacity for Kiowa, and its February 2026 release counts the campus toward its secured grid-connected power; IT versus facility load is not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3","s4"],"unit":"MW","value":1600},{"applies_to":"campus","as_of":"2026-02-05","basis":"planned","metric":"land_area","qualifier":"approximately","source_ids":["s3","s4"],"unit":"acres","value":2000},{"applies_to":"campus","as_of":"2026-09-08","basis":"acquired","metric":"land_area","note":"Bought for about USD 19 million according to property records cited by local news.","qualifier":"approximately","source_ids":["s4"],"unit":"acres","value":340},{"applies_to":"campus","as_of":"2026-09-08","basis":"planned","metric":"jobs_permanent","qualifier":"range","source_ids":["s4"],"unit":"count","value":100,"value_high":150}],"milestones":[{"date":"2026-02-05","event":"announced","kind":"actual","note":"IREN announced a new 1.6 GW Oklahoma campus without naming the town; its 10-K later lists the site as Kiowa, Oklahoma.","source_ids":["s3"]},{"date":"2026-04-21","event":"other","kind":"actual","note":"The county tax incentive district review committee approved the project plan.","source_ids":["s4"]},{"date":"2026-06-22","event":"other","kind":"actual","note":"County commissioners tabled the tax increment district decision and sent the plan back for renegotiation.","source_ids":["s6"]},{"date":"2028","event":"first_operational","kind":"planned","note":"IREN said in February 2026 that power is scheduled to ramp from 2028, and in May 2026 that additional Kiowa capacity is expected to ramp from 2028. News On 6 says production could begin in 2027, with completion in 2029.","source_ids":["s3","s1"]}],"name":"IREN Kiowa data center campus","notes":"IREN's February 2026 announcement names only Oklahoma; the link to Kiowa comes from IREN's 10-K and from local reporting on the Pittsburg County project. Local reports mention options for Google, Microsoft and AI startups as possible customers, but no tenant has been confirmed. IREN estimates more than USD 600 million in taxes and community payments over 25 years. News On 6 lists 2028 as the operational year in one place and completion in 2029 in another.","parties":[{"name":"IREN","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Public Service Company of Oklahoma","note":"Local reporting names PSO as the grid supplier; IREN's 10-K says the utility serving the Kiowa project has proposed a large-load rate subject to Oklahoma Corporation Commission review.","role":"utility","source_ids":["s2","s4"]},{"name":"Pittsburg County","note":"County commissioners are weighing a tax increment district and economic development plan for the project.","role":"government","source_ids":["s4","s6"]}],"power_sources":[{"description":"Grid connection via Public Service Company of Oklahoma, which local reports say will remain as backup if IREN later adds its own power system.","source_ids":["s2","s3","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-05-07","publisher":"IREN Ltd via SEC EDGAR","title":"IREN business update and Q3 FY26 results (Form 8-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1878848/000187884826000025/irenreportsq3fy26results.htm"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-27","publisher":"IREN Ltd via SEC EDGAR","title":"IREN Ltd annual report on Form 10-K for the fiscal year ended June 30, 2026","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1878848/000187884826000052/iren-20260630.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-02-05","publisher":"IREN","title":"IREN announces 1.6GW data center campus in Oklahoma","type":"company","url":"https://iren.com/resources/news/iren-oklahoma-1-6gw-data-center-campus"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260910130104/https://www.newson6.com/data-centers-in-oklahoma/what-to-know-kiowa-data-center-planned-for-pittsburg-county","id":"s4","published":"2026-09-08","publisher":"News On 6","title":"What to know: Kiowa data center planned for Pittsburg County","type":"news","url":"https://www.newson6.com/data-centers-in-oklahoma/what-to-know-kiowa-data-center-planned-for-pittsburg-county"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-08","publisher":"KOKH Fox 25","title":"Should Kiowa data center proposal go to a vote of the people?","type":"news","url":"https://okcfox.com/news/local/should-kiowa-data-center-proposal-go-to-a-vote-of-the-people"},{"accessed":"2026-10-09","id":"s6","published":"2026-06-22","publisher":"FOX23","title":"Pittsburg County delays decision on proposed data center tax increment district","type":"news","url":"https://fox23.com/news/local/pittsburg-county-delays-decision-on-proposed-data-center-tax-increment-district-06-23-2026"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Wikipedia","title":"Kiowa, Oklahoma","type":"other","url":"https://en.wikipedia.org/wiki/Kiowa,_Oklahoma"}],"status":"proposed","status_as_of":"2026-09-08","status_source_ids":["s4","s5"],"summary":"IREN plans a 1.6 GW grid-connected data center campus on a roughly 2,000-acre site just south of Kiowa in Pittsburg County, Oklahoma, between US 69 and Kiowa Lake Road. IREN announced the Oklahoma campus in February 2026, saying grid studies were complete and power would ramp from 2028; local reports say it had bought about 340 acres and would draw on Public Service Company of Oklahoma. A county tax incentive plan with an 85% property tax abatement was tabled in June 2026 for renegotiation, and in September 2026 the project still awaited county approval amid local opposition.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c17732e4-c073-50b6-8b87-20e3913f6b60","s2":"7d65dd59-1f92-5e99-978e-e5dd7a669bcb","s3":"ab274494-33ad-5e07-96d5-d86275bc0bb5","s4":"0e2edc42-b2dd-5f2e-be91-bbb3e5a2abad","s5":"cf79feb7-4d1d-5681-a57d-00e66eb8ff5d","s6":"e6cf4807-41b7-518a-82cf-4cfd94a1eade","s7":"04cdcd08-1dfc-59dc-9133-d6052c0175fa"},"source_file":"datacenters/projects/iren-kiowa-oklahoma.json","source_record_id":"iren-kiowa-oklahoma","source_record_sha256":"7a82fb1816b60ae0736e58a3073374185644fa92a93e57f59148f6d5c023d4fb","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4a3ace409a629d60e47a5528714fc7c45226403ff6c0c3f85f00097d4d710368"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f19474c4631ae00b2725/#project-39b97d53-5af7-55ea-bfc4-6f2f08f32e74 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/39b97d53-5af7-55ea-bfc4-6f2f08f32e74.json
39dca169-c304-53a7-b2a6-15a9a914e4d1 | imported:semiconductor-atlas:powerhouse-pennsylvania-digital-i-carlisle | vcc-site-07b3e2197c23d98b282e | imported:semiconductor-atlas:powerhouse-pennsylvania-digital-i-carlisle | Pennsylvania Digital I (PAX-1), Middlesex Township | United States | US | 40.2167 | -77.1164 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia point for Middlesex Township (s4). Local reporting places the site off Country Club Road about five miles northeast of Carlisle; the parcel was not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 0018bbb4-353b-533f-81ca-d19336a4c0f1 | announced | 2026-03-05 | 222 | imported_documented_status | fda41791-0eab-5673-8412-1bb0de11be5c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"0018bbb4-353b-533f-81ca-d19336a4c0f1","notes":"A division of American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"fda41791-0eab-5673-8412-1bb0de11be5c","notes":"A division of American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"0018bbb4-353b-533f-81ca-d19336a4c0f1","notes":null,"party":"Pennsylvania Data Center Partners","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"fda41791-0eab-5673-8412-1bb0de11be5c","notes":null,"party":"Pennsylvania Data Center Partners","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"e0c8f7d3-2413-5ec2-8fe0-2ceb65ac2d7c","notes":"Entity named as developer in the township subdivision approval and as signatory of the water and sewer agreement.","party":"Carlisle Development Partners LLC","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"fda41791-0eab-5673-8412-1bb0de11be5c","notes":"Entity named as developer in the township subdivision approval and as signatory of the water and sewer agreement.","party":"Carlisle Development Partners LLC","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"0018bbb4-353b-533f-81ca-d19336a4c0f1","notes":null,"party":"PPL Electric Utilities","relationship_scope":"unknown","role":"utility","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"fda41791-0eab-5673-8412-1bb0de11be5c","notes":null,"party":"PPL Electric Utilities","relationship_scope":"unknown","role":"utility","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"e0c8f7d3-2413-5ec2-8fe0-2ceb65ac2d7c","notes":null,"party":"Middlesex Township Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},{"evidence_id":"fda41791-0eab-5673-8412-1bb0de11be5c","notes":null,"party":"Middlesex Township Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://constructionreviewonline.com/450-mw-substation-approved-for-15b-pennsylvania-digital-i-pax-ai-data-center-in-carlisle/ | https://powerhousedata.com/news/pennsylvania-data-center-partners-and-powerhouse-data-centers-launch-joint-venture-to-build-next-gen-1-35-gw-hyperscale-data-center-campus-in-carlisle-pennsylvania | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry","master_park_with_multiple_subcampuses_not_individual_facility"],"rationale":"No matching named development in the 201-project release. Preserve Pennsylvania Digital I (PAX-1), Middlesex Township as an independent source record; its locality locator does not itself establish a surveyed physical site. Source encompasses a single explicitly bounded master park with multiple development subcampuses; retain that park-level scope.","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle"},"record":{"aliases":["Pennsylvania Digital I","Pennsylvania Digital 1","PAX-1","PAX"],"id":"powerhouse-pennsylvania-digital-i-carlisle","last_reviewed":"2026-10-09","location":{"admin1":"Pennsylvania","admin2":"Cumberland County","country":"US","lat":40.2167,"locality":"Middlesex Township","lon":-77.1164,"note":"Coordinates are the Wikipedia point for Middlesex Township (s4). Local reporting places the site off Country Club Road about five miles northeast of Carlisle; the parcel was not geocoded.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-07-15","basis":"planned","metric":"power_capacity","note":"Labelled utility capacity: three campuses, each with a dedicated 450 MW substation.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":1350},{"applies_to":"campus","as_of":"2025-07-15","basis":"planned","metric":"power_capacity","note":"Stated expansion potential.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s1","s3"],"unit":"MW","value":1800},{"applies_to":"phase","as_of":"2026-03-04","basis":"permitted","metric":"power_capacity","note":"Approved unanimously by township supervisors; the master plan gives each of the three campuses its own 450 MW substation.","phase_label":"Substation approved March 2026","power_scope":"grid_connection","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":450},{"applies_to":"phase","as_of":"2025-07-15","basis":"planned","metric":"power_capacity","note":"Targeted by the second quarter of 2027.","phase_label":"Near-term power delivery","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-07-15","basis":"announced","metric":"investment","note":"Trade press reports a split of about USD 9.8 billion for IT equipment, USD 3 billion for construction, USD 1.5 billion for power infrastructure and USD 750 million for cooling, security and land.","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"USD","value":15000000000},{"applies_to":"campus","as_of":"2026-01-09","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"acres","value":700},{"applies_to":"campus","as_of":"2026-01-09","basis":"planned","metric":"buildings","note":"Three campuses of six buildings each.","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":18},{"applies_to":"campus","as_of":"2026-03-05","basis":"reported","metric":"jobs_construction","note":"Peak construction jobs as reported by trade press; no company source for this figure was opened.","qualifier":"up_to","source_ids":["s3"],"unit":"count","value":30000},{"applies_to":"campus","as_of":"2026-03-05","basis":"reported","metric":"jobs_permanent","qualifier":"exact","source_ids":["s3"],"unit":"count","value":270}],"milestones":[{"date":"2025-07-15","event":"announced","kind":"actual","note":"Announced at the Pennsylvania Energy and Innovation Summit in Pittsburgh.","source_ids":["s1"]},{"date":"2026-01","event":"other","kind":"actual","note":"Township supervisors approved subdivision plans, as reported on 9 January 2026 (the vote date is not stated); land development plans and decisions on power and water were still needed before construction.","source_ids":["s2"]},{"date":"2026-01-15","event":"other","kind":"actual","note":"USD 14.1 million agreement with the township for rights to public water and sewer service.","source_ids":["s3"]},{"date":"2026-03-04","event":"permit_approved","kind":"actual","note":"Supervisors unanimously approved the first 450 MW substation; vertical construction had not yet begun.","source_ids":["s3"]},{"date":"2027-Q2","event":"first_operational","kind":"planned","note":"Target for the first 300 MW of power delivery.","source_ids":["s1","s3"]}],"name":"Pennsylvania Digital I (PAX-1), Middlesex Township","notes":"Construction Review (published 5 March 2026, updated 15 June 2026) also reports that supervisors rejected adding more than 214 acres along Harrisburg Pike and signalled a pause on further data center zoning changes until the comprehensive plan is updated. No report of a construction start after March 2026 was found. WHP580 reported in January 2026 that the Middlesex water authority had committed to reserve up to 400,000 gallons a day.","parties":[{"name":"PowerHouse Data Centers","note":"A division of American Real Estate Partners (AREP).","role":"developer","source_ids":["s1","s3"]},{"name":"Pennsylvania Data Center Partners","role":"developer","source_ids":["s1","s3"]},{"name":"Carlisle Development Partners LLC","note":"Entity named as developer in the township subdivision approval and as signatory of the water and sewer agreement.","role":"developer","source_ids":["s2","s3"]},{"name":"PPL Electric Utilities","role":"utility","source_ids":["s1","s3"]},{"name":"Middlesex Township Board of Supervisors","role":"government","source_ids":["s2","s3"]}],"power_sources":[{"description":"PPL Electric Utilities will connect the campuses to its transmission system through dedicated 450 MW substations.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260617125013/https://www.powerhousedata.com/news/pennsylvania-data-center-partners-and-powerhouse-data-centers-launch-joint-venture-to-build-next-gen-1-35-gw-hyperscale-data-center-campus-in-carlisle-pennsylvania","id":"s1","published":"2025-07-15","publisher":"PowerHouse Data Centers","title":"Pennsylvania Data Center Partners and PowerHouse Data Centers Launch Joint Venture to Build Next-Gen 1.35 GW Hyperscale Data Center Campus in Carlisle, Pennsylvania","type":"company","url":"https://powerhousedata.com/news/pennsylvania-data-center-partners-and-powerhouse-data-centers-launch-joint-venture-to-build-next-gen-1-35-gw-hyperscale-data-center-campus-in-carlisle-pennsylvania"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260114083108/https://bob949.iheart.com/featured/whp580-newsroom/content/2026-01-09-plans-approved-for-18-building-data-center-in-pennsylvania/","id":"s2","published":"2026-01-09","publisher":"WHP580 Newsroom (iHeartMedia)","title":"Plans Approved for 18-Building Data Center in Pennsylvania","type":"news","url":"https://bob949.iheart.com/featured/whp580-newsroom/content/2026-01-09-plans-approved-for-18-building-data-center-in-pennsylvania/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260509164158/https://constructionreviewonline.com/450-mw-substation-approved-for-15b-pennsylvania-digital-i-pax-ai-data-center-in-carlisle/","id":"s3","published":"2026-03-05","publisher":"Construction Review Online","title":"$15 Billion AI Data Center Project in Pennsylvania Clears Key Milestone","type":"trade_press","url":"https://constructionreviewonline.com/450-mw-substation-approved-for-15b-pennsylvania-digital-i-pax-ai-data-center-in-carlisle/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Middlesex Township, Cumberland County, Pennsylvania","type":"other","url":"https://en.wikipedia.org/wiki/Middlesex_Township,_Cumberland_County,_Pennsylvania"}],"status":"announced","status_as_of":"2026-03-05","status_source_ids":["s3"],"summary":"Hyperscale AI data center development on about 700 acres off Country Club Road in Middlesex Township, Cumberland County, roughly five miles northeast of Carlisle, Pennsylvania. Pennsylvania Data Center Partners and PowerHouse Data Centers announced the USD 15 billion joint venture in July 2025: three campuses of six buildings, each with its own 450 MW substation, for 1.35 GW of utility capacity expandable to 1.8 GW, connected by PPL Electric Utilities. Township supervisors approved subdivision plans in January 2026 and a 450 MW substation in March 2026, before vertical construction began. The developers target 300 MW of power by the second quarter of 2027.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"0018bbb4-353b-533f-81ca-d19336a4c0f1","s2":"e0c8f7d3-2413-5ec2-8fe0-2ceb65ac2d7c","s3":"fda41791-0eab-5673-8412-1bb0de11be5c","s4":"2fca3e43-9324-59c0-bde1-f38ea5ca4910"},"source_file":"datacenters/projects/powerhouse-pennsylvania-digital-i-carlisle.json","source_record_id":"powerhouse-pennsylvania-digital-i-carlisle","source_record_sha256":"0c0cb2497e4d2856da48fa35254909b5de6811fcf8e5589d7ecbcec7bdadded3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"2508d9e8e994b87fadbf70317086c9aa5eb855648aff9617fde30cc4cc393c54"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-07b3e2197c23d98b282e/#project-39dca169-c304-53a7-b2a6-15a9a914e4d1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/39dca169-c304-53a7-b2a6-15a9a914e4d1.json
39eada86-53aa-55d0-ae26-0ff35f9e1207 | imported:semiconductor-atlas:lancium-qts-hall-county-texas | vcc-site-990a491f49bc3fcbf938 | imported:semiconductor-atlas:lancium-qts-hall-county-texas | QTS and Lancium Hall County data center campus | United States | US | 34.3939 | -100.8953 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid of Turkey from Wikipedia (s2); the announcement says only that the campus is near Turkey in Hall County. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6c8c178e-7ec1-5458-96d5-446d5fa443fc | announced | 2026-07-13 | 92 | imported_documented_status | 6c8c178e-7ec1-5458-96d5-446d5fa443fc | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6c8c178e-7ec1-5458-96d5-446d5fa443fc","notes":"Owns the campus and provides electrical and civil infrastructure.","party":"Lancium","relationship_scope":"unknown","role":"owner","source_record_id":"lancium-qts-hall-county-texas"},{"evidence_id":"6c8c178e-7ec1-5458-96d5-446d5fa443fc","notes":"Will design and build the data center buildings.","party":"QTS","relationship_scope":"unknown","role":"developer","source_record_id":"lancium-qts-hall-county-texas"},{"evidence_id":"6c8c178e-7ec1-5458-96d5-446d5fa443fc","notes":null,"party":"QTS","relationship_scope":"unknown","role":"operator","source_record_id":"lancium-qts-hall-county-texas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Lancium | QTS |  |  |  | https://lancium.com/2026/07/13/qts-and-lancium-announce-data-center-campus-in-hall-county-texas/ | https://lancium.com/2026/07/13/qts-and-lancium-announce-data-center-campus-in-hall-county-texas/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve QTS and Lancium Hall County data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"lancium-qts-hall-county-texas"},"record":{"aliases":["Hall County Clean Campus"],"id":"lancium-qts-hall-county-texas","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Hall County","country":"US","lat":34.3939,"locality":"Turkey","lon":-100.8953,"note":"Town centroid of Turkey from Wikipedia (s2); the announcement says only that the campus is near Turkey in Hall County.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-13","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2026-07-13","basis":"planned","metric":"jobs_construction","note":"Estimated at peak construction.","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":7000},{"applies_to":"campus","as_of":"2026-07-13","basis":"planned","metric":"jobs_permanent","note":"Includes QTS staff, maintenance, security and tenant roles.","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":350}],"milestones":[{"date":"2026-07-13","event":"announced","kind":"actual","source_ids":["s1"]}],"name":"QTS and Lancium Hall County data center campus","parties":[{"name":"Lancium","note":"Owns the campus and provides electrical and civil infrastructure.","role":"owner","source_ids":["s1"]},{"name":"QTS","note":"Will design and build the data center buildings.","role":"developer","source_ids":["s1"]},{"name":"QTS","role":"operator","source_ids":["s1"]}],"power_sources":[{"description":"Lancium plans to bring its own power to the site using solar resources.","source_ids":["s1"],"type":"solar"},{"description":"Lancium plans battery storage as part of its own power supply for the site.","source_ids":["s1"],"type":"battery_storage"},{"description":"Lancium and QTS will fund all energy infrastructure improvements, described as modernizing the grid for existing customers.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-07-13","publisher":"Lancium","title":"QTS and Lancium Announce Data Center Campus in Hall County, Texas","type":"company","url":"https://lancium.com/2026/07/13/qts-and-lancium-announce-data-center-campus-in-hall-county-texas/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Wikipedia","title":"Turkey, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Turkey,_Texas"}],"status":"announced","status_as_of":"2026-07-13","status_source_ids":["s1"],"summary":"Lancium and QTS announced in July 2026 a data center campus near Turkey in Hall County, Texas, with more than 10 billion US dollars of planned capital investment. Lancium owns the campus and provides electrical and civil infrastructure, planning to bring its own power through battery storage and solar; QTS will design, build and operate the data center buildings. The companies said they would fund all needed energy infrastructure upgrades. Up to 7,000 construction jobs at peak and about 350 permanent jobs were projected. No capacity figure, tenant or construction dates were disclosed.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6c8c178e-7ec1-5458-96d5-446d5fa443fc","s2":"c0679470-41f4-5352-9e73-b58a0d3ca220"},"source_file":"datacenters/projects/lancium-qts-hall-county-texas.json","source_record_id":"lancium-qts-hall-county-texas","source_record_sha256":"4222f70fc7dc8ee04af42849cfb64b61e2a89b51e0d2fed9a253db2601422e60","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b7e19b3b09d5f4b313ad66063c4a0eaabaaf7ac5a4284b936f9342ebd50f009f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-990a491f49bc3fcbf938/#project-39eada86-53aa-55d0-ae26-0ff35f9e1207 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/39eada86-53aa-55d0-ae26-0ff35f9e1207.json
3a54ff50-0fd6-5767-86f2-c6818a515bb2 | imported:semiconductor-atlas:start-campus-sines | vcc-site-fdb92bb99c36b43e6162 | epoch-ai:data-center:1fb39208-53bc-5714-80d2-881a5c944551 | Start Campus SINES data center campus | Portugal | PT | 37.9349 | -8.8132 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Nominatim (OpenStreetMap) geocode of the industrial land-use area tagged Start Campus in Sines; sources name the campus in Sines but give no street address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 185ef1c7-2599-5b98-b3cb-e32b54ed5282 | partially_operational | 2026-08-03 | 71 | imported_documented_status | 185ef1c7-2599-5b98-b3cb-e32b54ed5282 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"185ef1c7-2599-5b98-b3cb-e32b54ed5282","notes":null,"party":"Start Campus","relationship_scope":"unknown","role":"developer","source_record_id":"start-campus-sines"},{"evidence_id":"c26c1506-4225-510a-b088-02cb3cee0fb5","notes":null,"party":"Start Campus","relationship_scope":"unknown","role":"developer","source_record_id":"start-campus-sines"},{"evidence_id":"185ef1c7-2599-5b98-b3cb-e32b54ed5282","notes":null,"party":"Start Campus","relationship_scope":"unknown","role":"operator","source_record_id":"start-campus-sines"},{"evidence_id":"8d5ef160-d4d4-5455-bee2-30cb60786f1a","notes":"Reported as majority owner of the campus; it and Pioneer Point fund the project through private equity vehicles.","party":"Davidson Kempner","relationship_scope":"unknown","role":"owner","source_record_id":"start-campus-sines"},{"evidence_id":"a2aa0e8f-373f-5374-8873-b74019927720","notes":"Reported as majority owner of the campus; it and Pioneer Point fund the project through private equity vehicles.","party":"Davidson Kempner","relationship_scope":"unknown","role":"owner","source_record_id":"start-campus-sines"},{"evidence_id":"8d5ef160-d4d4-5455-bee2-30cb60786f1a","notes":null,"party":"Pioneer Point Partners","relationship_scope":"unknown","role":"investor","source_record_id":"start-campus-sines"},{"evidence_id":"a2aa0e8f-373f-5374-8873-b74019927720","notes":null,"party":"Pioneer Point Partners","relationship_scope":"unknown","role":"investor","source_record_id":"start-campus-sines"},{"evidence_id":"185ef1c7-2599-5b98-b3cb-e32b54ed5282","notes":"Direct customer and build partner for SIN02; also deployed GPUs for Microsoft in SIN01.","party":"Nscale","relationship_scope":"unknown","role":"tenant","source_record_id":"start-campus-sines"},{"evidence_id":"530680ce-0ac6-56cb-92ab-13356fd52053","notes":"Direct customer and build partner for SIN02; also deployed GPUs for Microsoft in SIN01.","party":"Nscale","relationship_scope":"unknown","role":"tenant","source_record_id":"start-campus-sines"},{"evidence_id":"3e4c60b3-3674-5f32-8d30-a4ded842d8bc","notes":"Direct customer and build partner for SIN02; also deployed GPUs for Microsoft in SIN01.","party":"Nscale","relationship_scope":"unknown","role":"tenant","source_record_id":"start-campus-sines"},{"evidence_id":"8d5ef160-d4d4-5455-bee2-30cb60786f1a","notes":"Rents capacity through Nscale; reported to occupy part of SIN01 and all of SIN02.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"start-campus-sines"},{"evidence_id":"46367d7a-fc45-5794-bb02-14f8a8dada66","notes":"Rents capacity through Nscale; reported to occupy part of SIN01 and all of SIN02.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"start-campus-sines"},{"evidence_id":"3e4c60b3-3674-5f32-8d30-a4ded842d8bc","notes":"Rents capacity through Nscale; reported to occupy part of SIN01 and all of SIN02.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"start-campus-sines"},{"evidence_id":"185ef1c7-2599-5b98-b3cb-e32b54ed5282","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"start-campus-sines"},{"evidence_id":"530680ce-0ac6-56cb-92ab-13356fd52053","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"start-campus-sines"},{"evidence_id":"185ef1c7-2599-5b98-b3cb-e32b54ed5282","notes":"Portuguese transmission operator that awarded the additional grid power.","party":"REN","relationship_scope":"unknown","role":"utility","source_record_id":"start-campus-sines"},{"evidence_id":"c26c1506-4225-510a-b088-02cb3cee0fb5","notes":"Portuguese transmission operator that awarded the additional grid power.","party":"REN","relationship_scope":"unknown","role":"utility","source_record_id":"start-campus-sines"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Davidson Kempner | Start Campus |  | Microsoft; Nscale |  | https://www.startcampus.pt/ | https://www.startcampus.pt/ | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["approximate_locator_not_boundary","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Start Campus Sines six-building campus. Source includes operational SIN01 and future full campus; existing record specifically selects SIN02 construction.","source_record_id":"start-campus-sines","target_physical_site_stable_key":"epoch-ai:data-center:1fb39208-53bc-5714-80d2-881a5c944551"},"record":{"aliases":["SINES DC","SINES Data Campus","Sines 4.0"],"id":"start-campus-sines","last_reviewed":"2026-10-09","location":{"admin1":"Setúbal District","admin2":"Sines","country":"PT","lat":37.9349,"locality":"Sines","lon":-8.8132,"note":"Nominatim (OpenStreetMap) geocode of the industrial land-use area tagged Start Campus in Sines; sources name the campus in Sines but give no street address.","precision":"approximate_site","source_ids":["s1","s5"]},"metrics":[{"applies_to":"campus","as_of":"2024-08-15","basis":"planned","metric":"power_capacity","note":"Secured IT capacity after REN raised the grid allocation from an initial 495 MW (per the company site).","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":1200},{"applies_to":"phase","as_of":"2026-08-03","basis":"operational","metric":"power_capacity","note":"Earlier reports gave 14 MW expanding to 26 MW (2024) and 31 MW (January 2026) for this building.","phase_label":"SIN01","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s5"],"unit":"MW","value":37.5},{"applies_to":"phase","as_of":"2026-01-13","basis":"planned","metric":"power_capacity","note":"Lusa reported about 180 MW of IT load for the second building before its construction began.","phase_label":"SIN02","power_scope":"it_load","qualifier":"approximately","source_ids":["s6"],"unit":"MW","value":180},{"applies_to":"phase","as_of":"2026-08-03","basis":"under_construction","metric":"power_capacity","note":"The article body gives 180-240 MW of IT capacity; its introduction says 180-200 MW and the first suite for Nscale is described as 200 MW.","phase_label":"SIN02","power_scope":"it_load","qualifier":"range","source_ids":["s5"],"unit":"MW","value":180,"value_high":240},{"applies_to":"phase","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Company site lists SIN02 as the next planned facility at 200 MW; the page is undated, so as_of is the access date.","phase_label":"SIN02","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-01-13","basis":"announced","metric":"investment","note":"Total for the six-building campus.","qualifier":"approximately","source_ids":["s2","s6"],"unit":"EUR","value":8500000000},{"applies_to":"campus","as_of":"2025-11-11","basis":"announced","metric":"investment","note":"Microsoft's announced AI infrastructure spend tied to the Sines campus; separate from and not additive with the developer's figure.","qualifier":"exact","source_ids":["s1","s7"],"unit":"USD","value":10000000000},{"applies_to":"phase","as_of":"2026-05-05","basis":"reported","metric":"investment","note":"Amount the article says is earmarked for SIN02 development, alongside about EUR 230 million that Nscale plans for shared infrastructure; the article does not clearly name who spends the EUR 465 million.","phase_label":"SIN02","qualifier":"exact","source_ids":["s7"],"unit":"EUR","value":465000000},{"accelerator_model":"NVIDIA GB300 (Blackwell Ultra)","applies_to":"phase","as_of":"2026-05-05","basis":"installed","metric":"accelerators","phase_label":"SIN01","qualifier":"more_than","source_ids":["s1","s3","s7"],"unit":"count","value":12600},{"accelerator_model":"NVIDIA Vera Rubin","applies_to":"phase","as_of":"2026-08-03","basis":"planned","metric":"accelerators","phase_label":"SIN02","qualifier":"approximately","source_ids":["s1","s5","s7"],"unit":"count","value":66000},{"applies_to":"campus","as_of":"2026-03-02","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s4","s6"],"unit":"count","value":6},{"applies_to":"phase","as_of":"2026-01-13","basis":"planned","metric":"jobs_construction","note":"Typical workforce; peaks of about 2,500 expected.","phase_label":"SIN02","qualifier":"approximately","source_ids":["s6"],"unit":"count","value":1500}],"milestones":[{"date":"2024-08-08","event":"other","kind":"actual","note":"REN awarded additional grid power, lifting secured IT capacity to 1.2 GW.","source_ids":["s1","s2"]},{"date":"2024-Q4","event":"first_operational","kind":"actual","note":"SIN01 reported operational at the end of 2024; the company lists its inauguration on 2025-04-04.","source_ids":["s5"]},{"date":"2025-04-04","event":"other","kind":"actual","note":"Official inauguration of SIN01.","source_ids":["s1"]},{"date":"2025-10-14","event":"other","kind":"actual","note":"Microsoft agreed to rent Nscale GPU capacity at the campus.","source_ids":["s3"]},{"date":"2026-Q1","event":"construction_started","kind":"actual","note":"Start of SIN02 construction; preparatory works had run since late 2025.","source_ids":["s4","s6"]},{"date":"2027-Q4","event":"other","kind":"planned","note":"Delivery of a first 200 MW SIN02 suite to Nscale; Lusa reported first SIN02 clients expected by mid-2027.","source_ids":["s5","s6"]},{"date":"2030","event":"fully_operational","kind":"planned","note":"2024 target for all buildings; a 2026 report gives 2031 for project completion.","source_ids":["s2"]},{"date":"2031","event":"fully_operational","kind":"planned","source_ids":["s4"]}],"name":"Start Campus SINES data center campus","notes":"SIN01 capacity figures differ across sources (14-26 MW in 2024, 31 MW in January 2026, 37.5 MW in 2026). Microsoft's USD 10 billion pledge and the developer's EUR 8.5 billion estimate describe different spenders and should not be summed.","parties":[{"name":"Start Campus","role":"developer","source_ids":["s1","s2"]},{"name":"Start Campus","role":"operator","source_ids":["s1"]},{"name":"Davidson Kempner","note":"Reported as majority owner of the campus; it and Pioneer Point fund the project through private equity vehicles.","role":"owner","source_ids":["s3","s6"]},{"name":"Pioneer Point Partners","role":"investor","source_ids":["s3","s6"]},{"name":"Nscale","note":"Direct customer and build partner for SIN02; also deployed GPUs for Microsoft in SIN01.","role":"tenant","source_ids":["s1","s5","s7"]},{"name":"Microsoft","note":"Rents capacity through Nscale; reported to occupy part of SIN01 and all of SIN02.","role":"tenant","source_ids":["s3","s4","s7"]},{"name":"NVIDIA","role":"hardware_supplier","source_ids":["s1","s5"]},{"name":"REN","note":"Portuguese transmission operator that awarded the additional grid power.","role":"utility","source_ids":["s1","s2"]}],"power_sources":[{"description":"Grid connection secured from REN; the second-building works include a high-voltage substation and a 400/150 kV substation north of the campus. The company says the site uses 100% renewable energy and has an agreement with EDP on new renewable capacity.","source_ids":["s1","s5","s6"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Start Campus","title":"SINES Data Campus","type":"company","url":"https://www.startcampus.pt/"},{"accessed":"2026-10-09","id":"s2","published":"2024-08-15","publisher":"Data Center Frontier","title":"Fresh Start: SINES DC Eyes Sustainable 1.2 GW IT Capacity as Europe's Largest Colocation Campus","type":"trade_press","url":"https://datacenterfrontier.com/colocation/article/55133589/fresh-start-sines-dc-eyes-sustainable-12-gw-it-capacity-as-europes-largest-colocation-campus"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251016142807/https://www.datacenterknowledge.com/deals/microsoft-to-rent-nscale-ai-data-center-capacity-in-portugal","id":"s3","published":"2025-10-14","publisher":"Data Center Knowledge (Bloomberg)","title":"Microsoft to Rent Nscale AI Data Center Capacity in Portugal","type":"trade_press","url":"https://www.datacenterknowledge.com/deals/microsoft-to-rent-nscale-ai-data-center-capacity-in-portugal"},{"accessed":"2026-10-09","id":"s4","published":"2026-03-02","publisher":"Essential Business","title":"Start Campus in €2Bn deal to build Microsoft centre in Sines","type":"news","url":"https://www.essential-business.pt/2026/03/02/start-campus-in-e2bn-deal-to-build-microsoft-centre-in-sines/"},{"accessed":"2026-10-09","id":"s5","published":"2026-08-03","publisher":"Capacity","title":"Data centre of the month: Start Campus SINES development in Portugal","type":"trade_press","url":"https://capacityglobal.com/news/data-centre-of-the-month-start-campus-sines-portugal-interview/"},{"accessed":"2026-10-09","id":"s6","published":"2026-01-13","publisher":"Executive Digest (Lusa)","title":"Start Campus avança em fevereiro com segundo edifício do centro de dados de Sines","type":"news","url":"https://executivedigest.sapo.pt/?p=704935"},{"accessed":"2026-10-09","id":"s7","published":"2026-05-05","publisher":"Portal ERP","title":"Start Campus reforça posição de Portugal na infraestrutura europeia de IA com expansão em Sines","type":"trade_press","url":"https://portalerp.com/pt/noticia/start-campus-reforca-posicao-de-portugal-na-infraestrutura-europeia-de-ia-com-expansao-em-sines"}],"status":"partially_operational","status_as_of":"2026-08-03","status_source_ids":["s1","s5"],"summary":"Start Campus is building a six-building data center campus in Sines, Portugal, on a site with a decommissioned power plant, using seawater cooling. Grid power secured from REN gives the campus about 1.2 GW of IT capacity. The first building (SIN01) is in service and full; the much larger second building (SIN02) is under construction and is to be fully occupied by Nscale, which is deploying Nvidia systems for Microsoft. The full campus is targeted around 2030-2031.","workloads":["colocation","cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"185ef1c7-2599-5b98-b3cb-e32b54ed5282","s2":"c26c1506-4225-510a-b088-02cb3cee0fb5","s3":"8d5ef160-d4d4-5455-bee2-30cb60786f1a","s4":"46367d7a-fc45-5794-bb02-14f8a8dada66","s5":"530680ce-0ac6-56cb-92ab-13356fd52053","s6":"a2aa0e8f-373f-5374-8873-b74019927720","s7":"3e4c60b3-3674-5f32-8d30-a4ded842d8bc"},"source_file":"datacenters/projects/start-campus-sines.json","source_record_id":"start-campus-sines","source_record_sha256":"e191e9241fa8bdf6141fcf892c29124043391e1435e8be79ed7237aed12f6426","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"ddddec762a953d619f874a5e5e3a96597261bd1d6fe8e3807d19857a4e1ccd3a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fdb92bb99c36b43e6162/#project-3a54ff50-0fd6-5767-86f2-c6818a515bb2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3a54ff50-0fd6-5767-86f2-c6818a515bb2.json
3b636397-fbb2-5564-a352-fa1382a218b5 | curated:vantage-lighthouse-port-washington-campus:current-campus-build | vcc-site-d272a722ca415c1be654 | curated:vantage-lighthouse-port-washington-campus | Vantage Lighthouse Port Washington Current Campus Build | United States | US | 43.4307 | -87.8615 | Point | project | coordinates_to_point | official_project_coordinate | environmental_review_project_point | official_source | project_locator | Exact sign-and-decimal parsing of the DNR project coordinate; not a parcel, building, or construction footprint. |  | Wisconsin DNR publishes no bounded accuracy for the project coordinate. | 40f1c2ae-aacb-5aac-8edd-60e4a405c7fc | under_construction | 2026-06-12 | 123 | authoritative_physical_status_update | 928bbcd8-079d-5b85-a631-2477c6513a79 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"2853444c-d991-5aa9-82a6-31b621178535","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"2b179a35-b28d-57c4-86d4-e1ab5a58e8e7","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"8b9534a2-5109-5738-adc5-1f8a62f5c027","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"2b179a35-b28d-57c4-86d4-e1ab5a58e8e7","notes":"Named as a tenant with OpenAI, providing Oracle Cloud Infrastructure capacity for the project. Wisconsin Watch describes Oracle as co-developing the campus with OpenAI, and an Oracle subsidiary challenged state utility financial-security rules in court.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"8b9534a2-5109-5738-adc5-1f8a62f5c027","notes":"Named as a tenant with OpenAI, providing Oracle Cloud Infrastructure capacity for the project. Wisconsin Watch describes Oracle as co-developing the campus with OpenAI, and an Oracle subsidiary challenged state utility financial-security rules in court.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"3a993ad5-1b04-5754-9adb-eac65e528c2b","notes":"Named as a tenant with OpenAI, providing Oracle Cloud Infrastructure capacity for the project. Wisconsin Watch describes Oracle as co-developing the campus with OpenAI, and an Oracle subsidiary challenged state utility financial-security rules in court.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"2b179a35-b28d-57c4-86d4-e1ab5a58e8e7","notes":"End user under the Stargate program.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"8b9534a2-5109-5738-adc5-1f8a62f5c027","notes":"End user under the Stargate program.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"2853444c-d991-5aa9-82a6-31b621178535","notes":null,"party":"We Energies","relationship_scope":"unknown","role":"utility","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"3a993ad5-1b04-5754-9adb-eac65e528c2b","notes":null,"party":"We Energies","relationship_scope":"unknown","role":"utility","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"8b9534a2-5109-5738-adc5-1f8a62f5c027","notes":"Contractor on the second building to top out.","party":"Whiting-Turner Contracting","relationship_scope":"unknown","role":"builder","source_record_id":"oracle-vantage-port-washington"},{"evidence_id":"8b9534a2-5109-5738-adc5-1f8a62f5c027","notes":"Contractor on another of the data center buildings.","party":"The Weitz Co.","relationship_scope":"unknown","role":"builder","source_record_id":"oracle-vantage-port-washington"}] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | Vantage Data Centers |  |  | OpenAI; Oracle |  | https://dnr.wisconsin.gov/topic/EIA/Portwashington.html | https://dnr.wisconsin.gov/topic/EIA/Portwashington.html | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same Vantage Lighthouse four-building Port Washington campus for Oracle/OpenAI. Lighthouse alias, developer, locality and Wisconsin DNR identity agree.","source_record_id":"oracle-vantage-port-washington","target_project_stable_key":"curated:vantage-lighthouse-port-washington-campus:current-campus-build"},"record":{"aliases":["Lighthouse","Project Lighthouse","Stargate Wisconsin"],"id":"oracle-vantage-port-washington","last_reviewed":"2026-10-09","location":{"admin1":"Wisconsin","admin2":"Ozaukee County","country":"US","lat":43.3886,"locality":"Port Washington","lon":-87.8693,"note":"Port Washington city centroid from OpenStreetMap Nominatim. Sources place the campus on the city's north side, just west of Interstate 43, without giving an address or parcel.","precision":"locality","source_ids":["s1","s7","s8"]},"metrics":[{"applies_to":"campus","as_of":"2025-10-23","basis":"planned","metric":"power_capacity","note":"Announced as close to a gigawatt of AI capacity across four data centers.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s2"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Vantage's locations page lists the campus at 902 MW total without saying whether this is IT or facility power.","power_scope":"unspecified","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":902},{"applies_to":"campus","as_of":"2025-08-20","basis":"planned","metric":"power_capacity","note":"Local reporting on the 2025 city approval said the campus would use 1.3 GW of power; it does not reconcile this with the 902 MW figure.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":1300},{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"power_capacity","note":"Analyst estimate, not a company disclosure: Epoch AI's projection of total facility power.","power_scope":"facility","qualifier":"approximately","source_ids":["s4"],"unit":"MW","value":1300},{"applies_to":"campus","as_of":"2025-08-20","basis":"announced","metric":"investment","note":"Figure given by Vantage when the city approved the developer's agreement; Vantage said it was likely to grow.","qualifier":"at_least","source_ids":["s1"],"unit":"USD","value":8000000000},{"applies_to":"campus","as_of":"2026-09-11","basis":"reported","metric":"investment","qualifier":"approximately","source_ids":["s5","s6","s7"],"unit":"USD","value":15000000000},{"applies_to":"campus","as_of":"2025-08-20","basis":"acquired","metric":"land_area","note":"Total land Vantage bought on the city's north side; only the southern 672 acres are being developed.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":1900},{"applies_to":"campus","as_of":"2026-07-01","basis":"planned","metric":"land_area","qualifier":"approximately","source_ids":["s1","s6"],"unit":"acres","value":672},{"applies_to":"campus","as_of":"2025-10-23","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2","s6"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2026-07-01","basis":"planned","metric":"floor_area","note":"The 2025 plan described two buildings of about 560,000 sq ft and two of about 719,000 sq ft.","qualifier":"approximately","source_ids":["s1","s6","s7"],"unit":"sq_ft","value":2500000},{"applies_to":"campus","as_of":"2025-10-23","basis":"planned","metric":"jobs_construction","note":"Mostly union jobs. In mid-2026 about 1,700 workers were on site, expected to reach about 5,000 going into winter.","qualifier":"more_than","source_ids":["s2","s6"],"unit":"count","value":4000},{"applies_to":"campus","as_of":"2025-10-23","basis":"planned","metric":"jobs_permanent","note":"Figure from the October 2025 announcement and repeated in September 2026 coverage; in August 2025 Vantage spoke of about 300 long-term employees.","qualifier":"more_than","source_ids":["s1","s2","s7"],"unit":"count","value":1000}],"milestones":[{"date":"2025-08","event":"other","kind":"actual","note":"Port Washington approved a developer's agreement with Vantage for the campus.","source_ids":["s1"]},{"date":"2025-10","event":"announced","kind":"actual","note":"OpenAI, Oracle and Vantage announced the campus as a Stargate site.","source_ids":["s2"]},{"date":"2026-Q1","event":"construction_started","kind":"actual","note":"Analyst estimate, not a company disclosure: Epoch AI dates the start from satellite imagery showing foundation work by February 2026; ground preparation may have begun earlier.","source_ids":["s4"]},{"date":"2026-06","event":"other","kind":"actual","note":"An Oracle subsidiary sued Wisconsin utility regulators in Ozaukee County court over tightened financial-security requirements for data center customers of We Energies.","source_ids":["s5"]},{"date":"2026-06","event":"other","kind":"actual","note":"Second of four buildings topped out; the project was reported to be about 12 to 15 percent complete.","source_ids":["s6"]},{"date":"2026-10-02","event":"other","kind":"actual","note":"We Energies proposed letting Oracle subscribe to 10 to 20 percent of Point Beach nuclear plant output to help serve the campus, pending regulatory approval.","source_ids":["s8"]},{"date":"2028","event":"fully_operational","kind":"planned","source_ids":["s2","s7"]}],"name":"Vantage Lighthouse campus (Stargate Port Washington)","notes":"Capacity figures differ by source and basis: close to 1 GW at announcement, 902 MW on Vantage's site, 1.3 GW of power in local reporting, and a 1.3 GW facility-power projection from analyst Epoch AI that is not a company disclosure. Reported investment rose from at least $8 billion in August 2025 to about $15 billion by mid-2026. Related-story headlines on news pages suggest Oracle later dropped its lawsuit, but no article opened here reports that.","parties":[{"name":"Vantage Data Centers","role":"developer","source_ids":["s1","s2"]},{"name":"Vantage Data Centers","role":"owner","source_ids":["s6"]},{"name":"Oracle","note":"Named as a tenant with OpenAI, providing Oracle Cloud Infrastructure capacity for the project. Wisconsin Watch describes Oracle as co-developing the campus with OpenAI, and an Oracle subsidiary challenged state utility financial-security rules in court.","role":"tenant","source_ids":["s2","s6","s8"]},{"name":"OpenAI","note":"End user under the Stargate program.","role":"tenant","source_ids":["s2","s6"]},{"name":"We Energies","role":"utility","source_ids":["s1","s8"]},{"name":"Whiting-Turner Contracting","note":"Contractor on the second building to top out.","role":"builder","source_ids":["s6"]},{"name":"The Weitz Co.","note":"Contractor on another of the data center buildings.","role":"builder","source_ids":["s6"]}],"power_sources":[{"description":"Supplied by We Energies, with Vantage saying no cost of acquiring the energy will be passed on to other utility customers.","source_ids":["s1","s8"],"type":"grid"},{"description":"Roughly 70 percent of the campus supply is to come from zero-emission sources, which analyst Epoch AI lists as solar, wind and battery storage, with the rest offset through purchased credits.","source_ids":["s1","s4"],"type":"solar"},{"description":"Wind is part of the 70 percent clean supply mix described for the campus by analyst Epoch AI.","source_ids":["s4"],"type":"wind"},{"description":"Battery storage is part of the 70 percent clean supply mix described for the campus by analyst Epoch AI.","source_ids":["s4"],"type":"battery_storage"},{"description":"Proposed subscription by Oracle to 10 to 20 percent of Point Beach nuclear plant generation through We Energies, awaiting Public Service Commission approval.","source_ids":["s8"],"type":"nuclear"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251007204317/https://ozaukeepress.com/content/vantage-chief-calls-complex-large-even-its-standards","id":"s1","published":"2025-08-20","publisher":"Ozaukee Press","title":"Vantage chief calls complex large even by its standards","type":"news","url":"https://ozaukeepress.com/content/vantage-chief-calls-complex-large-even-its-standards"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260520191926/https://w.media/openai-oracle-and-vantage-data-centers-announce-stargate-data-center-site-in-wisconsin/","id":"s2","published":"2025-10-23","publisher":"W.Media","title":"OpenAI, Oracle and Vantage Data Centers announce Stargate data center site in Wisconsin","type":"trade_press","url":"https://w.media/openai-oracle-and-vantage-data-centers-announce-stargate-data-center-site-in-wisconsin/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Vantage Data Centers","title":"Data Center Locations - North America","type":"company","url":"https://vantage-dc.com/data-center-locations/north-america/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260517184326/https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand","id":"s4","published":"2026-04-17","publisher":"Epoch AI","title":"OpenAI Stargate: where the US sites stand","type":"analyst","url":"https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand"},{"accessed":"2026-10-09","id":"s5","published":"2026-06-24","publisher":"Wisconsin Public Radio","title":"Oracle sues Wisconsin utility regulators over financial requirements for data centers","type":"news","url":"https://www.wpr.org/news/oracle-sues-wisconsin-utility-regulators-psc-financial-requirements-data-centers"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260708013759/https://ozaukeepress.com/node/113525","id":"s6","published":"2026-07-01","publisher":"Ozaukee Press","title":"Another data center tops out","type":"news","url":"https://ozaukeepress.com/node/113525"},{"accessed":"2026-10-09","id":"s7","published":"2026-09-11","publisher":"FOX 11 News","title":"Companies behind Port Washington data centers meet with neighbors","type":"news","url":"https://fox11online.com/news/state/port-washington-data-center-project-lighthouse-construction-open-house-neighbor-concerns-companies-representatives-vantage-oracle-openai"},{"accessed":"2026-10-09","id":"s8","published":"2026-10-02","publisher":"Wisconsin Watch","title":"We Energies strikes deal to power Oracle data center with nuclear energy","type":"news","url":"https://wisconsinwatch.org/2026/10/wisconsin-we-energies-deal-oracle-data-center-nuclear-energy-power-point-beach-plant/"}],"status":"under_construction","status_as_of":"2026-09-11","status_source_ids":["s6","s7"],"summary":"Vantage Data Centers is building Lighthouse, a four-building campus on 672 acres on Port Washington's north side in Wisconsin, for Oracle and OpenAI under the Stargate program. OpenAI, Oracle and Vantage announced it as a Stargate site in October 2025, with close to 1 GW of capacity and completion targeted for 2028. Vantage now lists 902 MW, while local reporting and analyst Epoch AI cite 1.3 GW. The investment is reported at about $15 billion. Two buildings had topped out by mid-2026. We Energies supplies power; an Oracle subsidiary sued state regulators in June 2026 over financial-security rules, and in October 2026 We Energies proposed an Oracle share of nuclear output, pending approval.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2853444c-d991-5aa9-82a6-31b621178535","s2":"2b179a35-b28d-57c4-86d4-e1ab5a58e8e7","s3":"e48f7aba-8d30-5ea6-a73c-b08b38db13a8","s4":"e84a43f9-994e-55fb-98c0-b8e276a308b9","s5":"9dc519bd-57cf-5d31-815f-1801b51c031f","s6":"8b9534a2-5109-5738-adc5-1f8a62f5c027","s7":"d3e842a9-6621-51fb-b0cf-1c7ad3c01a2a","s8":"3a993ad5-1b04-5754-9adb-eac65e528c2b"},"source_file":"datacenters/projects/oracle-vantage-port-washington.json","source_record_id":"oracle-vantage-port-washington","source_record_sha256":"d9322bd7e03400684eb1de18b401871dbb56eee1f83f17ea7546f26ce30e37c7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3400afe27b31a4168bd0917a9a6248131c913bb69139456f93d0092790bd71d9"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d272a722ca415c1be654/#project-3b636397-fbb2-5564-a352-fa1382a218b5 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3b636397-fbb2-5564-a352-fa1382a218b5.json
3e074273-f5f7-5785-ab10-232a5ebd5c6b | curated:hut8-river-bend-ai-data-center-campus:245mw-critical-it-current-build | vcc-site-1f215e81ecc04c69b5d6 | curated:hut8-river-bend-ai-data-center-campus | Hut 8 River Bend 245 MW Critical IT Current Build | United States | US | 30.7279 | -91.2995 | Point | campus | Match direct campus page to the platform's same title and slug; dereference explicit geolocation fields; reproduce the site's six-decimal marker rounding; emit longitude then latitude. | operator_published_mapbox_campus_marker | operator_published_campus_reference_point | official_source | campus_locator | Exact operator-rendered named campus marker, not a survey, campus boundary, building centroid, construction footprint, or phase-specific location. |  | Publisher reports no bounded horizontal positional accuracy; decimal places and deterministic rounding do not establish site accuracy. | 688470de-c2fd-561a-93c3-5b4b00bcf981 | under_construction | 2026-08-04 | 70 | authoritative_physical_status_update | b89b0c05-a075-5b61-a0d4-2f673c68a1d3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.hut8.com/news-insights/press-releases/hut-8-reports-second-quarter-2026-results | https://www.hut8.com/data-centers/river-bend | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1f215e81ecc04c69b5d6/#project-3e074273-f5f7-5785-ab10-232a5ebd5c6b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3e074273-f5f7-5785-ab10-232a5ebd5c6b.json
3e853975-e7a4-52ba-bc38-6b3d09bfdaf0 | imported:semiconductor-atlas:aws-richmond-county-north-carolina | vcc-site-9b47e002ec40fe02a2d7 | imported:semiconductor-atlas:aws-richmond-county-north-carolina | AWS Richmond County data center campus | United States | US | 35 | -79.76 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | The opened sources name only Richmond County (the announcement was held in Hamlet); coordinates are the county point from its Wikipedia article (Nominatim was unavailable). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 8e2eac72-0b39-5b36-a8bd-abebd98c3c4c | under_construction | 2026-09-23 | 20 | imported_documented_status | bd64cb15-ff33-53ef-935c-18ce4cf570bf | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8e2eac72-0b39-5b36-a8bd-abebd98c3c4c","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-richmond-county-north-carolina"},{"evidence_id":"0ba7bc30-e024-58f4-96d3-dbe3da8693cd","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-richmond-county-north-carolina"},{"evidence_id":"8e2eac72-0b39-5b36-a8bd-abebd98c3c4c","notes":"Commissioners approved an incentive package of annual grants for 20 years linked to property taxes, contingent on job and investment thresholds.","party":"Richmond County","relationship_scope":"unknown","role":"government","source_record_id":"aws-richmond-county-north-carolina"},{"evidence_id":"8031ad5e-8cb0-5489-abeb-8336d647b76c","notes":"Commissioners approved an incentive package of annual grants for 20 years linked to property taxes, contingent on job and investment thresholds.","party":"Richmond County","relationship_scope":"unknown","role":"government","source_record_id":"aws-richmond-county-north-carolina"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.aboutamazon.com/news/aws/amazon-data-centers-locations-news | https://abc11.com/16658676 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AWS Richmond County data center campus as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"aws-richmond-county-north-carolina"},"record":{"aliases":[],"id":"aws-richmond-county-north-carolina","last_reviewed":"2026-10-09","location":{"admin1":"North Carolina","admin2":"Richmond County","country":"US","lat":35.0,"lon":-79.76,"note":"The opened sources name only Richmond County (the announcement was held in Hamlet); coordinates are the county point from its Wikipedia article (Nominatim was unavailable).","precision":"admin2","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2025-06-04","basis":"announced","metric":"investment","qualifier":"approximately","source_ids":["s1","s3"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2025-06-04","basis":"planned","metric":"jobs_permanent","qualifier":"at_least","source_ids":["s1","s3"],"unit":"count","value":500},{"applies_to":"campus","as_of":"2026-07-30","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s4"],"unit":"count","value":21}],"milestones":[{"date":"2025-06-03","event":"other","kind":"actual","note":"Richmond County commissioners approved the incentive package the day before the announcement.","source_ids":["s1","s2"]},{"date":"2025-06-04","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2025-10-17","event":"construction_started","kind":"actual","note":"Date of Amazon's post reporting the groundbreaking.","source_ids":["s4"]}],"name":"AWS Richmond County data center campus","notes":"In a July 2026 update Amazon said it had applied to the North Carolina Division of Air Quality for a permit for the campus backup generators; the application date was not given.","parties":[{"name":"Amazon Web Services","role":"developer","source_ids":["s1","s3"]},{"name":"Richmond County","note":"Commissioners approved an incentive package of annual grants for 20 years linked to property taxes, contingent on job and investment thresholds.","role":"government","source_ids":["s1","s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-06-04","publisher":"ABC11 (The Associated Press)","title":"Amazon planning $10B investment in North Carolina for data center and AI campus","type":"news","url":"https://abc11.com/16658676"},{"accessed":"2026-10-09","id":"s2","published":"2025-06-04","publisher":"WITN (The Associated Press)","title":"Amazon planning $10B investment in North Carolina for data center and AI campus","type":"news","url":"https://www.witn.com/2025/06/04/amazon-planning-10b-investment-north-carolina-data-center-ai-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260831105615/https://www.aboutamazon.com/news/aws/aws-investment-north-carolina-ai-cloud-infrastructure","id":"s3","published":null,"publisher":"Amazon","title":"Amazon plans to invest $10 billion in North Carolina to expand cloud computing infrastructure and advance AI innovation","type":"company","url":"https://www.aboutamazon.com/news/aws/aws-investment-north-carolina-ai-cloud-infrastructure"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Amazon","title":"Amazon data center communities: Here's what's happening near data centers across the US","type":"company","url":"https://www.aboutamazon.com/news/aws/amazon-data-centers-locations-news"}],"status":"under_construction","status_as_of":"2026-09-23","status_source_ids":["s4"],"summary":"Amazon Web Services campus in rural Richmond County, North Carolina, near the South Carolina line. Announced in June 2025 at an estimated $10 billion for cloud and AI infrastructure, with at least 500 jobs. The county approved 20-year cash grants tied to property taxes, contingent on job and investment targets. Amazon broke ground in October 2025, said in July 2026 that the campus would have 21 buildings, and has applied for an air permit for backup generators. County officials said water, wastewater and fiber upgrades would come at no cost to taxpayers.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8e2eac72-0b39-5b36-a8bd-abebd98c3c4c","s2":"8031ad5e-8cb0-5489-abeb-8336d647b76c","s3":"0ba7bc30-e024-58f4-96d3-dbe3da8693cd","s4":"bd64cb15-ff33-53ef-935c-18ce4cf570bf"},"source_file":"datacenters/projects/aws-richmond-county-north-carolina.json","source_record_id":"aws-richmond-county-north-carolina","source_record_sha256":"95811ce2b80c82e38fd95f89c057fbe796eb89e70f4ca39334c33a0ff1cb9e09","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4f97dccd7654b4406aadcab82064d70b4bdefaaea8f45c1f88d456313a5a895f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9b47e002ec40fe02a2d7/#project-3e853975-e7a4-52ba-bc38-6b3d09bfdaf0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3e853975-e7a4-52ba-bc38-6b3d09bfdaf0.json
3f13d78d-ac2f-533b-8e04-01009bd9d17b | imported:semiconductor-atlas:tract-buckeye | vcc-site-7cb4c635a0469cf8e507 | imported:semiconductor-atlas:tract-buckeye | Tract Buckeye data center park | United States | US | 33.3706 | -112.5908 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of Buckeye (s5). Local reporting places the park in southwest Buckeye, south of Interstate 10 on Johnson Road near Buckeye Municipal Airport; the parcel was not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | b46f3107-539f-500d-9ea3-bcc373b6e760 | announced | 2026-06-15 | 120 | imported_documented_status | e188412d-8228-5499-8431-62122baddd79 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"b46f3107-539f-500d-9ea3-bcc373b6e760","notes":"Denver-based master developer of the park, which is meant to host hyperscale and wholesale data center operators.","party":"Tract","relationship_scope":"unknown","role":"developer","source_record_id":"tract-buckeye"},{"evidence_id":"fb6f3e7c-c53d-5d43-8522-378dc9df557c","notes":"Denver-based master developer of the park, which is meant to host hyperscale and wholesale data center operators.","party":"Tract","relationship_scope":"unknown","role":"developer","source_record_id":"tract-buckeye"},{"evidence_id":"2a532c35-28a5-5706-9606-e1d4ccf2c03c","notes":"Denver-based master developer of the park, which is meant to host hyperscale and wholesale data center operators.","party":"Tract","relationship_scope":"unknown","role":"developer","source_record_id":"tract-buckeye"},{"evidence_id":"e188412d-8228-5499-8431-62122baddd79","notes":"Denver-based master developer of the park, which is meant to host hyperscale and wholesale data center operators.","party":"Tract","relationship_scope":"unknown","role":"developer","source_record_id":"tract-buckeye"},{"evidence_id":"b46f3107-539f-500d-9ea3-bcc373b6e760","notes":"Tract said it was working with APS on plans to support up to 1.8 GW; no supply agreement has been reported.","party":"Arizona Public Service","relationship_scope":"unknown","role":"utility","source_record_id":"tract-buckeye"},{"evidence_id":"e188412d-8228-5499-8431-62122baddd79","notes":"Tract said it was working with APS on plans to support up to 1.8 GW; no supply agreement has been reported.","party":"Arizona Public Service","relationship_scope":"unknown","role":"utility","source_record_id":"tract-buckeye"},{"evidence_id":"fb6f3e7c-c53d-5d43-8522-378dc9df557c","notes":"Approved the development agreement, including reimbursement of up to USD 50 million of public infrastructure costs once the project generates USD 60 million for the city.","party":"City of Buckeye","relationship_scope":"unknown","role":"government","source_record_id":"tract-buckeye"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://constructionreviewonline.com/tract-secures-approval-for-20-billion-data-center-in-buckeye/ | https://www.azfamily.com/2024/08/30/developer-wants-power-future-ai-buckeye-with-new-data-center | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Tract Buckeye data center park as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"tract-buckeye"},"record":{"aliases":["Tract Phoenix data center park"],"id":"tract-buckeye","last_reviewed":"2026-10-09","location":{"admin1":"Arizona","country":"US","lat":33.3706,"locality":"Buckeye","lon":-112.5908,"note":"Coordinates are the Wikipedia centroid of Buckeye (s5). Local reporting places the park in southwest Buckeye, south of Interstate 10 on Johnson Road near Buckeye Municipal Airport; the parcel was not geocoded.","precision":"locality","source_ids":["s1","s5"]},"metrics":[{"applies_to":"campus","as_of":"2024-08-29","basis":"planned","metric":"power_capacity","note":"Capacity Tract said it was planning with the local utility; the mayor said securing the power could take about seven years.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s4"],"unit":"MW","value":1800},{"applies_to":"campus","as_of":"2024-08-12","basis":"reported","metric":"investment","note":"Reported total value of the park at full build-out.","qualifier":"approximately","source_ids":["s1","s2"],"unit":"USD","value":20000000000},{"applies_to":"phase","as_of":"2024-08-12","basis":"announced","metric":"investment","note":"Tract's planned spending on water, power and transportation infrastructure for the site; reported separately from the city's development agreement terms.","phase_label":"Tract site infrastructure (water, power, transport)","qualifier":"at_least","source_ids":["s2","s4"],"unit":"USD","value":100000000},{"applies_to":"campus","as_of":"2024-08-31","basis":"reported","metric":"land_area","note":"Other reports round the site to nearly 2,000 or 2,100 acres.","qualifier":"approximately","source_ids":["s3","s4"],"unit":"acres","value":2069},{"applies_to":"campus","as_of":"2024-08-31","basis":"planned","metric":"buildings","qualifier":"up_to","source_ids":["s3","s4"],"unit":"count","value":40},{"applies_to":"campus","as_of":"2024-08-31","basis":"planned","metric":"floor_area","qualifier":"up_to","source_ids":["s1","s3","s4"],"unit":"sq_ft","value":20000000},{"applies_to":"campus","as_of":"2024-08-12","basis":"planned","metric":"jobs_construction","qualifier":"approximately","source_ids":["s2","s4"],"unit":"count","value":2000},{"applies_to":"campus","as_of":"2024-08-12","basis":"planned","metric":"jobs_permanent","note":"Full-time jobs estimated in August 2024 coverage of the council approval; Arizona's Family separately reported about 300 high-paying jobs.","qualifier":"approximately","source_ids":["s2","s4"],"unit":"count","value":500}],"milestones":[{"date":"2024-08-06","event":"zoning_approved","kind":"actual","note":"Buckeye City Council unanimously approved the development agreement with Tract and a major plan amendment creating the Buckeye Tech Corridor.","source_ids":["s2"]},{"date":"2024-08","event":"announced","kind":"actual","source_ids":["s1","s3"]},{"date":"2026","event":"other","kind":"actual","note":"Reported as having entered engineering and horizontal infrastructure preparation as of 2026.","source_ids":["s4"]}],"name":"Tract Buckeye data center park","notes":"The Construction Review article was first published on 8 August 2024 and updated on 15 June 2026; its statement that the park entered engineering and horizontal infrastructure preparation comes from that update, so status_as_of uses the update date. Status stays at announced because no data center building is reported under construction. Whether Tract holds an APS service commitment predating the utility's January 2024 cutoff was not found.","parties":[{"name":"Tract","note":"Denver-based master developer of the park, which is meant to host hyperscale and wholesale data center operators.","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Arizona Public Service","note":"Tract said it was working with APS on plans to support up to 1.8 GW; no supply agreement has been reported.","role":"utility","source_ids":["s1","s4"]},{"name":"City of Buckeye","note":"Approved the development agreement, including reimbursement of up to USD 50 million of public infrastructure costs once the project generates USD 60 million for the city.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"APS service planned; Tract said it was working with the utility on infrastructure for up to 1.8 GW. In September 2026 APS said it had made no commitments to serve additional data centers since January 2024 because of grid constraints; the article does not mention this park.","source_ids":["s1","s4","s6"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250723193452/https://www.azfamily.com/2024/08/30/developer-wants-power-future-ai-buckeye-with-new-data-center/","id":"s1","published":"2024-08-29","publisher":"Arizona's Family (KTVK/KPHO)","title":"Developer wants to power the future of AI in Buckeye with new data center","type":"news","url":"https://www.azfamily.com/2024/08/30/developer-wants-power-future-ai-buckeye-with-new-data-center"},{"accessed":"2026-10-09","id":"s2","published":"2024-08-12","publisher":"KTAR News (Phoenix Business Journal)","title":"$20 billion data center campus gets green light in Buckeye","type":"news","url":"https://ktar.com/arizona-news/20-billion-data-center-campus-gets-green-light-in-buckeye"},{"accessed":"2026-10-09","id":"s3","published":"2024-08-31","publisher":"Baxtel","title":"Tract announces new gigawatt-scale data center park in Phoenix, Arizona","type":"trade_press","url":"https://baxtel.com/news/tract-announces-new-gigawatt-scale-data-center-park-in-phoenix-arizona"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260612044401/https://constructionreviewonline.com/tract-secures-approval-for-20-billion-data-center-in-buckeye/","id":"s4","published":"2024-08-08","publisher":"Construction Review Online","title":"$20bn Tract Data Center Park in Buckeye Advances to Horizontal Infrastructure Preparation Phase","type":"trade_press","url":"https://constructionreviewonline.com/tract-secures-approval-for-20-billion-data-center-in-buckeye/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Buckeye, Arizona","type":"other","url":"https://en.wikipedia.org/wiki/Buckeye,_Arizona"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260904052909/https://www.kjzz.org/business/2026-09-02/aps-says-it-cant-commit-to-new-data-centers-because-of-electric-grid-constraints","id":"s6","published":"2026-09-02","publisher":"KJZZ","title":"APS says it can't commit to new data centers because of electric grid constraints","type":"news","url":"https://www.kjzz.org/business/2026-09-02/aps-says-it-cant-commit-to-new-data-centers-because-of-electric-grid-constraints"}],"status":"announced","status_as_of":"2026-06-15","status_source_ids":["s4"],"summary":"Master-planned data center park by land developer Tract on about 2,069 acres in southwest Buckeye, Arizona, south of Interstate 10 on Johnson Road near the municipal airport, on land once planned for a large housing community. Announced in August 2024 after the city council unanimously approved a development agreement and a Buckeye Tech Corridor plan amendment, it could hold up to 40 data centers and 20 million square feet, with Tract working with APS on plans for up to 1.8 GW. The project is valued at about USD 20 billion over a phased 15-year build-out. A June 2026 trade update said it had entered engineering and horizontal infrastructure preparation.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"b46f3107-539f-500d-9ea3-bcc373b6e760","s2":"fb6f3e7c-c53d-5d43-8522-378dc9df557c","s3":"2a532c35-28a5-5706-9606-e1d4ccf2c03c","s4":"e188412d-8228-5499-8431-62122baddd79","s5":"d0baaa06-e1be-5d2a-9e8f-b5ce1a0dfe29","s6":"96407f83-74f1-5031-a7a2-65caac905561"},"source_file":"datacenters/projects/tract-buckeye.json","source_record_id":"tract-buckeye","source_record_sha256":"310f1982a3fe50db0f439de7a123a0ed3dbd700b5d8471ba9b368d8d683560ee","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"15e7b23a4a095d2af1ec74da847cb844a14e1a0650280be7632a36cc14fbd191"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7cb4c635a0469cf8e507/#project-3f13d78d-ac2f-533b-8e04-01009bd9d17b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3f13d78d-ac2f-533b-8e04-01009bd9d17b.json
3fc18374-cbc2-5a11-9356-ab751ac3820c | imported:semiconductor-atlas:terranova-praia-grande | vcc-site-3a91e1c2ee3ef8dbd116 | imported:semiconductor-atlas:terranova-praia-grande | Terranova Praia Grande data center campus (proposed) | Brazil | BR | -24.0061 | -46.4028 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name the city of Praia Grande and say the site is near its submarine cable landing point, without an address. The point is the city coordinate from the Praia Grande Wikipedia article. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f170ffcd-17b7-5b11-99ba-f4f8a5d74ea8 | proposed | 2026-08-25 | 49 | imported_documented_status | dc52b8e4-d5d4-5456-9f53-3706a89c716d | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f170ffcd-17b7-5b11-99ba-f4f8a5d74ea8","notes":"Hyperscale data center platform backed by the investment fund Actis.","party":"Terranova","relationship_scope":"unknown","role":"developer","source_record_id":"terranova-praia-grande"},{"evidence_id":"dc52b8e4-d5d4-5456-9f53-3706a89c716d","notes":"Hyperscale data center platform backed by the investment fund Actis.","party":"Terranova","relationship_scope":"unknown","role":"developer","source_record_id":"terranova-praia-grande"},{"evidence_id":"f170ffcd-17b7-5b11-99ba-f4f8a5d74ea8","notes":"Fund backing Terranova.","party":"Actis","relationship_scope":"unknown","role":"investor","source_record_id":"terranova-praia-grande"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://constructionreviewonline.com/terranova-breaks-ground-on-216-mw-data-centre-in-campinas-sao-paulo/ | https://teletime.com.br/19/02/2026/terranova-tera-megaestruturas-e-estuda-expansao-de-data-centers-no-brasil/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Terranova Praia Grande data center campus (proposed) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"terranova-praia-grande"},"record":{"aliases":[],"id":"terranova-praia-grande","last_reviewed":"2026-10-09","location":{"admin1":"São Paulo","country":"BR","lat":-24.00611,"locality":"Praia Grande","lon":-46.40278,"note":"Sources name the city of Praia Grande and say the site is near its submarine cable landing point, without an address. The point is the city coordinate from the Praia Grande Wikipedia article.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-25","basis":"planned","metric":"power_capacity","note":"Grid access requested from the Operador Nacional do Sistema Elétrico (ONS); no approval had been reported in the sources.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":450},{"applies_to":"phase","as_of":"2026-02-19","basis":"planned","metric":"power_capacity","note":"Rough estimate given by Terranova's chief executive; later phases were said to be possible given the size of the land.","phase_label":"First phase (if ONS approves)","power_scope":"it_load","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":350},{"applies_to":"campus","as_of":"2026-02-19","basis":"reported","metric":"land_area","note":"Reported as about one million square metres, held under a land-control contract; the purchase depends on ONS approving the grid request.","qualifier":"approximately","source_ids":["s1","s2"],"unit":"hectares","value":100}],"milestones":[{"date":"2026-02","event":"other","kind":"actual","note":"Terranova disclosed the project, its land-control contract and its 450 MW request to ONS, and said it expected an ONS answer by early May 2026.","source_ids":["s1"]}],"name":"Terranova Praia Grande data center campus (proposed)","notes":"Only trade press covers this site; the August 2026 Construction Review article relays the February 2026 Teletime interview, so the two are not fully independent. Completion of the land purchase depends on ONS approving the 450 MW request; no source gives a date for it, and no ONS decision had been reported. Terranova's company-wide plan of about USD 1.5 billion over Brazil, Mexico and Chile is not a figure for this site. City coordinates come from Wikipedia (s3), used only for the map point. Terranova's Campinas campus is a separate record (terranova-campinas).","parties":[{"name":"Terranova","note":"Hyperscale data center platform backed by the investment fund Actis.","role":"developer","source_ids":["s1","s2"]},{"name":"Actis","note":"Fund backing Terranova.","role":"investor","source_ids":["s1"]}],"power_sources":[{"description":"Terranova requested 450 MW of access to the national grid from ONS.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-02-19","publisher":"TELETIME","title":"Terranova terá megaestruturas e estuda expansão de data centers no Brasil","type":"trade_press","url":"https://teletime.com.br/19/02/2026/terranova-tera-megaestruturas-e-estuda-expansao-de-data-centers-no-brasil/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260831101009/https://constructionreviewonline.com/terranova-breaks-ground-on-216-mw-data-centre-in-campinas-sao-paulo/","id":"s2","published":"2026-08-25","publisher":"Construction Review Online","title":"Terranova breaks ground on 216 MW data centre in Campinas, São Paulo","type":"trade_press","url":"https://constructionreviewonline.com/terranova-breaks-ground-on-216-mw-data-centre-in-campinas-sao-paulo/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007040332/https://en.wikipedia.org/wiki/Praia_Grande","id":"s3","published":null,"publisher":"Wikipedia","title":"Praia Grande","type":"other","url":"https://en.wikipedia.org/wiki/Praia_Grande"}],"status":"proposed","status_as_of":"2026-08-25","status_source_ids":["s2"],"summary":"Terranova, an Actis-backed Latin American hyperscale data center platform, has proposed a campus on a site of about one million square metres in Praia Grande on the São Paulo coast, close to the city's submarine cable landing point. It holds a land-control contract and has asked Brazil's grid operator ONS for 450 MW of grid access; the land purchase will close only if ONS approves. In February 2026 Terranova's chief executive estimated a first phase of roughly 350 MW of IT capacity. No investment figure or construction timeline has been disclosed, and an August 2026 report still described the purchase as awaiting ONS approval.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f170ffcd-17b7-5b11-99ba-f4f8a5d74ea8","s2":"dc52b8e4-d5d4-5456-9f53-3706a89c716d","s3":"10ba1957-5dd6-5ad0-aad7-d2437baa1e5e"},"source_file":"datacenters/projects/terranova-praia-grande.json","source_record_id":"terranova-praia-grande","source_record_sha256":"5c9ae8c619cac9aebd8c46a9f663565f736bbff88406ff9954317ab8129db32a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4a49ba855a28609628c4924f281da0039fc3288570f7a04d68137b93b0256be5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3a91e1c2ee3ef8dbd116/#project-3fc18374-cbc2-5a11-9356-ab751ac3820c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3fc18374-cbc2-5a11-9356-ab751ac3820c.json
3fe8297a-147b-56fe-a5a6-6ae165798506 | imported:semiconductor-atlas:airtrunk-tok1-inzai | vcc-site-d3117bafca6bdcc5007e | imported:semiconductor-atlas:airtrunk-tok1-inzai | AirTrunk TOK1 Tokyo East | Japan | JP | 35.8323 | 140.1453 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | AirTrunk's TOK1 page places the campus in Inzai's data center hub without an address; coordinates are the OpenStreetMap Nominatim centroid of Inzai City. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 4e36cb9c-336f-526e-bf8a-2fadaa356951 | partially_operational | 2026-03-10 | 217 | imported_documented_status | 4e36cb9c-336f-526e-bf8a-2fadaa356951 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"4e36cb9c-336f-526e-bf8a-2fadaa356951","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-tok1-inzai"},{"evidence_id":"b9680dc4-43e8-590a-947f-77574a2c9c27","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-tok1-inzai"},{"evidence_id":"3144acd5-1519-555c-941d-ba0e49895219","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-tok1-inzai"},{"evidence_id":"1c3bcbbc-7232-5a74-a3c0-c9c32a460a20","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-tok1-inzai"},{"evidence_id":"4e36cb9c-336f-526e-bf8a-2fadaa356951","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"operator","source_record_id":"airtrunk-tok1-inzai"},{"evidence_id":"1c3bcbbc-7232-5a74-a3c0-c9c32a460a20","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"operator","source_record_id":"airtrunk-tok1-inzai"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | AirTrunk |  |  |  | https://airtrunk.com/data-centres/tok1/ | https://airtrunk.com/data-centres/tok1/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AirTrunk TOK1 Tokyo East as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"airtrunk-tok1-inzai"},"record":{"aliases":["TOK1"],"id":"airtrunk-tok1-inzai","last_reviewed":"2026-10-09","location":{"admin1":"Chiba Prefecture","country":"JP","lat":35.8323,"locality":"Inzai","lon":140.1453,"note":"AirTrunk's TOK1 page places the campus in Inzai's data center hub without an address; coordinates are the OpenStreetMap Nominatim centroid of Inzai City.","precision":"locality","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-10","basis":"planned","metric":"power_capacity","note":"AirTrunk calls this total campus capacity without saying whether it is IT load.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2024-08-14","basis":"under_construction","metric":"power_capacity","note":"Topping out expected in August 2024.","phase_label":"Phase 3","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":50},{"applies_to":"phase","as_of":"2025-06-19","basis":"under_construction","metric":"power_capacity","phase_label":"Phase begun June 2025","power_scope":"unspecified","qualifier":"more_than","source_ids":["s3"],"unit":"MW","value":40},{"applies_to":"phase","as_of":"2026-03-10","basis":"under_construction","metric":"power_capacity","note":"May overlap with the phase that broke ground in June 2025; AirTrunk does not reconcile the two figures.","phase_label":"Next phases under construction in 2026","power_scope":"it_load","qualifier":"more_than","source_ids":["s4"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2026-10","basis":"reported","metric":"land_area","note":"Undated facility page viewed October 2026.","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":13},{"applies_to":"campus","as_of":"2026-10","basis":"planned","metric":"floor_area","note":"Data hall area across 102 data halls, per the undated facility page; excludes 9,600 square meters of office and storage space.","qualifier":"exact","source_ids":["s1"],"unit":"sq_m","value":80000}],"milestones":[{"date":"2024-08","event":"other","kind":"actual","note":"Phase 3 (50 MW) reported on schedule and topping out.","source_ids":["s2"]},{"date":"2025-06","event":"other","kind":"actual","note":"Groundbreaking on a 40 MW-plus phase announced 19 June 2025; earlier phases had already been built, so this is not the campus construction start.","source_ids":["s3"]},{"date":"2026-03-10","event":"other","kind":"actual","note":"JPY 191.6 billion (about US$1.24 billion) green loan closed to refinance existing TOK1 facilities and fund development of the next phases.","source_ids":["s4"]}],"name":"AirTrunk TOK1 Tokyo East","parties":[{"name":"AirTrunk","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"AirTrunk","role":"operator","source_ids":["s1","s4"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"AirTrunk","title":"TOK1 Tokyo East","type":"company","url":"https://airtrunk.com/data-centres/tok1/"},{"accessed":"2026-10-09","id":"s2","published":"2024-08-14","publisher":"AirTrunk","title":"AirTrunk TOK1 Phase 3 progressing at speed","type":"company","url":"https://airtrunk.com/airtrunk-tok1-phase-3-progressing-at-speed/"},{"accessed":"2026-10-09","id":"s3","published":"2025-06-19","publisher":"AirTrunk","title":"AirTrunk breaks ground on 40+MW phase of TOK1, Japan's largest hyperscale data centre campus.","type":"company","url":"https://airtrunk.com/airtrunk-breaks-ground-on-40mw-phase-of-tok1-japans-largest-hyperscale-data-centre-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260420024816/https://airtrunk.com/airtrunk-secures-largest-financing-for-a-data-centre-in-japan-with-us1-2-billion-green-loan-for-its-flagship-tokyo-campus/","id":"s4","published":"2026-03-10","publisher":"AirTrunk","title":"AirTrunk secures largest financing for a data centre in Japan with US$1.2 billion green loan","type":"company","url":"https://airtrunk.com/airtrunk-secures-largest-financing-for-a-data-centre-in-japan-with-us1-2-billion-green-loan-for-its-flagship-tokyo-campus/"}],"status":"partially_operational","status_as_of":"2026-03-10","status_source_ids":["s1","s4"],"summary":"TOK1 is AirTrunk's flagship hyperscale campus in the Inzai data center hub east of Tokyo, which AirTrunk bills as the biggest hyperscale campus in Japan measured in megawatts. The 13-hectare campus is scalable to more than 300 MW and already has facilities in service. In August 2024 AirTrunk said a 50 MW third phase was on schedule and topping out; it broke ground on a further 40 MW-plus phase in June 2025, and in March 2026 said it had recently begun building over 100 MW of additional IT load. That month it closed a JPY 191.6 billion green loan to refinance existing TOK1 facilities and fund the next phases.","workloads":["cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"4e36cb9c-336f-526e-bf8a-2fadaa356951","s2":"b9680dc4-43e8-590a-947f-77574a2c9c27","s3":"3144acd5-1519-555c-941d-ba0e49895219","s4":"1c3bcbbc-7232-5a74-a3c0-c9c32a460a20"},"source_file":"datacenters/projects/airtrunk-tok1-inzai.json","source_record_id":"airtrunk-tok1-inzai","source_record_sha256":"4c28605b649ccf51780503b5829856089f31072a900b71c243bb8f4e88762814","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"34d989830b304f3052a15d3c5eacb4540ee9112e50b3d3dbdca7af3d32398cc8"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d3117bafca6bdcc5007e/#project-3fe8297a-147b-56fe-a5a6-6ae165798506 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/3fe8297a-147b-56fe-a5a6-6ae165798506.json
409466ac-1b48-5098-adf6-4f3a2999b5f6 | imported:semiconductor-atlas:qts-eemshaven | vcc-site-5c6aac8d35554558a1fc | imported:semiconductor-atlas:qts-eemshaven | QTS Eemshaven data center campus | Netherlands | NL | 53.4375 | 6.8581 | Point | project | imported_reference_point | imported_reference_point | site | compiled_reference | project_locator | Point for the 'QTS Eemshaven Netherlands Data Center' building (OSM way 455499803, Huibertgatweg) from the local OpenStreetMap layer, matching the address on QTS's campus page. The layer also maps a QTS new build about 350 m to the north-west; the full 18-hectare campus boundary is not published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 404031a4-7ade-5c05-9e6c-4e2242a6d4d2 | partially_operational | 2026-10-09 | 4 | imported_documented_status | 404031a4-7ade-5c05-9e6c-4e2242a6d4d2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"84015ac2-f54c-51de-bdf6-1337c7e172ce","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-eemshaven"},{"evidence_id":"a9ac8986-169c-51e9-b547-357e430b32bf","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-eemshaven"},{"evidence_id":"404031a4-7ade-5c05-9e6c-4e2242a6d4d2","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-eemshaven"},{"evidence_id":"84015ac2-f54c-51de-bdf6-1337c7e172ce","notes":"Acquired the Eemshaven and Groningen facilities from TCN SIG Telehousing in 2019.","party":"QTS Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"qts-eemshaven"},{"evidence_id":"a9ac8986-169c-51e9-b547-357e430b32bf","notes":"Described as backing QTS; Blackstone-managed funds own QTS rather than this site directly.","party":"Blackstone (managed funds)","relationship_scope":"unknown","role":"investor","source_record_id":"qts-eemshaven"},{"evidence_id":"84015ac2-f54c-51de-bdf6-1337c7e172ce","notes":"Provided on-site operations, maintenance and customer support under a partnership announced in 2019; its current role was not checked.","party":"Zentrys Group","relationship_scope":"unknown","role":"operator","source_record_id":"qts-eemshaven"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | QTS Data Centers | Zentrys Group |  |  |  | https://www.q.com/data-centers/netherlands-eemshaven | https://www.q.com/data-centers/netherlands-eemshaven | [{"identity_decision":{"decision":"unique_site","flags":["source_site_point_not_surveyed_boundary"],"rationale":"No matching named development in the 201-project release. Preserve QTS Eemshaven data center campus as an independent source record; its site locator does not itself establish a surveyed physical site.","source_record_id":"qts-eemshaven"},"record":{"aliases":["QTS Eemshaven","EEMSDC1"],"id":"qts-eemshaven","last_reviewed":"2026-10-09","location":{"admin1":"Groningen","country":"NL","lat":53.437501,"locality":"Eemshaven","lon":6.858112,"note":"Point for the 'QTS Eemshaven Netherlands Data Center' building (OSM way 455499803, Huibertgatweg) from the local OpenStreetMap layer, matching the address on QTS's campus page. The layer also maps a QTS new build about 350 m to the north-west; the full 18-hectare campus boundary is not published.","precision":"site","source_ids":["s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"QTS describes this as planned gross renewable capacity delivered in phases; the undated campus page was read on 2026-10-09.","power_scope":"unspecified","qualifier":"exact","source_ids":["s5"],"unit":"MW","value":200},{"applies_to":"phase","as_of":"2019-04-29","basis":"operational","metric":"power_capacity","note":"Built-out capacity of about 20 gross MW in the building QTS bought, which was vacant at the time.","phase_label":"Existing building at 2019 acquisition","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":20},{"applies_to":"phase","as_of":"2025-07-14","basis":"reported","metric":"investment","note":"The Tech Capital also gives USD 1.5 billion as the equivalent.","phase_label":"Expansion reported in July 2025","qualifier":"exact","source_ids":["s2"],"unit":"EUR","value":1400000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"land_area","note":"Development scope including associated works and structures.","qualifier":"up_to","source_ids":["s5"],"unit":"hectares","value":18},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s5"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_construction","note":"Peak construction workforce.","qualifier":"more_than","source_ids":["s5"],"unit":"count","value":1400},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_permanent","qualifier":"more_than","source_ids":["s5"],"unit":"count","value":300}],"milestones":[{"date":"2019-04-23","event":"site_acquired","kind":"actual","note":"QTS closed the purchase of the Eemshaven and Groningen data centers for about USD 44 million including closing costs.","source_ids":["s1"]},{"date":"2025-03","event":"other","kind":"actual","note":"Groningen Seaports' March 2025 newsletter listed construction of a new QTS data center among port projects.","source_ids":["s4"]},{"date":"2025-07","event":"expansion_announced","kind":"actual","note":"EUR 1.4 billion expansion reported; Structure Research cited local media saying a second data center was under construction.","source_ids":["s2","s3"]}],"name":"QTS Eemshaven data center campus","notes":"Status, the 200 MW, 18-hectare and three-building figures and job counts come from QTS's undated campus page, so status_as_of is the access date. The EUR 1.4 billion figure comes from the visible lede of a paywalled Tech Capital article; Dutch press coverage of the expansion (including a 2029 timeline and the name EEMSDC2) could not be opened, so it is not recorded. QTS's 2019 release said the site neighbours a 500+ MW campus of a hyperscale cloud provider. The campus page also mentions a partnership with WarmteStad to share residual heat from QTS's Netherlands data centers, without saying it covers Eemshaven.","parties":[{"name":"QTS Data Centers","role":"developer","source_ids":["s1","s2","s5"]},{"name":"QTS Data Centers","note":"Acquired the Eemshaven and Groningen facilities from TCN SIG Telehousing in 2019.","role":"owner","source_ids":["s1"]},{"name":"Blackstone (managed funds)","note":"Described as backing QTS; Blackstone-managed funds own QTS rather than this site directly.","role":"investor","source_ids":["s2"]},{"name":"Zentrys Group","note":"Provided on-site operations, maintenance and customer support under a partnership announced in 2019; its current role was not checked.","role":"operator","source_ids":["s1"]}],"power_sources":[{"description":"On-site substation; QTS says renewable-sourced power is available.","source_ids":["s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2019-04-29","publisher":"QTS Data Centers","title":"QTS Expands International Platform with the Strategic Acquisition of Two Data Centers in the Netherlands","type":"company","url":"https://q.com/news/qts-expands-international-platform-with-the-strategic-acquisition-of-two-data-centers-in-the-netherlands/"},{"accessed":"2026-10-09","id":"s2","published":"2025-07-14","publisher":"The Tech Capital","title":"QTS Data Centers invests $1.5 billion in Dutch hyperscale expansion","type":"trade_press","url":"https://thetechcapital.com/qts-data-centers-invests-1-5-billion-in-dutch-hyperscale-expansion/"},{"accessed":"2026-10-09","id":"s3","published":"2025-07-24","publisher":"Structure Research","title":"QTS doubling down in northern Netherlands","type":"trade_press","url":"https://www.structureresearch.net/?p=100674"},{"accessed":"2026-10-09","id":"s4","published":"2025-03","publisher":"Groningen Seaports","title":"Ommelander advertorial Groningen Seaports, maart 2025","type":"other","url":"https://www.groningen-seaports.com/wp-content/uploads/Website_Ommelander_ADV_GSP_maart2025.pdf"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"QTS Data Centers","title":"Eemshaven, Netherlands data center","type":"company","url":"https://www.q.com/data-centers/netherlands-eemshaven"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s5"],"summary":"Data center campus of Blackstone-backed QTS Data Centers at Huibertgatweg 2 in the Eemshaven port area of Groningen, the Netherlands. QTS bought the existing, then vacant 20 gross MW building in 2019 and in July 2025 was reported to be investing EUR 1.4 billion to expand the campus and double its regional capacity. QTS's campus page now describes up to 18 hectares, three facilities and 200 MW of planned capacity delivered in phases: the first building is operational, the second is in phased delivery and the third is under construction.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"84015ac2-f54c-51de-bdf6-1337c7e172ce","s2":"a9ac8986-169c-51e9-b547-357e430b32bf","s3":"ce1dfd51-688b-5e22-b114-547a4fa89cc7","s4":"a8a60c38-8e76-5982-86fe-2e3f48740aa0","s5":"404031a4-7ade-5c05-9e6c-4e2242a6d4d2"},"source_file":"datacenters/projects/qts-eemshaven.json","source_record_id":"qts-eemshaven","source_record_sha256":"087dd58de5c17ce4a5bcc09c10bb2477785591fbf6d475652d92f008b9685806","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"f1d272439a5b52de9b22758b3ece07e46367cfcdecd71345eb352a00a3887354"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5c6aac8d35554558a1fc/#project-409466ac-1b48-5098-adf6-4f3a2999b5f6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/409466ac-1b48-5098-adf6-4f3a2999b5f6.json
40a718e2-038a-5edf-a495-ba05e3f76560 | imported:semiconductor-atlas:igoudar-dakhla | vcc-site-1057cda1149b646f7a24 | imported:semiconductor-atlas:igoudar-dakhla | Igoudar Dakhla green data centre complex | Western Sahara | EH | 23.7081 | -15.9456 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City coordinates from the Dakhla Wikipedia page; no site within Dakhla has been named. Dakhla is in Western Sahara (ISO code EH), a disputed territory administered by Morocco; the sources present the project as a Moroccan national programme. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 56fcfb3f-baa2-5c37-ad58-6c959485a7cb | announced | 2026-04-16 | 180 | imported_documented_status | e60b27a7-7822-5204-bebf-8cdba2469bfa | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e60b27a7-7822-5204-bebf-8cdba2469bfa","notes":"Signatory to the April 2026 agreement launching the studies.","party":"Moroccan Ministry of Digital Transition and Administration Reform","relationship_scope":"unknown","role":"government","source_record_id":"igoudar-dakhla"},{"evidence_id":"e60b27a7-7822-5204-bebf-8cdba2469bfa","notes":"Signatory to the April 2026 agreement launching the studies.","party":"Moroccan Ministry of Energy Transition and Sustainable Development","relationship_scope":"unknown","role":"government","source_record_id":"igoudar-dakhla"},{"evidence_id":"e60b27a7-7822-5204-bebf-8cdba2469bfa","notes":"Signatory to the April 2026 agreement launching the studies.","party":"Wilaya of Dakhla-Oued Ed-Dahab","relationship_scope":"unknown","role":"government","source_record_id":"igoudar-dakhla"},{"evidence_id":"e60b27a7-7822-5204-bebf-8cdba2469bfa","notes":"Signatory to the April 2026 agreement launching the studies.","party":"Regional Council of Dakhla-Oued Ed-Dahab","relationship_scope":"unknown","role":"government","source_record_id":"igoudar-dakhla"},{"evidence_id":"e60b27a7-7822-5204-bebf-8cdba2469bfa","notes":"State investment fund; signatory to the April 2026 studies agreement. No investment commitment is reported.","party":"Mohammed VI Investment Fund","relationship_scope":"unknown","role":"government","source_record_id":"igoudar-dakhla"},{"evidence_id":"e60b27a7-7822-5204-bebf-8cdba2469bfa","notes":"Public financial institution; signatory to the April 2026 studies agreement. No investment commitment is reported.","party":"Caisse de Dépôt et de Gestion (CDG)","relationship_scope":"unknown","role":"government","source_record_id":"igoudar-dakhla"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.fnh.ma/article/actualites-marocaines/datacenters-verts-dakhla-igoudar-numerique | https://w.media/morocco-plans-500-mw-green-data-center-in-dakhla/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Igoudar Dakhla green data centre complex as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"igoudar-dakhla"},"record":{"aliases":["Igoudar Numérique","Igoudar Dakhla"],"id":"igoudar-dakhla","last_reviewed":"2026-10-09","location":{"admin1":"Dakhla-Oued Ed-Dahab","country":"EH","lat":23.70806,"locality":"Dakhla","lon":-15.94556,"note":"City coordinates from the Dakhla Wikipedia page; no site within Dakhla has been named. Dakhla is in Western Sahara (ISO code EH), a disputed territory administered by Morocco; the sources present the project as a Moroccan national programme.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-09","basis":"planned","metric":"power_capacity","note":"Target capacity of the complex; the scope is not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":500}],"milestones":[{"date":"2025-11","event":"announced","kind":"actual","note":"Plans unveiled, with an agreement on the Igoudar programme signed in Dakhla that month; an earlier accord linking digital and energy strategies dates from July 2025.","source_ids":["s1","s2"]},{"date":"2026-04","event":"other","kind":"actual","note":"Agreement, reported on 16 April 2026 without a signing date, launching the strategic studies on governance, economic model, phasing and financing.","source_ids":["s2"]}],"name":"Igoudar Dakhla green data centre complex","notes":"Still at the study stage: the April 2026 agreement launched the studies that precede any investment decision. A September 2026 article still described the campus as targeting 500 MW with no schedule. Coverage uses both the names Igoudar Dakhla and Igoudar Numérique for the programme.","parties":[{"name":"Moroccan Ministry of Digital Transition and Administration Reform","note":"Signatory to the April 2026 agreement launching the studies.","role":"government","source_ids":["s2"]},{"name":"Moroccan Ministry of Energy Transition and Sustainable Development","note":"Signatory to the April 2026 agreement launching the studies.","role":"government","source_ids":["s2"]},{"name":"Wilaya of Dakhla-Oued Ed-Dahab","note":"Signatory to the April 2026 agreement launching the studies.","role":"government","source_ids":["s2"]},{"name":"Regional Council of Dakhla-Oued Ed-Dahab","note":"Signatory to the April 2026 agreement launching the studies.","role":"government","source_ids":["s2"]},{"name":"Mohammed VI Investment Fund","note":"State investment fund; signatory to the April 2026 studies agreement. No investment commitment is reported.","role":"government","source_ids":["s2"]},{"name":"Caisse de Dépôt et de Gestion (CDG)","note":"Public financial institution; signatory to the April 2026 studies agreement. No investment commitment is reported.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"Planned to run fully on green power from a dedicated solar and wind farm.","source_ids":["s1"],"type":"solar"},{"description":"Planned to run fully on green power from a dedicated solar and wind farm.","source_ids":["s1"],"type":"wind"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-24","publisher":"W.Media","title":"Morocco plans 500 MW green data center in Dakhla","type":"trade_press","url":"https://w.media/morocco-plans-500-mw-green-data-center-in-dakhla/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260418141606/https://fnh.ma/article/actualites-marocaines/datacenters-verts-dakhla-igoudar-numerique","id":"s2","published":"2026-04-16","publisher":"Finances News Hebdo","title":"Datacenters verts à Dakhla : le Maroc lance le campus « Igoudar Numérique » de 500 MW","type":"news","url":"https://www.fnh.ma/article/actualites-marocaines/datacenters-verts-dakhla-igoudar-numerique"},{"accessed":"2026-10-09","id":"s3","published":"2026-09","publisher":"The North Africa Post","title":"Morocco's Data Center Boom Raises a Power Question","type":"news","url":"https://northafricapost.com/?p=99949"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261009194514/https://en.wikipedia.org/wiki/Dakhla,_Western_Sahara","id":"s4","published":null,"publisher":"Wikipedia","title":"Dakhla, Western Sahara","type":"other","url":"https://en.wikipedia.org/wiki/Dakhla,_Western_Sahara"}],"status":"announced","status_as_of":"2026-04-16","status_source_ids":["s2"],"summary":"State-led programme for a green data centre complex in Dakhla targeting 500 MW, unveiled by Morocco in November 2025 for AI and high-performance computing, to be powered by a dedicated solar and wind farm. In April 2026 two ministries, the Dakhla-Oued Ed-Dahab wilaya and regional council, the Mohammed VI Investment Fund and CDG signed an agreement launching the strategic studies that are to set its governance, economic model, phasing and financing. It is planned in two parts, a sovereign segment for national needs and a segment open to private investors. The sources give no investment figure, operator or schedule.","workloads":["ai_unspecified","hpc","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"56fcfb3f-baa2-5c37-ad58-6c959485a7cb","s2":"e60b27a7-7822-5204-bebf-8cdba2469bfa","s3":"1a835559-f037-5b0a-a38e-3b9ed4315099","s4":"d46df9c1-76f9-53d2-ab70-54c5c8e2af45"},"source_file":"datacenters/projects/igoudar-dakhla.json","source_record_id":"igoudar-dakhla","source_record_sha256":"ecc303cf1bc6f0b2f56d8961bee667f83a9912a2a4f1b0a7c40a40887109dfcd","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"bc97c6d07929d1c6b16a281fe06098aa913af9173a42a3ce229d35c03fc7a2fe"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1057cda1149b646f7a24/#project-40a718e2-038a-5edf-a495-ba05e3f76560 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/40a718e2-038a-5edf-a495-ba05e3f76560.json
40abc164-3033-5172-b386-52422d1513b9 | imported:semiconductor-atlas:core-scientific-hunt-county | vcc-site-684f1565a0f48756e238 | imported:semiconductor-atlas:core-scientific-hunt-county | Core Scientific Hunt County data center site | United States | US | 33.12 | -96.09 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Core Scientific names Hunt County only. Coordinates are the Hunt County point from its Wikipedia article, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2fce484d-a8d3-5fb3-be18-3cb4c685c302 | announced | 2026-07-28 | 77 | imported_documented_status | 54345127-0df1-562a-8e87-54a1b61041b7 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2fce484d-a8d3-5fb3-be18-3cb4c685c302","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-hunt-county"},{"evidence_id":"54345127-0df1-562a-8e87-54a1b61041b7","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-hunt-county"},{"evidence_id":"54345127-0df1-562a-8e87-54a1b61041b7","notes":"Completed the land acquisition in 2026.","party":"Core Scientific","relationship_scope":"unknown","role":"owner","source_record_id":"core-scientific-hunt-county"},{"evidence_id":"1d9f465e-6826-5ca7-8f71-903dc85cf877","notes":"Named for this site only in Core Scientific's Q2 2026 earnings presentation (s3), which lists Hunt County as an AMD direct site with about 110 MW leased. The Q2 release (s4) gives the 15-year term for about 530 MW across five sites without naming them.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-hunt-county"},{"evidence_id":"07efc002-2951-51bc-bae2-76b8e0f7c949","notes":"Named for this site only in Core Scientific's Q2 2026 earnings presentation (s3), which lists Hunt County as an AMD direct site with about 110 MW leased. The Q2 release (s4) gives the 15-year term for about 530 MW across five sites without naming them.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-hunt-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Core Scientific |  |  | AMD |  | https://www.sec.gov/Archives/edgar/data/0001839341/000183934126000014/core-20260630.htm | https://investors.corescientific.com/news-events/press-releases/detail/136/core-scientific-announces-first-quarter-fiscal-year-2026-results | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Core Scientific Hunt County data center site as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"core-scientific-hunt-county"},"record":{"aliases":["Hunt County, TX campus"],"id":"core-scientific-hunt-county","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Hunt County","country":"US","lat":33.12,"lon":-96.09,"note":"Core Scientific names Hunt County only. Coordinates are the Hunt County point from its Wikipedia article, not the site.","precision":"admin2","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-28","basis":"planned","metric":"power_capacity","note":"Gross utility power capacity that the related electric service agreement is expected to support, per the 10-Q; the Q1 release cites an approved ERCOT interconnection ramp schedule.","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s1","s2"],"unit":"MW","value":430},{"applies_to":"phase","as_of":"2026-07-28","basis":"contracted","metric":"power_capacity","note":"Leased capacity; the presentation does not say whether this is critical IT load. It also lists about 192 MW of further power pipeline at the site.","phase_label":"AMD lease","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":110},{"applies_to":"campus","as_of":"2026-07-28","basis":"reported","metric":"investment","note":"Aggregate purchase price for the land and development rights, most of it allocated to development rights; not a construction budget.","qualifier":"approximately","source_ids":["s2"],"unit":"USD","value":233000000}],"milestones":[{"date":"2026-05-05","event":"site_acquired","kind":"actual","note":"The 10-Q dates completion of the land acquisition, with a related electric service agreement, to 5 May 2026; the Q1 release the next day reported the purchase of land and power as closed.","source_ids":["s2","s1"]},{"date":"2026-07-28","event":"other","kind":"actual","note":"Core Scientific announced its AMD partnership and listed Hunt County as an AMD site with about 110 MW leased.","source_ids":["s3","s4"]},{"date":"2028-H1","event":"first_operational","kind":"planned","note":"Estimated initial delivery of the AMD capacity.","source_ids":["s3"]}],"name":"Core Scientific Hunt County data center site","notes":"Status is announced because no source opened reports construction at the site; the 10-Q says Core Scientific intends to develop the land as a future data center site.","parties":[{"name":"Core Scientific","role":"developer","source_ids":["s1","s2"]},{"name":"Core Scientific","note":"Completed the land acquisition in 2026.","role":"owner","source_ids":["s2"]},{"name":"AMD","note":"Named for this site only in Core Scientific's Q2 2026 earnings presentation (s3), which lists Hunt County as an AMD direct site with about 110 MW leased. The Q2 release (s4) gives the 15-year term for about 530 MW across five sites without naming them.","role":"tenant","source_ids":["s3","s4"]}],"power_sources":[{"description":"Grid supply on the ERCOT system under an approved interconnection ramp schedule.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929001647/https://investors.corescientific.com/news-events/press-releases/detail/136/core-scientific-announces-first-quarter-fiscal-year-2026-results","id":"s1","published":"2026-05-06","publisher":"Core Scientific","title":"Core Scientific announces first quarter fiscal year 2026 results","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/136/core-scientific-announces-first-quarter-fiscal-year-2026-results"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-28","publisher":"Core Scientific, Inc. via SEC EDGAR","title":"Core Scientific, Inc. quarterly report on Form 10-Q for the period ended June 30, 2026","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001839341/000183934126000014/core-20260630.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929002832/https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm","id":"s3","published":"2026-07-28","publisher":"Core Scientific","title":"Core Scientific Q2 2026 earnings presentation (Form 8-K, Exhibit 99.2)","type":"regulatory_filing","url":"https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-28","publisher":"Core Scientific","title":"Core Scientific announces second quarter 2026 results","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Hunt County, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Hunt_County,_Texas"}],"status":"announced","status_as_of":"2026-07-28","status_source_ids":["s2","s3"],"summary":"Greenfield data center site in Hunt County, Texas, that Core Scientific bought in 2026 for about USD 233 million, with land and power expected to support about 430 MW of gross utility capacity on an approved ERCOT interconnection ramp schedule. In July 2026 Core Scientific listed it as an AMD site with about 110 MW leased under AMD's 15-year agreements, which cover roughly 530 MW across five Core Scientific sites, and estimated initial delivery in the first half of 2028.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2fce484d-a8d3-5fb3-be18-3cb4c685c302","s2":"54345127-0df1-562a-8e87-54a1b61041b7","s3":"1d9f465e-6826-5ca7-8f71-903dc85cf877","s4":"07efc002-2951-51bc-bae2-76b8e0f7c949","s5":"9461b5b8-8d2f-5db3-b852-b23aefd18688"},"source_file":"datacenters/projects/core-scientific-hunt-county.json","source_record_id":"core-scientific-hunt-county","source_record_sha256":"f3d8655922984d28b63705187f2e9186750a7799301fc3ba8ed58403f4c0acd3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"61c43fa75b12f88f291bc31c1b01b8a78db6f7ebe4a12cc7e070d7fc3737330f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-684f1565a0f48756e238/#project-40abc164-3033-5172-b386-52422d1513b9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/40abc164-3033-5172-b386-52422d1513b9.json
41ec9844-286f-5128-a8bf-54e1e328301f | imported:semiconductor-atlas:khazna-dammam | vcc-site-74a60737ad3cfc9e9a75 | imported:semiconductor-atlas:khazna-dammam | Khazna Data Centers Dammam campus | Saudi Arabia | SA | 26.433 | 50.1 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City coordinates from the Dammam Wikipedia page; Khazna has not published the plot location. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 65049f53-47cc-5d17-ba8b-143900d276d7 | announced | 2025-12-09 | 308 | imported_documented_status | 65049f53-47cc-5d17-ba8b-143900d276d7 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"65049f53-47cc-5d17-ba8b-143900d276d7","notes":null,"party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"khazna-dammam"},{"evidence_id":"d05f9f74-0d26-5029-b16e-7c74846928a0","notes":null,"party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"khazna-dammam"},{"evidence_id":"65049f53-47cc-5d17-ba8b-143900d276d7","notes":"Acquired the land for the campus.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"khazna-dammam"},{"evidence_id":"d05f9f74-0d26-5029-b16e-7c74846928a0","notes":"Acquired the land for the campus.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"khazna-dammam"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Khazna Data Centers |  |  |  |  | https://khaznadatacenters.com/press-release/khazna-data-centers-names-new-country-head-and-advances-expansion-plans-in-saudi-arabia-in-support-of-vision-2030/ | https://khaznadatacenters.com/press-release/khazna-data-centers-names-new-country-head-and-advances-expansion-plans-in-saudi-arabia-in-support-of-vision-2030/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Khazna Data Centers Dammam campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"khazna-dammam","source_relations":[{"reason":"Distinct HUMAIN initial Dammam build and Khazna first Saudi campus announcement; shared Dammam city coordinates do not establish the same physical site.","relationship":"separate_named_developments","source_id":"humain-dammam"}]},"record":{"aliases":["Khazna Dammam"],"id":"khazna-dammam","last_reviewed":"2026-10-09","location":{"admin1":"Eastern Province","country":"SA","lat":26.433,"locality":"Dammam","lon":50.1,"note":"City coordinates from the Dammam Wikipedia page; Khazna has not published the plot location.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2025-12-09","basis":"planned","metric":"power_capacity","note":"Described as AI-ready capacity; the scope is not stated.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2"],"unit":"MW","value":200}],"milestones":[{"date":"2025-12-09","event":"site_acquired","kind":"actual","note":"Date the land acquisition was announced in Riyadh.","source_ids":["s1","s2"]}],"name":"Khazna Data Centers Dammam campus","notes":"No 2026 update on the Dammam site was found. The 225,000 square metre plot size is kept in the summary only, because the record format stores land area in acres or hectares.","parties":[{"name":"Khazna Data Centers","role":"developer","source_ids":["s1","s2"]},{"name":"Khazna Data Centers","note":"Acquired the land for the campus.","role":"owner","source_ids":["s1","s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-12-09","publisher":"Khazna Data Centers","title":"Khazna Data Centers names new country head and advances expansion plans in Saudi Arabia in support of Vision 2030","type":"company","url":"https://khaznadatacenters.com/press-release/khazna-data-centers-names-new-country-head-and-advances-expansion-plans-in-saudi-arabia-in-support-of-vision-2030/"},{"accessed":"2026-10-09","id":"s2","published":"2025-12-10","publisher":"Enterprise AM","title":"Dubai-based Khazna Data Centers lands in KSA","type":"news","url":"https://enterpriseam.com/ksa/2025/12/10/dubai-based-khazna-data-centers-lands-in-ksa/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260926035310/https://en.wikipedia.org/wiki/Dammam","id":"s3","published":null,"publisher":"Wikipedia","title":"Dammam","type":"other","url":"https://en.wikipedia.org/wiki/Dammam"}],"status":"announced","status_as_of":"2025-12-09","status_source_ids":["s1"],"summary":"Khazna Data Centers, a UAE data centre operator, announced in December 2025 that it had acquired 225,000 square metres of land in Dammam, in Saudi Arabia's Eastern Province, for its first site in the kingdom. The campus is planned for up to 200 MW of AI-ready capacity in a modular design that can be configured for GPU clusters, aimed at cloud and AI hyperscale customers and built to LEED Gold standards. Khazna named a Saudi country head to lead the launch but gave no investment figure or construction schedule.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"65049f53-47cc-5d17-ba8b-143900d276d7","s2":"d05f9f74-0d26-5029-b16e-7c74846928a0","s3":"c9fcbf66-0533-5e42-bef7-f4f49eec1b77"},"source_file":"datacenters/projects/khazna-dammam.json","source_record_id":"khazna-dammam","source_record_sha256":"df16d608c6114981d143d53162203e397b0a837ad11d9b2b70e26e8a9311ab14","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"f19050947ae5568fa5f98f4930fc8602d507e4457dbfe76d32681da66b6dd84a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-74a60737ad3cfc9e9a75/#project-41ec9844-286f-5128-a8bf-54e1e328301f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/41ec9844-286f-5128-a8bf-54e1e328301f.json
4278fea3-2c31-5512-87d1-d713170569e2 | imported:semiconductor-atlas:stargate-uae | vcc-site-401adc8a0db451b1d581 | imported:semiconductor-atlas:stargate-uae | Stargate UAE / UAE-US AI Campus | United Arab Emirates | AE | 24.3438 | 55.1 | Point | project | imported_reference_point | imported_reference_point | admin1 | compiled_reference | admin1_context | Sources place the campus in Abu Dhabi without naming a district, and its exact site has not been published. Coordinates are the OpenStreetMap Nominatim centroid of the Abu Dhabi emirate, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | dcc56831-8961-557a-ae3e-0ff3f61cd95d | under_construction | 2026-08-13 | 61 | imported_documented_status | 3373b0d6-8b9e-501a-b14a-17562f635a14 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"dcc56831-8961-557a-ae3e-0ff3f61cd95d","notes":"G42 leads the consortium building the 5 GW campus and is named as the builder of the Stargate UAE cluster.","party":"G42","relationship_scope":"unknown","role":"developer","source_record_id":"stargate-uae"},{"evidence_id":"4c106dc2-5c12-5c74-a7d8-d258b4fd9824","notes":"G42 leads the consortium building the 5 GW campus and is named as the builder of the Stargate UAE cluster.","party":"G42","relationship_scope":"unknown","role":"developer","source_record_id":"stargate-uae"},{"evidence_id":"3373b0d6-8b9e-501a-b14a-17562f635a14","notes":"G42 data centre company developing the Stargate UAE cluster and delivering the campus build.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"stargate-uae"},{"evidence_id":"ff46c68d-fde5-5f73-ae38-60893437118e","notes":"G42 data centre company developing the Stargate UAE cluster and delivering the campus build.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"stargate-uae"},{"evidence_id":"6c1283e4-d8a0-53fa-9335-af2c7fde8499","notes":"G42 data centre company developing the Stargate UAE cluster and delivering the campus build.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"stargate-uae"},{"evidence_id":"dcc56831-8961-557a-ae3e-0ff3f61cd95d","notes":"Named with Oracle as an operator of the 1 GW Stargate UAE cluster.","party":"OpenAI","relationship_scope":"unknown","role":"operator","source_record_id":"stargate-uae"},{"evidence_id":"dcc56831-8961-557a-ae3e-0ff3f61cd95d","notes":"Named with OpenAI as an operator of the 1 GW Stargate UAE cluster.","party":"Oracle","relationship_scope":"unknown","role":"operator","source_record_id":"stargate-uae"},{"evidence_id":"dcc56831-8961-557a-ae3e-0ff3f61cd95d","notes":"To supply Grace Blackwell GB300 systems.","party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"stargate-uae"},{"evidence_id":"dcc56831-8961-557a-ae3e-0ff3f61cd95d","notes":"Described as providing zero-trust security and AI-ready network connectivity.","party":"Cisco","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"stargate-uae"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | OpenAI; Oracle |  |  |  | https://www.prnewswire.com/news-releases/g42-provides-update-on-construction-of-stargate-uae-ai-infrastructure-cluster-302586430.html | https://www.g42.ai/resources/news/global-tech-alliance-launches-stargate-uae | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Stargate UAE / UAE-US AI Campus as an independent source record; its admin1 locator does not itself establish a surveyed physical site.","source_record_id":"stargate-uae"},"record":{"aliases":["Stargate UAE","UAE-US AI Campus","UAE–U.S. AI Campus"],"id":"stargate-uae","last_reviewed":"2026-10-09","location":{"admin1":"Abu Dhabi","country":"AE","lat":24.3438,"lon":55.1,"note":"Sources place the campus in Abu Dhabi without naming a district, and its exact site has not been published. Coordinates are the OpenStreetMap Nominatim centroid of the Abu Dhabi emirate, not the site.","precision":"admin1","source_ids":["s1","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-05-15","basis":"planned","metric":"power_capacity","note":"Planned capacity of the whole UAE-US AI Campus, of which Stargate UAE is one part.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":5000},{"applies_to":"phase","as_of":"2025-10-16","basis":"planned","metric":"power_capacity","phase_label":"Stargate UAE cluster","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-08-13","basis":"under_construction","metric":"power_capacity","note":"Khazna said in August 2026 that two 100 MW buildings had been enclosed and fit-out was under way.","phase_label":"Stargate UAE first phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s3","s4","s6"],"unit":"MW","value":200},{"applies_to":"phase","as_of":"2026","basis":"planned","metric":"power_capacity","note":"The UAE Embassy in Washington says the first 500 MW of the campus is due online in 2026. This differs from the 200 MW first phase given by G42, Khazna and Mubadala, and the sources do not reconcile the two figures.","phase_label":"Capacity slated to come online in 2026 (UAE Embassy)","power_scope":"unspecified","qualifier":"exact","source_ids":["s7"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-01-26","basis":"reported","metric":"investment","note":"Cost estimate given by the UAE Minister of State for AI. The report attributes it to the 5 GW project and says it is 50 percent above an early estimate in the USD 20 billion range; no phase breakdown was given.","qualifier":"more_than","source_ids":["s5"],"unit":"USD","value":30000000000},{"applies_to":"campus","as_of":"2026-01-26","basis":"reported","metric":"land_area","note":"Reported as 19.2 square kilometres, converted exactly to hectares.","qualifier":"exact","source_ids":["s4","s5"],"unit":"hectares","value":1920},{"applies_to":"campus","as_of":"2025-05-22","basis":"reported","metric":"land_area","note":"G42 described the campus as about 10 square miles, converted at 640 acres per square mile. This is larger than the 19.2 square kilometres reported later by The National; the conflict is unresolved.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":6400},{"applies_to":"phase","as_of":"2026-08-13","basis":"under_construction","metric":"buildings","note":"Two 100 MW buildings.","phase_label":"Stargate UAE first phase","qualifier":"exact","source_ids":["s6"],"unit":"count","value":2},{"applies_to":"phase","as_of":"2025-12-05","basis":"reported","metric":"jobs_construction","note":"Workers on site as of December 2025.","phase_label":"Stargate UAE first phase","qualifier":"more_than","source_ids":["s4"],"unit":"count","value":5000}],"milestones":[{"date":"2025-05-15","event":"announced","kind":"actual","note":"5 GW UAE-US AI Campus unveiled in Abu Dhabi.","source_ids":["s2"]},{"date":"2025-05-22","event":"announced","kind":"actual","note":"Stargate UAE 1 GW cluster launched as the first block within the campus.","source_ids":["s1"]},{"date":"2025-10-16","event":"other","kind":"actual","note":"G42 reported that civil works were well advanced, all long-lead equipment had been procured and the first mechanical systems had arrived on site.","source_ids":["s3"]},{"date":"2026-Q3","event":"first_operational","kind":"planned","note":"Mubadala's chief executive said in December 2025 that the first 200 MW phase would be ready in the third quarter of 2026.","source_ids":["s4"]},{"date":"2026","event":"first_operational","kind":"planned","note":"Partners and Khazna have repeatedly targeted 2026 for the first 200 MW; Khazna said in August 2026 it remained on track despite regional conflict. No go-live had been confirmed in the sources reviewed.","source_ids":["s1","s6"]}],"name":"Stargate UAE / UAE-US AI Campus","notes":"Sources describe Stargate UAE as the first 1 GW cluster inside the 5 GW UAE-US AI Campus, so both are kept in one record with phase-level figures to avoid double counting. Some reports (for example The National in January 2026) use the Stargate UAE name for the whole 5 GW project. Khazna said in August 2026 that construction continued through that year's regional conflict. SoftBank Group is also named as a partner, but no source reviewed states its role, so it is not listed as a party.","parties":[{"name":"G42","note":"G42 leads the consortium building the 5 GW campus and is named as the builder of the Stargate UAE cluster.","role":"developer","source_ids":["s1","s2"]},{"name":"Khazna Data Centers","note":"G42 data centre company developing the Stargate UAE cluster and delivering the campus build.","role":"developer","source_ids":["s3","s4","s6"]},{"name":"OpenAI","note":"Named with Oracle as an operator of the 1 GW Stargate UAE cluster.","role":"operator","source_ids":["s1"]},{"name":"Oracle","note":"Named with OpenAI as an operator of the 1 GW Stargate UAE cluster.","role":"operator","source_ids":["s1"]},{"name":"NVIDIA","note":"To supply Grace Blackwell GB300 systems.","role":"hardware_supplier","source_ids":["s1"]},{"name":"Cisco","note":"Described as providing zero-trust security and AI-ready network connectivity.","role":"hardware_supplier","source_ids":["s1"]}],"power_sources":[{"description":"Partners said the campus would use nuclear power among its energy sources; the supply arrangement was not described.","source_ids":["s1"],"type":"nuclear"},{"description":"Solar power is named among the campus energy sources; no project or capacity was given.","source_ids":["s1"],"type":"solar"},{"description":"Natural gas is named among the campus energy sources; sources do not say whether generation is on site or via the grid.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-05-22","publisher":"G42","title":"Global Tech Alliance Launches Stargate UAE","type":"company","url":"https://www.g42.ai/resources/news/global-tech-alliance-launches-stargate-uae"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260913154255/https://www.g42.ai/resources/news/g42-lead-consortium-us-partners-build-5gw-uae-us-ai-campus","id":"s2","published":"2025-05-15","publisher":"G42","title":"G42 to lead a consortium with US partners to build 5GW UAE-US AI Campus","type":"company","url":"https://www.g42.ai/resources/news/g42-lead-consortium-us-partners-build-5gw-uae-us-ai-campus"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-16","publisher":"G42 via PR Newswire","title":"G42 Provides Update on Construction of Stargate UAE AI Infrastructure Cluster","type":"company","url":"https://www.prnewswire.com/news-releases/g42-provides-update-on-construction-of-stargate-uae-ai-infrastructure-cluster-302586430.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260908124441/https://www.thenationalnews.com/business/2025/12/05/stargate-uaes-first-phase-to-be-completed-in-third-quarter-of-2026/","id":"s4","published":"2025-12-05","publisher":"The National","title":"Stargate UAE's first phase to be completed in third quarter of 2026","type":"news","url":"https://www.thenationalnews.com/business/2025/12/05/stargate-uaes-first-phase-to-be-completed-in-third-quarter-of-2026"},{"accessed":"2026-10-09","id":"s5","published":"2026-01-26","publisher":"The National","title":"Stargate UAE data centre to cost more than $30bn, AI minister says","type":"news","url":"https://www.thenationalnews.com/future/technology/2026/01/26/stargate-uae-data-centre-to-cost-more-than-30bn-ai-minister-says/"},{"accessed":"2026-10-09","id":"s6","published":"2026-08-13","publisher":"Khaleej Times","title":"Abu Dhabi's 5GW UAE-US AI Campus stays on track despite regional conflict","type":"news","url":"https://www.khaleejtimes.com/uae/abu-dhabi-5gw-uae-us-ai-campus-on-track-regional-conflict"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Embassy of the United Arab Emirates, Washington DC","title":"The UAE-US AI & Advanced Tech Partnership","type":"government","url":"https://www.uae-embassy.org/uae-us-cooperation/economic/forging-future-ai-together-uae-us-advanced-tech-cooperation"}],"status":"under_construction","status_as_of":"2026-08-13","status_source_ids":["s3","s4","s6"],"summary":"A planned 5 GW AI data centre campus in Abu Dhabi, unveiled in May 2025 under a US-UAE technology partnership and led by G42. Its first 1 GW block, branded Stargate UAE, is being developed by G42 unit Khazna Data Centers, with OpenAI and Oracle named as operators and NVIDIA supplying GB300 systems. Construction of an initial 200 MW (two 100 MW buildings) was under way in 2026, with handover targeted for 2026; no completion dates have been given for the rest of the 1 GW cluster or the wider campus. A UAE minister put the cost at more than USD 30 billion in January 2026.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"dcc56831-8961-557a-ae3e-0ff3f61cd95d","s2":"4c106dc2-5c12-5c74-a7d8-d258b4fd9824","s3":"3373b0d6-8b9e-501a-b14a-17562f635a14","s4":"ff46c68d-fde5-5f73-ae38-60893437118e","s5":"f26c5777-d94c-56a4-a3b3-4379fc5b90f7","s6":"6c1283e4-d8a0-53fa-9335-af2c7fde8499","s7":"807b3bd6-04be-5bb6-9291-b598048d12b4"},"source_file":"datacenters/projects/stargate-uae.json","source_record_id":"stargate-uae","source_record_sha256":"fe5de8dd0f71cb9deccf394cd387a6f464e3e2b89be722d08e474a78600b11cf","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"aa0d3a7f712edd89e4f9225b5b0666974a750dda28dcbec949f40f7bb5054607"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-401adc8a0db451b1d581/#project-4278fea3-2c31-5512-87d1-d713170569e2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4278fea3-2c31-5512-87d1-d713170569e2.json
42ae14a5-797b-5251-a05a-c9a12ddc6603 | imported:semiconductor-atlas:pdg-jc4-bekasi | vcc-site-c606ab687ab04588148a | imported:semiconductor-atlas:pdg-jc4-bekasi | Princeton Digital Group JC4 Greater Jakarta | Indonesia | ID | -6.3836 | 107.1911 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | PDG places JC4 in the Greenland International Industrial Center (GIIC), Bekasi Regency, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the GIIC industrial estate and are shared with the nearby JC3 record. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 492bf081-e5dc-5500-97ce-502bfc37c051 | under_construction | 2026-04-30 | 166 | imported_documented_status | 492bf081-e5dc-5500-97ce-502bfc37c051 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"492bf081-e5dc-5500-97ce-502bfc37c051","notes":null,"party":"Princeton Digital Group","relationship_scope":"unknown","role":"developer","source_record_id":"pdg-jc4-bekasi"},{"evidence_id":"fec45400-a289-5a06-b213-1768756647cc","notes":null,"party":"Princeton Digital Group","relationship_scope":"unknown","role":"developer","source_record_id":"pdg-jc4-bekasi"},{"evidence_id":"492bf081-e5dc-5500-97ce-502bfc37c051","notes":"Acquired the powered land.","party":"Princeton Digital Group","relationship_scope":"unknown","role":"owner","source_record_id":"pdg-jc4-bekasi"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Princeton Digital Group |  |  |  |  | https://princetondg.com/press-releases/pdg-acquires-240-mw-of-powered-land-in-jakarta-advancing-its-rapid-expansion-across-asia/ | https://princetondg.com/press-releases/pdg-acquires-240-mw-of-powered-land-in-jakarta-advancing-its-rapid-expansion-across-asia/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Princeton Digital Group JC4 Greater Jakarta as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"pdg-jc4-bekasi","source_relations":[{"reason":"PDG describes JC4 about 1.7 km from JC3; both use the GIIC estate centroid. Preserve independent campus identities.","relationship":"separate_nearby_campuses","source_id":"pdg-jc3-bekasi"}]},"record":{"aliases":["JC4","PDG JC4"],"id":"pdg-jc4-bekasi","last_reviewed":"2026-10-09","location":{"admin1":"West Java","admin2":"Bekasi Regency","country":"ID","lat":-6.3836,"lon":107.1911,"note":"PDG places JC4 in the Greenland International Industrial Center (GIIC), Bekasi Regency, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the GIIC industrial estate and are shared with the nearby JC3 record.","precision":"approximate_site","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-30","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":240},{"applies_to":"campus","as_of":"2026-04-30","basis":"planned","metric":"buildings","note":"Four buildings of 60 MW each.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2026-04-30","basis":"acquired","metric":"land_area","note":"Reported as 106,217 square meters.","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":10.6217}],"milestones":[{"date":"2026-04-30","event":"site_acquired","kind":"actual","note":"Acquisition of 240 MW of powered land announced; PDG said construction had already commenced.","source_ids":["s1"]},{"date":"2026-05-07","event":"other","kind":"actual","note":"PDG referred to the recently announced launch of JC4 among its Indonesian milestones.","source_ids":["s2"]}],"name":"Princeton Digital Group JC4 Greater Jakarta","parties":[{"name":"Princeton Digital Group","role":"developer","source_ids":["s1","s2"]},{"name":"Princeton Digital Group","note":"Acquired the powered land.","role":"owner","source_ids":["s1"]}],"power_sources":[],"related_ids":["pdg-jc3-bekasi"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-04-30","publisher":"Princeton Digital Group","title":"PDG Acquires 240 MW of Powered Land in Jakarta, Advancing Its Rapid Expansion Across Asia","type":"company","url":"https://princetondg.com/press-releases/pdg-acquires-240-mw-of-powered-land-in-jakarta-advancing-its-rapid-expansion-across-asia/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004132014/https://princetondg.com/press-releases/pdg-raising-usd-856-million-debt-for-its-hyperscale-data-center-expansion-in-indonesia/","id":"s2","published":"2026-05-07","publisher":"Princeton Digital Group","title":"PDG Raising ~USD 856 Million Debt for its Hyperscale Data Center Expansion in Indonesia","type":"company","url":"https://princetondg.com/press-releases/pdg-raising-usd-856-million-debt-for-its-hyperscale-data-center-expansion-in-indonesia/"}],"status":"under_construction","status_as_of":"2026-04-30","status_source_ids":["s1"],"summary":"Princeton Digital Group announced in April 2026 that it had acquired powered land for JC4, a planned 240 MW campus of four 60 MW buildings on about 106,000 square meters in the Greenland International Industrial Center in Bekasi Regency, Greater Jakarta. The site is about 1.7 km from PDG's JC3 campus, allowing shared power and connectivity infrastructure, and PDG said construction had already begun. No investment figure or completion date has been published.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"492bf081-e5dc-5500-97ce-502bfc37c051","s2":"fec45400-a289-5a06-b213-1768756647cc"},"source_file":"datacenters/projects/pdg-jc4-bekasi.json","source_record_id":"pdg-jc4-bekasi","source_record_sha256":"4d00f805fe14e412907c3337e3798fb54b49cf5b3ce49af775cbc54882a9c872","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8ac1105bbdbc397e79da7ed495d74773d3cde3f65c90633c398ba1b52807be6a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c606ab687ab04588148a/#project-42ae14a5-797b-5251-a05a-c9a12ddc6603 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/42ae14a5-797b-5251-a05a-c9a12ddc6603.json
42e50e84-873d-562d-b6d2-945ccf04b0e8 | curated:stt-jakarta-data-centre-campus:stt-jakarta-5 | vcc-site-57a103a9de718a95ae14 | curated:stt-jakarta-data-centre-campus | STT Jakarta 5 | Indonesia | ID | -6.374 | 107.2011 | Polygon | campus | cross_source_overlay | openstreetmap_exactly_named_stt_jakarta_1_facility_polygon_as_shared_campus_locator | reviewed_openstreetmap_stt_jakarta_1_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for STT Jakarta 1, used only as one known-building anchor for the shared campus targeted by STT Jakarta 5. It is not the Jakarta 5 location or footprint, the campus boundary, a parcel, a construction extent, or a survey-accuracy claim. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral or survey geometry. | f16b034b-60d8-5826-841a-1acaa849a930 | under_construction | 2026-06-10 | 125 | authoritative_construction_start | a251b3bb-e0bc-56d3-b89a-97914d692f5d | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-06-10","base":40.0,"confidence":0.99,"evidence_id":"a251b3bb-e0bc-56d3-b89a-97914d692f5d","high":40.0,"low":40.0,"method":"reported","metric":"critical_it_mw","notes":"Planned critical-IT capacity for STT Jakarta 5 only. The source says the facility is planned to support 40 MW of IT load; this is not current load, gross facility power, grid draw, generation, annual energy, or measured consumption.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.sttelemediagdc.com/newsroom/stt-gdc-accelerates-jakarta-campus-expansion-power-indonesia-ai-and-digital-ambitions | https://www.openstreetmap.org/way/1533569836 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-57a103a9de718a95ae14/#project-42e50e84-873d-562d-b6d2-945ccf04b0e8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/42e50e84-873d-562d-b6d2-945ccf04b0e8.json
43ded2e8-5dcf-5174-b553-a4a04aaeebe3 | curated:merlin-lisbon-data-center-campus:phase-2-two-building-development | vcc-site-af26df3b9a306efc763c | curated:merlin-lisbon-data-center-campus | MERLIN Lisbon Phase II Two-Building Development | Portugal | PT | 38.9883 | -8.9637 | Point | campus | operator_published_literal_site_coordinates | operator_published_literal_site_coordinates | operator_campus_reference_point | official_source | campus_locator | The point identifies the campus, not the boundary or centroid of either Phase II building. Positional accuracy and survey provenance are not stated. The Edged Lisbon page prints these literal coordinates directly beneath its Lisbon Campus heading. MERLIN's named Lisbon campus page and its Phase II results disclosures identify the same Castanheira do Ribatejo campus. No redirect resolution is needed for the explicitly printed point. |  | Neither source states quantitative positional accuracy or survey provenance; coordinate digits are not an accuracy estimate. | bad12459-311d-512a-aca2-716918af6b40 | under_construction | 2026-07-27 | 78 | authoritative_physical_status_update | 406b5d16-6ad7-5298-b89f-18e3cb049f61 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ir.merlinproperties.com/en/merlin-increases-total-revenues-and-ebitda-by-11-7-thanks-to-the-data-centers-division-which-reaches-160-mw-leased/ | https://www.edged.es/lisbon | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-af26df3b9a306efc763c/#project-43ded2e8-5dcf-5174-b553-a4a04aaeebe3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/43ded2e8-5dcf-5174-b553-a4a04aaeebe3.json
441174d1-4dab-5b80-bfb2-76062cf675aa | imported:semiconductor-atlas:edgecore-mesa | vcc-site-54d4a697323404ecfc35 | imported:semiconductor-atlas:edgecore-mesa | EdgeCore Mesa data center campus | United States | US | 33.3442 | -111.6196 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Point from the local OpenStreetMap layer (datacenters/layers/osm/features.geojson): a building footprint tagged EdgeCore at South Everton Terrace, Mesa (OSM way 808979618). It marks one existing building, not the centroid of the expanded 84-acre campus. The cited sources name Mesa but give no street address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3b92e884-db33-5b13-be1e-bcb97a3e4344 | partially_operational | 2025-05-21 | 510 | imported_documented_status | 3b92e884-db33-5b13-be1e-bcb97a3e4344 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3b92e884-db33-5b13-be1e-bcb97a3e4344","notes":null,"party":"EdgeCore Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"edgecore-mesa"},{"evidence_id":"ab3cd05e-2e1f-549b-aa63-11daa1b7f34a","notes":null,"party":"EdgeCore Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"edgecore-mesa"},{"evidence_id":"37a8ffc7-4e5e-5503-9fee-9d738613bcef","notes":null,"party":"EdgeCore Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"edgecore-mesa"},{"evidence_id":"ab3cd05e-2e1f-549b-aa63-11daa1b7f34a","notes":"Described as a wholesale data center developer, owner and operator.","party":"EdgeCore Digital Infrastructure","relationship_scope":"unknown","role":"owner","source_record_id":"edgecore-mesa"},{"evidence_id":"ab3cd05e-2e1f-549b-aa63-11daa1b7f34a","notes":null,"party":"EdgeCore Digital Infrastructure","relationship_scope":"unknown","role":"operator","source_record_id":"edgecore-mesa"},{"evidence_id":"3b92e884-db33-5b13-be1e-bcb97a3e4344","notes":null,"party":"Salt River Project","relationship_scope":"unknown","role":"utility","source_record_id":"edgecore-mesa"},{"evidence_id":"ab3cd05e-2e1f-549b-aa63-11daa1b7f34a","notes":null,"party":"Salt River Project","relationship_scope":"unknown","role":"utility","source_record_id":"edgecore-mesa"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | EdgeCore Digital Infrastructure | EdgeCore Digital Infrastructure |  |  |  | https://edgecore.com/edgecore-digital-infrastructure-announces-expansion-of-its-metro-phoenix-data-center-market-to-over-450-mw/ | https://edgecore.com/edgecore-digital-infrastructure-announces-expansion-of-its-metro-phoenix-data-center-market-to-over-450-mw/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve EdgeCore Mesa data center campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"edgecore-mesa"},"record":{"aliases":["EdgeCore Phoenix campus","EdgeCore PH01-PH03"],"id":"edgecore-mesa","last_reviewed":"2026-10-09","location":{"admin1":"Arizona","country":"US","lat":33.3442,"locality":"Mesa","lon":-111.6196,"note":"Point from the local OpenStreetMap layer (datacenters/layers/osm/features.geojson): a building footprint tagged EdgeCore at South Everton Terrace, Mesa (OSM way 808979618). It marks one existing building, not the centroid of the expanded 84-acre campus. The cited sources name Mesa but give no street address.","precision":"approximate_site","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Critical IT load of the five-building campus on EdgeCore's undated campus page, dated here by access.","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":496},{"applies_to":"campus","as_of":"2025-05-20","basis":"planned","metric":"power_capacity","note":"Total announced with the May 2025 land purchase.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1","s2"],"unit":"MW","value":450},{"applies_to":"phase","as_of":"2025-05-20","basis":"planned","metric":"power_capacity","phase_label":"43.87-acre expansion parcel","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1","s2"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":84},{"applies_to":"phase","as_of":"2025-05-20","basis":"acquired","metric":"land_area","phase_label":"43.87-acre expansion parcel","qualifier":"exact","source_ids":["s1","s2"],"unit":"acres","value":43.87},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s3"],"unit":"count","value":5},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":2700000}],"milestones":[{"date":"2023-04","event":"other","kind":"actual","note":"EdgeCore dates the establishment of its first Mesa campus to April 2023.","source_ids":["s1","s2"]},{"date":"2025-05-20","event":"expansion_announced","kind":"actual","note":"Purchase of 43.87 more acres and expansion to over 450 MW announced.","source_ids":["s1","s2"]},{"date":"2025","event":"other","kind":"planned","note":"Completion year for one of the two buildings under construction; the sources give 2025 and 2026 for PH02 and PH03 without saying which is which.","source_ids":["s2"]},{"date":"2026","event":"other","kind":"planned","note":"Completion year for the other building under construction (PH02 or PH03).","source_ids":["s2"]}],"name":"EdgeCore Mesa data center campus","notes":"Status rests on the May 2025 release; no 2026 source confirming whether PH02 and PH03 were finished was found. EdgeCore's campus page is undated and does not give per-building status, so its figures carry the access date. The May 2025 release also said 206 MW had been built and commissioned on the original Mesa land while two buildings were still under construction; that figure is left out of the metrics because it is unclear what share was operating.","parties":[{"name":"EdgeCore Digital Infrastructure","role":"developer","source_ids":["s1","s2","s3"]},{"name":"EdgeCore Digital Infrastructure","note":"Described as a wholesale data center developer, owner and operator.","role":"owner","source_ids":["s2"]},{"name":"EdgeCore Digital Infrastructure","role":"operator","source_ids":["s2"]},{"name":"Salt River Project","role":"utility","source_ids":["s1","s2"]}],"power_sources":[{"description":"Salt River Project serves the operating building and was slated to power PH02 and PH03 on completion.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-05-20","publisher":"EdgeCore Digital Infrastructure","title":"EdgeCore Digital Infrastructure Announces Expansion of Its Metro Phoenix Data Center Market to Over 450 MW","type":"company","url":"https://edgecore.com/edgecore-digital-infrastructure-announces-expansion-of-its-metro-phoenix-data-center-market-to-over-450-mw/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260117165151/https://inbusinessphx.com/technology-innovation/data-center-developer-announces-expansion-of-metro-phoenix-infrastructure","id":"s2","published":"2025-05-21","publisher":"InBusiness Phoenix","title":"Data Center Developer Announces Expansion of Metro Phoenix Infrastructure","type":"trade_press","url":"https://inbusinessphx.com/technology-innovation/data-center-developer-announces-expansion-of-metro-phoenix-infrastructure"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"EdgeCore Digital Infrastructure","title":"Phoenix data center campus","type":"company","url":"https://edgecore.com/locations/phoenix-data-center"}],"status":"partially_operational","status_as_of":"2025-05-21","status_source_ids":["s1","s2"],"summary":"Wholesale hyperscale data center campus that EdgeCore Digital Infrastructure established in Mesa, Arizona, in April 2023, with power from Salt River Project. Its first building, PH01, was operating by 2025 while PH02 and PH03 were under construction for completion in 2025 and 2026. In May 2025 EdgeCore bought another 43.87 acres, more than doubling its buildable land in Mesa, and raised planned capacity to over 450 MW. EdgeCore's campus page now describes an 84-acre, five-building campus able to support 496 MW of critical IT load in about 2.7 million square feet.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3b92e884-db33-5b13-be1e-bcb97a3e4344","s2":"ab3cd05e-2e1f-549b-aa63-11daa1b7f34a","s3":"37a8ffc7-4e5e-5503-9fee-9d738613bcef"},"source_file":"datacenters/projects/edgecore-mesa.json","source_record_id":"edgecore-mesa","source_record_sha256":"11108ce31c1e8198f200d4be4681d069335589ece0fb1c2199fee548a18090d2","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d32b94b194c30dba40bff79ef74b21ea7a36e3842c000a463ca9cc87f9e2155a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-54d4a697323404ecfc35/#project-441174d1-4dab-5b80-bfb2-76062cf675aa | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/441174d1-4dab-5b80-bfb2-76062cf675aa.json
44130f9f-95af-5f19-9fcf-47aabd3a5c8b | curated:akashi-astana-data-center-campus:phase-1-current-build | vcc-site-cc8bbdad8c252d9ba4e2 | curated:akashi-astana-data-center-campus | Akashi Astana Phase 1 Current Build | Kazakhstan | KZ | 51.2068 | 71.4577 | Point | project | direct_geometry | authoritative_site_plan | same_parcel_infrastructure_reference_point | official_source | reviewed_site_locator | Official site-plan point for a substation within the same data-centre parcel; 500 metre stated uncertainty and not a hall footprint. | 500 |  | ff1fe928-217c-5369-8ab1-5dce1a637677 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | ad6f9a56-ffa6-527d-bcd3-a7d8932c31b9 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | colocation |  | 1337f6ef-1e09-5b6e-a1e0-55fbdcf95bf3 | [] | not established by selected evidence | [{"evidence_id":"1337f6ef-1e09-5b6e-a1e0-55fbdcf95bf3","party":"Akashi Data Center","relationship_scope":"intended","role":"operator"}] | [{"as_of_date":"2026-07-21","base":5.28,"confidence":0.99,"evidence_id":"ad6f9a56-ffa6-527d-bcd3-a7d8932c31b9","high":5.28,"low":5.28,"method":"reported","metric":"critical_it_mw","notes":"Reported phase-1 IT load retained at planned stage. It is not installed, energized, operational, current demand, grid capacity, generation, consumption, or annual energy.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | Akashi Data Center |  |  |  | https://akashi.cloud/construction-progress/ | https://ecoportal.kz/Rubric/RubService/LoadFile/59205 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cc8bbdad8c252d9ba4e2/#project-44130f9f-95af-5f19-9fcf-47aabd3a5c8b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/44130f9f-95af-5f19-9fcf-47aabd3a5c8b.json
447b19d9-b89b-59a6-9931-824aa1781fb0 | curated:goodman-lax01-los-angeles-program-anchor:first-site-current-development | vcc-site-e5029d978178bf23ae67 | curated:goodman-lax01-los-angeles-program-anchor | Goodman LAX01 First-Site Current Development | United States | US | 34.0051 | -118.2181 | Point | project | official_parcel_reference_point | official_exact_address_match_to_published_center_lat_lon_fields_without_atlas_centroiding | official_assessor_parcel_reference_point | official_source | project_locator | Current assessor parcel reference point for the exact owner-bound first-facility address at 3094 E Vernon Avenue. This is not the entire 3094/3200 property boundary, a building footprint, current construction extent, or surveyed building-center claim. |  | The selected county service result supplies no numeric horizontal accuracy for its reference-point fields. | 37013ce5-a12c-59d4-beb5-6ae9011daed7 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 874d0ee1-67d9-5eb2-9ee8-20ddb1757724 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | https://public.gis.lacounty.gov/public/rest/services/LACounty_Cache/LACounty_Parcel/MapServer/0/query?where=SitusHouseNo%3D'3094'%20AND%20SitusStreet%20LIKE%20'%25VERNON%25'&outFields=AIN%2CAPN%2CSitusHouseNo%2CSitusDirection%2CSitusStreet%2CSitusAddress%2CSitusCity%2CSitusZIP%2CCENTER_LAT%2CCENTER_LON&returnGeometry=true&outSR=4326&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e5029d978178bf23ae67/#project-447b19d9-b89b-59a6-9931-824aa1781fb0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/447b19d9-b89b-59a6-9931-824aa1781fb0.json
46434a5c-4980-5f79-ac83-000783b60566 | imported:semiconductor-atlas:blackstone-calatorao | vcc-site-62511f2ff7c107b083ea | imported:semiconductor-atlas:blackstone-calatorao | QTS Calatorao data center campus | Spain | ES | 41.5222 | -1.3464 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Nominatim centroid of the municipality of Calatorao; sources place the site on industrial land beside the A-2 about 7 km from the town centre, without a parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 1503cf45-fa45-5d59-a7fc-7ce360a11a88 | announced | 2025-08-27 | 412 | imported_documented_status | 078ea19d-9af1-51c4-938d-74a15d90c5e2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3532813c-b4a1-5d46-8164-c9c929b18eb7","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"blackstone-calatorao"},{"evidence_id":"2f20d843-ded1-5a00-a865-11fe3f8c9c66","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"blackstone-calatorao"},{"evidence_id":"3532813c-b4a1-5d46-8164-c9c929b18eb7","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"operator","source_record_id":"blackstone-calatorao"},{"evidence_id":"2f20d843-ded1-5a00-a865-11fe3f8c9c66","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"operator","source_record_id":"blackstone-calatorao"},{"evidence_id":"1503cf45-fa45-5d59-a7fc-7ce360a11a88","notes":"Funds managed by Blackstone affiliates finance the project; QTS is a Blackstone portfolio company.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"blackstone-calatorao"},{"evidence_id":"0ff34972-d808-5d05-8f04-291c5f48f7ae","notes":"Funds managed by Blackstone affiliates finance the project; QTS is a Blackstone portfolio company.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"blackstone-calatorao"},{"evidence_id":"3532813c-b4a1-5d46-8164-c9c929b18eb7","notes":"Funds managed by Blackstone affiliates finance the project; QTS is a Blackstone portfolio company.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"blackstone-calatorao"},{"evidence_id":"2f20d843-ded1-5a00-a865-11fe3f8c9c66","notes":"Funds managed by Blackstone affiliates finance the project; QTS is a Blackstone portfolio company.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"blackstone-calatorao"},{"evidence_id":"1503cf45-fa45-5d59-a7fc-7ce360a11a88","notes":"Granted the DIGA declaration and the initial PIGA approval.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"blackstone-calatorao"},{"evidence_id":"078ea19d-9af1-51c4-938d-74a15d90c5e2","notes":"Granted the DIGA declaration and the initial PIGA approval.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"blackstone-calatorao"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | QTS Data Centers |  |  |  | https://www.eldiario.es/aragon/politica/explosion-centros-datos-aragon-opacidad-choque-institucional-riesgo-colapso_1_12559021.amp.html | https://brainsre.news/blackstone-7500-millones-data-center-aragon/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve QTS Calatorao data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"blackstone-calatorao"},"record":{"aliases":["Proyecto Rodes","Project Rodes","Blackstone Aragon data center"],"id":"blackstone-calatorao","last_reviewed":"2026-10-09","location":{"admin1":"Aragón","admin2":"Zaragoza","country":"ES","lat":41.5222,"locality":"Calatorao","lon":-1.3464,"note":"Nominatim centroid of the municipality of Calatorao; sources place the site on industrial land beside the A-2 about 7 km from the town centre, without a parcel.","precision":"locality","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2024-10-14","basis":"announced","metric":"investment","note":"Investment Monitor, citing Reuters, reported that half the site would be developed first and a further EUR 7.5 billion invested later for the remainder; that second tranche is not added here.","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"EUR","value":7500000000},{"applies_to":"campus","as_of":"2024-10-16","basis":"planned","metric":"power_capacity","note":"Reported electrical capacity when fully operational; not confirmed on the QTS page.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2024-10-14","basis":"planned","metric":"land_area","qualifier":"exact","source_ids":["s1","s2","s3","s5"],"unit":"hectares","value":224}],"milestones":[{"date":"2024-10-14","event":"announced","kind":"actual","note":"Announced by Aragon's regional president.","source_ids":["s1"]},{"date":"2024-10","event":"other","kind":"actual","note":"Aragon's cabinet approved a declaration of regional general interest (DIGA), starting the planning process.","source_ids":["s1","s3"]},{"date":"2025-08","event":"other","kind":"actual","note":"Initial (not final) approval of the regional general-interest plan (PIGA), published in the Boletín Oficial de Aragón in late August 2025.","source_ids":["s4"]}],"name":"QTS Calatorao data center campus","notes":"Aragon cites up to 1,400 direct jobs in technology, construction and other sectors, and QTS about 1,400 direct plus up to 2,000 indirect jobs; these are not split by phase, so no jobs metric is recorded. No 2026 status update could be found; QTS's undated pages describe a proposed development worth several billion euros.","parties":[{"name":"QTS Data Centers","role":"developer","source_ids":["s5","s6"]},{"name":"QTS Data Centers","role":"operator","source_ids":["s5","s6"]},{"name":"Blackstone","note":"Funds managed by Blackstone affiliates finance the project; QTS is a Blackstone portfolio company.","role":"investor","source_ids":["s1","s2","s5","s6"]},{"name":"Gobierno de Aragón","note":"Granted the DIGA declaration and the initial PIGA approval.","role":"government","source_ids":["s1","s4"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260606020551/https://brainsre.news/blackstone-7500-millones-data-center-aragon/","id":"s1","published":"2024-10-14","publisher":"Brainsre.news","title":"Blackstone invertirá hasta 7.500 millones en un data center en Aragón","type":"trade_press","url":"https://brainsre.news/blackstone-7500-millones-data-center-aragon/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260613090146/https://www.investmentmonitor.ai/news/blackstone-to-make-8-2bn-data-centre-investment-in-spain/","id":"s2","published":"2024-10-16","publisher":"Investment Monitor","title":"Blackstone to make $8.2bn data centre investment in Spain","type":"trade_press","url":"https://www.investmentmonitor.ai/news/blackstone-to-make-8-2bn-data-centre-investment-in-spain"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20241202150640/https://www.merca2.es/2024/10/15/aragon-centros-datos-blackstone-2029461/","id":"s3","published":"2024-10-15","publisher":"Merca2","title":"Aragón, la mina de oro española de los centros de datos: Microsoft, AWS, Meta y Blackstone","type":"news","url":"https://www.merca2.es/2024/10/15/aragon-centros-datos-blackstone-2029461/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260815160219/https://www.eldiario.es/aragon/politica/explosion-centros-datos-aragon-opacidad-choque-institucional-riesgo-colapso_1_12559021.amp.html","id":"s4","published":"2025-08-27","publisher":"elDiario.es","title":"La explosión de los centros de datos en Aragón: entre la opacidad, el choque institucional y el riesgo de colapso","type":"news","url":"https://www.eldiario.es/aragon/politica/explosion-centros-datos-aragon-opacidad-choque-institucional-riesgo-colapso_1_12559021.amp.html"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"QTS Data Centers","title":"Calatorao data centre campus","type":"company","url":"https://q.com/data-centers/calatorao-en/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260420152346/https://q.com/data-centers/calatorao/","id":"s6","published":null,"publisher":"QTS Data Centers","title":"Campus de centros de datos de Calatorao","type":"company","url":"https://q.com/data-centers/calatorao/"}],"status":"announced","status_as_of":"2025-08-27","status_source_ids":["s4","s5"],"summary":"Blackstone, through its data center company QTS, proposes a 224-hectare data center campus on industrial land beside the A-2 motorway near Calatorao in Zaragoza province, Aragon. Announced in October 2024 at up to EUR 7.5 billion and reported at 300 MW of electrical capacity at full build-out, it received a regional general-interest declaration (DIGA) in October 2024 and initial approval of its regional general-interest plan (PIGA) in August 2025. QTS describes it as a proposed development and has not published a construction schedule.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"1503cf45-fa45-5d59-a7fc-7ce360a11a88","s2":"0ff34972-d808-5d05-8f04-291c5f48f7ae","s3":"b4db59c0-9e24-5b3f-81e3-26d557f8fd1a","s4":"078ea19d-9af1-51c4-938d-74a15d90c5e2","s5":"3532813c-b4a1-5d46-8164-c9c929b18eb7","s6":"2f20d843-ded1-5a00-a865-11fe3f8c9c66"},"source_file":"datacenters/projects/blackstone-calatorao.json","source_record_id":"blackstone-calatorao","source_record_sha256":"6afcb1fbc59cf3659ffc3e2d0aa618b2fd646f74ecfb8cd734af34d6d752dadf","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"809006638c4dc4beaaf5db9656e3859be9545d10813d822fab2e462375c982ab"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-62511f2ff7c107b083ea/#project-46434a5c-4980-5f79-ac83-000783b60566 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/46434a5c-4980-5f79-ac83-000783b60566.json
46abd4bf-bd8a-5525-9388-c938807fe2f0 | imported:semiconductor-atlas:box2bit-epila | vcc-site-60428cb258a38898ef68 | imported:semiconductor-atlas:box2bit-epila | Box2Bit Epilon data center campus (Épila) | Spain | ES | 41.6 | -1.283 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from the Épila Wikipedia article. Aragón Digital says the site has two accesses from the A-2 near the bonÀrea development; no parcel boundary is published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 7e303358-ae48-520e-be8a-8ed7407889de | announced | 2026-06-15 | 120 | imported_documented_status | 7e303358-ae48-520e-be8a-8ed7407889de | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"7e303358-ae48-520e-be8a-8ed7407889de","notes":"Aragón Digital describes the promoter as an independent Spanish company within a group whose parent is Quantum Global Assets.","party":"Box2Bit","relationship_scope":"unknown","role":"developer","source_record_id":"box2bit-epila"},{"evidence_id":"a1463b4f-a57e-521b-ba8c-afd9dc48a05d","notes":"Aragón Digital describes the promoter as an independent Spanish company within a group whose parent is Quantum Global Assets.","party":"Box2Bit","relationship_scope":"unknown","role":"developer","source_record_id":"box2bit-epila"},{"evidence_id":"9311eabe-3572-5e8b-ac95-2f9053ea299f","notes":"Aragón Digital describes the promoter as an independent Spanish company within a group whose parent is Quantum Global Assets.","party":"Box2Bit","relationship_scope":"unknown","role":"developer","source_record_id":"box2bit-epila"},{"evidence_id":"7e303358-ae48-520e-be8a-8ed7407889de","notes":"Declared the project an investment of regional interest with general interest of Aragón in January 2026.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"box2bit-epila"},{"evidence_id":"a1463b4f-a57e-521b-ba8c-afd9dc48a05d","notes":"Declared the project an investment of regional interest with general interest of Aragón in January 2026.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"box2bit-epila"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.aragonhoy.es/consejos-de-gobierno/respaldo-gobierno-aragon-proyecto-box2bit-creara-1-800-puestos-epila-103723 | https://www.aragonhoy.es/consejos-de-gobierno/respaldo-gobierno-aragon-proyecto-box2bit-creara-1-800-puestos-epila-103723 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Box2Bit Epilon data center campus (Épila) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"box2bit-epila"},"record":{"aliases":["Epilon","Epsilon"],"id":"box2bit-epila","last_reviewed":"2026-10-09","location":{"admin1":"Aragón","admin2":"Zaragoza","country":"ES","lat":41.6,"locality":"Épila","lon":-1.283,"note":"Town coordinates from the Épila Wikipedia article. Aragón Digital says the site has two accesses from the A-2 near the bonÀrea development; no parcel boundary is published.","precision":"locality","source_ids":["s1","s2","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-28","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1","s2","s3","s5"],"unit":"EUR","value":3900000000},{"applies_to":"phase","as_of":"2026-01-28","basis":"announced","metric":"investment","phase_label":"First phase","qualifier":"exact","source_ids":["s1","s2"],"unit":"EUR","value":1125000000},{"applies_to":"phase","as_of":"2026-01-28","basis":"announced","metric":"investment","phase_label":"Later phases","qualifier":"exact","source_ids":["s1","s2"],"unit":"EUR","value":2775000000},{"applies_to":"phase","as_of":"2026-01-28","basis":"contracted","metric":"power_capacity","note":"Aragón Digital says the first phase has guaranteed grid access for 150 MW; the government spokesperson said the first phase is secured and the second is still pending.","phase_label":"First phase","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2","s5"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2026-01-28","basis":"planned","metric":"power_capacity","note":"Capacity the later phases could reach; the additional supply has not been secured.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s2","s5"],"unit":"MW","value":520},{"applies_to":"phase","as_of":"2026-01-28","basis":"planned","metric":"land_area","phase_label":"First phase","qualifier":"approximately","source_ids":["s2"],"unit":"hectares","value":33},{"applies_to":"campus","as_of":"2026-01-28","basis":"planned","metric":"land_area","note":"Expansion area available if needed.","qualifier":"approximately","source_ids":["s2"],"unit":"hectares","value":100},{"applies_to":"phase","as_of":"2026-01-28","basis":"planned","metric":"floor_area","phase_label":"First phase","qualifier":"exact","source_ids":["s2"],"unit":"sq_m","value":66100},{"applies_to":"campus","as_of":"2026-01-28","basis":"planned","metric":"floor_area","note":"Floor area once all phases are complete.","qualifier":"up_to","source_ids":["s2"],"unit":"sq_m","value":227300},{"applies_to":"phase","as_of":"2026-01-28","basis":"planned","metric":"buildings","note":"Data processing buildings; the first phase also includes an access-control building.","phase_label":"First phase","qualifier":"exact","source_ids":["s2"],"unit":"count","value":2},{"applies_to":"phase","as_of":"2026-01-28","basis":"planned","metric":"jobs_construction","note":"Direct construction jobs; the government adds 1,000 indirect jobs. The regional president cited about 1,500 construction jobs in total.","phase_label":"First phase","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"count","value":550},{"applies_to":"phase","as_of":"2026-01-28","basis":"planned","metric":"jobs_permanent","note":"Direct operating jobs; the government adds 200 indirect jobs.","phase_label":"First phase","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":63}],"milestones":[{"date":"2026-01-28","event":"announced","kind":"actual","note":"The Aragón Governing Council approved the regional-interest declaration the same day the regional president announced the investment.","source_ids":["s1","s3"]},{"date":"2029","event":"first_operational","kind":"planned","note":"Target for completing the first phase.","source_ids":["s1","s2","s5"]}],"name":"Box2Bit Epilon data center campus (Épila)","notes":"Hoy Aragón reports that Box2Bit's earlier EUR 3.4 billion Cariñena plan was left out of Red Eléctrica's 2025-2030 grid planning; the government spokesperson called Épila complementary to Cariñena (Aragón Digital), while elDiario.es said the company had given Cariñena up. Hoy Aragón says the declaration lets the campus be processed through a PIGA, that it could not advance with certainty before the end of 2027, and that it lies a few hundred metres from Blackstone's planned site (record blackstone-calatorao). Forbes España (June 2026) repeats the EUR 3.9 billion, 150 MW, 520 MW and 2029 figures without naming the town; status_as_of uses that report.","parties":[{"name":"Box2Bit","note":"Aragón Digital describes the promoter as an independent Spanish company within a group whose parent is Quantum Global Assets.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Gobierno de Aragón","note":"Declared the project an investment of regional interest with general interest of Aragón in January 2026.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"Hoy Aragón says supply is guaranteed through the Calatorao substation, where Red Eléctrica's expansion was in its final phase; Aragón Digital says the campus can run on up to 100% renewable energy.","source_ids":["s2","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-28","publisher":"Gobierno de Aragón (Aragón Hoy)","title":"Respaldo del Gobierno de Aragón al proyecto de Box2Bit que creará más de 1.800 puestos de trabajo en Épila","type":"government","url":"https://www.aragonhoy.es/consejos-de-gobierno/respaldo-gobierno-aragon-proyecto-box2bit-creara-1-800-puestos-epila-103723"},{"accessed":"2026-10-09","id":"s2","published":"2026-01-28","publisher":"Aragón Digital","title":"La DGA precisa los detalles del centro de datos de Box2Bit en Épila: primera fase de 1.125 millones","type":"news","url":"https://www.aragondigital.es/articulo/economia/dga-precisa-detalles-centro-datos-box2bit-epila-primera-fase-1125-millones/20260128124944963318.html"},{"accessed":"2026-10-09","id":"s3","published":"2026-01-28","publisher":"elDiario.es","title":"La empresa Box2Bit invertirá 3.900 millones de euros en un centro de datos en Épila tras renunciar al de Cariñena","type":"news","url":"https://www.eldiario.es/aragon/economia/empresa-box2bit-invertira-3-900-millones-euros-centro-datos-epila-renunciar-carinena_1_12942482.html"},{"accessed":"2026-10-09","id":"s4","published":"2026-01-29","publisher":"Hoy Aragón","title":"El motivo real por el que Box2Bit abandona Cariñena y se va a Épila con 3.900 millones","type":"news","url":"https://www.hoyaragon.es/articulo/noticias-aragon/box2bit-epila-centro-datos-carinena/20260129112439121735.html"},{"accessed":"2026-10-09","id":"s5","published":"2026-06-15","publisher":"Forbes España","title":"Morgan Stanley eleva un 55% su previsión de capacidad de centros de datos en España, impulsada por Aragón","type":"news","url":"https://forbes.es/?p=956076"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Épila","type":"other","url":"https://en.wikipedia.org/wiki/%C3%89pila"}],"status":"announced","status_as_of":"2026-06-15","status_source_ids":["s1","s4","s5"],"summary":"AI-focused data center campus proposed by the Spanish company Box2Bit in Épila, Zaragoza, beside the A-2 motorway. On 28 January 2026 the Aragón government declared it an investment of regional and general interest, citing EUR 3.9 billion in total: EUR 1.125 billion for a first phase due in 2029 and EUR 2.775 billion for later phases. The first phase covers about 33 hectares, two data buildings and 150 MW with guaranteed grid access; later phases could take the site to about 100 hectares and 520 MW, but the additional power is not yet secured. The move followed the exclusion of Box2Bit's earlier Cariñena site from national grid planning.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"7e303358-ae48-520e-be8a-8ed7407889de","s2":"a1463b4f-a57e-521b-ba8c-afd9dc48a05d","s3":"9311eabe-3572-5e8b-ac95-2f9053ea299f","s4":"f53d7922-ef9f-512e-b0eb-ade21ce3c747","s5":"4106c579-4ff7-53d8-9603-16ba9a1213a1","s6":"d36f4973-beab-5cd9-aae8-279f4af062db"},"source_file":"datacenters/projects/box2bit-epila.json","source_record_id":"box2bit-epila","source_record_sha256":"c370dc69ad775dd57b1b7f2de036cbcdfb9c920f9b339d307309e1ac414d7444","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a99fa29b66fcadba9d70771d692d5e178477fd287bdac88d6b28ca5fc1d0c1a5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-60428cb258a38898ef68/#project-46abd4bf-bd8a-5525-9388-c938807fe2f0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/46abd4bf-bd8a-5525-9388-c938807fe2f0.json
48458229-1481-521a-8ee4-edcc2d7408bc | imported:semiconductor-atlas:red-admiral-rochfortbridge | vcc-site-a2932dfc186e6f2538c8 | imported:semiconductor-atlas:red-admiral-rochfortbridge | Red Admiral data centre campus, Rochfortbridge | Ireland | IE | 53.416 | -7.296 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Rochfortbridge village centroid from its Wikipedia article. The application covers several townlands around Rochfortbridge (Gneevebane, Oldtown, Farthingstown, Castlelost and Kiltotan, and Collinstown), but no cited source gives site coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 8d2bc043-b17a-55ab-9ace-cd8a44ea7a3a | proposed | 2026-10-09 | 4 | imported_documented_status | 8d2bc043-b17a-55ab-9ace-cd8a44ea7a3a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8d2bc043-b17a-55ab-9ace-cd8a44ea7a3a","notes":"Planning applicant.","party":"Red Admiral DC Limited","relationship_scope":"unknown","role":"developer","source_record_id":"red-admiral-rochfortbridge"},{"evidence_id":"641811ce-dd75-532f-97a4-5ecb7eb35f3f","notes":"Planning applicant.","party":"Red Admiral DC Limited","relationship_scope":"unknown","role":"developer","source_record_id":"red-admiral-rochfortbridge"},{"evidence_id":"641811ce-dd75-532f-97a4-5ecb7eb35f3f","notes":"The Westmeath Examiner says the development forms part of the group's wider plans; the corporate link to Red Admiral DC Limited is not stated.","party":"Lumcloon Energy Group","relationship_scope":"unknown","role":"developer","source_record_id":"red-admiral-rochfortbridge"},{"evidence_id":"8d2bc043-b17a-55ab-9ace-cd8a44ea7a3a","notes":"Planning authority that granted permission in June 2026.","party":"Westmeath County Council","relationship_scope":"unknown","role":"government","source_record_id":"red-admiral-rochfortbridge"},{"evidence_id":"641811ce-dd75-532f-97a4-5ecb7eb35f3f","notes":"Planning authority that granted permission in June 2026.","party":"Westmeath County Council","relationship_scope":"unknown","role":"government","source_record_id":"red-admiral-rochfortbridge"},{"evidence_id":"8d2bc043-b17a-55ab-9ace-cd8a44ea7a3a","notes":"Deciding third-party appeals against the permission.","party":"An Coimisiún Pleanála","relationship_scope":"unknown","role":"government","source_record_id":"red-admiral-rochfortbridge"},{"evidence_id":"641811ce-dd75-532f-97a4-5ecb7eb35f3f","notes":"Deciding third-party appeals against the permission.","party":"An Coimisiún Pleanála","relationship_scope":"unknown","role":"government","source_record_id":"red-admiral-rochfortbridge"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.pleanala.ie/en-ie/case/501596 | https://www.pleanala.ie/en-ie/case/501596 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Red Admiral data centre campus, Rochfortbridge as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"red-admiral-rochfortbridge"},"record":{"aliases":["Red Admiral DC"],"id":"red-admiral-rochfortbridge","last_reviewed":"2026-10-09","location":{"admin1":"County Westmeath","country":"IE","lat":53.416,"locality":"Rochfortbridge","lon":-7.296,"note":"Rochfortbridge village centroid from its Wikipedia article. The application covers several townlands around Rochfortbridge (Gneevebane, Oldtown, Farthingstown, Castlelost and Kiltotan, and Collinstown), but no cited source gives site coordinates.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-03","basis":"reported","metric":"investment","note":"Reported as the value of the Rochfortbridge data centre development.","qualifier":"exact","source_ids":["s2"],"unit":"EUR","value":1000000000},{"applies_to":"campus","as_of":"2026-07-03","basis":"reported","metric":"land_area","note":"Site including the solar farm, across several townlands.","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":600},{"applies_to":"campus","as_of":"2026-07-03","basis":"planned","metric":"buildings","note":"Six data centre units with data halls about 72 feet high.","qualifier":"exact","source_ids":["s2"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2026-07-03","basis":"planned","metric":"jobs_permanent","note":"Direct permanent jobs; about 1,000 indirect jobs were also cited for the five-year construction phase.","qualifier":"approximately","source_ids":["s2"],"unit":"count","value":760}],"milestones":[{"date":"2026-06","event":"permit_approved","kind":"actual","note":"Westmeath County Council granted ten-year permission subject to 32 conditions (council reference 2560344).","source_ids":["s2","s1"]},{"date":"2026-06-23","event":"other","kind":"actual","note":"Third-party appeals lodged with An Coimisiún Pleanála (case PL25M.501596); the case page gives 23 June 2026 as the lodged date. The Westmeath Examiner reports that one appeal was ruled invalid over its fee on 17 June.","source_ids":["s1","s2"]},{"date":"2026-10-27","event":"other","kind":"planned","note":"Date by which An Coimisiún Pleanála is due to decide the appeals.","source_ids":["s1","s2"]}],"name":"Red Admiral data centre campus, Rochfortbridge","notes":"Status date is the access date: the appeal board's undated case page still showed the appeal as lodged and undecided on 2026-10-09. No MW figure was found in the sources opened. Objectors argued the campus would burden the national grid, questioned its climate impact and visual effect, and said no emissions statement was provided. Separately, Lumcloon plans to seek changes to an approved energy storage facility to add a reserve gas-fired generator; the Westmeath Examiner does not say whether that facility is part of this campus.","parties":[{"name":"Red Admiral DC Limited","note":"Planning applicant.","role":"developer","source_ids":["s1","s2"]},{"name":"Lumcloon Energy Group","note":"The Westmeath Examiner says the development forms part of the group's wider plans; the corporate link to Red Admiral DC Limited is not stated.","role":"developer","source_ids":["s2"]},{"name":"Westmeath County Council","note":"Planning authority that granted permission in June 2026.","role":"government","source_ids":["s1","s2"]},{"name":"An Coimisiún Pleanála","note":"Deciding third-party appeals against the permission.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"The application includes a decentralised energy resource whose operation requires an EPA industrial emissions licence; its fuel is not stated in the sources opened.","source_ids":["s1","s2"],"type":"other"},{"description":"A solar farm is part of the development.","source_ids":["s2"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"An Coimisiún Pleanála","title":"Case reference PL25M.501596","type":"regulatory_filing","url":"https://www.pleanala.ie/en-ie/case/501596"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-03","publisher":"Westmeath Examiner","title":"Data centre appeals to An Coimisiún Pleanála","type":"news","url":"https://www.westmeathexaminer.ie/?p=128147"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Wikipedia","title":"Rochfortbridge","type":"other","url":"https://en.wikipedia.org/wiki/Rochfortbridge"}],"status":"proposed","status_as_of":"2026-10-09","status_source_ids":["s1","s2"],"summary":"Proposed six-unit data centre campus with a decentralised energy resource and a solar farm on a 600-acre site near Rochfortbridge, County Westmeath, Ireland. The applicant is Red Admiral DC Ltd, and the Westmeath Examiner says the development is part of the Lumcloon Energy Group's wider plans; it reports the project at EUR 1 billion. Westmeath County Council granted a ten-year permission with 32 conditions in early June 2026 despite more than 50 submissions. Third-party appeals were lodged with An Coimisiún Pleanála, with a decision due by 27 October 2026. The energy element needs an EPA industrial emissions licence.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8d2bc043-b17a-55ab-9ace-cd8a44ea7a3a","s2":"641811ce-dd75-532f-97a4-5ecb7eb35f3f","s3":"5c664a36-c14a-5422-9b77-7aac4bebadec"},"source_file":"datacenters/projects/red-admiral-rochfortbridge.json","source_record_id":"red-admiral-rochfortbridge","source_record_sha256":"ee1af68afd801bb6aea4f2522f3f30242d139695b9e1414b3cc5d5af0f880eb6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3e8aeb3449a05e45e952439811a65d975deb5567ede7299604b1a43a492bda0d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a2932dfc186e6f2538c8/#project-48458229-1481-521a-8ee4-edcc2d7408bc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/48458229-1481-521a-8ee4-edcc2d7408bc.json
484cf452-3a8f-5574-8003-a5b3f693c5d2 | curated:bitdeer-wenatchee-washington-campus:2026-ai-conversion-site-preparation | vcc-site-4ac69f22d359cc462f5b | curated:bitdeer-wenatchee-washington-campus | Bitdeer Wenatchee 2026 AI Conversion Site Preparation | United States | US | 47.4139 | -120.2093 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 626c5c59-9386-58ac-9de1-f81bc82d4900 | site_preparation | 2026-07-21 | 84 | authoritative_physical_status_update | 9bb3b9ad-0b64-5c9f-adc9-abc7463b1a61 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1899123/000121390026079816/ea029852701ex99-1.htm | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4ac69f22d359cc462f5b/#project-484cf452-3a8f-5574-8003-a5b3f693c5d2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/484cf452-3a8f-5574-8003-a5b3f693c5d2.json
48d82a4f-46ea-5641-a650-b6e147b30ae6 | imported:semiconductor-atlas:powerhouse-95-spotsylvania | vcc-site-6d5fe2fc2166ad27899f | imported:semiconductor-atlas:powerhouse-95-spotsylvania | PowerHouse 95 data center campus | United States | US | 38.18 | -77.65 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Sources say only that the campus is in Spotsylvania along the I-95 corridor near existing electrical infrastructure. The point is the Spotsylvania County coordinate from its Wikipedia article, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d440612d-86b8-51ec-96fc-7b670f03f886 | announced | 2026-10-09 | 4 | imported_documented_status | 5b280a15-6eba-5485-a6b5-07fd1b7c5915 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d440612d-86b8-51ec-96fc-7b670f03f886","notes":"Wholly owned by American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-95-spotsylvania"},{"evidence_id":"2bd6997a-8723-5dfc-a591-49bb888061d9","notes":"Wholly owned by American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-95-spotsylvania"},{"evidence_id":"5b280a15-6eba-5485-a6b5-07fd1b7c5915","notes":"Wholly owned by American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-95-spotsylvania"},{"evidence_id":"d440612d-86b8-51ec-96fc-7b670f03f886","notes":"Investment management firm and PowerHouse's joint venture partner; the land was acquired through the joint venture.","party":"Harrison Street","relationship_scope":"unknown","role":"investor","source_record_id":"powerhouse-95-spotsylvania"},{"evidence_id":"2bd6997a-8723-5dfc-a591-49bb888061d9","notes":"Investment management firm and PowerHouse's joint venture partner; the land was acquired through the joint venture.","party":"Harrison Street","relationship_scope":"unknown","role":"investor","source_record_id":"powerhouse-95-spotsylvania"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://powerhousedata.com/data-center/powerhouse-95 | https://convergedigest.com/powerhouse-plans-800-mw-data-center-campus-in-spotsylvania-va/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve PowerHouse 95 data center campus as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"powerhouse-95-spotsylvania"},"record":{"aliases":["PowerHouse 95","PH95","PH 95"],"id":"powerhouse-95-spotsylvania","last_reviewed":"2026-10-09","location":{"admin1":"Virginia","admin2":"Spotsylvania County","country":"US","lat":38.18,"lon":-77.65,"note":"Sources say only that the campus is in Spotsylvania along the I-95 corridor near existing electrical infrastructure. The point is the Spotsylvania County coordinate from its Wikipedia article, not the site.","precision":"admin2","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2024-01-25","basis":"planned","metric":"power_capacity","note":"Campus size as reported with the land purchase. The same reports describe three 300 MW substations, which would exceed this figure; they do not reconcile the two.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":800},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Maximum utility power listed on PowerHouse's undated campus page, accessed 2026-10-09.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s3"],"unit":"MW","value":900},{"applies_to":"phase","as_of":"2024-01-25","basis":"planned","metric":"power_capacity","note":"Expected by October 2025 according to Converge Digest; Lightwave gave October 2024 for the first substation coming online. The current campus page targets power delivery in Q3 2027.","phase_label":"First substation (initial delivery)","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2024-01-23","basis":"acquired","metric":"land_area","qualifier":"exact","source_ids":["s1","s2"],"unit":"acres","value":145},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"Acreage shown on the current campus page; the sources do not explain the increase from 145 acres.","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":227},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"Up to two stories each. In January 2024 Converge Digest described a design for four to eight powered shells.","qualifier":"up_to","source_ids":["s3"],"unit":"count","value":12},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Developable floor area listed on the campus page as 3.6M sq ft.","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":3600000}],"milestones":[{"date":"2024-01-23","event":"site_acquired","kind":"actual","note":"PowerHouse announced on this date that it had completed the purchase of 145 acres through the Harrison Street joint venture.","source_ids":["s1","s2"]},{"date":"2027-Q3","event":"other","kind":"planned","note":"Power delivery target on the campus page, which also lists construction and delivery running from Q2 2024 to Q4 2027 and, inconsistently, a Q3 2026 delivery date.","source_ids":["s3"]}],"name":"PowerHouse 95 data center campus","notes":"Status rests on PowerHouse's undated living campus page, so status_as_of is the access date. The page's construction window starting Q2 2024 suggests site work may have begun, but no dated source confirming a construction start or a tenant could be opened, so the status is kept at announced. The 2024 reports describe the campus as aimed at hyperscale users in northern Virginia.","parties":[{"name":"PowerHouse Data Centers","note":"Wholly owned by American Real Estate Partners (AREP).","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Harrison Street","note":"Investment management firm and PowerHouse's joint venture partner; the land was acquired through the joint venture.","role":"investor","source_ids":["s1","s2"]}],"power_sources":[{"description":"Utility power through substations: three 300 MW substations were planned in 2024; the utility is not named in the cited sources.","source_ids":["s1","s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20240301025938/https://convergedigest.com/powerhouse-plans-800-mw-data-center-campus-in-spotsylvania-va/","id":"s1","published":"2024-01-25","publisher":"Converge Digest","title":"PowerHouse plans 800 MW data center campus in Spotsylvania, VA","type":"trade_press","url":"https://convergedigest.com/powerhouse-plans-800-mw-data-center-campus-in-spotsylvania-va/"},{"accessed":"2026-10-09","id":"s2","published":"2024-01-30","publisher":"Lightwave","title":"PowerHouse Data Centers announces purchase of 145 acres in Spotsylvania, Va. for PowerHouse 95 campus","type":"trade_press","url":"https://www.lightwaveonline.com/data-center/article/14304356/powerhouse-data-centers-announces-purchase-of-145-acres-in-spotsylvania-va-for-powerhouse-95-campus"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260918144226/https://www.powerhousedata.com/data-center/powerhouse-95","id":"s3","published":null,"publisher":"PowerHouse Data Centers","title":"PowerHouse 95","type":"company","url":"https://powerhousedata.com/data-center/powerhouse-95"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260822162111/https://en.wikipedia.org/wiki/Spotsylvania_County,_Virginia","id":"s4","published":null,"publisher":"Wikipedia","title":"Spotsylvania County, Virginia","type":"other","url":"https://en.wikipedia.org/wiki/Spotsylvania_County,_Virginia"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s3"],"summary":"Campus aimed at hyperscale users, planned by PowerHouse Data Centers, a unit of American Real Estate Partners, along the I-95 corridor in Spotsylvania County, Virginia, through a joint venture with Harrison Street. PowerHouse completed the purchase of 145 acres in January 2024 and described an 800 MW campus served by three 300 MW substations, the first meant to deliver 150 MW. Its current campus page lists 227 acres, up to 900 MW of utility power, up to 12 buildings of up to two stories and about 3.6 million sq ft, with power delivery targeted for Q3 2027.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d440612d-86b8-51ec-96fc-7b670f03f886","s2":"2bd6997a-8723-5dfc-a591-49bb888061d9","s3":"5b280a15-6eba-5485-a6b5-07fd1b7c5915","s4":"63079fb8-ed1a-5481-9439-63c2f66005e1"},"source_file":"datacenters/projects/powerhouse-95-spotsylvania.json","source_record_id":"powerhouse-95-spotsylvania","source_record_sha256":"f0b18d16b3585dbcbd5b508f44acc06b6752ef0ee16c2c6b445248f02291d9c6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b7af86891ac1f351a9a3b7538e7808c52342d8f3c19f5ad1091aba8b2e211671"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6d5fe2fc2166ad27899f/#project-48d82a4f-46ea-5641-a650-b6e147b30ae6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/48d82a4f-46ea-5641-a650-b6e147b30ae6.json
48eb54d5-dd3f-51a3-aeed-1ddce1949763 | curated:adaniconnex-pune-data-center-campus:pnq04-current-build | vcc-site-52b1e1c3038357306a39 | curated:adaniconnex-pune-data-center-campus | AdaniConneX Pune PNQ04 Current Build | India | IN | 18.6467 | 73.8073 | Point | project | direct_geometry | official_project_report_coordinate_to_point | official_source_reported_project_reference_point | official_source | project_locator | Official source-reported point used only to locate the PNQ04 project. It is not a project centroid, footprint, parcel, building outline, construction extent, campus boundary, or survey-accuracy claim. |  | The report does not identify the coordinate's datum, reference feature, collection method, or horizontal accuracy. | 9e5f7eb0-994d-534d-8715-b16378b71787 | under_construction | 2026-06-01 | 134 | authoritative_physical_status_update | f3905471-9d3d-5be1-9e61-e78c956f4384 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://resources.adaniconnex.com/blog/scaling-indias-data-centres-responsibly-for-the-ai-era-bridging-people-planet-and-growth | https://www.adaniconnex.com/-/media/Project/AdaniConneX/AdaniConneX-AboutUs-Assets/Certifications/Post-EC-compliance-report-PNQ26--with-Anneure.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-52b1e1c3038357306a39/#project-48eb54d5-dd3f-51a3-aeed-1ddce1949763 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/48eb54d5-dd3f-51a3-aeed-1ddce1949763.json
493361d4-686f-5f75-af07-7f95dcf81323 | imported:semiconductor-atlas:xai-macrohardrr-southaven | vcc-site-64d29806f5007969e3b9 | imported:semiconductor-atlas:xai-macrohardrr-southaven | xAI MACROHARDRR data center (Southaven) | United States | US | 34.9935 | -90.0342 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Center of the OpenStreetMap building tagged 'xAI Macrohardrr' on Stateline Road West, taken from this project's OpenStreetMap data center layer (no geocoder call), about 0.5 km south of the Colossus 2 building. This matches Cleanview's address of 2400 Stateline Road, Southaven, and WREG's description of the warehouse as just south of Colossus 2. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | dbe7d792-d348-5083-ba1b-746c73feceff | operational | 2026-07-31 | 74 | imported_documented_status | c52407e5-1780-5f03-8e8f-48c0b2f8a1e6 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"dbe7d792-d348-5083-ba1b-746c73feceff","notes":null,"party":"xAI","relationship_scope":"unknown","role":"developer","source_record_id":"xai-macrohardrr-southaven"},{"evidence_id":"e95c5c49-e364-5a92-b52b-4559e4b1ae2b","notes":null,"party":"xAI","relationship_scope":"unknown","role":"developer","source_record_id":"xai-macrohardrr-southaven"},{"evidence_id":"dbe7d792-d348-5083-ba1b-746c73feceff","notes":"Approved the project for the state Data Center Incentive sales and use tax exemption.","party":"Mississippi Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"xai-macrohardrr-southaven"},{"evidence_id":"dbe7d792-d348-5083-ba1b-746c73feceff","notes":"Supports the project through a fee-in-lieu agreement.","party":"City of Southaven","relationship_scope":"unknown","role":"government","source_record_id":"xai-macrohardrr-southaven"},{"evidence_id":"dbe7d792-d348-5083-ba1b-746c73feceff","notes":"Supports the project through a fee-in-lieu agreement.","party":"DeSoto County","relationship_scope":"unknown","role":"government","source_record_id":"xai-macrohardrr-southaven"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.actionnews5.com/2026/07/31/xai-announces-fourth-data-center-turbines-be-removed-southaven-site/ | https://governorreeves.ms.gov/tech-leader-xai-investing-more-than-20-billion-in-southaven/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve xAI MACROHARDRR data center (Southaven) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"xai-macrohardrr-southaven","source_relations":[{"reason":"Colossus 2 Memphis and MACROHARDRR Southaven are separately named facilities in Tennessee and Mississippi; nearby coordinates do not merge them.","relationship":"separate_nearby_facilities","source_id":"xai-colossus-2-memphis"}]},"record":{"aliases":["MACROHARDRR","Macroharder","Macro-harder"],"id":"xai-macrohardrr-southaven","last_reviewed":"2026-10-09","location":{"admin1":"Mississippi","admin2":"DeSoto County","country":"US","lat":34.9935,"locality":"Southaven","lon":-90.0342,"note":"Center of the OpenStreetMap building tagged 'xAI Macrohardrr' on Stateline Road West, taken from this project's OpenStreetMap data center layer (no geocoder call), about 0.5 km south of the Colossus 2 building. This matches Cleanview's address of 2400 Stateline Road, Southaven, and WREG's description of the warehouse as just south of Colossus 2.","precision":"approximate_site","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-08","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1","s2"],"unit":"USD","value":20000000000},{"applies_to":"campus","as_of":"2026-01-08","basis":"under_construction","metric":"floor_area","note":"Size of the warehouse being retrofitted; Converge Digest and Cleanview give about 810,000 square feet and WREG gives 800,000.","qualifier":"approximately","source_ids":["s3","s5","s2"],"unit":"sq_ft","value":810000},{"accelerator_model":"NVIDIA GB300","applies_to":"campus","as_of":"2026-07-31","basis":"installed","metric":"accelerators","note":"Elon Musk's figure as relayed by WMC in July 2026; not confirmed in a company filing. No Colossus 2 figure is repeated here.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":220000}],"milestones":[{"date":"2025-12","event":"site_acquired","kind":"actual","note":"Musk disclosed the purchase of an 800,000-square-foot Southaven warehouse on December 30, 2025; the governor's release says xAI bought an existing building for the project.","source_ids":["s2","s1"]},{"date":"2026-01-08","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2026-02","event":"first_operational","kind":"planned","note":"Target stated at the January 2026 announcement; no source reviewed confirms the actual start date.","source_ids":["s1","s3"]}],"name":"xAI MACROHARDRR data center (Southaven)","notes":"Status is inferred from a July 2026 WMC report that calls Macro-harder an existing site equipped with 220,000 GB300 GPUs, relaying Elon Musk; no source reviewed confirms when operations began. Converge Digest labels the building 'Colossus 2 (MACROHARDRR)', and analyst estimates for Colossus 2 (xai-colossus-2-memphis) may include it; no Colossus 2 figure is repeated here. The 2 GW figure in the announcements refers to xAI's combined Colossus compute, not this building alone.","parties":[{"name":"xAI","role":"developer","source_ids":["s1","s2"]},{"name":"Mississippi Development Authority","note":"Approved the project for the state Data Center Incentive sales and use tax exemption.","role":"government","source_ids":["s1"]},{"name":"City of Southaven","note":"Supports the project through a fee-in-lieu agreement.","role":"government","source_ids":["s1"]},{"name":"DeSoto County","note":"Supports the project through a fee-in-lieu agreement.","role":"government","source_ids":["s1"]}],"power_sources":[],"related_ids":["xai-colossus-memphis","xai-colossus-2-memphis"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-08","publisher":"Office of Governor Tate Reeves","title":"Tech leader xAI investing more than $20 billion in Southaven","type":"government","url":"https://governorreeves.ms.gov/tech-leader-xai-investing-more-than-20-billion-in-southaven/"},{"accessed":"2026-10-09","id":"s2","published":"2026-01-08","publisher":"WREG (via Yahoo News)","title":"xAI investing $20B in Southaven, Mississippi facility, governor says","type":"news","url":"https://www.yahoo.com/news/articles/ms-governor-confirms-major-announcement-173629625.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260109084929/https://convergedigest.com/xai-commits-20b-to-2-gw-ai-data-center-in-mississippi/","id":"s3","published":"2026-01-08","publisher":"Converge Digest","title":"xAI Commits $20B to 2-GW AI Data Center in Mississippi","type":"trade_press","url":"https://convergedigest.com/xai-commits-20b-to-2-gw-ai-data-center-in-mississippi/"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-31","publisher":"WMC Action News 5","title":"xAI announces fourth data center; turbines to be removed from Southaven site","type":"news","url":"https://www.actionnews5.com/2026/07/31/xai-announces-fourth-data-center-turbines-be-removed-southaven-site/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Cleanview","title":"Colossus 1 & 2 ¦ Behind-the-Meter Data Centers","type":"analyst","url":"https://cleanview.co/reports/behind-the-meter-data-centers/full-report/colossus"}],"status":"operational","status_as_of":"2026-07-31","status_source_ids":["s4"],"summary":"Third xAI data center in the Memphis area, made by retrofitting a warehouse of roughly 800,000 square feet that xAI bought in late 2025 in Southaven, Mississippi, just south of Colossus 2 across the state line. Mississippi's governor announced it in January 2026 as an investment of more than $20 billion, the largest economic development project in state history, supported by a state sales and use tax exemption and local fee-in-lieu agreements. Musk said it would lift Colossus training compute to about 2 GW, and a July 2026 report relaying his comments said it holds 220,000 NVIDIA GB300 GPUs.","workloads":["ai_training"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"dbe7d792-d348-5083-ba1b-746c73feceff","s2":"e95c5c49-e364-5a92-b52b-4559e4b1ae2b","s3":"b5704d88-91a8-5275-b39b-7734d91b39fc","s4":"c52407e5-1780-5f03-8e8f-48c0b2f8a1e6","s5":"4f86e4e6-8bc3-5dbf-bd88-d502ab8f697f"},"source_file":"datacenters/projects/xai-macrohardrr-southaven.json","source_record_id":"xai-macrohardrr-southaven","source_record_sha256":"2572c4fde54bafc4d980d59bc119cb0b9bafddbeb07826d0fda56041cc74e91d","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"abf3551fad31d958a766d3a571a49c602f4511d97258795493fb0411254fead0"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-64d29806f5007969e3b9/#project-493361d4-686f-5f75-af07-7f95dcf81323 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/493361d4-686f-5f75-af07-7f95dcf81323.json
4a0d8f6f-b848-5650-a479-4f0caee97fa1 | imported:semiconductor-atlas:synapse-olds | vcc-site-7a7046b12f3789bb93a5 | imported:semiconductor-atlas:synapse-olds | Synapse Data Center (Olds) | Canada | CA | 51.7928 | -114.1067 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from the Olds Wikipedia page. The developer places the site in the town's industrial area at the northeast corner of Highways 2A and 27 (SW and NW quarters of Section 4-33-1-W5M). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3bb1bb6d-c4d0-57ac-9eb0-dc81963e6429 | proposed | 2026-10-09 | 4 | imported_documented_status | ff544e8d-d896-5594-bdd1-4d68196f843c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3bb1bb6d-c4d0-57ac-9eb0-dc81963e6429","notes":null,"party":"Synapse Real Estate Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"synapse-olds"},{"evidence_id":"ff544e8d-d896-5594-bdd1-4d68196f843c","notes":null,"party":"Synapse Real Estate Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"synapse-olds"},{"evidence_id":"1caa8d44-b6d4-5345-b24c-76b1cbaa5026","notes":null,"party":"Synapse Real Estate Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"synapse-olds"},{"evidence_id":"ff544e8d-d896-5594-bdd1-4d68196f843c","notes":"Registered as an intervener in the AUC proceeding, commissioned peer reviews of the air quality and noise studies and filed a statement of concern on the environmental application.","party":"Town of Olds","relationship_scope":"unknown","role":"government","source_record_id":"synapse-olds"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://engage.olds.ca/data-centre-development | https://www.olds.ca/media/y3cp0anv/synapse-data-center-project-information-package.pdf | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Synapse Data Center (Olds) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"synapse-olds"},"record":{"aliases":["Synapse Data Center Project","Synapse AI Data Center Olds"],"id":"synapse-olds","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","country":"CA","lat":51.79278,"locality":"Olds (northeast corner of Highways 2A and 27)","lon":-114.10667,"note":"Town coordinates from the Olds Wikipedia page. The developer places the site in the town's industrial area at the northeast corner of Highways 2A and 27 (SW and NW quarters of Section 4-33-1-W5M).","precision":"locality","source_ids":["s1","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-09","basis":"planned","metric":"power_capacity","note":"Data centre size; the sources do not say whether this is IT or total facility load.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-01-27","basis":"planned","metric":"power_capacity","note":"Proposed natural gas-fired plant using combined-cycle gas turbines on about 10% of the site.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":1400},{"applies_to":"campus","as_of":"2026-01-27","basis":"planned","metric":"jobs_construction","qualifier":"exact","source_ids":["s1"],"unit":"count","value":2000},{"applies_to":"campus","as_of":"2026-01-27","basis":"planned","metric":"jobs_permanent","qualifier":"at_least","source_ids":["s1"],"unit":"count","value":1000}],"milestones":[{"date":"2026-01","event":"announced","kind":"actual","note":"Synapse began public engagement in late January 2026 with a project information package for neighbours.","source_ids":["s1"]},{"date":"2026-03","event":"other","kind":"actual","note":"Reported on 9 March 2026: the AUC rejected the first power plant application, citing inadequate consultation, an environmental report that looked unfinished and signs that not all planned generating equipment was included.","source_ids":["s3"]},{"date":"2026-08-17","event":"other","kind":"actual","note":"AUC denied the power generation application in proceeding 30732, finding the site unsuitable for the proposed development.","source_ids":["s2"]}],"name":"Synapse Data Center (Olds)","notes":"Status stays proposed rather than paused: the August 2026 AUC denial covers the power plant application, and no source reports Synapse halting, withdrawing or appealing the project. It rests on the Town of Olds' undated engagement page, read 2026-10-09, which reports the AUC denial of 17 August 2026 and an Alberta environmental (EPEA) application still in progress. After the first rejection Synapse said it intended to reapply; no response to the August decision was found. The AUC regulates the power plant, not the data centre itself. The developer called it a multi-billion dollar investment without giving a figure.","parties":[{"name":"Synapse Real Estate Corp.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Town of Olds","note":"Registered as an intervener in the AUC proceeding, commissioned peer reviews of the air quality and noise studies and filed a statement of concern on the environmental application.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"A proposed 1.4 GW combined-cycle gas plant on site, with the data centre as the sole consumer of its output; the AUC denied the plant application in August 2026.","source_ids":["s1","s2"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-27","publisher":"Synapse Real Estate Corp. (hosted by the Town of Olds)","title":"Synapse Data Center Project Information Package","type":"company","url":"https://www.olds.ca/media/y3cp0anv/synapse-data-center-project-information-package.pdf"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Town of Olds","title":"Current Data Centre Projects in Olds","type":"government","url":"https://engage.olds.ca/data-centre-development"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-09","publisher":"The Logic","title":"Alberta regulator rejects proposal for massive data centre in Olds over deficient application","type":"news","url":"https://thelogic.co/briefing/alberta-regulator-rejects-proposal-for-massive-data-centre-in-olds-over-deficient-application/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Olds, Alberta","type":"other","url":"https://en.wikipedia.org/wiki/Olds,_Alberta"}],"status":"proposed","status_as_of":"2026-10-09","status_source_ids":["s2"],"summary":"Synapse Real Estate Corp. proposed a 1 GW AI data centre in the Town of Olds, Alberta, at the northeast corner of Highways 2A and 27, to be the sole user of a 1.4 GW on-site combined-cycle gas plant. The Alberta Utilities Commission rejected a first, deficient plant application in March 2026, and on 17 August 2026 it denied the application in proceeding 30732, finding the site unsuitable for the development. An environmental approval application with Alberta's environment ministry was still listed as in progress, and no development permit had been filed with the town.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3bb1bb6d-c4d0-57ac-9eb0-dc81963e6429","s2":"ff544e8d-d896-5594-bdd1-4d68196f843c","s3":"1caa8d44-b6d4-5345-b24c-76b1cbaa5026","s4":"637a9084-9227-566f-8c8d-9491bfbd98a8"},"source_file":"datacenters/projects/synapse-olds.json","source_record_id":"synapse-olds","source_record_sha256":"14fc93e0f111163a184e77ec2774f5d985878a5d18f5faf2fad82a140bde792d","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"e7f226b1cc6f5ca84ee1dd889e237a8004d4a142986dcf1c4583e737194bb93d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7a7046b12f3789bb93a5/#project-4a0d8f6f-b848-5650-a479-4f0caee97fa1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4a0d8f6f-b848-5650-a479-4f0caee97fa1.json
4a2847d7-f84f-5f89-a4c2-ee832e1f6cad | imported:semiconductor-atlas:project-sail-coweta-county | vcc-site-fcd641148c4f61598efc | imported:semiconductor-atlas:project-sail-coweta-county | Project Sail (Prologis data center campus, Coweta County) | United States | US | 33.376 | -84.788 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of Sargent (s5). The river group's fact sheet (s1) places the site in rural Sargent about 7 miles northwest of Newnan, with Wahoo Creek crossing the property; no parcel coordinates were found. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2866b764-c7b1-5435-8585-2f4a496a00f3 | announced | 2026-04-09 | 187 | imported_documented_status | 5a55722f-e850-58d1-b073-deb2fa1d1ba2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2866b764-c7b1-5435-8585-2f4a496a00f3","notes":null,"party":"Prologis","relationship_scope":"unknown","role":"developer","source_record_id":"project-sail-coweta-county"},{"evidence_id":"5a55722f-e850-58d1-b073-deb2fa1d1ba2","notes":null,"party":"Prologis","relationship_scope":"unknown","role":"developer","source_record_id":"project-sail-coweta-county"},{"evidence_id":"2866b764-c7b1-5435-8585-2f4a496a00f3","notes":"Original applicant for the rezoning. In June 2025 Prologis was reported to be set to buy the site from Atlas, with the deal not yet closed; later sources describe Prologis as the developer.","party":"Atlas Development LLC","relationship_scope":"unknown","role":"developer","source_record_id":"project-sail-coweta-county"},{"evidence_id":"f5d30e8a-cf3f-5526-ac8b-19c903e8420c","notes":"Original applicant for the rezoning. In June 2025 Prologis was reported to be set to buy the site from Atlas, with the deal not yet closed; later sources describe Prologis as the developer.","party":"Atlas Development LLC","relationship_scope":"unknown","role":"developer","source_record_id":"project-sail-coweta-county"},{"evidence_id":"77ada6db-09f8-5dbb-8a0c-4e844e3b1ef9","notes":"Prologis says Georgia Power has confirmed it can serve the campus.","party":"Georgia Power","relationship_scope":"unknown","role":"utility","source_record_id":"project-sail-coweta-county"},{"evidence_id":"2866b764-c7b1-5435-8585-2f4a496a00f3","notes":"Water and sewer provider.","party":"Coweta County Water & Sewerage Authority","relationship_scope":"unknown","role":"utility","source_record_id":"project-sail-coweta-county"},{"evidence_id":"77ada6db-09f8-5dbb-8a0c-4e844e3b1ef9","notes":"Water and sewer provider.","party":"Coweta County Water & Sewerage Authority","relationship_scope":"unknown","role":"utility","source_record_id":"project-sail-coweta-county"},{"evidence_id":"5a55722f-e850-58d1-b073-deb2fa1d1ba2","notes":"Approved the rezoning by a 3-2 vote; county staff had found it inconsistent with the comprehensive plan.","party":"Coweta County","relationship_scope":"unknown","role":"government","source_record_id":"project-sail-coweta-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://propmodo.com/?p=179099 | https://chattahoochee.org/wp-content/uploads/2026/03/Project-Sail-Fact-Sheet-March-2026.pdf | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Project Sail (Prologis data center campus, Coweta County) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"project-sail-coweta-county"},"record":{"aliases":["Project Sail","Prologis Coweta County data center campus"],"id":"project-sail-coweta-county","last_reviewed":"2026-10-09","location":{"admin1":"Georgia","admin2":"Coweta County","country":"US","lat":33.376,"locality":"Sargent","lon":-84.788,"note":"Coordinates are the Wikipedia centroid of Sargent (s5). The river group's fact sheet (s1) places the site in rural Sargent about 7 miles northwest of Newnan, with Wahoo Creek crossing the property; no parcel coordinates were found.","precision":"locality","source_ids":["s1","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-09","basis":"planned","metric":"power_capacity","note":"Trade press estimate of the campus's continuous power demand, first reported for the 13-building plan in 2025 and repeated at the April 2026 rezoning; neither source says whether it is IT or total load. Chattahoochee Riverkeeper's fact sheet (s1), an environmental group's figure, puts whole-campus demand at peak operation and full build-out at 910 MW. Prologis's project site gives no capacity.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3","s4"],"unit":"MW","value":900},{"applies_to":"campus","as_of":"2026-04-09","basis":"reported","metric":"investment","note":"Reported as the potential value of the campus, first for the 13-building plan in 2025 and again at the April 2026 rezoning. No investment figure appears on the Prologis project site.","qualifier":"exact","source_ids":["s3","s4"],"unit":"USD","value":17000000000},{"applies_to":"campus","as_of":"2026-03-26","basis":"reported","metric":"land_area","note":"Sources give 829, 830 and 831 acres.","qualifier":"approximately","source_ids":["s1","s3","s4"],"unit":"acres","value":830},{"applies_to":"campus","as_of":"2026-04-09","basis":"planned","metric":"buildings","note":"Reduced from 13 buildings in the plan reported in 2025.","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"count","value":9},{"applies_to":"campus","as_of":"2026-03-26","basis":"planned","metric":"floor_area","note":"Prologis says total floor area fell by 12% from the earlier plan, which trade press in 2025 put at nearly 5 million square feet.","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"sq_ft","value":4340000}],"milestones":[{"date":"2025-01","event":"announced","kind":"actual","note":"The river group says the project was first disclosed in early 2025 and lists Atlanta press coverage of the proposal dated 3 January 2025.","source_ids":["s1"]},{"date":"2025-05","event":"other","kind":"actual","note":"Coweta County imposed a 180-day moratorium on data center rezonings and permits while it rewrote its rules, holding up the application.","source_ids":["s3"]},{"date":"2026-04","event":"zoning_approved","kind":"actual","note":"Coweta County approved the rezoning 3-2, as reported on 9 April 2026; county staff had found it inconsistent with the comprehensive plan.","source_ids":["s4"]}],"name":"Project Sail (Prologis data center campus, Coweta County)","notes":"No report after the April 2026 rezoning of a closed land purchase or construction start was found. Prologis's project site is undated; it describes closed-loop air cooling without evaporative cooling, up to about 300,000 gallons of water a day at peak, and a tax estimate that assumes full build-out in 10 years. The 910 MW figure is Chattahoochee Riverkeeper's, an environmental group, not Prologis's; the metric uses the trade press estimate of about 900 MW instead.","parties":[{"name":"Prologis","role":"developer","source_ids":["s1","s4"]},{"name":"Atlas Development LLC","note":"Original applicant for the rezoning. In June 2025 Prologis was reported to be set to buy the site from Atlas, with the deal not yet closed; later sources describe Prologis as the developer.","role":"developer","source_ids":["s1","s3"]},{"name":"Georgia Power","note":"Prologis says Georgia Power has confirmed it can serve the campus.","role":"utility","source_ids":["s2"]},{"name":"Coweta County Water & Sewerage Authority","note":"Water and sewer provider.","role":"utility","source_ids":["s1","s2"]},{"name":"Coweta County","note":"Approved the rezoning by a 3-2 vote; county staff had found it inconsistent with the comprehensive plan.","role":"government","source_ids":["s4"]}],"power_sources":[{"description":"Georgia Power supply; Prologis says the utility has confirmed capacity. The site lies near Georgia Power's Plant Yates, which trade press cites as a factor in choosing the land.","source_ids":["s2","s3","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260825081713/https://chattahoochee.org/wp-content/uploads/2026/03/Project-Sail-Fact-Sheet-March-2026.pdf","id":"s1","published":"2026-03-26","publisher":"Chattahoochee Riverkeeper","title":"Coweta County Project Sail Data Center FAQ","type":"other","url":"https://chattahoochee.org/wp-content/uploads/2026/03/Project-Sail-Fact-Sheet-March-2026.pdf"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Prologis","title":"Project Sail, Coweta County","type":"company","url":"https://www.cowetaprojectsail.com/coweta-lp/"},{"accessed":"2026-10-09","id":"s3","published":"2025-06-11","publisher":"Telecom Review Americas","title":"A Massive Data Center Project Near Atlanta","type":"trade_press","url":"https://www.telecomreviewamericas.com/articles/wholesale-and-capacity/a-massive-data-center-project-near-atlanta/"},{"accessed":"2026-10-09","id":"s4","published":"2026-04-09","publisher":"Propmodo","title":"Prologis Wins Approval for Massive Georgia Data Center Project","type":"trade_press","url":"https://propmodo.com/?p=179099"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Sargent, Georgia","type":"other","url":"https://en.wikipedia.org/wiki/Sargent,_Georgia"}],"status":"announced","status_as_of":"2026-04-09","status_source_ids":["s4"],"summary":"Proposed hyperscale data center campus on roughly 830 acres in rural Sargent, about 7 miles northwest of Newnan in Coweta County, Georgia, near Georgia Power's Plant Yates. Atlas Development originally proposed the project, disclosed in early 2025 as a 13-building plan reported at USD 17 billion; Prologis took over development and cut the plan to nine buildings with about 4.34 million square feet. Trade press estimates the campus could need about 900 MW; Chattahoochee Riverkeeper, an environmental group, puts peak demand at full build-out at 910 MW. Coweta County approved the rezoning 3-2 in April 2026 after a moratorium and sustained local opposition.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2866b764-c7b1-5435-8585-2f4a496a00f3","s2":"77ada6db-09f8-5dbb-8a0c-4e844e3b1ef9","s3":"f5d30e8a-cf3f-5526-ac8b-19c903e8420c","s4":"5a55722f-e850-58d1-b073-deb2fa1d1ba2","s5":"adce4de0-c80b-5650-97a3-9f6dbee82134"},"source_file":"datacenters/projects/project-sail-coweta-county.json","source_record_id":"project-sail-coweta-county","source_record_sha256":"83972926247b9a72f27b4efd57a7891fdbfa7bef75f39efc5ace7d7bd6f0157a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"cf11e23564534700cd813ca376c5c4d39eec80181d8ef3f5be83b26b71083b69"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fcd641148c4f61598efc/#project-4a2847d7-f84f-5f89-a4c2-ee832e1f6cad | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4a2847d7-f84f-5f89-a4c2-ee832e1f6cad.json
4a2a09d1-1ace-5ff8-a80f-89996cda5799 | imported:semiconductor-atlas:rowan-project-temple | vcc-site-998792d68106140776c0 | imported:semiconductor-atlas:rowan-project-temple | Rowan Project Temple | United States | US | 31.1056 | -97.4208 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Temple, Texas. Bisnow places the 707-acre campus near Bob White Road and Lorraine Avenue, and Rowan places it in east Temple, so the site lies east of this point. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 33a59a67-e62e-5348-8fbb-5fc44302a000 | under_construction | 2026-05-29 | 137 | imported_documented_status | 0573a8b5-aea9-50f4-8ac3-b2cbe830d5df | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"13b41dff-6c36-562b-a775-d58b65d98d2e","notes":null,"party":"Rowan Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"rowan-project-temple"},{"evidence_id":"0573a8b5-aea9-50f4-8ac3-b2cbe830d5df","notes":null,"party":"Rowan Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"rowan-project-temple"},{"evidence_id":"33a59a67-e62e-5348-8fbb-5fc44302a000","notes":null,"party":"Rowan Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"rowan-project-temple"},{"evidence_id":"13b41dff-6c36-562b-a775-d58b65d98d2e","notes":null,"party":"Oncor","relationship_scope":"unknown","role":"utility","source_record_id":"rowan-project-temple"},{"evidence_id":"13b41dff-6c36-562b-a775-d58b65d98d2e","notes":"City council approved annexation and zoning and is party to Rowan's water infrastructure contribution.","party":"City of Temple","relationship_scope":"unknown","role":"government","source_record_id":"rowan-project-temple"},{"evidence_id":"f451982e-8599-5e46-b6ed-09eda42dfebf","notes":"City council approved annexation and zoning and is party to Rowan's water infrastructure contribution.","party":"City of Temple","relationship_scope":"unknown","role":"government","source_record_id":"rowan-project-temple"},{"evidence_id":"13b41dff-6c36-562b-a775-d58b65d98d2e","notes":"Commissioners Court approved the project unanimously, per Rowan.","party":"Bell County","relationship_scope":"unknown","role":"government","source_record_id":"rowan-project-temple"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://rowan.com/rowan-closes-3b-green-financing-for-turnkey-hyperscale-campus-in-high-growth-texas-market/ | https://www.bisnow.com/news/austin-san-antonio/data-center/sustainable-developer-bringing-data-center-campus-to-temple-134759 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Rowan Project Temple as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"rowan-project-temple","source_relations":[{"reason":"Meta operating Temple campus and Rowan Project Temple are separately named developments; both use the Temple city point.","relationship":"separate_named_developments","source_id":"meta-temple-texas"}]},"record":{"aliases":["Project Temple","Rowan Temple data center campus"],"id":"rowan-project-temple","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Bell County","country":"US","lat":31.1056,"locality":"Temple","lon":-97.4208,"note":"Wikipedia coordinates for Temple, Texas. Bisnow places the 707-acre campus near Bob White Road and Lorraine Avenue, and Rowan places it in east Temple, so the site lies east of this point.","precision":"locality","source_ids":["s4","s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-27","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-01-05","basis":"announced","metric":"investment","note":"Rowan's stated minimum investment in Central Texas when construction began.","qualifier":"at_least","source_ids":["s1"],"unit":"USD","value":700000000},{"applies_to":"campus","as_of":"2026-05-27","basis":"reported","metric":"investment","note":"Debt financing announced as closed for the Temple campus, not a total project cost.","qualifier":"approximately","source_ids":["s2","s4"],"unit":"USD","value":3000000000},{"applies_to":"campus","as_of":"2026-05-29","basis":"planned","metric":"land_area","note":"Rowan describes the site as roughly 700 acres.","qualifier":"exact","source_ids":["s4"],"unit":"acres","value":707},{"applies_to":"campus","as_of":"2026-05-29","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s4"],"unit":"sq_ft","value":1000000},{"applies_to":"campus","as_of":"2026-09-17","basis":"planned","metric":"buildings","note":"Rowan calls the Lasso Building the third and final building of Project Temple.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2026-01-05","basis":"planned","metric":"jobs_construction","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":600},{"applies_to":"campus","as_of":"2026-01-05","basis":"planned","metric":"jobs_permanent","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":40}],"milestones":[{"date":"2025","event":"zoning_approved","kind":"actual","note":"Temple City Council gave final approval to annex and zone the land. The year is derived: Bisnow's May 2026 article says the approval came last year.","source_ids":["s4"]},{"date":"2026-01","event":"construction_started","kind":"actual","note":"Rowan's 5 January 2026 release reported construction under way; its May 2026 release says it broke ground earlier in the year.","source_ids":["s1","s2"]},{"date":"2026-05-27","event":"other","kind":"actual","note":"Rowan announced it had closed nearly USD 3 billion of green debt financing for the campus; the release gives no separate closing date.","source_ids":["s2"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Rowan expects operations in 2027; Bisnow, writing in May 2026, expects construction to finish the following year.","source_ids":["s1","s4"]}],"name":"Rowan Project Temple","parties":[{"name":"Rowan Digital Infrastructure","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Oncor","role":"utility","source_ids":["s1"]},{"name":"City of Temple","note":"City council approved annexation and zoning and is party to Rowan's water infrastructure contribution.","role":"government","source_ids":["s1","s3"]},{"name":"Bell County","note":"Commissioners Court approved the project unanimously, per Rowan.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Power secured through a partnership with Oncor.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-05","publisher":"Rowan Digital Infrastructure","title":"Rowan Powers Texas Growth as Construction Begins on 300 MW Temple Data Center","type":"company","url":"https://rowan.com/rowan-powers-texas-growth-as-construction-begins-on-300-mw-temple-data-center/"},{"accessed":"2026-10-09","id":"s2","published":"2026-05-27","publisher":"Rowan Digital Infrastructure","title":"Rowan Closes $3B Green Financing for Turnkey Hyperscale Campus in High-Growth Texas Market","type":"company","url":"https://rowan.com/rowan-closes-3b-green-financing-for-turnkey-hyperscale-campus-in-high-growth-texas-market/"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-17","publisher":"Rowan Digital Infrastructure","title":"Rowan to Invest $38 Million in Temple Water Infrastructure and Sammons Community Center","type":"company","url":"https://rowan.com/rowan-to-invest-38-million-in-temple-water-infrastructure-and-sammons-community-center/"},{"accessed":"2026-10-09","id":"s4","published":"2026-05-29","publisher":"Bisnow","title":"Colorado Developer Secures $3B For Data Center Campus North Of Austin","type":"trade_press","url":"https://www.bisnow.com/news/austin-san-antonio/data-center/sustainable-developer-bringing-data-center-campus-to-temple-134759"}],"status":"under_construction","status_as_of":"2026-05-29","status_source_ids":["s2","s4"],"summary":"Rowan Digital Infrastructure is building a 300 MW hyperscale data center campus on about 700 acres in east Temple, Bell County, Texas, roughly 70 miles north of Austin. Temple's council gave final approval to annex and zone the land in 2025, and in January 2026 Rowan reported construction under way, with power secured through Oncor and an unnamed large technology company as the long-term customer. In May 2026 Rowan announced it had closed nearly USD 3 billion of debt financing, and it expects operations in 2027. A third and final building, the Lasso Building, is now planned on adjacent land, and Rowan has offered USD 38 million for city water programs and a planned community center."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"13b41dff-6c36-562b-a775-d58b65d98d2e","s2":"0573a8b5-aea9-50f4-8ac3-b2cbe830d5df","s3":"f451982e-8599-5e46-b6ed-09eda42dfebf","s4":"33a59a67-e62e-5348-8fbb-5fc44302a000"},"source_file":"datacenters/projects/rowan-project-temple.json","source_record_id":"rowan-project-temple","source_record_sha256":"ac6a9ba056d88fd802fe69828988dcb7d1f1434be4bf4235730b1b47e5aeeacb","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8fe20c86e81b104d6a630add48c6cf11e1f38b5c3ceb80f08ee6bb5e035229a4"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-998792d68106140776c0/#project-4a2a09d1-1ace-5ff8-a80f-89996cda5799 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4a2a09d1-1ace-5ff8-a80f-89996cda5799.json
4a934222-f3af-5945-bb46-b98bfaef89b7 | curated:alto-sp01-granada-data-center-campus:phase-1-10mw-critical-it | vcc-site-7e1b680aa925165fe2ef | curated:alto-sp01-granada-data-center-campus | Alto Infrastructure SP01 Phase 1 10 MW Critical IT | Spain | ES | 37.0833 | -3.752 | Point | project | direct_geometry | official_junta_sp01_event_location_link_to_coordinate_point | official_government_project_event_reference_point | official_source | project_locator | Official project-event locator point used only to locate SP01. The seven-decimal redirect coordinate is preserved as published but is not treated as survey accuracy, parcel geometry, or a project centroid. |  | Neither the Junta agenda nor linked location redirect states the reference feature, collection method, or numeric horizontal accuracy. | dfffb2f5-ca78-5c98-bef7-2b58e7c98238 | under_construction | 2026-07-09 | 96 | authoritative_construction_start | f9be097a-99d8-5f60-9672-146a49d37f53 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [{"as_of_date":"2026-07-09","confidence":0.99,"deployment_scope":"intended","evidence_id":"f9be097a-99d8-5f60-9672-146a49d37f53","method":"government_record","workload":"ai_specialized_unspecified"},{"as_of_date":"2026-07-09","confidence":0.99,"deployment_scope":"intended","evidence_id":"f9be097a-99d8-5f60-9672-146a49d37f53","method":"government_record","workload":"general_cloud"},{"as_of_date":"2026-07-09","confidence":0.99,"deployment_scope":"intended","evidence_id":"f9be097a-99d8-5f60-9672-146a49d37f53","method":"government_record","workload":"hpc"}] |  | [{"evidence_id":"afb9a2fa-7d6d-57ef-8cbb-ef73595ed596","party":"Alto Infrastructure","relationship_scope":"intended","role":"operator"}] | [{"as_of_date":"2026-07-09","base":10.0,"confidence":0.99,"evidence_id":"f9be097a-99d8-5f60-9672-146a49d37f53","high":10.0,"low":10.0,"method":"reported","metric":"critical_it_mw","notes":"Source-explicit planned Phase 1 IT capacity only. The nested later 25 MW and full-build 70 MW IT scopes, 15 MW unspecified electrical figure, contracted 100 MW total-power figure, 130 kV grid voltage, design PUE, current load, generation, and annual energy are not this row and are not added or converted.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | Alto Infrastructure |  |  |  | https://www.investinspain.org/es/noticias-main/2026/alto | https://www.juntadeandalucia.es/organismos/sobre-junta/altos-cargos/agenda/detalle/217027.html | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7e1b680aa925165fe2ef/#project-4a934222-f3af-5945-bb46-b98bfaef89b7 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4a934222-f3af-5945-bb46-b98bfaef89b7.json
4ac7a0d0-0faf-50c0-bed8-08d54e0bc62b | imported:semiconductor-atlas:pw-digital-gateway | vcc-site-cd315d5cbb01f749da8f | imported:semiconductor-atlas:pw-digital-gateway | PW Digital Gateway | United States | US | 38.7947 | -77.6206 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Gainesville, Virginia. WTOP places the roughly 2,000-acre corridor along Pageland Lane near Gainesville, next to Manassas National Battlefield Park; the court describes three adjoining rezoning areas, so the site extends several kilometres from this point. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | aceb4a50-9fe3-5a13-9418-ac919e40d9ba | cancelled | 2026-07-04 | 101 | imported_documented_status | 194a47cc-c9ee-5c10-91ad-b408ea61d7b9 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"b918967a-04da-5d6b-9614-2d97acc2176e","notes":"Blackstone-owned. Converge Digest reports QTS acted through its affiliate GW Acquisition Co.; the court names GW Acquisition Co., LLC and GW Acquisition Co. I, LLC as applicants for the DG South and DG North rezonings.","party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"pw-digital-gateway"},{"evidence_id":"194a47cc-c9ee-5c10-91ad-b408ea61d7b9","notes":"Blackstone-owned. Converge Digest reports QTS acted through its affiliate GW Acquisition Co.; the court names GW Acquisition Co., LLC and GW Acquisition Co. I, LLC as applicants for the DG South and DG North rezonings.","party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"pw-digital-gateway"},{"evidence_id":"870b3b9b-6c9a-5df4-b926-4a165f334d23","notes":"Blackstone-owned. Converge Digest reports QTS acted through its affiliate GW Acquisition Co.; the court names GW Acquisition Co., LLC and GW Acquisition Co. I, LLC as applicants for the DG South and DG North rezonings.","party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"pw-digital-gateway"},{"evidence_id":"b918967a-04da-5d6b-9614-2d97acc2176e","notes":null,"party":"Compass Datacenters","relationship_scope":"unknown","role":"developer","source_record_id":"pw-digital-gateway"},{"evidence_id":"b645ce9f-49e8-50aa-9026-594cd20bb658","notes":null,"party":"Compass Datacenters","relationship_scope":"unknown","role":"developer","source_record_id":"pw-digital-gateway"},{"evidence_id":"fc1f176a-5e50-5f01-ba6f-0dd650989058","notes":"Applicant for the largest rezoning, known as Compass; the court groups it with the two GW entities as the developers.","party":"H&H Capital Acquisitions, LLC","relationship_scope":"unknown","role":"developer","source_record_id":"pw-digital-gateway"},{"evidence_id":"fc1f176a-5e50-5f01-ba6f-0dd650989058","notes":"Adopted the three rezonings in December 2023 and voted in April 2026 to stop defending them.","party":"Prince William County Board of County Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"pw-digital-gateway"},{"evidence_id":"b918967a-04da-5d6b-9614-2d97acc2176e","notes":"Adopted the three rezonings in December 2023 and voted in April 2026 to stop defending them.","party":"Prince William County Board of County Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"pw-digital-gateway"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.bisnow.com/news/washington-dc/data-center-development/blackstones-qts-abandons-digital-gateway-project-ends-lawsuit-135295 | https://wtop.com/?p=29400462 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve PW Digital Gateway as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"pw-digital-gateway"},"record":{"aliases":["Prince William Digital Gateway","Digital Gateway"],"id":"pw-digital-gateway","last_reviewed":"2026-10-09","location":{"admin1":"Virginia","admin2":"Prince William County","country":"US","lat":38.7947,"locality":"Gainesville","lon":-77.6206,"note":"Wikipedia coordinates for Gainesville, Virginia. WTOP places the roughly 2,000-acre corridor along Pageland Lane near Gainesville, next to Manassas National Battlefield Park; the court describes three adjoining rezoning areas, so the site extends several kilometres from this point.","precision":"locality","source_ids":["s6","s1"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-29","basis":"planned","metric":"power_capacity","note":"Bisnow reports 1.7 GW of capacity for the whole project without saying whether it is IT load or facility power.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3","s4","s2"],"unit":"MW","value":1700},{"applies_to":"campus","as_of":"2026-07-02","basis":"planned","metric":"power_capacity","note":"Opponent's estimate: the American Battlefield Trust, which sued to stop the project, says the data centers were expected to draw up to 9 GW. It conflicts with the 1.7 GW trade-press figure, and the Trust does not explain its basis.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s7"],"unit":"MW","value":9000},{"applies_to":"campus","as_of":"2025-08-08","basis":"planned","metric":"land_area","note":"Overall Digital Gateway area as reported by Bisnow; later coverage rounds it to 2,100 acres. The three rezonings described by the court cover 884, 534 and 342 acres.","qualifier":"approximately","source_ids":["s2"],"unit":"acres","value":2139},{"applies_to":"campus","as_of":"2026-04-15","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s2","s3"],"unit":"sq_ft","value":22000000},{"applies_to":"campus","as_of":"2026-03-31","basis":"planned","metric":"buildings","note":"Court of Appeals description of the approved rezonings; Bisnow reports 34 buildings at full build-out.","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":37},{"applies_to":"campus","as_of":"2026-04-15","basis":"planned","metric":"buildings","note":"Trade-press figure that differs from the court's figure of up to 37 data centers.","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":34},{"applies_to":"phase","as_of":"2026-03-31","basis":"planned","metric":"land_area","phase_label":"Compass rezoning (REZ2022-00036)","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":884},{"applies_to":"phase","as_of":"2026-03-31","basis":"planned","metric":"floor_area","phase_label":"Compass rezoning (REZ2022-00036)","qualifier":"up_to","source_ids":["s1"],"unit":"sq_ft","value":11500000},{"applies_to":"phase","as_of":"2026-03-31","basis":"planned","metric":"land_area","phase_label":"DG North rezoning (REZ2022-00032)","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":534},{"applies_to":"phase","as_of":"2026-03-31","basis":"planned","metric":"floor_area","phase_label":"DG North rezoning (REZ2022-00032)","qualifier":"up_to","source_ids":["s1"],"unit":"sq_ft","value":7000000},{"applies_to":"phase","as_of":"2026-03-31","basis":"planned","metric":"land_area","phase_label":"DG South rezoning (REZ2022-00033)","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":342},{"applies_to":"phase","as_of":"2026-03-31","basis":"planned","metric":"floor_area","phase_label":"DG South rezoning (REZ2022-00033)","qualifier":"up_to","source_ids":["s1"],"unit":"sq_ft","value":3700000}],"milestones":[{"date":"2022-11-01","event":"other","kind":"actual","note":"County board enacted the Digital Gateway comprehensive plan amendment (CPA2021-00004) that preceded the rezoning applications.","source_ids":["s1"]},{"date":"2023-12-13","event":"zoning_approved","kind":"actual","note":"After a public hearing that began on 12 December, the board approved all three rezonings on 13 December by a four-to-three vote with one abstention.","source_ids":["s1"]},{"date":"2025-08","event":"other","kind":"actual","note":"Prince William Circuit Court Judge Kimberly Irving declared the rezonings void over defective public notice.","source_ids":["s2"]},{"date":"2026-03-31","event":"other","kind":"actual","note":"Court of Appeals of Virginia affirmed that the Compass, DG North and DG South rezonings were void from the start.","source_ids":["s1"]},{"date":"2026-04-14","event":"other","kind":"actual","note":"County board voted unanimously to drop its legal defense of the rezonings. The American Battlefield Trust gives the date as 14 April; Bisnow's Wednesday 15 April article places the vote on the preceding Tuesday.","source_ids":["s3","s7"]},{"date":"2026-04","event":"other","kind":"actual","note":"Compass Datacenters said it could not move forward with the project; the American Battlefield Trust says Compass declined to appeal further.","source_ids":["s4","s7"]},{"date":"2026-07-02","event":"cancelled","kind":"actual","note":"QTS withdrew its petitions to the Supreme Court of Virginia on 2 July and said it was terminating the project.","source_ids":["s5","s6","s8"]}],"name":"PW Digital Gateway","parties":[{"name":"QTS Data Centers","note":"Blackstone-owned. Converge Digest reports QTS acted through its affiliate GW Acquisition Co.; the court names GW Acquisition Co., LLC and GW Acquisition Co. I, LLC as applicants for the DG South and DG North rezonings.","role":"developer","source_ids":["s3","s5","s8"]},{"name":"Compass Datacenters","role":"developer","source_ids":["s3","s4"]},{"name":"H&H Capital Acquisitions, LLC","note":"Applicant for the largest rezoning, known as Compass; the court groups it with the two GW entities as the developers.","role":"developer","source_ids":["s1"]},{"name":"Prince William County Board of County Supervisors","note":"Adopted the three rezonings in December 2023 and voted in April 2026 to stop defending them.","role":"government","source_ids":["s1","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-03-31","publisher":"Court of Appeals of Virginia","title":"Board of County Supervisors of Prince William County v. Oak Valley Homeowners Association, Inc., et al. (Record Nos. 1590-25-4, 1584-25-4, 1592-25-4, 2025-24-4)","type":"court","url":"https://www.vacourts.gov/opinions/opncavwp/1592254.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2025-08-08","publisher":"Bisnow","title":"Judge Throws Out Zoning Approval For 2,100-Acre Northern Virginia Data Center Project","type":"trade_press","url":"https://www.bisnow.com/news/washington-dc/data-center/judge-throws-out-zoning-approval-for-2100-acre-northern-virginia-data-center-project-130496"},{"accessed":"2026-10-09","id":"s3","published":"2026-04-15","publisher":"Bisnow","title":"Officials End Efforts To Build One Of World's Largest Data Center Clusters","type":"trade_press","url":"https://www.bisnow.com/news/washington-dc/data-center-development/officials-end-fight-2100-acre-data-center-rezoning-killing-one-of-worlds-largest-planned-projects-134136"},{"accessed":"2026-10-09","id":"s4","published":"2026-04-29","publisher":"Bisnow","title":"Developer Abandons Massive Virginia Data Center Plan After Court Ruling","type":"trade_press","url":"https://www.bisnow.com/news/national/data-center-development/developer-backs-out-of-17-gw-virginia-data-center-plan-134341"},{"accessed":"2026-10-09","id":"s5","published":"2026-07-03","publisher":"Bisnow","title":"Blackstone's QTS Abandons Digital Gateway Project, Ends Legal Fight","type":"trade_press","url":"https://www.bisnow.com/news/washington-dc/data-center-development/blackstones-qts-abandons-digital-gateway-project-ends-lawsuit-135295"},{"accessed":"2026-10-09","id":"s6","published":"2026-07-02","publisher":"WTOP (republished from InsideNoVa)","title":"Digital Gateway data center project dies after final developer withdraws appeal","type":"news","url":"https://wtop.com/?p=29400462"},{"accessed":"2026-10-09","id":"s7","published":"2026-07-02","publisher":"American Battlefield Trust","title":"Victory at Manassas! Prince William Digital Gateway Project Dead After Developer Drops Appeal","type":"other","url":"https://www.battlefields.org/news/victory-manassas-prince-william-digital-gateway-project-dead-after-developer-drops-appeal"},{"accessed":"2026-10-09","id":"s8","published":"2026-07-04","publisher":"Converge Digest","title":"QTS Drops Digital Gateway Data Center Campus in VA","type":"trade_press","url":"https://convergedigest.com/qts-drops-digital-gateway-data-center-campus-in-va/"}],"status":"cancelled","status_as_of":"2026-07-04","status_source_ids":["s5","s6","s8"],"summary":"Proposed data center corridor of roughly 2,100 acres along Pageland Lane near Gainesville in western Prince William County, Virginia, next to Manassas National Battlefield Park. In December 2023 the county board approved three rezonings (Compass, DG North and DG South) that together allowed about 22 million square feet and up to 37 data centers for QTS and Compass Datacenters. Courts later held the rezonings void because the hearing was improperly advertised. The county and Compass stopped defending them in April 2026, and QTS withdrew its last appeal and ended the project in July 2026."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"fc1f176a-5e50-5f01-ba6f-0dd650989058","s2":"caceecfb-61b4-5dc8-ae00-fb3989f20a0c","s3":"b918967a-04da-5d6b-9614-2d97acc2176e","s4":"b645ce9f-49e8-50aa-9026-594cd20bb658","s5":"194a47cc-c9ee-5c10-91ad-b408ea61d7b9","s6":"aceb4a50-9fe3-5a13-9418-ac919e40d9ba","s7":"569df01b-b91d-500c-9253-2d1f3f802fba","s8":"870b3b9b-6c9a-5df4-b926-4a165f334d23"},"source_file":"datacenters/projects/pw-digital-gateway.json","source_record_id":"pw-digital-gateway","source_record_sha256":"bc280c373c02f7c258ed949cb09b655406e267bf48cb43edcd6d084ccc9e6fa5","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"55a39c19574c08418db086d6ad471b37fb588a9df92f2a145845d535b3596116"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cd315d5cbb01f749da8f/#project-4ac7a0d0-0faf-50c0-bed8-08d54e0bc62b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4ac7a0d0-0faf-50c0-bed8-08d54e0bc62b.json
4afd2551-1442-5f67-a1d9-0d245835088d | curated:firstcolo-fra7-rosbach-campus:fra7-current-build | vcc-site-23595034ead536d5a4cb | curated:firstcolo-fra7-rosbach-campus | firstcolo FRA7 Current Build | Germany | DE | 50.2948 | 8.6994 | Point | facility | coordinates_to_point | first_party_published_dms_coordinate_to_point | first_party_facility_reference_point | official_source | project_locator | First-party FRA7 factsheet coordinate converted exactly from degrees, minutes, and seconds and bound to the same named facility and street address. It is a facility locator, not a parcel, campus, building, project, entrance, centroid, or current-work boundary. |  | The factsheet supplies no reference-feature definition, collection method, or numeric horizontal-accuracy statement; decimal digits produced by the DMS conversion do not add precision. | 706814f6-ce3c-5619-83a7-174fea885db2 | under_construction | 2026-06-15 | 120 | authoritative_construction_start | 44aa682e-8b37-582c-9e56-2a8757f401d8 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.13 geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://firstcolo.net/en/250-million-euros-for-ai-infrastructure-firstcolo-breaks-ground-on-fra7-data-center-in-hesse/ | https://firstcolo.net/wp-content/uploads/factsheet-rosbach_dez_25_DE.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-23595034ead536d5a4cb/#project-4afd2551-1442-5f67-a1d9-0d245835088d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4afd2551-1442-5f67-a1d9-0d245835088d.json
4ea35229-9824-5086-8441-310876ea8911 | imported:semiconductor-atlas:scala-tambore-barueri | vcc-site-36fd6f2f441272102aa1 | imported:semiconductor-atlas:scala-tambore-barueri | Scala Data Centers Tamboré Campus | Brazil | BR | -23.4656 | -46.8419 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Releases place the campus in the Tamboré area of Barueri alongside the Rodoanel without a street address; coordinates are the Tamboré reference point (Portuguese Wikipedia), and Tamboré spans Barueri and neighbouring Santana de Parnaíba. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 28743ca1-9778-595d-974c-94ff2c3c980a | partially_operational | 2025-10-30 | 348 | imported_documented_status | 2d5bc456-aeed-594a-ab5b-cd46d905c58e | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"28743ca1-9778-595d-974c-94ff2c3c980a","notes":null,"party":"Scala Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"scala-tambore-barueri"},{"evidence_id":"2d5bc456-aeed-594a-ab5b-cd46d905c58e","notes":null,"party":"Scala Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"scala-tambore-barueri"},{"evidence_id":"28743ca1-9778-595d-974c-94ff2c3c980a","notes":null,"party":"Scala Data Centers","relationship_scope":"unknown","role":"operator","source_record_id":"scala-tambore-barueri"},{"evidence_id":"2d5bc456-aeed-594a-ab5b-cd46d905c58e","notes":null,"party":"Scala Data Centers","relationship_scope":"unknown","role":"operator","source_record_id":"scala-tambore-barueri"},{"evidence_id":"2d5bc456-aeed-594a-ab5b-cd46d905c58e","notes":"Signed a memorandum with Scala for approval of the campus master plan.","party":"Municipality of Barueri","relationship_scope":"unknown","role":"government","source_record_id":"scala-tambore-barueri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Scala Data Centers |  |  |  | https://www.prnewswire.com/news-releases/scala-data-centers-celebrates-historic-milestone-with-approval-of-the-master-plan-for-its-tambore-campus-in-sao-paulo---the-largest-and-most-advanced-in-latin-america-with-600-mw-of-capacity-302599995.html | https://www.prnewswire.com/news-releases/scala-data-centers-inaugurates-phase-2-of-tambore-campus-with-governor-tarcisio-de-freitas-present-committing-1-13-billion-302224370.html | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Scala Data Centers Tamboré Campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"scala-tambore-barueri"},"record":{"aliases":["Tamboré Campus","Campus Tamboré"],"id":"scala-tambore-barueri","last_reviewed":"2026-10-09","location":{"admin1":"São Paulo","admin2":"Barueri","country":"BR","lat":-23.4656,"locality":"Tamboré","lon":-46.8419,"note":"Releases place the campus in the Tamboré area of Barueri alongside the Rodoanel without a street address; coordinates are the Tamboré reference point (Portuguese Wikipedia), and Tamboré spans Barueri and neighbouring Santana de Parnaíba.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2025-10-30","basis":"planned","metric":"power_capacity","note":"Total at full development; the releases do not say whether this is IT load.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":600},{"applies_to":"phase","as_of":"2024-08-16","basis":"planned","metric":"power_capacity","phase_label":"Phase 2","power_scope":"it_load","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":158},{"applies_to":"campus","as_of":"2025-10-30","basis":"operational","metric":"power_capacity","note":"Reported as active capacity across seven operating buildings in October 2025. The August 2024 release had said the campus would total more than 200 MW across six operating and four under-construction buildings after Phase 2.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s2"],"unit":"MW","value":120},{"applies_to":"campus","as_of":"2025-10-30","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":17},{"applies_to":"campus","as_of":"2025-10-30","basis":"operational","metric":"buildings","qualifier":"exact","source_ids":["s2"],"unit":"count","value":7},{"applies_to":"phase","as_of":"2024-08-16","basis":"announced","metric":"investment","note":"Also given as USD 1.13 billion in the release.","phase_label":"Phase 2","qualifier":"exact","source_ids":["s1"],"unit":"BRL","value":6200000000},{"applies_to":"campus","as_of":"2025-10-30","basis":"reported","metric":"investment","note":"Cumulative investment reported for the campus to date.","qualifier":"more_than","source_ids":["s1","s2"],"unit":"BRL","value":10000000000}],"milestones":[{"date":"2024-08","event":"other","kind":"actual","note":"Phase 2 inaugurated with the São Paulo governor present; buildings SGRUTB08 and SGRUTB12 in operation for two hyperscale clients, with SGRUTB09, SGRUTB10, SGRUTB67 and a substation under construction.","source_ids":["s1"]},{"date":"2025-10-30","event":"other","kind":"actual","note":"Scala announced a memorandum with the Municipality of Barueri for approval of the 600 MW campus master plan; date is the release date.","source_ids":["s2"]}],"name":"Scala Data Centers Tamboré Campus","parties":[{"name":"Scala Data Centers","role":"developer","source_ids":["s1","s2"]},{"name":"Scala Data Centers","role":"operator","source_ids":["s1","s2"]},{"name":"Municipality of Barueri","note":"Signed a memorandum with Scala for approval of the campus master plan.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"Served by three power substations; Scala says it buys 100% renewable energy through long-term power purchase agreements tied to new wind and solar farms.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-08-16","publisher":"Scala Data Centers via PR Newswire","title":"Scala Data Centers inaugurates Phase 2 of Tamboré Campus with Governor Tarcísio de Freitas present, committing $1.13 billion","type":"company","url":"https://www.prnewswire.com/news-releases/scala-data-centers-inaugurates-phase-2-of-tambore-campus-with-governor-tarcisio-de-freitas-present-committing-1-13-billion-302224370.html"},{"accessed":"2026-10-09","id":"s2","published":"2025-10-30","publisher":"Scala Data Centers via PR Newswire","title":"Scala Data Centers celebrates historic milestone with approval of the master plan for its Tamboré Campus in São Paulo, the largest and most advanced in Latin America with 600 MW of capacity","type":"company","url":"https://www.prnewswire.com/news-releases/scala-data-centers-celebrates-historic-milestone-with-approval-of-the-master-plan-for-its-tambore-campus-in-sao-paulo---the-largest-and-most-advanced-in-latin-america-with-600-mw-of-capacity-302599995.html"}],"status":"partially_operational","status_as_of":"2025-10-30","status_source_ids":["s2"],"summary":"Scala Data Centers' Tamboré Campus in Barueri, Greater São Paulo, sits beside the Rodoanel ring road and is planned to reach 600 MW across 17 data centre buildings and three substations. Scala inaugurated Phase 2 (158 MW of IT capacity, BRL 6.2 billion) in August 2024 with two hyperscale buildings in service and more under construction. By October 2025 the company reported seven buildings operating, more than BRL 10 billion invested, and a memorandum with the Municipality of Barueri for approval of the campus master plan.","workloads":["cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"28743ca1-9778-595d-974c-94ff2c3c980a","s2":"2d5bc456-aeed-594a-ab5b-cd46d905c58e"},"source_file":"datacenters/projects/scala-tambore-barueri.json","source_record_id":"scala-tambore-barueri","source_record_sha256":"c955f764189fbe4105e203e5a35a47ec6a8ec43c417b4e88dc026f109542be57","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4fc2dddb08c0813609556dae262220485cc4e4b75d979daa0b082e0c2304bf72"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-36fd6f2f441272102aa1/#project-4ea35229-9824-5086-8441-310876ea8911 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4ea35229-9824-5086-8441-310876ea8911.json
4eea4b6a-9f71-5c9f-81bb-ae597972ddd5 | imported:semiconductor-atlas:wbs-power-baltic-data-center-campus | vcc-site-cd3c4380161bc1c0389f | imported:semiconductor-atlas:wbs-power-baltic-data-center-campus | WBS Power Baltic Data Center Campus, Lublewo | Poland | PL | 54.7597 | 17.9453 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | The press release and Gramwzielone name the site as Lublewo in Choczewo municipality; neither uses the official name Lublewo Lęborskie. Wikipedia lists Lublewo Lęborskie as the only village called Lublewo in Gmina Choczewo (the other similar name is Lublewko), so its village coordinates are used, at locality precision. County is from Wikipedia. No cited source gives site coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | c8683395-ab3c-5394-9f84-9a6b854c57f6 | announced | 2026-03-24 | 203 | imported_documented_status | c8683395-ab3c-5394-9f84-9a6b854c57f6 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c8683395-ab3c-5394-9f84-9a6b854c57f6","notes":null,"party":"WBS Power","relationship_scope":"unknown","role":"developer","source_record_id":"wbs-power-baltic-data-center-campus"},{"evidence_id":"fc5df45e-1ec4-5e5c-88fa-da361faa1b27","notes":null,"party":"WBS Power","relationship_scope":"unknown","role":"developer","source_record_id":"wbs-power-baltic-data-center-campus"},{"evidence_id":"64ef37b9-0d82-59e9-9810-8ac8342420f6","notes":null,"party":"WBS Power","relationship_scope":"unknown","role":"developer","source_record_id":"wbs-power-baltic-data-center-campus"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://tools.prnewswire.com/en-us/live/20823/release/20260324EN14682 | https://tools.prnewswire.com/en-us/live/20823/release/20260324EN14682 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve WBS Power Baltic Data Center Campus, Lublewo as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"wbs-power-baltic-data-center-campus"},"record":{"aliases":["Baltic Data Center Campus","Baltic DC Campus"],"id":"wbs-power-baltic-data-center-campus","last_reviewed":"2026-10-09","location":{"admin1":"Pomeranian Voivodeship","admin2":"Wejherowo County","country":"PL","lat":54.75972,"locality":"Lublewo (Choczewo municipality)","lon":17.94528,"note":"The press release and Gramwzielone name the site as Lublewo in Choczewo municipality; neither uses the official name Lublewo Lęborskie. Wikipedia lists Lublewo Lęborskie as the only village called Lublewo in Gmina Choczewo (the other similar name is Lublewko), so its village coordinates are used, at locality precision. County is from Wikipedia. No cited source gives site coordinates.","precision":"locality","source_ids":["s1","s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-24","basis":"planned","metric":"power_capacity","note":"Target capacity; scope not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":3200},{"applies_to":"phase","as_of":"2026-03-24","basis":"planned","metric":"power_capacity","phase_label":"Each of four phases","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":800},{"applies_to":"campus","as_of":"2026-03-24","basis":"permitted","metric":"power_capacity","note":"WBS Power says it has secured grid connection conditions for the full capacity; the grid operator is not named.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":3200}],"milestones":[{"date":"2026-03-17","event":"announced","kind":"actual","note":"Earliest report found; WBS Power's English press release followed on 24 March 2026.","source_ids":["s3"]},{"date":"2027","event":"other","kind":"planned","note":"Preparatory work for all four phases expected to be completed by the end of 2027.","source_ids":["s1","s2","s3"]},{"date":"2028","event":"first_operational","kind":"planned","note":"First data center targeted around 2028-2029.","source_ids":["s1","s2","s3"]}],"name":"WBS Power Baltic Data Center Campus, Lublewo","notes":"No investment figure, land area, investor or tenant was disclosed in the sources opened, and no zoning or environmental permit decision was found. The 3.2 GW figure is the developer's target. No update after March 2026 was found.","parties":[{"name":"WBS Power","role":"developer","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"Grid connection conditions secured for 3.2 GW at a site next to one of Poland's largest substations.","source_ids":["s1","s3"],"type":"grid"},{"description":"Battery energy storage integration is planned.","source_ids":["s1","s2"],"type":"battery_storage"},{"description":"WBS Power says power will come from conventional sources supplemented by renewables; specific generation contracts are not described.","source_ids":["s1","s3"],"type":"other"},{"description":"Nuclear power is cited only as a longer-term source; the Westinghouse AP1000 plant planned at Lubiatowo-Kopalino in Choczewo municipality targets commercial operation in 2033, with no supply agreement reported.","source_ids":["s2","s3"],"type":"nuclear"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-03-24","publisher":"WBS Power (via PR Newswire)","title":"WBS Power Advances 3.2 GW Energy Infrastructure for Hyperscale Data Center Campus","type":"company","url":"https://tools.prnewswire.com/en-us/live/20823/release/20260324EN14682"},{"accessed":"2026-10-09","id":"s2","published":"2026-03-24","publisher":"World Nuclear News","title":"Data centre to be built near planned Polish nuclear power plant","type":"trade_press","url":"https://wnn.world-nuclear.org/articles/data-centre-to-be-built-near-planned-polish-nuclear-power-plant"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-17","publisher":"Gramwzielone.pl","title":"Deweloper z rynku OZE postawi ogromne centrum danych na Pomorzu","type":"trade_press","url":"https://www.gramwzielone.pl/?p=20353659"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Lublewo Lęborskie","type":"other","url":"https://en.wikipedia.org/wiki/Lublewo_L%C4%99borskie"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260106053605/https://en.wikipedia.org/wiki/Gmina_Choczewo","id":"s5","published":null,"publisher":"Wikipedia","title":"Gmina Choczewo","type":"other","url":"https://en.wikipedia.org/wiki/Gmina_Choczewo"}],"status":"announced","status_as_of":"2026-03-24","status_source_ids":["s1","s2"],"summary":"Hyperscale campus proposed by WBS Power at Lublewo in Choczewo municipality, Pomerania, near the planned Lubiatowo-Kopalino nuclear power plant site. Announced in March 2026, it targets 3.2 GW in four 800 MW phases aimed at AI, HPC and cloud customers. WBS Power says it has grid connection conditions for the full 3.2 GW at a site next to one of Poland's largest substations, with power from conventional sources, renewables and battery storage, and nuclear in the longer term. Preparation of all phases is due by the end of 2027 and the first data center around 2028-2029. No investors, tenants or permits were named.","workloads":["ai_unspecified","hpc","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c8683395-ab3c-5394-9f84-9a6b854c57f6","s2":"fc5df45e-1ec4-5e5c-88fa-da361faa1b27","s3":"64ef37b9-0d82-59e9-9810-8ac8342420f6","s4":"c6276664-61e3-55cd-b113-424bec6dbe6f","s5":"f1d71e91-331b-540e-979d-1c89d8984b8a"},"source_file":"datacenters/projects/wbs-power-baltic-data-center-campus.json","source_record_id":"wbs-power-baltic-data-center-campus","source_record_sha256":"310e30666c498dbab8e0920b5458999e8df7d01c1044e242ea7de1d7bc79b801","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"73668d72a83acf18d14292b9f2f951611d56b56f3ec90e62acad02a856b4f551"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cd3c4380161bc1c0389f/#project-4eea4b6a-9f71-5c9f-81bb-ae597972ddd5 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4eea4b6a-9f71-5c9f-81bb-ae597972ddd5.json
4eeb97fa-8e1d-53de-ae86-eebc40e97d6f | curated:green-mountain-fra-mainz-campus:current-three-building-development | vcc-site-76ff9a11d8e0e21c29cb | curated:green-mountain-fra-mainz-campus | Green Mountain FRA-Mainz Current Three-Building Development | Germany | DE | 50.0276 | 8.2406 | Point | project | coordinates_to_point | energieatlas_named_green_rocks_project_point | official_government_project_reference_point | official_source | project_locator | Official Energieatlas point for the named Green Rocks project in Mainz, whose card identifies Green Mountain, KMW, Gaßnerallee, and the three-building facility. It is a project locator, not a parcel, campus, building, entrance, survey point, centroid, or current-work boundary. |  | Energieatlas supplies coordinate digits but no collection method, reference-feature definition, or bounded numeric horizontal-accuracy value. | 29bdb34b-54f1-5e00-b28e-877efbf2e828 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | b6a4a704-8176-570e-8d48-4f118e5990b8 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.15 global geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://greenmountain.no/data-center/fra-mainz/ | https://www.energieatlas.rlp.de/geoserver/earp/ows?service=WFS&version=1.0.0&request=GetFeature&typeName=earp%3Apraxisbeispiele&srsName=EPSG%3A4326&outputFormat=application%2Fjson&cql_filter=id%3D149%20AND%20typ%3D%27unternehmen%27 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-76ff9a11d8e0e21c29cb/#project-4eeb97fa-8e1d-53de-ae86-eebc40e97d6f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4eeb97fa-8e1d-53de-ae86-eebc40e97d6f.json
4f39070f-83dd-557a-a1b0-88408f56c1fb | curated:niger-national-data-center-pk5-niamey:current-build | vcc-site-4586aa46386f0cb18dc7 | curated:niger-national-data-center-pk5-niamey | Niger National Data Center PK5 Current Build | Niger | NE | 13.5597 | 2.1135 | Point | project | official_dms_coordinate_to_point | bnee_eies_project_area_coordinate | official_environmental_assessment_project_point | official_source | project_locator | The point is the EIES-reported coordinate of the project area at the selected Niger Telecom PK5 site. It is not a surveyed entrance, parcel centroid, building footprint, campus boundary, or current-work extent. |  | The EIES reports DMS precision but no survey method, datum-specific accuracy statement, or bounded horizontal uncertainty. | e8b0b9c1-e565-5bea-be8f-a8f5c4eeb6df | under_construction | 2026-06-18 | 117 | authoritative_physical_status_update | bfd574ee-1aca-5897-81a1-5d7d6a9cfbfb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.gouv.ne/index.php/actualite-des-ministeres/1200-communication-et-numerique-le-niger-ambitionne-de-devenir-un-hub-regional-des-telecommunications | https://www.bnee.ne/wp-content/uploads/2022/08/Rapport-de%CC%81finitif-EIES-DATACENTER-PK5-Niamey_VP.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4586aa46386f0cb18dc7/#project-4f39070f-83dd-557a-a1b0-88408f56c1fb | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4f39070f-83dd-557a-a1b0-88408f56c1fb.json
4f86e285-bcf1-537b-b31e-8af7b27ed556 | curated:goodman-fra02-frankfurt-data-centre-campus:phase-1-current-development | vcc-site-f95670603a10a1f6f24b | curated:goodman-fra02-frankfurt-data-centre-campus | Goodman FRA02 Phase 1 Current Development | Germany | DE | 50.0427 | 8.6855 | Point | campus | first_party_brochure_published_map_link_target | resolve_official_PDF_hyperlink_and_select_marker_coordinates_without_geocoding_or_centroiding | official_operator_published_campus_reference_point | official_source | campus_locator | Goodman's FRA II brochure links this campus point at Rathenaustrasse 31; the city identifies the same Rathenaustrasse project as FRA02. The point is not a specific building, phase, substation, parcel boundary, campus footprint or June 30 active-work extent. Two campus buildings remain one physical site. |  | Neither Goodman nor the linked marker supplies a numeric horizontal-accuracy statement or identifies a surveyed reference feature. | aaab4a40-99dd-50ee-a496-a7d7c2e44fe7 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | b886587a-20ed-5067-b88e-7553312596f6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | https://goo.gl/maps/HXytDcSqfrnEAHNs5 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f95670603a10a1f6f24b/#project-4f86e285-bcf1-537b-b31e-8af7b27ed556 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4f86e285-bcf1-537b-b31e-8af7b27ed556.json
4f8a32cf-b64b-51b4-8758-368320eb441d | imported:semiconductor-atlas:humain-al-saad-riyadh | vcc-site-a226e4ce3df02dee4be7 | imported:semiconductor-atlas:humain-al-saad-riyadh | HUMAIN Al-Saad hyperscale AI data centre campus | Saudi Arabia | SA | 24.6389 | 46.716 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the site in the Al-Saad area of east Riyadh. OpenStreetMap Nominatim did not resolve that district, so coordinates are the Riyadh city centroid from Nominatim. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | db21518c-9ab6-58b0-8572-18a1df09cf7f | announced | 2026-09-27 | 16 | imported_documented_status | 4e17a2ee-2bd7-5860-90d6-6c2b51abf43c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"db21518c-9ab6-58b0-8572-18a1df09cf7f","notes":"Client for the campus infrastructure works; supported by advisers Hatch, Egis and JLL.","party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"humain-al-saad-riyadh"},{"evidence_id":"4e17a2ee-2bd7-5860-90d6-6c2b51abf43c","notes":"Client for the campus infrastructure works; supported by advisers Hatch, Egis and JLL.","party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"humain-al-saad-riyadh"},{"evidence_id":"035cc4b0-57d1-5e19-8842-07ccc8b6f5ea","notes":"Client for the campus infrastructure works; supported by advisers Hatch, Egis and JLL.","party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"humain-al-saad-riyadh"},{"evidence_id":"4e17a2ee-2bd7-5860-90d6-6c2b51abf43c","notes":"Selected for the campus enabling infrastructure package under an early contractor involvement process. Construction Review notes that this is not yet a final appointment for all construction works.","party":"Al-Yamama Company for Trading & Contracting","relationship_scope":"unknown","role":"builder","source_record_id":"humain-al-saad-riyadh"},{"evidence_id":"035cc4b0-57d1-5e19-8842-07ccc8b6f5ea","notes":"Selected for the campus enabling infrastructure package under an early contractor involvement process. Construction Review notes that this is not yet a final appointment for all construction works.","party":"Al-Yamama Company for Trading & Contracting","relationship_scope":"unknown","role":"builder","source_record_id":"humain-al-saad-riyadh"},{"evidence_id":"36c2c165-107c-5b62-b856-6fa2c4b83cb4","notes":"Selected for the campus enabling infrastructure package under an early contractor involvement process. Construction Review notes that this is not yet a final appointment for all construction works.","party":"Al-Yamama Company for Trading & Contracting","relationship_scope":"unknown","role":"builder","source_record_id":"humain-al-saad-riyadh"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://guest.meed.com/contractor-wins-6gw-data-centre-campus-infrastructure/ | https://guest.meed.com/humain-tenders-6gw-data-centre-campus-infrastructure/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry","source_anchor_with_unresolved_possible_earlier_phase"],"rationale":"Named 6 GW Al-Saad campus in east Riyadh has no matching development in the current release. Preserve it as the source campus anchor; the earlier undifferentiated HUMAIN Riyadh 100 MW record is held because its relationship to Al-Saad is unproven. Do not sum both as independent projects.","source_record_id":"humain-al-saad-riyadh","source_relations":[{"reason":"Same developer and Riyadh centroid, but no source links the initial 100 MW site to the 6 GW Al-Saad proposal.","relationship":"unresolved_possible_same_campus","source_id":"humain-riyadh"}]},"record":{"aliases":["HUMAIN 6GW Riyadh campus"],"id":"humain-al-saad-riyadh","last_reviewed":"2026-10-09","location":{"admin1":"Riyadh Province","country":"SA","lat":24.6389,"locality":"Riyadh","lon":46.716,"note":"Sources place the site in the Al-Saad area of east Riyadh. OpenStreetMap Nominatim did not resolve that district, so coordinates are the Riyadh city centroid from Nominatim.","precision":"locality","source_ids":["s1","s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-09-24","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":6000},{"applies_to":"phase","as_of":"2026-09-24","basis":"planned","metric":"power_capacity","note":"MEED says the campus spans six plots delivered in two phases, each with 1 GW; the figure is read as per plot because six plots of 1 GW match the 6 GW total. Enterprise AM uses similar wording.","phase_label":"Each of six plots","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-09-24","basis":"reported","metric":"land_area","note":"Reported as 24 square kilometres, converted exactly to hectares.","qualifier":"exact","source_ids":["s1","s2","s3","s4"],"unit":"hectares","value":2400}],"milestones":[{"date":"2026-05","event":"other","kind":"actual","note":"HUMAIN tendered the campus enabling infrastructure package, with proposals due on 8 May.","source_ids":["s1","s3"]},{"date":"2026-09","event":"other","kind":"actual","note":"Al-Yamama reported as winner of the enabling infrastructure contract.","source_ids":["s2","s3","s4"]}],"name":"HUMAIN Al-Saad hyperscale AI data centre campus","notes":"Status is announced because only site enabling works have been contracted; no source reviewed reports data hall construction or a delivery date. MEED coverage is partly paywalled, and the other reports appear to draw on it.","parties":[{"name":"HUMAIN","note":"Client for the campus infrastructure works; supported by advisers Hatch, Egis and JLL.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Al-Yamama Company for Trading & Contracting","note":"Selected for the campus enabling infrastructure package under an early contractor involvement process. Construction Review notes that this is not yet a final appointment for all construction works.","role":"builder","source_ids":["s2","s3","s4"]}],"power_sources":[{"description":"Enabling works include a 380/132/33 kV distribution network, two substations of 500 MVA and 200 MVA, and a 2,000 MVA bulk supply point.","source_ids":["s1","s2","s3"],"type":"grid"}],"related_ids":["humain-riyadh","humain-dammam"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260512072557/https://guest.meed.com/humain-tenders-6gw-data-centre-campus-infrastructure/","id":"s1","published":"2026-05-04","publisher":"MEED","title":"Humain tenders infrastructure for 6GW data centre campus","type":"trade_press","url":"https://guest.meed.com/humain-tenders-6gw-data-centre-campus-infrastructure/"},{"accessed":"2026-10-09","id":"s2","published":"2026-09-24","publisher":"MEED","title":"Contractor wins 6GW data centre campus infrastructure","type":"trade_press","url":"https://guest.meed.com/contractor-wins-6gw-data-centre-campus-infrastructure/"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-27","publisher":"Enterprise AM","title":"Al Yamama takes the infrastructure contract for Humain's 6 GW Riyadh AI campus","type":"news","url":"https://enterpriseam.com/ksa/2026/09/27/al-yamama-takes-the-infrastructure-contract-for-humains-6-gw-riyadh-ai-campus/"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-24","publisher":"Construction Review Online","title":"Al-Yamama Wins Infrastructure Contract for 6GW Humain AI Data Center Campus in Riyadh","type":"trade_press","url":"https://constructionreviewonline.com/al-yamama-wins-infrastructure-contract-for-6gw-humain-ai-data-center-campus-in-riyadh/"}],"status":"announced","status_as_of":"2026-09-27","status_source_ids":["s2","s3","s4"],"summary":"HUMAIN, the AI company owned by Saudi Arabia's Public Investment Fund, plans a 6 GW hyperscale AI data centre campus on a 24 square kilometre site in the Al-Saad area of east Riyadh, to be built in two phases across six plots. HUMAIN tendered the campus enabling infrastructure in May 2026, covering high-voltage distribution, two substations, a 2,000 MVA bulk supply point, water, sewage, roads and fibre. In September 2026 Dammam-based Al-Yamama was reported as the selected contractor under an early contractor involvement process. Neither the contract value nor the total project cost has been disclosed.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"db21518c-9ab6-58b0-8572-18a1df09cf7f","s2":"4e17a2ee-2bd7-5860-90d6-6c2b51abf43c","s3":"035cc4b0-57d1-5e19-8842-07ccc8b6f5ea","s4":"36c2c165-107c-5b62-b856-6fa2c4b83cb4"},"source_file":"datacenters/projects/humain-al-saad-riyadh.json","source_record_id":"humain-al-saad-riyadh","source_record_sha256":"96bc082928e663285a75443429bde24b04b1e06b6936ea2388084e9d91203d90","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"bc3510e464d38087ca63b8e8813a3fa561fa124aa2fbbf7cc3e8d37cf3d497be"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a226e4ce3df02dee4be7/#project-4f8a32cf-b64b-51b4-8758-368320eb441d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/4f8a32cf-b64b-51b4-8758-368320eb441d.json
510a8216-64d9-5626-992a-3ca10f40fb90 | curated:tecra-ome-takinouecho:building-b | vcc-site-63daf0f8749544e0e6f4 | curated:tecra-ome-takinouecho | OME Data Center07 / DC5 Building B | Japan | JP | 35.7876 | 139.2569 | Point | campus | direct_geometry | developer_embedded_explicit_dms_target | developer_selected_parent_parcel_locator | official_source | campus_locator | Developer-selected original campus point decoded from explicit DMS target; not a building-B centroid or legal boundary. |  | No positional accuracy stated. Locator identifies the parent property; the exact subdivided data-center parcel and building outline are not established numerically. | e90c6601-0627-5995-8c17-9efee49ac630 | permitted | 2026-09-15 | 28 | authoritative_construction_permit | 85cffc8a-872c-5ce0-bba3-bd8f6880aced | authoritative_project_record_plus_scoped_location | FALSE | not_reviewed | unknown | not established by selected evidence | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://tecrowd.jp/column/construction-report/2026-09-fund-96-report/ | https://tecrowd.jp/funds/properties/103 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-63daf0f8749544e0e6f4/#project-510a8216-64d9-5626-992a-3ca10f40fb90 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/510a8216-64d9-5626-992a-3ca10f40fb90.json
511bfd88-0355-5080-b5ef-5a39ec51dfd8 | imported:semiconductor-atlas:ntt-gdc-tokyo-tky12-shiroi | vcc-site-627bed0b413c9b712d70 | imported:semiconductor-atlas:ntt-gdc-tokyo-tky12-shiroi | NTT Global Data Centers Tokyo TKY12 campus, Shiroi | Japan | JP | 35.7915 | 140.0563 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | NTT names Shiroi City, Chiba Prefecture, without an address. The point is the Shiroi city coordinate from its Wikipedia article, so it marks the city rather than the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 23498602-d954-533f-bdcc-e9bb8a865749 | announced | 2026-04-22 | 174 | imported_documented_status | 23498602-d954-533f-bdcc-e9bb8a865749 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"23498602-d954-533f-bdcc-e9bb8a865749","notes":"Data center subsidiary of NTT DATA Group, which co-issued the announcement.","party":"NTT Global Data Centers Corporation","relationship_scope":"unknown","role":"developer","source_record_id":"ntt-gdc-tokyo-tky12-shiroi"},{"evidence_id":"ffcd65e4-7913-5441-82ea-25b92f10501b","notes":"Data center subsidiary of NTT DATA Group, which co-issued the announcement.","party":"NTT Global Data Centers Corporation","relationship_scope":"unknown","role":"developer","source_record_id":"ntt-gdc-tokyo-tky12-shiroi"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.nttdata.com/global/ja/news/release/2026/041700/ | https://www.nttdata.com/global/ja/news/release/2026/041700/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve NTT Global Data Centers Tokyo TKY12 campus, Shiroi as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"ntt-gdc-tokyo-tky12-shiroi"},"record":{"aliases":["Tokyo TKY12","TKY12","東京TKY12データセンター"],"id":"ntt-gdc-tokyo-tky12-shiroi","last_reviewed":"2026-10-09","location":{"admin1":"Chiba Prefecture","country":"JP","lat":35.791472,"locality":"Shiroi","lon":140.056306,"note":"NTT names Shiroi City, Chiba Prefecture, without an address. The point is the Shiroi city coordinate from its Wikipedia article, so it marks the city rather than the site.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"power_capacity","note":"Total IT capacity of TKY12. NTT's headline figure of about 250 MW for the Inzai-Shiroi development matches TKY12 plus the nearby 50 MW TKY11, a separate facility, though the release does not break it down.","power_scope":"it_load","qualifier":"approximately","source_ids":["s1","s2"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":6}],"milestones":[{"date":"2026-04-17","event":"announced","kind":"actual","note":"NTT DATA and NTT GDC announced the start of development.","source_ids":["s1","s2"]},{"date":"2030","event":"first_operational","kind":"planned","note":"First building to start service in 2030 or later, after power is received from the utility.","source_ids":["s1","s2"]}],"name":"NTT Global Data Centers Tokyo TKY12 campus, Shiroi","notes":"The status is 'announced' because NTT described the start of development but gave no construction start date. TKY11, the nearby 50 MW facility due in April 2027, is not part of this record. Shiroi coordinates come from Wikipedia (s3), used only for the map point.","parties":[{"name":"NTT Global Data Centers Corporation","note":"Data center subsidiary of NTT DATA Group, which co-issued the announcement.","role":"developer","source_ids":["s1","s2"]}],"power_sources":[{"description":"Service at the first building depends on power being supplied by the local utility, which is not named.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260518175110/https://www.nttdata.com/global/ja/news/release/2026/041700/","id":"s1","published":"2026-04-17","publisher":"NTT DATA Group / NTT Global Data Centers","title":"国内最大級、千葉県印西・白井エリアで約250メガワット（MW）のデータセンターキャンパス開発を始動","type":"company","url":"https://www.nttdata.com/global/ja/news/release/2026/041700/"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-22","publisher":"W.Media","title":"NTT Data plans a 200 MW data center campus in Japan","type":"trade_press","url":"https://w.media/ntt-data-plans-a-200-mw-data-center-campus-in-japan/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260816121335/https://en.wikipedia.org/wiki/Shiroi","id":"s3","published":null,"publisher":"Wikipedia","title":"Shiroi","type":"other","url":"https://en.wikipedia.org/wiki/Shiroi"}],"status":"announced","status_as_of":"2026-04-22","status_source_ids":["s1","s2"],"summary":"NTT DATA Group and its data center arm NTT Global Data Centers announced in April 2026 that they had begun developing Tokyo TKY12, a six-building hyperscale campus in Shiroi City, Chiba Prefecture, in the Inzai-Shiroi data center cluster east of Tokyo. It is planned for about 200 MW of total IT capacity on a flat site about 20 m above sea level, near NTT's 50 MW TKY11 facility, which is due to open in April 2027. The first building is to enter service in 2030 or later, once the utility supplies power. No investment figure or construction start date has been disclosed.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"23498602-d954-533f-bdcc-e9bb8a865749","s2":"ffcd65e4-7913-5441-82ea-25b92f10501b","s3":"7abcc0e7-1bb1-5e8f-bd7b-a2e62f496464"},"source_file":"datacenters/projects/ntt-gdc-tokyo-tky12-shiroi.json","source_record_id":"ntt-gdc-tokyo-tky12-shiroi","source_record_sha256":"c52af1d01450703ae6fda9d5f4203a03ded8ba51f550658201e77e57c9ca559c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7d3b6bf29b3d9f3b4cfaafe76a0e0867e49d33ed83b25c0d5df1abf52ec66528"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-627bed0b413c9b712d70/#project-511bfd88-0355-5080-b5ef-5a39ec51dfd8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/511bfd88-0355-5080-b5ef-5a39ec51dfd8.json
51f3ec57-401e-5060-9d04-c2dfdfee6b1f | imported:semiconductor-atlas:elea-rio-ai-city | vcc-site-72339650a9d5c93e8286 | imported:semiconductor-atlas:elea-rio-ai-city | Rio AI City (Elea Data Centers) | Brazil | BR | -22.977 | -43.394 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Sources place the project in Rio de Janeiro's Olympic Park area without a parcel; coordinates are the Barra Olympic Park reference point (Wikipedia). Whether the existing RJO1 building sits inside the park was not stated. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 83146c8f-827a-54a2-8269-215420d9378e | partially_operational | 2026-10-09 | 4 | imported_documented_status | 83146c8f-827a-54a2-8269-215420d9378e | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"83146c8f-827a-54a2-8269-215420d9378e","notes":null,"party":"Elea Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"elea-rio-ai-city"},{"evidence_id":"b5c4278b-97d2-5e54-b148-35500a404e07","notes":null,"party":"Elea Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"elea-rio-ai-city"},{"evidence_id":"7fd232ad-4848-5625-bec1-83fd0705cb9a","notes":null,"party":"Elea Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"elea-rio-ai-city"},{"evidence_id":"b5c4278b-97d2-5e54-b148-35500a404e07","notes":null,"party":"Elea Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"elea-rio-ai-city"},{"evidence_id":"64a3981c-5cac-59cd-9830-9158e15b01ff","notes":"Completed its acquisition of Elea, per Elea's June 2026 release; terms not disclosed.","party":"I Squared Capital","relationship_scope":"unknown","role":"owner","source_record_id":"elea-rio-ai-city"},{"evidence_id":"83146c8f-827a-54a2-8269-215420d9378e","notes":"Provides institutional support through its economic development secretariat, CCPar and Invest.Rio; party to the 2025 memoranda.","party":"City of Rio de Janeiro","relationship_scope":"unknown","role":"government","source_record_id":"elea-rio-ai-city"},{"evidence_id":"b5c4278b-97d2-5e54-b148-35500a404e07","notes":"Provides institutional support through its economic development secretariat, CCPar and Invest.Rio; party to the 2025 memoranda.","party":"City of Rio de Janeiro","relationship_scope":"unknown","role":"government","source_record_id":"elea-rio-ai-city"},{"evidence_id":"55e3903f-88a9-5152-9541-fa5029bf0f5c","notes":"Provides institutional support through its economic development secretariat, CCPar and Invest.Rio; party to the 2025 memoranda.","party":"City of Rio de Janeiro","relationship_scope":"unknown","role":"government","source_record_id":"elea-rio-ai-city"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Elea Data Centers; I Squared Capital |  |  |  |  | https://www.prnewswire.com/news-releases/elea-announces-rio-ai-city-a-landmark-brazilian-data-center-project-with-capacity-up-to-3-2-gw-of-renewable-energy-supporting-ai-growth-302449289.html | https://www.prnewswire.com/news-releases/elea-announces-rio-ai-city-a-landmark-brazilian-data-center-project-with-capacity-up-to-3-2-gw-of-renewable-energy-supporting-ai-growth-302449289.html | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Rio AI City (Elea Data Centers) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"elea-rio-ai-city"},"record":{"aliases":["Rio AI City"],"id":"elea-rio-ai-city","last_reviewed":"2026-10-09","location":{"admin1":"Rio de Janeiro","country":"BR","lat":-22.977,"locality":"Rio de Janeiro (Olympic Park area)","lon":-43.394,"note":"Sources place the project in Rio de Janeiro's Olympic Park area without a parcel; coordinates are the Barra Olympic Park reference point (Wikipedia). Whether the existing RJO1 building sits inside the park was not stated.","precision":"approximate_site","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"phase","as_of":"2025-11-06","basis":"planned","metric":"power_capacity","note":"Described as energy capacity; the August 2025 release targets it for 2027.","phase_label":"Phase 1","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":1500},{"applies_to":"campus","as_of":"2025-11-06","basis":"planned","metric":"power_capacity","note":"Potential capacity by 2032 per the August and November 2025 releases; a June 2026 release refers to the project as 3 GW.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":3200},{"applies_to":"phase","as_of":"2025-05-08","basis":"under_construction","metric":"power_capacity","phase_label":"RJO2","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":80},{"applies_to":"phase","as_of":"2025-05-08","basis":"planned","metric":"power_capacity","phase_label":"RJO3 and RJO4","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":120}],"milestones":[{"date":"2025-05-08","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-08-14","event":"other","kind":"actual","note":"Memorandum of understanding signed by Elea, the City of Rio de Janeiro and Oracle to advance the project; Oracle's role was not specified.","source_ids":["s2"]},{"date":"2025-11-06","event":"other","kind":"actual","note":"Memorandum with the city, CCPar, Axia Energia, Light and Tapestry; the release presents Axia and Light as assurance of the city's ability to supply renewable energy to the project. Date is the release date.","source_ids":["s3"]},{"date":"2026","event":"other","kind":"planned","note":"Initial delivery of the RJO2 building.","source_ids":["s1","s4"]},{"date":"2027","event":"other","kind":"planned","note":"Target for the initial 1.5 GW.","source_ids":["s2"]}],"name":"Rio AI City (Elea Data Centers)","notes":"Elea's investment figures are inconsistent: the May 2025 release refers both to several billion dollars and to hundreds of billions of dollars of direct and indirect investment over a decade, so no investment metric is recorded. The status also rests on Elea's undated Rio AI City page, which lists RJO1 as operating and RJO2 as under construction, so status_as_of is the date it was read (2026-10-09). Axia Energia and Light signed the November 2025 memorandum, but no source states a supply or utility role for them, so they are not listed as parties.","parties":[{"name":"Elea Data Centers","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Elea Data Centers","role":"owner","source_ids":["s2"]},{"name":"I Squared Capital","note":"Completed its acquisition of Elea, per Elea's June 2026 release; terms not disclosed.","role":"owner","source_ids":["s5"]},{"name":"City of Rio de Janeiro","note":"Provides institutional support through its economic development secretariat, CCPar and Invest.Rio; party to the 2025 memoranda.","role":"government","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"Grid-connected; Elea says supply will be 100% renewable, certified energy.","source_ids":["s1","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260831105522/https://www.prnewswire.com/news-releases/elea-announces-rio-ai-city-a-landmark-brazilian-data-center-project-with-capacity-up-to-3-2-gw-of-renewable-energy-supporting-ai-growth-302449289.html","id":"s1","published":"2025-05-08","publisher":"Elea Data Centers via PR Newswire","title":"Elea announces Rio AI City, a landmark Brazilian data center project with capacity up to 3.2 GW of renewable energy supporting AI growth","type":"company","url":"https://www.prnewswire.com/news-releases/elea-announces-rio-ai-city-a-landmark-brazilian-data-center-project-with-capacity-up-to-3-2-gw-of-renewable-energy-supporting-ai-growth-302449289.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251006055127/https://www.prnewswire.com/news-releases/elea-signs-mou-with-oracle-and-rio-de-janeiro-city-hall-to-advance-data-center-project-302532403.html","id":"s2","published":"2025-08-18","publisher":"Elea Data Centers via PR Newswire","title":"Elea signs MoU with Oracle and Rio de Janeiro City Hall to advance data center project","type":"company","url":"https://www.prnewswire.com/news-releases/elea-signs-mou-with-oracle-and-rio-de-janeiro-city-hall-to-advance-data-center-project-302532403.html"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-06","publisher":"Elea Data Centers via PR Newswire","title":"Elea signs MoU with Tapestry to enhance assurance of Rio AI City's 1.5 GW energy capacity","type":"company","url":"https://www.prnewswire.com/news-releases/elea-signs-mou-with-tapestry-to-enhance-assurance-of-rio-ai-citys-1-5-gw-energy-capacity-302607345.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260514081519/http://eleadatacenters.com/rio-ai-city/","id":"s4","published":null,"publisher":"Elea Data Centers","title":"Rio AI City","type":"company","url":"https://eleadatacenters.com/rio-ai-city/"},{"accessed":"2026-10-09","id":"s5","published":"2026-06-03","publisher":"Elea Data Centers via PR Newswire","title":"Elea Data Centers appoints new board of directors to accelerate AI-ready infrastructure expansion in Brazil","type":"company","url":"https://www.prnewswire.com/news-releases/elea-data-centers-appoints-new-board-of-directors-to-accelerate-ai-ready-infrastructure-expansion-in-brazil-302790277.html"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s1","s4"],"summary":"Elea Data Centers is developing Rio AI City, a data centre hub in the Olympic Park area of Rio de Janeiro with institutional support from the city government. Announced in May 2025 with an initial 1.5 GW of energy capacity and potential growth to 3.2 GW, it was later targeted to reach 1.5 GW by 2027 and 3.2 GW by 2032. Elea counts its operating RJO1 facility in the first phase; RJO2 (about 80 MW) was under construction for initial delivery in 2026, and RJO3 and RJO4 would add 120 MW. Elea signed memoranda with the city and Oracle in August 2025 and with the city, energy companies and Tapestry in November 2025. I Squared Capital had completed its acquisition of Elea by June 2026.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"83146c8f-827a-54a2-8269-215420d9378e","s2":"b5c4278b-97d2-5e54-b148-35500a404e07","s3":"55e3903f-88a9-5152-9541-fa5029bf0f5c","s4":"7fd232ad-4848-5625-bec1-83fd0705cb9a","s5":"64a3981c-5cac-59cd-9830-9158e15b01ff"},"source_file":"datacenters/projects/elea-rio-ai-city.json","source_record_id":"elea-rio-ai-city","source_record_sha256":"a70ddfa5d408eb91c80390f034f2389a6219c51099d81f99882e101a2dccbf83","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"bea824de52d0566c84e4c3cb72e56bdb01896bd26b66fb8ddcfc551363f23849"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-72339650a9d5c93e8286/#project-51f3ec57-401e-5060-9d04-c2dfdfee6b1f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/51f3ec57-401e-5060-9d04-c2dfdfee6b1f.json
52b09d3a-44ac-5836-9724-7df5c69687bf | curated:university-edinburgh-acf:cr4-extension | vcc-site-315b5d219b6cb4413a2b | curated:university-edinburgh-acf | ACF CR4 extension | United Kingdom | GB | 55.8557 | -3.1995 | Point | campus | direct_geometry | bbox_center_of_named_osm_building | community_mapped_existing_campus_building_reference_point | community_source | campus_locator | Campus locator derived from the bounding-box centre of the existing named ACF building. OSM object address and name agree with the university procurement address. It does not delineate the CR4 extension, construction footprint, parcel or legal campus boundary. |  | OSM object states no positional accuracy | f0213b05-a7d9-5681-98b7-0bd38e6e0c53 | shell | 2026-09-22 | 21 | authoritative_physical_status_update | e18325f9-428c-5e08-af72-cbb1397d9f25 | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed | unknown | not established by selected evidence | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"2fcf925a-b3d0-5027-a685-797bf2096c0c","party":"University of Edinburgh","relationship_scope":"current","role":"owner"},{"evidence_id":"e18325f9-428c-5e08-af72-cbb1397d9f25","party":"EPCC, University of Edinburgh","relationship_scope":"current","role":"operator"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | University of Edinburgh | EPCC, University of Edinburgh |  |  |  | https://www.epcc.ed.ac.uk/whats-happening/articles/ai-minister-marks-milestone-supercomputer-build | https://www.openstreetmap.org/api/0.6/way/59574224/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-315b5d219b6cb4413a2b/#project-52b09d3a-44ac-5836-9724-7df5c69687bf | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/52b09d3a-44ac-5836-9724-7df5c69687bf.json
52d209cc-c8cd-5f8a-8337-cd887187f383 | curated:dansk-data-center-1-esbjerg-campus:ddc1-current-build | vcc-site-2c055eade62aa3fef4a9 | curated:dansk-data-center-1-esbjerg-campus | Dansk Data Center 1 Current Build | Denmark | DK | 55.4582 | 8.4599 | Point | campus | official_address_feature_to_point | dar_access_address_point_for_dma_bound_ddc1_site | official_access_address_point_as_campus_locator | official_source | campus_locator | Exact current DAR access-address point for Sahara 9, inherited through the DDC1 project_targets relationship. It is not a surveyed project point, entrance, parcel centroid, site boundary, building footprint, or construction extent. |  | DAR returns accuracy code A but the captured feature supplies no bounded numeric horizontal uncertainty applicable to this point. | d9a29ab2-cb25-5e79-a336-da8c0f65241c | under_construction | 2026-08-13 | 61 | authoritative_construction_start | e14a808e-a9b6-5304-9e5e-6e9a2cd1db0b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.cip.com/copenhagen-infrastructure-partners-p-s/r/cip-and-thylander-start-construction-of-energy-integrated-data-centre-in-denmark-backed-by-pensionda,c4383657?nfiid=3202 | https://api.dataforsyningen.dk/adgangsadresser/b0351879-20c7-47f9-8cde-54dad6a417a8?format=geojson&srid=4326 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2c055eade62aa3fef4a9/#project-52d209cc-c8cd-5f8a-8337-cd887187f383 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/52d209cc-c8cd-5f8a-8337-cd887187f383.json
52e21086-11ad-588d-a8a8-d9525e5e4744 | imported:semiconductor-atlas:google-kansas-city-north-missouri | vcc-site-210a7753dcf05471886c | imported:semiconductor-atlas:google-kansas-city-north-missouri | Google Kansas City data center campus (Hunt Midwest Business Center) | United States | US | 39.168 | -94.4788 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Approximate point on NE Parvin Road east of Interstate 435, within the Hunt Midwest Business Center that sources name as the site; the business park covers about 2,500 acres, so the data center parcel within it is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | aea3d2fe-d525-5a26-a903-592f579b298d | under_construction | 2026-10-09 | 4 | imported_documented_status | 923f1501-11f7-5010-927e-6ec8eadf0e42 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e365169e-229e-5558-ac33-be95c1c0b820","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"aea3d2fe-d525-5a26-a903-592f579b298d","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"62af04d0-bbdf-5718-bb48-f8e189bc272e","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"e61b8bc6-b13c-54ec-880d-6a70b1974074","notes":"Alphabet vehicle reported as buying the original 78.9 acres in 2019; the same report attributes a further 236.4-acre purchase in December 2021 to Google.","party":"Shalerock LLC","relationship_scope":"unknown","role":"owner","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"e365169e-229e-5558-ac33-be95c1c0b820","notes":null,"party":"Evergy","relationship_scope":"unknown","role":"utility","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"62af04d0-bbdf-5718-bb48-f8e189bc272e","notes":null,"party":"Evergy","relationship_scope":"unknown","role":"utility","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"81759cd0-cc6d-50b4-915d-1df10c3b28f8","notes":null,"party":"Evergy","relationship_scope":"unknown","role":"utility","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"e365169e-229e-5558-ac33-be95c1c0b820","notes":"Counterparty with DESRI to a PPA for 400 MW of new solar capacity from Beavertail Solar in Missouri; supply is grid-delivered, not on site.","party":"Ranger Power","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"aea3d2fe-d525-5a26-a903-592f579b298d","notes":"Counterparty with DESRI to a PPA for 400 MW of new solar capacity from Beavertail Solar in Missouri; supply is grid-delivered, not on site.","party":"Ranger Power","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"e365169e-229e-5558-ac33-be95c1c0b820","notes":"Counterparty with Ranger Power to the Beavertail Solar PPA.","party":"D. E. Shaw Renewable Investments","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"aea3d2fe-d525-5a26-a903-592f579b298d","notes":"Counterparty with Ranger Power to the Beavertail Solar PPA.","party":"D. E. Shaw Renewable Investments","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-kansas-city-north-missouri"},{"evidence_id":"e61b8bc6-b13c-54ec-880d-6a70b1974074","notes":"In 2019 the Port Authority of Kansas City authorized up to $25 billion of privately backed Chapter 68 bonds over 35 years with a property tax exemption for the project; officials said that ceiling did not reflect planned spending.","party":"Port KC","relationship_scope":"unknown","role":"government","source_record_id":"google-kansas-city-north-missouri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Shalerock LLC |  |  |  |  | https://datacenters.google/kansas-city-missouri/ | https://www.kshb.com/news/local-news/google-announces-1b-data-center-in-kansas-citys-northland | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Google Kansas City data center campus (Hunt Midwest Business Center) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"google-kansas-city-north-missouri"},"record":{"aliases":["Project Shale","Shale 1"],"id":"google-kansas-city-north-missouri","last_reviewed":"2026-10-09","location":{"admin1":"Missouri","admin2":"Clay County","country":"US","lat":39.168,"locality":"Kansas City","lon":-94.4788,"note":"Approximate point on NE Parvin Road east of Interstate 435, within the Hunt Midwest Business Center that sources name as the site; the business park covers about 2,500 acres, so the data center parcel within it is not pinpointed.","precision":"approximate_site","source_ids":["s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2024-03-20","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1","s2","s3","s4"],"unit":"USD","value":1000000000},{"applies_to":"phase","as_of":"2021-12-21","basis":"reported","metric":"investment","note":"Potential investment cited for the original 2019 proposal, before the 2024 announcement.","phase_label":"Project Shale phase 1 (2019 proposal on 78.9 acres)","qualifier":"exact","source_ids":["s5"],"unit":"USD","value":600000000},{"applies_to":"campus","as_of":"2021-12-21","basis":"acquired","metric":"land_area","qualifier":"more_than","source_ids":["s5","s7"],"unit":"acres","value":315},{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"floor_area","note":"Four-phase plan as described by a third-party data center listing; not confirmed by Google in an opened source.","qualifier":"approximately","source_ids":["s7"],"unit":"sq_ft","value":1435000}],"milestones":[{"date":"2021-12","event":"site_acquired","kind":"actual","note":"Purchase of 236.4 acres reported, adding to 78.9 acres bought in 2019.","source_ids":["s5"]},{"date":"2024-03-20","event":"announced","kind":"actual","source_ids":["s1","s2","s3","s4"]},{"date":"2025","event":"first_operational","kind":"actual","note":"Third-party listing gives 2025 as the year built and marks the first building operational, but its own description still says the campus is being developed; Google's page labels the Kansas City campus as in development. Unconfirmed.","source_ids":["s7"]}],"name":"Google Kansas City data center campus (Hunt Midwest Business Center)","notes":"Status follows Google's undated page, which labels Kansas City as in development with two new data centers being built, and an undated third-party listing that reports a building completed in 2025; status_as_of is the access date because neither page carries a publication date. The listing's claim that the first building is operational is not confirmed by Google, so the record is not marked partially operational. Google's March 2024 announcement tied the site to its AI and cloud business.","parties":[{"name":"Google","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Shalerock LLC","note":"Alphabet vehicle reported as buying the original 78.9 acres in 2019; the same report attributes a further 236.4-acre purchase in December 2021 to Google.","role":"owner","source_ids":["s5"]},{"name":"Evergy","role":"utility","source_ids":["s1","s3","s4"]},{"name":"Ranger Power","note":"Counterparty with DESRI to a PPA for 400 MW of new solar capacity from Beavertail Solar in Missouri; supply is grid-delivered, not on site.","role":"power_supplier","source_ids":["s1","s2"]},{"name":"D. E. Shaw Renewable Investments","note":"Counterparty with Ranger Power to the Beavertail Solar PPA.","role":"power_supplier","source_ids":["s1","s2"]},{"name":"Port KC","note":"In 2019 the Port Authority of Kansas City authorized up to $25 billion of privately backed Chapter 68 bonds over 35 years with a property tax exemption for the project; officials said that ceiling did not reflect planned spending.","role":"government","source_ids":["s5"]}],"power_sources":[{"description":"Evergy powers the site.","source_ids":["s1","s3"],"type":"grid"},{"description":"PPA for 400 MW of new-to-the-grid solar capacity from the Beavertail Solar farm in Missouri, with Ranger Power and DESRI.","source_ids":["s1","s2"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-03-20","publisher":"Missouri Public Service Commission (EFIS)","title":"Google announces $1 billion data center in Kansas City (exhibit ADS-D-4, Missouri PSC EFIS document 881306)","type":"regulatory_filing","url":"https://efis.psc.mo.gov/Document/Display/881306"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"KSHB 41","title":"Google announces $1B data center in Kansas City's Northland","type":"news","url":"https://www.kshb.com/news/local-news/google-announces-1b-data-center-in-kansas-citys-northland"},{"accessed":"2026-10-09","id":"s3","published":"2024-03-20","publisher":"Startland News","title":"Google to build $1B data center in Kansas City; aiming for 24/7 carbon-free energy use","type":"news","url":"https://www.startlandnews.com/2024/03/google-data-center-kansas-city/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250729182201/https://www.kctv5.com/2024/03/20/google-build-1-billion-data-center-kansas-city/","id":"s4","published":"2024-03-20","publisher":"KCTV5","title":"Google to build $1 billion data center in Kansas City","type":"news","url":"https://www.kctv5.com/2024/03/20/google-build-1-billion-data-center-kansas-city/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20240616014903/https://thetechcapital.com/google-eyes-315-acre-hyperscale-data-center-in-kansas/","id":"s5","published":"2021-12-21","publisher":"The Tech Capital","title":"Google eyes 315-acre hyperscale data center in Kansas","type":"trade_press","url":"https://thetechcapital.com/google-eyes-315-acre-hyperscale-data-center-in-kansas/"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Google","title":"Kansas City, Missouri - Google Data Center Location","type":"company","url":"https://datacenters.google/kansas-city-missouri/"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Baxtel","title":"Google: Shale 1 Data Center","type":"other","url":"https://baxtel.com/data-center/google-project-shale-0a8fa63e-b8b8-4b88-8e64-5c693d39337c"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s6","s7"],"summary":"Google's first Missouri data center campus, at the Hunt Midwest Business Center off NE Parvin Road in Kansas City's Northland (Clay County). Google announced the $1 billion project in March 2024, with Evergy powering the site and a 400 MW solar PPA from the Beavertail Solar farm with Ranger Power and DESRI. Google, partly through the Alphabet vehicle Shalerock LLC, had assembled more than 315 acres in the Northland by late 2021 for a project called Project Shale. Google's site now describes two new data centers in Kansas City as in development, while a third-party listing reports the first building operational since 2025 within a four-phase plan of about 1.435 million sq ft.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e365169e-229e-5558-ac33-be95c1c0b820","s2":"aea3d2fe-d525-5a26-a903-592f579b298d","s3":"62af04d0-bbdf-5718-bb48-f8e189bc272e","s4":"81759cd0-cc6d-50b4-915d-1df10c3b28f8","s5":"e61b8bc6-b13c-54ec-880d-6a70b1974074","s6":"923f1501-11f7-5010-927e-6ec8eadf0e42","s7":"ef0a3222-cfb6-5a0b-86ba-43a207bb86f5"},"source_file":"datacenters/projects/google-kansas-city-north-missouri.json","source_record_id":"google-kansas-city-north-missouri","source_record_sha256":"ff3821d41bcbe972e96eea44675b44c40ca6bf0de0fe22200f1d43ef1b6bc34c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"379285710e5e7a644ccdcd6da60bd24089a439f25f01b411566cf304514db23d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-210a7753dcf05471886c/#project-52e21086-11ad-588d-a8a8-d9525e5e4744 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/52e21086-11ad-588d-a8a8-d9525e5e4744.json
53a18106-0c3f-5249-8717-107230729abc | imported:semiconductor-atlas:softbank-sesterce-bosquel | vcc-site-6bf2ad82353d1ed7d3c9 | imported:semiconductor-atlas:softbank-sesterce-bosquel | SoftBank-Sesterce Bosquel AI data center | France | FR | 49.7391 | 2.2179 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Nominatim centroid of the commune of Bosquel (Somme); sources name the commune only. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f59be53e-26ee-5e1c-b1ad-7b5ff0f833ed | announced | 2026-06-01 | 134 | imported_documented_status | f59be53e-26ee-5e1c-b1ad-7b5ff0f833ed | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f59be53e-26ee-5e1c-b1ad-7b5ff0f833ed","notes":"Majority owner of the joint venture.","party":"SoftBank Group","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-sesterce-bosquel"},{"evidence_id":"27ef5292-9eef-504b-97ab-5d854f237d7f","notes":"Majority owner of the joint venture.","party":"SoftBank Group","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-sesterce-bosquel"},{"evidence_id":"f59be53e-26ee-5e1c-b1ad-7b5ff0f833ed","notes":"Joint venture partner; the venture as a whole was selected to develop and operate the campus.","party":"Sesterce","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-sesterce-bosquel"},{"evidence_id":"27ef5292-9eef-504b-97ab-5d854f237d7f","notes":"Joint venture partner; the venture as a whole was selected to develop and operate the campus.","party":"Sesterce","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-sesterce-bosquel"},{"evidence_id":"f59be53e-26ee-5e1c-b1ad-7b5ff0f833ed","notes":"Named as a partner; the Somme prefect refers to a call for expressions of interest launched by the CC2SO, the community of communes' abbreviation.","party":"Communauté de communes Somme Sud-Ouest","relationship_scope":"unknown","role":"government","source_record_id":"softbank-sesterce-bosquel"},{"evidence_id":"27ef5292-9eef-504b-97ab-5d854f237d7f","notes":"Named as a partner; the Somme prefect refers to a call for expressions of interest launched by the CC2SO, the community of communes' abbreviation.","party":"Communauté de communes Somme Sud-Ouest","relationship_scope":"unknown","role":"government","source_record_id":"softbank-sesterce-bosquel"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://group.softbank/en/news/press/20260531 | https://group.softbank/en/news/press/20260531 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve SoftBank-Sesterce Bosquel AI data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"softbank-sesterce-bosquel"},"record":{"aliases":["Bosquel AI campus"],"id":"softbank-sesterce-bosquel","last_reviewed":"2026-10-09","location":{"admin1":"Hauts-de-France","admin2":"Somme","country":"FR","lat":49.7391,"locality":"Bosquel","lon":2.2179,"note":"Nominatim centroid of the commune of Bosquel (Somme); sources name the commune only.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-31","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-05-31","basis":"planned","metric":"jobs_permanent","qualifier":"exact","source_ids":["s1"],"unit":"count","value":400}],"milestones":[{"date":"2026-05-30","event":"announced","kind":"actual","note":"Announced in Paris alongside SoftBank's 5 GW France plan at Choose France 2026.","source_ids":["s1","s3"]}],"name":"SoftBank-Sesterce Bosquel AI data center","notes":"SoftBank's France plan gives an initial EUR 45 billion for 3.1 GW across Dunkirk (Loon-Plage), Bosquel and Bouchain by 2031, without a per-site split, so no investment is attributed to Bosquel. The campus design is by architecture firm Patriarche.","parties":[{"name":"SoftBank Group","note":"Majority owner of the joint venture.","role":"developer","source_ids":["s1","s2"]},{"name":"Sesterce","note":"Joint venture partner; the venture as a whole was selected to develop and operate the campus.","role":"developer","source_ids":["s1","s2"]},{"name":"Communauté de communes Somme Sud-Ouest","note":"Named as a partner; the Somme prefect refers to a call for expressions of interest launched by the CC2SO, the community of communes' abbreviation.","role":"government","source_ids":["s1","s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-05-31","publisher":"SoftBank Group","title":"SoftBank Group and Sesterce to Develop 1 GW AI Data Center in Bosquel, France","type":"company","url":"https://group.softbank/en/news/press/20260531"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260719180330/https://www.sesterce.com/newsroom/softbank-group-sesterce-1gw-ai-data-center-bosquel-france","id":"s2","published":"2026-06-01","publisher":"Sesterce","title":"SoftBank Group and Sesterce to Develop 1 GW AI Data Center in Bosquel, France","type":"company","url":"https://www.sesterce.com/newsroom/softbank-group-sesterce-1gw-ai-data-center-bosquel-france"},{"accessed":"2026-10-09","id":"s3","published":"2026-05-31","publisher":"SoftBank Group","title":"SoftBank Group to Build 5 GW of AI Data Center Capacity in France","type":"company","url":"https://group.softbank/en/news/press/20260531_0"}],"status":"announced","status_as_of":"2026-06-01","status_source_ids":["s1","s2"],"summary":"A joint venture majority-owned by SoftBank Group and formed with Sesterce was selected to develop and operate a 1 GW AI data center campus in Bosquel, Somme, in the Hauts-de-France region. Announced on 2026-05-30 as part of the 2026 Choose France summit, it is one of three named Hauts-de-France sites in SoftBank's 5 GW France plan. No investment figure, construction schedule or permit status has been published for the site; SoftBank cites about 400 long-term jobs once it operates.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f59be53e-26ee-5e1c-b1ad-7b5ff0f833ed","s2":"27ef5292-9eef-504b-97ab-5d854f237d7f","s3":"e1cecd9d-e332-58f0-9b1b-4e7dfb13e101"},"source_file":"datacenters/projects/softbank-sesterce-bosquel.json","source_record_id":"softbank-sesterce-bosquel","source_record_sha256":"eb3ff773b740b83fac744a336f55d4b004403fa67da697dbc4c4340bb3aa23dd","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"87f6315aa67b2532e26f672b5172cf4c61921d629ae1c7cc9864f727d45400f5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6bf2ad82353d1ed7d3c9/#project-53a18106-0c3f-5249-8717-107230729abc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/53a18106-0c3f-5249-8717-107230729abc.json
5443b4c1-09dc-5f14-a9a3-ec32c05602fb | curated:datar-rellingen-campus:current-build | vcc-site-8511f5b23fe433a2c61f | curated:datar-rellingen-campus | dataR Rellingen Current Construction | Germany | DE | 53.635 | 9.8728 | Point | campus | Literal native OSM node point; named latitude/longitude axis order only; independently matched to same Nominatim node | community_named_exact_address_site_node | named_site_address_point | community_source | campus_locator | Exact mapped dataR site-address node only; not a current-work footprint, cadastral parcel, campus boundary, building centroid, headquarters substitute, road point or entrance. Decimal precision retained without an accuracy claim. |  | OSM native node and Nominatim result do not provide positional accuracy or original survey provenance. Seven-decimal storage precision is not feature accuracy. | 58396c5d-9232-5398-b381-bc3c594518f3 | under_construction | 2026-07-17 | 88 | authoritative_physical_status_update | 1fdde38e-79d4-5d65-83e5-f686e75392a1 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.datar.de/zwei-neue-kollegen-ein-gemeinsamer-start/ | https://api.openstreetmap.org/api/0.6/node/11707884695.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8511f5b23fe433a2c61f/#project-5443b4c1-09dc-5f14-a9a3-ec32c05602fb | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5443b4c1-09dc-5f14-a9a3-ec32c05602fb.json
546bf83f-2bb4-5539-b576-6b7100981420 | curated:databank-red-oak-campus:first-phase-current-build | vcc-site-de7d1b5d61517ef55cfe | curated:databank-red-oak-campus | DataBank Red Oak First-Phase Current Construction | United States | US | 32.5382 | -96.7349 | Point | campus | official_named_address_point | native_EPSG2276_to_EPSG4326_pyproj_NAD83_to_WGS84_1 | official_address_reference_point | official_source | campus_locator | One literal county Site address point at the exact operator-defined DFW10 address, used to locate the single Red Oak campus. Not a surveyed building point, boundary, centroid, entrance or observed work footprint; decimal digits retain computational precision only. |  | County supplies no numeric positional accuracy for this Site address point. Four-metre transformation operation accuracy is not feature accuracy. | 100ab544-05a4-5194-a4af-64a391377239 | under_construction | 2026-07-26 | 79 | authoritative_physical_status_update | 0d151e84-b2af-5d9b-b996-2fe97116bb58 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.databank.com/resources/news/inside-databanks-multibillion-dollar-red-oak-data-center-campus/ | https://maps.co.ellis.tx.us/arcgis/rest/services/Elections/External_Elections_Web_Map/MapServer/888/query?objectIds=70622&outFields=OBJECTID,Address,AddressLong,LandmkName,Placement,Parcel_ID,Source,DateUpdate,Post_Comm,Post_Code&returnGeometry=true&outSR=2276&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-de7d1b5d61517ef55cfe/#project-546bf83f-2bb4-5539-b576-6b7100981420 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/546bf83f-2bb4-5539-b576-6b7100981420.json
54782d37-d21e-5ddf-990b-a578130ac9d0 | imported:semiconductor-atlas:deutsche-telekom-nvidia-munich | vcc-site-9bb64eeea962a4cadd06 | imported:semiconductor-atlas:deutsche-telekom-nvidia-munich | Deutsche Telekom Industrial AI Cloud, Munich Tucherpark | Germany | DE | 48.1527 | 11.5991 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Nominatim geocode of the street Am Tucherpark in Munich; sources name the Tucherpark complex beside the Eisbach but give no street address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d6c36486-e845-5998-b33f-0204a765588a | partially_operational | 2026-02-04 | 251 | imported_documented_status | d6c36486-e845-5998-b33f-0204a765588a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"dd73e995-5ede-5599-8fd7-41810834d183","notes":"Provides the physical infrastructure; its subsidiary T-Systems runs the infrastructure and platform layer.","party":"Deutsche Telekom","relationship_scope":"unknown","role":"developer","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"d6c36486-e845-5998-b33f-0204a765588a","notes":"Provides the physical infrastructure; its subsidiary T-Systems runs the infrastructure and platform layer.","party":"Deutsche Telekom","relationship_scope":"unknown","role":"developer","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"d6c36486-e845-5998-b33f-0204a765588a","notes":"Telekom states that it operates the AI factory.","party":"Deutsche Telekom","relationship_scope":"unknown","role":"operator","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"d6c36486-e845-5998-b33f-0204a765588a","notes":"Telekom's data center partner that built the site with NVIDIA; heise reports that Polarise installs and operates the hardware.","party":"Polarise","relationship_scope":"unknown","role":"operator","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"3b4d4ed2-ae2c-5c50-97b6-3f7e70b1338e","notes":"Telekom's data center partner that built the site with NVIDIA; heise reports that Polarise installs and operates the hardware.","party":"Polarise","relationship_scope":"unknown","role":"operator","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"dd73e995-5ede-5599-8fd7-41810834d183","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"d6c36486-e845-5998-b33f-0204a765588a","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"dd73e995-5ede-5599-8fd7-41810834d183","notes":"Named by Telekom as an example user of the cloud; TechCrunch also said its robots would install server racks at the site.","party":"Agile Robots","relationship_scope":"unknown","role":"tenant","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"d6c36486-e845-5998-b33f-0204a765588a","notes":"Named by Telekom as an example user of the cloud; TechCrunch also said its robots would install server racks at the site.","party":"Agile Robots","relationship_scope":"unknown","role":"tenant","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"d6c36486-e845-5998-b33f-0204a765588a","notes":"Early customer.","party":"PhysicsX","relationship_scope":"unknown","role":"tenant","source_record_id":"deutsche-telekom-nvidia-munich"},{"evidence_id":"dd73e995-5ede-5599-8fd7-41810834d183","notes":"Named in the November 2025 announcement as planning in-country AI inference at the facility.","party":"Perplexity","relationship_scope":"unknown","role":"tenant","source_record_id":"deutsche-telekom-nvidia-munich"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Deutsche Telekom; Polarise |  | Agile Robots; Perplexity; PhysicsX |  | https://www.telekom.com/de/newsroom/aktuelles/medieninformationen/2026/02/deutschlands-erste-ki-fabrik-fuer-die-industrie | https://www.telekom.com/de/newsroom/aktuelles/medieninformationen/2026/02/deutschlands-erste-ki-fabrik-fuer-die-industrie | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Deutsche Telekom Industrial AI Cloud, Munich Tucherpark as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"deutsche-telekom-nvidia-munich"},"record":{"aliases":["Industrial AI Cloud","Telekom AI factory Munich","KI-Fabrik München"],"id":"deutsche-telekom-nvidia-munich","last_reviewed":"2026-10-09","location":{"admin1":"Bavaria","admin2":"Munich","country":"DE","lat":48.1527,"locality":"Munich (Tucherpark)","lon":11.5991,"note":"Nominatim geocode of the street Am Tucherpark in Munich; sources name the Tucherpark complex beside the Eisbach but give no street address.","precision":"approximate_site","source_ids":["s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-04","basis":"announced","metric":"investment","note":"Heise reports Telekom's statement that the sum was invested by Telekom and its partners.","qualifier":"approximately","source_ids":["s1","s3","s4"],"unit":"EUR","value":1000000000},{"accelerator_model":"NVIDIA Blackwell (DGX B200 and RTX PRO servers)","applies_to":"campus","as_of":"2026-02-04","basis":"planned","metric":"accelerators","note":"The November 2025 announcement gave up to 10,000 Blackwell GPUs.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"count","value":10000},{"applies_to":"campus","as_of":"2026-02-04","basis":"planned","metric":"power_capacity","note":"Trade press estimate of total supply and cooling capacity; not a company figure.","power_scope":"unspecified","qualifier":"range","source_ids":["s3"],"unit":"MW","value":15,"value_high":20},{"applies_to":"campus","as_of":"2026-02-04","basis":"operational","metric":"floor_area","note":"Area of the former data center that was gutted and modernized.","qualifier":"approximately","source_ids":["s2"],"unit":"sq_m","value":10700}],"milestones":[{"date":"2025-11-04","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025","event":"construction_started","kind":"actual","note":"Trade press says work had been under way since mid-2025.","source_ids":["s3"]},{"date":"2026-02-04","event":"first_operational","kind":"actual","note":"Official opening; Telekom said existing customers already used more than a third of its capacity.","source_ids":["s2","s3"]}],"name":"Deutsche Telekom Industrial AI Cloud, Munich Tucherpark","notes":"Qualifies on investment (about EUR 1 billion); reported power is far below 100 MW. Status is partially operational because the opening press reported the halls far from fully fitted out, while Telekom described the site as officially in operation. Germany Trade & Invest reports Telekom plans to double to 20,000 GPUs without naming a site.","parties":[{"name":"Deutsche Telekom","note":"Provides the physical infrastructure; its subsidiary T-Systems runs the infrastructure and platform layer.","role":"developer","source_ids":["s1","s2"]},{"name":"Deutsche Telekom","note":"Telekom states that it operates the AI factory.","role":"operator","source_ids":["s2"]},{"name":"Polarise","note":"Telekom's data center partner that built the site with NVIDIA; heise reports that Polarise installs and operates the hardware.","role":"operator","source_ids":["s2","s3"]},{"name":"NVIDIA","role":"hardware_supplier","source_ids":["s1","s2"]},{"name":"Agile Robots","note":"Named by Telekom as an example user of the cloud; TechCrunch also said its robots would install server racks at the site.","role":"tenant","source_ids":["s1","s2"]},{"name":"PhysicsX","note":"Early customer.","role":"tenant","source_ids":["s2"]},{"name":"Perplexity","note":"Named in the November 2025 announcement as planning in-country AI inference at the facility.","role":"tenant","source_ids":["s1"]}],"power_sources":[{"description":"Telekom says the facility runs entirely on renewable energy; the supply arrangement is not described. Cooling uses Eisbach stream water, and waste heat is to heat the Tucherpark quarter.","source_ids":["s2","s4"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251127060716/https://techcrunch.com/2025/11/04/nvidia-deutsche-telekom-strike-e1b-partnership-for-a-data-center-in-munich/","id":"s1","published":"2025-11-04","publisher":"TechCrunch","title":"Nvidia, Deutsche Telekom strike €1B partnership for a data center in Munich","type":"news","url":"https://techcrunch.com/2025/11/04/nvidia-deutsche-telekom-strike-e1b-partnership-for-a-data-center-in-munich"},{"accessed":"2026-10-09","id":"s2","published":"2026-02-04","publisher":"Deutsche Telekom","title":"Deutschlands erste KI-Fabrik für die Industrie geht in München offiziell in Betrieb","type":"company","url":"https://www.telekom.com/de/newsroom/aktuelles/medieninformationen/2026/02/deutschlands-erste-ki-fabrik-fuer-die-industrie"},{"accessed":"2026-10-09","id":"s3","published":"2026-02-04","publisher":"heise online","title":"Telekom data center to boost German AI performance by half","type":"trade_press","url":"https://heise.de/-11165327"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-15","publisher":"Germany Trade & Invest","title":"Industrial strength meets AI infrastructure","type":"government","url":"https://www.gtai.de/en/invest/service/publications/markets-germany/industrial-strength-meets-ai-infrastructure-2011304"}],"status":"partially_operational","status_as_of":"2026-02-04","status_source_ids":["s2","s3"],"summary":"Deutsche Telekom and NVIDIA converted an existing underground data center in Munich's Tucherpark into an AI factory branded the Industrial AI Cloud, at a reported cost of about EUR 1 billion from Telekom and its partners. It is designed for about 10,000 NVIDIA Blackwell GPUs (around 0.5 exaflops) and uses water from the Eisbach stream for cooling. The site officially opened on 2026-02-04 with first customers live, though trade press reported the four GPU halls were still far from complete.","workloads":["ai_inference","ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"dd73e995-5ede-5599-8fd7-41810834d183","s2":"d6c36486-e845-5998-b33f-0204a765588a","s3":"3b4d4ed2-ae2c-5c50-97b6-3f7e70b1338e","s4":"fd240270-e372-5abb-97ae-b009994f39ca"},"source_file":"datacenters/projects/deutsche-telekom-nvidia-munich.json","source_record_id":"deutsche-telekom-nvidia-munich","source_record_sha256":"4bcdf47b4a9cad5a44cc8dbea515091ace6e23bf69ea7cc718e42e346f184cfa","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0bdaff010bf1a8c44d17b5bd5b045011b3d5bd572c1cfed6e77f8170f2476655"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9bb64eeea962a4cadd06/#project-54782d37-d21e-5ddf-990b-a578130ac9d0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/54782d37-d21e-5ddf-990b-a578130ac9d0.json
55a2bfbb-45b2-5d51-bc40-4cc74d88ccfd | imported:semiconductor-atlas:humain-dammam | vcc-site-8f9f601fd64ed7dfc62c | imported:semiconductor-atlas:humain-dammam | HUMAIN Dammam AI data centre | Saudi Arabia | SA | 26.433 | 50.1 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Dammam only. Coordinates are the Dammam city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | c9f21c02-2182-5b65-8bc0-367b74112020 | under_construction | 2025-08-26 | 413 | imported_documented_status | c9f21c02-2182-5b65-8bc0-367b74112020 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c9f21c02-2182-5b65-8bc0-367b74112020","notes":null,"party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"humain-dammam"},{"evidence_id":"285df9c4-2bcd-53b6-b852-c3c1d5c66025","notes":null,"party":"HUMAIN","relationship_scope":"unknown","role":"developer","source_record_id":"humain-dammam"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.arabnews.com/node/2613050/business-economy | https://www.arabnews.com/node/2613050/business-economy | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve HUMAIN Dammam AI data centre as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"humain-dammam","source_relations":[{"reason":"Distinct HUMAIN initial Dammam build and Khazna first Saudi campus announcement; shared Dammam city coordinates do not establish the same physical site.","relationship":"separate_named_developments","source_id":"khazna-dammam"}]},"record":{"aliases":[],"id":"humain-dammam","last_reviewed":"2026-10-09","location":{"admin1":"Eastern Province","country":"SA","lat":26.433,"locality":"Dammam","lon":50.1,"note":"Sources name Dammam only. Coordinates are the Dammam city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"phase","as_of":"2025-08-26","basis":"planned","metric":"power_capacity","note":"Reuters, citing Bloomberg, gives up to 100 MW of initial capacity for each of the Riyadh and Dammam sites. Capacity's write-up of the same interview does not split the figure by site.","phase_label":"Initial capacity","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":100}],"milestones":[{"date":"2026-Q2","event":"first_operational","kind":"planned","note":"Reports of the August 2025 interview give both early 2026 and the second quarter of 2026 as the launch target.","source_ids":["s1","s2"]}],"name":"HUMAIN Dammam AI data centre","notes":"Both sources report the same Bloomberg interview with HUMAIN's chief executive. The second-quarter 2026 launch target has passed, and no source opened for this record confirms whether the site is operating.","parties":[{"name":"HUMAIN","role":"developer","source_ids":["s1","s2"]}],"power_sources":[],"related_ids":["humain-riyadh","humain-al-saad-riyadh"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-08-26","publisher":"Arab News (Reuters)","title":"Saudi Arabia's Humain to launch data centers with US chips in early 2026, Bloomberg News reports","type":"news","url":"https://www.arabnews.com/node/2613050/business-economy"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260218143715/https://capacityglobal.com/news/humain-data-centre-construction-saudi-arabia/","id":"s2","published":"2025-08-26","publisher":"Capacity","title":"How Humain plans to use US chips in new Saudi Arabia AI data centres","type":"trade_press","url":"https://capacityglobal.com/news/humain-data-centre-construction-saudi-arabia/"}],"status":"under_construction","status_as_of":"2025-08-26","status_source_ids":["s1","s2"],"summary":"One of the first two data centres of HUMAIN, the Public Investment Fund's AI company, under construction in Dammam in the Eastern Province as of August 2025. HUMAIN's chief executive said each of the two initial sites, in Riyadh and Dammam, would open with up to 100 MW, using US chips including NVIDIA's latest accelerators, with launch targeted for the second quarter of 2026 (headlines said early 2026). The sources reviewed give no district, building details or investment figure, and no later progress report was found.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c9f21c02-2182-5b65-8bc0-367b74112020","s2":"285df9c4-2bcd-53b6-b852-c3c1d5c66025"},"source_file":"datacenters/projects/humain-dammam.json","source_record_id":"humain-dammam","source_record_sha256":"9aef373592e1bca1eb175c6a68277e31943df1b2bc543a48f2af8a73ada08d22","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"466341e154fa7fe2a30d1b4b4d02a5a2b8fe8d4f4240ab1a972ddbf599bed805"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8f9f601fd64ed7dfc62c/#project-55a2bfbb-45b2-5d51-bc40-4cc74d88ccfd | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/55a2bfbb-45b2-5d51-bc40-4cc74d88ccfd.json
55df6642-2ef8-5b72-a965-996a28bdfb24 | imported:semiconductor-atlas:microsoft-middenmeer-campus-west | vcc-site-04be359939cf11193024 | imported:semiconductor-atlas:microsoft-middenmeer-campus-west | Microsoft Middenmeer Campus West expansion (Agriport Plot B) | Netherlands | NL | 52.783 | 5.0254 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Point of OSM way 1428523639 in the local OpenStreetMap layer, a Microsoft area tagged as a proposed datacenter expansion west of Microsoft's existing Agriport buildings; it is consistent with Microsoft's description of Plot B west of the A7 but is not confirmed by Microsoft. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d781093d-2c20-51bc-a765-09bc25052ccf | announced | 2026-03-25 | 202 | imported_documented_status | d781093d-2c20-51bc-a765-09bc25052ccf | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d781093d-2c20-51bc-a765-09bc25052ccf","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-middenmeer-campus-west"},{"evidence_id":"2f975102-6fc9-5fb4-8634-9b787db77ac8","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-middenmeer-campus-west"},{"evidence_id":"9b24d4d4-ca66-5373-bb0a-06cd55ffceca","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-middenmeer-campus-west"},{"evidence_id":"9b24d4d4-ca66-5373-bb0a-06cd55ffceca","notes":"Competent authority for the environmental permit; the Omgevingsdienst Noordzeekanaalgebied runs the EIA procedure on its behalf.","party":"Provincie Noord-Holland (Gedeputeerde Staten)","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-middenmeer-campus-west"},{"evidence_id":"d781093d-2c20-51bc-a765-09bc25052ccf","notes":"Described by Microsoft as a cooperation partner for the new phase.","party":"Gemeente Hollands Kroon","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-middenmeer-campus-west"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://local.microsoft.com/blog/microsoft-bouwt-aan-toekomstbestendige-datacentercampus-in-middenmeer/ | https://local.microsoft.com/blog/microsoft-bouwt-aan-toekomstbestendige-datacentercampus-in-middenmeer/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Middenmeer Campus West expansion (Agriport Plot B) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-middenmeer-campus-west"},"record":{"aliases":["Uitbreiding Campus West Microsoft","Microsoft Middenmeer Plot B"],"id":"microsoft-middenmeer-campus-west","last_reviewed":"2026-10-09","location":{"admin1":"Noord-Holland","admin2":"Hollands Kroon","country":"NL","lat":52.78304,"locality":"Middenmeer","lon":5.025355,"note":"Point of OSM way 1428523639 in the local OpenStreetMap layer, a Microsoft area tagged as a proposed datacenter expansion west of Microsoft's existing Agriport buildings; it is consistent with Microsoft's description of Plot B west of the A7 but is not confirmed by Microsoft.","precision":"approximate_site","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-25","basis":"planned","metric":"power_capacity","note":"Commission estimate derived from backup generator capacity, not planned datacenter demand published by Microsoft: the Commissie m.e.r. read the scoping document as planning 160 emergency generators of 3.3 MWe and six of about 1.1 MWe, and, assuming the power needed equals that installed generator capacity, put continuous electrical demand at about 535 MWe. It is not a permitted or contracted capacity.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":535},{"applies_to":"campus","as_of":"2025-12","basis":"planned","metric":"land_area","note":"Size of Plot B; the plan includes a 10-hectare publicly accessible nature area.","qualifier":"approximately","source_ids":["s2"],"unit":"hectares","value":53},{"applies_to":"campus","as_of":"2026-03-25","basis":"planned","metric":"buildings","note":"New double-storey datacenter buildings, joining the two existing AMS13-14 buildings to form an eight-building campus.","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":6}],"milestones":[{"date":"2025-09-10","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-12-03","event":"other","kind":"actual","note":"Public information market in Middenmeer; Microsoft's indicative timeline put the start of the EIA process in December 2025.","source_ids":["s1","s2"]},{"date":"2026-03-25","event":"other","kind":"actual","note":"Commissie m.e.r. issued its scoping advice on the environmental impact report, which is required because the emergency generators exceed 300 MW thermal.","source_ids":["s3"]},{"date":"2026-09","event":"other","kind":"planned","note":"Indicative date for submitting the permit application.","source_ids":["s2"]},{"date":"2027","event":"construction_started","kind":"planned","note":"Indicative start at the end of 2027, dependent on permitting.","source_ids":["s2"]}],"name":"Microsoft Middenmeer Campus West expansion (Agriport Plot B)","notes":"Covers only the new six-building phase and its link to AMS13-14 (Westlanderweg 50); the EIA commission says Microsoft already has nine datacenters in Middenmeer, not recorded here. The only power figure is the commission's 535 MWe estimate, which assumes continuous demand equals the planned emergency generator capacity; its background text mentions 120 to 150 generators. Microsoft's living campus page has no entry newer than 17 February 2026 (first trees planted on Plot B), so status rests on the March 2026 advice. No evidence of the planned September 2026 permit application was found; a July 2026 report of a further land purchase was not opened.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Provincie Noord-Holland (Gedeputeerde Staten)","note":"Competent authority for the environmental permit; the Omgevingsdienst Noordzeekanaalgebied runs the EIA procedure on its behalf.","role":"government","source_ids":["s3"]},{"name":"Gemeente Hollands Kroon","note":"Described by Microsoft as a cooperation partner for the new phase.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Emergency generators (120 to 150 in the commission's background text, 160 of 3.3 MWe plus six smaller units in its reading of the scoping document) and two substations; fuel is not stated, and Microsoft says it aims to stop using diesel for backup power by 2030.","source_ids":["s2","s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Microsoft","title":"Microsoft bouwt aan toekomstbestendige datacentercampus in Middenmeer","type":"company","url":"https://local.microsoft.com/blog/microsoft-bouwt-aan-toekomstbestendige-datacentercampus-in-middenmeer/"},{"accessed":"2026-10-09","id":"s2","published":"2025-12","publisher":"Microsoft","title":"Information market 3 December 2025: new datacentre development in Middenmeer","type":"company","url":"https://local.microsoft.com/wp-content/uploads/2026/01/Information-market-3-december-2025.pdf"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-25","publisher":"Commissie voor de milieueffectrapportage","title":"Uitbreiding Campus West Microsoft, provincie Noord-Holland: advies over reikwijdte en detailniveau van het milieueffectrapport","type":"government","url":"https://pas.commissiemer.nl/files/nl/4021/a4021rd.pdf"}],"status":"announced","status_as_of":"2026-03-25","status_source_ids":["s1","s3"],"summary":"Proposed expansion of Microsoft's datacenters at the Agriport A7 business park in Middenmeer, Hollands Kroon, North Holland. Announced in September 2025, it would add six double-storey datacenter buildings on Plot B, a site of about 53 hectares west of the A7 next to Microsoft's AMS13-14 datacenters, plus a 10-hectare public nature area, forming one eight-building campus. Microsoft has published no capacity figure; in March 2026 the national EIA commission put the planned emergency generator capacity at about 535 MWe and used it as a proxy for electrical demand. Microsoft's indicative timeline targets a permit application in September 2026 and construction from late 2027.","workloads":["cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d781093d-2c20-51bc-a765-09bc25052ccf","s2":"2f975102-6fc9-5fb4-8634-9b787db77ac8","s3":"9b24d4d4-ca66-5373-bb0a-06cd55ffceca"},"source_file":"datacenters/projects/microsoft-middenmeer-campus-west.json","source_record_id":"microsoft-middenmeer-campus-west","source_record_sha256":"bb6c8959847a730e9c12e50d71fd7ff9b9bee6a5b5f421c55bca81ca920154d7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"36216e5a3351f393ffc7ae1eeec910c6afabd6432d5782c5a7a2d32e6fb41bf5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-04be359939cf11193024/#project-55df6642-2ef8-5b72-a965-996a28bdfb24 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/55df6642-2ef8-5b72-a965-996a28bdfb24.json
55f4eb88-750d-5aa5-b4cb-bd5b8e746fe6 | curated:aws-walqa-huesca-data-center:current-build | vcc-site-d6e7826cfaef008088a0 | curated:aws-walqa-huesca-data-center | AWS Walqa Current Data Center Build | Spain | ES | 42.1138 | -0.45644 | Point | project | direct_geometry | official_aragon_piga_project_report_dms_coordinate_to_point | official_source_reported_project_reference_point | official_source | project_locator | Official project-report point used only to locate the proposed/current Walqa build. The reported 0.01-arc-second display precision is preserved but is not converted into survey accuracy. |  | The report prints DMS precision but does not state datum, surveyed reference feature, collection method, or horizontal accuracy. | a66352ad-9007-510c-ad30-c88e41cbe37a | under_construction | 2026-06-25 | 110 | authoritative_construction_start | bbc73b1a-ea07-52d6-a1a9-07e972f45a67 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | tracked_blind_reject_locally_unsealed_identity_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.aragonhoy.es/economia-competitividad-y-empleo/walqa-refuerza-crecimiento-nueva-conexion-directa-huesca-105562 | https://www.aragon.es/documents/d/guest/tomo-i-memoria-justificativa-pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d6e7826cfaef008088a0/#project-55f4eb88-750d-5aa5-b4cb-bd5b8e746fe6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/55f4eb88-750d-5aa5-b4cb-bd5b8e746fe6.json
561d28db-c1e2-5bbc-bda9-e10cbee90d7d | imported:semiconductor-atlas:microsoft-union-city-georgia | vcc-site-deed58b28fabd02848f5 | imported:semiconductor-atlas:microsoft-union-city-georgia | Microsoft Union City data center campus (EdgeConneX) | United States | US | 33.605 | -84.4936 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | The July 2024 regional-impact report gives the street address 4810 Stonewall Tell Road but no coordinates. The point is the Union City coordinate from its Wikipedia article, so it marks the city rather than the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d9584c37-4753-57d5-9a45-ab4450dbf7f6 | under_construction | 2026-08-06 | 68 | imported_documented_status | 9d9e44c7-788c-5eed-b327-ed2b8516e5d3 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9d9e44c7-788c-5eed-b327-ed2b8516e5d3","notes":"The August 2026 report (which spells it EdgeConnex) says the company developed the campus; it does not say who owns it.","party":"EdgeConneX","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-union-city-georgia"},{"evidence_id":"9d9e44c7-788c-5eed-b327-ed2b8516e5d3","notes":"Described in August 2026 as leasing space at the campus, which it does not own. The July 2024 report (s1) instead described three buildings that Microsoft would own and operate.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"microsoft-union-city-georgia"},{"evidence_id":"d9584c37-4753-57d5-9a45-ab4450dbf7f6","notes":"Role as reported in July 2024, when a Microsoft executive said the company had purchased additional Fulton County property to support data center construction already under way. Later reporting (s3) describes the campus as EdgeConneX-developed and leased.","party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-union-city-georgia"},{"evidence_id":"d9584c37-4753-57d5-9a45-ab4450dbf7f6","notes":"Was scheduled to discuss the USD 75 million ten-year tax abatement in July 2024. The 2026 report says the break was ultimately granted by Union City's development authority after Develop Fulton first considered it.","party":"Development Authority of Fulton County (Develop Fulton)","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-union-city-georgia"},{"evidence_id":"9d9e44c7-788c-5eed-b327-ed2b8516e5d3","notes":"Was scheduled to discuss the USD 75 million ten-year tax abatement in July 2024. The 2026 report says the break was ultimately granted by Union City's development authority after Develop Fulton first considered it.","party":"Development Authority of Fulton County (Develop Fulton)","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-union-city-georgia"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | Microsoft |  | https://www.ajc.com/business/2026/08/microsoft-aims-to-void-property-tax-breaks-for-its-data-centers-near-atlanta/ | https://southernbusiness.com/?p=644089 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Union City data center campus (EdgeConneX) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-union-city-georgia"},"record":{"aliases":["EdgeConneX Union City campus","4810 Stonewall Tell Road"],"id":"microsoft-union-city-georgia","last_reviewed":"2026-10-09","location":{"admin1":"Georgia","admin2":"Fulton County","country":"US","lat":33.605,"locality":"Union City","lon":-84.4936,"note":"The July 2024 regional-impact report gives the street address 4810 Stonewall Tell Road but no coordinates. The point is the Union City coordinate from its Wikipedia article, so it marks the city rather than the parcel.","precision":"locality","source_ids":["s1","s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2024-07-25","basis":"reported","metric":"investment","note":"Appears only in the headline of a Southern Business & Development report that credits the Atlanta Journal-Constitution as its source; the figure is not attributed to the company or a filing.","qualifier":"exact","source_ids":["s2"],"unit":"USD","value":1800000000},{"applies_to":"campus","as_of":"2026-08-06","basis":"reported","metric":"investment","note":"Given in a photo caption as a price tag of nearly USD 2 billion.","qualifier":"approximately","source_ids":["s3"],"unit":"USD","value":2000000000},{"applies_to":"campus","as_of":"2024-07-02","basis":"planned","metric":"buildings","note":"Planned buildings as reported by the Atlanta Business Chronicle and relayed by Southern Business & Development.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2024-07-25","basis":"planned","metric":"floor_area","note":"From the Development of Regional Impact filing, as reported by Southern Business & Development crediting the Atlanta Journal-Constitution.","qualifier":"approximately","source_ids":["s2"],"unit":"sq_ft","value":2100000},{"applies_to":"campus","as_of":"2026-08-06","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":136}],"milestones":[{"date":"2024-07","event":"other","kind":"actual","note":"Microsoft was confirmed, per the Atlanta Business Chronicle as relayed by Southern Business & Development, as the company seeking a USD 75 million, ten-year property tax abatement from the Development Authority of Fulton County.","source_ids":["s1"]},{"date":"2024-07","event":"other","kind":"actual","note":"A Development of Regional Impact filing describing the roughly 2.1 million sq ft campus was made public.","source_ids":["s2"]},{"date":"2026-08","event":"other","kind":"actual","note":"When Microsoft moved to unwind tax incentives for its own metro Atlanta projects in East Point, Palmetto and Douglasville, tax breaks tied to leased facilities such as the Union City campus were reported as unaffected.","source_ids":["s3"]}],"name":"Microsoft Union City data center campus (EdgeConneX)","notes":"No megawatt figure was found in the sources that could be opened. Ownership is described differently over time: in July 2024 the buildings were to be Microsoft owned and operated (s1), while in August 2026 the campus is EdgeConneX-developed with Microsoft leasing space (s3); each framing is kept with its own source and date. The July 2024 report put site development costs at about USD 43.5 million. The July 2024 regional-impact report said Microsoft had paid at least USD 171 million that year for more than 480 acres on Atlanta's Southside, including the Union City site; that is a multi-site figure, not a campus figure.","parties":[{"name":"EdgeConneX","note":"The August 2026 report (which spells it EdgeConnex) says the company developed the campus; it does not say who owns it.","role":"developer","source_ids":["s3"]},{"name":"Microsoft","note":"Described in August 2026 as leasing space at the campus, which it does not own. The July 2024 report (s1) instead described three buildings that Microsoft would own and operate.","role":"tenant","source_ids":["s3"]},{"name":"Microsoft","note":"Role as reported in July 2024, when a Microsoft executive said the company had purchased additional Fulton County property to support data center construction already under way. Later reporting (s3) describes the campus as EdgeConneX-developed and leased.","role":"developer","source_ids":["s1"]},{"name":"Development Authority of Fulton County (Develop Fulton)","note":"Was scheduled to discuss the USD 75 million ten-year tax abatement in July 2024. The 2026 report says the break was ultimately granted by Union City's development authority after Develop Fulton first considered it.","role":"government","source_ids":["s1","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-07-02","publisher":"Southern Business & Development (via Atlanta Business Chronicle)","title":"Microsoft confirmed as company seeking tax break for Fulton County, Ga. data center","type":"trade_press","url":"https://southernbusiness.com/?p=644089"},{"accessed":"2026-10-09","id":"s2","published":"2024-07-25","publisher":"Southern Business & Development (via The Atlanta Journal-Constitution)","title":"New details revealed about Microsoft's $1.8B data center near Atlanta","type":"trade_press","url":"https://southernbusiness.com/?p=644448"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260811000026/https://www.ajc.com/business/2026/08/microsoft-aims-to-void-property-tax-breaks-for-its-data-centers-near-atlanta/","id":"s3","published":"2026-08-06","publisher":"The Atlanta Journal-Constitution","title":"Microsoft works to unwind tax breaks for its metro Atlanta data centers","type":"news","url":"https://www.ajc.com/business/2026/08/microsoft-aims-to-void-property-tax-breaks-for-its-data-centers-near-atlanta/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Union City, Georgia","type":"other","url":"https://en.wikipedia.org/wiki/Union_City,_Georgia"}],"status":"under_construction","status_as_of":"2026-08-06","status_source_ids":["s3"],"summary":"Data center campus on 136 acres at 4810 Stonewall Tell Road in Union City, Fulton County, on metro Atlanta's Southside. In July 2024 Microsoft was confirmed as the company seeking a USD 75 million, ten-year property tax break for three planned buildings, and a regional-impact filing described about 2.1 million sq ft in a project a trade report, crediting the Atlanta Journal-Constitution, headlined at USD 1.8 billion. In August 2026 the Atlanta Journal-Constitution described it as an EdgeConneX-developed campus, still under construction, in which Microsoft leases space, with a price tag of nearly USD 2 billion.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d9584c37-4753-57d5-9a45-ab4450dbf7f6","s2":"44254fa1-0ebf-5a1e-80bd-b7a128119fbd","s3":"9d9e44c7-788c-5eed-b327-ed2b8516e5d3","s4":"a73a4558-186f-5c41-8349-d1e4084042c9"},"source_file":"datacenters/projects/microsoft-union-city-georgia.json","source_record_id":"microsoft-union-city-georgia","source_record_sha256":"8f5b1fa686dc9ca7dec35d9536ac6efd13307b6219f4410c824a8270a79eea1a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1e2e606e7579a4e77734966e44470d65f99e68221ef42b1e75044a4414e8918c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-deed58b28fabd02848f5/#project-561d28db-c1e2-5bbc-bda9-e10cbee90d7d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/561d28db-c1e2-5bbc-bda9-e10cbee90d7d.json
58129708-0b52-5984-afbc-f8f38e085df1 | curated:green-campus-zrh1-lupfig:data-center-4 | vcc-site-c61c3aef755484b5c52d | curated:green-campus-zrh1-lupfig | Green Campus ZRH1 Data Center 4 | Switzerland | CH | 47.4464 | 8.2108 | Polygon | campus | cross_source_overlay | openstreetmap_exactly_addressed_data_center_building_polygon_as_campus_locator | reviewed_openstreetmap_addressed_green_data_center_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for one data-center building at Green's exact first-party Campus ZRH1 address, used only to locate Campus ZRH1. It is not the DC4 footprint or centroid, the Campus ZRH1 boundary, a parcel, a construction extent, or a survey-accuracy claim. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | a488471c-6dc2-593f-92df-db707862cbfc | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | 96087e89-0485-5ce0-8d2c-f7bdfe47d834 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.green.ch/en/enterprise/data-center-locations/green-switzerland/campus-zrh1-lupfig/datacenter-4-lupfig | https://www.openstreetmap.org/way/242248627 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c61c3aef755484b5c52d/#project-58129708-0b52-5984-afbc-f8f38e085df1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/58129708-0b52-5984-afbc-f8f38e085df1.json
58f9a985-bfa8-521c-ab85-132aec6799ed | curated:cyrusone-fra7-frankfurt-westside-campus:current-multi-building-development | vcc-site-274ba04f1a143a081314 | curated:cyrusone-fra7-frankfurt-westside-campus | CyrusOne FRA7 Current Multi-Building Development | Germany | DE | 50.0934 | 8.5805 | Point | project | official_coordinate_transform | rp_darmstadt_ff7_l1_etrs89_utm32_coordinate_to_wgs84_point | official_source_reported_ff7_l1_reference_point | official_source | project_locator | Official-source coordinate for the FF7 L1 permit site/building, used only to locate the current FRA7 development. It is not a building centroid, parcel polygon, two-building campus boundary, current work zone, construction extent, or survey-accuracy claim. |  | The permit and CRS reference do not state the feature represented by the coordinate, collection method, epoch-specific transform parameters, or horizontal positional accuracy. | 850336d5-4d8f-5821-ae65-cb195961e7b6 | under_construction | 2026-06-12 | 123 | authoritative_physical_status_update | 6bf6472d-a1f7-53fd-b0d5-2317d80df706 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.linkedin.com/posts/cyrusone_datacenters-digitalinfrastructure-operationalexcellence-activity-7471180193492078592-WzIz | https://rp-darmstadt.hessen.de/sites/rp-darmstadt.hessen.de/files/2026-07/bescheid-4_ndma-ff7-cyrusone_end.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-274ba04f1a143a081314/#project-58f9a985-bfa8-521c-ab85-132aec6799ed | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/58f9a985-bfa8-521c-ab85-132aec6799ed.json
59a74e45-2dd2-5204-9c65-5430e8fc3148 | curated:teraco-ct1-rondebosch-data-centre:current-expansion | vcc-site-2a7b2edfacb6958b2186 | curated:teraco-ct1-rondebosch-data-centre | Teraco CT1 Rondebosch Expansion | South Africa | ZA | -33.9712 | 18.4649 | Point | campus | direct_geometry | first_party_facility_page_displayed_gps_coordinate_to_point | official_source_reported_facility_reference_point | official_source | campus_locator | The point locates the CT1 facility/campus only. It is not specific to the current expansion and is not a centroid, parcel, building outline, construction extent, or boundary. |  | The page does not identify datum, reference feature, collection method, or horizontal accuracy; GPS wording supports geographic-point semantics but not survey accuracy. | 3f9c9345-6060-57f1-af90-8f61f17e2cab | under_construction | 2026-07-17 | 88 | authoritative_physical_status_update | d54597bf-8089-5001-969c-0357d6218721 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-17","base":2.0,"confidence":0.99,"evidence_id":"d54597bf-8089-5001-969c-0357d6218721","high":2.0,"low":2.0,"method":"reported","metric":"critical_it_mw","notes":"Publisher-reported additional 2 MW critical IT load planned for the named expansion. It is not current operating load, gross facility demand, utility supply, generation, annual energy, measured consumption, or a completion claim.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.teraco.co.za/news/teraco-announces-ct1-data-centre-expansion-in-rondebosch-cape-town/ | https://www.teraco.co.za/data-centre-locations/cape-town/?tab=rondebosch-ct1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2a7b2edfacb6958b2186/#project-59a74e45-2dd2-5204-9c65-5430e8fc3148 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/59a74e45-2dd2-5204-9c65-5430e8fc3148.json
5ace12f8-658e-5956-9173-d78e625d4df9 | curated:dataone-vineland-ai-data-center-campus:phase-2-expansion-current-build | vcc-site-c14008c0552564c11274 | curated:dataone-vineland-ai-data-center-campus | DataOne Vineland Phase 2 Expansion Current Build | United States | US | 39.4252 | -75.0135 | Polygon | campus | exact_single_public_municipal_parcel_ring_server_projected_with_explicit_epsg1188 | municipal_block_lot_query_native_epsg3424_to_epsg4326 | official_mapped_constituent_parcel_as_campus_locator | official_source | campus_locator | Only the exact municipal mapped Block 7503 Lot 35.01 parcel is selected to locate the one campus shared by both phases. Not a surveyed cadastral boundary, complete campus boundary, security fence, Phase 2 building footprint or active-work extent. Derived display anchor is not an additional authoritative point. Old Lot 33.01 is not added or inferred merged. |  | City expressly warns some GIS data use assumptions and estimates and supplies no numerical positional accuracy. Coordinate digits, projection agreement and transformation operation accuracy are not a survey-accuracy estimate. | 1973e08d-0c30-5b25-a128-58ccfb617a19 | under_construction | 2026-08-07 | 67 | authoritative_physical_status_update | 9d7cd0fc-858f-5f77-b275-bb6bc2a77e1b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.vinelandcity.org/wp-content/uploads/2026/08/Data-One-Meeting-Post-8.7.pdf | https://gisportal.vinelandcity.org/arcgis/rest/services/Cadastre/Parcel_Public_Viewer/MapServer/0/query?f=pjson&where=BLOCK%3D%277503%27%20AND%20LOT%3D%2735.01%27&outFields=OBJECTID_1,MUN,BLOCK,LOT,UNIQUEID,ParcelAddr,Owner&returnGeometry=true&outSR=4326&datumTransformation=1188 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c14008c0552564c11274/#project-5ace12f8-658e-5956-9173-d78e625d4df9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5ace12f8-658e-5956-9173-d78e625d4df9.json
5ae9f639-4de6-5ce4-af8d-a40d6f8a3bec | curated:skygard-osl1-hovinbyen-campus:phase-2 | vcc-site-94d1b580090a69685f9f | curated:skygard-osl1-hovinbyen-campus | Skygard OSL1 Phase 2 | Norway | NO | 59.9294 | 10.8181 | Point | campus | cross_source_overlay | official_nve_site_address_to_matrikkelen_epsg4326_address_point | official_matrikkelen_verified_address_representative_point | official_source | campus_locator | Official address representative point used only to locate the OSL1 campus inherited by Phase 2. It is not the Phase 2 location or footprint, a building centroid, parcel, campus boundary, construction extent, or survey-accuracy claim. |  | The response marks the address point verified but does not publish numeric horizontal accuracy for this record. | 8d4c81f8-cb29-54f6-b5b4-c6e5f1f6b628 | under_construction | 2026-06-16 | 119 | authoritative_construction_start | 6f19756c-fdec-5499-9064-14ddf738cd39 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"a71bfa0b-8b6e-51ec-9e42-a71adfd62d1b","party":"Skygard","relationship_scope":"intended","role":"operator"}] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | Skygard |  |  |  | https://www.sentiagruppen.no/press/hent-inngar-kontrakt-pa-byggetrinn-2-osl1-datasenter-pa-okern | https://ws.geonorge.no/adresser/v1/sok?sok=%C3%98stre%20Aker%20vei%2024C%2C%200581%20Oslo&utkoordsys=4326&treffPerSide=10 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-94d1b580090a69685f9f/#project-5ae9f639-4de6-5ce4-af8d-a40d6f8a3bec | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5ae9f639-4de6-5ce4-af8d-a40d6f8a3bec.json
5b11c034-5a3b-5e5d-bc6a-b7122e21fbec | curated:qts-cambois-data-centre-campus:2026-earthworks | vcc-site-ee33430200d597833ebe | curated:qts-cambois-data-centre-campus | QTS Cambois 2026 Earthworks | United Kingdom | GB | 55.1509 | -1.5336 | Point | campus | official_coordinate_transform | applicant_report_osgb36_national_grid_reference_to_wgs84 | government_hosted_applicant_report_wider_campus_reference_point | official_source | campus_locator | Government-hosted applicant report's approximate centre for the wider Cambois Campus, transformed once from NGR NZ 29820 84164. It is not the Phase A point, east- or south-side earthworks location, parcel, campus, building, project, or current-work boundary. |  | The report explicitly calls the NGR an approximate centre and supplies no numeric horizontal-accuracy statement; transformed digits do not add accuracy. | a4ff7674-bfdc-5a88-92cd-673e02250b1a | civil_works | 2026-07-01 | 104 | authoritative_physical_status_update | b3d96fed-4eb9-53a1-a67b-848bbe9c4c4d | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.13 geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://q.com/data-centers/cambois/ | https://consult.environment-agency.gov.uk/psc/ne22-7bl-rainton-construction-limited-a001/supporting_documents/application-bespoke-a001-gbr1-dczz-cdl-ste-xx-rp-b-0018_-essd-171125pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ee33430200d597833ebe/#project-5b11c034-5a3b-5e5d-bc6a-b7122e21fbec | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5b11c034-5a3b-5e5d-bc6a-b7122e21fbec.json
5b52a118-2f46-5f43-b308-a3237e99e065 | curated:ascenty-sumare-campus:sumare-3 | vcc-site-74bd4d30e1805ec36812 | curated:ascenty-sumare-campus | Ascenty Sumaré 3 | Brazil | BR | -22.8123 | -47.2129 | Point | campus | copy_named_SUM01_literal_latitude_longitude_as_parent_campus_locator | first_party_site_coordinate_with_verified_WGS84_provider_contract | named_constituent_facility_point | official_source | campus_locator | Publisher point for SUM01 is a broad Sumaré campus locator only. It is not the SUM03 building, entrance, parcel, campus boundary, surveyed centroid or active-work extent. |  | Publisher gives no numeric horizontal accuracy; decimal digits do not establish accuracy. | 90f962ca-3e44-5141-beaa-f6485628fc91 | under_construction | 2026-05-28 | 138 | authoritative_physical_status_update | 4d651a1e-f8f0-5c20-8d86-257cdef382ae | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://pt.linkedin.com/posts/chris-torto_ascenty-datacenter-ia-activity-7465819505873702912-8_Vq | https://www.digitalrealty.com/data-centers/americas/sao-paulo/sum01 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-74bd4d30e1805ec36812/#project-5b52a118-2f46-5f43-b308-a3237e99e065 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5b52a118-2f46-5f43-b308-a3237e99e065.json
5b758548-2a2a-5643-9ebb-d8381bbd2c52 | curated:qts-york-county-south-carolina-data-center-campus:initial-phase-building-1 | vcc-site-382d4c7030c7ed7c700d | curated:qts-york-county-south-carolina-data-center-campus | QTS York County Initial-Phase Building 1 | United States | US | 35.0354 | -81.1034 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The exact address is asserted only for the parent QTS York campus. Building 1 remains at its source-explicit York locality, so the point is a campus locator only. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 6600dddb-f2d8-5458-8e71-b43f77cc5e01 | shell | 2026-06-30 | 105 | authoritative_physical_status_update | 913d7da6-9208-5382-a8e3-10f507b88fe6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.12 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.gilbaneco.com/about/whats-new/news/gilbane-marks-steel-topping-out-milestone-for-data-center-campus-in-upstate-south-carolina/ | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-382d4c7030c7ed7c700d/#project-5b758548-2a2a-5643-9ebb-d8381bbd2c52 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5b758548-2a2a-5643-9ebb-d8381bbd2c52.json
5bfb4ad8-a8f4-5937-9242-a96f9292c385 | curated:csc-lumi-ai-data-center-renforsin-ranta-kajaani:current-build | vcc-site-770ec5f91c36fa41886d | curated:csc-lumi-ai-data-center-renforsin-ranta-kajaani | CSC LUMI-AI Data Center Current Build | Finland | FI | 64.232 | 27.6915 | Point | campus | provider_supplied_named_CSC_LUMI_building_centroid_bound_to_official_same_hall_expansion | copy_Nominatim_lat_lon_for_OSM_way_705545655_then_bind_CSC_LUMI_names_and_Tehdaskatu_15_to_primary_same_hall_campus_identity | community_constituent_building_reference_point | community_source | campus_locator | Exact provider-returned centroid of the community industrial building named CSC, alt_name LUMI, at Tehdaskatu 15. Primary CSC sources identify its Kajaani data center at that address and the LUMI-AI expansion in the same hall as LUMI/Roihu. This locates one shared physical campus, not the expansion's exact room, parcel, whole-campus boundary, surveyed entrance or active-work extent. No imagery verification is claimed. |  | No selected source quantifies positional accuracy. Decimal digit count does not establish accuracy. | 1293fc76-3f6d-560f-9cb3-7ea2a0751450 | under_construction | 2026-08-20 | 54 | authoritative_physical_status_update | f6f13bec-804c-554b-ba4b-a3df91b37eb4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://csc.fi/en/news/csc-strengthens-the-future-of-kainuu/ | https://nominatim.openstreetmap.org/search?q=CSC%20Kajaani&format=jsonv2&addressdetails=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-770ec5f91c36fa41886d/#project-5bfb4ad8-a8f4-5937-9242-a96f9292c385 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5bfb4ad8-a8f4-5937-9242-a96f9292c385.json
5c366d64-4bb5-5c28-ab62-ec20d60fb31a | curated:cdc-eastern-creek-campus:ec6-current-build | vcc-site-3c1f872aa59b74b065ea | curated:cdc-eastern-creek-campus | CDC Eastern Creek EC6 Current Build | Australia | AU | -33.8181 | 150.8377 | Point | project | direct_geometry | authoritative_site_plan | shared_campus_reference_point | official_source | reviewed_site_locator | Official NSW project-site representative point for the shared Eastern Creek campus; not an EC6 building footprint. | 250 |  | 6e5dc4f7-2b39-5a4a-8dc3-f0e20691527b | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | c8ca490d-34ed-5e9c-93d5-3d12f2217d8f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://cdc.com.au/locations/sydney/ | https://www.planningportal.nsw.gov.au/major-projects/projects/roberts-road-data-centre | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3c1f872aa59b74b065ea/#project-5c366d64-4bb5-5c28-ab62-ec20d60fb31a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5c366d64-4bb5-5c28-ab62-ec20d60fb31a.json
5c691ba6-a630-5ab4-a45d-4d676e3e4d53 | imported:semiconductor-atlas:applied-digital-polaris-forge-2 | vcc-site-847f0ddc67e6e40ce38a | curated:applied-digital-polaris-forge-2-harwood | Applied Digital Polaris Forge 2 | United States | US | 46.9769 | -96.8811 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid of Harwood from its Wikipedia coordinates (s6), which also places Harwood in Cass County; company sources say only that the campus is near Harwood and give no parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2c0bc98f-0caf-5723-971e-4cacbedf9e34 | under_construction | 2026-10-07 | 6 | imported_documented_status | cfd695a9-59dd-573d-82d5-a24fbab9a149 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2c0bc98f-0caf-5723-971e-4cacbedf9e34","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-polaris-forge-2"},{"evidence_id":"5e422ddb-c0f8-5918-b384-dda547507e80","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-polaris-forge-2"},{"evidence_id":"2c0bc98f-0caf-5723-971e-4cacbedf9e34","notes":"Named as the power provider; in August 2025 the cooperative said it was finalizing an agreement.","party":"Cass County Electric Cooperative","relationship_scope":"unknown","role":"utility","source_record_id":"applied-digital-polaris-forge-2"},{"evidence_id":"effa7366-d2a3-56ec-af00-394d9e83cff6","notes":"Named as the power provider; in August 2025 the cooperative said it was finalizing an agreement.","party":"Cass County Electric Cooperative","relationship_scope":"unknown","role":"utility","source_record_id":"applied-digital-polaris-forge-2"},{"evidence_id":"effa7366-d2a3-56ec-af00-394d9e83cff6","notes":"Reported by Valley News Live in March 2026 without attribution; Applied Digital describes the tenant only as an unnamed US investment-grade hyperscaler, so this is not confirmed by the companies.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"applied-digital-polaris-forge-2"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | Oracle |  | https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year | https://ir.applieddigital.com/news-events/press-releases/detail/127/applied-digital-to-break-ground-on-3-billion-polaris-forge | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Harwood campus, confirmed by shared issuer results source. Source includes 1 GW campus potential and first 200 MW leases; existing current construction is a narrower active-build scope.","source_record_id":"applied-digital-polaris-forge-2","target_physical_site_stable_key":"curated:applied-digital-polaris-forge-2-harwood"},"record":{"aliases":["Polaris Forge 2 AI Factory Campus","Applied Digital Harwood AI campus"],"id":"applied-digital-polaris-forge-2","last_reviewed":"2026-10-09","location":{"admin1":"North Dakota","admin2":"Cass County","country":"US","lat":46.9769,"locality":"Harwood","lon":-96.8811,"note":"Town centroid of Harwood from its Wikipedia coordinates (s6), which also places Harwood in Cass County; company sources say only that the campus is near Harwood and give no parcel.","precision":"locality","source_ids":["s1","s2","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2025-08-18","basis":"announced","metric":"investment","note":"Figure given with the original 280 MW plan.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":3000000000},{"applies_to":"campus","as_of":"2025-08-18","basis":"planned","metric":"power_capacity","note":"Initial size at announcement; the release said the campus could scale beyond this.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":280},{"applies_to":"phase","as_of":"2025-10-22","basis":"contracted","metric":"power_capacity","note":"Critical IT load leased to an unnamed hyperscaler for an estimated 15 years, about 5 billion US dollars of contracted revenue.","phase_label":"Initial two buildings","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s4"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2025-10-22","basis":"planned","metric":"power_capacity","note":"Described as a 1 GW campus; the tenant holds a right of first refusal on a further 800 MW of critical IT load representing the full expansion.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2025-08-18","basis":"reported","metric":"land_area","note":"Land the company says it has contracted.","qualifier":"more_than","source_ids":["s1","s2"],"unit":"acres","value":900},{"applies_to":"phase","as_of":"2025-10-22","basis":"planned","metric":"buildings","phase_label":"Initial two buildings","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2025-08-18","basis":"planned","metric":"jobs_permanent","note":"Full-time employees expected at full operation, plus long-term contractors.","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":200}],"milestones":[{"date":"2025-08-18","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-09","event":"construction_started","kind":"planned","note":"Groundbreaking target given at announcement; by October 2025 the company described the campus as under construction.","source_ids":["s1","s2"]},{"date":"2025-10-22","event":"other","kind":"actual","note":"Lease of 200 MW of critical IT load to an unnamed US investment-grade hyperscaler announced.","source_ids":["s2"]},{"date":"2026-03-10","event":"other","kind":"actual","note":"Closing of 2.15 billion US dollars of 6.75 percent senior secured notes due 2031 to fund the 200 MW build.","source_ids":["s3","s4"]},{"date":"2026","event":"first_operational","kind":"planned","note":"In October 2026 the company said initial operations here would bring its delivered North Dakota capacity to 300 MW by the end of calendar 2026.","source_ids":["s2","s5"]},{"date":"2027","event":"fully_operational","kind":"planned","note":"Target for reaching the full initial 200 MW.","source_ids":["s2"]}],"name":"Applied Digital Polaris Forge 2","parties":[{"name":"Applied Digital","role":"developer","source_ids":["s1","s2"]},{"name":"Cass County Electric Cooperative","note":"Named as the power provider; in August 2025 the cooperative said it was finalizing an agreement.","role":"utility","source_ids":["s1","s3"]},{"name":"Oracle","note":"Reported by Valley News Live in March 2026 without attribution; Applied Digital describes the tenant only as an unnamed US investment-grade hyperscaler, so this is not confirmed by the companies.","role":"tenant","source_ids":["s3"]}],"power_sources":[{"description":"Power secured through Cass County Electric Cooperative, with Minnkota Power Cooperative also working toward a final agreement as of August 2025.","source_ids":["s1"],"type":"grid"}],"related_ids":["applied-digital-polaris-forge-1","applied-digital-polaris-forge-3"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260801091137/https://ir.applieddigital.com/news-events/press-releases/detail/127/applied-digital-to-break-ground-on-3-billion-polaris-forge","id":"s1","published":"2025-08-18","publisher":"Applied Digital","title":"Applied Digital to Break Ground on $3 Billion Polaris Forge 2 Campus in September 2025","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/127/applied-digital-to-break-ground-on-3-billion-polaris-forge"},{"accessed":"2026-10-09","id":"s2","published":"2025-10-22","publisher":"Applied Digital via GlobeNewswire (FinancialContent)","title":"Applied Digital Announces $5 Billion AI Factory Lease with U.S. Based Investment Grade Hyperscaler at Polaris Forge 2 ND Campus","type":"company","url":"https://markets.financialcontent.com/franklincredit/article/gnwcq-2025-10-22-applied-digital-announces-5-billion-ai-factory-lease-with-us-based-investment-grade-hyperscaler-at-polaris-forge-2-nd-campus"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260310230902/https://www.valleynewslive.com/2026/03/10/applied-digital-closes-215b-deal-build-out-harwood-ai-campus/","id":"s3","published":"2026-03-10","publisher":"Valley News Live","title":"Applied Digital closes $2.15B deal to build out Harwood AI campus","type":"news","url":"https://www.valleynewslive.com/2026/03/10/applied-digital-closes-215b-deal-build-out-harwood-ai-campus/"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-27","publisher":"Applied Digital","title":"Applied Digital Reports Fiscal Fourth Quarter and Full Year 2026 Results","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year"},{"accessed":"2026-10-09","id":"s5","published":"2026-10-07","publisher":"U.S. Securities and Exchange Commission (Applied Digital filing)","title":"Applied Digital Reports Fiscal First Quarter 2027 Results (Form 8-K exhibit)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001144879/000114487926000057/apldq127earningsrelease.htm"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Harwood, North Dakota","type":"other","url":"https://en.wikipedia.org/wiki/Harwood,_North_Dakota"}],"status":"under_construction","status_as_of":"2026-10-07","status_source_ids":["s4","s5"],"summary":"Applied Digital AI data center campus near Harwood in Cass County, North Dakota, on more than 900 acres. Announced in August 2025 as a 3 billion US dollar, 280 MW project, it was later described as a 1 GW campus. An unnamed US investment-grade hyperscaler leased the first 200 MW of critical IT load in two buildings for about 15 years and holds a right of first refusal on 800 MW more. Construction is funded partly by 2.15 billion US dollars of senior secured notes issued in March 2026; the company expects initial operations by the end of 2026 and the full 200 MW in 2027.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2c0bc98f-0caf-5723-971e-4cacbedf9e34","s2":"5e422ddb-c0f8-5918-b384-dda547507e80","s3":"effa7366-d2a3-56ec-af00-394d9e83cff6","s4":"cfd695a9-59dd-573d-82d5-a24fbab9a149","s5":"53a8fdc4-de9a-5092-b40c-34dd11266c42","s6":"0b89abc2-dbd0-5721-9607-fb26c955d09c"},"source_file":"datacenters/projects/applied-digital-polaris-forge-2.json","source_record_id":"applied-digital-polaris-forge-2","source_record_sha256":"c28d9e66605af454a76ac320e9b833d6efe8fe36b481ef4868d8867964ae7278","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"047b9b505b31894458144560324dbb84fcdb981e323fb2a820e72ffb50852454"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-847f0ddc67e6e40ce38a/#project-5c691ba6-a630-5ab4-a45d-4d676e3e4d53 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5c691ba6-a630-5ab4-a45d-4d676e3e4d53.json
5d11dbb6-e8aa-5602-9c7c-8997b1c620c1 | imported:semiconductor-atlas:eni-khazna-ferrera-erbognone | vcc-site-47f902912a847a235f3d | imported:semiconductor-atlas:eni-khazna-ferrera-erbognone | Eni and Khazna AI data center campus, Ferrera Erbognone | Italy | IT | 45.117 | 8.867 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Municipality centroid from the Ferrera Erbognone Wikipedia article. Sources name the municipality only. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a7222596-74ce-5d03-8348-f324c5280b8d | announced | 2026-08-10 | 64 | imported_documented_status | 3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a7222596-74ce-5d03-8348-f324c5280b8d","notes":"Joint venture partner.","party":"Eni","relationship_scope":"unknown","role":"developer","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a","notes":"Joint venture partner.","party":"Eni","relationship_scope":"unknown","role":"developer","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"a7222596-74ce-5d03-8348-f324c5280b8d","notes":"To supply power from a new high-efficiency gas plant with carbon capture.","party":"Eni","relationship_scope":"unknown","role":"power_supplier","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"5b709fe6-737f-5e00-805f-0c1c9a39e15b","notes":"To supply power from a new high-efficiency gas plant with carbon capture.","party":"Eni","relationship_scope":"unknown","role":"power_supplier","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a","notes":"To supply power from a new high-efficiency gas plant with carbon capture.","party":"Eni","relationship_scope":"unknown","role":"power_supplier","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"a7222596-74ce-5d03-8348-f324c5280b8d","notes":"Joint venture partner appointed to design and develop the phased master plan, bringing data center design and operations expertise.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"5b709fe6-737f-5e00-805f-0c1c9a39e15b","notes":"Joint venture partner appointed to design and develop the phased master plan, bringing data center design and operations expertise.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a","notes":"Joint venture partner appointed to design and develop the phased master plan, bringing data center design and operations expertise.","party":"Khazna Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a","notes":"Cleared the joint venture under the simplified merger procedure in August 2026.","party":"European Commission","relationship_scope":"unknown","role":"government","source_record_id":"eni-khazna-ferrera-erbognone"},{"evidence_id":"029f0c50-dc53-50c2-a0bd-44f17b527093","notes":"Cleared the joint venture under the simplified merger procedure in August 2026.","party":"European Commission","relationship_scope":"unknown","role":"government","source_record_id":"eni-khazna-ferrera-erbognone"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://en.ilsole24ore.com/art/data-centre-eu-gives-green-light-to-eni-khazna-joint-venture-lombardy-hub-to-be-accelerated-AJl2Zcj | https://www.eni.com/en-IT/media/press-release/2025/07/pr-khazna-data-centers-eni-partner-develop-i-data-center-campus.html | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Eni and Khazna AI data center campus, Ferrera Erbognone as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"eni-khazna-ferrera-erbognone"},"record":{"aliases":["Eni-Khazna AI Data Center Campus"],"id":"eni-khazna-ferrera-erbognone","last_reviewed":"2026-10-09","location":{"admin1":"Lombardy","admin2":"Province of Pavia","country":"IT","lat":45.117,"locality":"Ferrera Erbognone","lon":8.867,"note":"Municipality centroid from the Ferrera Erbognone Wikipedia article. Sources name the municipality only.","precision":"locality","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-10","basis":"planned","metric":"power_capacity","note":"Total IT capacity, to be reached in phases on a modular design.","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":500}],"milestones":[{"date":"2025-02","event":"other","kind":"actual","note":"Italy-UAE strategic partnership launched, targeting up to 1 GW of IT capacity in Italy.","source_ids":["s1","s2"]},{"date":"2025-07-11","event":"announced","kind":"actual","note":"Heads of terms for the joint venture signed in Rome.","source_ids":["s1","s2"]},{"date":"2026-08","event":"other","kind":"actual","note":"European Commission merger clearance of the Eni-Khazna joint venture, finding no competition concerns.","source_ids":["s3","s4"]}],"name":"Eni and Khazna AI data center campus, Ferrera Erbognone","notes":"No investment figure, phase schedule or operating date has been disclosed. Eni said development activities were under way when the heads of terms were signed, but in August 2026 Il Sole 24 Ore described the campus as still being designed; no construction start was found.","parties":[{"name":"Eni","note":"Joint venture partner.","role":"developer","source_ids":["s1","s3"]},{"name":"Eni","note":"To supply power from a new high-efficiency gas plant with carbon capture.","role":"power_supplier","source_ids":["s1","s2","s3"]},{"name":"Khazna Data Centers","note":"Joint venture partner appointed to design and develop the phased master plan, bringing data center design and operations expertise.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"European Commission","note":"Cleared the joint venture under the simplified merger procedure in August 2026.","role":"government","source_ids":["s3","s4"]}],"power_sources":[{"description":"Eni is to supply what it calls blue power from a new high-efficiency gas-fired plant designed to capture its CO2, which would be sent to a storage site in Ravenna. The plant's location relative to the campus is not stated.","source_ids":["s1","s2","s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001233652/https://www.eni.com/en-IT/media/press-release/2025/07/pr-khazna-data-centers-eni-partner-develop-i-data-center-campus.html","id":"s1","published":"2025-07-11","publisher":"Eni","title":"Khazna Data Centers and Eni partner to develop 500 MW AI Data Center Campus near Milan","type":"company","url":"https://www.eni.com/en-IT/media/press-release/2025/07/pr-khazna-data-centers-eni-partner-develop-i-data-center-campus.html"},{"accessed":"2026-10-09","id":"s2","published":"2025-07-11","publisher":"G42","title":"Khazna Data Centers and Eni Partner to Develop 500 MW AI Data Center Campus Near Milan","type":"company","url":"https://www.g42.ai/resources/news/khazna-data-centers-and-eni-partner-develop-500-mw-ai-data-center-campus-near-milan"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-10","publisher":"Il Sole 24 Ore","title":"Data centres: EU gives the green light to the Eni-Khazna joint venture. Lombardy hub set to accelerate","type":"news","url":"https://en.ilsole24ore.com/art/data-centre-eu-gives-green-light-to-eni-khazna-joint-venture-lombardy-hub-to-be-accelerated-AJl2Zcj"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-10","publisher":"Eunews","title":"EU Commission approves Khazna–ENI joint venture, says it does “not raise competition concerns”","type":"news","url":"https://www.eunews.it/en/2026/08/10/eu-commission-approves-khazna-eni-joint-venture-says-it-does-not-raise-competition-concerns/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260316013115/https://en.wikipedia.org/wiki/Ferrera_Erbognone","id":"s5","published":null,"publisher":"Wikipedia","title":"Ferrera Erbognone","type":"other","url":"https://en.wikipedia.org/wiki/Ferrera_Erbognone"}],"status":"announced","status_as_of":"2026-08-10","status_source_ids":["s3","s4"],"summary":"Planned AI data center campus of 500 MW of IT capacity at Ferrera Erbognone in the province of Pavia, Lombardy, near Milan. Eni and the UAE operator Khazna Data Centers signed heads of terms in July 2025 for a joint venture in which Khazna designs and develops a phased master plan and Eni supplies low-carbon power from a new gas-fired plant designed to capture its CO2 for storage at Ravenna. It is the first project in an Italy-UAE programme for up to 1 GW of IT capacity. The European Commission cleared the joint venture in August 2026, when the campus was described as still in design.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a7222596-74ce-5d03-8348-f324c5280b8d","s2":"5b709fe6-737f-5e00-805f-0c1c9a39e15b","s3":"3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a","s4":"029f0c50-dc53-50c2-a0bd-44f17b527093","s5":"c1d35c79-3955-5d20-859b-aba1f85f1dcf"},"source_file":"datacenters/projects/eni-khazna-ferrera-erbognone.json","source_record_id":"eni-khazna-ferrera-erbognone","source_record_sha256":"a0cb3643305f3a5a888c331dde151b57fce4ada563e49634d96a348a6f0ea568","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5d6f173907b551c8d0863cbddd6acafe7403c26409eb13fbd0fcf1d906bac40b"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-47f902912a847a235f3d/#project-5d11dbb6-e8aa-5602-9c7c-8997b1c620c1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5d11dbb6-e8aa-5602-9c7c-8997b1c620c1.json
5e0d1954-690d-51cb-816a-88cec595f51a | curated:leitwerk-baden-cloud-lahr-campus:current-build | vcc-site-f671a7ae44bca4e0f1f1 | curated:leitwerk-baden-cloud-lahr-campus | LEITWERK BADEN CLOUD Lahr Data Center Current Build | Germany | DE | 48.3623 | 7.817 | Point | campus | official_INSPIRE_address_position_for_exact_operator_stated_site_address | LGL_BW_INSPIRE_AD_Address_DEBWhx01000s9CqQ_native_EPSG25832_to_WGS84_via_ETRS89_to_WGS84_1_round7 | official_address_point_for_campus_site_address | official_source | campus_locator | Baden-Württemberg's official address position for Einsteinallee 14, the exact site address that the operator's own pages give for the Lahr data centre. It locates the addressed campus, not a data hall, phase, parcel boundary, footprint or current work extent. Native millimetre-serialized UTM coordinates were transformed once and rounded to seven decimals. |  | The service publishes the position's placement intent (building) and method (by administrator) but no positional accuracy for individual points. The 1 m figure is the ETRS89 to WGS 84 operation's accuracy, not the point's accuracy. | 988e5b50-461f-56e3-9254-779362733688 | under_construction | 2026-06-19 | 116 | authoritative_physical_status_update | c60dbdb5-30b1-5fc8-baf0-b9930a3977dc | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.e-werk-mittelbaden.de/sites/default/files/media_document/2026-06/20260619_Bilanz-Pressekonferenz-final.pdf | https://owsproxy.lgl-bw.de/owsproxy/wfs/WFS_INSP_BW_Adr_Hauskoord_ALKIS?SERVICE=WFS&VERSION=2.0.0&REQUEST=GetFeature&TYPENAMES=ad:Address&BBOX=48.36210,7.81680,48.36240,7.81720,urn:ogc:def:crs:EPSG::4258&COUNT=100 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f671a7ae44bca4e0f1f1/#project-5e0d1954-690d-51cb-816a-88cec595f51a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/5e0d1954-690d-51cb-816a-88cec595f51a.json
602d4e58-abef-54a7-b8f6-894a714e7174 | imported:semiconductor-atlas:bitdeer-fox-creek | vcc-site-63cd8442296ed3e4fc36 | imported:semiconductor-atlas:bitdeer-fox-creek | Bitdeer Fox Creek energy and computing facility | Canada | CA | 54.395 | -116.8092 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from the Fox Creek Wikipedia page; Bitdeer places the site about 1.5 km from the town but gives no exact location. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 0ceb23a4-a4de-5d14-8ae4-328ee9bf3212 | under_construction | 2026-08-10 | 64 | imported_documented_status | 0ceb23a4-a4de-5d14-8ae4-328ee9bf3212 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d5997cfb-4d90-51fd-9d9f-49a503ddc80c","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-fox-creek"},{"evidence_id":"0ceb23a4-a4de-5d14-8ae4-328ee9bf3212","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-fox-creek"},{"evidence_id":"a38bb9bf-9193-59d1-b029-d7fdf8905125","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-fox-creek"},{"evidence_id":"d5997cfb-4d90-51fd-9d9f-49a503ddc80c","notes":"Acquired the site and gas power project in an all-cash deal announced in February 2025.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"owner","source_record_id":"bitdeer-fox-creek"},{"evidence_id":"a38bb9bf-9193-59d1-b029-d7fdf8905125","notes":"Acquired the site and gas power project in an all-cash deal announced in February 2025.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"owner","source_record_id":"bitdeer-fox-creek"},{"evidence_id":"0ceb23a4-a4de-5d14-8ae4-328ee9bf3212","notes":"Named as the original developer of the site's power project before Bitdeer's acquisition.","party":"Kiwetinohk Energy Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-fox-creek"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Bitdeer Technologies Group |  |  |  |  | https://www.bnnbloomberg.ca/press-releases/2026/06/02/bitdeer-breaks-ground-on-new-energy-and-digital-infrastructure-facility-in-alberta-canada/ | https://www.bnnbloomberg.ca/press-releases/2026/06/02/bitdeer-breaks-ground-on-new-energy-and-digital-infrastructure-facility-in-alberta-canada/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bitdeer Fox Creek energy and computing facility as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"bitdeer-fox-creek"},"record":{"aliases":["Bitdeer Fox Creek"],"id":"bitdeer-fox-creek","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","admin2":"Municipal District of Greenview No. 16","country":"CA","lat":54.395,"locality":"Fox Creek (about 1.5 km from the town)","lon":-116.80917,"note":"Town coordinates from the Fox Creek Wikipedia page; Bitdeer places the site about 1.5 km from the town but gives no exact location.","precision":"locality","source_ids":["s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-10","basis":"planned","metric":"power_capacity","note":"On-site natural gas power plant; ground was broken in June 2026.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":101},{"applies_to":"campus","as_of":"2026-06-02","basis":"planned","metric":"power_capacity","note":"Described as computing capacity of the data centre; the release does not say whether this is IT load.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s2"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2026-06-02","basis":"permitted","metric":"power_capacity","note":"Approved interconnection with the Alberta Electric System Operator grid.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":99},{"applies_to":"campus","as_of":"2026-06-02","basis":"announced","metric":"investment","note":"Stated as about CAD 214 million. The 2025 site purchase was reported at $21.7 million without a stated currency, and Bitdeer's filing shows USD 21.9 million paid for the site and gas power project in the first half of 2025.","qualifier":"exact","source_ids":["s2"],"unit":"USD","value":155000000},{"applies_to":"campus","as_of":"2026-06-02","basis":"acquired","metric":"land_area","note":"Also given as 7.7 hectares.","qualifier":"exact","source_ids":["s1","s2"],"unit":"acres","value":19},{"applies_to":"campus","as_of":"2026-06-02","basis":"planned","metric":"jobs_construction","qualifier":"exact","source_ids":["s2"],"unit":"count","value":300},{"applies_to":"campus","as_of":"2026-06-02","basis":"planned","metric":"jobs_permanent","qualifier":"exact","source_ids":["s2"],"unit":"count","value":30}],"milestones":[{"date":"2025-02-04","event":"site_acquired","kind":"actual","note":"Date the acquisition was reported.","source_ids":["s1"]},{"date":"2026-06-02","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony for the power plant.","source_ids":["s2","s3"]},{"date":"2027-Q4","event":"first_operational","kind":"planned","note":"Energization target as of August 2026; earlier targets were Q4 2026 (February 2025) and Q2 2027 (June 2026).","source_ids":["s1","s2","s3"]}],"name":"Bitdeer Fox Creek energy and computing facility","notes":"Groundbreaking in June 2026 was for the power plant; Bitdeer's August 2026 results said data centre design for both AI and crypto loads was under way and listed the site among pipeline capacity, not online sites. Calgary.Tech's February 2025 report said the site could potentially scale to 1 GW. The release places the site in the Municipal District of Greenview No. 16 but also calls it the Regional Municipality of Greenview.","parties":[{"name":"Bitdeer Technologies Group","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Bitdeer Technologies Group","note":"Acquired the site and gas power project in an all-cash deal announced in February 2025.","role":"owner","source_ids":["s1","s3"]},{"name":"Kiwetinohk Energy Corp.","note":"Named as the original developer of the site's power project before Bitdeer's acquisition.","role":"developer","source_ids":["s2"]}],"power_sources":[{"description":"A 101 MW on-site gas plant would power the data centre directly under Alberta's bring-your-own-generation framework; Bitdeer plans to capture and use CO2 from the plant.","source_ids":["s1","s2","s3"],"type":"natural_gas_onsite"},{"description":"The plant keeps an approved 99 MW AESO grid connection, and at peak demand the facility can curtail computing and send power to the grid.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260516141829/https://calgary.tech/2025/02/04/bitdeer-acquires-101-mw-alberta-site-for-bitcoin-mining-expansion/","id":"s1","published":"2025-02-04","publisher":"Calgary.Tech","title":"Bitdeer acquires 101 MW Alberta site for bitcoin mining expansion","type":"news","url":"https://calgary.tech/2025/02/04/bitdeer-acquires-101-mw-alberta-site-for-bitcoin-mining-expansion/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260603075313/https://www.bnnbloomberg.ca/press-releases/2026/06/02/bitdeer-breaks-ground-on-new-energy-and-digital-infrastructure-facility-in-alberta-canada/","id":"s2","published":"2026-06-02","publisher":"Bitdeer Technologies Group (press release via BNN Bloomberg)","title":"Bitdeer breaks ground on new energy and digital infrastructure facility in Alberta, Canada","type":"company","url":"https://www.bnnbloomberg.ca/press-releases/2026/06/02/bitdeer-breaks-ground-on-new-energy-and-digital-infrastructure-facility-in-alberta-canada/"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-10","publisher":"Bitdeer Technologies Group (U.S. Securities and Exchange Commission filing)","title":"Bitdeer Reports Unaudited Financial Results for the Second Quarter of 2026 (Form 6-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001899123/000121390026086938/ea030131301ex99-1.htm"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Fox Creek, Alberta","type":"other","url":"https://en.wikipedia.org/wiki/Fox_Creek,_Alberta"}],"status":"under_construction","status_as_of":"2026-08-10","status_source_ids":["s2","s3"],"summary":"Bitdeer is building a 101 MW natural gas power plant and a data centre of about 100 MW of computing capacity on a 19-acre site about 1.5 km from Fox Creek, Alberta, in the Municipal District of Greenview. Bitdeer bought the permitted site, with a 99 MW grid interconnection approval, in an all-cash deal in February 2025 and broke ground in June 2026 on a USD 155 million project. It will start with bitcoin mining while the data centre is designed to also suit AI workloads. Energization slipped from Q4 2026 to Q2 2027 and then to Q4 2027.","workloads":["crypto_mining","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d5997cfb-4d90-51fd-9d9f-49a503ddc80c","s2":"0ceb23a4-a4de-5d14-8ae4-328ee9bf3212","s3":"a38bb9bf-9193-59d1-b029-d7fdf8905125","s4":"3a24f856-066d-5c00-9451-e88d2b2e59da"},"source_file":"datacenters/projects/bitdeer-fox-creek.json","source_record_id":"bitdeer-fox-creek","source_record_sha256":"f745c0fc027e66d0a064cde500d844a27c571e80ddd2d7fad377deefd0e77fe1","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"644dbce5e9ae4b1ed14316380a9c634ed698ce4680a4910ee39cf1a953852712"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-63cd8442296ed3e4fc36/#project-602d4e58-abef-54a7-b8f6-894a714e7174 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/602d4e58-abef-54a7-b8f6-894a714e7174.json
60485ece-bd7e-5f82-9f1b-6e271b8dcf45 | curated:aws-thane-balkum-majiwada-campus:ec-477127-current-build | vcc-site-cde9b25f26b96465e0dd | curated:aws-thane-balkum-majiwada-campus | AWS Thane Balkum & Majiwada Data Centre EC 477127 Current Build | India | IN | 19.218 | 72.9873 | Polygon | campus | source_KML_project_polygon_XY_preserved | PARIVESH_CAF157807_2024_active_Amazon_kml_placemark0_WGS84_lonlat_no_transform | proponent_submitted_environmental_project_polygon | official_source | campus_locator | Exact source polygon vertices from the active CAF attachment, whose extremes equal the EC annexure's site coordinates. A government-hosted proponent filing establishes a project-specific campus locator, not cadastral, surveyed or current-work-extent accuracy. The display anchor is the planar shoelace centroid of the source ring in source vertex order, verified inside it; it is not a publisher point, entrance or surveyed location. |  | Neither the KML, the CAF nor the EC states a positional accuracy, survey method, geodetic realization or control points. Decimal count and government hosting do not establish accuracy. | 49f2eb1c-bf1e-5e48-b9d5-e47463fdc97d | under_construction | 2026-05-27 | 139 | authoritative_physical_status_update | be298ea7-134d-5f4b-812d-a910c58a7f3f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=1544616&refId=1229589086&refType=COMPLIANCE&uuid=aeac2226-55e4-4d6e-9ec5-e5526c7cd02e&version=1.0 | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=40829&refId=48515968&refType=caf&uuid=918097ab-55a6-4361-be07-77242df79e0e&version=1.0 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cde9b25f26b96465e0dd/#project-60485ece-bd7e-5f82-9f1b-6e271b8dcf45 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/60485ece-bd7e-5f82-9f1b-6e271b8dcf45.json
619c5358-cf99-5e82-a690-4ae5c58f07f1 | imported:semiconductor-atlas:meta-bowling-green | vcc-site-a39bc0fe88ed4e44ee52 | imported:semiconductor-atlas:meta-bowling-green | Meta Bowling Green data center | United States | US | 41.4743 | -83.6661 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Township point from OpenStreetMap Nominatim. BG Independent places the adjacent power plant at the northeast corner of Ohio 582 and Mercer Road, but no source gives the data center parcel itself. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 815af14a-2c15-522b-a396-8c38b60d9cf0 | under_construction | 2026-10-09 | 4 | imported_documented_status | 60ccd753-62cf-5e7b-bc01-b678c6746297 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"815af14a-2c15-522b-a396-8c38b60d9cf0","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-bowling-green"},{"evidence_id":"60ccd753-62cf-5e7b-bc01-b678c6746297","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-bowling-green"},{"evidence_id":"815af14a-2c15-522b-a396-8c38b60d9cf0","notes":"Meta refers readers to JE Dunn Construction for construction information.","party":"JE Dunn Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-bowling-green"},{"evidence_id":"815af14a-2c15-522b-a396-8c38b60d9cf0","notes":"Meta says it planned the site's energy needs with Toledo Edison from the start.","party":"Toledo Edison","relationship_scope":"unknown","role":"utility","source_record_id":"meta-bowling-green"},{"evidence_id":"60ccd753-62cf-5e7b-bc01-b678c6746297","notes":"Named in Meta's fact sheet as an energy-planning partner.","party":"FirstEnergy","relationship_scope":"unknown","role":"utility","source_record_id":"meta-bowling-green"},{"evidence_id":"60ccd753-62cf-5e7b-bc01-b678c6746297","notes":"Named in Meta's fact sheet as an energy-planning partner; its specific role is not described there.","party":"Williams","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-bowling-green"},{"evidence_id":"4a7bed57-9a5b-571c-b016-a8ad1ef5ebc1","notes":"Will build and operate the adjacent behind-the-meter gas plant.","party":"Will-Power OH","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-bowling-green"},{"evidence_id":"4a7bed57-9a5b-571c-b016-a8ad1ef5ebc1","notes":"Approved the adjacent gas plant in February 2026.","party":"Ohio Power Siting Board","relationship_scope":"unknown","role":"government","source_record_id":"meta-bowling-green"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Bowling-Green-Data-Center.pdf | https://datacenters.atmeta.com/2025/04/hello-bowling-green/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Bowling Green data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-bowling-green"},"record":{"aliases":["Bowling Green Data Center"],"id":"meta-bowling-green","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Wood County","country":"US","lat":41.4743,"locality":"Middleton Township","lon":-83.6661,"note":"Township point from OpenStreetMap Nominatim. BG Independent places the adjacent power plant at the northeast corner of Ohio 582 and Mercer Road, but no source gives the data center parcel itself.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-02-03","basis":"permitted","metric":"power_capacity","note":"Net output of the behind-the-meter Apollo gas plant approved to serve only the adjacent Meta data center; the article gives no figure for the data center's own load.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":350},{"applies_to":"campus","as_of":"2025-04-09","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1","s3","s4"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2025-04-09","basis":"planned","metric":"floor_area","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":715000},{"applies_to":"campus","as_of":"2025-04-09","basis":"planned","metric":"jobs_construction","note":"Meta's fact sheet gives 1,000 without a qualifier.","qualifier":"more_than","source_ids":["s1","s4"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2025-04-09","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s1","s3"],"unit":"count","value":100}],"milestones":[{"date":"2025-04-09","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025","event":"construction_started","kind":"actual","note":"Meta's location list gives 2025 as the groundbreaking year.","source_ids":["s4"]},{"date":"2026-02-03","event":"permit_approved","kind":"actual","note":"Ohio Power Siting Board approval, under its expedited process, of the adjacent 350 MW Apollo gas plant.","source_ids":["s2"]}],"name":"Meta Bowling Green data center","notes":"The status rests on two undated Meta pages: the U.S. location list, which gives 2025 as the groundbreaking year, and the fact sheet, which describes the data center in the future tense. status_as_of is therefore the date both were read (2026-10-09). The fact sheet PDF shows no publication date; its embedded file creation date is 2026-09-01.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s3"]},{"name":"JE Dunn Construction","note":"Meta refers readers to JE Dunn Construction for construction information.","role":"builder","source_ids":["s1"]},{"name":"Toledo Edison","note":"Meta says it planned the site's energy needs with Toledo Edison from the start.","role":"utility","source_ids":["s1"]},{"name":"FirstEnergy","note":"Named in Meta's fact sheet as an energy-planning partner.","role":"utility","source_ids":["s3"]},{"name":"Williams","note":"Named in Meta's fact sheet as an energy-planning partner; its specific role is not described there.","role":"power_supplier","source_ids":["s3"]},{"name":"Will-Power OH","note":"Will build and operate the adjacent behind-the-meter gas plant.","role":"power_supplier","source_ids":["s2"]},{"name":"Ohio Power Siting Board","note":"Approved the adjacent gas plant in February 2026.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"The Apollo Power Generation Facility, a 350 MW gas plant on 147 acres next to the data center, is approved to serve only the data center with no physical grid connection. Will-Power OH will build and run it, with part of the output expected by mid-2027 and the rest by late 2027.","source_ids":["s2"],"type":"natural_gas_onsite"},{"description":"About 120 MW of battery storage approved as part of the same plant.","source_ids":["s2"],"type":"battery_storage"},{"description":"Meta says it planned the site's energy needs with Toledo Edison, and names FirstEnergy and Williams as planning partners in its fact sheet; it says it pays the full cost of the energy used.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929221639/https://datacenters.atmeta.com/2025/04/hello-bowling-green/","id":"s1","published":"2025-04-09","publisher":"Meta Platforms","title":"Hello, Bowling Green!","type":"company","url":"https://datacenters.atmeta.com/2025/04/hello-bowling-green/"},{"accessed":"2026-10-09","id":"s2","published":"2026-02-03","publisher":"BG Independent News","title":"Power plant for Meta data center in Wood County fast tracked – approved by state with no public hearings","type":"news","url":"https://bgindependentmedia.org/?p=115392"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Meta Platforms","title":"Meta Bowling Green Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Bowling-Green-Data-Center.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007122559/https://datacenters.atmeta.com/us-locations/","id":"s4","published":null,"publisher":"Meta Platforms","title":"United States - Meta Data Centers","type":"company","url":"https://datacenters.atmeta.com/us-locations/"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s3","s4"],"summary":"Meta data center campus of 715,000 square feet in Middleton Township, Wood County, Ohio, near Bowling Green, announced in April 2025 as an investment of more than USD 800 million and described as optimized for Meta's AI workloads. Meta's location list gives 2025 as the groundbreaking year. In February 2026 the Ohio Power Siting Board approved, without public hearings, a 350 MW behind-the-meter gas plant with about 120 MW of batteries next to the data center, to be built and run by Will-Power OH. Meta names Toledo Edison, FirstEnergy and Williams as energy-planning partners and refers readers to JE Dunn Construction for construction information.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"815af14a-2c15-522b-a396-8c38b60d9cf0","s2":"4a7bed57-9a5b-571c-b016-a8ad1ef5ebc1","s3":"60ccd753-62cf-5e7b-bc01-b678c6746297","s4":"ff7fed35-fa05-5483-94b1-33ea0a61e6ce"},"source_file":"datacenters/projects/meta-bowling-green.json","source_record_id":"meta-bowling-green","source_record_sha256":"37c3a8f68096bd2305057b5ebd4d553a90b5763392eec950ea1b02b45abc4b5e","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"edc77570c4cfff3a8564a642b195d028af90ea8e2cec2b97147e264cf066a96e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a39bc0fe88ed4e44ee52/#project-619c5358-cf99-5e82-a690-4ae5c58f07f1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/619c5358-cf99-5e82-a690-4ae5c58f07f1.json
632aad8a-8c12-5a02-bd17-1138e6b03b6c | imported:semiconductor-atlas:openai-stargate-abilene | vcc-site-85b3549bb55293336132 | curated:lancium-clean-campus-abilene-ai-data-center | Stargate Abilene (Crusoe campus on Lancium land) | United States | US | 32.4465 | -99.7476 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Abilene city centroid from an OpenStreetMap Nominatim lookup. Cited sources name the city but give no street address or parcel, so the campus itself is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 23d44bfc-7613-5581-8585-2f23cd7c0f75 | partially_operational | 2026-10-05 | 8 | imported_documented_status | 7ac9775e-a093-54a2-a511-0434f71a2eac | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"23d44bfc-7613-5581-8585-2f23cd7c0f75","notes":"Crusoe develops, builds and operates the campus and leases it to Oracle for OpenAI.","party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-abilene"},{"evidence_id":"e9020492-72bd-51b1-b517-133f3d5fbb49","notes":"Crusoe develops, builds and operates the campus and leases it to Oracle for OpenAI.","party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-abilene"},{"evidence_id":"c0aabc2c-e022-5239-b704-d8e5a8e6d769","notes":"Crusoe develops, builds and operates the campus and leases it to Oracle for OpenAI.","party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-abilene"},{"evidence_id":"23d44bfc-7613-5581-8585-2f23cd7c0f75","notes":"Co-sponsor of the $15 billion joint venture, investing through funds managed by its Real Assets platform.","party":"Blue Owl Capital","relationship_scope":"unknown","role":"investor","source_record_id":"openai-stargate-abilene"},{"evidence_id":"23d44bfc-7613-5581-8585-2f23cd7c0f75","notes":"Co-sponsor of the joint venture funding construction.","party":"Primary Digital Infrastructure","relationship_scope":"unknown","role":"investor","source_record_id":"openai-stargate-abilene"},{"evidence_id":"c0aabc2c-e022-5239-b704-d8e5a8e6d769","notes":"Crusoe describes the Abilene campus land as Lancium-owned.","party":"Lancium","relationship_scope":"unknown","role":"owner","source_record_id":"openai-stargate-abilene"},{"evidence_id":"44f25ffe-6cc2-59fc-ba41-fcdab041c5e4","notes":"Leases the buildings and runs Oracle Cloud Infrastructure capacity there for OpenAI. Analyst Epoch AI, not a company disclosure, lists Oracle as owner of the AI chips.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-abilene"},{"evidence_id":"e9020492-72bd-51b1-b517-133f3d5fbb49","notes":"Leases the buildings and runs Oracle Cloud Infrastructure capacity there for OpenAI. Analyst Epoch AI, not a company disclosure, lists Oracle as owner of the AI chips.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-abilene"},{"evidence_id":"7ac9775e-a093-54a2-a511-0434f71a2eac","notes":"Leases the buildings and runs Oracle Cloud Infrastructure capacity there for OpenAI. Analyst Epoch AI, not a company disclosure, lists Oracle as owner of the AI chips.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-abilene"},{"evidence_id":"44f25ffe-6cc2-59fc-ba41-fcdab041c5e4","notes":"End user of the compute, served through Oracle Cloud Infrastructure.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-abilene"},{"evidence_id":"e9020492-72bd-51b1-b517-133f3d5fbb49","notes":"End user of the compute, served through Oracle Cloud Infrastructure.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-abilene"},{"evidence_id":"7ac9775e-a093-54a2-a511-0434f71a2eac","notes":"End user of the compute, served through Oracle Cloud Infrastructure.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-abilene"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Lancium |  |  | OpenAI; Oracle |  | https://epoch.ai/data/ai-data-centers/directory/openai-stargate-abilene | https://www.crusoe.ai/resources/newsroom/crusoe-blue-owl-capital-and-primary-digital-infrastructure-enter-joint-venture | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same original eight-building Crusoe/Oracle/OpenAI campus on Lancium land. Source includes the first operating buildings and full 1.2 GW program; existing record selects the remaining six-building expansion. Adjacent Crusoe Microsoft campus is separate.","source_record_id":"openai-stargate-abilene","source_relations":[{"reason":"Source explicitly describes Microsoft campus as second and adjacent to original Oracle/OpenAI campus; distinct building programs and tenants.","relationship":"separate_adjacent_campuses","source_id":"crusoe-abilene-microsoft"}],"target_physical_site_stable_key":"curated:lancium-clean-campus-abilene-ai-data-center"},"record":{"aliases":["Stargate Abilene","Lancium Clean Campus","Crusoe Abilene"],"id":"openai-stargate-abilene","last_reviewed":"2026-10-09","location":{"admin1":"Texas","country":"US","lat":32.4465,"locality":"Abilene","lon":-99.7476,"note":"Abilene city centroid from an OpenStreetMap Nominatim lookup. Cited sources name the city but give no street address or parcel, so the campus itself is not pinpointed.","precision":"locality","source_ids":["s1","s3","s7"]},"metrics":[{"applies_to":"campus","as_of":"2025-05-21","basis":"planned","metric":"power_capacity","note":"Full eight-building campus. Sources do not say whether this is IT or facility power.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1","s3"],"unit":"MW","value":1200},{"applies_to":"phase","as_of":"2025-11-18","basis":"operational","metric":"power_capacity","note":"The first two buildings, reported operational since September 2025, provide more than 200 MW of IT capacity.","phase_label":"Phase 1 (buildings 1-2)","power_scope":"it_load","qualifier":"more_than","source_ids":["s3"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-07-28","basis":"operational","metric":"power_capacity","note":"Analyst estimate, not a company disclosure: Epoch AI's estimate of operating IT power with four buildings running, built from satellite imagery, filings and cooling models. Epoch projects about 843 MW of IT power by Q4 2026.","power_scope":"it_load","qualifier":"approximately","source_ids":["s7"],"unit":"MW","value":421},{"applies_to":"campus","as_of":"2026-04","basis":"permitted","metric":"power_capacity","note":"Analyst report, not a company disclosure: Cleanview gives this initial combined gas turbine capacity from permit documents and estimates from satellite imagery that the plant was finished in January 2026.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s6"],"unit":"MW","value":360},{"applies_to":"phase","as_of":"2025-09-24","basis":"planned","metric":"power_capacity","note":"Announced in September 2025 as a potential expansion near the flagship site. In March 2026 Industrial Info relayed a Bloomberg report that the expansion was off; OpenAI said it put the capacity elsewhere and Oracle called the reports false.","phase_label":"Potential expansion near Abilene (reported dropped in 2026)","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":600},{"applies_to":"campus","as_of":"2025-05-21","basis":"announced","metric":"investment","note":"Size of the Crusoe, Blue Owl and Primary Digital joint venture funding the campus.","qualifier":"approximately","source_ids":["s1"],"unit":"USD","value":15000000000},{"applies_to":"campus","as_of":"2025-05-21","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s3"],"unit":"count","value":8},{"applies_to":"phase","as_of":"2025-11-18","basis":"operational","metric":"floor_area","phase_label":"Phase 1 (buildings 1-2)","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":980000},{"applies_to":"campus","as_of":"2025-11-18","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":4000000},{"applies_to":"campus","as_of":"2025-11-18","basis":"reported","metric":"jobs_construction","note":"Workers Crusoe said come to Abilene every day to build the campus, cited at the final topping out. In May 2025 the joint venture reported about 3,000 daily workers, expected to approach 5,000.","qualifier":"approximately","source_ids":["s1","s3"],"unit":"count","value":7000}],"milestones":[{"date":"2024-06","event":"construction_started","kind":"actual","note":"Crusoe dates the start of phase 1 to June 2024; one trade article gives July 2024.","source_ids":["s1","s3","s9"]},{"date":"2025-03","event":"other","kind":"actual","note":"Construction of phase 2 (six more buildings) began.","source_ids":["s1"]},{"date":"2025-09","event":"first_operational","kind":"actual","note":"Crusoe announced the first phase live in September 2025. Analyst Epoch AI judges only building 1 fully operational then and building 2 by December 2025.","source_ids":["s3","s6","s7"]},{"date":"2025-09-23","event":"expansion_announced","kind":"actual","note":"A potential 600 MW expansion near Abilene was announced alongside five new Stargate sites.","source_ids":["s2"]},{"date":"2025-11","event":"other","kind":"actual","note":"Eighth and final building topped out.","source_ids":["s3"]},{"date":"2026-03","event":"other","kind":"actual","note":"Bloomberg reported, as relayed by Industrial Info, that plans to expand the campus were dropped; Oracle called the reports false. Analyst Epoch AI also describes OpenAI as having reversed a plan to expand the site.","source_ids":["s4","s5"]},{"date":"2026","event":"fully_operational","kind":"planned","note":"Crusoe targeted energizing phase 2 by mid-2026. Analyst Epoch AI, not a company source, projects buildings 5 to 8 operational around November 2026.","source_ids":["s1","s7"]}],"name":"Stargate Abilene (Crusoe campus on Lancium land)","notes":"Estimates of how much of the campus is live differ: an Oracle post in April 2026 said 200 MW was operating, analyst Epoch AI estimated about 0.3 GW of facility power then and about 421 MW of IT load by mid-2026, and The Tech Capital reported six buildings delivered to OpenAI in late September 2026. Epoch figures are analyst estimates, not company disclosures. Crusoe is separately building a 900 MW data center on adjacent Lancium-owned land, which Epoch links to Microsoft; it is a different project.","parties":[{"name":"Crusoe","note":"Crusoe develops, builds and operates the campus and leases it to Oracle for OpenAI.","role":"developer","source_ids":["s1","s3","s9"]},{"name":"Blue Owl Capital","note":"Co-sponsor of the $15 billion joint venture, investing through funds managed by its Real Assets platform.","role":"investor","source_ids":["s1"]},{"name":"Primary Digital Infrastructure","note":"Co-sponsor of the joint venture funding construction.","role":"investor","source_ids":["s1"]},{"name":"Lancium","note":"Crusoe describes the Abilene campus land as Lancium-owned.","role":"owner","source_ids":["s9"]},{"name":"Oracle","note":"Leases the buildings and runs Oracle Cloud Infrastructure capacity there for OpenAI. Analyst Epoch AI, not a company disclosure, lists Oracle as owner of the AI chips.","role":"tenant","source_ids":["s2","s3","s7"]},{"name":"OpenAI","note":"End user of the compute, served through Oracle Cloud Infrastructure.","role":"tenant","source_ids":["s2","s3","s7"]}],"power_sources":[{"description":"Connected to the ERCOT grid, per analyst Cleanview. Analyst Epoch AI reports a 200 MW substation serving the first buildings and a larger 1 GW substation that looked complete in July 2026 imagery.","source_ids":["s6","s7"],"type":"grid"},{"description":"On-site gas turbines, including GE Vernova LM2500XPRESS and Solar Titan 350 units, per permit records summarized by analyst Cleanview; analyst Epoch AI saw the on-site plant looking complete by March 2026.","source_ids":["s6","s7"],"type":"natural_gas_onsite"},{"description":"Crusoe cited the region's low-cost wind power as a major factor in choosing the site; analyst Epoch AI notes the grid supply includes local wind.","source_ids":["s1","s5"],"type":"wind"}],"related_ids":["crusoe-abilene-microsoft"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-05-21","publisher":"Crusoe","title":"Crusoe, Blue Owl Capital and Primary Digital Infrastructure Enter Second Phase of $15 Billion Joint Venture","type":"company","url":"https://www.crusoe.ai/resources/newsroom/crusoe-blue-owl-capital-and-primary-digital-infrastructure-enter-joint-venture"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-24","publisher":"SoftBank Group Corp.","title":"OpenAI, Oracle, and SoftBank expand Stargate with five new AI data center sites","type":"company","url":"https://group.softbank/en/news/press/20250924"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-18","publisher":"W.Media","title":"Crusoe tops off final AI data center in Abilene, Texas","type":"trade_press","url":"https://w.media/crusoe-tops-off-final-ai-data-center-in-abilene-texas/"},{"accessed":"2026-10-09","id":"s4","published":"2026-03-10","publisher":"Industrial Info Resources","title":"Flagship Stargate Data Center Campus Expansion in Texas is Questioned","type":"trade_press","url":"https://www.industrialinfo.com/iirenergy/industry-news/article/flagship-stargate-data-center-campus-expansion-in-texas-is-questioned--354568"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260517184326/https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand","id":"s5","published":"2026-04-17","publisher":"Epoch AI","title":"OpenAI Stargate: where the US sites stand","type":"analyst","url":"https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Cleanview","title":"Behind-the-meter data centers: Stargate Abilene","type":"analyst","url":"https://cleanview.co/reports/behind-the-meter-data-centers/full-report/stargate-abilene"},{"accessed":"2026-10-09","id":"s7","published":"2026-10-05","publisher":"Epoch AI","title":"OpenAI Stargate Abilene (AI data center directory)","type":"analyst","url":"https://epoch.ai/data/ai-data-centers/directory/openai-stargate-abilene"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006030644/https://thetechcapital.com/abilene-stargate-data-centre-update/","id":"s8","published":"2026-09-29","publisher":"The Tech Capital","title":"An Abilene update: What's happening at the first Stargate data centre?","type":"trade_press","url":"https://thetechcapital.com/abilene-stargate-data-centre-update/"},{"accessed":"2026-10-09","id":"s9","published":"2026-07-15","publisher":"Crusoe","title":"Crusoe and Lancium Announce 1.0 Gigawatt AI Data Center Campus in Childress, Texas","type":"company","url":"https://www.crusoe.ai/resources/newsroom/crusoe-and-lancium-announce-1-gigawatt-ai-data-center-campus-in-childress-texas"}],"status":"partially_operational","status_as_of":"2026-10-05","status_source_ids":["s7","s8"],"summary":"Crusoe-developed eight-building AI campus in Abilene, Texas, planned at about 1.2 GW and leased to Oracle, which runs it for OpenAI as the flagship Stargate site. Construction began in mid-2024; the first buildings came online in September 2025 and the last building was topped out in November 2025. The build is funded through a Crusoe, Blue Owl and Primary Digital joint venture on Lancium-owned land. A potential 600 MW expansion nearby was floated in 2025, but reports in March 2026 said it had been dropped, which Oracle disputed. In late September 2026 trade press reported six buildings delivered to OpenAI, and analyst Epoch AI projected all eight running by November 2026.","workloads":["ai_training","ai_inference"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"23d44bfc-7613-5581-8585-2f23cd7c0f75","s2":"44f25ffe-6cc2-59fc-ba41-fcdab041c5e4","s3":"e9020492-72bd-51b1-b517-133f3d5fbb49","s4":"70033f2a-1700-5a67-9781-3e13e4124467","s5":"21aa3998-cc7d-5a18-be05-a691da505426","s6":"ba0df664-b659-5b68-93ec-69ee62e92884","s7":"7ac9775e-a093-54a2-a511-0434f71a2eac","s8":"83d1f116-5518-5a75-833d-72a44dc2cd1c","s9":"c0aabc2c-e022-5239-b704-d8e5a8e6d769"},"source_file":"datacenters/projects/openai-stargate-abilene.json","source_record_id":"openai-stargate-abilene","source_record_sha256":"066c9529d28eb79b7fc21ed2ed0dd80e325c61e382e4ef4017df6b302effa713","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3d5e26cae202f2c893720da67cbdf1d23c0fe50dbdafd1f787a8c1db57b23e76"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-85b3549bb55293336132/#project-632aad8a-8c12-5a02-bd17-1138e6b03b6c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/632aad8a-8c12-5a02-bd17-1138e6b03b6c.json
64289119-458d-5fc9-bf51-5af6097220eb | curated:microsoft-finland-kirkkonummi-campus:building-1 | vcc-site-004b39e14dadd642b1e8 | curated:microsoft-finland-kirkkonummi-campus | Microsoft Kirkkonummi First Datacenter Building | Finland | FI | 60.1451 | 24.5488 | Point | campus | official_permit_activity_reference_coordinate_transformed | source_E363900_N6670100_tm35_interpreted_as_EPSG3067_to_EPSG4326 | official_environmental_permit_activity_site_reference_point | official_source | campus_locator | Municipal source-reported reference point for Microsoft's named data-center activity/rock-crushing permit site. Native values are E 363900, N 6670100 labelled tm-35; the explicit EPSG:3067 interpretation is transformed without claiming a building center, boundary, construction footprint or survey accuracy. |  | The source states no numeric positional accuracy or surveyed reference feature. Its coordinate notation does not justify an accuracy estimate. | 6096de66-dad6-5326-8155-173cfe6969a4 | under_construction | 2026-06-26 | 109 | authoritative_physical_status_update | d3721ce7-7e2b-5fe8-8023-d1c1f1d0109f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://winthrop.ie/kirkkonummi-finland-project-updates/ | https://kirkkonummi.oncloudos.com/kokous/20241842-11-115303.PDF | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-004b39e14dadd642b1e8/#project-64289119-458d-5fc9-bf51-5af6097220eb | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/64289119-458d-5fc9-bf51-5af6097220eb.json
64f6ec20-7a91-530a-85f2-7748b0e320f8 | imported:semiconductor-atlas:sk-aws-ulsan-ai-data-center | vcc-site-e8f2d5efccb035e9135a | imported:semiconductor-atlas:sk-aws-ulsan-ai-data-center | SK AI Data Center Ulsan | Korea, Republic of | KR | 35.5392 | 129.3119 | Point | project | imported_reference_point | imported_reference_point | admin1 | compiled_reference | admin1_context | Sources place the site in the Mipo National Industrial Complex in Ulsan without an address, and the complex could not be geocoded; coordinates are the OpenStreetMap Nominatim centroid of Ulsan Metropolitan City. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | c4cbb4ab-c343-5664-82db-472e1cbb7b1a | under_construction | 2026-09-14 | 29 | imported_documented_status | d1d938f7-bb10-5a92-9e71-2f4bb296b1b7 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c4cbb4ab-c343-5664-82db-472e1cbb7b1a","notes":null,"party":"SK Telecom","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"9d369ee9-b9c0-589b-ab51-599b8956e66b","notes":null,"party":"SK Telecom","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"34892ffa-c4fb-555f-844d-cc3736146fc2","notes":null,"party":"SK Telecom","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"57b70ddd-b004-54f4-91e9-8d20ab4c8b8f","notes":null,"party":"SK Telecom","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"dfa0da14-d583-55d6-affc-17a1537f6618","notes":null,"party":"SK Telecom","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"c4cbb4ab-c343-5664-82db-472e1cbb7b1a","notes":"Named alongside SK Telecom as leading the project and as co-purchaser of the site.","party":"SK Broadband","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"a964f858-5693-51d7-bb08-4833ee37adb1","notes":"Named alongside SK Telecom as leading the project and as co-purchaser of the site.","party":"SK Broadband","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"57b70ddd-b004-54f4-91e9-8d20ab4c8b8f","notes":"Named alongside SK Telecom as leading the project and as co-purchaser of the site.","party":"SK Broadband","relationship_scope":"unknown","role":"developer","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"34892ffa-c4fb-555f-844d-cc3736146fc2","notes":null,"party":"SK Ecoplant","relationship_scope":"unknown","role":"builder","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"57b70ddd-b004-54f4-91e9-8d20ab4c8b8f","notes":null,"party":"SK Ecoplant","relationship_scope":"unknown","role":"builder","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"c4cbb4ab-c343-5664-82db-472e1cbb7b1a","notes":"Described as SK's partner in the project and expected to invest about USD 4 billion, according to reports citing industry sources; the companies' own figures were not found.","party":"Amazon Web Services","relationship_scope":"unknown","role":"investor","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"a964f858-5693-51d7-bb08-4833ee37adb1","notes":"Described as SK's partner in the project and expected to invest about USD 4 billion, according to reports citing industry sources; the companies' own figures were not found.","party":"Amazon Web Services","relationship_scope":"unknown","role":"investor","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"34892ffa-c4fb-555f-844d-cc3736146fc2","notes":"Described as SK's partner in the project and expected to invest about USD 4 billion, according to reports citing industry sources; the companies' own figures were not found.","party":"Amazon Web Services","relationship_scope":"unknown","role":"investor","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"9d369ee9-b9c0-589b-ab51-599b8956e66b","notes":null,"party":"SK Multi-Utility","relationship_scope":"unknown","role":"power_supplier","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"34892ffa-c4fb-555f-844d-cc3736146fc2","notes":null,"party":"SK Multi-Utility","relationship_scope":"unknown","role":"power_supplier","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"a964f858-5693-51d7-bb08-4833ee37adb1","notes":"Supplies LNG to the nearby cogeneration plant.","party":"SK Gas","relationship_scope":"unknown","role":"power_supplier","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"9d369ee9-b9c0-589b-ab51-599b8956e66b","notes":"Supplies LNG to the nearby cogeneration plant.","party":"SK Gas","relationship_scope":"unknown","role":"power_supplier","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"34892ffa-c4fb-555f-844d-cc3736146fc2","notes":"Supplies LNG to the nearby cogeneration plant.","party":"SK Gas","relationship_scope":"unknown","role":"power_supplier","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"34892ffa-c4fb-555f-844d-cc3736146fc2","notes":"Signed an MoU with SK Telecom on regional revitalization and expanding the site.","party":"Ulsan Metropolitan City","relationship_scope":"unknown","role":"government","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"57b70ddd-b004-54f4-91e9-8d20ab4c8b8f","notes":"Signed an MoU with SK Telecom on regional revitalization and expanding the site.","party":"Ulsan Metropolitan City","relationship_scope":"unknown","role":"government","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"d1d938f7-bb10-5a92-9e71-2f4bb296b1b7","notes":"Planned spin-off of SK Broadband's data center business that is to run the Ulsan AI data center under construction; SK Telecom targets establishing it in the first quarter of 2027, pending shareholder and government approvals.","party":"SK Horizon","relationship_scope":"unknown","role":"operator","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"57b70ddd-b004-54f4-91e9-8d20ab4c8b8f","notes":"Planned spin-off of SK Broadband's data center business that is to run the Ulsan AI data center under construction; SK Telecom targets establishing it in the first quarter of 2027, pending shareholder and government approvals.","party":"SK Horizon","relationship_scope":"unknown","role":"operator","source_record_id":"sk-aws-ulsan-ai-data-center"},{"evidence_id":"dfa0da14-d583-55d6-affc-17a1537f6618","notes":"Planned spin-off of SK Broadband's data center business that is to run the Ulsan AI data center under construction; SK Telecom targets establishing it in the first quarter of 2027, pending shareholder and government approvals.","party":"SK Horizon","relationship_scope":"unknown","role":"operator","source_record_id":"sk-aws-ulsan-ai-data-center"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | SK Horizon |  |  |  | https://www.lightreading.com/data-centers/sk-telecom-creates-sk-horizon-in-2-2b-data-center-spin-off-deal | https://amchamkorea.org/pp/latest_news/members_news/read/?idx=2451 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve SK AI Data Center Ulsan as an independent source record; its admin1 locator does not itself establish a surveyed physical site.","source_record_id":"sk-aws-ulsan-ai-data-center"},"record":{"aliases":["SK-AWS Ulsan AI data center","Ulsan AI data center"],"id":"sk-aws-ulsan-ai-data-center","last_reviewed":"2026-10-09","location":{"admin1":"Ulsan","country":"KR","lat":35.5392,"locality":"Ulsan","lon":129.3119,"note":"Sources place the site in the Mipo National Industrial Complex in Ulsan without an address, and the complex could not be geocoded; coordinates are the OpenStreetMap Nominatim centroid of Ulsan Metropolitan City.","precision":"admin1","source_ids":["s1","s2","s6"]},"metrics":[{"applies_to":"phase","as_of":"2025-06-16","basis":"planned","metric":"power_capacity","note":"A September 2026 report gives about 40 MW for this phase.","phase_label":"Phase 1 (target November 2027)","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":41},{"applies_to":"campus","as_of":"2025-06-16","basis":"planned","metric":"power_capacity","note":"Full initial build targeted for February 2029.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s6"],"unit":"MW","value":103},{"applies_to":"campus","as_of":"2025-08-29","basis":"planned","metric":"power_capacity","note":"TelecomTV's rounded figure at groundbreaking; other reports give 103 MW.","power_scope":"unspecified","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2026-07","basis":"planned","metric":"power_capacity","note":"Long-term gigawatt-scale aim without a timeline, first reported in June 2025 and restated by SK Telecom in July 2026. In September 2026 SK's chairman said planned capacity at Ulsan was approaching 900 MW.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s6"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2025-06-16","basis":"planned","metric":"accelerators","qualifier":"exact","source_ids":["s1","s2","s6"],"unit":"count","value":60000},{"applies_to":"campus","as_of":"2025-08-29","basis":"reported","metric":"investment","note":"TelecomTV attributes the 7 trillion won figure to South Korea's ICT ministry.","qualifier":"approximately","source_ids":["s4","s6"],"unit":"KRW","value":7000000000000},{"applies_to":"campus","as_of":"2025-06-16","basis":"reported","metric":"investment","note":"AWS's expected contribution, per reports citing industry sources; TelecomTV describes it as part of the 7 trillion won total, so the two figures should not be added.","qualifier":"approximately","source_ids":["s1","s2","s4"],"unit":"USD","value":4000000000},{"applies_to":"campus","as_of":"2025-06-16","basis":"acquired","metric":"land_area","note":"Reported as about 36,000 square meters bought from SK Chemicals for 28.3 billion won.","qualifier":"approximately","source_ids":["s2","s6"],"unit":"hectares","value":3.6}],"milestones":[{"date":"2025-04","event":"site_acquired","kind":"actual","source_ids":["s2","s6"]},{"date":"2025-06","event":"announced","kind":"actual","note":"Plans first reported by Korean media citing industry sources in mid-June 2025.","source_ids":["s1","s2"]},{"date":"2025-08-29","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony attended by SK, AWS and city officials.","source_ids":["s3","s4","s6"]},{"date":"2027-11","event":"first_operational","kind":"planned","note":"Target for the roughly 41 MW first phase.","source_ids":["s1","s2","s6"]},{"date":"2029-02","event":"other","kind":"planned","note":"Target for expanding the site to about 103 MW in a second phase; SK has since signalled a much larger build-out.","source_ids":["s1","s2","s6"]},{"date":"2026-08-27","event":"other","kind":"actual","note":"SK Telecom signed agreements to spin SK Broadband's data center business, including the Ulsan AI data center under construction, into SK Horizon with 3.08 trillion won of equity from KKR and an IMM Investment-Stonebridge consortium; completion is targeted for the first quarter of 2027.","source_ids":["s5","s6","s7"]}],"name":"SK AI Data Center Ulsan","parties":[{"name":"SK Telecom","role":"developer","source_ids":["s1","s3","s4","s6","s7"]},{"name":"SK Broadband","note":"Named alongside SK Telecom as leading the project and as co-purchaser of the site.","role":"developer","source_ids":["s1","s2","s6"]},{"name":"SK Ecoplant","role":"builder","source_ids":["s4","s6"]},{"name":"Amazon Web Services","note":"Described as SK's partner in the project and expected to invest about USD 4 billion, according to reports citing industry sources; the companies' own figures were not found.","role":"investor","source_ids":["s1","s2","s4"]},{"name":"SK Multi-Utility","role":"power_supplier","source_ids":["s3","s4"]},{"name":"SK Gas","note":"Supplies LNG to the nearby cogeneration plant.","role":"power_supplier","source_ids":["s2","s3","s4"]},{"name":"Ulsan Metropolitan City","note":"Signed an MoU with SK Telecom on regional revitalization and expanding the site.","role":"government","source_ids":["s4","s6"]},{"name":"SK Horizon","note":"Planned spin-off of SK Broadband's data center business that is to run the Ulsan AI data center under construction; SK Telecom targets establishing it in the first quarter of 2027, pending shareholder and government approvals.","role":"operator","source_ids":["s5","s6","s7"]}],"power_sources":[{"description":"Power from a nearby LNG-fuelled cogeneration plant run by SK Multi-Utility with fuel from SK Gas, with LNG cold energy proposed for cooling.","source_ids":["s2","s3","s4","s6"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-06-17","publisher":"AMCHAM Korea / The Chosun Daily","title":"SK, AWS to build South Korea's largest AI data center in Ulsan (reprint of The Chosun Daily)","type":"news","url":"https://amchamkorea.org/pp/latest_news/members_news/read/?idx=2451"},{"accessed":"2026-10-09","id":"s2","published":"2025-06-16","publisher":"iTnews Asia","title":"SK Group and AWS to build South Korea's largest AI data centre in Ulsan","type":"trade_press","url":"https://www.itnews.asia/news/sk-group-and-aws-to-build-south-koreas-largest-ai-data-centre-in-ulsan-617900"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260714114045/https://www.koreajoongangdaily.com/business/sk-group-breaks-ground-on-ai-only-data-center-in-ulsan/12451117","id":"s3","published":"2025-08-29","publisher":"Korea JoongAng Daily","title":"SK Group breaks ground on AI-only data center in Ulsan","type":"news","url":"https://www.koreajoongangdaily.com/business/sk-group-breaks-ground-on-ai-only-data-center-in-ulsan/12451117"},{"accessed":"2026-10-09","id":"s4","published":"2025-08-29","publisher":"TelecomTV","title":"Under the hood of SKT's Ulsan AI datacentre","type":"trade_press","url":"https://www.telecomtv.com/content/ai/under-the-hood-of-skt-s-ulsan-ai-datacentre-53720/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260906000318/https://www.lightreading.com/data-centers/sk-telecom-creates-sk-horizon-in-2-2b-data-center-spin-off-deal","id":"s5","published":"2026-08-28","publisher":"Light Reading","title":"SK Telecom creates SK Horizon in $2.2B data center spin-off deal","type":"trade_press","url":"https://www.lightreading.com/data-centers/sk-telecom-creates-sk-horizon-in-2-2b-data-center-spin-off-deal"},{"accessed":"2026-10-09","id":"s6","published":"2026-09-14","publisher":"Construction Review Online","title":"SK AI Data Center Ulsan: Chairman Says Site Nearing 900 Megawatts","type":"trade_press","url":"https://constructionreviewonline.com/sk-ai-data-center-ulsan-chairman-says-site-nearing-900-megawatts/"},{"accessed":"2026-10-09","id":"s7","published":"2026-08-27","publisher":"SK Telecom","title":"SK Telecom Launches AI Data Center Infrastructure Company 'SK Horizon' and Secures Investments from KKR and IMM","type":"company","url":"https://news.sktelecom.com/en/3290"}],"status":"under_construction","status_as_of":"2026-09-14","status_source_ids":["s5","s6","s7"],"summary":"SK Telecom and other SK Group companies are building an AI data center with Amazon Web Services on a former SK Chemicals site in the Mipo National Industrial Complex in Ulsan, South Korea. Plans call for a first phase of about 41 MW by November 2027 and about 103 MW by February 2029, with up to 60,000 GPUs and a longer-term aim of gigawatt scale. Power is to come from a nearby LNG-fuelled cogeneration plant. Construction began with an August 2025 groundbreaking. In August 2026 SK Telecom agreed to move SK Broadband's data center business, including the Ulsan build, into a new company, SK Horizon, backed by KKR and an IMM-Stonebridge consortium, subject to approvals.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c4cbb4ab-c343-5664-82db-472e1cbb7b1a","s2":"a964f858-5693-51d7-bb08-4833ee37adb1","s3":"9d369ee9-b9c0-589b-ab51-599b8956e66b","s4":"34892ffa-c4fb-555f-844d-cc3736146fc2","s5":"d1d938f7-bb10-5a92-9e71-2f4bb296b1b7","s6":"57b70ddd-b004-54f4-91e9-8d20ab4c8b8f","s7":"dfa0da14-d583-55d6-affc-17a1537f6618"},"source_file":"datacenters/projects/sk-aws-ulsan-ai-data-center.json","source_record_id":"sk-aws-ulsan-ai-data-center","source_record_sha256":"efedefcd9b321f667a41f68c35a639ab91f3254b2e9d1437d44ee3298e289fd6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"67cb26b51f214198940925d2d1180fb872b9a7cedd0f5f66dc61cc031d24e5e7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e8f2d5efccb035e9135a/#project-64f6ec20-7a91-530a-85f2-7748b0e320f8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/64f6ec20-7a91-530a-85f2-7748b0e320f8.json
65e8849e-2ebe-5d58-be63-299cbbcf8d23 | curated:coresite-de3-race-street-campus:de3 | vcc-site-782c0112e90a5282be53 | curated:coresite-de3-race-street-campus | CoreSite DE3 | United States | US | 39.7861 | -104.9628 | Polygon | project | direct_geometry | authoritative_tax_parcel | tax_parcel_boundary | official_source | official_boundary | Exact Denver tax-parcel polygon whose returned owner is CoreSite Real Estate DE3 LLC; not a building footprint. |  | official source does not state positional accuracy | 58cd4851-129d-59c4-9cb0-4f24070a71a9 | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | ff80fe7d-ec91-5ce0-877e-6efc6f9289a5 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | tracked_blind_clear_locally_unsealed_identity_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | colocation |  | 6c2aaeb4-6f26-515c-99d8-8e8a0bd2f65b | [] | not established by selected evidence | [{"evidence_id":"276847d4-183f-5995-ab80-90d4636b467b","party":"CoreSite","relationship_scope":"intended","role":"operator"}] | [{"as_of_date":"2026-07-20","base":18.0,"confidence":0.99,"evidence_id":"39ca2ddf-3a1e-5d9c-983e-4a30ae537dc7","high":18.0,"low":18.0,"method":"reported","metric":"critical_it_mw","notes":"Planned DE3 critical-power design capacity reported as 18 CMW; CoreSite's retained top-out release expands the same campus CMW label as critical megawatts. This project value is nested within and non-additive with the 60-MW campus row. It is not grid connection, gross facility demand, generation, installed or energized capacity, current load, annual energy, measured consumption, or proof of operation.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | CoreSite |  |  |  | https://www.coresite.com/en-us/data-centers/denver/de3-construction | https://services1.arcgis.com/zdB7qR0BtYrg0Xpl/arcgis/rest/services/ODC_PROP_PARCELS_A/FeatureServer/245/query?where=SITUS_ADDRESS_ID%3D23973%20AND%20SCHEDNUM%3D%270214400131000%27&outFields=OBJECTID%2CSCHEDNUM%2CSITUS_ADDRESS_ID%2CSITUS_ADDRESS_LINE1%2CSITUS_CITY%2CSITUS_STATE%2CSITUS_ZIP%2COWNER_NAME%2CPARCELNUM&returnGeometry=true&returnCentroid=true&outSR=4326&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-782c0112e90a5282be53/#project-65e8849e-2ebe-5d58-be63-299cbbcf8d23 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/65e8849e-2ebe-5d58-be63-299cbbcf8d23.json
6788c655-d9ed-520c-8012-56d246d29a0c | imported:semiconductor-atlas:microsoft-aragon-zaragoza-puerto-venecia | vcc-site-1e165cace19ab3a9b463 | imported:semiconductor-atlas:microsoft-aragon-zaragoza-puerto-venecia | Microsoft Zaragoza (Puerto Venecia) datacenter campus | Spain | ES | 41.6088 | -0.8872 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Nominatim point for Puerto Venecia (Torrero-La Paz district); sources place the campus next to Puerto Venecia and Parque Venecia, but the parcel boundary is not published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2765ea35-4037-5771-8cab-3cbd7f180977 | announced | 2026-09-04 | 39 | imported_documented_status | 96ffa587-b68d-5fb3-bf51-46c182fc5f78 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2765ea35-4037-5771-8cab-3cbd7f180977","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia"},{"evidence_id":"79caf0b6-9546-531d-be52-ffd8cb6cbb8e","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia"},{"evidence_id":"96ffa587-b68d-5fb3-bf51-46c182fc5f78","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia"},{"evidence_id":"2765ea35-4037-5771-8cab-3cbd7f180977","notes":"Declared the campus of general interest, started expropriation and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia"},{"evidence_id":"79caf0b6-9546-531d-be52-ffd8cb6cbb8e","notes":"Declared the campus of general interest, started expropriation and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia"},{"evidence_id":"96ffa587-b68d-5fb3-bf51-46c182fc5f78","notes":"Declared the campus of general interest, started expropriation and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.eldiario.es/aragon/economia/prioridad-extranjera-pp-vox-aragon-expropian-suelo-centro-datos-microsoft-2-euros-metro_1_13417031.html | https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Zaragoza (Puerto Venecia) datacenter campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia"},"record":{"aliases":[],"id":"microsoft-aragon-zaragoza-puerto-venecia","last_reviewed":"2026-10-09","location":{"admin1":"Aragón","admin2":"Zaragoza","country":"ES","lat":41.6088,"locality":"Zaragoza","lon":-0.8872,"note":"Nominatim point for Puerto Venecia (Torrero-La Paz district); sources place the campus next to Puerto Venecia and Parque Venecia, but the parcel boundary is not published.","precision":"approximate_site","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-14","basis":"reported","metric":"investment","note":"Per-site figure in the November 2025 PIGA as reported by elDiario.es.","qualifier":"exact","source_ids":["s1"],"unit":"EUR","value":1443000000},{"applies_to":"phase","as_of":"2025-11-14","basis":"planned","metric":"power_capacity","phase_label":"First phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":50},{"applies_to":"campus","as_of":"2025-11-14","basis":"planned","metric":"power_capacity","note":"Second-phase aspiration per campus in the PIGA, as reported by elDiario.es; Forbes gives 250-300 MW per campus over about ten years.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-11-14","basis":"planned","metric":"land_area","note":"elDiario.es reported in August 2026 that about 16.5 hectares of private land at the site were being expropriated.","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":57}],"milestones":[{"date":"2025-09","event":"other","kind":"actual","note":"Regional government declared the campus of general interest and opened expropriation of private land.","source_ids":["s3"]},{"date":"2025-11-14","event":"other","kind":"actual","note":"Initial approval of the PIGA Región MSFT plan covering La Muela, Villamayor de Gállego and Zaragoza, opening a public information period.","source_ids":["s1","s2"]},{"date":"2026-07-30","event":"other","kind":"actual","note":"A modification of the PIGA was published in the Boletín Oficial de Aragón for public comment; the ZeC party filed 25 objections citing trees, flood risk and water and energy use.","source_ids":["s4"]},{"date":"2030","event":"first_operational","kind":"planned","note":"Forbes reported the first phase was expected to operate from 2030; Microsoft's plan foresees about four years for the first phase after final approval.","source_ids":["s2","s3"]}],"name":"Microsoft Zaragoza (Puerto Venecia) datacenter campus","notes":"Landowners facing expropriation say work has begun, which Microsoft disputes, saying only land clearing is permitted before the plan is finally approved. 2026 coverage also mentions a second large data centre planned on rural land at Cartuja Baja in Zaragoza without naming its developer; it is not part of this record. No government primary source was opened; Boletín Oficial de Aragón entries should be added when available.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Gobierno de Aragón","note":"Declared the campus of general interest, started expropriation and is processing the PIGA regional plan.","role":"government","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"Grid supply through the Torrero-Valdeconsejo substation, starting at 132 kV with a later upgrade to 220 kV.","source_ids":["s1"],"type":"grid"}],"related_ids":["microsoft-aragon-la-muela","microsoft-aragon-villamayor-de-gallego"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-14","publisher":"elDiario.es","title":"Microsoft avanza con su red de centros de datos en Zaragoza, donde proyecta una de sus mayores regiones en Europa","type":"news","url":"https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-14","publisher":"Forbes España","title":"Microsoft obtiene luz verde para su ambicioso proyecto de centros de datos en Aragón","type":"news","url":"https://forbes.es/empresas/828243/microsoft-obtiene-luz-verde-para-su-ambicioso-proyecto-de-centros-de-datos-en-aragon/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006005223/https://www.eldiario.es/aragon/economia/prioridad-extranjera-pp-vox-aragon-expropian-suelo-centro-datos-microsoft-2-euros-metro_1_13417031.html","id":"s3","published":"2026-08-02","publisher":"elDiario.es","title":"La 'prioridad extranjera' para PP y Vox en Aragón: expropian suelo para un centro de datos de Microsoft a 2 euros el metro","type":"news","url":"https://www.eldiario.es/aragon/economia/prioridad-extranjera-pp-vox-aragon-expropian-suelo-centro-datos-microsoft-2-euros-metro_1_13417031.html"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-04","publisher":"elDiario.es","title":"ZeC presenta 25 alegaciones al plan de Microsoft y exige a la alcaldesa de Zaragoza paralizar un centro de datos","type":"news","url":"https://www.eldiario.es/aragon/politica/zec-presenta-25-alegaciones-plan-microsoft-exige-alcaldesa-zaragoza-paralizar-centro-datos_1_13487405.html"}],"status":"announced","status_as_of":"2026-09-04","status_source_ids":["s3","s4"],"summary":"Planned Microsoft datacenter campus in the city of Zaragoza beside the Puerto Venecia shopping area, one of three campuses in the PIGA Región MSFT regional plan. The November 2025 plan assigns it 57 hectares and about EUR 1.44 billion, with 50 MW secured for a first phase and up to 300 MW sought later via the Torrero-Valdeconsejo substation. The regional government declared it of general interest in September 2025 and began expropriating about 16.5 hectares of private land. Landowners and the ZeC party contested the project in 2026. Microsoft says only land clearing is authorized until the plan receives final approval.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2765ea35-4037-5771-8cab-3cbd7f180977","s2":"79caf0b6-9546-531d-be52-ffd8cb6cbb8e","s3":"96ffa587-b68d-5fb3-bf51-46c182fc5f78","s4":"85f32114-6639-53a3-8db3-ea1e17541b02"},"source_file":"datacenters/projects/microsoft-aragon-zaragoza-puerto-venecia.json","source_record_id":"microsoft-aragon-zaragoza-puerto-venecia","source_record_sha256":"4d1630963fc53925a1148c968d421f54888d88d4da82a9f12a33249ea81824f7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3d59dcc594169abc505b4a4bbbfd8e5aadcd23b47f5b4b3c67ed1368e41c7fc5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1e165cace19ab3a9b463/#project-6788c655-d9ed-520c-8012-56d246d29a0c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/6788c655-d9ed-520c-8012-56d246d29a0c.json
6799aac4-c4f8-5902-b8ae-2fffb6fa893d | imported:semiconductor-atlas:bitdeer-clarington-ohio | vcc-site-4551992e6d4d1487d1ab | imported:semiconductor-atlas:bitdeer-clarington-ohio | Bitdeer Clarington data center site | United States | US | 39.7728 | -80.8708 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Bitdeer names only Clarington, Ohio. Coordinates are the village point from its Wikipedia article, which also gives the county; the site itself is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a2bccfaf-e1b2-5d80-8e08-ff37122f1c29 | announced | 2026-08-10 | 64 | imported_documented_status | 331ffac3-a2e5-5120-b0f7-a7fac2e79d12 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a2bccfaf-e1b2-5d80-8e08-ff37122f1c29","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-clarington-ohio"},{"evidence_id":"f38a7fa6-302c-5a1e-b8bc-c76c256b2a77","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-clarington-ohio"},{"evidence_id":"331ffac3-a2e5-5120-b0f7-a7fac2e79d12","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-clarington-ohio"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm | https://www.sec.gov/Archives/edgar/data/0001899123/000121390025098957/ea026118901ex99-1_bitdeer.htm | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bitdeer Clarington data center site as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"bitdeer-clarington-ohio"},"record":{"aliases":["Clarington, Ohio site"],"id":"bitdeer-clarington-ohio","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Monroe County","country":"US","lat":39.7728,"locality":"Clarington","lon":-80.8708,"note":"Bitdeer names only Clarington, Ohio. Coordinates are the village point from its Wikipedia article, which also gives the county; the site itself is not pinpointed.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-10","basis":"contracted","metric":"power_capacity","note":"Power under contract with an unnamed local utility. In October 2025 Bitdeer said the utility confirmed the full amount would be available by the end of Q3 2026; by 2026 the ready-for-service date was listed as to be updated.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":570}],"milestones":[{"date":"2025-10-14","event":"announced","kind":"actual","note":"Bitdeer reported it had begun design and layout planning for the site; this is the earliest source opened for this record, not necessarily the first disclosure.","source_ids":["s1"]},{"date":"2026-02-10","event":"other","kind":"actual","note":"Bitdeer first cited legal proceedings by neighboring American Heavy Plate Solutions as a risk to the timing of power and construction in the sources opened.","source_ids":["s2"]},{"date":"2027-Q2","event":"first_operational","kind":"planned","note":"October 2025 target for completing power and data center infrastructure, after substation energization in the first half of 2027. From February 2026 Bitdeer listed the timing as to be updated.","source_ids":["s1"]}],"name":"Bitdeer Clarington data center site","notes":"Bitdeer's intended use for the site has shifted: bitcoin mining built for later AI conversion (October 2025), HPC/AI (February 2026), colocation with tenant talks under way (March 2026), and colocation or crypto (August 2026). The workloads list reflects all of these. No 2026 source opened reports construction beyond design and preparation work.","parties":[{"name":"Bitdeer Technologies Group","role":"developer","source_ids":["s1","s2","s4"]}],"power_sources":[{"description":"570 MW contracted from an unnamed local utility, with a planned substation.","source_ids":["s1","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-10-14","publisher":"Bitdeer Technologies Group via SEC EDGAR","title":"Bitdeer announces September 2025 production and operations update (Form 6-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001899123/000121390025098957/ea026118901ex99-1_bitdeer.htm"},{"accessed":"2026-10-09","id":"s2","published":"2026-02-10","publisher":"Bitdeer Technologies Group via SEC EDGAR","title":"Bitdeer announces January 2026 production and operations update (Form 6-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1899123/000121390026013949/ea027632501ex99-1_bitdeer.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-16","publisher":"Bitdeer Technologies Group via SEC EDGAR","title":"Bitdeer announces February 2026 production and operations update (Form 6-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1899123/000121390026028021/ea028179501ex99-1.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929005222/https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm","id":"s4","published":"2026-08-10","publisher":"Bitdeer Technologies Group via SEC EDGAR","title":"Bitdeer reports unaudited financial results for the second quarter of 2026 (Form 6-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Clarington, Ohio","type":"other","url":"https://en.wikipedia.org/wiki/Clarington,_Ohio"}],"status":"announced","status_as_of":"2026-08-10","status_source_ids":["s4"],"summary":"Bitdeer development site at Clarington, Monroe County, Ohio, with 570 MW of power under contract with an unnamed local utility. In October 2025 Bitdeer planned a bitcoin mining data center whose core infrastructure would be designed for easy conversion to AI, targeting substation energization in the first half of 2027. Through 2026 the site stayed in design and preparation: legal proceedings filed by neighboring company American Heavy Plate Solutions left the timing of power and construction uncertain, and Bitdeer's listed use for the site moved from HPC/AI in February 2026 to colocation and crypto mining by August 2026.","workloads":["crypto_mining","colocation","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a2bccfaf-e1b2-5d80-8e08-ff37122f1c29","s2":"f38a7fa6-302c-5a1e-b8bc-c76c256b2a77","s3":"65d3684a-11e1-50fc-aea3-27d1ec900b1f","s4":"331ffac3-a2e5-5120-b0f7-a7fac2e79d12","s5":"b9186652-9d37-5bb1-aa9c-928486b916ce"},"source_file":"datacenters/projects/bitdeer-clarington-ohio.json","source_record_id":"bitdeer-clarington-ohio","source_record_sha256":"10a76766bcfe1bdddcc1859f59d9d9215325db951e58914f679613022357efa3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"815585f768f64af8591e94affcecb6c1e622f535ace83d659a7d80945b952c8d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4551992e6d4d1487d1ab/#project-6799aac4-c4f8-5902-b8ae-2fffb6fa893d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/6799aac4-c4f8-5902-b8ae-2fffb6fa893d.json
688df4a2-dc56-5cde-901a-87c87a08137e | imported:semiconductor-atlas:nextdc-s7-eastern-creek | vcc-site-dd0f231b23c8dd96495b | imported:semiconductor-atlas:nextdc-s7-eastern-creek | NEXTDC S7 Sydney | Australia | AU | -33.8059 | 150.85 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | NEXTDC names the suburb of Eastern Creek, about 45 km west of the Sydney CBD, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the suburb. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 22e3e100-6fac-50ab-ac5c-44d1960cfbf1 | announced | 2025-12-05 | 312 | imported_documented_status | ba2d3717-6fc9-5378-b316-250d91634f00 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"22e3e100-6fac-50ab-ac5c-44d1960cfbf1","notes":null,"party":"NEXTDC","relationship_scope":"unknown","role":"developer","source_record_id":"nextdc-s7-eastern-creek"},{"evidence_id":"ba2d3717-6fc9-5378-b316-250d91634f00","notes":null,"party":"NEXTDC","relationship_scope":"unknown","role":"developer","source_record_id":"nextdc-s7-eastern-creek"},{"evidence_id":"50c32be3-6305-56c1-aac1-5ae7c2897ec4","notes":null,"party":"NEXTDC","relationship_scope":"unknown","role":"developer","source_record_id":"nextdc-s7-eastern-creek"},{"evidence_id":"22e3e100-6fac-50ab-ac5c-44d1960cfbf1","notes":"Agreed in October 2024 to buy the land for about A$353 million before taxes and costs, with parcels to settle progressively across FY25; the December 2025 release refers to it as NEXTDC's S7 site.","party":"NEXTDC","relationship_scope":"unknown","role":"owner","source_record_id":"nextdc-s7-eastern-creek"},{"evidence_id":"ba2d3717-6fc9-5378-b316-250d91634f00","notes":"Agreed in October 2024 to buy the land for about A$353 million before taxes and costs, with parcels to settle progressively across FY25; the December 2025 release refers to it as NEXTDC's S7 site.","party":"NEXTDC","relationship_scope":"unknown","role":"owner","source_record_id":"nextdc-s7-eastern-creek"},{"evidence_id":"ba2d3717-6fc9-5378-b316-250d91634f00","notes":"Under a December 2025 memorandum of understanding, OpenAI and NEXTDC would collaborate on planning, developing and operating the campus and a GPU supercluster; the release does not describe a definitive agreement.","party":"OpenAI","relationship_scope":"unknown","role":"developer","source_record_id":"nextdc-s7-eastern-creek"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | NEXTDC |  |  |  |  | https://www.nextdc.com/news/building-the-next-generation-of-sovereign-ai-infrastructure-in-australia | https://www.nextdc.com/news/nextdc-acquires-new-sydney-data-centre-s7 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve NEXTDC S7 Sydney as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"nextdc-s7-eastern-creek"},"record":{"aliases":["S7 Sydney","S7 Eastern Creek"],"id":"nextdc-s7-eastern-creek","last_reviewed":"2026-10-09","location":{"admin1":"New South Wales","country":"AU","lat":-33.8059,"locality":"Eastern Creek","lon":150.85,"note":"NEXTDC names the suburb of Eastern Creek, about 45 km west of the Sydney CBD, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the suburb.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2024-10-17","basis":"planned","metric":"power_capacity","note":"Subject to development approval.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":550},{"applies_to":"campus","as_of":"2026-10","basis":"planned","metric":"power_capacity","note":"Undated NEXTDC facility page, viewed October 2026, lists 550MW+ of IT capacity.","power_scope":"it_load","qualifier":"at_least","source_ids":["s3"],"unit":"MW","value":550},{"applies_to":"campus","as_of":"2024-10-17","basis":"acquired","metric":"land_area","note":"Reported as about 258,000 square meters of developable land.","qualifier":"approximately","source_ids":["s1"],"unit":"hectares","value":25.8}],"milestones":[{"date":"2024-10-17","event":"site_acquired","kind":"actual","note":"Purchase agreement announced at about A$353 million before taxes and costs, with land parcels to settle progressively across FY25 subject to conditions.","source_ids":["s1"]},{"date":"2025-12-05","event":"other","kind":"actual","note":"NEXTDC and OpenAI signed a memorandum of understanding for the S7 campus and a GPU supercluster.","source_ids":["s2"]},{"date":"2027-H2","event":"first_operational","kind":"planned","note":"First phase expected in the second half of calendar 2027, subject to approvals.","source_ids":["s2"]}],"name":"NEXTDC S7 Sydney","parties":[{"name":"NEXTDC","role":"developer","source_ids":["s1","s2","s3"]},{"name":"NEXTDC","note":"Agreed in October 2024 to buy the land for about A$353 million before taxes and costs, with parcels to settle progressively across FY25; the December 2025 release refers to it as NEXTDC's S7 site.","role":"owner","source_ids":["s1","s2"]},{"name":"OpenAI","note":"Under a December 2025 memorandum of understanding, OpenAI and NEXTDC would collaborate on planning, developing and operating the campus and a GPU supercluster; the release does not describe a definitive agreement.","role":"developer","source_ids":["s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260608052956/https://www.nextdc.com/news/nextdc-acquires-new-sydney-data-centre-s7","id":"s1","published":"2024-10-17","publisher":"NEXTDC","title":"NEXTDC Announces Massive Expansion Plans with Acquisition of S7 Data Centre Site in Sydney","type":"company","url":"https://www.nextdc.com/news/nextdc-acquires-new-sydney-data-centre-s7"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260912152241/https://www.nextdc.com/news/building-the-next-generation-of-sovereign-ai-infrastructure-in-australia","id":"s2","published":"2025-12-05","publisher":"NEXTDC","title":"NEXTDC to Join OpenAI in Australia as an Infrastructure Partner","type":"company","url":"https://www.nextdc.com/news/building-the-next-generation-of-sovereign-ai-infrastructure-in-australia"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929101338/https://www.nextdc.com/data-centres/sydney-data-centres/s7-sydney","id":"s3","published":null,"publisher":"NEXTDC","title":"S7 Sydney Data Centre","type":"company","url":"https://www.nextdc.com/data-centres/sydney-data-centres/s7-sydney"}],"status":"announced","status_as_of":"2025-12-05","status_source_ids":["s2","s3"],"summary":"NEXTDC plans a hyperscale data center campus of about 550 MW on roughly 258,000 square meters of land it agreed to buy in Eastern Creek, western Sydney, in October 2024, subject to development approval. In December 2025 NEXTDC signed a memorandum of understanding with OpenAI to collaborate on planning, developing and operating the S7 campus and a large GPU supercluster as part of OpenAI's program for countries, with a first phase expected in the second half of 2027 if approvals are secured. NEXTDC's site still lists S7 as in planning.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"22e3e100-6fac-50ab-ac5c-44d1960cfbf1","s2":"ba2d3717-6fc9-5378-b316-250d91634f00","s3":"50c32be3-6305-56c1-aac1-5ae7c2897ec4"},"source_file":"datacenters/projects/nextdc-s7-eastern-creek.json","source_record_id":"nextdc-s7-eastern-creek","source_record_sha256":"9785caf78f3771cd71892e9d6971b50ee7bad038bc1e48b3298d25779be39e15","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8bf5c57e463069295572989c14e27565e89723b7cdefb27f1e9daa04a7847d72"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dd0f231b23c8dd96495b/#project-688df4a2-dc56-5cde-901a-87c87a08137e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/688df4a2-dc56-5cde-901a-87c87a08137e.json
6a3cb870-eb89-5d4b-a486-44eb7d10f8b0 | curated:runze-hong-kong-sandy-ridge-data-facility-cluster:initial-build | vcc-site-d0dffbb1f095b96397b5 | curated:runze-hong-kong-sandy-ridge-data-facility-cluster | Range Hong Kong Sandy Ridge Campus Current Infrastructure Build | Hong Kong | HK | 22.5318 | 114.1224 | Polygon | campus | official_lot_boundary_ring_transformed_EPSG2326_to_WGS84 | CSDI_LandsD_lot_layer_query_LotCSUID_145000953_native_ring_PROJ_HK1980_to_WGS84_1_round7 | official_land_grant_lot_boundary | official_source | campus_locator | Every native lot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. The lot is the government-identified site of the data facility cluster; it is a land-grant boundary, not a building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it. |  | The lot layer states no positional tolerance for this boundary; the datum-operation accuracy is not a boundary accuracy. | 50580ff2-c627-53a7-ac15-a975a9bd027f | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | f20cf9d5-dea2-5c33-8e2a-8a0379483381 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | http://static.cninfo.com.cn/finalpage/2026-08-28/1225521959.PDF | https://portal.csdi.gov.hk/server/rest/services/common/landsd_rcd_1637217253134_22729/FeatureServer/0/query?where=LotCSUID%3D%27145000953%27&outFields=*&returnGeometry=true&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d0dffbb1f095b96397b5/#project-6a3cb870-eb89-5d4b-a486-44eb7d10f8b0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/6a3cb870-eb89-5d4b-a486-44eb7d10f8b0.json
6aa46e28-dd40-513b-8722-f514b6503b02 | imported:semiconductor-atlas:brookfield-strangnas | vcc-site-6548266e7ea8549844f6 | imported:semiconductor-atlas:brookfield-strangnas | Brookfield AI center, Strängnäs | Sweden | SE | 59.367 | 17.033 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid from the Strängnäs Wikipedia article. Dagens PS places the site at Gorsingeberget on the outskirts of Strängnäs, but no cited source gives a parcel or coordinates, so the site itself is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6e8e9bad-0a96-5cfb-98da-f6af9ca3e60d | announced | 2025-06-04 | 496 | imported_documented_status | 6e8e9bad-0a96-5cfb-98da-f6af9ca3e60d | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6e8e9bad-0a96-5cfb-98da-f6af9ca3e60d","notes":null,"party":"Brookfield Asset Management","relationship_scope":"unknown","role":"developer","source_record_id":"brookfield-strangnas"},{"evidence_id":"51d611d9-d411-5a89-b168-8dfb345d234c","notes":null,"party":"Brookfield Asset Management","relationship_scope":"unknown","role":"developer","source_record_id":"brookfield-strangnas"},{"evidence_id":"51d611d9-d411-5a89-b168-8dfb345d234c","notes":"Reported in June 2025 as intending to sign a land allocation agreement selling about 350,000 square metres to Brookfield for SEK 525 million, with two years of exclusive planning rights.","party":"Strängnäs Municipality","relationship_scope":"unknown","role":"government","source_record_id":"brookfield-strangnas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://mfn.se/one/a/brookfield-asset-management-inc/brookfield-to-advance-ai-infrastructure-in-sweden-through-sek-95-billion-investment-884da3a0 | https://mfn.se/one/a/brookfield-asset-management-inc/brookfield-to-advance-ai-infrastructure-in-sweden-through-sek-95-billion-investment-884da3a0 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Brookfield AI center, Strängnäs as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"brookfield-strangnas"},"record":{"aliases":["Gorsingeberget AI center"],"id":"brookfield-strangnas","last_reviewed":"2026-10-09","location":{"admin1":"Södermanland County","admin2":"Strängnäs Municipality","country":"SE","lat":59.367,"locality":"Strängnäs","lon":17.033,"note":"Town centroid from the Strängnäs Wikipedia article. Dagens PS places the site at Gorsingeberget on the outskirts of Strängnäs, but no cited source gives a parcel or coordinates, so the site itself is not pinpointed.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2025-06-04","basis":"planned","metric":"power_capacity","note":"Brookfield described the site as currently 300 MW, rising to 750 MW if the additional land is allocated. IT versus facility scope is not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":750},{"applies_to":"phase","as_of":"2025-06-04","basis":"planned","metric":"land_area","note":"Reported as about 350,000 square metres of land in addition to the property already in the project.","phase_label":"Additional land under the planned land allocation agreement","qualifier":"approximately","source_ids":["s1","s2"],"unit":"hectares","value":35},{"applies_to":"campus","as_of":"2025-06-04","basis":"planned","metric":"jobs_permanent","note":"Dagens PS gives 3,000 jobs in total, of which 1,000 permanent.","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2025-06-04","basis":"planned","metric":"jobs_construction","note":"Additional jobs Brookfield links to the 10 to 15 year construction process.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":2000}],"milestones":[{"date":"2025-06-04","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2025-06","event":"other","kind":"actual","note":"The municipality was reported as intending to sign a land allocation agreement giving Brookfield two years of exclusive planning rights; whether it was signed was not confirmed by the sources opened.","source_ids":["s2"]}],"name":"Brookfield AI center, Strängnäs","notes":"Brookfield announced up to SEK 95 billion (about USD 10 billion) of AI infrastructure investment in Sweden, centred on the Strängnäs AI center but also covering data transfer, chip storage and energy generation, with no breakdown for the site; it is therefore not recorded as a campus investment. The record qualifies on the 750 MW site figure. No 2026 update on the land allocation agreement, detailed planning, grid connection or construction start was found; status reflects the June 2025 announcement.","parties":[{"name":"Brookfield Asset Management","role":"developer","source_ids":["s1","s2"]},{"name":"Strängnäs Municipality","note":"Reported in June 2025 as intending to sign a land allocation agreement selling about 350,000 square metres to Brookfield for SEK 525 million, with two years of exclusive planning rights.","role":"government","source_ids":["s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-06-04","publisher":"Brookfield Asset Management (via MFN)","title":"Brookfield To Advance AI Infrastructure in Sweden Through SEK 95 Billion Investment","type":"company","url":"https://mfn.se/one/a/brookfield-asset-management-inc/brookfield-to-advance-ai-infrastructure-in-sweden-through-sek-95-billion-investment-884da3a0"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260219062102/https://www.dagensps.se/foretag/digitalisering-ai/ai-jatte-etablerar-sig-i-strangnas-tusentals-nya-jobb/","id":"s2","published":"2025-06-04","publisher":"Dagens PS","title":"AI-jätte etablerar sig i Strängnäs – tusentals nya jobb","type":"news","url":"https://www.dagensps.se/foretag/digitalisering-ai/ai-jatte-etablerar-sig-i-strangnas-tusentals-nya-jobb/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260804205131/https://en.wikipedia.org/wiki/Str%C3%A4ngn%C3%A4s","id":"s3","published":null,"publisher":"Wikipedia","title":"Strängnäs","type":"other","url":"https://en.wikipedia.org/wiki/Str%C3%A4ngn%C3%A4s"}],"status":"announced","status_as_of":"2025-06-04","status_source_ids":["s1","s2"],"summary":"Brookfield Asset Management plans a large AI data center in Strängnäs, Sweden, announced in June 2025. Brookfield said a land allocation agreement for about 350,000 square metres of extra land would let the site grow from 300 MW to 750 MW. Local press placed the site at Gorsingeberget on the edge of town, with the municipality intending to sell the land for SEK 525 million and grant two years of exclusive planning rights. Brookfield expects more than 1,000 permanent jobs and a 10 to 15 year build-out. No 2026 progress report was found.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6e8e9bad-0a96-5cfb-98da-f6af9ca3e60d","s2":"51d611d9-d411-5a89-b168-8dfb345d234c","s3":"3b0268bc-5706-536f-b8be-bc6e7eb102ac"},"source_file":"datacenters/projects/brookfield-strangnas.json","source_record_id":"brookfield-strangnas","source_record_sha256":"8c82afafd59fa623fa44dc63c720db2bc356d54172b0ba49e5439118f88a9364","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"13eea0a5bcc56bfddfb3df6637cade823395af20037b134a81d39aa5ec051415"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6548266e7ea8549844f6/#project-6aa46e28-dd40-513b-8722-f514b6503b02 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/6aa46e28-dd40-513b-8722-f514b6503b02.json
6b11de63-a6b0-5513-87a1-b77ff3b71bfb | epoch-ai:data-center:dd4bfd7c-adf8-5312-9a4a-f2728f1fe791:cb-5-current-build | vcc-site-88b1acf055e1ab6200e4 | epoch-ai:data-center:dd4bfd7c-adf8-5312-9a4a-f2728f1fe791 | Lake Mariner CB-5 Current Build | United States | US | 43.3489 | -78.6029 | Point | project | official_census_street_address_range_interpolation | exact_issuer_defined_CB5_address_Census_NAD83_to_WGS84_pyproj_3_8_0 | official_project_street_address_locator | official_source | project_locator | Exact source-bound CB-5 postal-address interpolation along Lake Road. It is not the physical CB-5 building position, entrance, centre, construction footprint, surveyed parcel or campus boundary. No interior-campus position is claimed. |  | Census provides no site-specific accuracy for the address-range interpolation. | 8d8b2825-0c0b-585b-a596-7bfcdd59da40 | under_construction | 2026-08-05 | 69 | authoritative_physical_status_update | a323547e-8da2-5485-8748-8ab3cdf4f5b6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=7725%20Lake%20Road%2C%20Barker%2C%20NY%2014012&benchmark=Public_AR_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88b1acf055e1ab6200e4/#project-6b11de63-a6b0-5513-87a1-b77ff3b71bfb | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/6b11de63-a6b0-5513-87a1-b77ff3b71bfb.json
6b62c459-dc75-5f31-87d4-d6dbf47de8b0 | curated:edgecore-as02-sterling-virginia-campus:as02-data-center | vcc-site-191fa12b770b8f520c6e | curated:edgecore-as02-sterling-virginia-campus | EdgeCore AS02 Data Center | United States | US | 38.995 | -77.4461 | Polygon | project | direct_geometry | official_parcel_polygon | assessor_linked_project_parcel | official_source | project_locator | Exact geometryPrecision=8 county parcel geometry for MCPI 045465016000, identity-linked through assessor records to the AS02 address; project locator only, not a surveyed data-center or active-work footprint. |  | Loudoun County disclaims accuracy and supplies no survey-grade horizontal error. | dc629454-e376-50b1-aecf-b16ac4408021 | under_construction | 2026-07-01 | 104 | authoritative_physical_status_update | 2143d0c4-d059-55ca-8019-5785af3e2ed2 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/posts/edgecore-digital-infrastructure_yesterday-edgecore-celebrated-the-topping-activity-7478135212778938368-t979 | https://logis.loudoun.gov/gis/rest/services/COL_WebMercator/Parcels4DIT/MapServer/0/query | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-191fa12b770b8f520c6e/#project-6b62c459-dc75-5f31-87d4-d6dbf47de8b0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/6b62c459-dc75-5f31-87d4-d6dbf47de8b0.json
6f0acd88-cd04-5f3f-915c-48a71fd51f39 | curated:oracle-project-jupiter-dona-ana-campus:current-campus-build | vcc-site-f65d3c659a862ad07679 | curated:oracle-project-jupiter-dona-ana-campus | Oracle Project Jupiter Doña Ana County Current Campus Build | United States | US | 31.8183 | -106.6653 | Polygon | facility | cross_source_geometry | frozen_openstreetmap_exact_project_jupiter_named_development_polygon_as_parent_campus_locator | reviewed_openstreetmap_named_project_jupiter_development_polygon | community_mapped | campus_locator | Contributor-mapped Project Jupiter development polygon used only to locate the parent campus. It is not an official parcel, legal campus boundary, project footprint, building outline, security boundary, or current construction-progress extent. |  | OpenStreetMap supplies no survey, cadastral, planning-boundary, or numeric horizontal-accuracy statement. | 0cad69d1-3151-5073-af8e-73f8401bf2cb | under_construction | 2026-09-14 | 29 | authoritative_physical_status_update | 14a5995c-d88f-58cc-90f1-32f1639dd609 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"ca91c791-2e8a-56ad-adce-3d281dbd9edb","notes":"Role reported by analysts Epoch AI and Cleanview; not confirmed in a company source opened here.","party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-dona-ana-county"},{"evidence_id":"1d43f3d5-ca96-50d2-aadc-660f30981b8c","notes":"Role reported by analysts Epoch AI and Cleanview; not confirmed in a company source opened here.","party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-dona-ana-county"},{"evidence_id":"1d43f3d5-ca96-50d2-aadc-660f30981b8c","notes":"Role reported by analyst Cleanview; not confirmed in a company source opened here.","party":"BorderPlex Digital Assets","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-dona-ana-county"},{"evidence_id":"ca91c791-2e8a-56ad-adce-3d281dbd9edb","notes":"Analyst reporting, not a company disclosure: Cleanview reports an 18-year Oracle lease from BorderPlex, and Epoch AI lists Oracle as owner of the AI hardware. SoftBank's release groups the site with the Stargate sites being developed by Oracle.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-dona-ana-county"},{"evidence_id":"1d43f3d5-ca96-50d2-aadc-660f30981b8c","notes":"Analyst reporting, not a company disclosure: Cleanview reports an 18-year Oracle lease from BorderPlex, and Epoch AI lists Oracle as owner of the AI hardware. SoftBank's release groups the site with the Stargate sites being developed by Oracle.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-dona-ana-county"},{"evidence_id":"ceae2a2c-6865-53e9-8fac-62bfbc81528a","notes":"Ultimate customer through Oracle under the Stargate program.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-dona-ana-county"},{"evidence_id":"1d43f3d5-ca96-50d2-aadc-660f30981b8c","notes":"Ultimate customer through Oracle under the Stargate program.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-dona-ana-county"},{"evidence_id":"1d43f3d5-ca96-50d2-aadc-660f30981b8c","notes":"Analyst Cleanview reports Bloom as the planned sole supplier of on-site fuel cells after the April 2026 switch away from gas turbines.","party":"Bloom Energy","relationship_scope":"unknown","role":"power_supplier","source_record_id":"openai-stargate-dona-ana-county"}] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  |  |  | OpenAI; Oracle |  | https://www.oracle.com/news/announcement/project-jupiter-statement-on-construction-permitting-2026-09-14/ | https://www.openstreetmap.org/way/1476734418 | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same Project Jupiter four-building Oracle/STACK/BorderPlex campus in Dona Ana County. Explicit Project Jupiter alias and developer/tenant identities resolve the match despite the source county centroid being 59 km from the campus.","source_record_id":"openai-stargate-dona-ana-county","target_project_stable_key":"curated:oracle-project-jupiter-dona-ana-campus:current-campus-build"},"record":{"aliases":["Project Jupiter","Stargate New Mexico","Stargate Project Jupiter"],"id":"openai-stargate-dona-ana-county","last_reviewed":"2026-10-09","location":{"admin1":"New Mexico","admin2":"Doña Ana County","country":"US","lat":32.3282,"lon":-106.8494,"note":"Doña Ana County centroid from OpenStreetMap Nominatim. Sources name only the county; a September 2026 community release about the project was datelined Santa Teresa and focused on Santa Teresa and Sunland Park, but no site address was found.","precision":"admin2","source_ids":["s1","s3","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"power_capacity","note":"Analyst estimate, not a company disclosure: Epoch AI's projection of total facility power at completion.","power_scope":"facility","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":2200},{"applies_to":"campus","as_of":"2026-04","basis":"planned","metric":"power_capacity","note":"Planned Bloom fuel cell microgrid as reported by analyst Cleanview, not a company disclosure. It replaced an earlier design of two gas microgrids totaling about 2,210 MW whose air permit applications were withdrawn.","power_scope":"onsite_generation","qualifier":"up_to","source_ids":["s4"],"unit":"MW","value":2450},{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"buildings","note":"Reported by analysts Epoch AI and Cleanview, not a company disclosure.","qualifier":"exact","source_ids":["s3","s4"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2026-09-03","basis":"reported","metric":"jobs_construction","note":"New Mexico residents working on site to build the campus.","qualifier":"more_than","source_ids":["s5"],"unit":"count","value":700}],"milestones":[{"date":"2025-09-23","event":"announced","kind":"actual","note":"Named as one of three new Stargate sites under the OpenAI and Oracle agreement.","source_ids":["s1","s2"]},{"date":"2025-09","event":"construction_started","kind":"actual","note":"Analyst dates, not company disclosures: Cleanview dates the start to September 2025, while Epoch AI places it in Q4 2025 and saw foundation work in February 2026 imagery.","source_ids":["s3","s4"]},{"date":"2026-03","event":"other","kind":"actual","note":"The New Mexico State Land Office denied permits to route a proposed gas supply pipeline across state trust land, as reported by analyst Cleanview.","source_ids":["s4"]},{"date":"2026-04-27","event":"other","kind":"actual","note":"Oracle and BorderPlex announced a switch from gas turbines to Bloom fuel cells after withdrawing the turbine air permit applications; a new application restarted review. Reported by analyst Cleanview.","source_ids":["s4"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Analyst estimate, not a company target: Cleanview judges the first buildings unlikely to come online before mid-2027.","source_ids":["s4"]},{"date":"2028-Q4","event":"fully_operational","kind":"planned","note":"Analyst estimate by Epoch AI, not a company date.","source_ids":["s3"]}],"name":"Project Jupiter (Stargate New Mexico, Doña Ana County)","notes":"Developer, lease, capacity and timing details come mainly from analysts Cleanview and Epoch AI and are not company disclosures. No primary source for the project's total investment was opened, so no investment figure is recorded. The September 2026 release attributes about $80 million in state and local tax revenue for January through June and more than $4.7 billion of expected economic impact to the project; these are not investment figures.","parties":[{"name":"STACK Infrastructure","note":"Role reported by analysts Epoch AI and Cleanview; not confirmed in a company source opened here.","role":"developer","source_ids":["s3","s4"]},{"name":"BorderPlex Digital Assets","note":"Role reported by analyst Cleanview; not confirmed in a company source opened here.","role":"developer","source_ids":["s4"]},{"name":"Oracle","note":"Analyst reporting, not a company disclosure: Cleanview reports an 18-year Oracle lease from BorderPlex, and Epoch AI lists Oracle as owner of the AI hardware. SoftBank's release groups the site with the Stargate sites being developed by Oracle.","role":"tenant","source_ids":["s3","s4"]},{"name":"OpenAI","note":"Ultimate customer through Oracle under the Stargate program.","role":"tenant","source_ids":["s1","s4"]},{"name":"Bloom Energy","note":"Analyst Cleanview reports Bloom as the planned sole supplier of on-site fuel cells after the April 2026 switch away from gas turbines.","role":"power_supplier","source_ids":["s4"]}],"power_sources":[{"description":"Single off-grid microgrid of Bloom solid oxide fuel cells of up to 2.45 GW, the plan after April 2026 as reported by analyst Cleanview.","source_ids":["s4"],"type":"fuel_cell"},{"description":"Originally planned as two on-site natural gas microgrids, per analysts Epoch AI and Cleanview; the turbine design was dropped in April 2026, while a proposed gas supply pipeline still faces federal and state challenges.","source_ids":["s3","s4"],"type":"natural_gas_onsite"},{"description":"Developers committed to 500 MW of renewable energy by 2028 and another 500 MW by 2032, per analyst Cleanview.","source_ids":["s4"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-09-24","publisher":"SoftBank Group Corp.","title":"OpenAI, Oracle, and SoftBank expand Stargate with five new AI data center sites","type":"company","url":"https://group.softbank/en/news/press/20250924"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260313130748/https://www.datacenterknowledge.com/data-center-site-selection/openai-expands-stargate-with-five-new-data-center-sites-across-us","id":"s2","published":"2025-09-24","publisher":"Data Center Knowledge (Bloomberg)","title":"OpenAI Expands Stargate With Five New Data Center Sites Across US","type":"trade_press","url":"https://www.datacenterknowledge.com/data-center-site-selection/openai-expands-stargate-with-five-new-data-center-sites-across-us"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260517184326/https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand","id":"s3","published":"2026-04-17","publisher":"Epoch AI","title":"OpenAI Stargate: where the US sites stand","type":"analyst","url":"https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Cleanview","title":"Behind-the-meter data centers: Stargate Project Jupiter","type":"analyst","url":"https://cleanview.co/reports/behind-the-meter-data-centers/full-report/stargate-jupiter"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260911192503/https://www.bloomenergy.com/news/oracle-and-bloom-energy-announce-400000-in-support-for-roadrunner-food-bank-to-expand-food-access-in-santa-teresa-and-sunland-park/","id":"s5","published":"2026-09-03","publisher":"Bloom Energy","title":"Oracle and Bloom Energy Announce $400,000 in Support for Roadrunner Food Bank to Expand Food Access in Santa Teresa and Sunland Park","type":"company","url":"https://www.bloomenergy.com/news/oracle-and-bloom-energy-announce-400000-in-support-for-roadrunner-food-bank-to-expand-food-access-in-santa-teresa-and-sunland-park/"}],"status":"under_construction","status_as_of":"2026-09-03","status_source_ids":["s3","s5"],"summary":"Project Jupiter is a four-building AI campus in Doña Ana County, New Mexico, named in September 2025 as one of the new Oracle-linked Stargate sites serving OpenAI. Analysts report STACK Infrastructure and BorderPlex Digital Assets as developers and an 18-year Oracle lease. The campus is off-grid: it was first planned around two gas microgrids, but in April 2026 Oracle and BorderPlex withdrew those air permit applications in favor of up to 2.45 GW of Bloom fuel cells, per analyst Cleanview. Analyst Epoch AI projects about 2.2 GW at completion around late 2028. Foundations were under way by early 2026, and in September 2026 more than 700 New Mexico residents were working on site.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"ceae2a2c-6865-53e9-8fac-62bfbc81528a","s2":"bd448e1c-0346-5f3a-a89f-fb149a33857c","s3":"ca91c791-2e8a-56ad-adce-3d281dbd9edb","s4":"1d43f3d5-ca96-50d2-aadc-660f30981b8c","s5":"f7bf5e56-bdc6-543f-bb3e-84bebaeb13bc"},"source_file":"datacenters/projects/openai-stargate-dona-ana-county.json","source_record_id":"openai-stargate-dona-ana-county","source_record_sha256":"8e31c0a50f8ac2a25edc79eb491092d84a4d788513541c7270cf128763c98146","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"156ac01301ce08972f66809a5a42cd4aa10ee42a2c854aab06a6d3c5a5d5f659"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f65d3c659a862ad07679/#project-6f0acd88-cd04-5f3f-915c-48a71fd51f39 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/6f0acd88-cd04-5f3f-915c-48a71fd51f39.json
709cd37b-7f3a-5313-b3e2-a18ddc0885ec | curated:core-scientific-pecos-cottonwood-campus:initial-hdc-current-build | vcc-site-779f30ba676706e8e5db | curated:core-scientific-pecos-cottonwood-campus | Core Scientific Pecos Initial HDC Current Build | United States | US | 31.5342 | -103.8027 | Point | campus | source_community_representative_point | exact_OSM_relation20669718_Nominatim_representative_lon_lat | community_constituent_campus_reference_point | community_source | campus_locator | Exact named 1851 FM 2119 Core Scientific Pecos constituent locator within the issuer-grouped Cottonwood 1 and 2 campus. Not the new data hall, active construction extent, entrance, surveyed boundary, or an assertion that nearby COT2 is physically contiguous. One conservative campus group, no additional site for either constituent. The existing OSM facility identity is preserved. |  | Community feature and representative point have no documented site-specific numeric accuracy. | e95c68d5-dcea-51c7-a21a-11eaa2bf9140 | under_construction | 2026-06-02 | 133 | authoritative_physical_status_update | 58c85baa-cab9-55dd-b9b1-23bddefda121 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/posts/adamtsullivan_corescientific-aiinfrastructure-datacenters-activity-7467608574056300546-4pYw | https://nominatim.openstreetmap.org/lookup?osm_ids=R20669718&format=jsonv2&addressdetails=1&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-779f30ba676706e8e5db/#project-709cd37b-7f3a-5313-b3e2-a18ddc0885ec | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/709cd37b-7f3a-5313-b3e2-a18ddc0885ec.json
715ba9aa-f36a-5afb-b266-caeb7681b54e | imported:semiconductor-atlas:crusoe-lancium-childress-texas | vcc-site-5cc5c2b2cb554d5a3255 | imported:semiconductor-atlas:crusoe-lancium-childress-texas | Crusoe and Lancium Childress AI data center campus | United States | US | 34.4281 | -100.215 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City centroid of Childress from Wikipedia (s3); the announcements name the city and county but give no address for the 270-acre site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | c00fd435-d289-5c04-9091-11d567b1ae79 | announced | 2026-07-15 | 90 | imported_documented_status | c00fd435-d289-5c04-9091-11d567b1ae79 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c00fd435-d289-5c04-9091-11d567b1ae79","notes":"Designs and builds the data center.","party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"crusoe-lancium-childress-texas"},{"evidence_id":"d2e4e4c6-706c-5c7b-9563-afd037b97388","notes":"Designs and builds the data center.","party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"crusoe-lancium-childress-texas"},{"evidence_id":"c00fd435-d289-5c04-9091-11d567b1ae79","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"operator","source_record_id":"crusoe-lancium-childress-texas"},{"evidence_id":"d2e4e4c6-706c-5c7b-9563-afd037b97388","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"operator","source_record_id":"crusoe-lancium-childress-texas"},{"evidence_id":"c00fd435-d289-5c04-9091-11d567b1ae79","notes":"Owns the 270-acre site; secures the power interconnection and develops and manages the energy infrastructure.","party":"Lancium","relationship_scope":"unknown","role":"owner","source_record_id":"crusoe-lancium-childress-texas"},{"evidence_id":"d2e4e4c6-706c-5c7b-9563-afd037b97388","notes":"Owns the 270-acre site; secures the power interconnection and develops and manages the energy infrastructure.","party":"Lancium","relationship_scope":"unknown","role":"owner","source_record_id":"crusoe-lancium-childress-texas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Lancium | Crusoe |  |  |  | https://www.crusoe.ai/resources/newsroom/crusoe-and-lancium-announce-1-gigawatt-ai-data-center-campus-in-childress-texas | https://www.crusoe.ai/resources/newsroom/crusoe-and-lancium-announce-1-gigawatt-ai-data-center-campus-in-childress-texas | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Crusoe and Lancium Childress AI data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"crusoe-lancium-childress-texas","source_relations":[{"reason":"Crusoe/Lancium newly announced campus and IREN mining/HPC conversion campus are separately described operators/developments, sharing only the Childress town centroid.","relationship":"separate_named_developments","source_id":"iren-childress"}]},"record":{"aliases":["Childress County Clean Campus"],"id":"crusoe-lancium-childress-texas","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Childress County","country":"US","lat":34.4281,"locality":"Childress","lon":-100.215,"note":"City centroid of Childress from Wikipedia (s3); the announcements name the city and county but give no address for the 270-acre site.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-15","basis":"planned","metric":"power_capacity","note":"Grid-connected capacity at full scale; IT versus total not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-07-15","basis":"acquired","metric":"land_area","qualifier":"exact","source_ids":["s1","s2"],"unit":"acres","value":270},{"applies_to":"campus","as_of":"2026-07-15","basis":"planned","metric":"jobs_permanent","qualifier":"more_than","source_ids":["s1","s2"],"unit":"count","value":100}],"milestones":[{"date":"2026-07-15","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2026-Q3","event":"construction_started","kind":"planned","source_ids":["s1","s2"]}],"name":"Crusoe and Lancium Childress AI data center campus","parties":[{"name":"Crusoe","note":"Designs and builds the data center.","role":"developer","source_ids":["s1","s2"]},{"name":"Crusoe","role":"operator","source_ids":["s1","s2"]},{"name":"Lancium","note":"Owns the 270-acre site; secures the power interconnection and develops and manages the energy infrastructure.","role":"owner","source_ids":["s1","s2"]}],"power_sources":[{"description":"Grid-connected campus with the interconnection secured by Lancium.","source_ids":["s1","s2"],"type":"grid"},{"description":"Behind-the-meter solar described in Lancium's release.","source_ids":["s2"],"type":"solar"},{"description":"Energy storage resources at the campus, described as supporting grid reliability and efficiency.","source_ids":["s1","s2"],"type":"battery_storage"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-07-15","publisher":"Crusoe","title":"Crusoe and Lancium Announce 1.0 Gigawatt AI Data Center Campus in Childress, Texas","type":"company","url":"https://www.crusoe.ai/resources/newsroom/crusoe-and-lancium-announce-1-gigawatt-ai-data-center-campus-in-childress-texas"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-15","publisher":"Lancium","title":"Crusoe and Lancium Announce 1.0 Gigawatt AI Data Center Campus in Childress, Texas","type":"company","url":"https://lancium.com/2026/07/15/crusoe-and-lancium-announce-1-0-gigawatt-ai-data-center-campus-in-childress-texas/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260828090738/https://en.wikipedia.org/wiki/Childress,_Texas","id":"s3","published":null,"publisher":"Wikipedia","title":"Childress, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Childress,_Texas"}],"status":"announced","status_as_of":"2026-07-15","status_source_ids":["s1","s2"],"summary":"Crusoe and Lancium announced in July 2026 a grid-connected AI data center campus of 1.0 GW on 270 acres owned by Lancium in Childress, Texas, repeating the partnership model used at Abilene. Lancium owns the land, secures the interconnection and develops the energy infrastructure, including behind-the-meter solar and storage; Crusoe designs, builds and operates the data center for an unnamed hyperscale technology company. Construction was expected to start in the third quarter of 2026, using closed-loop liquid cooling.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c00fd435-d289-5c04-9091-11d567b1ae79","s2":"d2e4e4c6-706c-5c7b-9563-afd037b97388","s3":"177d1598-ed7b-59f6-bc0f-941cf1a828b0"},"source_file":"datacenters/projects/crusoe-lancium-childress-texas.json","source_record_id":"crusoe-lancium-childress-texas","source_record_sha256":"a80783e043af94acc3d310b6b23c3ec5da45db230e987b2ba158e15964808b6a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"ac584d99cba53770df1c187c4d5a09cbdd16010a4dcd712152cb0803e738b736"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5cc5c2b2cb554d5a3255/#project-715ba9aa-f36a-5afb-b266-caeb7681b54e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/715ba9aa-f36a-5afb-b266-caeb7681b54e.json
7206a400-093d-5c92-b1c5-c4243807de29 | curated:kao-data-harlow-campus:klon-03-building | vcc-site-c48f4a7325dfc30566cd | curated:kao-data-harlow-campus | KAO Data KLON-03 Data Centre Building | United Kingdom | GB | 51.7701 | 0.1305 | Point | campus | coordinates_to_point | government_hosted_report_coordinate_conversion | government_report_campus_centre_point | official_source | reviewed_site_locator | Campus-centre point derived deterministically from EPSG:27700 easting 547101 and northing 210080 supplied by the government-hosted KLON-03 site report. It is not a parcel, campus boundary, KLON-03 building centroid or footprint, and the report states no horizontal positional accuracy. |  | official source does not state positional accuracy | b133a4dc-126f-5e44-8841-f770b6fa9ad0 | under_construction | 2026-05-26 | 140 | authoritative_construction_start | e1894c7c-8c01-5b4d-9b09-4d28bcd050c2 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | tracked_identity_bound_uncertain_with_unadjudicated_later_clear_conflict_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://api.nzx.com/public/announcement/473284/attachment/469320/473284-469320.pdf | https://consult.environment-agency.gov.uk/psc/cmr-we4588ab-v017-9na-harlow-operations-limited/supporting_documents/Application%20%20Variation%20V002%20%20APPENDIX%20H%20%20Interim%20Baseline%20Report%20%20Kao%20Data%20Centre%202025%2031032025.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c48f4a7325dfc30566cd/#project-7206a400-093d-5c92-b1c5-c4243807de29 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7206a400-093d-5c92-b1c5-c4243807de29.json
726d6e35-8381-58ae-8dcd-eeb9ae23583a | curated:goodman-hkg10-tsuen-wan-data-centre:current-redevelopment | vcc-site-549acc09ba21cef52928 | curated:goodman-hkg10-tsuen-wan-data-centre | Goodman HKG10 Current Redevelopment | Hong Kong | HK | 22.3645 | 114.1198 | Polygon | campus | official_lot_boundary_ring_transformed_EPSG2326_to_WGS84 | CSDI_LandsD_lot_layer_query_LotCSUID_463000472_A_native_ring_PROJ_HK1980_to_WGS84_1_round7 | official_land_grant_lot_boundary | official_source | campus_locator | Every native vertex of D.D. 443 Lot 472 S.A is transformed once with the recorded PROJ operation and rounded to seven decimals. The lot is the government-recorded land of the Goodman Texaco Centre, whose conversion is HKG10; it is a land-grant lot section, not a building footprint, data-hall extent or current work extent. The government address point for Goodman Texaco Centre and Goodman's own listing point both fall inside it and are not selected. The display anchor is the planar shoelace centroid of the transformed ring in source vertex order, verified inside it. |  | The lot layer states no positional tolerance for this boundary; the datum-operation accuracy is not a boundary accuracy. | a421efb9-4743-597d-8207-ce31b596dc4f | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 3285e666-f6bb-575c-9571-01ed3c5bcf8f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | https://portal.csdi.gov.hk/server/rest/services/common/landsd_rcd_1637217253134_22729/FeatureServer/0/query?where=LotCSUID%3D%27463000472%20%20%20%20A%27&outFields=*&returnGeometry=true&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-549acc09ba21cef52928/#project-726d6e35-8381-58ae-8dcd-eeb9ae23583a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/726d6e35-8381-58ae-8dcd-eeb9ae23583a.json
7352e9b5-ecec-5497-8c62-3e6a8c7bd012 | curated:colt-frankfurt3-sossenheim-campus:frankfurt3-current-facility-build | vcc-site-78e17687e90595467a13 | curated:colt-frankfurt3-sossenheim-campus | Colt Frankfurt 3 Current Facility Build | Germany | DE | 50.1245 | 8.5876 | Polygon | building | cross_source_geometry | openstreetmap_exactly_named_colt_fra3_building_polygon_as_current_facility_build_locator | reviewed_openstreetmap_colt_fra3_named_building_polygon | community_mapped | project_locator | Contributor-mapped polygon for the named Colt FRA3 building, used only as a facility/project locator. It is not an official site or parcel boundary, not the complete campus, and not evidence that the entire mapped building equals the current first-phase build or present construction extent. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | d0865f65-7e1e-59ab-989c-2d49ec5ce196 | under_construction | 2026-07-19 | 86 | authoritative_physical_status_update | bf2135c6-1aa5-58e8-a318-7e67915aa1bb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-19","base":32.4,"confidence":0.99,"evidence_id":"bf2135c6-1aa5-58e8-a318-7e67915aa1bb","high":32.4,"low":32.4,"method":"reported","metric":"critical_it_mw","notes":"Planned critical-IT capacity for the completed Frankfurt 3 facility as a whole. The source does not allocate 32.4 MW to phase one; this is not phase-one capacity, current load, gross facility power, grid draw, generation, measured energy consumption, or proof of completion or operation.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.coltdatacentres.net/en-GB/our-locations/data-centre-locations-europe/frankfurt-three | https://www.openstreetmap.org/way/1417621831 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-78e17687e90595467a13/#project-7352e9b5-ecec-5497-8c62-3e6a8c7bd012 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7352e9b5-ecec-5497-8c62-3e6a8c7bd012.json
735e570e-2923-5425-a0af-2a13e94f49e3 | imported:semiconductor-atlas:microsoft-pecos-texas | vcc-site-91ad5264ef3af020a0ed | imported:semiconductor-atlas:microsoft-pecos-texas | Microsoft Pecos datacenter campus | United States | US | 31.4156 | -103.5 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Pecos city coordinates from its Wikipedia page. Sources name Pecos and Reeves County but give no site or acreage. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ebbafd06-419e-5b39-9468-e6032100b037 | announced | 2026-07-02 | 103 | imported_documented_status | ebbafd06-419e-5b39-9468-e6032100b037 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ebbafd06-419e-5b39-9468-e6032100b037","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-pecos-texas"},{"evidence_id":"45451e60-0ef9-54f8-a31b-67101d32a6f4","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-pecos-texas"},{"evidence_id":"45451e60-0ef9-54f8-a31b-67101d32a6f4","notes":"Energy Forge One LLC, a wholly owned Chevron subsidiary, signed a 20-year, multi-gigawatt power purchase agreement to supply the campus from the co-located Project Kilby gas plant.","party":"Chevron (Energy Forge One LLC)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"microsoft-pecos-texas"},{"evidence_id":"7f43e8a0-39b3-5926-9d59-3cc928abebf9","notes":"Energy Forge One LLC, a wholly owned Chevron subsidiary, signed a 20-year, multi-gigawatt power purchase agreement to supply the campus from the co-located Project Kilby gas plant.","party":"Chevron (Energy Forge One LLC)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"microsoft-pecos-texas"},{"evidence_id":"cbdd78ec-28ca-5eda-84a2-873eb943bbfd","notes":"Energy Forge One LLC, a wholly owned Chevron subsidiary, signed a 20-year, multi-gigawatt power purchase agreement to supply the campus from the co-located Project Kilby gas plant.","party":"Chevron (Energy Forge One LLC)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"microsoft-pecos-texas"},{"evidence_id":"7f43e8a0-39b3-5926-9d59-3cc928abebf9","notes":"Developing Project Kilby with Chevron.","party":"Engine No. 1","relationship_scope":"unknown","role":"power_supplier","source_record_id":"microsoft-pecos-texas"},{"evidence_id":"cbdd78ec-28ca-5eda-84a2-873eb943bbfd","notes":"Developing Project Kilby with Chevron.","party":"Engine No. 1","relationship_scope":"unknown","role":"power_supplier","source_record_id":"microsoft-pecos-texas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://blogs.microsoft.com/blog/2026/06/22/powering-the-next-wave-of-ai-expanding-capacity-with-our-new-datacenter-in-pecos/ | https://blogs.microsoft.com/blog/2026/06/22/powering-the-next-wave-of-ai-expanding-capacity-with-our-new-datacenter-in-pecos/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Pecos datacenter campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-pecos-texas","source_relations":[{"reason":"Core Scientific Cottonwood on FM 2119 and Microsoft/Chevron Project Kilby are distinct named developments; shared city coordinate does not imply identity.","relationship":"separate_named_developments","source_id":"core-scientific-pecos"}]},"record":{"aliases":[],"id":"microsoft-pecos-texas","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Reeves County","country":"US","lat":31.4156,"locality":"Pecos","lon":-103.5,"note":"Coordinates are the Pecos city coordinates from its Wikipedia page. Sources name Pecos and Reeves County but give no site or acreage.","precision":"locality","source_ids":["s1","s3","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-22","basis":"planned","metric":"power_capacity","note":"Capacity Microsoft says the campus adds to its global datacenter fleet.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":2000},{"applies_to":"campus","as_of":"2026-06-23","basis":"planned","metric":"power_capacity","note":"Chevron's co-located Project Kilby gas plant, to be built in modular phases and run behind the meter for the campus; subject to a final investment decision.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s3","s4"],"unit":"MW","value":2670},{"applies_to":"campus","as_of":"2026-06-22","basis":"planned","metric":"jobs_construction","note":"At peak build-out; Microsoft also expects hundreds of permanent operational jobs.","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"count","value":6000}],"milestones":[{"date":"2026-06-22","event":"announced","kind":"actual","source_ids":["s1","s3"]},{"date":"2028","event":"other","kind":"planned","note":"Project Kilby is expected to begin delivering power, subject to Chevron's final investment decision expected later in 2026.","source_ids":["s3","s4"]}],"name":"Microsoft Pecos datacenter campus","notes":"Microsoft gives no dollar figure beyond a multibillion-dollar investment, so no investment metric is recorded. Whether the 2 GW is IT or facility power is not stated. No report of construction start was found as of October 2026.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2"]},{"name":"Chevron (Energy Forge One LLC)","note":"Energy Forge One LLC, a wholly owned Chevron subsidiary, signed a 20-year, multi-gigawatt power purchase agreement to supply the campus from the co-located Project Kilby gas plant.","role":"power_supplier","source_ids":["s2","s3","s4"]},{"name":"Engine No. 1","note":"Developing Project Kilby with Chevron.","role":"power_supplier","source_ids":["s3","s4"]}],"power_sources":[{"description":"Co-located Project Kilby gas plant by Chevron with Engine No. 1, using GE Vernova turbines plus Solar Turbines units, designed to scale to 2.67 GW and operate behind the meter with selective catalytic reduction for nitrogen oxides; Microsoft says it funds the new generation.","source_ids":["s1","s3","s4"],"type":"natural_gas_onsite"},{"description":"Microsoft expects to connect the plant and campus to the wider grid over time, in coordination with utilities and local authorities; no timeline is given.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-06-22","publisher":"Microsoft","title":"Powering the next wave of AI: Expanding capacity with our new datacenter in Pecos","type":"company","url":"https://blogs.microsoft.com/blog/2026/06/22/powering-the-next-wave-of-ai-expanding-capacity-with-our-new-datacenter-in-pecos/"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-02","publisher":"Orrick","title":"Microsoft Expands Global Data Center Capacity with 2 GW Data Center and Co-Located Power Facility in West Texas","type":"other","url":"https://www.orrick.com/en/News/2026/07/Microsoft-Expands-Global-Data-Center-Capacity-with-2-GW-Data-Center-and-Co-Located-Power-Facility"},{"accessed":"2026-10-09","id":"s3","published":"2026-06-22","publisher":"The Energy Mag","title":"Microsoft to Build 2GW AI Data Center Campus in West Texas With Onsite Gas Power","type":"trade_press","url":"https://theenergymag.com/news/2026-06-22/microsoft-2-gigawatt-ai-data-center-west-texas-onsite-gas"},{"accessed":"2026-10-09","id":"s4","published":"2026-06-23","publisher":"W.Media","title":"Microsoft's upcoming data center campus in Texas to expand global capacity by 2 GW","type":"trade_press","url":"https://w.media/microsofts-new-dc-pecos-texas/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Pecos, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Pecos,_Texas"}],"status":"announced","status_as_of":"2026-07-02","status_source_ids":["s1","s2"],"summary":"Microsoft campus announced in June 2026 for Pecos in Reeves County, West Texas, adding about 2 GW of capacity for AI and cloud services through a multibillion-dollar investment over five to seven years. At launch it will run behind the meter on a co-located gas plant, Chevron's Project Kilby, built with Engine No. 1 and GE Vernova and sized to reach 2.67 GW in phases under a 20-year power deal; first power is expected in 2028, subject to Chevron's final investment decision. Microsoft says it funds the generation, plans to connect to the wider grid later, and will use closed-loop cooling.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"ebbafd06-419e-5b39-9468-e6032100b037","s2":"45451e60-0ef9-54f8-a31b-67101d32a6f4","s3":"7f43e8a0-39b3-5926-9d59-3cc928abebf9","s4":"cbdd78ec-28ca-5eda-84a2-873eb943bbfd","s5":"b9c3f53f-79ac-5fb9-bf5e-f72a4a9b5bda"},"source_file":"datacenters/projects/microsoft-pecos-texas.json","source_record_id":"microsoft-pecos-texas","source_record_sha256":"7ce5572946d5d112689909ab6b9d9430e8fb5b485daf5e271025b759da7b7572","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"c0d45bed51b7d96a8403eadd894ba6f1f35864bc709679ea7c66616e9ec68367"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-91ad5264ef3af020a0ed/#project-735e570e-2923-5425-a0af-2a13e94f49e3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/735e570e-2923-5425-a0af-2a13e94f49e3.json
74d6b0be-d450-509d-a406-ddfed7ede756 | imported:semiconductor-atlas:prometheus-hyperscale-evanston | vcc-site-a393d0e2bc6a6f9efbd5 | imported:semiconductor-atlas:prometheus-hyperscale-evanston | Prometheus Hyperscale Evanston campus | United States | US | 41.2683 | -110.9632 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of Evanston (s5). Local reporting places the site about 12 miles east of Evanston on the south side of Interstate 80, so the campus lies some distance east of this point. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 60251015-30da-5d17-8ff5-4e2de7e27afc | announced | 2026-06-22 | 113 | imported_documented_status | 00fc7415-5229-515f-8ed4-aa7207226c06 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"60251015-30da-5d17-8ff5-4e2de7e27afc","notes":null,"party":"Prometheus Hyperscale","relationship_scope":"unknown","role":"developer","source_record_id":"prometheus-hyperscale-evanston"},{"evidence_id":"00fc7415-5229-515f-8ed4-aa7207226c06","notes":null,"party":"Prometheus Hyperscale","relationship_scope":"unknown","role":"developer","source_record_id":"prometheus-hyperscale-evanston"},{"evidence_id":"d9e09958-cfd3-559e-af83-401c8e882905","notes":null,"party":"Prometheus Hyperscale","relationship_scope":"unknown","role":"developer","source_record_id":"prometheus-hyperscale-evanston"},{"evidence_id":"c6d27185-15ec-5415-8497-38db17cb1fb2","notes":null,"party":"Prometheus Hyperscale","relationship_scope":"unknown","role":"developer","source_record_id":"prometheus-hyperscale-evanston"},{"evidence_id":"60251015-30da-5d17-8ff5-4e2de7e27afc","notes":"Granted the conditional use permit and earlier approved letters of support addressed to Meta and Microsoft at the developer's request.","party":"Uinta County Board of Commissioners","relationship_scope":"unknown","role":"government","source_record_id":"prometheus-hyperscale-evanston"},{"evidence_id":"d9e09958-cfd3-559e-af83-401c8e882905","notes":"Granted the conditional use permit and earlier approved letters of support addressed to Meta and Microsoft at the developer's request.","party":"Uinta County Board of Commissioners","relationship_scope":"unknown","role":"government","source_record_id":"prometheus-hyperscale-evanston"},{"evidence_id":"c6d27185-15ec-5415-8497-38db17cb1fb2","notes":"Granted the conditional use permit and earlier approved letters of support addressed to Meta and Microsoft at the developer's request.","party":"Uinta County Board of Commissioners","relationship_scope":"unknown","role":"government","source_record_id":"prometheus-hyperscale-evanston"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://townlift.com/2026/06/proposed-ai-data-center-near-evanston-advances-as-prometheus-courts-major-tech-clients/ | https://www.kpcw.org/state-regional/2026-06-19/1-25gw-data-center-approved-on-ranchland-near-evanston-wyoming | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Prometheus Hyperscale Evanston campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"prometheus-hyperscale-evanston"},"record":{"aliases":["Prometheus Hyperscale flagship campus","Wyoming Hyperscale Whitebox"],"id":"prometheus-hyperscale-evanston","last_reviewed":"2026-10-09","location":{"admin1":"Wyoming","admin2":"Uinta County","country":"US","lat":41.2683,"locality":"Evanston","lon":-110.9632,"note":"Coordinates are the Wikipedia centroid of Evanston (s5). Local reporting places the site about 12 miles east of Evanston on the south side of Interstate 80, so the campus lies some distance east of this point.","precision":"locality","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"phase","as_of":"2026-06-22","basis":"planned","metric":"power_capacity","note":"Described as the initial capacity, with the first phase expected to take 48 to 60 months to build. Cowboy State Daily rounded it to 1.2 GW in February 2026. IT versus facility scope is not stated.","phase_label":"Initial phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s3","s4"],"unit":"MW","value":1250},{"applies_to":"campus","as_of":"2026-06-22","basis":"planned","metric":"power_capacity","note":"Company-stated long-term development path; no schedule given.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s3"],"unit":"MW","value":5000},{"applies_to":"campus","as_of":"2026-06-19","basis":"reported","metric":"land_area","note":"Ranchland held by the founder's family.","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"acres","value":506},{"applies_to":"campus","as_of":"2026-02-14","basis":"reported","metric":"jobs_construction","note":"Estimate given by the county economic development director.","qualifier":"range","source_ids":["s4"],"unit":"count","value":1500,"value_high":2000},{"applies_to":"campus","as_of":"2026-06-22","basis":"planned","metric":"jobs_construction","note":"Construction positions by 2029 claimed by Prometheus and the Build Wyoming initiative, within a total of nearly 12,000 direct and indirect jobs. Much higher than the county's February 2026 estimate.","qualifier":"approximately","source_ids":["s2"],"unit":"count","value":8000},{"applies_to":"campus","as_of":"2026-02-14","basis":"reported","metric":"jobs_permanent","note":"Initial permanent jobs estimated by the county economic development director.","qualifier":"range","source_ids":["s4"],"unit":"count","value":300,"value_high":400}],"milestones":[{"date":"2024","event":"announced","kind":"actual","note":"The project, formerly called Wyoming Hyperscale Whitebox, was relaunched in 2024 after an original 120 MW plan in 2020.","source_ids":["s3"]},{"date":"2026-02","event":"other","kind":"actual","note":"Uinta County approved letters of support addressed to Meta and Microsoft, written at the developer's request.","source_ids":["s4"]},{"date":"2026-06","event":"permit_approved","kind":"actual","note":"Uinta County commissioners unanimously approved a conditional use permit after the county planning commission recommended approval; reported on 19 June 2026 as a Tuesday vote.","source_ids":["s1","s3"]}],"name":"Prometheus Hyperscale Evanston campus","notes":"Meta and Microsoft are not listed as tenants: the county's support letters were written at the developer's request, and in February 2026 the county chair said any deal was a long way off. Prometheus says its closed-loop water-glycol cooling will not draw groundwater, surface water or Bear River water, with a private on-site well for domestic plumbing. No report of final permitting or a construction start after June 2026 was found.","parties":[{"name":"Prometheus Hyperscale","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Uinta County Board of Commissioners","note":"Granted the conditional use permit and earlier approved letters of support addressed to Meta and Microsoft at the developer's request.","role":"government","source_ids":["s1","s3","s4"]}],"power_sources":[{"description":"Planned on-site natural gas generation run as an islanded microgrid instead of a grid interconnection, which the company says avoids interconnection delays. The founder has said he eventually wants to add nuclear power.","source_ids":["s1","s2","s3"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260718111208/https://www.kpcw.org/state-regional/2026-06-19/1-25gw-data-center-approved-on-ranchland-near-evanston-wyoming","id":"s1","published":"2026-06-19","publisher":"KPCW","title":"1.25GW data center approved on ranchland near Evanston, Wyoming","type":"news","url":"https://www.kpcw.org/state-regional/2026-06-19/1-25gw-data-center-approved-on-ranchland-near-evanston-wyoming"},{"accessed":"2026-10-09","id":"s2","published":"2026-06-22","publisher":"TownLift","title":"Proposed AI data center near Evanston advances as Prometheus courts major tech clients","type":"news","url":"https://townlift.com/2026/06/proposed-ai-data-center-near-evanston-advances-as-prometheus-courts-major-tech-clients/"},{"accessed":"2026-10-09","id":"s3","published":"2026-06-22","publisher":"Baxtel","title":"Wyoming Approves Prometheus Hyperscale's Gigawatt Data Center Campus","type":"trade_press","url":"https://baxtel.com/news/wyoming-approves-prometheus-hyperscale-s-gigawatt-data-center-campus"},{"accessed":"2026-10-09","id":"s4","published":"2026-02-14","publisher":"Cowboy State Daily","title":"1.2-Gigawatt Data Center Near Evanston In Talks With Meta And Microsoft","type":"news","url":"https://cowboystatedaily.com/2026/02/14/data-center-near-evanston-is-talking-to-microsoft-meta/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Evanston, Wyoming","type":"other","url":"https://en.wikipedia.org/wiki/Evanston,_Wyoming"}],"status":"announced","status_as_of":"2026-06-22","status_source_ids":["s2","s3"],"summary":"Proposed AI data center campus on about 506 acres of family ranchland roughly 12 miles east of Evanston, Wyoming, south of Interstate 80 in Uinta County. Prometheus Hyperscale plans 1.25 GW in a first phase with a stated path to 5 GW, run as an islanded microgrid on on-site natural gas generation rather than the public grid. Uinta County commissioners unanimously granted a conditional use permit in June 2026; the company says construction could start within six months of final permitting and take four to five years. The county sent support letters to Meta and Microsoft, but no tenant has been confirmed.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"60251015-30da-5d17-8ff5-4e2de7e27afc","s2":"00fc7415-5229-515f-8ed4-aa7207226c06","s3":"d9e09958-cfd3-559e-af83-401c8e882905","s4":"c6d27185-15ec-5415-8497-38db17cb1fb2","s5":"491f7a0e-b853-5f93-8da6-3cbf7c744a33"},"source_file":"datacenters/projects/prometheus-hyperscale-evanston.json","source_record_id":"prometheus-hyperscale-evanston","source_record_sha256":"96fae3106ce00d84906fe415cb9a42d8ad8e78e863fa6a9a76f62c1a4430ca5c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8a379e650d83c37fb15431359dd0c005f7c3d62830ef93407788400280adbed6"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a393d0e2bc6a6f9efbd5/#project-74d6b0be-d450-509d-a406-ddfed7ede756 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/74d6b0be-d450-509d-a406-ddfed7ede756.json
75596cc6-0434-596d-be35-53be39de9c0a | imported:semiconductor-atlas:softbank-sakai | vcc-site-d9155165962c78be00da | imported:semiconductor-atlas:softbank-sakai | SoftBank Osaka Sakai AI data center | Japan | JP | 34.596 | 135.4333 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | SoftBank names Sharp's Sakai LCD plant in Sakai City; Sharp gives the plant address as 1 Takumi-cho, Sakai-ku. Coordinates are the OpenStreetMap Nominatim centroid of the Takumi-cho neighbourhood, so they approximate the plant complex rather than the exact SoftBank portion (about 60% of the plant land). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 91c22675-230e-5b67-a4f1-96c461b4eb5b | under_construction | 2026-06-23 | 112 | imported_documented_status | a05d05b8-991f-5529-9c7b-10cf3a915972 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"91c22675-230e-5b67-a4f1-96c461b4eb5b","notes":null,"party":"SoftBank Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-sakai"},{"evidence_id":"0efd0f29-b8d7-5a51-9714-1ed7cb45140d","notes":null,"party":"SoftBank Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-sakai"},{"evidence_id":"a05d05b8-991f-5529-9c7b-10cf3a915972","notes":null,"party":"SoftBank Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-sakai"},{"evidence_id":"0efd0f29-b8d7-5a51-9714-1ed7cb45140d","notes":"Signed a purchase agreement with Sharp Corporation in March 2025 for the land and buildings; Sharp was the seller.","party":"SoftBank Corp.","relationship_scope":"unknown","role":"owner","source_record_id":"softbank-sakai"},{"evidence_id":"04c12ac4-c0e4-5912-9150-44d384663222","notes":"Signed a purchase agreement with Sharp Corporation in March 2025 for the land and buildings; Sharp was the seller.","party":"SoftBank Corp.","relationship_scope":"unknown","role":"owner","source_record_id":"softbank-sakai"},{"evidence_id":"04c12ac4-c0e4-5912-9150-44d384663222","notes":"TechCrunch cited a Nikkei report that OpenAI intends to use GPUs at the Sakai site to develop models for Japan; OpenAI declined to comment, SoftBank did not confirm, and SoftBank's releases do not name OpenAI as a tenant.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"softbank-sakai"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | SoftBank Corp. |  |  | OpenAI |  | https://www.softbank.jp/en/sbnews/entry/20260623_01 | https://www.softbank.jp/en/corp/news/press/sbkk/2024/20240607_01 | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve SoftBank Osaka Sakai AI data center as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"softbank-sakai"},"record":{"aliases":["Osaka Sakai Activation Base","Sharp Sakai Plant AI data center"],"id":"softbank-sakai","last_reviewed":"2026-10-09","location":{"admin1":"Osaka Prefecture","admin2":"Sakai-ku","country":"JP","lat":34.596,"locality":"Sakai","lon":135.4333,"note":"SoftBank names Sharp's Sakai LCD plant in Sakai City; Sharp gives the plant address as 1 Takumi-cho, Sakai-ku. Coordinates are the OpenStreetMap Nominatim centroid of the Takumi-cho neighbourhood, so they approximate the plant complex rather than the exact SoftBank portion (about 60% of the plant land).","precision":"approximate_site","source_ids":["s1","s3","s7"]},"metrics":[{"applies_to":"phase","as_of":"2024-06-07","basis":"planned","metric":"power_capacity","note":"Initial capacity stated in the June 2024 memorandum announcement.","phase_label":"Initial phase (2024 MoU plan)","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2024-06-07","basis":"planned","metric":"power_capacity","note":"Long-term figure from the June 2024 announcement; later SoftBank releases cite expansion beyond 250 MW instead.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":400},{"applies_to":"phase","as_of":"2025-03-14","basis":"planned","metric":"power_capacity","note":"SoftBank describes this as receiving (utility intake) capacity.","phase_label":"Initial phase targeted for 2026","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s2","s3"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2025-03-14","basis":"planned","metric":"power_capacity","note":"Future receiving capacity. The December 2024 release says the 250 MW-class supply was expected about four years after the purchase is completed and made the purchase conditional on it.","power_scope":"grid_connection","qualifier":"more_than","source_ids":["s2","s3"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2025-03-14","basis":"planned","metric":"power_capacity","note":"TechCrunch's eventual figure, which differs slightly from SoftBank's own 250 MW-plus figure.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s4"],"unit":"MW","value":240},{"applies_to":"phase","as_of":"2026-05-12","basis":"planned","metric":"power_capacity","note":"SoftBank's May 2026 growth strategy gives 140 MW as the power assumed for the AI computing infrastructure under development at Sakai.","phase_label":"AX Factory AI computing infrastructure","power_scope":"unspecified","qualifier":"exact","source_ids":["s5"],"unit":"MW","value":140},{"applies_to":"campus","as_of":"2025-03-14","basis":"announced","metric":"investment","note":"Purchase price for the plant land and buildings only; no total build cost has been published by SoftBank.","qualifier":"approximately","source_ids":["s2","s3","s4"],"unit":"JPY","value":100000000000},{"applies_to":"campus","as_of":"2024-06-07","basis":"planned","metric":"land_area","note":"Reported as about 440,000 square meters, roughly 60% of the plant land, in the 2024 memorandum announcement.","qualifier":"approximately","source_ids":["s1"],"unit":"hectares","value":44},{"applies_to":"campus","as_of":"2025-03-14","basis":"acquired","metric":"land_area","note":"Reported as about 450,000 square meters in the purchase releases.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"hectares","value":45},{"applies_to":"campus","as_of":"2025-03-14","basis":"planned","metric":"floor_area","note":"Total floor area of the existing plant buildings being acquired; the 2024 memorandum release gave about 750,000.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"sq_m","value":840000}],"milestones":[{"date":"2024-06-07","event":"announced","kind":"actual","note":"Memorandum of understanding with Sharp announced.","source_ids":["s1"]},{"date":"2024-12-20","event":"other","kind":"actual","note":"SoftBank board conditionally approved acquiring the land and buildings.","source_ids":["s2"]},{"date":"2025-03-14","event":"site_acquired","kind":"actual","note":"Purchase and sale agreement signed with Sharp; the date of final closing was not found.","source_ids":["s3","s4"]},{"date":"2026","event":"first_operational","kind":"planned","note":"Target for the initial roughly 150 MW phase in the December 2024 and March 2025 releases. No 2026 source found confirms that operation has begun.","source_ids":["s2","s3"]},{"date":"2025","event":"first_operational","kind":"planned","note":"Original June 2024 target for full-scale operation; later releases moved the target to 2026.","source_ids":["s1"]}],"name":"SoftBank Osaka Sakai AI data center","parties":[{"name":"SoftBank Corp.","role":"developer","source_ids":["s1","s3","s6"]},{"name":"SoftBank Corp.","note":"Signed a purchase agreement with Sharp Corporation in March 2025 for the land and buildings; Sharp was the seller.","role":"owner","source_ids":["s3","s4"]},{"name":"OpenAI","note":"TechCrunch cited a Nikkei report that OpenAI intends to use GPUs at the Sakai site to develop models for Japan; OpenAI declined to comment, SoftBank did not confirm, and SoftBank's releases do not name OpenAI as a tenant.","role":"tenant","source_ids":["s4"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-06-07","publisher":"SoftBank Corp.","title":"SoftBank Corp. to Construct Large-scale AI Data Center that Utilizes Sharp Sakai Plant","type":"company","url":"https://www.softbank.jp/en/corp/news/press/sbkk/2024/20240607_01"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260927010220/https://www.softbank.jp/corp/news/press/sbkk/2024/20241220_03/","id":"s2","published":"2024-12-20","publisher":"SoftBank Corp.","title":"Resolution on acquisition of land and buildings at Sharp's Sakai Plant for an AI data center (Japanese)","type":"company","url":"https://www.softbank.jp/corp/news/press/sbkk/2024/20241220_03"},{"accessed":"2026-10-09","id":"s3","published":"2025-03-14","publisher":"SoftBank Corp.","title":"AIデータセンターの構築に向けて、シャープ堺工場の土地や建物の取得に関する契約を締結","type":"company","url":"https://www.softbank.jp/corp/news/press/sbkk/2025/20250314_01"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260828164909/https://techcrunch.com/2025/03/14/softbank-buys-676m-old-sharp-plant-for-its-openai-collab-in-japan/","id":"s4","published":"2025-03-14","publisher":"TechCrunch","title":"SoftBank buys $676M old Sharp plant for its OpenAI collab in Japan","type":"news","url":"https://techcrunch.com/2025/03/14/softbank-buys-676m-old-sharp-plant-for-its-openai-collab-in-japan"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260922125042/https://www.softbank.jp/en/sbnews/entry/20260512_01","id":"s5","published":"2026-05-12","publisher":"SoftBank Corp. (SoftBank News)","title":"Activating AI for Society: SoftBank Corp.'s New Growth Strategy to Continuously Achieve Record-High Profits","type":"company","url":"https://www.softbank.jp/en/sbnews/entry/20260512_01"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260922125049/https://www.softbank.jp/en/sbnews/entry/20260623_01","id":"s6","published":"2026-06-23","publisher":"SoftBank Corp. (SoftBank News)","title":"SoftBank Corp.'s 40th Annual General Meeting of Shareholders: Building on Telecommunications Foundation to Unlock Potential of AI","type":"company","url":"https://www.softbank.jp/en/sbnews/entry/20260623_01"},{"accessed":"2026-10-09","id":"s7","published":"2009-04-08","publisher":"Sharp Corporation","title":"New LCD Panel Plant under Construction in Sakai City to Start Operations in October 2009","type":"company","url":"https://global.sharp/corporate/news/090408_2.html"}],"status":"under_construction","status_as_of":"2026-06-23","status_source_ids":["s6"],"summary":"SoftBank Corp. is converting part of Sharp's former LCD panel plant in Sakai, Osaka into a large AI data center, reusing the plant's land, buildings, power and cooling infrastructure. SoftBank agreed in March 2025 to buy the land and buildings for about 100 billion yen, targeting operation of an initial phase of roughly 150 MW receiving capacity in 2026 and later expansion beyond 250 MW. In 2026 SoftBank described the site as under construction and as the planned home of GPU cloud and sovereign cloud services, alongside AI server assembly and battery manufacturing.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"91c22675-230e-5b67-a4f1-96c461b4eb5b","s2":"46dd12fb-126f-577a-8243-ce05f713c3ad","s3":"0efd0f29-b8d7-5a51-9714-1ed7cb45140d","s4":"04c12ac4-c0e4-5912-9150-44d384663222","s5":"ea43b470-9454-5146-8ec7-71209859da21","s6":"a05d05b8-991f-5529-9c7b-10cf3a915972","s7":"8323be0d-a18f-5d51-b73c-6c86cb8a6a77"},"source_file":"datacenters/projects/softbank-sakai.json","source_record_id":"softbank-sakai","source_record_sha256":"03bed245e3fd6adfb416da230450efa6ff1009a2f6cdecf8a5e45419a5e1039d","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a2fc50cdfd93ac1ebb5425d3cee8f1a89a1f06616a43101e00d6b54978e3c043"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d9155165962c78be00da/#project-75596cc6-0434-596d-be35-53be39de9c0a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/75596cc6-0434-596d-be35-53be39de9c0a.json
755ec57c-df00-5ee2-a290-9997607440b4 | imported:semiconductor-atlas:bridge-chonburi-khlong-tamru | vcc-site-8345f1f9d37238aa593f | imported:semiconductor-atlas:bridge-chonburi-khlong-tamru | Bridge Data Centres Chonburi hyperscale campus | Thailand | TH | 13.3619 | 100.9792 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Bridge names Khlong Tamru subdistrict in Chonburi Province and W.Media adds Mueang District, without an address; the point is the district coordinate from the Mueang Chonburi district Wikipedia article, so it marks the district rather than the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | cdb912f3-7a04-528a-ae5e-b5fbd9f7823a | announced | 2025-10-21 | 357 | imported_documented_status | cdb912f3-7a04-528a-ae5e-b5fbd9f7823a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"fcb9c992-4412-5508-a577-35a92a3ec53b","notes":"Thai unit of Bain Capital-backed Bridge Data Centres.","party":"Bridge Data Centres (Thailand) Co., Ltd.","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-chonburi-khlong-tamru"},{"evidence_id":"cdb912f3-7a04-528a-ae5e-b5fbd9f7823a","notes":"Thai unit of Bain Capital-backed Bridge Data Centres.","party":"Bridge Data Centres (Thailand) Co., Ltd.","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-chonburi-khlong-tamru"},{"evidence_id":"dd438608-b0bd-5c20-887f-951793d603a1","notes":"Thai unit of Bain Capital-backed Bridge Data Centres.","party":"Bridge Data Centres (Thailand) Co., Ltd.","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-chonburi-khlong-tamru"},{"evidence_id":"fcb9c992-4412-5508-a577-35a92a3ec53b","notes":"Backer of the Bridge Data Centres platform.","party":"Bain Capital","relationship_scope":"unknown","role":"investor","source_record_id":"bridge-chonburi-khlong-tamru"},{"evidence_id":"cdb912f3-7a04-528a-ae5e-b5fbd9f7823a","notes":"Granted investment promotion approval for the project.","party":"Thailand Board of Investment","relationship_scope":"unknown","role":"government","source_record_id":"bridge-chonburi-khlong-tamru"},{"evidence_id":"dd438608-b0bd-5c20-887f-951793d603a1","notes":"Granted investment promotion approval for the project.","party":"Thailand Board of Investment","relationship_scope":"unknown","role":"government","source_record_id":"bridge-chonburi-khlong-tamru"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.bridgedatacentres.com/bridge-data-centres-becomes-eastwater-stecon-utilities-first-data-centre-client/ | https://www.bridgedatacentres.com/bridge-data-centres-becomes-eastwater-stecon-utilities-first-data-centre-client/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bridge Data Centres Chonburi hyperscale campus as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"bridge-chonburi-khlong-tamru"},"record":{"aliases":["BDC Chonburi campus"],"id":"bridge-chonburi-khlong-tamru","last_reviewed":"2026-10-09","location":{"admin1":"Chonburi","admin2":"Mueang Chonburi District","country":"TH","lat":13.3619,"locality":"Khlong Tamru","lon":100.9792,"note":"Bridge names Khlong Tamru subdistrict in Chonburi Province and W.Media adds Mueang District, without an address; the point is the district coordinate from the Mueang Chonburi district Wikipedia article, so it marks the district rather than the site.","precision":"admin2","source_ids":["s2","s3","s4"]},"metrics":[{"applies_to":"phase","as_of":"2025-10-16","basis":"planned","metric":"power_capacity","note":"Described as the power capacity of phase 1, without saying whether it is IT load.","phase_label":"Phase 1","power_scope":"unspecified","qualifier":"approximately","source_ids":["s2","s3"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2025-04-11","basis":"planned","metric":"power_capacity","note":"The April 2025 Thai-language release gives a maximum power capacity of up to 200 MW for the facilities without naming phases.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2025-04-11","basis":"announced","metric":"investment","note":"Investment over three years; the October 2025 sources call it about US$1.2 billion and tie it to the Khlong Tamru campus.","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"USD","value":1200000000},{"applies_to":"campus","as_of":"2025-10-16","basis":"reported","metric":"land_area","note":"About 100 rai.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"hectares","value":16}],"milestones":[{"date":"2025-04-11","event":"announced","kind":"actual","note":"Thai-language Bridge release announcing US$1.2 billion of investment in Chonburi, presented to the provincial governor; the page is dated 11 April 2025 while the release text carries a 15 April dateline.","source_ids":["s1"]},{"date":"2025-10-16","event":"other","kind":"actual","note":"Ten-year industrial water purchase agreement signed with Eastwater Stecon Utilities, with supply from May 2026; W.Media reports a cap of 3.3 million cubic metres a year. Bridge is the utility's first data center client.","source_ids":["s2","s3"]}],"name":"Bridge Data Centres Chonburi hyperscale campus","notes":"Status is kept at announced because no opened source reports a construction start or opening; the October 2025 sources call the campus upcoming, and water supply was scheduled from May 2026. Bridge's undated Thailand locations page lists facilities QHI01 and QHI02 at 193 MW of IT capacity in four buildings with a 115 kV intake, but it does not give their location, so those figures are not recorded for this campus. Wikipedia is cited only for the district coordinate.","parties":[{"name":"Bridge Data Centres (Thailand) Co., Ltd.","note":"Thai unit of Bain Capital-backed Bridge Data Centres.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Bain Capital","note":"Backer of the Bridge Data Centres platform.","role":"investor","source_ids":["s1"]},{"name":"Thailand Board of Investment","note":"Granted investment promotion approval for the project.","role":"government","source_ids":["s2","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260306212457/https://www.bridgedatacentres.com/bridge-data-centres-%E0%B8%A5%E0%B8%87%E0%B8%97%E0%B8%B8%E0%B8%99-1-2-%E0%B8%9E%E0%B8%B1%E0%B8%99%E0%B8%A5%E0%B9%89%E0%B8%B2%E0%B8%99%E0%B8%94%E0%B8%AD%E0%B8%A5%E0%B8%A5%E0%B8%B2%E0%B8%A3%E0%B9%8C/","id":"s1","published":"2025-04-11","publisher":"Bridge Data Centres","title":"Bridge Data Centres to invest US$1.2 billion in Chonburi (Thai-language release)","type":"company","url":"https://www.bridgedatacentres.com/bridge-data-centres-%e0%b8%a5%e0%b8%87%e0%b8%97%e0%b8%b8%e0%b8%99-1-2-%e0%b8%9e%e0%b8%b1%e0%b8%99%e0%b8%a5%e0%b9%89%e0%b8%b2%e0%b8%99%e0%b8%94%e0%b8%ad%e0%b8%a5%e0%b8%a5%e0%b8%b2%e0%b8%a3%e0%b9%8c/"},{"accessed":"2026-10-09","id":"s2","published":"2025-10-16","publisher":"Bridge Data Centres","title":"Bridge Data Centres Becomes Eastwater-Stecon Utilities First Data Centre Client","type":"company","url":"https://www.bridgedatacentres.com/bridge-data-centres-becomes-eastwater-stecon-utilities-first-data-centre-client/"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-21","publisher":"W.Media","title":"Bridge Data Centres inks water deal for its data center in Thailand","type":"trade_press","url":"https://w.media/bridge-data-centres-inks-water-deal-for-its-data-center-in-thailand/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Mueang Chonburi district","type":"other","url":"https://en.wikipedia.org/wiki/Mueang_Chonburi_district"}],"status":"announced","status_as_of":"2025-10-21","status_source_ids":["s2","s3"],"summary":"Bridge Data Centres is developing a hyperscale campus on about 100 rai (16 hectares) in Khlong Tamru subdistrict, Mueang Chonburi District, Chonburi Province, Thailand. Bridge announced the project in April 2025 with about US$1.2 billion of investment over three years and up to 200 MW of power; by October 2025 Bridge and trade press described a first phase of about 200 MW and said the project had Board of Investment promotion. In October 2025 Bridge signed a 10-year industrial water supply deal with Eastwater Stecon Utilities, with supply from May 2026. No construction start or opening has been reported in the sources.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"fcb9c992-4412-5508-a577-35a92a3ec53b","s2":"cdb912f3-7a04-528a-ae5e-b5fbd9f7823a","s3":"dd438608-b0bd-5c20-887f-951793d603a1","s4":"edf12e25-e9ea-5d9c-b6d4-8c3e0b151275"},"source_file":"datacenters/projects/bridge-chonburi-khlong-tamru.json","source_record_id":"bridge-chonburi-khlong-tamru","source_record_sha256":"2ecd02fb68c05567bb7c89c5fe44933cf9ee43f63ea23d139e2b021a1dc49aac","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"992562ae9e719643e27163f3519ce78a60d35967399c53797c2e8ec14572b9a8"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8345f1f9d37238aa593f/#project-755ec57c-df00-5ee2-a290-9997607440b4 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/755ec57c-df00-5ee2-a290-9997607440b4.json
762397cd-ffc7-55c2-936e-af38cb8d4d0c | curated:monarch-compute-campus-point-pleasant-west-virginia:current-site-preparation | vcc-site-fe662eaf021a8dc4f203 | curated:monarch-compute-campus-point-pleasant-west-virginia | Monarch Point Pleasant Current Site Preparation | United States | US | 38.9169 | -82.1111 | Point | campus | exact_official_registration_geometry | WVDEP_WVR113311_native3857_to_source4326_independently_checked | official_constituent_campus_reference_point | official_source | campus_locator | Exact official Power Generation Pad South registration point, associated by explicit integrated-campus identity plus analyst reconciliation. Not a data-center hall, entrance, construction footprint, campus centroid, surveyed location or1100/2250-acre boundary. |  | No source numerical positional accuracy or point-placement method. | 561599d5-1050-50f3-842f-9112db1fca3f | under_construction | 2026-07-14 | 91 | authoritative_physical_status_update | 8b81f62b-dfaa-57e8-9307-74e7f643ca98 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://dep.wv.gov/news/Pages/WVDEP-Issues-Enforcement-Order-Following-Stormwater-Violations-at-Monarch-Cloud-Campus-Construction-Site.aspx | https://tagis.dep.wv.gov/arcgis/rest/services/WVDEP_enterprise/water_resources/MapServer/2/query?f=json&where=permit_id+%3D+%27WVR113311%27&outFields=*&returnGeometry=true&outSR=4326 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fe662eaf021a8dc4f203/#project-762397cd-ffc7-55c2-936e-af38cb8d4d0c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/762397cd-ffc7-55c2-936e-af38cb8d4d0c.json
77b8badc-29e2-55ce-b570-5d4387e30505 | imported:semiconductor-atlas:atnorth-solleftea-swe04 | vcc-site-424c62f417d6e6ef2c93 | imported:semiconductor-atlas:atnorth-solleftea-swe04 | atNorth SWE04 Sollefteå mega site | Sweden | SE | 63.1785 | 17.0671 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Site is the Hamre property (Hamre 4:87 after subdivision) in Hamre Industrial Park, Långsele; the Långsele village centroid from Nominatim is used because the parcel was not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 5633b2ba-7c68-53a7-aa22-b84d9bb65d02 | announced | 2026-06-16 | 119 | imported_documented_status | 5633b2ba-7c68-53a7-aa22-b84d9bb65d02 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"5633b2ba-7c68-53a7-aa22-b84d9bb65d02","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-solleftea-swe04"},{"evidence_id":"a7c9573a-a38a-5ad0-950b-0dbdf9a61f7d","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-solleftea-swe04"},{"evidence_id":"d0485433-9ca5-56d7-b0f9-fc61e7812867","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-solleftea-swe04"},{"evidence_id":"d0485433-9ca5-56d7-b0f9-fc61e7812867","notes":"The consultation document lists atNorth AB as owner of the land within the site.","party":"atNorth AB","relationship_scope":"unknown","role":"owner","source_record_id":"atnorth-solleftea-swe04"},{"evidence_id":"d0485433-9ca5-56d7-b0f9-fc61e7812867","notes":"atNorth states it will sign a grid connection agreement with E.ON.","party":"E.ON","relationship_scope":"unknown","role":"utility","source_record_id":"atnorth-solleftea-swe04"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | atNorth AB |  |  |  |  | https://www.atnorth.com/news/new-300mw-mega-site-in-solleftea-sweden/ | https://www.atnorth.com/news/new-300mw-mega-site-in-solleftea-sweden/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve atNorth SWE04 Sollefteå mega site as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"atnorth-solleftea-swe04"},"record":{"aliases":["SWE04","Sollefteå mega site","atNorth Långsele"],"id":"atnorth-solleftea-swe04","last_reviewed":"2026-10-09","location":{"admin1":"Västernorrland County","admin2":"Sollefteå Municipality","country":"SE","lat":63.1785,"locality":"Långsele","lon":17.0671,"note":"Site is the Hamre property (Hamre 4:87 after subdivision) in Hamre Industrial Park, Långsele; the Långsele village centroid from Nominatim is used because the parcel was not geocoded.","precision":"locality","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-02-23","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"power_capacity","note":"The FAQ on atNorth's site page cites a 200 MW path to power, conflicting with the 300 MW headline on the same page.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-02-23","basis":"reported","metric":"land_area","note":"The site page FAQ separately calls the campus 4 hectares, which conflicts with its own 50-hectare headline.","qualifier":"exact","source_ids":["s1","s2"],"unit":"hectares","value":50},{"applies_to":"campus","as_of":"2026-06","basis":"reported","metric":"land_area","note":"The consultation document gives the property area as about 160,000 square metres, smaller than the 50 hectares in atNorth's announcement.","qualifier":"approximately","source_ids":["s3"],"unit":"hectares","value":16},{"applies_to":"campus","as_of":"2026-06","basis":"planned","metric":"buildings","note":"Three main buildings of roughly 160 by 130 metres, up to 26 metres high.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":3}],"milestones":[{"date":"2026-02-23","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2026-06","event":"other","kind":"actual","note":"Consultation document published ahead of an environmental permit application to the Land and Environment Court, with Västernorrland County Administrative Board as supervisory authority.","source_ids":["s3"]},{"date":"2028-H1","event":"first_operational","kind":"planned","source_ids":["s1"]}],"name":"atNorth SWE04 Sollefteå mega site","parties":[{"name":"atNorth","role":"developer","source_ids":["s1","s2","s3"]},{"name":"atNorth AB","note":"The consultation document lists atNorth AB as owner of the land within the site.","role":"owner","source_ids":["s3"]},{"name":"E.ON","note":"atNorth states it will sign a grid connection agreement with E.ON.","role":"utility","source_ids":["s3"]}],"power_sources":[{"description":"Grid connection agreement to be signed with E.ON; atNorth cites renewable energy access at the park.","source_ids":["s1","s3"],"type":"grid"},{"description":"145 backup generators running on HVO, biodiesel or similar fuel, with total installed combustion input of about 1,200 MW and fuel for up to 24 hours.","source_ids":["s3"],"type":"diesel_backup"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261005091906/https://www.atnorth.com/news/new-300mw-mega-site-in-solleftea-sweden/","id":"s1","published":"2026-02-23","publisher":"atNorth","title":"New 300MW mega site in Sollefteå, Sweden","type":"company","url":"https://www.atnorth.com/news/new-300mw-mega-site-in-solleftea-sweden/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260915182340/https://www.atnorth.com/nordic-data-centers/sweden-data-centers/solleftea-swe04/","id":"s2","published":null,"publisher":"atNorth","title":"Sollefteå mega site (SWE04)","type":"company","url":"https://www.atnorth.com/nordic-data-centers/sweden-data-centers/solleftea-swe04/"},{"accessed":"2026-10-09","id":"s3","published":"2026-06-16","publisher":"atNorth AB (prepared by COWI)","title":"Samrådsunderlag för atNorths tillståndsansökan för datacenter i Långsele, Sollefteå kommun","type":"regulatory_filing","url":"https://www.atnorth.com/wp-content/uploads/2026/06/SWE04-Samradsunderlag-260616.pdf"}],"status":"announced","status_as_of":"2026-06-16","status_source_ids":["s1","s3"],"summary":"atNorth announced in February 2026 a 300 MW campus, SWE04, at Hamre Industrial Park in Långsele, about 7 km west of Sollefteå in northern Sweden, on a zoned plot it describes as 50 hectares, with operation expected in the first half of 2028. In June 2026 it published a consultation document for an environmental permit application to the Land and Environment Court, describing three main buildings on a property of about 16 hectares, 145 backup generators running on HVO or similar fuel with about 1,200 MW of combustion input, and a planned grid connection agreement with E.ON. Investment has not been disclosed.","workloads":["colocation","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"5633b2ba-7c68-53a7-aa22-b84d9bb65d02","s2":"a7c9573a-a38a-5ad0-950b-0dbdf9a61f7d","s3":"d0485433-9ca5-56d7-b0f9-fc61e7812867"},"source_file":"datacenters/projects/atnorth-solleftea-swe04.json","source_record_id":"atnorth-solleftea-swe04","source_record_sha256":"d368aca4aaf58255a65962aea71d2ce7288b3d209402a55fc16bbf2c94bbbe2c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"34a817b565e9c05e94e96586d55fc27c3c37e1588ab116b74dbb5d49d816d843"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-424c62f417d6e6ef2c93/#project-77b8badc-29e2-55ce-b570-5d4387e30505 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/77b8badc-29e2-55ce-b570-5d4387e30505.json
77f10b6a-00c1-5bf7-974e-d4dc4467b35e | imported:semiconductor-atlas:vantage-jhb1-sedenak | vcc-site-d70371ee13abb96e26fb | imported:semiconductor-atlas:vantage-jhb1-sedenak | Vantage Data Centers Johor campus (JHB1), Sedenak Tech Park | Malaysia | MY | 1.7137 | 103.5248 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Sedenak Tech Park in Johor without an address. The point is the Sedenak coordinate from its Wikipedia article (which also gives Kulai District), so it marks the locality rather than the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 9a802eef-12cf-5e0b-a459-c17fab1ce0d9 | partially_operational | 2026-10-09 | 4 | imported_documented_status | 44818d76-06e5-5bfb-98a5-346ce564cd15 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9a802eef-12cf-5e0b-a459-c17fab1ce0d9","notes":"Original developer, which sold the campus to Vantage in 2025.","party":"Yondr Group","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-jhb1-sedenak"},{"evidence_id":"91d089f8-fb27-546c-a8f5-43e798f1e5bf","notes":"Original developer, which sold the campus to Vantage in 2025.","party":"Yondr Group","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-jhb1-sedenak"},{"evidence_id":"9a802eef-12cf-5e0b-a459-c17fab1ce0d9","notes":"Bought the campus from Yondr; the deal closed in November 2025.","party":"Vantage Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"vantage-jhb1-sedenak"},{"evidence_id":"91d089f8-fb27-546c-a8f5-43e798f1e5bf","notes":"Bought the campus from Yondr; the deal closed in November 2025.","party":"Vantage Data Centers","relationship_scope":"unknown","role":"owner","source_record_id":"vantage-jhb1-sedenak"},{"evidence_id":"44818d76-06e5-5bfb-98a5-346ce564cd15","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"operator","source_record_id":"vantage-jhb1-sedenak"},{"evidence_id":"44818d76-06e5-5bfb-98a5-346ce564cd15","notes":null,"party":"Tenaga Nasional Berhad (TNB)","relationship_scope":"unknown","role":"utility","source_record_id":"vantage-jhb1-sedenak"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Vantage Data Centers | Vantage Data Centers |  |  |  | https://vantage-dc.com/data-center-locations/apac/johor-malaysia | https://vantage-dc.com/news/vantage-data-centers-secures-1-6b-investment-in-apac-platform-from-gic-and-adia/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Vantage Data Centers Johor campus (JHB1), Sedenak Tech Park as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"vantage-jhb1-sedenak","source_relations":[{"reason":"Bridge MY06 and Vantage JHB1 are separately named campuses in Sedenak Tech Park; identical park/locality coordinates are not evidence of co-location.","relationship":"separate_named_developments","source_id":"bridge-my06-sedenak"}]},"record":{"aliases":["JHB1","Yondr Johor campus"],"id":"vantage-jhb1-sedenak","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Kulai District","country":"MY","lat":1.713667,"locality":"Sedenak (Sedenak Tech Park)","lon":103.524778,"note":"Sources name Sedenak Tech Park in Johor without an address. The point is the Sedenak coordinate from its Wikipedia article (which also gives Kulai District), so it marks the locality rather than the parcel.","precision":"locality","source_ids":["s1","s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-24","basis":"planned","metric":"power_capacity","note":"IT capacity across three data centers once fully developed; the campus page gives 300MW+ of critical IT load.","power_scope":"it_load","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-11-24","basis":"reported","metric":"land_area","note":"The campus page gives 73 acres (30 hectares).","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"acres","value":73},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Given as more than 930,000 square feet (87,000 square metres).","qualifier":"more_than","source_ids":["s3"],"unit":"sq_ft","value":930000},{"applies_to":"campus","as_of":"2025-11-24","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"count","value":3}],"milestones":[{"date":"2025-09-10","event":"other","kind":"actual","note":"Vantage announced it would acquire the campus from Yondr Group.","source_ids":["s1"]},{"date":"2025-11-24","event":"other","kind":"actual","note":"Acquisition completed, with more than 30 Yondr staff joining Vantage.","source_ids":["s2"]}],"name":"Vantage Data Centers Johor campus (JHB1), Sedenak Tech Park","notes":"The partially operational status rests on Vantage's undated campus page (s3), read on 2026-10-09, which says the first facility is operational; no dated source gives when it opened or its capacity. The price paid for the campus was not disclosed. The US$1.6 billion was raised for Vantage's whole Asia-Pacific platform, led by an affiliate of GIC with a subsidiary of the Abu Dhabi Investment Authority, and only part of it went to this acquisition, so it is not a campus figure and those investors are not listed as campus parties. When Yondr began building the campus was not found in the sources opened. Sedenak coordinates and Kulai District come from Wikipedia (s4), used only for the location.","parties":[{"name":"Yondr Group","note":"Original developer, which sold the campus to Vantage in 2025.","role":"developer","source_ids":["s1","s2"]},{"name":"Vantage Data Centers","note":"Bought the campus from Yondr; the deal closed in November 2025.","role":"owner","source_ids":["s1","s2"]},{"name":"Vantage Data Centers","role":"operator","source_ids":["s3"]},{"name":"Tenaga Nasional Berhad (TNB)","role":"utility","source_ids":["s3"]}],"power_sources":[{"description":"Supplied by TNB through dedicated dual 275 kV feeds, with multiple 33 kV feeds per building.","source_ids":["s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-09-10","publisher":"Vantage Data Centers","title":"Vantage Data Centers Secures $1.6B Investment in APAC Platform from GIC and ADIA","type":"company","url":"https://vantage-dc.com/news/vantage-data-centers-secures-1-6b-investment-in-apac-platform-from-gic-and-adia/"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-24","publisher":"W.Media","title":"Vantage Data Centers completes purchase of Yondr's 300MW data center in Johor; closes US$1.6B investment in APAC","type":"trade_press","url":"https://w.media/vantage-data-centers-completes-purchase-of-yondrs-300mw-data-center-in-johor-closes-us1-6b-investment-in-apac/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260920080346/https://vantage-dc.com/data-center-locations/apac/johor-malaysia","id":"s3","published":null,"publisher":"Vantage Data Centers","title":"Johor, Malaysia Data Center Campus","type":"company","url":"https://vantage-dc.com/data-center-locations/apac/johor-malaysia"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251231122840/https://en.wikipedia.org/wiki/Sedenak","id":"s4","published":null,"publisher":"Wikipedia","title":"Sedenak","type":"other","url":"https://en.wikipedia.org/wiki/Sedenak"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s3"],"summary":"Hyperscale campus of nearly 73 acres in Sedenak Tech Park, Johor, inside the Johor-Singapore Special Economic Zone. Developed by Yondr Group with green-loan financing, it is planned for more than 300 MW of IT capacity across three data centers. Vantage Data Centers agreed in September 2025 to buy it, alongside a US$1.6 billion investment in its Asia-Pacific platform that partly funded the deal, and completed the purchase in November 2025. Vantage's campus page, viewed in October 2026, says the first facility is operational and the rest are under development.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9a802eef-12cf-5e0b-a459-c17fab1ce0d9","s2":"91d089f8-fb27-546c-a8f5-43e798f1e5bf","s3":"44818d76-06e5-5bfb-98a5-346ce564cd15","s4":"604050f1-a6dc-5b1b-a9fe-45bc645fd410"},"source_file":"datacenters/projects/vantage-jhb1-sedenak.json","source_record_id":"vantage-jhb1-sedenak","source_record_sha256":"317ab3dc86d1df60c1f75fd9d8df97fce104101b4c41421e248e33290fca881a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"bd46211bd673a78d63aa4e12630f7fc11b9ba465e0b30e2cf88b7e067b56a650"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d70371ee13abb96e26fb/#project-77f10b6a-00c1-5bf7-974e-d4dc4467b35e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/77f10b6a-00c1-5bf7-974e-d4dc4467b35e.json
79276528-66df-572a-8baf-0afce2bb01e4 | imported:semiconductor-atlas:cyrusone-bosque-county | vcc-site-119a6992bb6bb25cc011 | imported:semiconductor-atlas:cyrusone-bosque-county | CyrusOne Bosque County data center campus (Thad Hill) | United States | US | 31.9 | -97.63 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Coordinates are the Wikipedia point for Bosque County (s5). Sources place the campus next to the Thad Hill Energy Center in Bosque County but give no address; the site was not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 5d8d2d25-a113-5f7c-bc17-ebe03191d0ff | under_construction | 2025-11-03 | 344 | imported_documented_status | d85027b0-db8e-51ae-a723-7aabfa704009 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"5d8d2d25-a113-5f7c-bc17-ebe03191d0ff","notes":null,"party":"CyrusOne","relationship_scope":"unknown","role":"developer","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"d85027b0-db8e-51ae-a723-7aabfa704009","notes":null,"party":"CyrusOne","relationship_scope":"unknown","role":"developer","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"06de5624-4429-5d56-a4eb-d9e3f87ca265","notes":null,"party":"CyrusOne","relationship_scope":"unknown","role":"developer","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"5d8d2d25-a113-5f7c-bc17-ebe03191d0ff","notes":"Described as a data center developer and operator; backed by KKR and Global Infrastructure Partners.","party":"CyrusOne","relationship_scope":"unknown","role":"operator","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"d85027b0-db8e-51ae-a723-7aabfa704009","notes":"Described as a data center developer and operator; backed by KKR and Global Infrastructure Partners.","party":"CyrusOne","relationship_scope":"unknown","role":"operator","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"5d8d2d25-a113-5f7c-bc17-ebe03191d0ff","notes":"Supplies power under the powered land agreement at its Thad Hill Energy Center; by February 2026 Calpine was a business unit of Constellation.","party":"Calpine","relationship_scope":"unknown","role":"power_supplier","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"d85027b0-db8e-51ae-a723-7aabfa704009","notes":"Supplies power under the powered land agreement at its Thad Hill Energy Center; by February 2026 Calpine was a business unit of Constellation.","party":"Calpine","relationship_scope":"unknown","role":"power_supplier","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"06de5624-4429-5d56-a4eb-d9e3f87ca265","notes":"Supplies power under the powered land agreement at its Thad Hill Energy Center; by February 2026 Calpine was a business unit of Constellation.","party":"Calpine","relationship_scope":"unknown","role":"power_supplier","source_record_id":"cyrusone-bosque-county"},{"evidence_id":"ab3fd801-bb1c-5b3d-9f28-b4777e67cd8c","notes":"Supplies power under the powered land agreement at its Thad Hill Energy Center; by February 2026 Calpine was a business unit of Constellation.","party":"Calpine","relationship_scope":"unknown","role":"power_supplier","source_record_id":"cyrusone-bosque-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | CyrusOne |  |  |  | https://www.calpine.com/calpine-and-cyrusone-announce-phase-2-of-powered-land-agreement-to-support-hyperscale-data-center-at-thad-hill-energy-center-in-texas/ | https://www.publicpower.org/periodical/article/calpine-unveils-190-mw-agreement-serve-new-texas-data-center | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve CyrusOne Bosque County data center campus (Thad Hill) as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"cyrusone-bosque-county"},"record":{"aliases":["CyrusOne DFW10","Bosque County Data Center","Thad Hill Energy Center data center"],"id":"cyrusone-bosque-county","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Bosque County","country":"US","lat":31.9,"lon":-97.63,"note":"Coordinates are the Wikipedia point for Bosque County (s5). Sources place the campus next to the Thad Hill Energy Center in Bosque County but give no address; the site was not geocoded.","precision":"admin2","source_ids":["s1","s2","s3","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-03","basis":"contracted","metric":"power_capacity","note":"Combined power under the two Calpine agreements.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s4"],"unit":"MW","value":400},{"applies_to":"phase","as_of":"2025-07-31","basis":"contracted","metric":"power_capacity","phase_label":"Phase 1","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":190},{"applies_to":"phase","as_of":"2025-11-03","basis":"contracted","metric":"power_capacity","phase_label":"Phase 2","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":210},{"applies_to":"campus","as_of":"2025-07-31","basis":"reported","metric":"investment","note":"Investment reported in July 2025, when only the 190 MW first phase had been announced; no updated figure was found after the phase 2 agreement.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1200000000},{"applies_to":"phase","as_of":"2025-07-31","basis":"under_construction","metric":"floor_area","phase_label":"Phase 1","qualifier":"more_than","source_ids":["s1"],"unit":"sq_ft","value":190000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"Two buildings in phase 1 and three in phase 2, per CyrusOne's undated campus page.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":5}],"milestones":[{"date":"2025-07-30","event":"announced","kind":"actual","note":"Calpine announced the 190 MW agreement; the campus was already under construction.","source_ids":["s1"]},{"date":"2025-11-03","event":"expansion_announced","kind":"actual","note":"Phase 2 agreement for another 210 MW.","source_ids":["s2"]},{"date":"2026-Q4","event":"first_operational","kind":"planned","note":"Target given by Calpine in 2025.","source_ids":["s1","s2"]},{"date":"2027-Q3","event":"other","kind":"planned","note":"Later target for completing phase 1 on CyrusOne's campus page.","source_ids":["s3"]},{"date":"2027-Q4","event":"fully_operational","kind":"planned","source_ids":["s3"]}],"name":"CyrusOne Bosque County data center campus (Thad Hill)","notes":"Status conflict: Calpine said in July and November 2025 that the facility was under construction, but CyrusOne's undated campus page (it mentions events up to June 2026) labels it in development, refers to a county review process and describes some pre-construction steps as still ahead; its delivery dates are also later than Calpine's target. Status stays at under construction from Calpine's latest statement; no 2026 source confirms any building operating. The page says operating water comes from an on-site well permitted by the Middle Trinity Groundwater Conservation District, about 250,000 gallons per building a year. CyrusOne's Freestone Energy Center campus is a separate record.","parties":[{"name":"CyrusOne","role":"developer","source_ids":["s1","s2","s3"]},{"name":"CyrusOne","note":"Described as a data center developer and operator; backed by KKR and Global Infrastructure Partners.","role":"operator","source_ids":["s1","s2"]},{"name":"Calpine","note":"Supplies power under the powered land agreement at its Thad Hill Energy Center; by February 2026 Calpine was a business unit of Constellation.","role":"power_supplier","source_ids":["s1","s2","s3","s4"]}],"power_sources":[{"description":"Powered land agreement with Calpine at its Thad Hill Energy Center, covering power supply, grid connection and land; CyrusOne says it will pay for required transmission upgrades, and the campus is designed to respond during ERCOT grid emergencies.","source_ids":["s1","s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-07-31","publisher":"American Public Power Association","title":"Calpine Unveils 190-MW Agreement to Serve New Texas Data Center","type":"trade_press","url":"https://www.publicpower.org/periodical/article/calpine-unveils-190-mw-agreement-serve-new-texas-data-center"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007144613/https://www.calpine.com/calpine-and-cyrusone-announce-phase-2-of-powered-land-agreement-to-support-hyperscale-data-center-at-thad-hill-energy-center-in-texas/","id":"s2","published":"2025-11-03","publisher":"Calpine","title":"Calpine and CyrusOne Announce Phase 2 of Powered Land Agreement to Support Hyperscale Data Center at Thad Hill Energy Center in Texas","type":"company","url":"https://www.calpine.com/calpine-and-cyrusone-announce-phase-2-of-powered-land-agreement-to-support-hyperscale-data-center-at-thad-hill-energy-center-in-texas/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"CyrusOne","title":"Bosque County Data Center","type":"company","url":"https://www.cyrusone.com/data-centers/north-america/bosque-county-tx"},{"accessed":"2026-10-09","id":"s4","published":"2026-02-09","publisher":"CyrusOne","title":"Constellation and CyrusOne Announce Agreement to Support New Data Center Facility at Freestone Energy Center in Texas","type":"company","url":"https://www.cyrusone.com/resources/press-releases/constellation-and-cyrusone-announce-agreement-to-support-new-data-center-facility-at-freestone-energy-center-in-texas"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260724174458/https://en.wikipedia.org/wiki/Bosque_County,_Texas","id":"s5","published":null,"publisher":"Wikipedia","title":"Bosque County, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Bosque_County,_Texas"}],"status":"under_construction","status_as_of":"2025-11-03","status_source_ids":["s2"],"summary":"Hyperscale data center campus that CyrusOne is building next to Calpine's Thad Hill Energy Center in Bosque County, Texas, under a powered land agreement covering power, grid connection and land. Calpine announced a 190 MW first phase in July 2025, when the project was reported as a USD 1.2 billion investment, and added 210 MW in November 2025 for 400 MW in total. Calpine then said the facility was under construction for operation by the fourth quarter of 2026. CyrusOne's campus page now lists five buildings in two phases, with phase 1 due by the third quarter of 2027 and all phases by the fourth quarter of 2027.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"5d8d2d25-a113-5f7c-bc17-ebe03191d0ff","s2":"d85027b0-db8e-51ae-a723-7aabfa704009","s3":"06de5624-4429-5d56-a4eb-d9e3f87ca265","s4":"ab3fd801-bb1c-5b3d-9f28-b4777e67cd8c","s5":"06401c9f-9251-5d21-af37-495cc1759f3e"},"source_file":"datacenters/projects/cyrusone-bosque-county.json","source_record_id":"cyrusone-bosque-county","source_record_sha256":"083700c73d0cef1c843251f67ac8c9c1039c441b433603e8408a84f4d522909a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0ae3d7456b03642277e888689587f215de4fe669bbeeaab08bbb159f55dbc633"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-119a6992bb6bb25cc011/#project-79276528-66df-572a-8baf-0afce2bb01e4 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/79276528-66df-572a-8baf-0afce2bb01e4.json
7a05f519-bf3a-5423-bd7f-fcb8e1cd6c0f | imported:semiconductor-atlas:crusoe-tallgrass-cheyenne | vcc-site-f6a2889114e99d84b372 | imported:semiconductor-atlas:crusoe-tallgrass-cheyenne | Crusoe and Tallgrass AI data center campus near Cheyenne (Project Jade) | United States | US | 41.2737 | -104.7268 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Laramie County centroid from OpenStreetMap Nominatim. The announcement says only southeast Wyoming near Tallgrass's CO2 sequestration hub; analyst Cleanview places the project in Laramie County outside Cheyenne. No address or parcel was found. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 96e1e9b5-df0a-50d4-ab97-2b6ffff786ce | announced | 2025-07-24 | 446 | imported_documented_status | 96e1e9b5-df0a-50d4-ab97-2b6ffff786ce | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"96e1e9b5-df0a-50d4-ab97-2b6ffff786ce","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"crusoe-tallgrass-cheyenne"},{"evidence_id":"dd33ddad-a113-5bed-b239-cb08716cd825","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"crusoe-tallgrass-cheyenne"},{"evidence_id":"96e1e9b5-df0a-50d4-ab97-2b6ffff786ce","notes":"Contributes its Wyoming natural gas, water and CO2 assets; analyst Cleanview describes the Blackstone-backed company as developing the adjacent power generation facility.","party":"Tallgrass","relationship_scope":"unknown","role":"power_supplier","source_record_id":"crusoe-tallgrass-cheyenne"},{"evidence_id":"dd33ddad-a113-5bed-b239-cb08716cd825","notes":"Contributes its Wyoming natural gas, water and CO2 assets; analyst Cleanview describes the Blackstone-backed company as developing the adjacent power generation facility.","party":"Tallgrass","relationship_scope":"unknown","role":"power_supplier","source_record_id":"crusoe-tallgrass-cheyenne"},{"evidence_id":"dd33ddad-a113-5bed-b239-cb08716cd825","notes":"Analyst report, not a company disclosure: Cleanview says AEP appears to be involved, citing AEP's purchase of up to 900 MW of Bloom fuel cells and a 20-year offtake with an unnamed customer. No company has confirmed the link to this campus.","party":"American Electric Power","relationship_scope":"unknown","role":"power_supplier","source_record_id":"crusoe-tallgrass-cheyenne"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://tallgrass.com/newsroom/press-releases/Crusoe | https://tallgrass.com/newsroom/press-releases/Crusoe | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Crusoe and Tallgrass AI data center campus near Cheyenne (Project Jade) as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"crusoe-tallgrass-cheyenne"},"record":{"aliases":["Project Jade","Crusoe Wyoming campus"],"id":"crusoe-tallgrass-cheyenne","last_reviewed":"2026-10-09","location":{"admin1":"Wyoming","admin2":"Laramie County","country":"US","lat":41.2737,"lon":-104.7268,"note":"Laramie County centroid from OpenStreetMap Nominatim. The announcement says only southeast Wyoming near Tallgrass's CO2 sequestration hub; analyst Cleanview places the project in Laramie County outside Cheyenne. No address or parcel was found.","precision":"admin2","source_ids":["s1","s2"]},"metrics":[{"applies_to":"phase","as_of":"2025-07-24","basis":"planned","metric":"power_capacity","note":"The announcement does not say whether this is IT or facility power.","phase_label":"Initial campus","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":1800},{"applies_to":"campus","as_of":"2025-07-24","basis":"planned","metric":"power_capacity","note":"Design scale at full build-out.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":10000},{"applies_to":"phase","as_of":"2026-01","basis":"planned","metric":"power_capacity","note":"Analyst report, not a company disclosure: Cleanview says phase 1 on-site generation grew from 1.8 GW to 2.7 GW by January 2026, combining up to 900 MW of fuel cells with roughly 1.8 GW of gas turbines.","phase_label":"Phase 1","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":2700}],"milestones":[{"date":"2025-07-24","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-09-25","event":"other","kind":"actual","note":"BFC Power LLC applied to the Wyoming Department of Environmental Quality for a fuel cell facility of up to 900 MW, as reported by analyst Cleanview rather than disclosed by the companies.","source_ids":["s2"]},{"date":"2025-10","event":"other","kind":"actual","note":"Laramie County approved the Switchgrass Industrial Park, per analyst Cleanview's project timeline; the source does not say whether this was a zoning decision.","source_ids":["s2"]},{"date":"2026-01","event":"permit_approved","kind":"actual","note":"Laramie County commissioners unanimously approved the site plans on January 5-6, 2026, as reported by analyst Cleanview rather than disclosed by the companies.","source_ids":["s2"]},{"date":"2026-05-15","event":"other","kind":"actual","note":"Tallgrass and Mitsubishi Power announced turbines for a gas-fired Cheyenne Power Hub dedicated to a large data center in the Switchgrass Industrial Park. The release does not name Crusoe.","source_ids":["s3"]},{"date":"2026-Q1","event":"construction_started","kind":"planned","note":"Target reported by analyst Cleanview, not a company disclosure; no confirmation of a start was found.","source_ids":["s2"]},{"date":"2027-Q2","event":"first_operational","kind":"planned","note":"Target for energizing the first buildings as reported by analyst Cleanview, not a company disclosure.","source_ids":["s2"]}],"name":"Crusoe and Tallgrass AI data center campus near Cheyenne (Project Jade)","notes":"Linking the Cheyenne Power Hub to this campus rests on analyst Cleanview naming the hub as the project's power facility and listing the Switchgrass Industrial Park approval in its timeline; neither Tallgrass release opened here ties the two explicitly. Cleanview's figures and dates are analyst reporting, not company disclosures. No source confirming that data center construction has started was found, so status remains announced.","parties":[{"name":"Crusoe","role":"developer","source_ids":["s1","s2"]},{"name":"Tallgrass","note":"Contributes its Wyoming natural gas, water and CO2 assets; analyst Cleanview describes the Blackstone-backed company as developing the adjacent power generation facility.","role":"power_supplier","source_ids":["s1","s2"]},{"name":"American Electric Power","note":"Analyst report, not a company disclosure: Cleanview says AEP appears to be involved, citing AEP's purchase of up to 900 MW of Bloom fuel cells and a 20-year offtake with an unnamed customer. No company has confirmed the link to this campus.","role":"power_supplier","source_ids":["s2"]}],"power_sources":[{"description":"On-site gas generation drawing on Tallgrass's Wyoming natural gas assets, with roughly 1.8 GW of turbines reported by analyst Cleanview. Tallgrass separately announced a Cheyenne Power Hub (about 1,150 MW in phase 1, over $7 billion) for an unnamed data center in the same industrial park.","source_ids":["s1","s2","s3"],"type":"natural_gas_onsite"},{"description":"Bloom Energy solid oxide fuel cells of up to 900 MW, per a state air quality application summarized by analyst Cleanview rather than a company disclosure.","source_ids":["s2"],"type":"fuel_cell"},{"description":"Future regional renewable projects are expected to supplement gas, and the site's proximity to Tallgrass's CO2 sequestration hub is meant to allow carbon capture.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-07-24","publisher":"Tallgrass","title":"Crusoe and Tallgrass Announce AI Data Center in Wyoming","type":"company","url":"https://tallgrass.com/newsroom/press-releases/Crusoe"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Cleanview","title":"Behind-the-meter data centers: Project Jade","type":"analyst","url":"https://cleanview.co/reports/behind-the-meter-data-centers/full-report/project-jade"},{"accessed":"2026-10-09","id":"s3","published":"2026-05-15","publisher":"Tallgrass","title":"Tallgrass and Mitsubishi Power Americas Announce Turbine Allocation for Cheyenne Power Hub","type":"company","url":"https://tallgrass.com/newsroom/press-releases/tallgrass-and-mitsubishi-power-americas-announce-turbine-allocation-for-cheyenne-power-hub-051526"}],"status":"announced","status_as_of":"2025-07-24","status_source_ids":["s1","s2"],"summary":"Crusoe and Tallgrass announced in July 2025 an AI data center campus in southeast Wyoming, starting at 1.8 GW and designed to scale to 10 GW, powered mainly by natural gas from Tallgrass's Wyoming assets and sited near Tallgrass's CO2 sequestration hub. Analyst Cleanview identifies it as Project Jade in Laramie County outside Cheyenne and reports a 900 MW fuel cell air permit application, county approval of the Switchgrass Industrial Park, unanimous site plan approval in January 2026, and phase 1 on-site generation since raised to 2.7 GW. Cleanview gives targets of early 2026 for construction and Q2 2027 for first energization. No tenant has been named.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"96e1e9b5-df0a-50d4-ab97-2b6ffff786ce","s2":"dd33ddad-a113-5bed-b239-cb08716cd825","s3":"413baf76-7037-5689-baad-1b5c468bca41"},"source_file":"datacenters/projects/crusoe-tallgrass-cheyenne.json","source_record_id":"crusoe-tallgrass-cheyenne","source_record_sha256":"c455bb46fb9dbfadd5d67f54fbd5e52e6ba4e3c372c8b6789feba6f11b165eac","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b391bcd30fc2637b774d52c8bc51e3aad0fb4f9ff5c96910c1e96e9e8c36ac10"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f6a2889114e99d84b372/#project-7a05f519-bf3a-5423-bd7f-fcb8e1cd6c0f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7a05f519-bf3a-5423-bd7f-fcb8e1cd6c0f.json
7a5658df-f9c8-55e3-8623-b1a0fa40ce1d | imported:semiconductor-atlas:terawulf-muskie | vcc-site-133b0abe4851d7ed6df5 | imported:semiconductor-atlas:terawulf-muskie | TeraWulf Muskie Data Campus | United States | US | 38.36 | -82.69 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Local media place the site in EastPark near Ashland and Interstate 64, spanning the Boyd and Greenup county line; TeraWulf's Q2 2026 release describes it as Grayson, Eastern Kentucky. Coordinates are the Boyd County point from its Wikipedia article, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f8fe5488-ecbb-5edb-9c8e-aa35059c9c26 | announced | 2026-10-05 | 8 | imported_documented_status | 5adf16c1-6d68-50e1-ad23-f3e9da93b37d | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f8fe5488-ecbb-5edb-9c8e-aa35059c9c26","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-muskie"},{"evidence_id":"cc0e63e2-9331-5484-919a-a18dd6bfc722","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-muskie"},{"evidence_id":"5adf16c1-6d68-50e1-ad23-f3e9da93b37d","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-muskie"},{"evidence_id":"f8fe5488-ecbb-5edb-9c8e-aa35059c9c26","notes":"Acquired the campus in May 2026; owns or controls about 285 acres.","party":"TeraWulf","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-muskie"},{"evidence_id":"5adf16c1-6d68-50e1-ad23-f3e9da93b37d","notes":"Acquired the campus in May 2026; owns or controls about 285 acres.","party":"TeraWulf","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-muskie"},{"evidence_id":"f8fe5488-ecbb-5edb-9c8e-aa35059c9c26","notes":"AEP subsidiary; signed transmission and electric service agreements and is building the serving substation.","party":"Kentucky Power","relationship_scope":"unknown","role":"utility","source_record_id":"terawulf-muskie"},{"evidence_id":"5adf16c1-6d68-50e1-ad23-f3e9da93b37d","notes":"AEP subsidiary; signed transmission and electric service agreements and is building the serving substation.","party":"Kentucky Power","relationship_scope":"unknown","role":"utility","source_record_id":"terawulf-muskie"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | TeraWulf |  |  |  |  | https://investors.terawulf.com/news-events/press-releases/detail/146/terawulf-expands-contracted-power-capacity-at-its-muskie-data-campus-to-1-gw | https://investors.terawulf.com/news-events/press-releases/detail/141/terawulf-expands-infrastructure-platform-with-acquisition-of-1-gw-eastern-kentucky-hpc-campus | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve TeraWulf Muskie Data Campus as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"terawulf-muskie"},"record":{"aliases":["Muskie Data Campus"],"id":"terawulf-muskie","last_reviewed":"2026-10-09","location":{"admin1":"Kentucky","admin2":"Boyd County","country":"US","lat":38.36,"lon":-82.69,"note":"Local media place the site in EastPark near Ashland and Interstate 64, spanning the Boyd and Greenup county line; TeraWulf's Q2 2026 release describes it as Grayson, Eastern Kentucky. Coordinates are the Boyd County point from its Wikipedia article, not the site.","precision":"admin2","source_ids":["s1","s4","s5","s6","s7"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-05","basis":"contracted","metric":"power_capacity","note":"Contracted electric service with Kentucky Power. The October 2026 release says an amended agreement raised it from 500 MW to 1 GW, with the second 500 MW still needing Kentucky Public Service Commission approval; the August 2026 release already described agreements providing for up to 1 GW.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Initial phase, targeted to begin ramping in the second half of 2028.","phase_label":"Phase 1","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Long-term potential TeraWulf is evaluating, subject to further utility planning and agreements; not a commitment.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s3","s6"],"unit":"MW","value":2000},{"applies_to":"campus","as_of":"2026-05-26","basis":"acquired","metric":"land_area","note":"Owned or controlled within the roughly 1,000-acre EastPark Industrial Park, with optional adjacent land for expansion; local reports describe nearly 300 acres.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":285},{"applies_to":"campus","as_of":"2026-08-05","basis":"acquired","metric":"land_area","note":"Size given in TeraWulf's Q2 2026 release; the May 2026 release gave about 285 acres.","qualifier":"approximately","source_ids":["s2"],"unit":"acres","value":308}],"milestones":[{"date":"2026-05-26","event":"site_acquired","kind":"actual","note":"TeraWulf announced the acquisition from Industrial Equity Partners together with signed transmission and energy service agreements; the site was already zoned and permitting was under way.","source_ids":["s1","s2"]},{"date":"2026-10-05","event":"expansion_announced","kind":"actual","note":"Contracted power raised from 500 MW to 1 GW and the second phase moved up from 2030 to 2029.","source_ids":["s3"]},{"date":"2028-H2","event":"first_operational","kind":"planned","note":"First 500 MW to start ramping; the Q2 2026 release gives initial service in Q4 2028.","source_ids":["s1","s2","s3"]},{"date":"2029","event":"other","kind":"planned","note":"Target for the second 500 MW, subject to Kentucky PSC approval and Kentucky Power's construction schedule.","source_ids":["s3"]}],"name":"TeraWulf Muskie Data Campus","notes":"The campus straddles Boyd and Greenup counties, so admin2 records Boyd County only as the reference point used for coordinates. Boyd County's judge-executive told a June 2026 town hall that the site would use a closed-loop water system and that the company would pay for on-site power upgrades.","parties":[{"name":"TeraWulf","role":"developer","source_ids":["s1","s2","s3"]},{"name":"TeraWulf","note":"Acquired the campus in May 2026; owns or controls about 285 acres.","role":"owner","source_ids":["s1","s3"]},{"name":"Kentucky Power","note":"AEP subsidiary; signed transmission and electric service agreements and is building the serving substation.","role":"utility","source_ids":["s1","s3"]}],"power_sources":[{"description":"Kentucky Power is building a 765/345 kV substation tied to the existing 765 kV transmission network to serve the campus under large-load tariff agreements.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006181909/https://investors.terawulf.com/news-events/press-releases/detail/141/terawulf-expands-infrastructure-platform-with-acquisition-of-1-gw-eastern-kentucky-hpc-campus","id":"s1","published":"2026-05-26","publisher":"TeraWulf","title":"TeraWulf expands infrastructure platform with acquisition of 1+ GW Eastern Kentucky HPC campus","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/141/terawulf-expands-infrastructure-platform-with-acquisition-of-1-gw-eastern-kentucky-hpc-campus"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004051013/https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results","id":"s2","published":"2026-08-05","publisher":"TeraWulf","title":"TeraWulf reports second quarter 2026 results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006181437/https://investors.terawulf.com/news-events/press-releases/detail/146/terawulf-expands-contracted-power-capacity-at-its-muskie-data-campus-to-1-gw","id":"s3","published":"2026-10-05","publisher":"TeraWulf","title":"TeraWulf expands contracted power capacity at its Muskie Data Campus to 1 GW","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/146/terawulf-expands-contracted-power-capacity-at-its-muskie-data-campus-to-1-gw"},{"accessed":"2026-10-09","id":"s4","published":"2026-05-26","publisher":"WEKU","title":"New data center project announced in northeastern Kentucky","type":"news","url":"https://www.weku.org/text/the-commonwealth/2026-05-26/new-data-center-project-announced-in-northeastern-kentucky"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260618034955/https://www.wsaz.com/2026/06/02/neighbors-ask-questions-address-concerns-data-center-town-hall/","id":"s5","published":"2026-06-01","publisher":"WSAZ","title":"Neighbors ask questions and address concerns in data center town hall","type":"news","url":"https://www.wsaz.com/2026/06/02/neighbors-ask-questions-address-concerns-data-center-town-hall/"},{"accessed":"2026-10-09","id":"s6","published":"2026-08-06","publisher":"WEKU","title":"TeraWulf tells investors it could double the size of one of its Kentucky data center projects","type":"news","url":"https://www.weku.org/the-commonwealth/2026-08-06/terawulf-tells-investors-it-could-double-the-size-of-one-of-its-ky-data-center-projects"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260720100408/https://en.wikipedia.org/wiki/Boyd_County,_Kentucky","id":"s7","published":null,"publisher":"Wikipedia","title":"Boyd County, Kentucky","type":"other","url":"https://en.wikipedia.org/wiki/Boyd_County,_Kentucky"}],"status":"announced","status_as_of":"2026-10-05","status_source_ids":["s3"],"summary":"TeraWulf AI and HPC campus in the EastPark Industrial Park in northeast Kentucky, near Ashland on the Boyd and Greenup county line, bought from Industrial Equity Partners in May 2026 with about 285 acres owned or controlled (308 acres per its August release). Kentucky Power, an AEP company, is building a 765/345 kV substation to serve it. In October 2026 TeraWulf raised contracted power to 1 GW under an amended service agreement: the first 500 MW is due to start ramping in 2028 and the second 500 MW was pulled forward to 2029, subject to state regulatory approval. TeraWulf is studying up to 2 GW; no tenant has been named.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f8fe5488-ecbb-5edb-9c8e-aa35059c9c26","s2":"cc0e63e2-9331-5484-919a-a18dd6bfc722","s3":"5adf16c1-6d68-50e1-ad23-f3e9da93b37d","s4":"922614a8-1851-5a29-8018-045930f5964c","s5":"eea17dca-45dd-57e2-a69a-1eb14796bc20","s6":"ed8bcf8a-3c1b-589f-a71b-c8a34415f4be","s7":"50d1302f-f701-578c-a292-d5404f6deeeb"},"source_file":"datacenters/projects/terawulf-muskie.json","source_record_id":"terawulf-muskie","source_record_sha256":"14b836d3f75b4d2fa65551982c71fab2493bcc8fa1d3ec7d915c65d2659404b3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3aefa629da658522eb1e62d6f67bb8f586bf6818211dc51ba5f00635b9dfe4ed"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-133b0abe4851d7ed6df5/#project-7a5658df-f9c8-55e3-8623-b1a0fa40ce1d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7a5658df-f9c8-55e3-8623-b1a0fa40ce1d.json
7ac977cb-cbe2-5dfd-b058-f26707f86b6c | curated:merlin-edged-bilbao-arasur-campus:building-2-current-build | vcc-site-26279485fb1f7f11e894 | curated:merlin-edged-bilbao-arasur-campus | MERLIN Edged Bilbao-Arasur Building 2 Current Build | Spain | ES | 42.6977 | -2.9092 | Point | campus | operator_published_campus_location_link_literal_coordinate_query | operator_published_campus_location_link_literal_coordinate_query | operator_campus_reference_point | official_source | campus_locator | A campus locator may point to another constituent of a multi-building campus. It is not asserted to be the footprint or centroid of the selected new building. The named owner asset page provides the Supermanzana 6 campus address and LOCATION link. The captured 302 Location is a literal latitude/longitude search query. Coordinates are copied in reversed order for GeoJSON, without geocoding or selecting a map viewport. |  | Neither source states quantitative positional accuracy or survey provenance; coordinate digits are not an accuracy estimate. | 8c9736bc-10fe-5095-8011-14bd5162c919 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | a61e26a1-c065-5b53-9d12-44f564fd76c2 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ir.merlinproperties.com/wp-content/uploads/2026/07/RI-6M26-MERLIN-Properties_eng.pdf | https://maps.app.goo.gl/RfVFYuWfAxX9qTFp7 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-26279485fb1f7f11e894/#project-7ac977cb-cbe2-5dfd-b058-f26707f86b6c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7ac977cb-cbe2-5dfd-b058-f26707f86b6c.json
7b86e3a5-3492-5bb1-b47c-2010427939cd | curated:tecra-ome-shinmachi-9a:building | vcc-site-c1a8be222fca1d1646d2 | curated:tecra-ome-shinmachi-9a | OME Data Center04 Shinmachi9-A Building | Japan | JP | 35.7828 | 139.3177 | Point | campus | direct_geometry | developer_selected_map_feature_coordinates | developer_selected_parent_parcel_locator | compiled_reference | campus_locator | Developer-selected mapped parent-parcel address point; not the exact subdivided data-center lot or new-building footprint. |  | No positional accuracy stated. Locator identifies the parent property; the exact subdivided data-center parcel and building outline are not established numerically. | 75fa711b-93d1-5930-ba55-8a741000f1c7 | under_construction | 2026-07-15 | 90 | authoritative_physical_status_update | dc24a39a-56b3-5e0c-8016-7f5161d4eb6d | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed | unknown | not established by selected evidence | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"86f6df91-fbff-53b6-ae5c-af504067063f","party":"Unsung Fields","relationship_scope":"intended","role":"operator"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | Unsung Fields |  |  |  | https://tecrowd.jp/column/construction-report/construction-report-2026-07-fund-93-report-2/ | https://maps.google.com/?cid=3463469169659058608 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c1a8be222fca1d1646d2/#project-7b86e3a5-3492-5bb1-b47c-2010427939cd | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7b86e3a5-3492-5bb1-b47c-2010427939cd.json
7c43c342-562c-5d46-b793-39a4dd2a8cc0 | imported:semiconductor-atlas:qts-fayetteville-georgia | vcc-site-32a95caf9128d7dd56c8 | imported:semiconductor-atlas:qts-fayetteville-georgia | QTS Fayetteville campus | United States | US | 33.4478 | -84.4617 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Fayetteville, Georgia. The campus is at 1435 Highway 54 West, bounded by Highway 54 West, Tyrone Road and Flat Creek Trail; no cited source gives site coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 25e20e63-5e98-5bda-9722-480996fbd354 | partially_operational | 2025-11-21 | 326 | imported_documented_status | 9e80bdae-4016-59cb-a6ae-76145102a7a9 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e93427c0-a150-53fc-9fc1-51ccf0879ddc","notes":"Blackstone subsidiary. The Citizen says the land was bought by QTS Fayetteville 1, LLC, and the city's 2023 development agreement names National Acquisition Company, LLC as the other party.","party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-fayetteville-georgia"},{"evidence_id":"9f794367-bc44-5aa4-a28b-f0743691fab1","notes":"Blackstone subsidiary. The Citizen says the land was bought by QTS Fayetteville 1, LLC, and the city's 2023 development agreement names National Acquisition Company, LLC as the other party.","party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-fayetteville-georgia"},{"evidence_id":"9e80bdae-4016-59cb-a6ae-76145102a7a9","notes":"Blackstone subsidiary. The Citizen says the land was bought by QTS Fayetteville 1, LLC, and the city's 2023 development agreement names National Acquisition Company, LLC as the other party.","party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-fayetteville-georgia"},{"evidence_id":"87eb234a-26d3-5cac-a7ad-cdb4883b6efd","notes":"Blackstone subsidiary. The Citizen says the land was bought by QTS Fayetteville 1, LLC, and the city's 2023 development agreement names National Acquisition Company, LLC as the other party.","party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-fayetteville-georgia"},{"evidence_id":"7fe05f16-1ac3-5c3b-96af-15421a2fcacd","notes":"Sold the 615-acre site to QTS.","party":"Fayette County Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"qts-fayetteville-georgia"},{"evidence_id":"25e20e63-5e98-5bda-9722-480996fbd354","notes":"Its planning and zoning commission approved the conceptual site plan and its council adopted a development agreement for the campus in 2023.","party":"City of Fayetteville","relationship_scope":"unknown","role":"government","source_record_id":"qts-fayetteville-georgia"},{"evidence_id":"9e80bdae-4016-59cb-a6ae-76145102a7a9","notes":"Reported, not confirmed by the companies. The Citizen cites a 2024 Bloomberg report that Microsoft signed on as a tenant; the AJC infers from city records that Microsoft's Fayetteville facility is on this campus. QTS does not disclose customers and Microsoft did not give a location. Microsoft's facility is covered by the separate record microsoft-fairwater-atlanta.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"qts-fayetteville-georgia"},{"evidence_id":"87eb234a-26d3-5cac-a7ad-cdb4883b6efd","notes":"Reported, not confirmed by the companies. The Citizen cites a 2024 Bloomberg report that Microsoft signed on as a tenant; the AJC infers from city records that Microsoft's Fayetteville facility is on this campus. QTS does not disclose customers and Microsoft did not give a location. Microsoft's facility is covered by the separate record microsoft-fairwater-atlanta.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"qts-fayetteville-georgia"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | Microsoft |  | https://thecitizen.com/?p=234517 | https://thecitizen.com/?p=109827 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve QTS Fayetteville campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"qts-fayetteville-georgia","source_relations":[{"reason":"Both records cite the same AJC permitting investigation; tenant/campus linkage is reported but not company-confirmed. QTS remains the campus anchor; Fairwater record is held from independent site/project counts.","relationship":"reported_same_campus_tenant_scope","source_id":"microsoft-fairwater-atlanta"}]},"record":{"aliases":["Project Excalibur","QTS Data Center Fayetteville"],"id":"qts-fayetteville-georgia","last_reviewed":"2026-10-09","location":{"admin1":"Georgia","admin2":"Fayette County","country":"US","lat":33.4478,"locality":"Fayetteville","lon":-84.4617,"note":"Wikipedia coordinates for Fayetteville, Georgia. The campus is at 1435 Highway 54 West, bounded by Highway 54 West, Tyrone Road and Flat Creek Trail; no cited source gives site coordinates.","precision":"locality","source_ids":["s4","s3"]},"metrics":[{"applies_to":"campus","as_of":"2022-08-15","basis":"acquired","metric":"land_area","note":"The 2023 city development agreement describes the site as 612 acres.","qualifier":"approximately","source_ids":["s1","s3"],"unit":"acres","value":615},{"applies_to":"campus","as_of":"2022-09-19","basis":"reported","metric":"investment","note":"Bisnow's 2022 report that the project was expected to cost QTS more than USD 1 billion; the AJC later describes the investment only as billions of dollars. The separate land price was USD 153.8 million.","qualifier":"more_than","source_ids":["s2"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2025-11-21","basis":"planned","metric":"floor_area","note":"Includes supporting office space; Bisnow's 2022 breakdown was about 6.6 million square feet of data center space plus about 400,000 square feet of offices.","qualifier":"up_to","source_ids":["s3","s4","s6","s2"],"unit":"sq_ft","value":7000000},{"applies_to":"campus","as_of":"2022-09-21","basis":"planned","metric":"buildings","note":"Count from the 2022 Development of Regional Impact filing.","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":16},{"applies_to":"campus","as_of":"2025-11-15","basis":"planned","metric":"buildings","note":"The Citizen's 2025 account of nine planned data center buildings conflicts with the 16 in the 2022 filing and with its own reference to a Building 10.","qualifier":"exact","source_ids":["s5"],"unit":"count","value":9},{"applies_to":"campus","as_of":"2025-11-15","basis":"operational","metric":"buildings","qualifier":"exact","source_ids":["s5"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2025-11-15","basis":"under_construction","metric":"buildings","note":"Buildings 3, 5, 9 and 10 were described as under development.","qualifier":"exact","source_ids":["s5"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2025-11-15","basis":"planned","metric":"jobs_permanent","qualifier":"range","source_ids":["s5"],"unit":"count","value":800,"value_high":1000},{"applies_to":"campus","as_of":"2025-11-15","basis":"reported","metric":"jobs_construction","note":"Construction workers on site on a typical day in late 2025.","qualifier":"range","source_ids":["s5"],"unit":"count","value":4500,"value_high":5000}],"milestones":[{"date":"2022-08","event":"announced","kind":"actual","note":"Campus first unveiled as Project Excalibur.","source_ids":["s6"]},{"date":"2022","event":"site_acquired","kind":"actual","note":"Purchase of 615 acres from the Fayette County Development Authority for about USD 153.8 million, reported on 15 August 2022; the article gives no closing date.","source_ids":["s1"]},{"date":"2023-02-02","event":"other","kind":"actual","note":"Fayetteville Planning and Zoning Commission approved the conceptual site plan. The year is derived: the June 2023 article dates the approval to 2 February earlier that year.","source_ids":["s4"]},{"date":"2023-06-15","event":"other","kind":"actual","note":"Fayetteville City Council unanimously adopted the development agreement for the campus.","source_ids":["s4"]},{"date":"2025-05","event":"first_operational","kind":"actual","note":"City issued a certificate of occupancy for the first building, followed by a construction completion certificate on 25 September. The AJC, writing in November 2025, gives these dates without a year; they are read as 2025.","source_ids":["s6"]},{"date":"2027","event":"fully_operational","kind":"planned","note":"Completion target reported in November 2025.","source_ids":["s5"]},{"date":"2032","event":"fully_operational","kind":"planned","note":"Earlier build-out year in the 2022 regional impact filing.","source_ids":["s2","s3"]}],"name":"QTS Fayetteville campus","notes":"The AJC places Microsoft's Fayetteville Fairwater AI facility on this campus because city records show it as the only Fayetteville site permitted for data center occupancy; neither company has confirmed this. That facility is recorded separately as microsoft-fairwater-atlanta, and its statements are not repeated here.","parties":[{"name":"QTS Data Centers","note":"Blackstone subsidiary. The Citizen says the land was bought by QTS Fayetteville 1, LLC, and the city's 2023 development agreement names National Acquisition Company, LLC as the other party.","role":"developer","source_ids":["s2","s3","s5","s6"]},{"name":"Fayette County Development Authority","note":"Sold the 615-acre site to QTS.","role":"government","source_ids":["s1"]},{"name":"City of Fayetteville","note":"Its planning and zoning commission approved the conceptual site plan and its council adopted a development agreement for the campus in 2023.","role":"government","source_ids":["s4"]},{"name":"Microsoft","note":"Reported, not confirmed by the companies. The Citizen cites a 2024 Bloomberg report that Microsoft signed on as a tenant; the AJC infers from city records that Microsoft's Fayetteville facility is on this campus. QTS does not disclose customers and Microsoft did not give a location. Microsoft's facility is covered by the separate record microsoft-fairwater-atlanta.","role":"tenant","source_ids":["s5","s6"]}],"power_sources":[],"related_ids":["microsoft-fairwater-atlanta"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2022-08-15","publisher":"REBusinessOnline","title":"QTS Buys 615 Acres in Fayetteville, Georgia for 'World's Largest Multi-Tenant Data Center Campus'","type":"trade_press","url":"https://rebusinessonline.com/?p=324851"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251113090555/https://www.bisnow.com/atlanta/news/data-center/qts-project-excalibur-to-span-7m-sf-in-fayetteville-115472","id":"s2","published":"2022-09-19","publisher":"Bisnow","title":"QTS' 'Project Excalibur' To Span 7M SF In Fayetteville","type":"trade_press","url":"https://www.bisnow.com/atlanta/news/data-center/qts-project-excalibur-to-span-7m-sf-in-fayetteville-115472"},{"accessed":"2026-10-09","id":"s3","published":"2022-09-21","publisher":"The Citizen (Fayette County)","title":"State reviewing massive Fayetteville data center plans","type":"news","url":"https://thecitizen.com/?p=104756"},{"accessed":"2026-10-09","id":"s4","published":"2023-06-19","publisher":"The Citizen (Fayette County)","title":"Fayetteville approves development agreement for 612-acre QTS Data Center on Hwy. 54 West","type":"news","url":"https://thecitizen.com/?p=109827"},{"accessed":"2026-10-09","id":"s5","published":"2025-11-15","publisher":"The Citizen (Fayette County)","title":"QTS unveils new multi-use path as part of expanding community partnership in Fayetteville","type":"news","url":"https://thecitizen.com/?p=234517"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260829020236/https://www.ajc.com/business/2025/11/microsofts-newest-ai-superfactory-opens-at-sprawling-fayetteville-campus/","id":"s6","published":"2025-11-21","publisher":"The Atlanta Journal-Constitution","title":"Microsoft's newest AI 'superfactory' opens at sprawling Fayetteville campus","type":"news","url":"https://www.ajc.com/business/2025/11/microsofts-newest-ai-superfactory-opens-at-sprawling-fayetteville-campus/"}],"status":"partially_operational","status_as_of":"2025-11-21","status_source_ids":["s5","s6"],"summary":"QTS is building a multi-building data center campus on about 615 acres along Georgia Highway 54 West in Fayetteville, Georgia, about 25 miles south of Atlanta. QTS bought the site from the Fayette County Development Authority in 2022, when the campus was first unveiled as Project Excalibur, and Bisnow reported it was expected to cost QTS more than USD 1 billion. City filings describe about 7 million square feet of data center and office space. The first building received a certificate of occupancy in May 2025, and by November 2025 two buildings were operating with four more under development. Microsoft has been reported, but not confirmed, as a tenant.","workloads":["colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"7fe05f16-1ac3-5c3b-96af-15421a2fcacd","s2":"e93427c0-a150-53fc-9fc1-51ccf0879ddc","s3":"9f794367-bc44-5aa4-a28b-f0743691fab1","s4":"25e20e63-5e98-5bda-9722-480996fbd354","s5":"9e80bdae-4016-59cb-a6ae-76145102a7a9","s6":"87eb234a-26d3-5cac-a7ad-cdb4883b6efd"},"source_file":"datacenters/projects/qts-fayetteville-georgia.json","source_record_id":"qts-fayetteville-georgia","source_record_sha256":"ea566795916692c88310a339616e1dea6edc33a46d1339e5b0ef908029aae32f","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a95bb65756ade86f346463b6b7e1b7cffd3a93a4b94023dbc007e97c05631250"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-32a95caf9128d7dd56c8/#project-7c43c342-562c-5d46-b793-39a4dd2a8cc0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7c43c342-562c-5d46-b793-39a4dd2a8cc0.json
7c5eed16-f5f1-515a-b9ee-b7c30754fc10 | imported:semiconductor-atlas:microsoft-mount-pleasant-durand-avenue | vcc-site-c9f14a3df329db2670d8 | imported:semiconductor-atlas:microsoft-mount-pleasant-durand-avenue | Microsoft Mount Pleasant Durand Avenue datacenter campus | United States | US | 42.6965 | -87.947 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Approximate point where Durand Avenue meets Hewitt Memorial Drive, the two roads Microsoft names for Phase 3, from Nominatim lookups of each road in Mount Pleasant. The 791-acre parcel boundary is not published in the sources. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a5fe32e0-fc83-54bf-84bc-075b875d3693 | under_construction | 2026-07-01 | 104 | imported_documented_status | ebf3d086-030c-542f-8b25-790015be90db | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a5fe32e0-fc83-54bf-84bc-075b875d3693","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-mount-pleasant-durand-avenue"},{"evidence_id":"ef4b024d-a16d-56c7-84ce-29492edebcd6","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-mount-pleasant-durand-avenue"},{"evidence_id":"a5fe32e0-fc83-54bf-84bc-075b875d3693","notes":"A Microsoft spokesperson said the land was bought in 2024; a village spokesperson said it came from the village or private owners.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-mount-pleasant-durand-avenue"},{"evidence_id":"a1cfb15c-6f5f-5c5e-a086-8fb10335f311","notes":"A Microsoft spokesperson said the land was bought in 2024; a village spokesperson said it came from the village or private owners.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-mount-pleasant-durand-avenue"},{"evidence_id":"ef4b024d-a16d-56c7-84ce-29492edebcd6","notes":"A Microsoft spokesperson said the land was bought in 2024; a village spokesperson said it came from the village or private owners.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-mount-pleasant-durand-avenue"},{"evidence_id":"a5fe32e0-fc83-54bf-84bc-075b875d3693","notes":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","party":"Village of Mount Pleasant","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-mount-pleasant-durand-avenue"},{"evidence_id":"a1cfb15c-6f5f-5c5e-a086-8fb10335f311","notes":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","party":"Village of Mount Pleasant","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-mount-pleasant-durand-avenue"},{"evidence_id":"224ed1fd-1f35-59ea-a767-96481a580872","notes":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","party":"Village of Mount Pleasant","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-mount-pleasant-durand-avenue"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Microsoft |  |  |  |  | https://local.microsoft.com/blog/mount-pleasant-datacenter-project-update/ | https://www.wpr.org/news/microsoft-15-more-data-centers-mount-pleasant | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Mount Pleasant Durand Avenue datacenter campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-mount-pleasant-durand-avenue","source_relations":[{"reason":"County Road KR phases 1/2 and Durand/Hewitt Memorial Phase 3 occupy separately described development parcels.","relationship":"separate_campus_parcels","source_id":"microsoft-fairwater-mount-pleasant"},{"reason":"Distinct 791-acre nine-building Durand campus and 530-acre six-building International Drive campus.","relationship":"separate_campus_parcels","source_id":"microsoft-mount-pleasant-international-drive"}]},"record":{"aliases":["Mount Pleasant Phase 3 (Durand & Hewitt Memorial Drive)"],"id":"microsoft-mount-pleasant-durand-avenue","last_reviewed":"2026-10-09","location":{"admin1":"Wisconsin","admin2":"Racine County","country":"US","lat":42.6965,"locality":"Mount Pleasant","lon":-87.947,"note":"Approximate point where Durand Avenue meets Hewitt Memorial Drive, the two roads Microsoft names for Phase 3, from Nominatim lookups of each road in Mount Pleasant. The 791-acre parcel boundary is not published in the sources.","precision":"approximate_site","source_ids":["s1","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-20","basis":"reported","metric":"investment","note":"The municipality's estimated taxable value for the development, from village planning documents reported by WPR; not a company investment figure.","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":7970000000},{"applies_to":"campus","as_of":"2026-01-27","basis":"planned","metric":"buildings","note":"Datacenter buildings only; an office and other related buildings are additional.","qualifier":"exact","source_ids":["s1","s3","s4"],"unit":"count","value":9},{"applies_to":"campus","as_of":"2026-01-20","basis":"planned","metric":"floor_area","note":"Total development size from village planning documents reported by WPR; the office and related buildings are not broken out.","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":5200000},{"applies_to":"campus","as_of":"2026-01-21","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1","s2"],"unit":"acres","value":791}],"milestones":[{"date":"2024","event":"site_acquired","kind":"actual","note":"A Microsoft spokesperson, quoted by WPR and Spectrum News, gave 2024; Spectrum News itself said the land was bought the previous year (2025).","source_ids":["s1","s2","s3"]},{"date":"2026-01-20","event":"announced","kind":"actual","note":"Site plans became public ahead of the plan commission meeting; Microsoft called them preliminary.","source_ids":["s1","s3"]},{"date":"2026-01-26","event":"zoning_approved","kind":"actual","note":"Plan commission recommended approval on 2026-01-21 and the village board approved the site plan unanimously on 2026-01-26, conditional on a traffic study and compliance with water-use rules.","source_ids":["s2","s4"]},{"date":"2026-03","event":"construction_started","kind":"actual","note":"Microsoft's March 2026 update reports preliminary earthwork under way at Phase 3 (Durand and Hewitt Memorial Drive), starting mid-March. Epoch AI separately reports grading for a new 9-building design northwest of the first buildings by May 2026. No vertical construction timeline has been published.","source_ids":["s5","s6"]}],"name":"Microsoft Mount Pleasant Durand Avenue datacenter campus","notes":"Village documents treat this as an additional campus separate from the Fairwater Phase 1 and 2 site, while Microsoft labels Durand and Hewitt Memorial Drive as Phase 3 of its Mount Pleasant work and Epoch AI folds a 9-building plan into its Fairwater Wisconsin projection; the sources do not explicitly state that these describe the same nine buildings. Spectrum News reports that part of the expansion land was originally part of the Foxconn project. status_as_of uses the first day of the month of the latest entry on Microsoft's month-dated update page. No power figure has been published; Microsoft told WPR an energy estimate was not available.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s3"]},{"name":"Microsoft","note":"A Microsoft spokesperson said the land was bought in 2024; a village spokesperson said it came from the village or private owners.","role":"owner","source_ids":["s1","s2","s3"]},{"name":"Village of Mount Pleasant","note":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","role":"government","source_ids":["s1","s2","s4"]}],"power_sources":[],"related_ids":["microsoft-fairwater-mount-pleasant","microsoft-mount-pleasant-international-drive"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-20","publisher":"Wisconsin Public Radio","title":"Microsoft wants to build 15 more data centers in Mount Pleasant","type":"news","url":"https://www.wpr.org/news/microsoft-15-more-data-centers-mount-pleasant"},{"accessed":"2026-10-09","id":"s2","published":"2026-01-21","publisher":"Wisconsin Public Radio","title":"Mount Pleasant commission approves Microsoft's plans for data center expansion","type":"news","url":"https://www.wpr.org/news/mount-pleasant-approves-microsoft-data-center-expansion"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260205013908/https://spectrumnews1.com/wi/milwaukee/news/2026/01/21/microsoft-to-expand-data-center-in-mount-pleasant-","id":"s3","published":"2026-01-21","publisher":"Spectrum News 1","title":"Microsoft to expand data center in Mount Pleasant","type":"news","url":"https://spectrumnews1.com/wi/milwaukee/news/2026/01/21/microsoft-to-expand-data-center-in-mount-pleasant-"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260223142131/https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval","id":"s4","published":"2026-01-27","publisher":"Spectrum News 1","title":"Mount Pleasant village board approves Microsoft data center expansion","type":"news","url":"https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260911205220/https://local.microsoft.com/blog/mount-pleasant-datacenter-project-update/","id":"s5","published":"2026-07","publisher":"Microsoft Local","title":"Mount Pleasant datacenter project update","type":"company","url":"https://local.microsoft.com/blog/mount-pleasant-datacenter-project-update/"},{"accessed":"2026-10-09","id":"s6","published":"2026-10-05","publisher":"Epoch AI","title":"Microsoft Fairwater Wisconsin","type":"analyst","url":"https://epoch.ai/data/ai-data-centers/directory/microsoft-fairwater-wisconsin"}],"status":"under_construction","status_as_of":"2026-07-01","status_source_ids":["s5"],"summary":"Planned nine-building Microsoft datacenter campus near Durand Avenue in Mount Pleasant, Wisconsin, on a 791-acre parcel Microsoft says it bought in 2024. Village planning documents reported by WPR describe 5.2 million sq ft of development, including a 96,000 sq ft office and other related buildings, with an estimated taxable value of more than USD 7.97 billion. The plan commission recommended the site plan with conditions on traffic and water use, and the village board approved it unanimously in January 2026. Microsoft's construction page reports preliminary earthwork under way since March 2026 at a Phase 3 site at Durand Avenue and Hewitt Memorial Drive."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a5fe32e0-fc83-54bf-84bc-075b875d3693","s2":"a1cfb15c-6f5f-5c5e-a086-8fb10335f311","s3":"ef4b024d-a16d-56c7-84ce-29492edebcd6","s4":"224ed1fd-1f35-59ea-a767-96481a580872","s5":"ebf3d086-030c-542f-8b25-790015be90db","s6":"7a699d1b-3b42-512d-81ac-53ed04573210"},"source_file":"datacenters/projects/microsoft-mount-pleasant-durand-avenue.json","source_record_id":"microsoft-mount-pleasant-durand-avenue","source_record_sha256":"d8ced53f6564dffee42db2b1d9fcde39cfad69294d3e5cab7cc9b1a817f79650","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"6422e87f57229adc149c7a4308ef6b5c4fde411ea62bb970a4792f4fa2287863"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c9f14a3df329db2670d8/#project-7c5eed16-f5f1-515a-b9ee-b7c30754fc10 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7c5eed16-f5f1-515a-b9ee-b7c30754fc10.json
7c7b8437-ca56-55a0-aa36-54155f43760e | curated:atnorth-fin04-kouvola-campus:phase-1 | vcc-site-4c2cf1101b80a8a4c17e | curated:atnorth-fin04-kouvola-campus | atNorth FIN04 Phase 1 | Finland | FI | 60.7834 | 26.7644 | MultiPolygon | campus | official_coordinate_transform | nls_official_cadastral_multipolygon_as_fin04_shared_campus_locator | official_cadastral_property_as_shared_campus_locator | official_source | campus_locator | NLS property 286-423-20-1 transformed from EPSG:3067 using pyproj 3.7.2 / PROJ 9.5.1 after the Kouvola permit binds atNorth and Lossitie 26 to that property. Its three disconnected cadastral features are retained as one exact MultiPolygon only as a shared-campus locator, not a Phase 1, campus, building, current-work, or publication-target official boundary. |  | NLS supplies authoritative source geometry but no bounded numeric horizontal-accuracy value applicable to this transformed publication; transformed digits do not add accuracy. | 6fa1a931-3b5c-5259-9b15-853187c9ae2a | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | a49b85ce-f91a-56b8-af06-3b663336bdf8 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.15 global geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.yitgroup.com/en/news-repository/investor-news/yit-and-atnorth-agree-on-construction-of-a-data-center-in-kouvola--value-for-yit-approximately-eur-300-million | https://inspire-wfs.maanmittauslaitos.fi/inspire-wfs/cp/ows?service=WFS&version=2.0.0&request=GetFeature&typeNames=cp%3ACadastralParcel&outputFormat=application%2Fjson&CQL_FILTER=nationalCadastralReference%3D%2728642300200001%27 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4c2cf1101b80a8a4c17e/#project-7c7b8437-ca56-55a0-aa36-54155f43760e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7c7b8437-ca56-55a0-aa36-54155f43760e.json
7c9397d2-971c-5d1e-ad58-210d19777a37 | imported:semiconductor-atlas:google-fort-wayne-indiana | vcc-site-e2ec9daea00e4e3d9dc1 | imported:semiconductor-atlas:google-fort-wayne-indiana | Google Fort Wayne data center | United States | US | 41.018 | -85.058 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Approximate intersection of East Tillman Road and Adams Center Road, derived from OpenStreetMap geometry for the two roads named by the state announcement; the parcel itself is not mapped. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3ac3ad9e-8831-5419-8130-9e60d24342e6 | operational | 2026-10-09 | 4 | imported_documented_status | 1375d1b3-7de9-5b6a-8109-6c33626a675e | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3ac3ad9e-8831-5419-8130-9e60d24342e6","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-fort-wayne-indiana"},{"evidence_id":"1375d1b3-7de9-5b6a-8109-6c33626a675e","notes":null,"party":"Google","relationship_scope":"unknown","role":"operator","source_record_id":"google-fort-wayne-indiana"},{"evidence_id":"3ac3ad9e-8831-5419-8130-9e60d24342e6","notes":"Committed a 35-year data center sales tax exemption for a minimum of $800 million of eligible capital, with 5-year extensions per additional $800 million up to 50 years.","party":"Indiana Economic Development Corporation","relationship_scope":"unknown","role":"government","source_record_id":"google-fort-wayne-indiana"},{"evidence_id":"3ac3ad9e-8831-5419-8130-9e60d24342e6","notes":"Google announced a collaboration with the utility to bring new clean energy resources to the local grid.","party":"Indiana Michigan Power","relationship_scope":"unknown","role":"utility","source_record_id":"google-fort-wayne-indiana"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Google |  |  |  | https://datacenters.google/locations/indiana/ | https://iedc.in.gov/events/news/details/2024/04/26/gov.-holcomb-announces-google-is-building-a-2b-data-center-in-northeast-indiana | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Google Fort Wayne data center as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"google-fort-wayne-indiana"},"record":{"aliases":[],"id":"google-fort-wayne-indiana","last_reviewed":"2026-10-09","location":{"admin1":"Indiana","admin2":"Allen County","country":"US","lat":41.018,"locality":"Fort Wayne","lon":-85.058,"note":"Approximate intersection of East Tillman Road and Adams Center Road, derived from OpenStreetMap geometry for the two roads named by the state announcement; the parcel itself is not mapped.","precision":"approximate_site","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2024-04-26","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":2000000000},{"applies_to":"campus","as_of":"2024-04-26","basis":"planned","metric":"jobs_permanent","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":200}],"milestones":[{"date":"2024-04-26","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024-04-26","event":"construction_started","kind":"actual","note":"Groundbreaking held on the day of the announcement.","source_ids":["s1","s2"]}],"name":"Google Fort Wayne data center","notes":"Status comes from Google's undated Indiana locations page, which lists a 2026 milestone and calls Fort Wayne an operational data center; status_as_of is therefore the access date. The state announcement said the site would support Google's AI work and cloud business. No opening date or power capacity was found in an opened source.","parties":[{"name":"Google","role":"developer","source_ids":["s1"]},{"name":"Google","role":"operator","source_ids":["s2"]},{"name":"Indiana Economic Development Corporation","note":"Committed a 35-year data center sales tax exemption for a minimum of $800 million of eligible capital, with 5-year extensions per additional $800 million up to 50 years.","role":"government","source_ids":["s1"]},{"name":"Indiana Michigan Power","note":"Google announced a collaboration with the utility to bring new clean energy resources to the local grid.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Served from the local grid; Google announced a collaboration with Indiana Michigan Power to add new clean energy resources to it.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260920164906/https://iedc.in.gov/events/news/details/2024/04/26/gov.-holcomb-announces-google-is-building-a-2b-data-center-in-northeast-indiana","id":"s1","published":"2024-04-26","publisher":"Indiana Economic Development Corporation","title":"Gov. Holcomb announces Google is building a $2B Data Center in Northeast Indiana","type":"government","url":"https://iedc.in.gov/events/news/details/2024/04/26/gov.-holcomb-announces-google-is-building-a-2b-data-center-in-northeast-indiana"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260831105554/https://datacenters.google/locations/indiana/","id":"s2","published":null,"publisher":"Google","title":"Indiana - Google Data Center Location","type":"company","url":"https://datacenters.google/locations/indiana/"}],"status":"operational","status_as_of":"2026-10-09","status_source_ids":["s2"],"summary":"Google data center near East Tillman Road and Adams Center Road in Fort Wayne, Allen County, Indiana. Google and the governor announced the $2 billion project and broke ground on 26 April 2024, projecting up to 200 jobs. The state committed a performance-based 35-year data center sales tax exemption, tied to at least $800 million of eligible capital and extendable with further investment. Google announced a collaboration with Indiana Michigan Power to add new clean energy resources to the local grid. Google's Indiana page now describes the Fort Wayne site as operational; no capacity figure has been published.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3ac3ad9e-8831-5419-8130-9e60d24342e6","s2":"1375d1b3-7de9-5b6a-8109-6c33626a675e"},"source_file":"datacenters/projects/google-fort-wayne-indiana.json","source_record_id":"google-fort-wayne-indiana","source_record_sha256":"140e615990e16bd1d60c983ff139345118f93e72fd9ebd3a99658c8db663db69","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5e6ad02fb65f107b646fa311ed2098ca115ec58fb9a0cea0337e6a836a4c16a0"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e2ec9daea00e4e3d9dc1/#project-7c9397d2-971c-5d1e-ad58-210d19777a37 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7c9397d2-971c-5d1e-ad58-210d19777a37.json
7d6333d2-26e6-548c-979a-324c7113281b | imported:semiconductor-atlas:homer-city-redevelopment | vcc-site-f49882717c93278a3c62 | imported:semiconductor-atlas:homer-city-redevelopment | Homer City Energy Campus | United States | US | 40.5108 | -79.1936 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Coordinates of the former Homer City Generating Station from Wikipedia (s6), which places it in Center Township near the borough of Homer City; the campus is built on the former station site, which covers a large area, so the point is approximate. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 78e4189f-fca3-5ade-9969-696d30129b77 | under_construction | 2026-09-04 | 39 | imported_documented_status | 97df27dd-a5e1-5fe6-894a-95ac5c5609eb | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"66dee0cf-aaa0-5561-889d-7609ee252494","notes":null,"party":"Homer City Redevelopment","relationship_scope":"unknown","role":"developer","source_record_id":"homer-city-redevelopment"},{"evidence_id":"08c1fde3-35eb-5cf1-a141-822cfefed1f4","notes":null,"party":"Homer City Redevelopment","relationship_scope":"unknown","role":"developer","source_record_id":"homer-city-redevelopment"},{"evidence_id":"66dee0cf-aaa0-5561-889d-7609ee252494","notes":"Engineering, procurement and construction contractor.","party":"Kiewit Power Constructors Co.","relationship_scope":"unknown","role":"builder","source_record_id":"homer-city-redevelopment"},{"evidence_id":"41d3b525-b2df-5a76-99bf-155814c1264d","notes":"Engineering, procurement and construction contractor.","party":"Kiewit Power Constructors Co.","relationship_scope":"unknown","role":"builder","source_record_id":"homer-city-redevelopment"},{"evidence_id":"97df27dd-a5e1-5fe6-894a-95ac5c5609eb","notes":"Engineering, procurement and construction contractor.","party":"Kiewit Power Constructors Co.","relationship_scope":"unknown","role":"builder","source_record_id":"homer-city-redevelopment"},{"evidence_id":"66dee0cf-aaa0-5561-889d-7609ee252494","notes":"Supplier of the seven gas turbines.","party":"GE Vernova","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"homer-city-redevelopment"},{"evidence_id":"41d3b525-b2df-5a76-99bf-155814c1264d","notes":"Supplier of the seven gas turbines.","party":"GE Vernova","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"homer-city-redevelopment"},{"evidence_id":"41d3b525-b2df-5a76-99bf-155814c1264d","notes":"Named on the project FAQ as providing financing.","party":"Knighthead Capital Management","relationship_scope":"unknown","role":"investor","source_record_id":"homer-city-redevelopment"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.homercityredevelopment.com/post/homer-city-energy-campus-workforce-grows-to-more-than-1-800-workers-including-members-of-9-building | https://www.pasenategop.com/news/pittman-hails-new-wave-of-energy-advancement-in-pennsylvania/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Homer City Energy Campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"homer-city-redevelopment"},"record":{"aliases":["Homer City Redevelopment","Homer City Generation"],"id":"homer-city-redevelopment","last_reviewed":"2026-10-09","location":{"admin1":"Pennsylvania","admin2":"Indiana County","country":"US","lat":40.5108,"locality":"Center Township","lon":-79.1936,"note":"Coordinates of the former Homer City Generating Station from Wikipedia (s6), which places it in Center Township near the borough of Homer City; the campus is built on the former station site, which covers a large area, so the point is approximate.","precision":"approximate_site","source_ids":["s3","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2025-12-11","basis":"planned","metric":"power_capacity","note":"Gas-fired generation capacity intended to power the data centers on the campus, with surplus to the grid.","power_scope":"onsite_generation","qualifier":"up_to","source_ids":["s1","s4"],"unit":"MW","value":4400},{"applies_to":"campus","as_of":"2025-04-02","basis":"announced","metric":"investment","note":"Figure cited by the Pennsylvania Senate majority leader on the announcement date.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"Developer FAQ projects initial capital for power infrastructure and site readiness to exceed this amount, with data center development adding billions more. The page is undated and was accessed on this date.","qualifier":"more_than","source_ids":["s2"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2025-12-11","basis":"reported","metric":"land_area","qualifier":"more_than","source_ids":["s1","s4"],"unit":"acres","value":3200},{"applies_to":"campus","as_of":"2026-09-04","basis":"planned","metric":"jobs_construction","note":"Direct on-site construction jobs expected over about five years.","qualifier":"more_than","source_ids":["s1","s5"],"unit":"count","value":10000},{"applies_to":"campus","as_of":"2026-09-04","basis":"planned","metric":"jobs_permanent","note":"Total direct and indirect permanent positions once operating.","qualifier":"approximately","source_ids":["s1","s5"],"unit":"count","value":1000}],"milestones":[{"date":"2025-04-02","event":"announced","kind":"actual","source_ids":["s1","s3"]},{"date":"2025-11-18","event":"permit_approved","kind":"actual","note":"Air-quality permit issued by the Pennsylvania Department of Environmental Protection.","source_ids":["s4"]},{"date":"2026-09-04","event":"other","kind":"actual","note":"Developer reported more than 1,800 workers on site and site-readiness milestones completed.","source_ids":["s5"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Target for power production; turbine deliveries were expected to begin in 2026.","source_ids":["s2","s4"]}],"name":"Homer City Energy Campus","parties":[{"name":"Homer City Redevelopment","role":"developer","source_ids":["s1","s4"]},{"name":"Kiewit Power Constructors Co.","note":"Engineering, procurement and construction contractor.","role":"builder","source_ids":["s1","s2","s5"]},{"name":"GE Vernova","note":"Supplier of the seven gas turbines.","role":"hardware_supplier","source_ids":["s1","s2"]},{"name":"Knighthead Capital Management","note":"Named on the project FAQ as providing financing.","role":"investor","source_ids":["s2"]}],"power_sources":[{"description":"Seven GE Vernova 7HA.02 hydrogen-enabled gas turbines on site, burning Marcellus Shale gas; EQT is reported as the gas supplier.","source_ids":["s1","s2","s4"],"type":"natural_gas_onsite"},{"description":"The site keeps the former plant's connections to PJM and NYISO, and the campus is expected to supply some power to the local grid.","source_ids":["s2","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Homer City Redevelopment","title":"Project Overview","type":"company","url":"https://www.homercityredevelopment.com/project-overview"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261002183713/https://www.homercityredevelopment.com/faq","id":"s2","published":null,"publisher":"Homer City Redevelopment","title":"FAQ","type":"company","url":"https://www.homercityredevelopment.com/faq"},{"accessed":"2026-10-09","id":"s3","published":"2025-04-02","publisher":"Pennsylvania Senate Republicans","title":"Pittman Hails New Wave of Energy Advancement in Pennsylvania","type":"government","url":"https://www.pasenategop.com/news/pittman-hails-new-wave-of-energy-advancement-in-pennsylvania/"},{"accessed":"2026-10-09","id":"s4","published":"2025-12-11","publisher":"Yale Environment 360","title":"To Feed Data Centers, Pennsylvania Faces a New Fracking Surge","type":"news","url":"https://e360.yale.edu/features/pennsylvania-data-centers-natural-gas"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-04","publisher":"Homer City Redevelopment","title":"Homer City Energy Campus Workforce Grows to More Than 1,800 Workers, Including Members of 9 Building and Construction Trade Unions","type":"company","url":"https://www.homercityredevelopment.com/post/homer-city-energy-campus-workforce-grows-to-more-than-1-800-workers-including-members-of-9-building"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260421060149/https://en.wikipedia.org/wiki/Homer_City_Generating_Station","id":"s6","published":null,"publisher":"Wikipedia","title":"Homer City Generating Station","type":"other","url":"https://en.wikipedia.org/wiki/Homer_City_Generating_Station"}],"status":"under_construction","status_as_of":"2026-09-04","status_source_ids":["s5"],"summary":"Redevelopment of the retired Homer City coal-fired generating station in Indiana County, Pennsylvania, into a gas-fired power and data center campus of more than 3,200 acres. Seven GE Vernova 7HA.02 turbines are planned to deliver up to 4.4 GW for multiple large data center customers, with some power also supplied to the local grid. The developer projects more than 10 billion US dollars for power infrastructure and site readiness, with data centers adding more. Pennsylvania regulators issued an air permit in November 2025; by September 2026 more than 1,800 workers were on site, with power production targeted for 2027. No data center tenant has been named.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"66dee0cf-aaa0-5561-889d-7609ee252494","s2":"41d3b525-b2df-5a76-99bf-155814c1264d","s3":"78e4189f-fca3-5ade-9969-696d30129b77","s4":"08c1fde3-35eb-5cf1-a141-822cfefed1f4","s5":"97df27dd-a5e1-5fe6-894a-95ac5c5609eb","s6":"edfc18b9-9ea2-5d47-87f6-6610c5f66dfc"},"source_file":"datacenters/projects/homer-city-redevelopment.json","source_record_id":"homer-city-redevelopment","source_record_sha256":"df51c430e2602ca76bfc730c4a832dc4378f8c2783e5e0d87db5fa2704e614db","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d0717abb8b9441401da026b4470274bec5ee412c94ed706de4ad41dd1c89dda7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f49882717c93278a3c62/#project-7d6333d2-26e6-548c-979a-324c7113281b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7d6333d2-26e6-548c-979a-324c7113281b.json
7d936c4e-29f2-592f-984b-61f5d6367fc8 | curated:related-openai-oracle-stargate-michigan-saline:current-build | vcc-site-249f52c31025c0aa2ef2 | curated:related-openai-oracle-stargate-michigan-saline | The Barn Stargate Current Data Center Build | United States | US | 42.1239 | -83.8821 | Polygon | campus | cross_source_overlay | openstreetmap_named_website_tagged_construction_site_polygon_as_campus_locator | reviewed_openstreetmap_named_website_tagged_barn_construction_site_polygon | community_mapped | campus_locator | The frozen global-open-v3 Polygon is a contributor-mapped construction-site locator for the named Barn data-center campus, inherited by the current-build project through the explicit v14 project_targets relationship. It is not an official, cadastral, or survey boundary; a verified complete 250-acre campus extent; a building or project footprint; a construction extent; or a source of lifecycle, capacity, energy, operating-status, or imagery claims. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | 2c1a0857-1368-581b-adfa-96bf72cc9c16 | under_construction | 2026-09-28 | 15 | authoritative_physical_status_update | 46cf8bef-428b-5ca2-b0ce-2eeb73b943d4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | tracked_identity_bound_visible_change_followup_only_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [{"as_of_date":"2026-06-01","confidence":0.99,"deployment_scope":"intended","evidence_id":"ec302d8d-d1c0-594f-88f7-708f6642e827","method":"company_disclosure","workload":"ai_specialized_unspecified"}] |  | [{"evidence_id":"ec302d8d-d1c0-594f-88f7-708f6642e827","party":"OpenAI","relationship_scope":"intended","role":"customer"},{"evidence_id":"ec302d8d-d1c0-594f-88f7-708f6642e827","party":"Oracle","relationship_scope":"intended","role":"customer"},{"evidence_id":"bfff2e88-a792-5a83-bcfe-ab9fc39f3967","notes":null,"party":"Related Digital","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"6e1be437-bfeb-5fec-a923-e97f44095404","notes":null,"party":"Related Digital","relationship_scope":"unknown","role":"developer","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"6e1be437-bfeb-5fec-a923-e97f44095404","notes":"Provides equity alongside Blackstone-affiliated funds.","party":"Related Digital","relationship_scope":"unknown","role":"investor","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"bfff2e88-a792-5a83-bcfe-ab9fc39f3967","notes":"The campus is being developed exclusively for Oracle, and the first buildings are slated for delivery to Oracle.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"6e1be437-bfeb-5fec-a923-e97f44095404","notes":"The campus is being developed exclusively for Oracle, and the first buildings are slated for delivery to Oracle.","party":"Oracle","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"6e1be437-bfeb-5fec-a923-e97f44095404","notes":"Oracle's Stargate partner; the campus is described as purpose-built for Oracle and OpenAI.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"bfff2e88-a792-5a83-bcfe-ab9fc39f3967","notes":"General contractor.","party":"Walbridge","relationship_scope":"unknown","role":"builder","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"6e1be437-bfeb-5fec-a923-e97f44095404","notes":"General contractor.","party":"Walbridge","relationship_scope":"unknown","role":"builder","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"6e1be437-bfeb-5fec-a923-e97f44095404","notes":"Equity through affiliated funds.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"6e1be437-bfeb-5fec-a923-e97f44095404","notes":"PIMCO-managed funds and accounts anchor the fixed-rate, long-term debt financing.","party":"PIMCO","relationship_scope":"unknown","role":"investor","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"bfff2e88-a792-5a83-bcfe-ab9fc39f3967","notes":null,"party":"DTE Energy","relationship_scope":"unknown","role":"utility","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"9436f3d3-7560-569c-95e7-9bf2f9650f62","notes":null,"party":"DTE Energy","relationship_scope":"unknown","role":"utility","source_record_id":"openai-stargate-saline-township"},{"evidence_id":"9436f3d3-7560-569c-95e7-9bf2f9650f62","notes":"Approved DTE's energy contracts to serve the campus.","party":"Michigan Public Service Commission","relationship_scope":"unknown","role":"government","source_record_id":"openai-stargate-saline-township"}] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  |  |  | OpenAI; Oracle | OpenAI; Oracle | https://www.oracle.com/news/announcement/blog/one-million-union-craft-hours-building-michigans-future-2026-09-28/ | https://www.openstreetmap.org/way/1528327802 | [{"identity_decision":{"decision":"exact_project","flags":["approximate_locator_not_boundary"],"rationale":"Same The Barn three-building Stargate campus developed by Related Digital for Oracle/OpenAI in Saline Township. Name alias, parties and construction program agree.","source_record_id":"openai-stargate-saline-township","target_project_stable_key":"curated:related-openai-oracle-stargate-michigan-saline:current-build"},"record":{"aliases":["The Barn","Stargate Michigan","Related Digital Saline Township"],"id":"openai-stargate-saline-township","last_reviewed":"2026-10-09","location":{"admin1":"Michigan","admin2":"Washtenaw County","country":"US","lat":42.1248,"locality":"Saline Township","lon":-83.8587,"note":"Sources place the site entrance off Michigan Avenue, and news photos show the campus from West Michigan Avenue and from Braun Road on its back side. The point lies on West Michigan Avenue in Saline Township near the line of Braun Road, derived from OpenStreetMap Nominatim road geometry; the county is named in the June 2026 release. It is not a surveyed parcel location.","precision":"approximate_site","source_ids":["s1","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-10-30","basis":"planned","metric":"power_capacity","note":"Figure given at announcement.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-08-02","basis":"planned","metric":"power_capacity","note":"Figure used in news coverage of the DTE contract approval and later construction; the articles do not say whether it is IT load or total demand.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s4"],"unit":"MW","value":1400},{"applies_to":"campus","as_of":"2026-04-17","basis":"planned","metric":"power_capacity","note":"Analyst estimate, not a company disclosure: Epoch AI's projection of total facility power.","power_scope":"facility","qualifier":"approximately","source_ids":["s5"],"unit":"MW","value":1400},{"applies_to":"campus","as_of":"2026-06-01","basis":"announced","metric":"investment","note":"Planned site construction spending cited by the project team; the overall project is described only as multi-billion-dollar.","qualifier":"more_than","source_ids":["s3"],"unit":"USD","value":5000000000},{"applies_to":"campus","as_of":"2026-08-02","basis":"reported","metric":"investment","note":"Spectrum News reported that an original $4.8 billion cost estimate had risen and the project was now valued at more than $43 billion; the article does not attribute the figure to a named source, and no company source opened here confirms it.","qualifier":"more_than","source_ids":["s4"],"unit":"USD","value":43000000000},{"applies_to":"campus","as_of":"2025-10-30","basis":"planned","metric":"land_area","note":"Related Digital also plans to preserve more than 750 adjacent acres as open space, farmland and wetlands.","qualifier":"approximately","source_ids":["s1","s3"],"unit":"acres","value":250},{"applies_to":"campus","as_of":"2026-06-01","basis":"under_construction","metric":"buildings","qualifier":"exact","source_ids":["s1","s3"],"unit":"count","value":3},{"applies_to":"phase","as_of":"2026-06-01","basis":"under_construction","metric":"floor_area","phase_label":"Each of the three buildings","qualifier":"approximately","source_ids":["s1","s3"],"unit":"sq_ft","value":550000},{"applies_to":"campus","as_of":"2025-10-30","basis":"planned","metric":"jobs_construction","note":"Union construction jobs; more than 700 Michigan tradespeople were on site in June 2026.","qualifier":"more_than","source_ids":["s1","s3"],"unit":"count","value":2500},{"applies_to":"campus","as_of":"2025-10-30","basis":"planned","metric":"jobs_permanent","note":"On-site jobs; the developers also project more than 1,500 county-wide jobs.","qualifier":"more_than","source_ids":["s1","s3"],"unit":"count","value":450}],"milestones":[{"date":"2025-10-30","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-12-18","event":"other","kind":"actual","note":"The Michigan Public Service Commission unanimously approved DTE's energy contracts to serve the campus, reviewing them on an ex parte basis.","source_ids":["s2"]},{"date":"2025-Q4","event":"construction_started","kind":"actual","note":"Analyst estimate from imagery by Epoch AI, not a company disclosure; the developer had said construction would begin in early 2026 after regulatory approval.","source_ids":["s1","s5"]},{"date":"2026-06-01","event":"other","kind":"actual","note":"Construction celebration with the governor; all buildings under construction and the first nearing completion.","source_ids":["s3"]},{"date":"2028-Q4","event":"fully_operational","kind":"planned","note":"Analyst estimate by Epoch AI, not a company date.","source_ids":["s5"]}],"name":"The Barn (Stargate Michigan, Saline Township)","notes":"Local residents have continued to oppose the project at township and state regulator meetings. Cost figures in the record differ widely and may reflect different scopes. Epoch AI figures and dates are analyst estimates, not company disclosures.","parties":[{"name":"Related Digital","role":"developer","source_ids":["s1","s3"]},{"name":"Related Digital","note":"Provides equity alongside Blackstone-affiliated funds.","role":"investor","source_ids":["s3"]},{"name":"Oracle","note":"The campus is being developed exclusively for Oracle, and the first buildings are slated for delivery to Oracle.","role":"tenant","source_ids":["s1","s3"]},{"name":"OpenAI","note":"Oracle's Stargate partner; the campus is described as purpose-built for Oracle and OpenAI.","role":"tenant","source_ids":["s3"]},{"name":"Walbridge","note":"General contractor.","role":"builder","source_ids":["s1","s3"]},{"name":"Blackstone","note":"Equity through affiliated funds.","role":"investor","source_ids":["s3"]},{"name":"PIMCO","note":"PIMCO-managed funds and accounts anchor the fixed-rate, long-term debt financing.","role":"investor","source_ids":["s3"]},{"name":"DTE Energy","role":"utility","source_ids":["s1","s2"]},{"name":"Michigan Public Service Commission","note":"Approved DTE's energy contracts to serve the campus.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"DTE Energy is to supply all of the campus's electricity from existing resources under long-term contracts approved by state regulators.","source_ids":["s1","s2","s3"],"type":"grid"},{"description":"New battery storage financed entirely by the project supplements DTE's supply.","source_ids":["s1","s3"],"type":"battery_storage"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260428234555/https://www.related.com/press-releases/2025-10-30/openai-oracle-and-related-digital-announce-stargate-data-center-site","id":"s1","published":"2025-10-30","publisher":"Related Companies","title":"OpenAI, Oracle and Related Digital announce Stargate data center site in Michigan","type":"company","url":"https://www.related.com/press-releases/2025-10-30/openai-oracle-and-related-digital-announce-stargate-data-center-site"},{"accessed":"2026-10-09","id":"s2","published":"2025-12-20","publisher":"Spectrum News","title":"Michigan Public Service Commission approves DTE contracts for proposed Saline Township data center","type":"news","url":"https://spectrumlocalnews.com/mi/michigan/news/2025/12/20/mpsc-approves-dte-contracts"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260610135039/https://www.webwire.com/ViewPressRel.asp?aId=355624","id":"s3","published":"2026-06-02","publisher":"Oracle, Related Digital, Blackstone, OpenAI and Walbridge (via WebWire)","title":"Oracle, Related Digital, Blackstone, OpenAI, Walbridge and Governor Whitmer Celebrate Construction of Stargate Campus in Saline Township","type":"company","url":"https://www.webwire.com/ViewPressRel.asp?aId=355624"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-02","publisher":"Spectrum News","title":"PHOTOS: Construction continues on Related Digital's Saline Township data center","type":"news","url":"https://spectrumlocalnews.com/mi/michigan/news/2026/08/02/related-digital-saline-township-data-center-construction-progress"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260517184326/https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand","id":"s5","published":"2026-04-17","publisher":"Epoch AI","title":"OpenAI Stargate: where the US sites stand","type":"analyst","url":"https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand"}],"status":"under_construction","status_as_of":"2026-08-02","status_source_ids":["s3","s4"],"summary":"Related Digital is building The Barn, a 250-acre campus of three single-story buildings in Saline Township, Michigan, exclusively for Oracle, serving OpenAI under the Oracle-OpenAI Stargate expansion. Announced in October 2025 at more than 1 GW, it is described in later coverage as 1.4 GW. DTE Energy is to supply all power, alongside new battery storage paid for by the project. State regulators approved DTE's contracts for the campus in December 2025. In June 2026 the partners marked construction with all buildings under way and the first nearing completion. Walbridge is general contractor; financing mixes Related Digital and Blackstone-affiliated equity with PIMCO-anchored debt.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"bfff2e88-a792-5a83-bcfe-ab9fc39f3967","s2":"9436f3d3-7560-569c-95e7-9bf2f9650f62","s3":"6e1be437-bfeb-5fec-a923-e97f44095404","s4":"34f3ebce-3c8f-5366-ba0d-990f25bda04e","s5":"78f860d7-2bce-5940-985b-c8de304fccd5"},"source_file":"datacenters/projects/openai-stargate-saline-township.json","source_record_id":"openai-stargate-saline-township","source_record_sha256":"94ad5442cd8eb9d4cd6dc401ca97cd335b9bce574ef89935df559b03d300316f","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1858e480c5b3ec6bdd169c110b83a8b7178ba20600c04fcc8a3c101f999fe203"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-249f52c31025c0aa2ef2/#project-7d936c4e-29f2-592f-984b-61f5d6367fc8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/7d936c4e-29f2-592f-984b-61f5d6367fc8.json
803e9da5-cd1e-5849-813c-fe7c5b5f126b | imported:semiconductor-atlas:meta-hyperion-richland-parish | vcc-site-33110c77390f92dc4432 | curated:meta-richland-parish-data-center | Meta Richland Parish data center (Hyperion) | United States | US | 32.4676 | -91.6268 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the campus on the former Franklin Farm megasite between Rayville and Delhi; the 2026 state release is datelined Holly Ridge and WRKF refers to the Holly Ridge site. Coordinates are the Holly Ridge community point from OpenStreetMap Nominatim, not a surveyed site boundary. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 5a7175e6-9682-5800-91dd-b7c4d5de627e | under_construction | 2026-07-14 | 91 | imported_documented_status | 2b7eb369-a205-5ca1-93c4-3a6a2058b8a7 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"5a7175e6-9682-5800-91dd-b7c4d5de627e","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"2b7eb369-a205-5ca1-93c4-3a6a2058b8a7","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"fb1aac41-ec76-5e30-9c4d-71a378ffc056","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"ab392225-f519-5c13-8113-ce5f587efb89","notes":"Holds 20% of the joint venture that owns the campus and keeps the development and property-management role.","party":"Meta Platforms","relationship_scope":"unknown","role":"owner","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"b27b5754-60c7-5c40-a6b6-59cfdedcce28","notes":"Holds 20% of the joint venture that owns the campus and keeps the development and property-management role.","party":"Meta Platforms","relationship_scope":"unknown","role":"owner","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"ab392225-f519-5c13-8113-ce5f587efb89","notes":"Anchor tenant leasing the facilities from the joint venture.","party":"Meta Platforms","relationship_scope":"unknown","role":"tenant","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"ab392225-f519-5c13-8113-ce5f587efb89","notes":"Funds managed by Blue Owl hold 80% of the joint venture formed in late 2025.","party":"Blue Owl Capital (managed funds)","relationship_scope":"unknown","role":"owner","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"b27b5754-60c7-5c40-a6b6-59cfdedcce28","notes":"Funds managed by Blue Owl hold 80% of the joint venture formed in late 2025.","party":"Blue Owl Capital (managed funds)","relationship_scope":"unknown","role":"owner","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"ab392225-f519-5c13-8113-ce5f587efb89","notes":"Led the debt placements that helped finance the joint venture.","party":"PIMCO","relationship_scope":"unknown","role":"investor","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"5a7175e6-9682-5800-91dd-b7c4d5de627e","notes":null,"party":"Entergy Louisiana","relationship_scope":"unknown","role":"utility","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"f97052f5-ffa1-5891-9048-536982584e9c","notes":null,"party":"Entergy Louisiana","relationship_scope":"unknown","role":"utility","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"2b7eb369-a205-5ca1-93c4-3a6a2058b8a7","notes":null,"party":"Entergy Louisiana","relationship_scope":"unknown","role":"utility","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"ab392225-f519-5c13-8113-ce5f587efb89","notes":"Named as a general contractor.","party":"Turner Construction Company","relationship_scope":"unknown","role":"builder","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"ab392225-f519-5c13-8113-ce5f587efb89","notes":"Named as a general contractor.","party":"DPR Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"ab392225-f519-5c13-8113-ce5f587efb89","notes":"Named as a general contractor.","party":"Mortenson","relationship_scope":"unknown","role":"builder","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"5a7175e6-9682-5800-91dd-b7c4d5de627e","notes":null,"party":"Louisiana Economic Development","relationship_scope":"unknown","role":"government","source_record_id":"meta-hyperion-richland-parish"},{"evidence_id":"2b7eb369-a205-5ca1-93c4-3a6a2058b8a7","notes":null,"party":"Louisiana Economic Development","relationship_scope":"unknown","role":"government","source_record_id":"meta-hyperion-richland-parish"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Blue Owl Capital (managed funds); Meta Platforms |  |  | Meta Platforms |  | https://www.opportunitylouisiana.gov/news/meta-commits-more-than-50-billion-for-north-louisiana-project-becoming-one-of-the-largest-data-centers-in-history | https://opportunitylouisiana.gov/news/meta-selects-northeast-louisiana-as-site-of-10-billion-artificial-intelligence-optimized-data-center-governor-jeff-landry-calls-investment-a-new-chapter-for-state | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Meta Franklin Farm/Richland Parish Hyperion campus. Source includes the 5 GW long-term campus expansion; release evidence explicitly delimits observed phase 1/phase 2 construction, so preserve a broader campus scope.","source_record_id":"meta-hyperion-richland-parish","target_physical_site_stable_key":"curated:meta-richland-parish-data-center"},"record":{"aliases":["Hyperion","Richland Parish Data Center","Holly Ridge"],"id":"meta-hyperion-richland-parish","last_reviewed":"2026-10-09","location":{"admin1":"Louisiana","admin2":"Richland Parish","country":"US","lat":32.4676,"locality":"Holly Ridge","lon":-91.6268,"note":"Sources place the campus on the former Franklin Farm megasite between Rayville and Delhi; the 2026 state release is datelined Holly Ridge and WRKF refers to the Holly Ridge site. Coordinates are the Holly Ridge community point from OpenStreetMap Nominatim, not a surveyed site boundary.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-13","basis":"planned","metric":"power_capacity","note":"The state release calls this IT capacity; Meta's fact sheet describes the same 5 GW as compute capacity to house Hyperion, which it calls its largest AI cluster.","power_scope":"it_load","qualifier":"exact","source_ids":["s4","s6"],"unit":"MW","value":5000},{"applies_to":"phase","as_of":"2025-11-05","basis":"planned","metric":"power_capacity","note":"Reported before the 2026 expansion as the initial capacity target, with possible growth toward 5 GW.","phase_label":"Initial build targeted by 2030","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":2000},{"applies_to":"campus","as_of":"2025-08-20","basis":"planned","metric":"power_capacity","note":"Power requirement cited in coverage of the August 2025 utility approval, before the 5 GW expansion.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s2"],"unit":"MW","value":2500},{"applies_to":"campus","as_of":"2024-12-04","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2025-11-05","basis":"reported","metric":"investment","note":"Expected total development cost of the Meta and Blue Owl joint venture, covering buildings and long-lived power, cooling and connectivity infrastructure.","qualifier":"approximately","source_ids":["s3","s7"],"unit":"USD","value":27000000000},{"applies_to":"campus","as_of":"2026-07-13","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s4","s6"],"unit":"USD","value":50000000000},{"applies_to":"campus","as_of":"2024-12-04","basis":"planned","metric":"floor_area","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":4000000},{"applies_to":"campus","as_of":"2026-07-13","basis":"planned","metric":"floor_area","note":"Described as nearly 10 million square feet after the 2026 expansion.","qualifier":"approximately","source_ids":["s4"],"unit":"sq_ft","value":10000000},{"applies_to":"campus","as_of":"2024-12-04","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":2250},{"applies_to":"campus","as_of":"2026-07-14","basis":"reported","metric":"land_area","note":"Eventual footprint reported after the 2026 expansion.","qualifier":"more_than","source_ids":["s5"],"unit":"acres","value":3200},{"applies_to":"campus","as_of":"2024-12-04","basis":"planned","metric":"jobs_construction","note":"Peak construction workforce projected at announcement.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":5000},{"applies_to":"campus","as_of":"2026-07-13","basis":"planned","metric":"jobs_construction","note":"Peak construction workforce projected after the expansion.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":7500},{"applies_to":"campus","as_of":"2024-12-04","basis":"planned","metric":"jobs_permanent","qualifier":"at_least","source_ids":["s1"],"unit":"count","value":500},{"applies_to":"campus","as_of":"2026-07-13","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s4","s6"],"unit":"count","value":1000}],"milestones":[{"date":"2024-12-04","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024-12","event":"construction_started","kind":"actual","note":"The state said site work would begin in December; later reporting dates the groundbreaking to December 2024.","source_ids":["s1","s5"]},{"date":"2025-08","event":"other","kind":"actual","note":"The Louisiana Public Service Commission voted 4-1 to approve Entergy Louisiana's three new gas plants tied to the campus, as reported on 2025-08-20.","source_ids":["s2"]},{"date":"2025-10","event":"other","kind":"actual","note":"Meta announced the joint venture with Blue Owl-managed funds at the end of October 2025 and on 21 October cited a development cost of about USD 27 billion.","source_ids":["s3","s7"]},{"date":"2026-07-13","event":"expansion_announced","kind":"actual","note":"Expansion to 5 GW of IT capacity and more than USD 50 billion of investment.","source_ids":["s4","s5"]},{"date":"2030","event":"other","kind":"planned","note":"Target for roughly 2 GW of initial capacity, as reported before the 2026 expansion.","source_ids":["s3"]},{"date":"2036","event":"fully_operational","kind":"planned","note":"Officials expect the full build-out of both phases by 2036.","source_ids":["s5"]}],"name":"Meta Richland Parish data center (Hyperion)","notes":"Meta's fact sheet PDF (s6) shows no publication date; its embedded file creation date is 2026-09-01. The KTVE article (s7) shows only a relative date.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s4","s6"]},{"name":"Meta Platforms","note":"Holds 20% of the joint venture that owns the campus and keeps the development and property-management role.","role":"owner","source_ids":["s3","s7"]},{"name":"Meta Platforms","note":"Anchor tenant leasing the facilities from the joint venture.","role":"tenant","source_ids":["s3"]},{"name":"Blue Owl Capital (managed funds)","note":"Funds managed by Blue Owl hold 80% of the joint venture formed in late 2025.","role":"owner","source_ids":["s3","s7"]},{"name":"PIMCO","note":"Led the debt placements that helped finance the joint venture.","role":"investor","source_ids":["s3"]},{"name":"Entergy Louisiana","role":"utility","source_ids":["s1","s2","s4"]},{"name":"Turner Construction Company","note":"Named as a general contractor.","role":"builder","source_ids":["s3"]},{"name":"DPR Construction","note":"Named as a general contractor.","role":"builder","source_ids":["s3"]},{"name":"Mortenson","note":"Named as a general contractor.","role":"builder","source_ids":["s3"]},{"name":"Louisiana Economic Development","role":"government","source_ids":["s1","s4"]}],"power_sources":[{"description":"Supplied by Entergy Louisiana under a 20-year agreement. Regulators approved three new combined-cycle gas units in 2025 (two in Richland Parish, one at Waterford) along with transmission upgrades; the 2026 state release refers to seven new gas plants, while WRKF reports Entergy sought approval for ten. These are utility plants rather than on-site generation.","source_ids":["s2","s3","s4","s5"],"type":"grid"},{"description":"Three grid-scale battery systems are part of the Entergy arrangement announced with the 2026 expansion.","source_ids":["s4"],"type":"battery_storage"},{"description":"The 2026 arrangement includes possible nuclear development, including an output increase at Entergy's Waterford 3 plant.","source_ids":["s4"],"type":"nuclear"},{"description":"Entergy was cleared to fast-track up to 1,500 MW of solar; Meta earlier pledged to help bring at least 1,500 MW of new renewables to the grid and in 2026 committed to fund up to 2.5 GW of clean energy.","source_ids":["s1","s3","s4"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-12-04","publisher":"Louisiana Economic Development","title":"Meta Selects Northeast Louisiana as Site of $10 Billion Artificial Intelligence Optimized Data Center; Governor Jeff Landry Calls Investment 'A New Chapter' for State","type":"government","url":"https://opportunitylouisiana.gov/news/meta-selects-northeast-louisiana-as-site-of-10-billion-artificial-intelligence-optimized-data-center-governor-jeff-landry-calls-investment-a-new-chapter-for-state"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250821033352/https://www.kalb.com/2025/08/21/la-regulators-approve-entergy-power-plants-metas-ai-data-center/","id":"s2","published":"2025-08-20","publisher":"KALB","title":"La. regulators approve Entergy power plants for Meta's AI data center","type":"news","url":"https://www.kalb.com/2025/08/21/la-regulators-approve-entergy-power-plants-metas-ai-data-center/"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-05","publisher":"Data Center Frontier","title":"Meta's $27B Hyperion Campus: A New Blueprint for AI Infrastructure Finance","type":"trade_press","url":"https://www.datacenterfrontier.com/hyperscale/article/55325337/metas-27b-hyperion-campus-a-new-blueprint-for-ai-infrastructure-finance"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260911184712/https://www.opportunitylouisiana.gov/news/meta-commits-more-than-50-billion-for-north-louisiana-project-becoming-one-of-the-largest-data-centers-in-history?","id":"s4","published":"2026-07-13","publisher":"Louisiana Economic Development","title":"Meta Commits More Than $50 Billion for North Louisiana Project, Becoming One of the Largest Data Centers in History","type":"government","url":"https://www.opportunitylouisiana.gov/news/meta-commits-more-than-50-billion-for-north-louisiana-project-becoming-one-of-the-largest-data-centers-in-history"},{"accessed":"2026-10-09","id":"s5","published":"2026-07-14","publisher":"WRKF","title":"Meta is investing $40B more to expand Richland Parish data center project","type":"news","url":"https://www.wrkf.org/2026-07-14/meta-is-investing-40b-more-to-expand-richland-parish-data-center-project"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260911180758/https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Richland-Parish-Data-Center.pdf","id":"s6","published":null,"publisher":"Meta Platforms","title":"Meta Richland Parish Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Richland-Parish-Data-Center.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251106093133/https://www.myarklamiss.com/news/as-development-continues-the-cost-of-metas-data-center-in-richland-parish-will-be-3x-more-than-originally-projected/amp/","id":"s7","published":null,"publisher":"KTVE (myarklamiss.com)","title":"As development continues, the cost of Meta's data center in Richland Parish will be 3x more than originally projected","type":"news","url":"https://www.myarklamiss.com/news/as-development-continues-the-cost-of-metas-data-center-in-richland-parish-will-be-3x-more-than-originally-projected/amp"}],"status":"under_construction","status_as_of":"2026-07-14","status_source_ids":["s4","s5"],"summary":"Meta campus on the former Franklin Farm megasite in Richland Parish, northeast Louisiana, built to house Hyperion, which Meta calls its largest AI cluster. Announced in December 2024 as a USD 10 billion project, it was placed in late 2025 in a joint venture 80% owned by Blue Owl-managed funds and expanded in July 2026 to a planned 5 GW of IT capacity and more than USD 50 billion of investment. Entergy Louisiana is adding gas-fired generation, batteries and transmission upgrades to serve the site under a 20-year agreement. Construction began in December 2024, and officials expect full build-out around 2036.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"5a7175e6-9682-5800-91dd-b7c4d5de627e","s2":"f97052f5-ffa1-5891-9048-536982584e9c","s3":"ab392225-f519-5c13-8113-ce5f587efb89","s4":"2b7eb369-a205-5ca1-93c4-3a6a2058b8a7","s5":"8cb69023-eb1a-5305-a41a-5117d50adfb9","s6":"fb1aac41-ec76-5e30-9c4d-71a378ffc056","s7":"b27b5754-60c7-5c40-a6b6-59cfdedcce28"},"source_file":"datacenters/projects/meta-hyperion-richland-parish.json","source_record_id":"meta-hyperion-richland-parish","source_record_sha256":"32572f3cc36c74b52139674363a64f8dc1cb863db825b2f7c38e412c404e5ebe","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"60f52885979d54cae121ce62142985ac61bf565dea5b18fd463e8c93e21ca115"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-33110c77390f92dc4432/#project-803e9da5-cd1e-5849-813c-fe7c5b5f126b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/803e9da5-cd1e-5849-813c-fe7c5b5f126b.json
81d20134-d073-5e0c-ad1c-7f8a97f2dadb | imported:semiconductor-atlas:tbc-partners-cambois | vcc-site-b3a2be1a532755abcfa9 | imported:semiconductor-atlas:tbc-partners-cambois | TBC Partners Cambois data centre campus | United Kingdom | GB | 55.1453 | -1.5309 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | The site is on Factory Road, Cambois, beside the A189 just south of the River Wansbeck. Nominatim did not resolve Factory Road, so the Cambois village centroid is used. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 07eeb2a7-7bc4-59bf-953c-00879a92180d | proposed | 2026-08-18 | 56 | imported_documented_status | 07eeb2a7-7bc4-59bf-953c-00879a92180d | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2cd48493-bff6-5366-9b52-98b724d14f7c","notes":null,"party":"TBC Partners","relationship_scope":"unknown","role":"developer","source_record_id":"tbc-partners-cambois"},{"evidence_id":"07eeb2a7-7bc4-59bf-953c-00879a92180d","notes":null,"party":"TBC Partners","relationship_scope":"unknown","role":"developer","source_record_id":"tbc-partners-cambois"},{"evidence_id":"07eeb2a7-7bc4-59bf-953c-00879a92180d","notes":"Planning authority asked for the screening opinion.","party":"Northumberland County Council","relationship_scope":"unknown","role":"government","source_record_id":"tbc-partners-cambois"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://bebeez.eu/2026/08/18/application-filed-for-data-center-campus-near-qts-site-in-northumberland-uk/ | https://bebeez.eu/2026/08/18/application-filed-for-data-center-campus-near-qts-site-in-northumberland-uk/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve TBC Partners Cambois data centre campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"tbc-partners-cambois","source_relations":[{"reason":"TBC proposal on Factory Road is explicitly described as near the QTS former power-station campus; identical Cambois centroid is administrative only.","relationship":"separate_nearby_campuses","source_id":"qts-cambois-blyth"}]},"record":{"aliases":["TBC Partners Blyth data centre"],"id":"tbc-partners-cambois","last_reviewed":"2026-10-09","location":{"admin1":"England","admin2":"Northumberland","country":"GB","lat":55.1453,"locality":"Cambois","lon":-1.5309,"note":"The site is on Factory Road, Cambois, beside the A189 just south of the River Wansbeck. Nominatim did not resolve Factory Road, so the Cambois village centroid is used.","precision":"locality","source_ids":["s2"]},"metrics":[{"applies_to":"campus","as_of":"2025-01","basis":"contracted","metric":"power_capacity","note":"TBC Partners describes two 300 MW projects, at Blyth and Didcot, and says both have procured 300 MW demand connections.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-08-18","basis":"planned","metric":"power_capacity","note":"Trade report says the Cambois campus could total 300 MW, citing TBC's website; full project details had not been published.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-08-18","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s2"],"unit":"hectares","value":12}],"milestones":[{"date":"2025-01","event":"announced","kind":"actual","note":"A January 2025 news item on TBC Partners' website says it had begun developing two UK data centres, at Didcot and Blyth.","source_ids":["s1"]},{"date":"2026-08","event":"other","kind":"actual","note":"Request to Northumberland County Council for an EIA screening opinion; no full planning application yet.","source_ids":["s2"]},{"date":"2030","event":"first_operational","kind":"planned","note":"Occupation and operation intended from 2030 to 2035 after about 24 months of construction.","source_ids":["s2"]}],"name":"TBC Partners Cambois data centre campus","parties":[{"name":"TBC Partners","role":"developer","source_ids":["s1","s2"]},{"name":"Northumberland County Council","note":"Planning authority asked for the screening opinion.","role":"government","source_ids":["s2"]}],"power_sources":[],"related_ids":["qts-cambois-blyth"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251010131544/https://tbcpartners.co.uk/","id":"s1","published":null,"publisher":"TBC Partners","title":"TBC Partners","type":"company","url":"https://www.tbcpartners.co.uk/"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-18","publisher":"BeBeez International (republishing DatacenterDynamics)","title":"Application filed for data center campus near QTS' site in Northumberland, UK","type":"trade_press","url":"https://bebeez.eu/2026/08/18/application-filed-for-data-center-campus-near-qts-site-in-northumberland-uk/"}],"status":"proposed","status_as_of":"2026-08-18","status_source_ids":["s2"],"summary":"TBC Partners, a UK joint family office focused on energy transition and impact investments, said in January 2025 it had started developing data centres at Blyth and Didcot, describing them as two 300 MW projects with procured demand connections. In August 2026 it asked Northumberland County Council for a screening opinion on whether an environmental impact assessment is needed for a campus of about 12 hectares on Factory Road, Cambois, near the QTS campus. Construction would take about two years, with occupation and operation intended between 2030 and 2035. A full planning application had not been filed.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2cd48493-bff6-5366-9b52-98b724d14f7c","s2":"07eeb2a7-7bc4-59bf-953c-00879a92180d"},"source_file":"datacenters/projects/tbc-partners-cambois.json","source_record_id":"tbc-partners-cambois","source_record_sha256":"1ed67826272efcc8bff6bd33ef12dcbc0ab7f5e8ee6f3b1cac4e60aa1808b7e4","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"58a9db58dfa3a70967ba84221d28332a6113a3722e182c6e330572c764f5e49e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b3a2be1a532755abcfa9/#project-81d20134-d073-5e0c-ad1c-7f8a97f2dadb | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/81d20134-d073-5e0c-ad1c-7f8a97f2dadb.json
825dd9ee-ffe9-525e-8d9f-ec8e370d9944 | curated:iron-mountain-lon-3-london-data-center:25mw-build | vcc-site-b2ce7bc4242acd906a7b | curated:iron-mountain-lon-3-london-data-center | Iron Mountain LON-3 25 MW Build | United Kingdom | GB | 51.5202 | -0.62006 | Point | campus | official_environmental_report_site_grid_reference | EPSG_27700_to_EPSG_4326_always_xy_with_documented_OSGB36_transform | official_environmental_report_campus_reference_point | official_source | campus_locator | The report's National Grid Reference locates the LON3 site at 111 Buckingham Avenue. It is not a parcel, building centre, full Slough campus boundary or observed construction extent. LON1, LON2 and LON3 campus relationships do not create separate site additions. |  | No source-specific numeric horizontal accuracy is published; transform operation accuracy is not site-locator uncertainty. | dc67d965-3723-5231-ac1f-ca26516929b0 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 681761fe-09c6-5f22-b508-1e20945f632d | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1020569/000102056926000068/q22026srpfinal.htm | https://consult.environment-agency.gov.uk/psc/sl1-4pf-iron-mountain-uk-data-centre-limited-a001/supporting_documents/Application%20%20Bespoke%20%20Site%20Condition%20Report_REH2023N04112RAMRP00003%2030092024.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b2ce7bc4242acd906a7b/#project-825dd9ee-ffe9-525e-8d9f-ec8e370d9944 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/825dd9ee-ffe9-525e-8d9f-ec8e370d9944.json
82f20665-aa7b-51d5-b303-ddf63792d77b | curated:israel-mega-dc-mdcil1-modiin-site:phase-b | vcc-site-4325075080f62b6ecff4 | curated:israel-mega-dc-mdcil1-modiin-site | Mega D.C. MDCIL-1 Modi'in Phase B Current Build | Israel | IL | 31.9168 | 34.9688 | Polygon | campus | approved_plan_land_use_plot_ring_transformed_EPSG2039_to_WGS84 | Xplan_layer4_plot_query_native_ring_PROJ_Israel1993_to_WGS84_2_round7 | approved_statutory_plan_land_use_plot | official_source | campus_locator | Every native plot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. Plot 62 of plan 420-1456037 is bound to the campus by the issuer's own plot references; it is a planning plot, not a surveyed cadastral boundary, building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it. |  | The planning service states no positional accuracy and disclaims official status; the 0.5 m datum-operation figure is not a plot accuracy. | 30404c19-2608-5791-98f7-8411cde80c3c | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | b646f62e-d587-5494-ab8f-1f98299c5c4b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://megaor.co.il/wp-content/uploads/2026/08/דוח-רבעון-2-לשנת-2026.pdf | https://ags.iplan.gov.il/arcgisiplan/rest/services/PlanningPublic/Xplan/MapServer/4/query?where=num%3D%2762%27+AND+pl_number%3D%27420-1456037%27&outFields=*&returnGeometry=true&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4325075080f62b6ecff4/#project-82f20665-aa7b-51d5-b303-ddf63792d77b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/82f20665-aa7b-51d5-b303-ddf63792d77b.json
83efe2e8-3b4b-5260-b4ca-d1dbc653b792 | curated:cdc-brooklyn-melbourne-campus:remaining-facilities-current-build | vcc-site-6ec62bca94b5d5e1db03 | curated:cdc-brooklyn-melbourne-campus | CDC Brooklyn Remaining Facilities Current Build | Australia | AU | -37.8174 | 144.8438 | Point | campus | coordinates_to_point | official_regulatory_site_coordinate | addressed_regulatory_site_point | official_source | campus_locator | Exact ACMA-published six-decimal coordinate for a CDC-linked radio site at the named campus address; not a parcel, building, work area, or facility-allocation boundary. |  | ACMA publishes no bounded positional accuracy for this radio-site coordinate. | 69b44d85-4d17-5832-aaf7-8c2ba2bcf14f | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | dbcd6b98-bd03-5c22-b783-83ec2859ea0b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.cdc.com.au/locations/melbourne/ | https://api.acma.gov.au/SpectrumLicensingAPIOuterService/OuterService.svc/SiteSearchJSON/10038207?searchField=SITE_ID | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6ec62bca94b5d5e1db03/#project-83efe2e8-3b4b-5260-b4ca-d1dbc653b792 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/83efe2e8-3b4b-5260-b4ca-d1dbc653b792.json
8560b48f-07cb-54c8-8b8d-163dc196caee | imported:semiconductor-atlas:edgecore-louisa-county | vcc-site-ebc20ddd515fd9367ea7 | imported:semiconductor-atlas:edgecore-louisa-county | EdgeCore Louisa County campus | United States | US | 37.99 | -77.96 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Wikipedia coordinates for Louisa County, Virginia. EdgeCore places the campus in the Shannon Hill Regional Business Park, which no cited source locates precisely. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6857f912-65fa-51fd-8bf5-88f9bde79ed1 | announced | 2026-10-09 | 4 | imported_documented_status | 863d6628-d7a5-5afa-a51a-cd487a9fefa4 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6857f912-65fa-51fd-8bf5-88f9bde79ed1","notes":null,"party":"EdgeCore Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"edgecore-louisa-county"},{"evidence_id":"345b448f-5907-513d-a752-69d014e7aa34","notes":null,"party":"EdgeCore Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"edgecore-louisa-county"},{"evidence_id":"345b448f-5907-513d-a752-69d014e7aa34","notes":"Investment firm backing EdgeCore; not described as investing in this campus specifically.","party":"Partners Group","relationship_scope":"unknown","role":"investor","source_record_id":"edgecore-louisa-county"},{"evidence_id":"6857f912-65fa-51fd-8bf5-88f9bde79ed1","notes":null,"party":"Rappahannock Electric Cooperative","relationship_scope":"unknown","role":"utility","source_record_id":"edgecore-louisa-county"},{"evidence_id":"345b448f-5907-513d-a752-69d014e7aa34","notes":null,"party":"Rappahannock Electric Cooperative","relationship_scope":"unknown","role":"utility","source_record_id":"edgecore-louisa-county"},{"evidence_id":"345b448f-5907-513d-a752-69d014e7aa34","notes":"Bought the business park land in 2018, rezoned it for technology uses and sold the site to EdgeCore.","party":"Louisa County","relationship_scope":"unknown","role":"government","source_record_id":"edgecore-louisa-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://edgecore.com/locations/louisa-county-data-center | https://edgecore.com/resources/press-releases/new-louisa-county-virginia-data-center-campus | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve EdgeCore Louisa County campus as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"edgecore-louisa-county"},"record":{"aliases":["EdgeCore Shannon Hill campus"],"id":"edgecore-louisa-county","last_reviewed":"2026-10-09","location":{"admin1":"Virginia","admin2":"Louisa County","country":"US","lat":37.99,"lon":-77.96,"note":"Wikipedia coordinates for Louisa County, Virginia. EdgeCore places the campus in the Shannon Hill Regional Business Park, which no cited source locates precisely.","precision":"admin2","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2025-06-25","basis":"planned","metric":"power_capacity","note":"The announcement gives more than 1.1 GW without a scope; EdgeCore's campus page describes the figure as critical IT load at full build-out.","power_scope":"it_load","qualifier":"more_than","source_ids":["s2","s1"],"unit":"MW","value":1100},{"applies_to":"campus","as_of":"2025-06-25","basis":"announced","metric":"investment","note":"Bisnow describes the investment as close to USD 17 billion.","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":17000000000},{"applies_to":"campus","as_of":"2025-06-25","basis":"acquired","metric":"land_area","note":"Bisnow reports EdgeCore bought the site from the county for USD 42 million.","qualifier":"exact","source_ids":["s1","s3"],"unit":"acres","value":697},{"applies_to":"campus","as_of":"2025-06-25","basis":"planned","metric":"floor_area","note":"Figure in the June 2025 announcement; Bisnow reported nearly 4 million square feet.","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":3900000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Figure on EdgeCore's undated campus page as viewed on the access date; it is lower than the announcement's 3.9 million square feet.","qualifier":"exact","source_ids":["s2"],"unit":"sq_ft","value":3100000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"Single-tenant data centers, per the undated campus page as viewed on the access date.","qualifier":"at_least","source_ids":["s2"],"unit":"count","value":6}],"milestones":[{"date":"2019","event":"other","kind":"actual","note":"Louisa County rezoned the business park land, bought in 2018, for technology uses.","source_ids":["s3"]},{"date":"2025-06-25","event":"announced","kind":"actual","source_ids":["s1","s3"]}],"name":"EdgeCore Louisa County campus","notes":"Status rests on EdgeCore's undated campus page, viewed on 2026-10-09, which still describes the campus in planning terms and gives no construction or delivery dates.","parties":[{"name":"EdgeCore Digital Infrastructure","role":"developer","source_ids":["s1","s3"]},{"name":"Partners Group","note":"Investment firm backing EdgeCore; not described as investing in this campus specifically.","role":"investor","source_ids":["s3"]},{"name":"Rappahannock Electric Cooperative","role":"utility","source_ids":["s1","s3"]},{"name":"Louisa County","note":"Bought the business park land in 2018, rezoned it for technology uses and sold the site to EdgeCore.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"Rappahannock Electric Cooperative expects to work with EdgeCore and the county to power the campus; the release also names Hyperscale Energy as the cooperative's affiliate without giving it a role.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260807051838/https://edgecore.com/resources/press-releases/new-louisa-county-virginia-data-center-campus","id":"s1","published":"2025-06-25","publisher":"EdgeCore Digital Infrastructure","title":"EdgeCore Digital Infrastructure Announces Plans to Invest $17B+ in Louisa County, VA through the Development of 1.1+ Gigawatt Data Center Campus","type":"company","url":"https://edgecore.com/resources/press-releases/new-louisa-county-virginia-data-center-campus"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"EdgeCore Digital Infrastructure","title":"Louisa County Data Centers","type":"company","url":"https://edgecore.com/locations/louisa-county-data-center"},{"accessed":"2026-10-09","id":"s3","published":"2025-06-25","publisher":"Bisnow","title":"New $17B Project Continues Data Center Surge In Small Virginia County","type":"trade_press","url":"https://www.bisnow.com/news/national/data-center/17b-campus-continues-data-center-surge-in-small-virginia-county-129918"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s2","s1"],"summary":"EdgeCore Digital Infrastructure plans a hyperscale data center campus on 697 acres it bought from Louisa County in the Shannon Hill Regional Business Park, about 40 miles northwest of Richmond, Virginia. Announced in June 2025, the campus is planned for more than 1.1 GW, which EdgeCore's campus page describes as critical IT load, with investment of more than USD 17 billion. Rappahannock Electric Cooperative is expected to provide power. EdgeCore's announcement cited 3.9 million square feet, while its current campus page lists 3.1 million square feet in at least six single-tenant buildings.","workloads":["ai_training","ai_inference","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6857f912-65fa-51fd-8bf5-88f9bde79ed1","s2":"863d6628-d7a5-5afa-a51a-cd487a9fefa4","s3":"345b448f-5907-513d-a752-69d014e7aa34"},"source_file":"datacenters/projects/edgecore-louisa-county.json","source_record_id":"edgecore-louisa-county","source_record_sha256":"4818450653b73fabd55a50a76634714a88cddcb9cc5097779c29293d08ddf993","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"03299f12f0a76a4f50b67c04e4b16a9b2a4f7a40e3d0d0899a50213b7da8c69b"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ebc20ddd515fd9367ea7/#project-8560b48f-07cb-54c8-8b8d-163dc196caee | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8560b48f-07cb-54c8-8b8d-163dc196caee.json
85cb6e56-ec73-5685-82e7-15e4ef96106b | curated:edged-council-bluffs-data-center-campus:first-data-center | vcc-site-7cc1c64f44550b086450 | curated:edged-council-bluffs-data-center-campus | Edged Council Bluffs First Data Center | United States | US | 41.275 | -95.7912 | Point | project | official_address_point | official_address_point | project_address_point | official_source | project_locator | Exact county address point for the permit-linked 2313 College Road site; not a parcel, building footprint, or current work boundary. |  | The county address-point layer states no bounded capture accuracy. | 0fff6073-2536-58db-b16e-b82141605ef5 | shell | 2026-07-17 | 88 | authoritative_physical_status_update | cab7dc15-ee5d-56ec-8e4c-3157a35255e7 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/posts/edgedenergy_edgedus-councilbluffs-omaha-activity-7483966398021390336-wI13 | https://gis.pottcounty-ia.gov/arcgis/rest/services/OpenData/MapServer/9/query | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7cc1c64f44550b086450/#project-85cb6e56-ec73-5685-82e7-15e4ef96106b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/85cb6e56-ec73-5685-82e7-15e4ef96106b.json
867d91cb-7a17-59db-a92e-4a50a499f54f | osm:way/1383040176:development-project | vcc-site-495790bb0eec99f8d10f | osm:way/1383040176 | Microsoft L’Ancienne-Lorette Development Project | Canada | CA | 46.7919 | -71.3468 | Point | campus | official_address_range_interpolation | EPSG4617_to_EPSG4326_NAD83CSRS_to_WGS84_2 | official_interpolated_address_reference_point | official_source | campus_locator | Source-matched unsuffixed address record interpolated along a road-address range. Not an entrance, exact building, parcel centroid, or current work footprint. Exact decimal output preserves calculation only. |  | Official source labels geometry geocoded and supplies no numeric positional accuracy. The 1m datum operation accuracy is not the much less constrained address-interpolation accuracy. | f1de17cc-40e9-5de3-8054-8d23d670f770 | under_construction | 2026-06-08 | 127 | authoritative_physical_status_update | 56801cf5-482f-5da1-b795-f71c04fd85c0 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.ccq.org/-/media/Project/Ccq/Ccq-Website/PDF/Recherche/ChantiersImportants/Juin2026/Quebec.pdf?rev=f6c6681d730744f7bf856c79a7b114a0&sc_lang=fr-CA | https://servicescarto.mern.gouv.qc.ca/pes/rest/services/Territoire/RQA_WMS/MapServer/0/query?where=NUMERO_MUNICIPAL%3D6505%20AND%20SPECIFIQUE_ODONYME%3D%27Yvon-Dolbec%27&outFields=*&returnGeometry=true&outSR=4617&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-495790bb0eec99f8d10f/#project-867d91cb-7a17-59db-a92e-4a50a499f54f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/867d91cb-7a17-59db-a92e-4a50a499f54f.json
869dffc7-22ea-5f40-8810-13d87c696908 | imported:semiconductor-atlas:nextdc-m4-port-melbourne | vcc-site-78289e1b65e2284a986f | curated:nextdc-m4-melbourne | NEXTDC M4 Melbourne | Australia | AU | -37.833 | 144.9124 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | NEXTDC gives the address 127 Todd Road, Port Melbourne. OpenStreetMap Nominatim matched Todd Road but not the house number, so coordinates are a point on Todd Road near the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 822a36e0-a36b-55dc-b617-b1f6f3fdeb48 | announced | 2026-01-19 | 267 | imported_documented_status | c035f6ad-ba8f-544f-82b5-f1fd3afa8fb1 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"822a36e0-a36b-55dc-b617-b1f6f3fdeb48","notes":null,"party":"NEXTDC","relationship_scope":"unknown","role":"developer","source_record_id":"nextdc-m4-port-melbourne"},{"evidence_id":"c035f6ad-ba8f-544f-82b5-f1fd3afa8fb1","notes":null,"party":"NEXTDC","relationship_scope":"unknown","role":"developer","source_record_id":"nextdc-m4-port-melbourne"},{"evidence_id":"e1b7f87f-679a-5762-ad17-0fca03d9e04c","notes":null,"party":"NEXTDC","relationship_scope":"unknown","role":"developer","source_record_id":"nextdc-m4-port-melbourne"},{"evidence_id":"c035f6ad-ba8f-544f-82b5-f1fd3afa8fb1","notes":"Granted development approval.","party":"Victorian Government","relationship_scope":"unknown","role":"government","source_record_id":"nextdc-m4-port-melbourne"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.nextdc.com/news/m4-technology-campus-approved | https://www.nextdc.com/news/nextdc-announces-2-billion-ai-factory-and-technology-campus-at-fishermans-bend | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["approximate_locator_not_boundary","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same NEXTDC M4 campus at 127 Todd Road, Port Melbourne. Source retains the approved full campus while existing record selects June 2026 initial early works; its older announced status must not replace the observed site preparation.","source_record_id":"nextdc-m4-port-melbourne","target_physical_site_stable_key":"curated:nextdc-m4-melbourne"},"record":{"aliases":["M4 Technology Campus","Fishermans Bend AI Factory and Technology Campus"],"id":"nextdc-m4-port-melbourne","last_reviewed":"2026-10-09","location":{"admin1":"Victoria","country":"AU","lat":-37.833,"locality":"Port Melbourne","lon":144.9124,"note":"NEXTDC gives the address 127 Todd Road, Port Melbourne. OpenStreetMap Nominatim matched Todd Road but not the house number, so coordinates are a point on Todd Road near the site.","precision":"approximate_site","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2025-06-12","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2026-01-19","basis":"planned","metric":"power_capacity","note":"Capacity stated in NEXTDC's development approval announcement; the release does not say whether the approval itself sets a power limit or whether the figure is IT load.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":162},{"applies_to":"campus","as_of":"2026-10","basis":"planned","metric":"power_capacity","note":"Undated facility page, viewed October 2026, gives a target of 150 MW of IT capacity and 26,400 square meters of technical space.","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2025-06-12","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1","s2"],"unit":"AUD","value":2000000000},{"applies_to":"campus","as_of":"2025-06-12","basis":"planned","metric":"floor_area","note":"Area given for mission-critical facilities.","qualifier":"exact","source_ids":["s1"],"unit":"sq_m","value":50000}],"milestones":[{"date":"2025-06-12","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2026-01","event":"permit_approved","kind":"actual","note":"Development approval announced on 19 January 2026; the approval date itself was not stated.","source_ids":["s2"]}],"name":"NEXTDC M4 Melbourne","parties":[{"name":"NEXTDC","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Victorian Government","note":"Granted development approval.","role":"government","source_ids":["s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-06-12","publisher":"NEXTDC","title":"NEXTDC Announces $2 Billion AI Factory and Technology Campus at Fishermans Bend","type":"company","url":"https://www.nextdc.com/news/nextdc-announces-2-billion-ai-factory-and-technology-campus-at-fishermans-bend"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260324052816/https://www.nextdc.com/news/m4-technology-campus-approved","id":"s2","published":"2026-01-19","publisher":"NEXTDC","title":"M4 Technology Campus Approved","type":"company","url":"https://www.nextdc.com/news/m4-technology-campus-approved"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260608053007/https://www.nextdc.com/data-centres/melbourne-data-centres/m4-melbourne","id":"s3","published":null,"publisher":"NEXTDC","title":"M4 Melbourne Data Centre","type":"company","url":"https://www.nextdc.com/data-centres/melbourne-data-centres/m4-melbourne"}],"status":"announced","status_as_of":"2026-01-19","status_source_ids":["s2"],"summary":"NEXTDC plans an AI factory and technology campus, called M4, on the former Westgate Park printing complex at 127 Todd Road in Port Melbourne's Fishermans Bend precinct. Announced in June 2025 as an A$2 billion project of up to 150 MW, designed for very high-density Nvidia-class AI racks and linked with university, defence and research partners, it received development approval from the Victorian Government by January 2026, when NEXTDC cited 162 MW. Construction timing has not been published.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"822a36e0-a36b-55dc-b617-b1f6f3fdeb48","s2":"c035f6ad-ba8f-544f-82b5-f1fd3afa8fb1","s3":"e1b7f87f-679a-5762-ad17-0fca03d9e04c"},"source_file":"datacenters/projects/nextdc-m4-port-melbourne.json","source_record_id":"nextdc-m4-port-melbourne","source_record_sha256":"6f7a67858387aa588a2888e9fa9aad66fc0faa8f8058ed30c3267a013360d62e","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1e5605f20f502c7f1a5e664d6e05704db6b4deae003c6b58f2c4736315a30533"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-78289e1b65e2284a986f/#project-869dffc7-22ea-5f40-8810-13d87c696908 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/869dffc7-22ea-5f40-8810-13d87c696908.json
86bcbcd1-702d-5afa-aeb8-1cb145224b97 | curated:microsoft-hebron-oh-datacenter:initial-site-preparation | vcc-site-1589f325b3b39da5fb19 | curated:microsoft-hebron-oh-datacenter | Microsoft Hebron Initial Site Preparation | United States | US | 39.972 | -82.4889 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 1de91fed-9b38-5c47-886d-5fa766be2aa0 | site_preparation | 2026-07-01 | 104 | authoritative_physical_status_update | 46947788-7664-564d-8408-61a49b6fc3ab | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://local.microsoft.com/blog/hebron-datacenter-construction-update/ | https://geocoding.geo.census.gov/geocoder/ | [{"identity_decision":{"decision":"multi_site_program","flags":["administrative_locator_not_project_geometry","multiple_sites_no_single_map_point"],"rationale":"Source explicitly describes separate Microsoft campuses in Heath, Hebron and New Albany. Each already has its own release identity and site locator; attach regional context to all three without merging their statuses or capacities. Source statement that no New Albany update was found differs from the release's July 2026 official New Albany observation.","related_project_stable_keys":["curated:microsoft-heath-oh-datacenter:initial-site-preparation","curated:microsoft-hebron-oh-datacenter:initial-site-preparation","curated:microsoft-new-albany-oh-datacenter:initial-site-preparation"],"source_record_id":"microsoft-licking-county-ohio"},"record":{"aliases":["Microsoft Heath datacenter","Microsoft Hebron datacenter","Microsoft New Albany datacenter"],"id":"microsoft-licking-county-ohio","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Licking County","country":"US","lat":40.1318,"lon":-82.4628,"note":"County centroid from Nominatim, because the record covers a three-site program in different municipalities (New Albany, Heath and Hebron). Microsoft's pages place the Heath construction entrance on Thornwood Drive and a temporary Hebron construction entrance on Canyon Road.","precision":"admin2","source_ids":["s1","s2","s6","s7"]},"metrics":[{"applies_to":"campus","as_of":"2024-10-28","basis":"announced","metric":"investment","note":"Initial investment announced for the three campuses together; no per-site split was given, and POWER does not say whether the New Albany USD 420 million is part of it.","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"USD","value":1000000000},{"applies_to":"phase","as_of":"2024-10","basis":"announced","metric":"investment","note":"New Albany's city council approved a 15-year, 100 percent property tax abatement for this building.","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s1","s2"],"unit":"USD","value":420000000},{"applies_to":"phase","as_of":"2025-04-10","basis":"planned","metric":"floor_area","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s2"],"unit":"sq_ft","value":245000},{"applies_to":"phase","as_of":"2025-04-10","basis":"reported","metric":"land_area","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":197}],"milestones":[{"date":"2024-10-28","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-04-07","event":"paused","kind":"actual","note":"Microsoft said it would not move forward at that time, would keep evaluating the sites, would make land at two sites farmable (Heath and Hebron, per ENR), and would still fund road and utility upgrades under its development agreements.","source_ids":["s2","s3","s4"]},{"date":"2026-02-24","event":"construction_started","kind":"actual","note":"Ceremonial groundbreaking at the Heath site off Thornwood Drive; Microsoft's Heath and Hebron pages report mass grading from February 2026 and tree clearing in March 2026.","source_ids":["s5","s6","s7"]},{"date":"2026-11","event":"other","kind":"planned","note":"Target finish of mass grading at Heath and Hebron; Microsoft says early site preparation should be largely done by year-end and has not set a vertical construction timeline.","source_ids":["s6","s7"]}],"name":"Microsoft Licking County three-site datacenter program (New Albany, Heath, Hebron)","notes":"This record groups three sites because the cited sources present them as one program under a single USD 1 billion announcement; split into per-site records if site-level power or investment figures are found. Status reflects site preparation at Heath and Hebron; the New Albany building was on hold as of April 2025 and no later update was found. status_as_of uses the first day of July 2026, the month of the latest entries on Microsoft's month-dated update pages.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2"]},{"name":"Microsoft","note":"ENR and Fox 28 report that Microsoft owns the Licking County sites and will keep the land.","role":"owner","source_ids":["s2","s3"]},{"name":"Ames Construction","note":"Contractor clearing the New Albany site before the 2025 pause (ENR) and main contractor for the Heath and Hebron site work in 2026 (Microsoft).","role":"builder","source_ids":["s2","s6","s7"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-10-28","publisher":"POWER Magazine","title":"Microsoft Announces $1 Billion Investment in Ohio Data Centers as Officials Ponder Power Demands","type":"trade_press","url":"https://www.powermag.com/microsoft-announces-1-billion-investment-in-ohio-data-centers-as-officials-ponder-power-demands"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260516063141/https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio","id":"s2","published":"2025-04-10","publisher":"Engineering News-Record","title":"Microsoft Hits Pause Button on $1B in Data Centers in Ohio","type":"trade_press","url":"https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio"},{"accessed":"2026-10-09","id":"s3","published":"2025-04-08","publisher":"WSYX/WTTE (Fox 28 Columbus)","title":"Microsoft 'not moving forward' with $1B Licking County data center plans right now","type":"news","url":"https://myfox28columbus.com/news/local/microsoft-backs-off-1b-licking-county-data-center-plans"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250410023315/https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/","id":"s4","published":"2025-04-09","publisher":"Associated Press (via News4JAX)","title":"Microsoft says it's 'slowing or pausing' some AI data center projects, including $1B plan for Ohio","type":"news","url":"https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260227140645/https://abc6onyourside.com/news/local/heath-columbus-ohio-break-ground-microsoft-data-center-expected-bring-hundreds-jobs-tech-technology-ai-artificial-intelligence-cloud-computing-digital-services","id":"s5","published":"2026-02-24","publisher":"WSYX ABC 6","title":"Heath breaks ground on Microsoft data center expected to bring hundreds of jobs","type":"news","url":"https://www.abc6onyourside.com/news/local/heath-columbus-ohio-break-ground-microsoft-data-center-expected-bring-hundreds-jobs-tech-technology-ai-artificial-intelligence-cloud-computing-digital-services"},{"accessed":"2026-10-09","id":"s6","published":"2026-07","publisher":"Microsoft Local","title":"Heath datacenter construction updates","type":"company","url":"https://local.microsoft.com/blog/heath-datacenter-construction-updates/"},{"accessed":"2026-10-09","id":"s7","published":"2026-07","publisher":"Microsoft Local","title":"Hebron datacenter construction update","type":"company","url":"https://local.microsoft.com/blog/hebron-datacenter-construction-update/"}],"status":"under_construction","status_as_of":"2026-07-01","status_source_ids":["s5","s6","s7"],"summary":"Three-site Microsoft datacenter program in Licking County, east of Columbus, Ohio, with separate campuses in New Albany, Heath and Hebron. Announced in October 2024 as an initial USD 1 billion investment for Azure cloud capacity, it included a USD 420 million, 245,000 sq ft building on 197 acres in New Albany. In April 2025 Microsoft paused the program, keeping the land and saying two sites would be made farmable. Work resumed in 2026: Heath broke ground in February, and Microsoft's Heath and Hebron pages report tree clearing, mass grading through November 2026 and planned substation work, with no vertical construction timeline. No 2026 update was found for New Albany.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"53a991df-b72c-5ce1-9102-4b2936f3ed84","s2":"3da0d477-2381-54c6-bca3-e3552b21b523","s3":"52512d65-d545-5d59-a6f4-27e8e186eaab","s4":"c9565490-4acd-5d00-97a2-af07b6b2aeae","s5":"c27c9dd5-6622-5355-bd70-7dc3d703241e","s6":"9b8c42cb-65b2-50cc-860d-bd61eed97709","s7":"6591b6d1-867c-59b3-aa1f-ddbe9c167308"},"source_file":"datacenters/projects/microsoft-licking-county-ohio.json","source_record_id":"microsoft-licking-county-ohio","source_record_sha256":"aa63c46124d3685f68abaa56575f892aa7a9a9c91345273642a9a103e42db940","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4efd2bbab8400f3312e0d7e8b453b7bf64695c7208d12e44522b6d32b8cd9cae"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1589f325b3b39da5fb19/#project-86bcbcd1-702d-5afa-aeb8-1cb145224b97 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/86bcbcd1-702d-5afa-aeb8-1cb145224b97.json
86c83f59-88b9-5791-bc15-ab6c32f256a7 | imported:semiconductor-atlas:hut8-beacon-point | vcc-site-a15d402305ed80ba8cba | curated:hut8-beacon-point-ai-data-center-campus | Hut 8 Beacon Point AI data center campus | United States | US | 27.74 | -97.52 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Filings name Nueces County only, with no town, address or parcel. Coordinates are the Nueces County point from its Wikipedia article. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 782f9d8b-cff9-52ea-aa39-5c0b7f15d328 | under_construction | 2026-08-04 | 70 | imported_documented_status | 4aa541b2-aec6-5f8e-a0e2-4026cf7bf141 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"782f9d8b-cff9-52ea-aa39-5c0b7f15d328","notes":"Develops the campus through its wholly owned subsidiary Beacon Point DC LLC, which issued the project notes.","party":"Hut 8","relationship_scope":"unknown","role":"developer","source_record_id":"hut8-beacon-point"},{"evidence_id":"4aa541b2-aec6-5f8e-a0e2-4026cf7bf141","notes":"Develops the campus through its wholly owned subsidiary Beacon Point DC LLC, which issued the project notes.","party":"Hut 8","relationship_scope":"unknown","role":"developer","source_record_id":"hut8-beacon-point"},{"evidence_id":"60c7066e-006c-536c-bb3c-20ae9774a0e9","notes":"Develops the campus through its wholly owned subsidiary Beacon Point DC LLC, which issued the project notes.","party":"Hut 8","relationship_scope":"unknown","role":"developer","source_record_id":"hut8-beacon-point"},{"evidence_id":"4aa541b2-aec6-5f8e-a0e2-4026cf7bf141","notes":"Provides electric delivery service under the campus interconnection agreement.","party":"AEP Texas","relationship_scope":"unknown","role":"utility","source_record_id":"hut8-beacon-point"},{"evidence_id":"48d9033d-fb4b-5857-8502-f645e3889cfc","notes":"Provides electric delivery service under the campus interconnection agreement.","party":"AEP Texas","relationship_scope":"unknown","role":"utility","source_record_id":"hut8-beacon-point"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.sec.gov/Archives/edgar/data/1964789/000110465926084862/tm2620835d1_ex99-1.htm | https://www.sec.gov/Archives/edgar/data/1964789/000110465926070744/tm2616926d1_ex99-1.htm | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Hut 8 Beacon Point campus and shared issuer quarterly source. Source includes both 352 MW phases and 1 GW utility capacity; existing project is explicitly the first 352 MW critical-IT lease build.","source_record_id":"hut8-beacon-point","target_physical_site_stable_key":"curated:hut8-beacon-point-ai-data-center-campus"},"record":{"aliases":["Beacon Point AI Data Center Campus","Beacon Point DC"],"id":"hut8-beacon-point","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Nueces County","country":"US","lat":27.74,"lon":-97.52,"note":"Filings name Nueces County only, with no town, address or parcel. Coordinates are the Nueces County point from its Wikipedia article.","precision":"admin2","source_ids":["s1","s2","s7"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-20","basis":"contracted","metric":"power_capacity","note":"Utility capacity secured under an interconnection agreement with AEP Texas; Hut 8 calls Beacon Point a 1 GW campus on this basis.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2","s4"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-07-20","basis":"contracted","metric":"power_capacity","note":"IT capacity leased to the single tenant across both phases after the second lease.","power_scope":"it_load","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":704},{"applies_to":"phase","as_of":"2026-07-20","basis":"under_construction","metric":"power_capacity","note":"Critical IT capacity of the first leased data center, across six data halls. The Energy Mag reports that a redesign raised the first building from 224 MW to 352 MW without more land or utility capacity.","phase_label":"Phase 1 (six data halls)","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":352},{"applies_to":"phase","as_of":"2026-05-06","basis":"contracted","metric":"power_capacity","note":"Share of the 1,000 MW utility capacity supporting the first 352 MW IT phase.","phase_label":"Phase 1","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s4"],"unit":"MW","value":500},{"applies_to":"phase","as_of":"2026-07-20","basis":"contracted","metric":"power_capacity","note":"Second 15-year lease with the same tenant; site preparation under way and long-lead equipment procured.","phase_label":"Phase 2","power_scope":"it_load","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":352},{"applies_to":"phase","as_of":"2026-08-04","basis":"under_construction","metric":"power_capacity","note":"Utility capacity for phase 2, which Hut 8 moved into its energy-capacity-under-construction category after 30 June 2026; it needs no capacity beyond the campus interconnection.","phase_label":"Phase 2","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2","s5"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-06-04","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":521}],"milestones":[{"date":"2026-05-06","event":"announced","kind":"actual","note":"Hut 8 announced the first 15-year, 352 MW IT lease, commercializing phase 1 of the campus.","source_ids":["s3","s4"]},{"date":"2026-06-09","event":"other","kind":"actual","note":"Hut 8 closed USD 4.25 billion of investment-grade project notes to finance construction of the Beacon Point data center.","source_ids":["s6"]},{"date":"2026-07-20","event":"expansion_announced","kind":"actual","note":"Second 352 MW IT lease signed with the existing tenant, fully committing the campus utility capacity. Hut 8 said phase 1 construction had already begun.","source_ids":["s2"]},{"date":"2027-Q1","event":"other","kind":"planned","note":"Target for initial energization of the first phase.","source_ids":["s2","s4"]},{"date":"2027-Q3","event":"first_operational","kind":"planned","note":"Target for delivery of the first data hall, as reported by The Energy Mag.","source_ids":["s4"]},{"date":"2028-Q2","event":"other","kind":"planned","note":"Target for delivery of the first phase 2 data hall.","source_ids":["s2"]}],"name":"Hut 8 Beacon Point AI data center campus","notes":"The tenant is not named; Hut 8 describes it as a high-investment-grade company (rated AA- or higher in the notes offering). Leases are triple-net with 15-year base terms worth USD 19.6 billion for the campus. Phase 1 is financed with USD 4.25 billion of non-recourse project notes issued by Beacon Point DC LLC; this is debt financing, not a disclosed project cost. The Energy Mag reports the site was first underwritten for affiliated miner American Bitcoin; Hut 8's releases opened do not say so. Hut 8 names AEP, Vertiv and Jacobs as delivery-model counterparties and an NVIDIA DSX reference design. The 1 GW label refers to utility capacity, not IT load.","parties":[{"name":"Hut 8","note":"Develops the campus through its wholly owned subsidiary Beacon Point DC LLC, which issued the project notes.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"AEP Texas","note":"Provides electric delivery service under the campus interconnection agreement.","role":"utility","source_ids":["s2","s4"]}],"power_sources":[{"description":"Grid supply from AEP Texas under a 1,000 MW interconnection agreement, with a substation being built on the property as part of the phase 1 project.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-06-04","publisher":"Hut 8 Corp. via SEC EDGAR","title":"Hut 8 announces pricing of $4.25 billion of investment-grade senior secured notes for Beacon Point data center project (Form 8-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1964789/000110465926070744/tm2616926d1_ex99-1.htm"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-20","publisher":"Hut 8 Corp. via SEC EDGAR","title":"Hut 8 fully commercializes 1 GW Beacon Point AI data center campus with second 352 MW IT lease, bringing campus-level base-term contract value to $19.6 billion (Form 8-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1964789/000110465926084862/tm2620835d1_ex99-1.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-05-06","publisher":"Hut 8","title":"Hut 8 commercializes first phase of 1 GW Beacon Point AI data center campus with 15-year, 352 MW IT lease","type":"company","url":"https://www.hut8.com/news-insights/press-releases/hut-8-commercializes-first-phase-of-1-gw-beacon-point-ai-data-center-campus-with-15-year-352-mw"},{"accessed":"2026-10-09","id":"s4","published":"2026-05-06","publisher":"The Energy Mag","title":"Hut 8 Surges 30% After Landing Second AI Data Center Lease Worth $9.8 Billion","type":"news","url":"https://www.theenergymag.com/news/2026-05-06/hut-ai-beacon-point"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007015824/https://www.hut8.com/news-insights/press-releases/hut-8-reports-second-quarter-2026-results","id":"s5","published":"2026-08-04","publisher":"Hut 8","title":"Hut 8 reports second quarter 2026 results","type":"company","url":"https://www.hut8.com/news-insights/press-releases/hut-8-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","id":"s6","published":"2026-06-09","publisher":"Hut 8","title":"Hut 8 closes $4.25 billion of investment-grade senior secured notes for Beacon Point data center project","type":"company","url":"https://www.hut8.com/news-insights/press-releases/hut-8-closes-usd4-25-billion-of-investment-grade-senior-secured-notes-for-beacon-point-data"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Wikipedia","title":"Nueces County, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Nueces_County,_Texas"}],"status":"under_construction","status_as_of":"2026-08-04","status_source_ids":["s2","s5"],"summary":"Hut 8 AI data center campus on about 521 acres in Nueces County, Texas, backed by 1,000 MW of utility capacity under an AEP Texas interconnection agreement. In 2026 Hut 8 signed two 15-year leases of 352 MW of IT capacity each with one unnamed high-investment-grade tenant, for 704 MW in total, worth about USD 9.8 billion each in base-term value. Hut 8 said in July 2026 that phase 1 construction had begun and phase 2 site preparation was under way; initial energization is targeted for Q1 2027 and the first phase 2 data hall for Q2 2028.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"782f9d8b-cff9-52ea-aa39-5c0b7f15d328","s2":"4aa541b2-aec6-5f8e-a0e2-4026cf7bf141","s3":"60c7066e-006c-536c-bb3c-20ae9774a0e9","s4":"48d9033d-fb4b-5857-8502-f645e3889cfc","s5":"54364762-f941-5711-a127-51429967cd42","s6":"67eec335-37c6-5d6f-a671-62c82981802a","s7":"4dbda20c-a924-5873-85a1-385bbea1f0b1"},"source_file":"datacenters/projects/hut8-beacon-point.json","source_record_id":"hut8-beacon-point","source_record_sha256":"e1cd61da260ce328a44132696eb80adcc8c25ff91b15c5f2cd3b9d2efba4718a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d8b20c31668fe64a618d09db8c4fde048f5a1629adca59b4d144c1c8b0696b70"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a15d402305ed80ba8cba/#project-86c83f59-88b9-5791-bc15-ab6c32f256a7 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/86c83f59-88b9-5791-bc15-ab6c32f256a7.json
8715738f-39ac-5058-a01a-b62758b49831 | curated:nextdc-m4-melbourne:initial-early-works | vcc-site-78289e1b65e2284a986f | curated:nextdc-m4-melbourne | NEXTDC M4 Initial Early Works | Australia | AU | -37.8287 | 144.9115 | Point | campus | exact_official_primary_virtual_address_point | preserve_Vicmap_PFI214016983_point_response_in_EPSG4326_bound_to_NEXTDC_M4_127_Todd_Road | official_virtual_address_campus_reference_point | official_source | campus_locator | Primary virtual address point for 127 Todd Road; source location descriptor PART is retained. The exact operator address and CP172440L government site record bind the campus. Not a surveyed entrance, full campus boundary, built footprint or June30 work extent; not the near-coincident non-primary entrance point. |  | No feature-specific quantitative positional-accuracy estimate is supplied by the selected point source. Coordinate digits are retained without asserting survey accuracy. | a53097c1-06e3-589b-9748-1e9a83879720 | site_preparation | 2026-06-30 | 105 | authoritative_physical_status_update | c39d71f0-c36f-5942-85a8-d7c235f5ea32 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nextdc.com/hubfs/Financial%20Reports/FY26/FY26%20Results%20Announcement.pdf | https://services-ap1.arcgis.com/P744lA0wf4LlBZ84/arcgis/rest/services/Vicmap_Address/FeatureServer/0/query?where=pfi%20IN%20%28%27214016983%27%2C%27460240432%27%29&outFields=*&outSR=4326&returnGeometry=true&f=pjson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-78289e1b65e2284a986f/#project-8715738f-39ac-5058-a01a-b62758b49831 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8715738f-39ac-5058-a01a-b62758b49831.json
88c15bf1-8080-55a3-b2cd-dbd795654bf3 | imported:semiconductor-atlas:aker-nscale-korgen | vcc-site-35381f89404ef4c2a035 | imported:semiconductor-atlas:aker-nscale-korgen | Aker Nscale Korgen AI data center | Norway | NO | 66.0766 | 13.8219 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Korgen village centroid from Nominatim; sources say the plot is in a designated area at Korgen, possibly at Nedre Røssåga power station, but do not give a parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 88844eaa-3de7-5991-bf0e-d3ddbfa00b26 | announced | 2025-10-27 | 351 | imported_documented_status | 88844eaa-3de7-5991-bf0e-d3ddbfa00b26 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"88844eaa-3de7-5991-bf0e-d3ddbfa00b26","notes":"Joint venture of Aker and Nscale when the plan was reported; Aker transferred its 50% stake in the joint venture to Nscale in March 2026.","party":"Aker Nscale","relationship_scope":"unknown","role":"developer","source_record_id":"aker-nscale-korgen"},{"evidence_id":"fc74fa9c-3425-5128-b333-43a97fd53e1e","notes":"Joint venture of Aker and Nscale when the plan was reported; Aker transferred its 50% stake in the joint venture to Nscale in March 2026.","party":"Aker Nscale","relationship_scope":"unknown","role":"developer","source_record_id":"aker-nscale-korgen"},{"evidence_id":"69e707d9-317c-5f3f-88da-1eb6dacf93e6","notes":"Joint venture of Aker and Nscale when the plan was reported; Aker transferred its 50% stake in the joint venture to Nscale in March 2026.","party":"Aker Nscale","relationship_scope":"unknown","role":"developer","source_record_id":"aker-nscale-korgen"},{"evidence_id":"c6592575-3334-52f2-8782-c978fa4bbbd4","notes":"Joint venture of Aker and Nscale when the plan was reported; Aker transferred its 50% stake in the joint venture to Nscale in March 2026.","party":"Aker Nscale","relationship_scope":"unknown","role":"developer","source_record_id":"aker-nscale-korgen"},{"evidence_id":"88844eaa-3de7-5991-bf0e-d3ddbfa00b26","notes":"Grid operator from which the project awaits a power allocation.","party":"Statnett","relationship_scope":"unknown","role":"utility","source_record_id":"aker-nscale-korgen"},{"evidence_id":"fc74fa9c-3425-5128-b333-43a97fd53e1e","notes":"Grid operator from which the project awaits a power allocation.","party":"Statnett","relationship_scope":"unknown","role":"utility","source_record_id":"aker-nscale-korgen"},{"evidence_id":"88844eaa-3de7-5991-bf0e-d3ddbfa00b26","notes":"Its proposed land-use plan zones the plot for commercial use.","party":"Hemnes Municipality","relationship_scope":"unknown","role":"government","source_record_id":"aker-nscale-korgen"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://en.highnorthnews.com/business/aker-nscale-planning-another-ai-data-center-in-northern-norway/118322 | https://en.highnorthnews.com/business/aker-nscale-planning-another-ai-data-center-in-northern-norway/118322 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Aker Nscale Korgen AI data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"aker-nscale-korgen"},"record":{"aliases":["Nscale Korgen"],"id":"aker-nscale-korgen","last_reviewed":"2026-10-09","location":{"admin1":"Nordland","admin2":"Hemnes Municipality","country":"NO","lat":66.0766,"locality":"Korgen","lon":13.8219,"note":"Korgen village centroid from Nominatim; sources say the plot is in a designated area at Korgen, possibly at Nedre Røssåga power station, but do not give a parcel.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2025-10-22","basis":"planned","metric":"power_capacity","note":"Estimate by Aker's investment director of the grid capacity the data center would use.","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s1","s2"],"unit":"MW","value":250},{"applies_to":"campus","as_of":"2025-10-27","basis":"reported","metric":"investment","note":"Figure appears in the trade press article's unattributed summary; the full text is paywalled and its basis is not explained.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":5400000000}],"milestones":[{"date":"2025-10-22","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-10","event":"other","kind":"actual","note":"Reported that Aker Nscale had bought out Nordkraft's position, including the option on a plot next to Statkraft's facility that Nordkraft had held since 2019, and taken over the landowner agreements.","source_ids":["s1"]},{"date":"2025-10","event":"other","kind":"actual","note":"Grid power application delayed by zoning; the project was waiting in line for a Statnett allocation.","source_ids":["s1","s2"]},{"date":"2026-03-27","event":"other","kind":"actual","note":"Aker transferred its 50% stake in the Aker Nscale joint venture to Nscale; the release does not mention Korgen.","source_ids":["s4"]}],"name":"Aker Nscale Korgen AI data center","parties":[{"name":"Aker Nscale","note":"Joint venture of Aker and Nscale when the plan was reported; Aker transferred its 50% stake in the joint venture to Nscale in March 2026.","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Statnett","note":"Grid operator from which the project awaits a power allocation.","role":"utility","source_ids":["s1","s2"]},{"name":"Hemnes Municipality","note":"Its proposed land-use plan zones the plot for commercial use.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Planned grid draw of about 250 MW subject to a Statnett allocation; the site may sit at the Nedre Røssåga power station.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260418113408/https://en.highnorthnews.com/business/aker-nscale-planning-another-ai-data-center-in-northern-norway/118322","id":"s1","published":"2025-10-22","publisher":"High North News","title":"Aker Nscale Planning Another AI Data Center in Northern Norway","type":"news","url":"https://en.highnorthnews.com/business/aker-nscale-planning-another-ai-data-center-in-northern-norway/118322"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251214074501/https://www.datacenter-forum.com/nscale/aker-nscale-plans-to-build-large-ai-data-center-in-northern-norway","id":"s2","published":"2025-10","publisher":"Datacenter Forum","title":"Aker Nscale plans to build large AI data center in northern Norway","type":"trade_press","url":"https://www.datacenter-forum.com/nscale/aker-nscale-plans-to-build-large-ai-data-center-in-northern-norway"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-27","publisher":"The Tech Capital","title":"Nscale expands AI infrastructure with new 250 MW data centre project in Norway","type":"trade_press","url":"https://thetechcapital.com/nscale-expands-ai-infrastructure-with-new-250-mw-data-centre-project-in-norway/"},{"accessed":"2026-10-09","id":"s4","published":"2026-03-27","publisher":"Aker ASA (via Placera)","title":"Aker completes investment in Nscale's Series C funding round","type":"company","url":"https://www.placera.se/pressmeddelanden/aker-aker-completes-investment-in-nscales-series-c-funding-round-20260327"}],"status":"announced","status_as_of":"2025-10-27","status_source_ids":["s1","s2","s3"],"summary":"Aker Nscale, then a joint venture of Aker and Nscale, plans an AI data center at Korgen in Hemnes municipality, Nordland, possibly at Statkraft's Nedre Røssåga power station. In October 2025 an Aker investment director estimated the site would draw about 250 MW of grid capacity and said it could be as large as the Narvik project. Aker Nscale had bought out Nordkraft's position and landowner agreements for a plot zoned for commercial use in Hemnes's proposed land-use plan, and was waiting in line for a Statnett power allocation. Trade press put the project at about USD 5.4bn. Aker passed its joint-venture stake to Nscale in March 2026; no later Korgen-specific update was found.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"88844eaa-3de7-5991-bf0e-d3ddbfa00b26","s2":"fc74fa9c-3425-5128-b333-43a97fd53e1e","s3":"69e707d9-317c-5f3f-88da-1eb6dacf93e6","s4":"c6592575-3334-52f2-8782-c978fa4bbbd4"},"source_file":"datacenters/projects/aker-nscale-korgen.json","source_record_id":"aker-nscale-korgen","source_record_sha256":"d6cd136c42be7d540228829d64ff514bd857653eb7b2974369781012a8d0f775","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"503b32dd135f5fe7679802d2ab9ad4eda2bfb77b188ea5de8830a7d7cfeb20f7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-35381f89404ef4c2a035/#project-88c15bf1-8080-55a3-b2cd-dbd795654bf3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/88c15bf1-8080-55a3-b2cd-dbd795654bf3.json
892af381-b656-528b-a9db-61013937174e | imported:semiconductor-atlas:google-franklin-township-indianapolis | vcc-site-65784844ad2a20822ec7 | imported:semiconductor-atlas:google-franklin-township-indianapolis | Google Franklin Township data center proposal (Project Flo) | United States | US | 39.6803 | -86.0275 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Franklin Township coordinates from its Wikipedia page. Sources name the township but give no parcel location, so the site is not pinpointed. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 40118eda-3e71-5638-a2a0-cdcd65a28e83 | cancelled | 2025-09-22 | 386 | imported_documented_status | 40118eda-3e71-5638-a2a0-cdcd65a28e83 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"40118eda-3e71-5638-a2a0-cdcd65a28e83","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-franklin-township-indianapolis"},{"evidence_id":"5090fec0-8412-51ee-8d76-703cfbc8650e","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-franklin-township-indianapolis"},{"evidence_id":"5090fec0-8412-51ee-8d76-703cfbc8650e","notes":"Described by Baxtel as the Google affiliate through which the proposal was made.","party":"Deep Meadow Ventures LLC","relationship_scope":"unknown","role":"developer","source_record_id":"google-franklin-township-indianapolis"},{"evidence_id":"40118eda-3e71-5638-a2a0-cdcd65a28e83","notes":"Approved the rezoning request on 20 August 2025.","party":"Indianapolis Metropolitan Development Commission","relationship_scope":"unknown","role":"government","source_record_id":"google-franklin-township-indianapolis"},{"evidence_id":"40118eda-3e71-5638-a2a0-cdcd65a28e83","notes":"Scheduled a public hearing on the rezoning (Proposal No. 306); Google withdrew before a vote.","party":"Indianapolis City-County Council","relationship_scope":"unknown","role":"government","source_record_id":"google-franklin-township-indianapolis"},{"evidence_id":"7238fb6f-930b-5fb5-904e-a2c74ab5909a","notes":"Scheduled a public hearing on the rezoning (Proposal No. 306); Google withdrew before a vote.","party":"Indianapolis City-County Council","relationship_scope":"unknown","role":"government","source_record_id":"google-franklin-township-indianapolis"},{"evidence_id":"cda4ee4b-00cd-51d5-93ad-d97b25baf745","notes":"Scheduled a public hearing on the rezoning (Proposal No. 306); Google withdrew before a vote.","party":"Indianapolis City-County Council","relationship_scope":"unknown","role":"government","source_record_id":"google-franklin-township-indianapolis"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.insideindianabusiness.com/?p=191728 | https://www.insideindianabusiness.com/?p=191728 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Google Franklin Township data center proposal (Project Flo) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"google-franklin-township-indianapolis"},"record":{"aliases":["Project Flo"],"id":"google-franklin-township-indianapolis","last_reviewed":"2026-10-09","location":{"admin1":"Indiana","admin2":"Marion County","country":"US","lat":39.6803,"locality":"Franklin Township, Indianapolis","lon":-86.0275,"note":"Coordinates are the Franklin Township coordinates from its Wikipedia page. Sources name the township but give no parcel location, so the site is not pinpointed.","precision":"locality","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-09-22","basis":"reported","metric":"investment","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2025-09-22","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2","s3","s4"],"unit":"acres","value":468}],"milestones":[{"date":"2025-08-20","event":"zoning_approved","kind":"actual","note":"Approval by the Metropolitan Development Commission, later called up for review by the City-County Council.","source_ids":["s1"]},{"date":"2025-09-22","event":"cancelled","kind":"actual","note":"Google's attorney announced the withdrawal of the rezoning petition at the City-County Council meeting.","source_ids":["s1","s2","s3"]}],"name":"Google Franklin Township data center proposal (Project Flo)","notes":"The Metropolitan Development Commission's rules allowed Google to refile after three months; no refiling was found in the sources reviewed as of October 2026. Baxtel's undated third-party listing (accessed 2026-10-09) shows the project as withdrawn.","parties":[{"name":"Google","role":"developer","source_ids":["s1","s4"]},{"name":"Deep Meadow Ventures LLC","note":"Described by Baxtel as the Google affiliate through which the proposal was made.","role":"developer","source_ids":["s4"]},{"name":"Indianapolis Metropolitan Development Commission","note":"Approved the rezoning request on 20 August 2025.","role":"government","source_ids":["s1"]},{"name":"Indianapolis City-County Council","note":"Scheduled a public hearing on the rezoning (Proposal No. 306); Google withdrew before a vote.","role":"government","source_ids":["s1","s2","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-09-22","publisher":"Inside INdiana Business (Indianapolis Business Journal)","title":"Google to withdraw rezoning request for data center in Franklin Township","type":"news","url":"https://www.insideindianabusiness.com/?p=191728"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-22","publisher":"Mirror Indy","title":"Southsiders prevail in fight against Google data center","type":"news","url":"https://mirrorindy.org/google-withdraws-southside-data-center-proposal-franklin-township/"},{"accessed":"2026-10-09","id":"s3","published":"2025-09-23","publisher":"WRTV Indianapolis","title":"Google withdraws rezoning petition for proposed data center in Franklin Township","type":"news","url":"https://www.wrtv.com/news/local-news/google-withdraws-rezoning-petition-for-proposed-data-center-in-franklin-township"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Baxtel","title":"Google: Indianapolis (Project Flo) Data Center","type":"other","url":"https://baxtel.com/data-center/google-indianapolis-project-flo"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Franklin Township, Marion County, Indiana","type":"other","url":"https://en.wikipedia.org/wiki/Franklin_Township,_Marion_County,_Indiana"}],"status":"cancelled","status_as_of":"2025-09-22","status_source_ids":["s1","s2"],"summary":"Proposed Google data center on about 468 acres of farmland in Franklin Township on the southeast side of Indianapolis, reported as a USD 1 billion project; tracker Baxtel says Google proposed it through an affiliate, Deep Meadow Ventures. The Metropolitan Development Commission approved the rezoning in August 2025, but the City-County Council scheduled its own public hearing amid opposition from residents worried about water use, flooding and electricity bills. Google's attorney announced the withdrawal of the rezoning petition at the council meeting on 22 September 2025. No later refiling was found.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"40118eda-3e71-5638-a2a0-cdcd65a28e83","s2":"7238fb6f-930b-5fb5-904e-a2c74ab5909a","s3":"cda4ee4b-00cd-51d5-93ad-d97b25baf745","s4":"5090fec0-8412-51ee-8d76-703cfbc8650e","s5":"dd391866-8cf7-5f8b-8225-ffd8c17bee64"},"source_file":"datacenters/projects/google-franklin-township-indianapolis.json","source_record_id":"google-franklin-township-indianapolis","source_record_sha256":"b7595a098a35f148c2c4d1a1bd778e9048b803747881762428f236a5a5dc8120","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d62835d6345deff459e3f4590dc504bb0f455f540e3328a806a60b43e7110bdc"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-65784844ad2a20822ec7/#project-892af381-b656-528b-a9db-61013937174e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/892af381-b656-528b-a9db-61013937174e.json
898b0895-99d6-545b-8053-79813ae63ffa | curated:envia-tel-datacenter-leipzig-campus:leipzig-2-fourth-section-current-build | vcc-site-6d5b0030886927a4cf46 | curated:envia-tel-datacenter-leipzig-campus | envia TEL Leipzig2 Fourth Section Current Construction | Germany | DE | 51.3727 | 12.4728 | Point | campus | Nominatim centroid of exact address named OSM building; axis reorder only | community_named_exact_address_constituent_building_centroid | constituent_building_point_for_shared_campus | community_source | campus_locator | Literal provider precision retained; constituent building centroid only. Not a fourth-section footprint, official survey, cadastral parcel, whole-campus boundary, headquarters, road or entrance. |  | Neither OSM object nor Nominatim response supplies positional accuracy. Decimal places and centroid semantics are not accuracy. | ad832a5d-9162-5c63-a11b-673cbc572545 | under_construction | 2026-05-27 | 139 | authoritative_physical_status_update | ebae5423-e4f4-5190-b3ff-ef2ce09c7d75 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.enviatel.de/presse-events/pm/PM/2026/05/27/envia-tel-schafft-sichere-digitale-infrastrukturen-f%C3%BCr-mitteldeutschland | https://nominatim.openstreetmap.org/search?street=116a%20Leipziger%20Stra%C3%9Fe&city=Taucha&country=Germany&postalcode=04425&format=jsonv2&polygon_geojson=1&addressdetails=1&extratags=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6d5b0030886927a4cf46/#project-898b0895-99d6-545b-8053-79813ae63ffa | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/898b0895-99d6-545b-8053-79813ae63ffa.json
8a5fbd17-48b6-5484-8c37-ce406068bf3e | curated:nextdc-s3-sydney:incremental-in-progress-fit-out | vcc-site-bf97558b9c05a083995c | curated:nextdc-s3-sydney | NEXTDC S3 Incremental In-Progress Fit-Out | Australia | AU | -33.8191 | 151.1846 | Point | campus | community_exact_address_named_campus_representative_point | preserve_Nominatim_way1225879499_lat_lon_and_bind_S3_operator_URL_ref_and_exact_2_Broadcast_Way_address | community_campus_reference_point | community_source | campus_locator | The named S3 community feature includes exact operator, facility URL, ref S3 and 2 Broadcast Way address. Its Sidney spelling is a source label, not a new campus. Adjacent S6 is not separately counted. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate. |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | 22eac0e1-71fa-59dd-a6d7-4378a663ab9d | mep_electrical | 2026-06-30 | 105 | authoritative_physical_status_update | 43bd6a30-6bac-5500-afd1-74b0e425d6b0 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nextdc.com/hubfs/Financial%20Reports/FY26/FY26%20Results%20Announcement.pdf | https://nominatim.openstreetmap.org/search?q=NEXTDC%20S3&format=jsonv2&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bf97558b9c05a083995c/#project-8a5fbd17-48b6-5484-8c37-ce406068bf3e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8a5fbd17-48b6-5484-8c37-ce406068bf3e.json
8aa8e9f5-915e-51f6-bc08-463822cf16f9 | imported:semiconductor-atlas:hut8-river-bend-louisiana | vcc-site-1f215e81ecc04c69b5d6 | curated:hut8-river-bend-ai-data-center-campus | Hut 8 River Bend AI data center campus | United States | US | 30.87 | -91.42 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Parish coordinates from Wikipedia; the sources name the parish but not a street address or town. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 932ebe4b-b0e1-5949-9d37-8cdc24107263 | under_construction | 2026-10-05 | 8 | imported_documented_status | 0dd7a6bd-41cb-5875-a335-cd3a5bf7fc2f | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"34c18a94-daee-58ac-a05d-5e7953ceeffb","notes":null,"party":"Hut 8","relationship_scope":"unknown","role":"developer","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"932ebe4b-b0e1-5949-9d37-8cdc24107263","notes":null,"party":"Hut 8","relationship_scope":"unknown","role":"developer","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"9b3fe3a6-8cd3-5ca4-a84b-c6c3023d721c","notes":null,"party":"Hut 8","relationship_scope":"unknown","role":"developer","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"932ebe4b-b0e1-5949-9d37-8cdc24107263","notes":"Phase I tenant for 245 MW of critical IT load; holds a right of first offer on expansion capacity.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"9b3fe3a6-8cd3-5ca4-a84b-c6c3023d721c","notes":"Phase I tenant for 245 MW of critical IT load; holds a right of first offer on expansion capacity.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"3a625ff7-d3f3-5a72-bdb7-713ce15a8145","notes":"Phase I tenant for 245 MW of critical IT load; holds a right of first offer on expansion capacity.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"61f0da8a-025f-50f1-b3da-32ba0a073c46","notes":"Reported end user of the capacity leased to Fluidstack: the Motley Fool says the infrastructure will be delivered to Anthropic and WAFB says the facility will serve Claude. Hut 8's release headline announces a partnership with Anthropic and Fluidstack, but its text could not be read, so Anthropic's role at River Bend is not confirmed by the companies in the sources reviewed.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"b3252878-e738-59ab-82da-7b01f9adbdc3","notes":"Reported end user of the capacity leased to Fluidstack: the Motley Fool says the infrastructure will be delivered to Anthropic and WAFB says the facility will serve Claude. Hut 8's release headline announces a partnership with Anthropic and Fluidstack, but its text could not be read, so Anthropic's role at River Bend is not confirmed by the companies in the sources reviewed.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"0dd7a6bd-41cb-5875-a335-cd3a5bf7fc2f","notes":"Reported end user of the capacity leased to Fluidstack: the Motley Fool says the infrastructure will be delivered to Anthropic and WAFB says the facility will serve Claude. Hut 8's release headline announces a partnership with Anthropic and Fluidstack, but its text could not be read, so Anthropic's role at River Bend is not confirmed by the companies in the sources reviewed.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"932ebe4b-b0e1-5949-9d37-8cdc24107263","notes":null,"party":"Entergy Louisiana","relationship_scope":"unknown","role":"utility","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"9b3fe3a6-8cd3-5ca4-a84b-c6c3023d721c","notes":null,"party":"Entergy Louisiana","relationship_scope":"unknown","role":"utility","source_record_id":"hut8-river-bend-louisiana"},{"evidence_id":"932ebe4b-b0e1-5949-9d37-8cdc24107263","notes":"Its secretary was quoted in the announcement and it estimated the indirect jobs; Hut 8 is expected to use the state sales and use tax rebate on data center equipment and the Quality Jobs program.","party":"Louisiana Economic Development","relationship_scope":"unknown","role":"government","source_record_id":"hut8-river-bend-louisiana"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | Anthropic; Fluidstack |  | https://www.wafb.com/2026/10/05/first-look-west-felicianas-data-center/ | https://www.expansionsolutionsmagazine.com/hut-8-selects-southeast-louisiana-for-10b-ai-data-center-campus/ | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Hut 8 River Bend campus in West Feliciana Parish and shared issuer quarterly source. Source combines phase I 245 MW critical IT with potential 1 GW campus growth; existing record is the scoped 245 MW current build.","source_record_id":"hut8-river-bend-louisiana","target_physical_site_stable_key":"curated:hut8-river-bend-ai-data-center-campus"},"record":{"aliases":["River Bend campus"],"id":"hut8-river-bend-louisiana","last_reviewed":"2026-10-09","location":{"admin1":"Louisiana","admin2":"West Feliciana Parish","country":"US","lat":30.87,"lon":-91.42,"note":"Parish coordinates from Wikipedia; the sources name the parish but not a street address or town.","precision":"admin2","source_ids":["s3","s4","s7","s8"]},"metrics":[{"applies_to":"phase","as_of":"2025-12-17","basis":"contracted","metric":"power_capacity","phase_label":"Phase I (Fluidstack lease)","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s4"],"unit":"MW","value":245},{"applies_to":"phase","as_of":"2025-12-17","basis":"planned","metric":"power_capacity","note":"Initial utility capacity from Entergy Louisiana.","phase_label":"Phase I","power_scope":"grid_connection","qualifier":"exact","source_ids":["s3","s4"],"unit":"MW","value":330},{"applies_to":"campus","as_of":"2025-12-17","basis":"planned","metric":"power_capacity","note":"Announcement materials say the campus could scale to 1,000 MW of utility capacity; Hut 8's August 2026 results describe 1,000 MW of potential expansion capacity at River Bend subject to added power.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s3","s4","s6"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2025-12-17","basis":"planned","metric":"power_capacity","note":"Motley Fool says Hut 8 and Fluidstack could deliver as much as 2,295 MW of AI data center infrastructure to Anthropic at River Bend. This exceeds the 1,000 MW utility scale-up cited by other sources, and Hut 8 material that could be read does not state it.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s5"],"unit":"MW","value":2295},{"applies_to":"phase","as_of":"2025-12-17","basis":"announced","metric":"investment","phase_label":"Phase I","qualifier":"up_to","source_ids":["s3","s4"],"unit":"USD","value":10000000000},{"applies_to":"phase","as_of":"2025-12-17","basis":"planned","metric":"jobs_construction","phase_label":"Phase I peak","qualifier":"approximately","source_ids":["s3","s4"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2026-10-05","basis":"reported","metric":"jobs_construction","note":"Construction workers reported on site in October 2026.","qualifier":"exact","source_ids":["s7"],"unit":"count","value":1200},{"applies_to":"phase","as_of":"2025-12-17","basis":"planned","metric":"jobs_permanent","phase_label":"Phase I","qualifier":"at_least","source_ids":["s3","s4"],"unit":"count","value":75}],"milestones":[{"date":"2025-12-17","event":"announced","kind":"actual","source_ids":["s1","s3"]},{"date":"2027-Q2","event":"first_operational","kind":"planned","note":"Target at announcement; WAFB reported in October 2026 that the facility is expected to be operational by the end of 2027.","source_ids":["s3","s4","s7"]}],"name":"Hut 8 River Bend AI data center campus","parties":[{"name":"Hut 8","role":"developer","source_ids":["s1","s3","s4"]},{"name":"Fluidstack","note":"Phase I tenant for 245 MW of critical IT load; holds a right of first offer on expansion capacity.","role":"tenant","source_ids":["s3","s4","s6"]},{"name":"Anthropic","note":"Reported end user of the capacity leased to Fluidstack: the Motley Fool says the infrastructure will be delivered to Anthropic and WAFB says the facility will serve Claude. Hut 8's release headline announces a partnership with Anthropic and Fluidstack, but its text could not be read, so Anthropic's role at River Bend is not confirmed by the companies in the sources reviewed.","role":"tenant","source_ids":["s2","s5","s7"]},{"name":"Entergy Louisiana","role":"utility","source_ids":["s3","s4"]},{"name":"Louisiana Economic Development","note":"Its secretary was quoted in the announcement and it estimated the indirect jobs; Hut 8 is expected to use the state sales and use tax rebate on data center equipment and the Quality Jobs program.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"Entergy Louisiana is to supply an initial 330 MW, with possible growth to 1,000 MW; WAFB reports a new on-site substation being built with Entergy and funded by the company.","source_ids":["s4","s7"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-12-17","publisher":"Hut 8","title":"Hut 8 Signs 15-Year, 245 MW AI Data Center Lease at River Bend Campus with Total Contract Value of $7.0 Billion","type":"company","url":"https://www.hut8.com/news-insights/press-releases/hut-8-signs-15-year-245-mw-ai-data-center-lease-at-river-bend-campus-with-total-contract-value"},{"accessed":"2026-10-09","id":"s2","published":"2025-12-17","publisher":"Hut 8","title":"Hut 8 Announces AI Infrastructure Partnership with Anthropic and Fluidstack","type":"company","url":"https://www.hut8.com/news-insights/press-releases/hut-8-announces-ai-infrastructure-partnership-with-anthropic-and-fluidstack"},{"accessed":"2026-10-09","id":"s3","published":"2025-12-17","publisher":"Expansion Solutions Magazine","title":"Hut 8 Selects Southeast Louisiana for $10B AI Data Center Campus","type":"trade_press","url":"https://www.expansionsolutionsmagazine.com/hut-8-selects-southeast-louisiana-for-10b-ai-data-center-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251230201057/https://www.tdworld.com/smart-utility/news/55339947/hut-8-selects-entergy-southeast-louisiana-for-10-billion-artificial-intelligence-data-center","id":"s4","published":"2025-12-22","publisher":"T&D World","title":"Hut 8 Selects Entergy, Southeast Louisiana for $10 Billion Artificial Intelligence Data Center","type":"trade_press","url":"https://www.tdworld.com/smart-utility/news/55339947/hut-8-selects-entergy-southeast-louisiana-for-10-billion-artificial-intelligence-data-center"},{"accessed":"2026-10-09","id":"s5","published":"2025-12-18","publisher":"The Motley Fool (via Yahoo Finance)","title":"Why Hut 8 Stock Popped Today","type":"news","url":"https://finance.yahoo.com/news/why-hut-8-stock-popped-005207470.html"},{"accessed":"2026-10-09","id":"s6","published":"2026-08-04","publisher":"Hut 8","title":"Hut 8 Reports Second Quarter 2026 Results","type":"company","url":"https://www.hut8.com/news-insights/press-releases/hut-8-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007003735/https://www.wafb.com/2026/10/05/first-look-west-felicianas-data-center/","id":"s7","published":"2026-10-05","publisher":"WAFB","title":"First Look: West Feliciana's data center","type":"news","url":"https://www.wafb.com/2026/10/05/first-look-west-felicianas-data-center/"},{"accessed":"2026-10-09","id":"s8","published":null,"publisher":"Wikipedia","title":"West Feliciana Parish, Louisiana","type":"other","url":"https://en.wikipedia.org/wiki/West_Feliciana_Parish,_Louisiana"}],"status":"under_construction","status_as_of":"2026-10-05","status_source_ids":["s7","s4"],"summary":"AI data center campus under construction by Hut 8 in West Feliciana Parish, Louisiana. Phase I is leased to Fluidstack for 245 MW of critical IT load under a 15-year lease valued at $7.0 billion, with Google backstopping the lease obligations; Hut 8 announced a partnership with Anthropic and Fluidstack the same day, and news reports say the capacity is for Anthropic. Entergy Louisiana is to supply an initial 330 MW, with potential to scale to 1,000 MW. Phase I investment is up to $10 billion. Local reporting in October 2026 counted about 1,200 construction workers on site and said the facility will serve Anthropic's Claude.","workloads":["ai_training","ai_inference"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"34c18a94-daee-58ac-a05d-5e7953ceeffb","s2":"61f0da8a-025f-50f1-b3da-32ba0a073c46","s3":"932ebe4b-b0e1-5949-9d37-8cdc24107263","s4":"9b3fe3a6-8cd3-5ca4-a84b-c6c3023d721c","s5":"b3252878-e738-59ab-82da-7b01f9adbdc3","s6":"3a625ff7-d3f3-5a72-bdb7-713ce15a8145","s7":"0dd7a6bd-41cb-5875-a335-cd3a5bf7fc2f","s8":"db8a5f41-54a7-5429-a346-43a9dcef1a7f"},"source_file":"datacenters/projects/hut8-river-bend-louisiana.json","source_record_id":"hut8-river-bend-louisiana","source_record_sha256":"fb7eeaf52bb6e7789effaf24b3ee0bb7e31922a38047e56ede8f20f89e9b204a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a57ccc13004e57961708a310b651c4b92ffd423c798405ef1944b84fd1f8f50e"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1f215e81ecc04c69b5d6/#project-8aa8e9f5-915e-51f6-bc08-463822cf16f9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8aa8e9f5-915e-51f6-bc08-463822cf16f9.json
8ac449d0-47a8-5735-a32a-d4eb2a6def53 | imported:semiconductor-atlas:tract-morris-technology-park | vcc-site-6e1076932d6836b39df9 | imported:semiconductor-atlas:tract-morris-technology-park | Morris Technology Park | United States | US | 41.38 | -88.4244 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Morris. Bisnow places the parcel off Interstate 80 in Morris but gives no address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 448aa44d-8acb-5a23-ace6-59eb47fbba83 | announced | 2026-01-27 | 259 | imported_documented_status | 448aa44d-8acb-5a23-ace6-59eb47fbba83 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"448aa44d-8acb-5a23-ace6-59eb47fbba83","notes":"Bought the site through an affiliate.","party":"Tract","relationship_scope":"unknown","role":"developer","source_record_id":"tract-morris-technology-park"},{"evidence_id":"448aa44d-8acb-5a23-ace6-59eb47fbba83","notes":"Party to a transmission security agreement for the site.","party":"ComEd","relationship_scope":"unknown","role":"utility","source_record_id":"tract-morris-technology-park"},{"evidence_id":"448aa44d-8acb-5a23-ace6-59eb47fbba83","notes":"Granted city approval for the project in 2025.","party":"City of Morris","relationship_scope":"unknown","role":"government","source_record_id":"tract-morris-technology-park"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.bisnow.com/news/chicago/data-center-capital-markets/data-center-infrastructure-developer-takes-343-acre-chicago-area-swing-132919 | https://www.bisnow.com/news/chicago/data-center-capital-markets/data-center-infrastructure-developer-takes-343-acre-chicago-area-swing-132919 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Morris Technology Park as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"tract-morris-technology-park"},"record":{"aliases":["Tract Morris data center park"],"id":"tract-morris-technology-park","last_reviewed":"2026-10-09","location":{"admin1":"Illinois","admin2":"Grundy County","country":"US","lat":41.38,"locality":"Morris","lon":-88.4244,"note":"Wikipedia coordinates for Morris. Bisnow places the parcel off Interstate 80 in Morris but gives no address.","precision":"locality","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-27","basis":"planned","metric":"power_capacity","note":"Tract targets a full 1 GW load ramp by 2032.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-01-27","basis":"acquired","metric":"land_area","note":"Purchase from an affiliate of Clarius Partners for about USD 51.5 million, per public records cited by Bisnow; the article gives no closing date.","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":343},{"applies_to":"campus","as_of":"2026-01-27","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s1"],"unit":"sq_ft","value":2900000}],"milestones":[{"date":"2025","event":"zoning_approved","kind":"actual","note":"City approval reported without a month. The year is derived: Bisnow's January 2026 article says approval came last year.","source_ids":["s1"]},{"date":"2028-06","event":"first_operational","kind":"planned","note":"Target for initial energization.","source_ids":["s1"]},{"date":"2032","event":"fully_operational","kind":"planned","note":"Target for reaching the full 1 GW load.","source_ids":["s1"]}],"name":"Morris Technology Park","parties":[{"name":"Tract","note":"Bought the site through an affiliate.","role":"developer","source_ids":["s1"]},{"name":"ComEd","note":"Party to a transmission security agreement for the site.","role":"utility","source_ids":["s1"]},{"name":"City of Morris","note":"Granted city approval for the project in 2025.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"ComEd transmission service under a transmission security agreement.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-27","publisher":"Bisnow","title":"Data Center Infrastructure Developer Takes 343-Acre Chicago-Area Swing","type":"trade_press","url":"https://www.bisnow.com/news/chicago/data-center-capital-markets/data-center-infrastructure-developer-takes-343-acre-chicago-area-swing-132919"}],"status":"announced","status_as_of":"2026-01-27","status_source_ids":["s1"],"summary":"Data center land developer Tract, through an affiliate, bought 343 acres of vacant farmland off Interstate 80 in Morris, Grundy County, Illinois, about 65 miles from downtown Chicago, for a planned 1 GW data center campus of roughly 2.9 million square feet. The project won city approval in 2025, the site is annexed and zoned for it, and it has a transmission security agreement with ComEd. Tract targets initial energization in June 2028 and a full 1 GW load by 2032. Tract's model is to entitle and service raw land and then offer it to large data center users or developers; no end user has been named for this site."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"448aa44d-8acb-5a23-ace6-59eb47fbba83"},"source_file":"datacenters/projects/tract-morris-technology-park.json","source_record_id":"tract-morris-technology-park","source_record_sha256":"1d63fcf09122631902f7dd47c05423b3dadd6fc0161ea4a3e02e2653e52c8001","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"51240dc2bc5887b2f3dd259dcb6f78db220061c3a732903a810818147bb404ec"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6e1076932d6836b39df9/#project-8ac449d0-47a8-5735-a32a-d4eb2a6def53 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8ac449d0-47a8-5735-a32a-d4eb2a6def53.json
8c2ed321-ddad-5bb1-ab38-bd5b66bf4f2b | imported:semiconductor-atlas:adaniconnex-noida | vcc-site-c4475d593124b26a70cd | imported:semiconductor-atlas:adaniconnex-noida | AdaniConneX Noida data centre campus | India | IN | 28.57 | 77.32 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Noida only. Coordinates are the Noida city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d9f7e0af-ae46-5af6-9d9a-39f54b5b80fd | partially_operational | 2026-10-09 | 4 | imported_documented_status | d9f7e0af-ae46-5af6-9d9a-39f54b5b80fd | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d9f7e0af-ae46-5af6-9d9a-39f54b5b80fd","notes":null,"party":"AdaniConneX","relationship_scope":"unknown","role":"developer","source_record_id":"adaniconnex-noida"},{"evidence_id":"c57836f8-858f-57cd-887e-45098a9fd5c8","notes":null,"party":"AdaniConneX","relationship_scope":"unknown","role":"developer","source_record_id":"adaniconnex-noida"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.adaniconnex.com/data-centers | https://www.adaniconnex.com/data-centers | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AdaniConneX Noida data centre campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"adaniconnex-noida","source_relations":[{"reason":"Distinct AdaniConneX and Sify named developments; exactly shared coordinates are Noida city locators.","relationship":"separate_named_developments","source_id":"sify-noida-02"}]},"record":{"aliases":[],"id":"adaniconnex-noida","last_reviewed":"2026-10-09","location":{"admin1":"Uttar Pradesh","admin2":"Gautam Buddha Nagar","country":"IN","lat":28.57,"locality":"Noida","lon":77.32,"note":"Sources name Noida only. Coordinates are the Noida city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"power_capacity","note":"Listed by the company as potential capacity in IT load.","power_scope":"it_load","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"phase","as_of":"2023-06-23","basis":"under_construction","metric":"power_capacity","phase_label":"Build financed in June 2023","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":50}],"milestones":[{"date":"2023-06-23","event":"other","kind":"actual","note":"AdaniConneX announced a USD 213 million construction financing facility covering the Noida campus and its Chennai 1 campus.","source_ids":["s2"]},{"date":"2025-01","event":"first_operational","kind":"actual","note":"Company lists Phase 1 as live from January 2025.","source_ids":["s1"]}],"name":"AdaniConneX Noida data centre campus","notes":"The status comes from the company's undated campus page, accessed on 2026-10-09, so status_as_of is that access date. The 2023 financing was shared with the Chennai campus and is not split by site, so no investment figure is recorded here.","parties":[{"name":"AdaniConneX","role":"developer","source_ids":["s1","s2"]}],"power_sources":[{"description":"Company states up to 100% renewable energy; the supply arrangement is not described.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"AdaniConneX","title":"Data Centers","type":"company","url":"https://www.adaniconnex.com/data-centers"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260902153948/https://resources.adaniconnex.com/press-release/adaniconnex-raises-usd-213-mn-construction-financing-facility","id":"s2","published":"2023-06-23","publisher":"AdaniConneX","title":"AdaniConneX Seals the Largest Data Center Financing Deal in India with a USD 213 Mn Construction Financing Facility","type":"company","url":"https://resources.adaniconnex.com/press-release/adaniconnex-raises-usd-213-mn-construction-financing-facility"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s1"],"summary":"AdaniConneX, the Adani group's data centre business, lists a Noida campus in the Delhi NCR region with a potential capacity of 150 MW of IT load and a first phase live from January 2025. In June 2023 the company said a USD 213 million construction loan would fund a 50 MW Noida campus then being built, alongside its Chennai site. The company says the campus can use up to 100% renewable power. The site address and tenants have not been published.","workloads":["colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d9f7e0af-ae46-5af6-9d9a-39f54b5b80fd","s2":"c57836f8-858f-57cd-887e-45098a9fd5c8"},"source_file":"datacenters/projects/adaniconnex-noida.json","source_record_id":"adaniconnex-noida","source_record_sha256":"4e633b735e877df6f0289b3cf56b22df014af2e4bf3045669e8340a322d7d27b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"02bf4b77017bb110b1b9fbfbd23a963b0ad025113b0d9a7b53c88560701891ee"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c4475d593124b26a70cd/#project-8c2ed321-ddad-5bb1-ab38-bd5b66bf4f2b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8c2ed321-ddad-5bb1-ab38-bd5b66bf4f2b.json
8c926b8f-0190-533b-aa7e-3223971b9e23 | curated:flexential-douglasville-north-river-campus:douglasville-2-current-build | vcc-site-5c75a2f4b8b62cd1f40a | curated:flexential-douglasville-north-river-campus | Flexential Douglasville 2 Current Build | United States | US | 33.7307 | -84.6112 | Point | campus | source_community_representative_point | exact_OSM_way1258702591_Nominatim_lon_lat | named_community_building_reference_point | community_source | campus_locator | Exact D2-named, address-bound community building point used only to locate the North River campus. Not a legal campus boundary, active-work extent, surveyed footprint, entrance or D1 point. |  | No numeric source-specific accuracy for community geometry or representative-point placement. | fa35b333-9224-5eaa-8c0e-2a614d99bdee | under_construction | 2026-08-18 | 56 | authoritative_physical_status_update | 615f2604-fa9b-501e-b499-883102ddcfed | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.prnewswire.com/news-releases/flexential-secures-800-million-to-fund-data-center-development-across-four-high-growth-markets-302853453.html | https://nominatim.openstreetmap.org/lookup?osm_ids=W1258702591&format=jsonv2&addressdetails=1&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5c75a2f4b8b62cd1f40a/#project-8c926b8f-0190-533b-aa7e-3223971b9e23 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8c926b8f-0190-533b-aa7e-3223971b9e23.json
8ce04eb2-b1ed-5375-a685-122f79fc2ee6 | imported:semiconductor-atlas:core-scientific-pecos | vcc-site-779f30ba676706e8e5db | curated:core-scientific-pecos-cottonwood-campus | Core Scientific Pecos data center campus | United States | US | 31.4156 | -103.5 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Core Scientific gives the address as FM 2119, Pecos, TX 79772, which is not a point location. Coordinates are the Pecos city point from its Wikipedia article, which also names the county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 51ab226d-9e61-5abd-918c-f7d0f49da9d0 | announced | 2026-07-28 | 77 | imported_documented_status | 0368978b-07f1-5d7b-b5e8-3c25ccf751a8 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"51ab226d-9e61-5abd-918c-f7d0f49da9d0","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-pecos"},{"evidence_id":"8eae36a6-9c52-5a2a-999c-b6e50014bf25","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-pecos"},{"evidence_id":"0368978b-07f1-5d7b-b5e8-3c25ccf751a8","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-pecos"},{"evidence_id":"51ab226d-9e61-5abd-918c-f7d0f49da9d0","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"operator","source_record_id":"core-scientific-pecos"},{"evidence_id":"a62168ff-9687-509c-8ada-92b14b7ef26d","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"operator","source_record_id":"core-scientific-pecos"},{"evidence_id":"0368978b-07f1-5d7b-b5e8-3c25ccf751a8","notes":"Named for this site only in Core Scientific's Q2 2026 earnings presentation (s4), which lists Pecos as an AMD direct site with about 185 MW leased. The Q2 release (s5) gives the 15-year term for about 530 MW across five sites without naming them.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-pecos"},{"evidence_id":"2a8a3d06-a59f-570b-82cf-2dfa6b118607","notes":"Named for this site only in Core Scientific's Q2 2026 earnings presentation (s4), which lists Pecos as an AMD direct site with about 185 MW leased. The Q2 release (s5) gives the 15-year term for about 530 MW across five sites without naming them.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-pecos"},{"evidence_id":"a62168ff-9687-509c-8ada-92b14b7ef26d","notes":null,"party":"Texas-New Mexico Power","relationship_scope":"unknown","role":"utility","source_record_id":"core-scientific-pecos"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Core Scientific |  | AMD |  | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm | https://corescientific.com/high-density-data-centers/pecos-tx/ | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Core Scientific Cottonwood/Pecos campus on FM 2119, linked by the same operator facility URL. Source describes the whole mining-to-HDC campus and proposed 1.5 GW expansion; existing record selects initial HDC vertical construction.","source_record_id":"core-scientific-pecos","source_relations":[{"reason":"Core Scientific Cottonwood on FM 2119 and Microsoft/Chevron Project Kilby are distinct named developments; shared city coordinate does not imply identity.","relationship":"separate_named_developments","source_id":"microsoft-pecos-texas"}],"target_physical_site_stable_key":"curated:core-scientific-pecos-cottonwood-campus"},"record":{"aliases":["Cottonwood 1 & 2","Pecos, Texas Data Center"],"id":"core-scientific-pecos","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Reeves County","country":"US","lat":31.4156,"locality":"Pecos","lon":-103.5,"note":"Core Scientific gives the address as FM 2119, Pecos, TX 79772, which is not a point location. Coordinates are the Pecos city point from its Wikipedia article, which also names the county.","precision":"locality","source_ids":["s1","s2","s7"]},"metrics":[{"applies_to":"phase","as_of":"2026-03-02","basis":"contracted","metric":"power_capacity","note":"Gross utility power capacity from Texas-New Mexico Power listed in the 10-K; the company site page gives 300 MW total power capacity.","phase_label":"Existing Pecos site","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2026-07-28","basis":"contracted","metric":"power_capacity","note":"Leased capacity; the presentation does not say whether this is critical IT load.","phase_label":"AMD lease","power_scope":"unspecified","qualifier":"approximately","source_ids":["s4"],"unit":"MW","value":185},{"applies_to":"campus","as_of":"2026-05-07","basis":"planned","metric":"power_capacity","note":"Planned gross power after expansion, not defined as IT or facility load. The Q2 2026 presentation lists about 815 MW of further power pipeline at Pecos.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3","s6"],"unit":"MW","value":1500},{"applies_to":"phase","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"From the undated company site page, accessed 2026-10-09.","phase_label":"Existing campus footprint","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":100},{"applies_to":"phase","as_of":"2026-10-09","basis":"operational","metric":"floor_area","note":"Total square footage of the existing facility listed on the undated company site page.","phase_label":"Existing campus buildings","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":125000}],"milestones":[{"date":"2026-04","event":"expansion_announced","kind":"actual","note":"Trade press dates the plan to scale Pecos to about 1.5 GW to April 2026; Core Scientific's Q1 results on 2026-05-06 restated it.","source_ids":["s3","s6"]},{"date":"2026-07-28","event":"other","kind":"actual","note":"Core Scientific announced 15-year AMD leases, including about 185 MW at Pecos.","source_ids":["s4","s5"]},{"date":"2027-H1","event":"first_operational","kind":"planned","note":"Estimated initial delivery of the AMD capacity.","source_ids":["s4"]}],"name":"Core Scientific Pecos data center campus","notes":"Status is set to announced because the sources opened do not say whether construction of the AMD capacity has started. The 10-K lists 300 MW of gross utility power at the existing Pecos facility. Core Scientific says it is repurposing its remaining mining facilities for colocation without naming them, and Data Center Knowledge ties the Pecos plan to existing bitcoin mining infrastructure; current use of the existing capacity is not recorded here. The AMD agreements total about 530 MW across five sites; the Pecos share comes from the company's earnings presentation.","parties":[{"name":"Core Scientific","role":"developer","source_ids":["s1","s3","s4"]},{"name":"Core Scientific","role":"operator","source_ids":["s1","s2"]},{"name":"AMD","note":"Named for this site only in Core Scientific's Q2 2026 earnings presentation (s4), which lists Pecos as an AMD direct site with about 185 MW leased. The Q2 release (s5) gives the 15-year term for about 530 MW across five sites without naming them.","role":"tenant","source_ids":["s4","s5"]},{"name":"Texas-New Mexico Power","role":"utility","source_ids":["s2"]}],"power_sources":[{"description":"Grid supply from Texas-New Mexico Power, 300 MW gross at the existing site.","source_ids":["s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929001316/https://corescientific.com/high-density-data-centers/pecos-tx/","id":"s1","published":null,"publisher":"Core Scientific","title":"Pecos, Texas data center (Cottonwood 1 & 2)","type":"company","url":"https://corescientific.com/high-density-data-centers/pecos-tx/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260303001537/https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm","id":"s2","published":"2026-03-02","publisher":"Core Scientific, Inc. via SEC EDGAR","title":"Core Scientific, Inc. Form 10-K for the fiscal year ended December 31, 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929001647/https://investors.corescientific.com/news-events/press-releases/detail/136/core-scientific-announces-first-quarter-fiscal-year-2026-results","id":"s3","published":"2026-05-06","publisher":"Core Scientific","title":"Core Scientific announces first quarter fiscal year 2026 results","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/136/core-scientific-announces-first-quarter-fiscal-year-2026-results"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929002832/https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm","id":"s4","published":"2026-07-28","publisher":"Core Scientific","title":"Core Scientific Q2 2026 earnings presentation (Form 8-K, Exhibit 99.2)","type":"regulatory_filing","url":"https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm"},{"accessed":"2026-10-09","id":"s5","published":"2026-07-28","publisher":"Core Scientific","title":"Core Scientific announces second quarter 2026 results","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results"},{"accessed":"2026-10-09","id":"s6","published":"2026-05-07","publisher":"Data Center Knowledge","title":"Core Scientific's Muskogee bet: can crypto-era infrastructure fuel AI?","type":"trade_press","url":"https://www.datacenterknowledge.com/build-design/core-scientific-bets-on-1-5-gw-ai-campus-in-oklahoma"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260910002024/https://en.wikipedia.org/wiki/Pecos,_Texas","id":"s7","published":null,"publisher":"Wikipedia","title":"Pecos, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Pecos,_Texas"}],"status":"announced","status_as_of":"2026-07-28","status_source_ids":["s4","s5"],"summary":"Core Scientific campus on FM 2119 in Pecos, Texas, in the Permian Basin, listed with 300 MW of gross utility power from Texas-New Mexico Power and a 100-acre footprint. In spring 2026 Core Scientific announced a plan to scale Pecos to about 1.5 GW of gross power; trade press says the plan repurposes existing bitcoin mining infrastructure. In July 2026 its earnings presentation listed AMD as tenant of about 185 MW at Pecos, part of roughly 530 MW of 15-year AMD leases across five sites, with initial delivery expected in the first half of 2027.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"51ab226d-9e61-5abd-918c-f7d0f49da9d0","s2":"a62168ff-9687-509c-8ada-92b14b7ef26d","s3":"8eae36a6-9c52-5a2a-999c-b6e50014bf25","s4":"0368978b-07f1-5d7b-b5e8-3c25ccf751a8","s5":"2a8a3d06-a59f-570b-82cf-2dfa6b118607","s6":"d113a458-9f61-5d3a-a2f9-c3d8dda4eaad","s7":"1803578b-9a35-5a2f-a022-63de34cf79d9"},"source_file":"datacenters/projects/core-scientific-pecos.json","source_record_id":"core-scientific-pecos","source_record_sha256":"ab37ccfdcc0bc48d95f588d7a62361846b812822a0cd61b3d36fc6ae2dea2784","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"f0dbb6853792968c8fcef8cfecfdb01c8c050c163f8ef8bd8513f51c0e7d2c78"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-779f30ba676706e8e5db/#project-8ce04eb2-b1ed-5375-a685-122f79fc2ee6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8ce04eb2-b1ed-5375-a685-122f79fc2ee6.json
8d08b021-e457-5102-9ef2-33528ad786d1 | imported:semiconductor-atlas:aws-hobart-indiana | vcc-site-c51acbb151880f9815b8 | imported:semiconductor-atlas:aws-hobart-indiana | Amazon Web Services Hobart data center campus | United States | US | 41.5286 | -87.2675 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Hobart city coordinates from its Wikipedia page. The cited sources name the city but give no parcel or street location. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 0eda5c21-7b89-54f5-92a8-531e280f0d17 | announced | 2026-08-25 | 49 | imported_documented_status | 01200511-2e49-573b-bd74-ab830c2253b5 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a68e0313-96de-5976-b76d-7bc89eee614b","notes":"Hobart reports name the company only as Amazon; Amazon's Indiana announcement refers to AWS.","party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-hobart-indiana"},{"evidence_id":"0eda5c21-7b89-54f5-92a8-531e280f0d17","notes":"Hobart reports name the company only as Amazon; Amazon's Indiana announcement refers to AWS.","party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-hobart-indiana"},{"evidence_id":"01200511-2e49-573b-bd74-ab830c2253b5","notes":"Hobart reports name the company only as Amazon; Amazon's Indiana announcement refers to AWS.","party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-hobart-indiana"},{"evidence_id":"0eda5c21-7b89-54f5-92a8-531e280f0d17","notes":"The council approved the project and an economic revitalization area designation; the plan commission approved a fill permit. A resident and her group are suing the city over the approval process.","party":"City of Hobart","relationship_scope":"unknown","role":"government","source_record_id":"aws-hobart-indiana"},{"evidence_id":"01200511-2e49-573b-bd74-ab830c2253b5","notes":"The council approved the project and an economic revitalization area designation; the plan commission approved a fill permit. A resident and her group are suing the city over the approval process.","party":"City of Hobart","relationship_scope":"unknown","role":"government","source_record_id":"aws-hobart-indiana"},{"evidence_id":"c865c196-6f05-5703-9fea-e06561ebd331","notes":"The council approved the project and an economic revitalization area designation; the plan commission approved a fill permit. A resident and her group are suing the city over the approval process.","party":"City of Hobart","relationship_scope":"unknown","role":"government","source_record_id":"aws-hobart-indiana"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://fox32chicago.com/news/hobart-approves-11b-amazon-data-center-details-still-unclear | https://www.21alivenews.com/2025/11/25/hobart-reaches-agreement-with-amazon-next-gen-data-center/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Amazon Web Services Hobart data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"aws-hobart-indiana"},"record":{"aliases":[],"id":"aws-hobart-indiana","last_reviewed":"2026-10-09","location":{"admin1":"Indiana","admin2":"Lake County","country":"US","lat":41.5286,"locality":"Hobart","lon":-87.2675,"note":"Coordinates are the Hobart city coordinates from its Wikipedia page. The cited sources name the city but give no parcel or street location.","precision":"locality","source_ids":["s2","s3","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-02-05","basis":"reported","metric":"investment","note":"Figure reported for the project approved by the Hobart City Council; the source does not say who produced it.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":11000000000},{"applies_to":"campus","as_of":"2026-02-08","basis":"planned","metric":"buildings","note":"The mayor's estimate; the city and Amazon had not confirmed the number or size of buildings.","qualifier":"up_to","source_ids":["s3","s4"],"unit":"count","value":25},{"applies_to":"campus","as_of":"2026-02-05","basis":"planned","metric":"jobs_permanent","note":"Amazon's figure to the city.","qualifier":"more_than","source_ids":["s3","s4"],"unit":"count","value":400},{"applies_to":"campus","as_of":"2025-11-25","basis":"planned","metric":"jobs_permanent","note":"The mayor's estimate of long-term jobs when the agreement was confirmed; differs from Amazon's later figure of more than 400.","qualifier":"approximately","source_ids":["s2"],"unit":"count","value":1000}],"milestones":[{"date":"2025-11-25","event":"announced","kind":"actual","note":"Hobart confirmed an agreement for a campus less than a day after Amazon's USD 15 billion northern Indiana announcement.","source_ids":["s2"]},{"date":"2026-01","event":"zoning_approved","kind":"actual","note":"City council approval, which Fox 32 describes as re-zoning the property as an economic revitalization area, with tax abatements.","source_ids":["s3"]},{"date":"2026-02","event":"permit_approved","kind":"actual","note":"The plan commission approved a fill permit for soil testing; residents sought an injunction in Lake County court.","source_ids":["s4"]},{"date":"2026","event":"construction_started","kind":"planned","source_ids":["s2","s3"]},{"date":"2028","event":"fully_operational","kind":"planned","note":"Targeted completion of construction.","source_ids":["s3"]}],"name":"Amazon Web Services Hobart data center campus","notes":"Amazon's USD 15 billion and 2.4 GW figures cover all of its new northern Indiana campuses, whose locations Amazon did not name; they are not recorded as Hobart metrics. Amazon's framework with NIPSCO's new generation subsidiary covers those campuses, but no opened source explicitly ties it to Hobart, so NIPSCO is not listed as a party. Fox 32 reports the Hobart project at USD 11 billion without saying who produced the estimate. No source opened confirms that construction had begun by October 2026; a fill permit for soil testing was approved in February 2026.","parties":[{"name":"Amazon Web Services","note":"Hobart reports name the company only as Amazon; Amazon's Indiana announcement refers to AWS.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"City of Hobart","note":"The council approved the project and an economic revitalization area designation; the plan commission approved a fill permit. A resident and her group are suing the city over the approval process.","role":"government","source_ids":["s2","s3","s4"]}],"power_sources":[{"description":"Expected to rely on the local utility's power; Amazon's November 2025 northern Indiana announcement set up a framework with NIPSCO under which Amazon pays fees for existing lines and covers new plants and lines, though sources do not tie it to Hobart explicitly. Residents raised reliability concerns after an August 2026 storm outage.","source_ids":["s1","s2","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-24","publisher":"Amazon","title":"Amazon to invest $15 billion in Indiana for new data centers","type":"company","url":"https://aboutamazon.com/news/company-news/amazon-15-billion-indiana-data-centers"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-25","publisher":"21Alive News (WPTA), from Inside INdiana Business","title":"Hobart reaches agreement with Amazon for next-gen data center","type":"news","url":"https://www.21alivenews.com/2025/11/25/hobart-reaches-agreement-with-amazon-next-gen-data-center/"},{"accessed":"2026-10-09","id":"s3","published":"2026-02-05","publisher":"FOX 32 Chicago","title":"'We want transparency before approvals happen': Residents oppose proposed $11 billion Amazon data center","type":"news","url":"https://fox32chicago.com/news/hobart-approves-11b-amazon-data-center-details-still-unclear"},{"accessed":"2026-10-09","id":"s4","published":"2026-02-08","publisher":"FOX 32 Chicago","title":"Lawsuit seeks to block Amazon data center permit in Hobart, Ind.","type":"news","url":"https://www.fox32chicago.com/news/lawsuit-seeks-block-amazon-data-center-permit-hobart-ind"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260901054307/https://www.wbur.org/hereandnow/2026/08/25/indiana-power-data-centers","id":"s5","published":"2026-08-25","publisher":"WBUR (Here & Now)","title":"Indiana power outage raises concerns about data centers","type":"news","url":"https://www.wbur.org/hereandnow/2026/08/25/indiana-power-data-centers"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Hobart, Indiana","type":"other","url":"https://en.wikipedia.org/wiki/Hobart,_Indiana"}],"status":"announced","status_as_of":"2026-08-25","status_source_ids":["s3","s5"],"summary":"Planned Amazon data center campus on hundreds of acres of undeveloped land in Hobart, Lake County, Indiana. Hobart confirmed an agreement for the campus less than a day after Amazon announced USD 15 billion for new northern Indiana campuses in November 2025. The city council approved the project, reported at USD 11 billion, in January 2026 with a ten-year tax abatement and a long IT equipment exemption; Amazon has paid the city USD 47 million, with further payments tied to construction milestones. The mayor has estimated up to 25 buildings, with work slated to start in 2026 and finish in 2028. A resident's lawsuit over the approval process was still described as ongoing in August 2026.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a68e0313-96de-5976-b76d-7bc89eee614b","s2":"0eda5c21-7b89-54f5-92a8-531e280f0d17","s3":"01200511-2e49-573b-bd74-ab830c2253b5","s4":"c865c196-6f05-5703-9fea-e06561ebd331","s5":"39b564fe-6296-50b9-9ef8-4718b4e12f97","s6":"5588e9e5-ffc9-5caa-9af6-f8634adb91be"},"source_file":"datacenters/projects/aws-hobart-indiana.json","source_record_id":"aws-hobart-indiana","source_record_sha256":"51fd6e547d8fd5c8eaa8837b69b75043041b5ae8f9bec2a94b1b95328b7c679b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"f2ce9535d16087690864b90f1781cf9f90ad27c1059a9800bd5680af3178790d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c51acbb151880f9815b8/#project-8d08b021-e457-5102-9ef2-33528ad786d1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8d08b021-e457-5102-9ef2-33528ad786d1.json
8d1ed9d7-795d-55a8-b8cf-41e51579dd27 | imported:semiconductor-atlas:nscale-kvandal-narvik | vcc-site-2fb799e38497b94b3ed1 | curated:nscale-kvandal-narvik-ai-data-center-campus | Nscale Kvandal AI data center (Narvik) | Norway | NO | 68.2899 | 17.0865 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Sources place the site at Kvandal, just outside Narvik, and Nscale says the operator's main office is on site in Bjerkvik. Kvandal itself was not resolved to a point, so a Narvik municipality centroid is used. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 9289eae2-9237-5f3a-9e60-0dec15d2fe23 | under_construction | 2026-09-02 | 41 | imported_documented_status | 05a43522-dea2-5e51-a479-742c80d8477c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9289eae2-9237-5f3a-9e60-0dec15d2fe23","notes":"Nscale leads design and build; the April 2026 release says the project is solely managed by Nscale.","party":"Nscale","relationship_scope":"unknown","role":"developer","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"77e928f5-611c-5778-a20f-f35d7724475a","notes":"Nscale leads design and build; the April 2026 release says the project is solely managed by Nscale.","party":"Nscale","relationship_scope":"unknown","role":"developer","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"803f1767-292c-5266-9fc0-1ce5600ec2df","notes":"Owns the former Aker Nscale joint venture after Aker transferred its 50% stake in March 2026.","party":"Nscale","relationship_scope":"unknown","role":"owner","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"77e928f5-611c-5778-a20f-f35d7724475a","notes":"Owns the former Aker Nscale joint venture after Aker transferred its 50% stake in March 2026.","party":"Nscale","relationship_scope":"unknown","role":"owner","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"9289eae2-9237-5f3a-9e60-0dec15d2fe23","notes":"50% owner of the Aker Nscale joint venture from its formation until it transferred the stake to Nscale on 27 March 2026.","party":"Aker ASA","relationship_scope":"unknown","role":"owner","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"803f1767-292c-5266-9fc0-1ce5600ec2df","notes":"50% owner of the Aker Nscale joint venture from its formation until it transferred the stake to Nscale on 27 March 2026.","party":"Aker ASA","relationship_scope":"unknown","role":"owner","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"a67e827d-2b5c-5fe0-a224-9779af45c9b7","notes":"Five-year customer agreement of about USD 6.2bn signed in September 2025, expanded in April 2026 with more than 30,000 NVIDIA Rubin GPUs for 2027.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"77e928f5-611c-5778-a20f-f35d7724475a","notes":"Five-year customer agreement of about USD 6.2bn signed in September 2025, expanded in April 2026 with more than 30,000 NVIDIA Rubin GPUs for 2027.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"9289eae2-9237-5f3a-9e60-0dec15d2fe23","notes":"Named as initial offtaker in July 2025; reported in April 2026 to have dropped out, with Microsoft taking the capacity.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"9e4e6125-77e9-56bf-b0f1-988fcd404266","notes":"Named as initial offtaker in July 2025; reported in April 2026 to have dropped out, with Microsoft taking the capacity.","party":"OpenAI","relationship_scope":"unknown","role":"tenant","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"9289eae2-9237-5f3a-9e60-0dec15d2fe23","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"77e928f5-611c-5778-a20f-f35d7724475a","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"05a43522-dea2-5e51-a479-742c80d8477c","notes":"Sentia subsidiary holding civil, structural and architectural contracts for three buildings.","party":"HENT","relationship_scope":"unknown","role":"builder","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"ae08c7f6-c209-5c4d-86dc-a6c38e5e3835","notes":"Operating company owned 51% by Nscale Norway AS and 49% by Nordkraft AS.","party":"Nordscale Operations AS","relationship_scope":"unknown","role":"operator","source_record_id":"nscale-kvandal-narvik"},{"evidence_id":"2e7e6bb8-ba6f-5df9-8212-a0e1b93471ca","notes":"Power purchase agreement covering a significant share of first-phase demand from 2027 to 2031; volume not disclosed.","party":"Vattenfall","relationship_scope":"unknown","role":"power_supplier","source_record_id":"nscale-kvandal-narvik"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Aker ASA; Nscale | Nordscale Operations AS |  | Microsoft; OpenAI |  | https://www.inderes.se/releases/hent-a-subsidiary-of-sentia-has-signed-a-contract-for-the-expansion-of-nscales-data-center-in-the-narvik-region | https://www.mfn.se/ob/a/aker/nscale-aker-and-openai-to-establish-stargate-norway-a-100-000-nvidia-gpu-ai-gigafactory-powered-by-renewable-energy-in-northern-norway-bb68d573 | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Kvandal/Bjerkvik Nscale campus, with exact shared Nordscale issuer source. Source encompasses Stargate Norway and three-building/100 MW development; existing record is the initial 25 MW EPC build. Its municipality centroid is 38 km away from the reviewed parcel locator.","source_record_id":"nscale-kvandal-narvik","target_physical_site_stable_key":"curated:nscale-kvandal-narvik-ai-data-center-campus"},"record":{"aliases":["Stargate Norway","Kvandal North Campus","Aker Nscale Narvik"],"id":"nscale-kvandal-narvik","last_reviewed":"2026-10-09","location":{"admin1":"Nordland","admin2":"Narvik Municipality","country":"NO","lat":68.2899,"locality":"Kvandal","lon":17.0865,"note":"Sources place the site at Kvandal, just outside Narvik, and Nscale says the operator's main office is on site in Bjerkvik. Kvandal itself was not resolved to a point, so a Narvik municipality centroid is used.","precision":"admin2","source_ids":["s1","s8","s9"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-14","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s5","s10"],"unit":"MW","value":230},{"applies_to":"phase","as_of":"2025-07-31","basis":"planned","metric":"power_capacity","note":"Stated as an ambition for additional capacity beyond the 230 MW.","phase_label":"Possible expansion","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":290},{"applies_to":"phase","as_of":"2025-07-31","basis":"planned","metric":"power_capacity","phase_label":"Initial phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":20},{"applies_to":"phase","as_of":"2026-05-11","basis":"planned","metric":"power_capacity","note":"An uncommitted USD 790m accordion could fund this further expansion.","phase_label":"Accordion-funded expansion","power_scope":"unspecified","qualifier":"exact","source_ids":["s6"],"unit":"MW","value":115},{"applies_to":"phase","as_of":"2026-09-02","basis":"under_construction","metric":"power_capacity","note":"Combined capacity of the three buildings HENT is contracted to build, including two added in September 2026 totalling 75 MW; the release says construction is under way but does not relate this to the 230 MW figure.","phase_label":"HENT-contracted buildings","power_scope":"unspecified","qualifier":"exact","source_ids":["s9"],"unit":"MW","value":100},{"applies_to":"phase","as_of":"2025-07-31","basis":"announced","metric":"investment","note":"Committed by Nscale and Aker, including upwards of USD 250m of equity shared equally.","phase_label":"Initial 20 MW phase","qualifier":"approximately","source_ids":["s1"],"unit":"USD","value":1000000000},{"accelerator_model":"NVIDIA GPUs (model not specified)","applies_to":"campus","as_of":"2025-07-31","basis":"planned","metric":"accelerators","note":"Original target of 100,000 GPUs by end of 2026 under the Stargate Norway plan.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":100000},{"accelerator_model":"NVIDIA GB300","applies_to":"campus","as_of":"2025-10-15","basis":"planned","metric":"accelerators","note":"GPUs to be delivered to Microsoft from the Narvik campus under a multi-year agreement.","qualifier":"approximately","source_ids":["s3"],"unit":"count","value":52000},{"accelerator_model":"NVIDIA Rubin","applies_to":"campus","as_of":"2026-04-14","basis":"planned","metric":"accelerators","note":"Expansion of the Microsoft deal for 2027 delivery.","qualifier":"more_than","source_ids":["s5"],"unit":"count","value":30000},{"applies_to":"phase","as_of":"2026-09-02","basis":"under_construction","metric":"buildings","phase_label":"HENT-contracted buildings","qualifier":"exact","source_ids":["s9"],"unit":"count","value":3}],"milestones":[{"date":"2025-07-31","event":"announced","kind":"actual","note":"Nscale and Aker said they were beginning preparatory work and mobilising for construction.","source_ids":["s1"]},{"date":"2025-09-17","event":"other","kind":"actual","note":"Nscale, Aker and Microsoft signed a binding five-year customer agreement worth about USD 6.2bn, with staged deployments from 2026.","source_ids":["s2"]},{"date":"2026-03-27","event":"other","kind":"actual","note":"Aker completed the transfer of its 50% stake in the Aker Nscale joint venture to Nscale as part of Nscale's Series C.","source_ids":["s4"]},{"date":"2026-04-14","event":"other","kind":"actual","note":"Microsoft expanded its deal with more than 30,000 Rubin GPUs for 2027; OpenAI was reported to have dropped out.","source_ids":["s5","s10"]},{"date":"2026-05-11","event":"other","kind":"actual","note":"USD 790m debt financing from ABN AMRO, DNB, Eksfin, Nordea and SEB.","source_ids":["s6"]},{"date":"2026-09-02","event":"expansion_announced","kind":"actual","note":"HENT contracted for two additional buildings totalling 75 MW.","source_ids":["s9"]},{"date":"2027","event":"first_operational","kind":"planned","source_ids":["s7","s9"]}],"name":"Nscale Kvandal AI data center (Narvik)","parties":[{"name":"Nscale","note":"Nscale leads design and build; the April 2026 release says the project is solely managed by Nscale.","role":"developer","source_ids":["s1","s5"]},{"name":"Nscale","note":"Owns the former Aker Nscale joint venture after Aker transferred its 50% stake in March 2026.","role":"owner","source_ids":["s4","s5"]},{"name":"Aker ASA","note":"50% owner of the Aker Nscale joint venture from its formation until it transferred the stake to Nscale on 27 March 2026.","role":"owner","source_ids":["s1","s4"]},{"name":"Microsoft","note":"Five-year customer agreement of about USD 6.2bn signed in September 2025, expanded in April 2026 with more than 30,000 NVIDIA Rubin GPUs for 2027.","role":"tenant","source_ids":["s2","s5"]},{"name":"OpenAI","note":"Named as initial offtaker in July 2025; reported in April 2026 to have dropped out, with Microsoft taking the capacity.","role":"tenant","source_ids":["s1","s10"]},{"name":"NVIDIA","role":"hardware_supplier","source_ids":["s1","s5"]},{"name":"HENT","note":"Sentia subsidiary holding civil, structural and architectural contracts for three buildings.","role":"builder","source_ids":["s9"]},{"name":"Nordscale Operations AS","note":"Operating company owned 51% by Nscale Norway AS and 49% by Nordkraft AS.","role":"operator","source_ids":["s8"]},{"name":"Vattenfall","note":"Power purchase agreement covering a significant share of first-phase demand from 2027 to 2031; volume not disclosed.","role":"power_supplier","source_ids":["s7"]}],"power_sources":[{"description":"Secured grid capacity with entirely renewable electricity; a Vattenfall PPA covers a significant share of first-phase demand from 2027 to 2031, generation assets not disclosed.","source_ids":["s2","s7"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-07-31","publisher":"Aker ASA","title":"Nscale, Aker and OpenAI to establish Stargate Norway: a 100,000 NVIDIA GPU AI gigafactory powered by renewable energy in Northern Norway","type":"company","url":"https://www.mfn.se/ob/a/aker/nscale-aker-and-openai-to-establish-stargate-norway-a-100-000-nvidia-gpu-ai-gigafactory-powered-by-renewable-energy-in-northern-norway-bb68d573"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-17","publisher":"Aker ASA","title":"Aker-Nscale JV signs multi-billion dollar AI infrastructure agreement with Microsoft","type":"company","url":"https://mfn.se/ob/a/aker/aker-aker-nscale-jv-signs-multi-billion-dollar-ai-infrastructure-agreement-with-microsoft-cad81224"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-15","publisher":"Nscale","title":"Nscale Contracts Approximately 200,000 NVIDIA GB300 GPUs with Microsoft to Deliver NVIDIA AI Infrastructure Across Europe and the U.S.","type":"company","url":"https://nscale.com/press-releases/nscale-microsoft-2025"},{"accessed":"2026-10-09","id":"s4","published":"2026-03-27","publisher":"Aker ASA (via Placera)","title":"Aker completes investment in Nscale's Series C funding round","type":"company","url":"https://www.placera.se/pressmeddelanden/aker-aker-completes-investment-in-nscales-series-c-funding-round-20260327"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929093618/https://www.nscale.com/press-releases/nscale-microsoft-norway","id":"s5","published":"2026-04-14","publisher":"Nscale","title":"Nscale announces expanded deal with Microsoft in Norway","type":"company","url":"https://www.nscale.com/press-releases/nscale-microsoft-norway"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260707185336/https://www.nscale.com/press-releases/nscale-secures-790-million-norway","id":"s6","published":"2026-05-11","publisher":"Nscale","title":"Nscale Secures $790 Million in Financing to Support AI Infrastructure Buildout in Norway","type":"company","url":"https://www.nscale.com/press-releases/nscale-secures-790-million-norway"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261002113335/https://www.datacenter-forum.com/nscale/nscale-signs-ppa-with-vattenfall-for-kvandal-data-center-norway","id":"s7","published":"2026-06","publisher":"Datacenter Forum","title":"Nscale signs PPA with Vattenfall for Kvandal data center Norway","type":"trade_press","url":"https://www.datacenter-forum.com/nscale/nscale-signs-ppa-with-vattenfall-for-kvandal-data-center-norway"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260707185255/https://www.nscale.com/press-releases/nordscale","id":"s8","published":"2026-07-06","publisher":"Nscale","title":"Nscale and Nordkraft Enter Strategic Partnership to Support Data Center Operations in Narvik","type":"company","url":"https://www.nscale.com/press-releases/nordscale"},{"accessed":"2026-10-09","id":"s9","published":"2026-09-02","publisher":"Sentia (via Inderes)","title":"HENT, a subsidiary of Sentia, has signed a contract for the expansion of Nscale's data center in the Narvik region","type":"company","url":"https://www.inderes.se/releases/hent-a-subsidiary-of-sentia-has-signed-a-contract-for-the-expansion-of-nscales-data-center-in-the-narvik-region"},{"accessed":"2026-10-09","id":"s10","published":"2026-04-17","publisher":"AmCham Norway","title":"Microsoft contracts 30,000 GPUs from Nscale at Norway data center as OpenAI drops out of latest Stargate","type":"news","url":"https://amcham.no/microsoft-contracts-30000-gpus-from-nscale-at-norway-data-center-as-openai-drops-out-of-latest-stargate/"}],"status":"under_construction","status_as_of":"2026-09-02","status_source_ids":["s9"],"summary":"AI data center campus at Kvandal outside Narvik in northern Norway, announced in July 2025 as Stargate Norway by Nscale, Aker and OpenAI with 230 MW planned and ambitions for 290 MW more. The Aker-Nscale joint venture signed a five-year Microsoft contract worth about USD 6.2bn in September 2025, and in April 2026 Microsoft took the capacity first linked to OpenAI, adding more than 30,000 NVIDIA Rubin GPUs for 2027. Aker transferred its half of the joint venture to Nscale in March 2026. Nscale raised USD 790m of debt in May 2026, and in September 2026 contractor HENT held contracts for three buildings totalling 100 MW, with construction under way and completion expected in 2027.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9289eae2-9237-5f3a-9e60-0dec15d2fe23","s10":"9e4e6125-77e9-56bf-b0f1-988fcd404266","s2":"a67e827d-2b5c-5fe0-a224-9779af45c9b7","s3":"4c37f447-c665-5bf8-a027-d1b5b4494a94","s4":"803f1767-292c-5266-9fc0-1ce5600ec2df","s5":"77e928f5-611c-5778-a20f-f35d7724475a","s6":"8d7836d4-bb30-5388-9bbd-77de798cbcf6","s7":"2e7e6bb8-ba6f-5df9-8212-a0e1b93471ca","s8":"ae08c7f6-c209-5c4d-86dc-a6c38e5e3835","s9":"05a43522-dea2-5e51-a479-742c80d8477c"},"source_file":"datacenters/projects/nscale-kvandal-narvik.json","source_record_id":"nscale-kvandal-narvik","source_record_sha256":"b6e0ecf7f879e1a240a2261292267e94077cb03a765ee2aa5afb2c430537adf1","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"93bc05c4c106396860938b0b6d6dee41ccbb96ea63d1c7546db16651b1bdf1da"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2fb799e38497b94b3ed1/#project-8d1ed9d7-795d-55a8-b8cf-41e51579dd27 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8d1ed9d7-795d-55a8-b8cf-41e51579dd27.json
8d3985c2-7777-5c6b-9a7f-fcab6c9b6a4f | imported:semiconductor-atlas:meta-mesa-arizona | vcc-site-cb8ab0ad35bb603ea3ba | imported:semiconductor-atlas:meta-mesa-arizona | Meta Mesa Data Center | United States | US | 33.4222 | -111.8228 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Mesa city coordinates from its Wikipedia page, not the site. Sources give the street address (3841 S. Ellsworth Road, at the southeast corner of Elliot and Ellsworth Roads), but it was not converted to coordinates because no geocoder was used. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f2e0aa56-e925-51e3-94a6-43ac3a38be1c | partially_operational | 2025-01-31 | 620 | imported_documented_status | 2e1d8fdc-f473-5df8-9053-04a2a58431d3 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"90c086dc-2fb1-531c-b7de-c5482be9c676","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-mesa-arizona"},{"evidence_id":"98c5d27d-61ea-54ae-a5a9-e821ce87858e","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-mesa-arizona"},{"evidence_id":"2e1d8fdc-f473-5df8-9053-04a2a58431d3","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"meta-mesa-arizona"},{"evidence_id":"16e36e46-4aa0-575e-b78d-bf6521024466","notes":null,"party":"DPR Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-mesa-arizona"},{"evidence_id":"90c086dc-2fb1-531c-b7de-c5482be9c676","notes":null,"party":"Salt River Project","relationship_scope":"unknown","role":"utility","source_record_id":"meta-mesa-arizona"},{"evidence_id":"f2e0aa56-e925-51e3-94a6-43ac3a38be1c","notes":null,"party":"Salt River Project","relationship_scope":"unknown","role":"utility","source_record_id":"meta-mesa-arizona"},{"evidence_id":"f2e0aa56-e925-51e3-94a6-43ac3a38be1c","notes":"Partner with Salt River Project on the Brittlebush solar plant, whose entire output is dedicated to the Mesa data center.","party":"EDP Renewables North America","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-mesa-arizona"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Meta Platforms |  |  |  | https://ktar.com/arizona-news/mesa-data-center-mesa | https://ktar.com/arizona-news/new-srp-solar-facility-to-provide-power-for-meta-data-center-in-mesa | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Mesa Data Center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-mesa-arizona"},"record":{"aliases":["Mesa Data Center"],"id":"meta-mesa-arizona","last_reviewed":"2026-10-09","location":{"admin1":"Arizona","admin2":"Maricopa County","country":"US","lat":33.4222,"locality":"Mesa","lon":-111.8228,"note":"Coordinates are the Mesa city coordinates from its Wikipedia page, not the site. Sources give the street address (3841 S. Ellsworth Road, at the southeast corner of Elliot and Ellsworth Roads), but it was not converted to coordinates because no geocoder was used.","precision":"locality","source_ids":["s4","s5","s6"]},"metrics":[{"applies_to":"campus","as_of":"2021","basis":"announced","metric":"investment","note":"Original two-building plan.","qualifier":"exact","source_ids":["s2","s4"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2022-05-06","basis":"announced","metric":"investment","note":"After the expansion to five buildings.","qualifier":"more_than","source_ids":["s2","s3","s4"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"Figure on Meta's current fact sheet, given as investment in Arizona.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1200000000},{"applies_to":"campus","as_of":"2025-01-31","basis":"acquired","metric":"land_area","qualifier":"exact","source_ids":["s4","s5"],"unit":"acres","value":396},{"applies_to":"campus","as_of":"2023-12-06","basis":"planned","metric":"floor_area","note":"About 2.5 million sq ft after the 2022 expansion; Construction Dive gives more than 2.5 million sq ft of data center and administrative space across five buildings.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"sq_ft","value":2500000},{"applies_to":"campus","as_of":"2023-12-06","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s3","s5"],"unit":"count","value":5},{"applies_to":"phase","as_of":"2025-01-31","basis":"operational","metric":"buildings","phase_label":"Phase 1","qualifier":"exact","source_ids":["s5"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"jobs_construction","note":"Skilled trade workers on site at peak construction, per Meta's fact sheet.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":2000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_permanent","note":"Operational jobs once the campus is complete.","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":200}],"milestones":[{"date":"2021","event":"site_acquired","kind":"actual","source_ids":["s5"]},{"date":"2021-08","event":"construction_started","kind":"actual","note":"Groundbreaking in August 2021.","source_ids":["s1","s2"]},{"date":"2022-05","event":"expansion_announced","kind":"actual","note":"Three buildings added to the original two.","source_ids":["s2"]},{"date":"2025-01-30","event":"first_operational","kind":"actual","note":"Meta announced that the first two buildings were serving traffic.","source_ids":["s5"]},{"date":"2026","event":"fully_operational","kind":"planned","note":"Builder DPR targeted completion in 2026, and Meta said the second phase would likely open that year.","source_ids":["s3","s5"]}],"name":"Meta Mesa Data Center","notes":"No 2026 report was found confirming that buildings three to five are in service; Meta's fact sheet (s1) says the data center went online in 2025 but gives no building status. The fact sheet shows no publication date (embedded file creation date 2026-09-02), so figures that rest on it alone are dated to the access date, 2026-10-09. Meta bought the 396-acre site in 2021 for USD 123.2 million.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Meta Platforms","role":"operator","source_ids":["s5"]},{"name":"DPR Construction","role":"builder","source_ids":["s3"]},{"name":"Salt River Project","role":"utility","source_ids":["s1","s4"]},{"name":"EDP Renewables North America","note":"Partner with Salt River Project on the Brittlebush solar plant, whose entire output is dedicated to the Mesa data center.","role":"power_supplier","source_ids":["s4"]}],"power_sources":[{"description":"Supplied by Salt River Project; Meta says it planned its energy needs with the utility and pays the full cost of the energy it uses.","source_ids":["s1"],"type":"grid"},{"description":"The 200 MW Brittlebush Solar Park near Coolidge in Pinal County, a Salt River Project collaboration with EDP Renewables North America, has all of its capacity dedicated to the Mesa data center.","source_ids":["s4"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Meta Platforms","title":"Meta Mesa Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Mesa-Data-Center.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2022-05-06","publisher":"Data Center Knowledge","title":"Meta Is Adding Three Data Centers to Already Massive Mesa Campus","type":"trade_press","url":"https://www.datacenterknowledge.com/hyperscalers/meta-is-adding-three-data-centers-to-already-massive-mesa-campus"},{"accessed":"2026-10-09","id":"s3","published":"2023-12-06","publisher":"Construction Dive","title":"Meta selects DPR for $1B Arizona data center","type":"trade_press","url":"https://www.constructiondive.com/news/meta-dpr-arizona-data-center-mesa-phoenix/701776/"},{"accessed":"2026-10-09","id":"s4","published":"2024-08-04","publisher":"KTAR News","title":"New SRP solar facility to provide power for Meta data center in Mesa","type":"news","url":"https://ktar.com/arizona-news/new-srp-solar-facility-to-provide-power-for-meta-data-center-in-mesa"},{"accessed":"2026-10-09","id":"s5","published":"2025-01-31","publisher":"KTAR News","title":"First phase of Meta's Mesa data center project open; more under construction","type":"news","url":"https://ktar.com/arizona-news/mesa-data-center-mesa"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004044024/https://en.wikipedia.org/wiki/Mesa,_Arizona","id":"s6","published":null,"publisher":"Wikipedia","title":"Mesa, Arizona","type":"other","url":"https://en.wikipedia.org/wiki/Mesa,_Arizona"}],"status":"partially_operational","status_as_of":"2025-01-31","status_source_ids":["s5"],"summary":"Five-building Meta campus on 396 acres at the southeast corner of Elliot and Ellsworth Roads in Mesa, Arizona (3841 S. Ellsworth Road). Meta broke ground in August 2021 on a USD 800 million, two-building plan; in May 2022 it added three buildings, taking the campus to about 2.5 million sq ft and more than USD 1 billion. DPR Construction is the builder. The first two buildings went live in January 2025, with the rest expected around 2026, and Meta now cites a USD 1.2 billion investment. Salt River Project's 200 MW Brittlebush solar plant dedicates its full output to the campus.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"90c086dc-2fb1-531c-b7de-c5482be9c676","s2":"98c5d27d-61ea-54ae-a5a9-e821ce87858e","s3":"16e36e46-4aa0-575e-b78d-bf6521024466","s4":"f2e0aa56-e925-51e3-94a6-43ac3a38be1c","s5":"2e1d8fdc-f473-5df8-9053-04a2a58431d3","s6":"0c2462c8-8407-550b-8c6a-a49848f1c879"},"source_file":"datacenters/projects/meta-mesa-arizona.json","source_record_id":"meta-mesa-arizona","source_record_sha256":"690a5d65866311037933f9ddd4b78f9f474ed7fab8310573de902132c5585030","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"bd117cd7cdcf6360cf8e778d8064cf2b9baaf689dc24bf195152b3752916351d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cb8ab0ad35bb603ea3ba/#project-8d3985c2-7777-5c6b-9a7f-fcab6c9b6a4f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8d3985c2-7777-5c6b-9a7f-fcab6c9b6a4f.json
8dbc82d0-1a4d-5d8e-955e-c5e4973ea19e | curated:flexential-parker-compark-campus:first-data-center | vcc-site-aa53021c0d413ab5dd3d | curated:flexential-parker-compark-campus | Flexential Parker Data Center Current Build | United States | US | 39.5609 | -104.8119 | Point | project | official_census_street_address_range_interpolation | exact_official_postal_address_Census_NAD83_to_WGS84_pyproj_3_8_0 | official_project_street_address_locator | official_source | project_locator | Census interpolation for exact 15255 Compark Blvd, bound by Town Flexential DEN12 record and county postal alias. Not a campus centre, surveyed point, building footprint, parcel boundary, entrance or active-work extent. No county coordinate selected. |  | No source-specific numeric horizontal accuracy published for the address-range interpolation. | 03627a5f-061f-575a-8f9f-a0431558c660 | under_construction | 2026-08-18 | 56 | authoritative_physical_status_update | 7119195b-d4e0-5478-b914-14434bd195fd | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.prnewswire.com/news-releases/flexential-secures-800-million-to-fund-data-center-development-across-four-high-growth-markets-302853453.html | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=15255%20Compark%20Blvd%2C%20Englewood%2C%20CO%2080112&benchmark=Public_AR_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-aa53021c0d413ab5dd3d/#project-8dbc82d0-1a4d-5d8e-955e-c5e4973ea19e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8dbc82d0-1a4d-5d8e-955e-c5e4973ea19e.json
8e72e640-c0e0-5e58-8a76-e53c011dcf92 | imported:semiconductor-atlas:powerhouse-big-watt-taylor | vcc-site-450769770dfe5ea908d6 | imported:semiconductor-atlas:powerhouse-big-watt-taylor | Taylor Technology Campus (Big Watt Digital and PowerHouse) | United States | US | 30.5725 | -97.4167 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Bisnow gives the address 3301 Farm to Market Road 112; KUT places the site just outside Taylor's city limits in unincorporated Williamson County, pending annexation. The point is the Taylor city coordinate from its Wikipedia article, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 900327af-48bd-5ddf-a20d-83ef31e1ec24 | proposed | 2026-10-09 | 4 | imported_documented_status | 1f5b7d3a-f4d6-5215-8d66-ac2de4a9cb41 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"900327af-48bd-5ddf-a20d-83ef31e1ec24","notes":null,"party":"Big Watt Digital","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-big-watt-taylor"},{"evidence_id":"76979786-74cf-5050-ae76-55068bbd2c36","notes":null,"party":"Big Watt Digital","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-big-watt-taylor"},{"evidence_id":"1f5b7d3a-f4d6-5215-8d66-ac2de4a9cb41","notes":null,"party":"Big Watt Digital","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-big-watt-taylor"},{"evidence_id":"900327af-48bd-5ddf-a20d-83ef31e1ec24","notes":null,"party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-big-watt-taylor"},{"evidence_id":"76979786-74cf-5050-ae76-55068bbd2c36","notes":null,"party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-big-watt-taylor"},{"evidence_id":"1f5b7d3a-f4d6-5215-8d66-ac2de4a9cb41","notes":null,"party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-big-watt-taylor"},{"evidence_id":"76979786-74cf-5050-ae76-55068bbd2c36","notes":"Negotiated an annexation agreement letting it set standards on water use, noise, setbacks and air quality; the council approved it unanimously.","party":"City of Taylor","relationship_scope":"unknown","role":"government","source_record_id":"powerhouse-big-watt-taylor"},{"evidence_id":"1f5b7d3a-f4d6-5215-8d66-ac2de4a9cb41","notes":"Negotiated an annexation agreement letting it set standards on water use, noise, setbacks and air quality; the council approved it unanimously.","party":"City of Taylor","relationship_scope":"unknown","role":"government","source_record_id":"powerhouse-big-watt-taylor"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.kut.org/energy-environment/2026-10-09/taylor-tx-annex-data-center-power-plant | https://www.bisnow.com/news/austin-san-antonio/data-center/taylor-deciding-annexation-zoning-data-center-campus-powerhouse | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Taylor Technology Campus (Big Watt Digital and PowerHouse) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"powerhouse-big-watt-taylor"},"record":{"aliases":["Taylor Technology Campus","Project Mustang"],"id":"powerhouse-big-watt-taylor","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Williamson County","country":"US","lat":30.5725,"locality":"Taylor","lon":-97.4167,"note":"Bisnow gives the address 3301 Farm to Market Road 112; KUT places the site just outside Taylor's city limits in unincorporated Williamson County, pending annexation. The point is the Taylor city coordinate from its Wikipedia article, not the site.","precision":"locality","source_ids":["s1","s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Bisnow describes the campus as encompassing 500 MW of data center load alongside behind-the-meter on-site generation, without naming a source. Whether this is IT or facility load is not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"phase","as_of":"2026-10-05","basis":"planned","metric":"power_capacity","note":"Reported second-hand: Bisnow attributes this to the Austin Business Journal.","phase_label":"Potential addition by an unnamed tenant","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"Bisnow, citing the Austin Business Journal, reported that the developers did not yet own the site.","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"acres","value":664},{"applies_to":"campus","as_of":"2026-10-05","basis":"planned","metric":"jobs_permanent","note":"Full-time jobs estimated in a report commissioned for the project, as cited by Bisnow.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":320}],"milestones":[{"date":"2026-09","event":"other","kind":"actual","note":"Developers withdrew their annexation and zoning application to negotiate further on noise, water use, setbacks and community benefits, about two weeks after the planning and zoning commission delayed the item for 90 days in August.","source_ids":["s1","s2","s3"]},{"date":"2026-10-08","event":"other","kind":"actual","note":"Taylor City Council unanimously approved the agreement to annex the planned development at its Thursday meeting, which KUT had said was scheduled for 8 October.","source_ids":["s2","s3"]}],"name":"Taylor Technology Campus (Big Watt Digital and PowerHouse)","notes":"Status stays proposed: the approval clears annexation, but no construction start, tenant or site purchase was reported. Per a city press release cited by Bisnow, cooling is closed-loop with reclaimed water (initial fill about 1.6 million gallons, no potable water), and the developers pay for utility improvements and landscaping buffers. KUT reports about USD 28.2 million in community investments, including more than USD 10 million for Taylor ISD and local students. A commissioned report cited by Bisnow estimated about USD 1.4 billion of gross tax revenue for Taylor from 2027 to 2046; no capital investment figure was found. Taylor projects by KDC and Blueprint Projects are different builds.","parties":[{"name":"Big Watt Digital","role":"developer","source_ids":["s1","s2","s3"]},{"name":"PowerHouse Data Centers","role":"developer","source_ids":["s1","s2","s3"]},{"name":"City of Taylor","note":"Negotiated an annexation agreement letting it set standards on water use, noise, setbacks and air quality; the council approved it unanimously.","role":"government","source_ids":["s2","s3"]}],"power_sources":[{"description":"Behind-the-meter on-site power plant intended to meet the campus's electricity needs; the fuel is not stated by the developers or the city in the cited sources, though a resident opposing the deal referred to gas power plants.","source_ids":["s1","s2","s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006121233/https://www.bisnow.com/news/austin-san-antonio/data-center/taylor-deciding-annexation-zoning-data-center-campus-powerhouse","id":"s1","published":"2026-10-05","publisher":"Bisnow","title":"Austin Suburb Set To Decide On Annexation, Zoning For Data Center Campus","type":"trade_press","url":"https://www.bisnow.com/news/austin-san-antonio/data-center/taylor-deciding-annexation-zoning-data-center-campus-powerhouse"},{"accessed":"2026-10-09","id":"s2","published":"2026-10-02","publisher":"KUT News","title":"Taylor has struck a deal on a nearby data center, allowing it to annex the site and set conditions","type":"news","url":"https://www.kut.org/energy-environment/2026-10-02/taylor-annexing-data-center-development"},{"accessed":"2026-10-09","id":"s3","published":"2026-10-09","publisher":"KUT News","title":"Taylor City Council approves deal to clear the way for a nearby data center and power plant","type":"news","url":"https://www.kut.org/energy-environment/2026-10-09/taylor-tx-annex-data-center-power-plant"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Taylor, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Taylor,_Texas"}],"status":"proposed","status_as_of":"2026-10-09","status_source_ids":["s3"],"summary":"Proposed 664-acre data center campus with an on-site power plant at 3301 Farm to Market Road 112, just outside Taylor in unincorporated Williamson County, Texas, developed by Big Watt Digital and PowerHouse Data Centers. Bisnow describes 500 MW of data center load with behind-the-meter generation and, citing the Austin Business Journal, says an unnamed tenant could add 500 MW. After withdrawing their annexation and zoning request in September 2026, the developers struck a deal letting the city regulate water use, noise and air quality, with reclaimed-water closed-loop cooling and about USD 28.2 million in community investments; the City Council approved it unanimously on 8 October 2026.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"900327af-48bd-5ddf-a20d-83ef31e1ec24","s2":"76979786-74cf-5050-ae76-55068bbd2c36","s3":"1f5b7d3a-f4d6-5215-8d66-ac2de4a9cb41","s4":"20bca9c3-7ad1-5ecb-b2f3-0f993680faf7"},"source_file":"datacenters/projects/powerhouse-big-watt-taylor.json","source_record_id":"powerhouse-big-watt-taylor","source_record_sha256":"fdd4764a33b08456c9173f8afbfd7ea9a7fc8a466505b3f720f9157bcfcccc1c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b9ae36453c5bc2d5e7dbd46d36652e96b338fba97598638e5166d6b9de6f29b5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-450769770dfe5ea908d6/#project-8e72e640-c0e0-5e58-8a76-e53c011dcf92 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8e72e640-c0e0-5e58-8a76-e53c011dcf92.json
8efbf742-c042-5872-9bbe-82d576865125 | imported:semiconductor-atlas:cloudhq-gru-paulinia | vcc-site-68fa7b1f6e39bd438e45 | imported:semiconductor-atlas:cloudhq-gru-paulinia | CloudHQ GRU Campus (Paulínia) | Brazil | BR | -22.7709 | -47.1043 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Coordinates are the point published on CloudHQ's campus page; they were not checked against a parcel boundary. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 5e4b28c3-60ce-52ab-81c0-062eea76a31e | under_construction | 2026-04-08 | 188 | imported_documented_status | d6797f19-e57e-5c70-b1dd-3aa3aaf189b8 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"5e4b28c3-60ce-52ab-81c0-062eea76a31e","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"cd6622c7-d672-545b-971d-166ac0170bcd","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"f1464677-58f0-5227-903f-fe8a10798af0","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"d6797f19-e57e-5c70-b1dd-3aa3aaf189b8","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"bae34ad9-7602-520e-ac0d-95f1e9411f57","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"bae34ad9-7602-520e-ac0d-95f1e9411f57","notes":"Civil construction contractor.","party":"Afonso França Engenharia","relationship_scope":"unknown","role":"builder","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"d6797f19-e57e-5c70-b1dd-3aa3aaf189b8","notes":"Engineering partner for the power infrastructure and substation.","party":"LZA Engenharia","relationship_scope":"unknown","role":"builder","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"bae34ad9-7602-520e-ac0d-95f1e9411f57","notes":"Engineering partner for the power infrastructure and substation.","party":"LZA Engenharia","relationship_scope":"unknown","role":"builder","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"d6797f19-e57e-5c70-b1dd-3aa3aaf189b8","notes":"Substation equipment supplier.","party":"WEG","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"cloudhq-gru-paulinia"},{"evidence_id":"bae34ad9-7602-520e-ac0d-95f1e9411f57","notes":"Substation equipment supplier.","party":"WEG","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"cloudhq-gru-paulinia"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://switchgear-magazine.com/tm-news/business/cloudhq-powers-sao-paulo-data-campus/ | https://cloudhq.com/campus/gru-campus/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve CloudHQ GRU Campus (Paulínia) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"cloudhq-gru-paulinia"},"record":{"aliases":["GRU Campus","GRU Technology Campus","CloudHQ Paulínia"],"id":"cloudhq-gru-paulinia","last_reviewed":"2026-10-09","location":{"admin1":"São Paulo","admin2":"Paulínia","country":"BR","lat":-22.77089,"locality":"Paulínia","lon":-47.10425,"note":"Coordinates are the point published on CloudHQ's campus page; they were not checked against a parcel boundary.","precision":"approximate_site","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2023-03-14","basis":"planned","metric":"power_capacity","note":"Six buildings of 48 MW each in two phases; CloudHQ's undated page still lists 288 MW.","power_scope":"it_load","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"MW","value":288},{"applies_to":"phase","as_of":"2026-04-08","basis":"planned","metric":"power_capacity","phase_label":"Phase 1 (three 48 MW buildings)","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s5"],"unit":"MW","value":144},{"applies_to":"phase","as_of":"2026-03-12","basis":"planned","metric":"power_capacity","note":"Larger phase 1 configuration reported in March 2026; it conflicts with the 48 MW building plan.","phase_label":"Phase 1 (three 120 MW buildings)","power_scope":"it_load","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":360},{"applies_to":"campus","as_of":"2026-04-08","basis":"operational","metric":"power_capacity","note":"Rating of the dedicated on-site substation, which was energised and connected to the national grid by early 2026.","power_scope":"grid_connection","qualifier":"range","source_ids":["s5"],"unit":"MW","value":225,"value_high":250},{"applies_to":"campus","as_of":"2026-03-12","basis":"planned","metric":"power_capacity","note":"Total network capacity the campus grid link could support, per Switchgear Magazine.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s4"],"unit":"MW","value":1100},{"applies_to":"campus","as_of":"2023-03-07","basis":"announced","metric":"investment","note":"Construction Review also cites USD 2 to 3 billion at the 2023 groundbreaking.","qualifier":"exact","source_ids":["s3","s5"],"unit":"USD","value":3000000000},{"applies_to":"campus","as_of":"2026-04-08","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2","s5"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2023-03-14","basis":"planned","metric":"jobs_construction","note":"Expected civil construction jobs.","qualifier":"approximately","source_ids":["s2"],"unit":"count","value":1000}],"milestones":[{"date":"2023-03","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony attended by Brazil's vice-president and the São Paulo governor.","source_ids":["s2","s3"]},{"date":"2024-H1","event":"first_operational","kind":"planned","note":"Completion target reported at the 2023 groundbreaking; it was missed.","source_ids":["s2"]},{"date":"2026-03","event":"other","kind":"actual","note":"Reported by 12 March 2026: the on-site 440 kV substation was energised and connected to the national grid.","source_ids":["s4","s5"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Staged commissioning and first operations expected through 2027.","source_ids":["s5"]}],"name":"CloudHQ GRU Campus (Paulínia)","notes":"No dated CloudHQ statement on building completion or a signed tenant was found. Capacity figures conflict: CloudHQ's undated page and 2023 coverage give six 48 MW buildings (288 MW), Switchgear Magazine (citing BNamericas) gives three 120 MW buildings in phase 1, and Construction Review gives 288 to 360 MW across six buildings, with more than 210 MW expected in early operations. Construction Review's article is dated 8 April 2026 as updated from a September 2025 original.","parties":[{"name":"CloudHQ","role":"developer","source_ids":["s1","s2","s3","s4","s5"]},{"name":"Afonso França Engenharia","note":"Civil construction contractor.","role":"builder","source_ids":["s5"]},{"name":"LZA Engenharia","note":"Engineering partner for the power infrastructure and substation.","role":"builder","source_ids":["s4","s5"]},{"name":"WEG","note":"Substation equipment supplier.","role":"hardware_supplier","source_ids":["s4","s5"]}],"power_sources":[{"description":"A dedicated on-site substation connected at high voltage (440 kV) to Brazil's national transmission network.","source_ids":["s1","s4","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251012045820/https://cloudhq.com/campus/gru-campus/","id":"s1","published":null,"publisher":"CloudHQ","title":"GRU Campus","type":"company","url":"https://cloudhq.com/campus/gru-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260123050109/https://capacityglobal.com/news/cloudhq-breaks-ground-on-first-data-centre-campus-in-brazil/","id":"s2","published":"2023-03-14","publisher":"Capacity","title":"CloudHQ breaks ground on first data centre campus in Brazil","type":"trade_press","url":"https://capacityglobal.com/news/cloudhq-breaks-ground-on-first-data-centre-campus-in-brazil/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20240805160553/https://thetechcapital.com/cloudhq-breaks-ground-on-3-billion-data-centre-in-brazil-heres-the-plan/","id":"s3","published":"2023-03-07","publisher":"The Tech Capital","title":"CloudHQ breaks ground on $3 billion data centre in Brazil - here's the plan","type":"trade_press","url":"https://thetechcapital.com/cloudhq-breaks-ground-on-3-billion-data-centre-in-brazil-heres-the-plan/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260414031849/https://switchgear-magazine.com/tm-news/business/cloudhq-powers-sao-paulo-data-campus/","id":"s4","published":"2026-03-12","publisher":"Switchgear Magazine","title":"CloudHQ powers São Paulo data campus","type":"trade_press","url":"https://switchgear-magazine.com/tm-news/business/cloudhq-powers-sao-paulo-data-campus/"},{"accessed":"2026-10-09","id":"s5","published":"2026-04-08","publisher":"Construction Review Online","title":"CloudHQ's Paulínia hyperscale campus powers up as Brazil's largest data hub enters delivery phase","type":"trade_press","url":"https://constructionreviewonline.com/cloudhq-breaks-ground-on-the-new-paulinia-hyperscale-campus-in-brazil/"}],"status":"under_construction","status_as_of":"2026-04-08","status_source_ids":["s4","s5"],"summary":"CloudHQ's first campus in Brazil, in Paulínia in the Campinas region of São Paulo state, was launched with a groundbreaking in March 2023 as a USD 3 billion project of six buildings and up to 288 MW of IT load, in two phases of three 48 MW buildings. Its on-site high-voltage substation, of about 225 to 250 MW, was energised and connected to Brazil's grid by early 2026, well after the original 2024 opening target. 2026 trade reports describe the campus as ready for tenants, with phased commissioning and first operations expected through 2027; one report gives a larger first phase of three 120 MW buildings.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"5e4b28c3-60ce-52ab-81c0-062eea76a31e","s2":"cd6622c7-d672-545b-971d-166ac0170bcd","s3":"f1464677-58f0-5227-903f-fe8a10798af0","s4":"d6797f19-e57e-5c70-b1dd-3aa3aaf189b8","s5":"bae34ad9-7602-520e-ac0d-95f1e9411f57"},"source_file":"datacenters/projects/cloudhq-gru-paulinia.json","source_record_id":"cloudhq-gru-paulinia","source_record_sha256":"96a8d7dec29e5d2196eaddda24447703730a2eb72394ef4c320f043df43da59b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4faf2ad916d74ed2d2f6795bd9016689c4edec70387e1d00fa72c750cb7b3fe7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-68fa7b1f6e39bd438e45/#project-8efbf742-c042-5872-9bbe-82d576865125 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8efbf742-c042-5872-9bbe-82d576865125.json
8f5c2434-0b2d-547e-ac2c-e25ddeefe1b7 | curated:schwarz-digits-luebbenau-campus:current-build | vcc-site-8a73ede727ab01225667 | curated:schwarz-digits-luebbenau-campus | Lübbenau Data Center Current Build | Germany | DE | 51.8471 | 13.961 | Point | campus | copy_exact_LGB_address_WKT_point_to_GeoJSON | exact_operator_street_house_number_postal_code_city_to_official_LGB_address_object | official_house_number_address_reference_point | official_source | campus_locator | Official Kraftwerkstraße 24 address point only. No exact new data-center hall, active construction footprint, site boundary or surveyed entrance is asserted. LGB metadata permits a parcel point when an address is reserved or has no building. The source supplies no quantitative positional accuracy for this record; decimal places do not establish survey precision. |  | No numerical positional accuracy or reserved-address classification supplied for this individual government address record. | 905c48e3-76d6-5aed-8e41-0ca3486f7998 | under_construction | 2026-08-18 | 56 | authoritative_physical_status_update | db51e0ad-4722-5125-8298-a867e91485b6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"f37710dd-c563-56f6-aca4-c10750e880b4","notes":null,"party":"Schwarz Digits","relationship_scope":"unknown","role":"developer","source_record_id":"schwarz-digits-luebbenau"},{"evidence_id":"2180537b-28c6-58b2-828b-653522117316","notes":null,"party":"Schwarz Digits","relationship_scope":"unknown","role":"developer","source_record_id":"schwarz-digits-luebbenau"},{"evidence_id":"23891a1e-e8d2-5b57-afb7-c97a6aa838d7","notes":null,"party":"Schwarz Digits","relationship_scope":"unknown","role":"developer","source_record_id":"schwarz-digits-luebbenau"},{"evidence_id":"2180537b-28c6-58b2-828b-653522117316","notes":"Schwarz Group cloud provider; the site is its fifth data center.","party":"STACKIT","relationship_scope":"unknown","role":"operator","source_record_id":"schwarz-digits-luebbenau"},{"evidence_id":"23891a1e-e8d2-5b57-afb7-c97a6aa838d7","notes":"Group-internal workloads such as logistics, payments and customer data.","party":"Lidl","relationship_scope":"unknown","role":"tenant","source_record_id":"schwarz-digits-luebbenau"},{"evidence_id":"23891a1e-e8d2-5b57-afb7-c97a6aa838d7","notes":"Group-internal workloads.","party":"Kaufland","relationship_scope":"unknown","role":"tenant","source_record_id":"schwarz-digits-luebbenau"},{"evidence_id":"3f27d558-e84e-56cd-8bb9-7ee9b5f1dd99","notes":"Named as a client in a 2026 news report.","party":"Baden-Württemberg Police","relationship_scope":"unknown","role":"tenant","source_record_id":"schwarz-digits-luebbenau"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected |  | STACKIT |  | Baden-Württemberg Police; Kaufland; Lidl |  | https://www.convis.com/neues-von-der-baustelle-pressetermin-am-mega-rechenzentrum-in-luebbenau/ | https://search.geobasis-bb.de/v2/search?query=Kraftwerkstra%C3%9Fe&limit=50&filter%5BassignMunicipality.keyword%5D=L%C3%BCbbenau%2FSpreewald%20%5BLubnjow%2FB%C5%82ota%5D | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same Schwarz Digits/STACKIT development on the former Luebbenau power-plant site. Both records describe construction of that named development; town centroid is not the site.","source_record_id":"schwarz-digits-luebbenau","target_project_stable_key":"curated:schwarz-digits-luebbenau-campus:current-build"},"record":{"aliases":["STACKIT Lübbenau"],"id":"schwarz-digits-luebbenau","last_reviewed":"2026-10-09","location":{"admin1":"Brandenburg","admin2":"Oberspreewald-Lausitz","country":"DE","lat":51.868,"locality":"Lübbenau/Spreewald","lon":13.9689,"note":"Nominatim centroid of Lübbenau/Spreewald; sources describe a former power plant site in the town but give no address.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-18","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"EUR","value":11000000000},{"applies_to":"phase","as_of":"2026-01-12","basis":"under_construction","metric":"power_capacity","note":"Reported as the connection capacity of the initial construction phase; further modules are planned.","phase_label":"First phase","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-08-24","basis":"planned","metric":"accelerators","qualifier":"up_to","source_ids":["s1","s2","s4"],"unit":"count","value":100000},{"applies_to":"campus","as_of":"2025-11-18","basis":"planned","metric":"land_area","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"hectares","value":13},{"applies_to":"campus","as_of":"2026-08-24","basis":"planned","metric":"jobs_permanent","note":"Initial staffing (about 30 security and 30 technical roles).","qualifier":"approximately","source_ids":["s4"],"unit":"count","value":60}],"milestones":[{"date":"2025-11-18","event":"announced","kind":"actual","source_ids":["s2"]},{"date":"2025-11","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony reported with the announcement.","source_ids":["s2"]},{"date":"2027-Q4","event":"first_operational","kind":"planned","note":"First module and server rooms due by the end of 2027.","source_ids":["s1","s3","s4"]}],"name":"Schwarz Digits Lübbenau data center","notes":"Despite the Euronews headline wording, the article describes active construction with first server rooms due end-2027. Reports that Schwarz Group and Deutsche Telekom discussed a joint EU AI gigafactory bid were unconfirmed by the companies and are not tied to this site.","parties":[{"name":"Schwarz Digits","role":"developer","source_ids":["s1","s2","s3"]},{"name":"STACKIT","note":"Schwarz Group cloud provider; the site is its fifth data center.","role":"operator","source_ids":["s2"]},{"name":"Lidl","note":"Group-internal workloads such as logistics, payments and customer data.","role":"tenant","source_ids":["s3"]},{"name":"Kaufland","note":"Group-internal workloads.","role":"tenant","source_ids":["s3"]},{"name":"Baden-Württemberg Police","note":"Named as a client in a 2026 news report.","role":"tenant","source_ids":["s4"]}],"power_sources":[{"description":"Company aims to run the site entirely on green electricity; supply contracts are not described.","source_ids":["s1","s2"],"type":"other"},{"description":"Rooftop and campus photovoltaics expected to produce up to 520,000 kWh per year.","source_ids":["s1","s2","s4"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-19","publisher":"ESM Magazine","title":"Schwarz Digits Invests €11bn In New Data Centre","type":"trade_press","url":"https://www.esmmagazine.com/technology/schwarz-digits-invests-e11bn-in-new-data-centre-300560"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260117040451/https://www.startbase.com/news/schwarz-digits-investiert-11-milliarden-euro-in-digitale-souveraenitaet/","id":"s2","published":"2025-11-18","publisher":"Startbase","title":"Schwarz Digits investiert 11 Milliarden Euro in digitale Souveränität","type":"trade_press","url":"https://www.startbase.com/news/schwarz-digits-investiert-11-milliarden-euro-in-digitale-souveraenitaet/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260228082658/https://thetechcapital.com/lidl-and-kaufland-owner-advances-12-billion-data-centre-project-amid-eu-ai-infrastructure-talks/","id":"s3","published":"2026-01-12","publisher":"The Tech Capital","title":"Lidl and Kaufland owner advances $12 billion data centre project amid EU AI infrastructure talks","type":"trade_press","url":"https://thetechcapital.com/lidl-and-kaufland-owner-advances-12-billion-data-centre-project-amid-eu-ai-infrastructure-talks/"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-24","publisher":"Euronews","title":"Un des plus grands centres de données IA d'Europe à 11 milliards d'euros ouvre dans le Brandebourg","type":"news","url":"https://fr.euronews.com/my-europe/2026/08/24/un-des-plus-grands-centres-de-donnees-ia-deurope-a-11-milliards-deuros-ouvre-dans-le-brand"}],"status":"under_construction","status_as_of":"2026-08-24","status_source_ids":["s4"],"summary":"Schwarz Digits, the IT arm of Lidl and Kaufland owner Schwarz Group, is building an EUR 11 billion AI and cloud data center on a 13-hectare former power plant site in Lübbenau (Spreewald), Brandenburg. The first phase has a 200 MW connection and the modular design allows up to 100,000 GPUs over time. Work began in November 2025; the first module is due by the end of 2027, and waste heat is to feed the town's district heating from 2028. The group's cloud unit STACKIT will run it.","workloads":["ai_unspecified","cloud","enterprise"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f37710dd-c563-56f6-aca4-c10750e880b4","s2":"2180537b-28c6-58b2-828b-653522117316","s3":"23891a1e-e8d2-5b57-afb7-c97a6aa838d7","s4":"3f27d558-e84e-56cd-8bb9-7ee9b5f1dd99"},"source_file":"datacenters/projects/schwarz-digits-luebbenau.json","source_record_id":"schwarz-digits-luebbenau","source_record_sha256":"9de167e8b0193e174395c2d0ff0f822919f334b7d7d9e2bc4b4bb25ec6ea9ab6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7442cfe4646dc7f890b689770f56fd5278cbc0c9d472f36a35f0c4f925e52e03"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8a73ede727ab01225667/#project-8f5c2434-0b2d-547e-ac2c-e25ddeefe1b7 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8f5c2434-0b2d-547e-ac2c-e25ddeefe1b7.json
8f8c241d-ee6b-5182-8a76-ebb101a3f4c2 | curated:verne-mantsala-data-center-campus:current-development | vcc-site-00808116377785b5c125 | curated:verne-mantsala-data-center-campus | Verne Mäntsälä Current Campus Development | Finland | FI | 60.6353 | 25.2862 | Polygon | campus | direct_geometry | authoritative_site_plan | official_cadastral_campus_parcel_boundary | official_source | official_boundary | Exact municipal cadastral polygon for property 505-407-7-137, inherited through the explicit project-to-campus link; it is the full campus parcel, not a building or the current 70 MW development footprint. |  | official source does not state positional accuracy | 708cee21-4519-5840-a07c-2f1f8398cb87 | under_construction | 2026-06-17 | 118 | authoritative_construction_start | 0176052f-124b-5bf9-b361-a5c97cb98b62 | recent_authoritative_physical_observation_plus_official_boundary | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.verne.co/news/news-verne-begins-construction-of-the-first-70-mw-on-its-data-center-campus-in-m%C3%A4nts%C3%A4l%C3%A4 | https://mantsala.karttatiimi.fi/maps/search.ashx | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-00808116377785b5c125/#project-8f8c241d-ee6b-5182-8a76-ebb101a3f4c2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8f8c241d-ee6b-5182-8a76-ebb101a3f4c2.json
8fc14c03-d70a-5634-81e4-883a2fd6eec9 | imported:semiconductor-atlas:cipher-barber-lake | vcc-site-ad9a83cc2040a19f7750 | imported:semiconductor-atlas:cipher-barber-lake | Cipher Barber Lake data center | United States | US | 32.3961 | -100.8622 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from Wikipedia; Cipher places the Barber Lake site in Colorado City but gives no address or county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 51b65782-8eb9-5ff6-8178-9322da57ed43 | under_construction | 2026-09-25 | 18 | imported_documented_status | 22c3b82d-1a57-5d67-aecc-52234ce7a7de | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"51b65782-8eb9-5ff6-8178-9322da57ed43","notes":"Announced the lease as Cipher Mining in 2025; the 2026 filings under the same SEC registrant use the name Cipher Digital.","party":"Cipher Digital (formerly Cipher Mining)","relationship_scope":"unknown","role":"developer","source_record_id":"cipher-barber-lake"},{"evidence_id":"b855d554-333a-545c-a8c7-721832da265f","notes":"Announced the lease as Cipher Mining in 2025; the 2026 filings under the same SEC registrant use the name Cipher Digital.","party":"Cipher Digital (formerly Cipher Mining)","relationship_scope":"unknown","role":"developer","source_record_id":"cipher-barber-lake"},{"evidence_id":"22c3b82d-1a57-5d67-aecc-52234ce7a7de","notes":"Announced the lease as Cipher Mining in 2025; the 2026 filings under the same SEC registrant use the name Cipher Digital.","party":"Cipher Digital (formerly Cipher Mining)","relationship_scope":"unknown","role":"developer","source_record_id":"cipher-barber-lake"},{"evidence_id":"51b65782-8eb9-5ff6-8178-9322da57ed43","notes":"Lessee under the Barber Lake lease; Google backstops $1.4 billion of its obligations. The September 2026 extension adds a binding 10-year commitment from an unnamed leading AI lab.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"cipher-barber-lake"},{"evidence_id":"22c3b82d-1a57-5d67-aecc-52234ce7a7de","notes":"Lessee under the Barber Lake lease; Google backstops $1.4 billion of its obligations. The September 2026 extension adds a binding 10-year commitment from an unnamed leading AI lab.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"cipher-barber-lake"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | Fluidstack |  | https://www.sec.gov/Archives/edgar/data/1819989/000181998926000043/barberlakeleaseamendmentpr.htm | https://www.sec.gov/Archives/edgar/data/1819989/000095010325012168/dp234624_ex9901.htm | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Cipher Barber Lake data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"cipher-barber-lake"},"record":{"aliases":["Barber Lake"],"id":"cipher-barber-lake","last_reviewed":"2026-10-09","location":{"admin1":"Texas","country":"US","lat":32.3961,"locality":"Colorado City","lon":-100.8622,"note":"Town coordinates from Wikipedia; Cipher places the Barber Lake site in Colorado City but gives no address or county.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-09-25","basis":"contracted","metric":"power_capacity","power_scope":"it_load","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":168},{"applies_to":"campus","as_of":"2025-09-25","basis":"planned","metric":"power_capacity","note":"Maximum gross capacity supporting the leased IT load.","power_scope":"facility","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":244},{"applies_to":"phase","as_of":"2025-09-25","basis":"planned","metric":"power_capacity","note":"Cipher cites potential for a 500 MW capacity expansion at the site; not leased or scheduled.","phase_label":"Potential expansion","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2025-09-25","basis":"reported","metric":"land_area","note":"Described as surrounding land at the site.","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":587}],"milestones":[{"date":"2025-09-25","event":"announced","kind":"actual","note":"Fluidstack lease, Google backstop and warrants announced.","source_ids":["s1"]},{"date":"2026-08-04","event":"other","kind":"actual","note":"Cipher reported that the tenant had begun beneficial use, including partial occupancy and network rack deployment.","source_ids":["s2","s3"]},{"date":"2026-09-25","event":"other","kind":"actual","note":"Lease extended from 10 to 20 years with an added commitment from an unnamed AI lab.","source_ids":["s4"]},{"date":"2026-Q4","event":"first_operational","kind":"planned","note":"First data hall delivery and rent commencement; the August 2026 update had targeted initial delivery in September 2026.","source_ids":["s4","s3"]},{"date":"2027-Q1","event":"fully_operational","kind":"planned","note":"Last data halls expected.","source_ids":["s4"]}],"name":"Cipher Barber Lake data center","parties":[{"name":"Cipher Digital (formerly Cipher Mining)","note":"Announced the lease as Cipher Mining in 2025; the 2026 filings under the same SEC registrant use the name Cipher Digital.","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Fluidstack","note":"Lessee under the Barber Lake lease; Google backstops $1.4 billion of its obligations. The September 2026 extension adds a binding 10-year commitment from an unnamed leading AI lab.","role":"tenant","source_ids":["s1","s4"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260714071123/https://www.sec.gov/Archives/edgar/data/1819989/000095010325012168/dp234624_ex9901.htm","id":"s1","published":"2025-09-25","publisher":"Cipher Mining","title":"Cipher Mining Signs 168 MW, 10-Year AI Hosting Agreement with Fluidstack (Form 8-K Exhibit 99.1)","type":"company","url":"https://www.sec.gov/Archives/edgar/data/1819989/000095010325012168/dp234624_ex9901.htm"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-04","publisher":"Cipher Digital","title":"Cipher Digital Provides Second Quarter 2026 Business Update (Form 8-K Exhibit 99.1)","type":"company","url":"https://www.sec.gov/Archives/edgar/data/1819989/000181998926000038/q226_earningsxprxdraftxvf.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006075929/https://www.sec.gov/Archives/edgar/data/1819989/000181998926000038/cipherdigital_businessup.htm","id":"s3","published":"2026-08-04","publisher":"Cipher Digital","title":"Cipher Digital business update presentation (Form 8-K Exhibit 99.2)","type":"company","url":"https://www.sec.gov/Archives/edgar/data/1819989/000181998926000038/cipherdigital_businessup.htm"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-25","publisher":"Cipher Digital","title":"Cipher Digital Expands Barber Lake Lease Term to 20 Years, Increasing Revenue to Over $9 Billion (Form 8-K Exhibit 99.1)","type":"company","url":"https://www.sec.gov/Archives/edgar/data/1819989/000181998926000043/barberlakeleaseamendmentpr.htm"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Colorado City, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Colorado_City,_Texas"}],"status":"under_construction","status_as_of":"2026-09-25","status_source_ids":["s4","s2"],"summary":"AI hosting data center under construction by Cipher Mining, since renamed Cipher Digital, at its Barber Lake site in Colorado City, Texas. In September 2025 Fluidstack leased 168 MW of critical IT load, supported by up to 244 MW of gross capacity, for an initial 10 years; Google backstopped $1.4 billion of Fluidstack's lease obligations and received warrants in Cipher. In September 2026 the lease was extended to 20 years, backed by an added 10-year commitment from an unnamed AI lab, lifting contracted revenue to more than $9 billion. The tenant had begun partial occupancy by August 2026, and data halls are due from the fourth quarter of 2026 through the first quarter of 2027.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"51b65782-8eb9-5ff6-8178-9322da57ed43","s2":"b855d554-333a-545c-a8c7-721832da265f","s3":"9ddac39e-e50f-52b9-9c46-ebdf7cabe507","s4":"22c3b82d-1a57-5d67-aecc-52234ce7a7de","s5":"ff53866a-0576-5804-b5e8-d383b37c2521"},"source_file":"datacenters/projects/cipher-barber-lake.json","source_record_id":"cipher-barber-lake","source_record_sha256":"d3ec6727593ff92e05524c4162ede0f1fc5ba4db9109696c94c4021d888ba151","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3b80933abba304d18d78b0ea2c435b0243f7519c19186ac4a394940d0100ae0c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ad9a83cc2040a19f7750/#project-8fc14c03-d70a-5634-81e4-883a2fd6eec9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/8fc14c03-d70a-5634-81e4-883a2fd6eec9.json
9002afae-5b81-5c8c-a6f9-4504c91e8624 | imported:semiconductor-atlas:xai-colossus-2-memphis | vcc-site-62e42a722eab77bd5345 | imported:semiconductor-atlas:xai-colossus-2-memphis | xAI Colossus 2 (Memphis) | United States | US | 34.998 | -90.0349 | Point | project | imported_reference_point | imported_reference_point | site | compiled_reference | project_locator | Center of the OpenStreetMap building tagged 'xAI Macrohard Colossus 2' at 5420 Tulane Road, taken from this project's OpenStreetMap data center layer (no geocoder call); Cleanview gives the same address. MLGW describes the facility as on Tulane Road very near the Tennessee-Mississippi line. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 206aff59-d746-56e5-af7e-4ce594a6af30 | partially_operational | 2026-10-05 | 8 | imported_documented_status | df6ae365-3303-5098-805a-fccbbb55eb8a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"69c0a462-635f-5a28-a0fa-2addf0737441","notes":null,"party":"xAI","relationship_scope":"unknown","role":"developer","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"206aff59-d746-56e5-af7e-4ce594a6af30","notes":null,"party":"xAI","relationship_scope":"unknown","role":"developer","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"df6ae365-3303-5098-805a-fccbbb55eb8a","notes":"Epoch AI (analyst) lists the owner as SpaceXAI and WMC's July 2026 report refers to SpaceXAI; Anthropic describes its Colossus 2 capacity agreement as being with SpaceX. No company filing reviewed states ownership.","party":"SpaceX","relationship_scope":"unknown","role":"owner","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"535d58bb-f29e-57f3-a441-be4e33a629eb","notes":"Epoch AI (analyst) lists the owner as SpaceXAI and WMC's July 2026 report refers to SpaceXAI; Anthropic describes its Colossus 2 capacity agreement as being with SpaceX. No company filing reviewed states ownership.","party":"SpaceX","relationship_scope":"unknown","role":"owner","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"e9d820a3-caef-54b1-85a9-fa80a43dae22","notes":"Epoch AI (analyst) lists the owner as SpaceXAI and WMC's July 2026 report refers to SpaceXAI; Anthropic describes its Colossus 2 capacity agreement as being with SpaceX. No company filing reviewed states ownership.","party":"SpaceX","relationship_scope":"unknown","role":"owner","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"e9d820a3-caef-54b1-85a9-fa80a43dae22","notes":"Anthropic's May 2026 funding announcement cites an agreement with SpaceX for GPU capacity in Colossus 1 and Colossus 2; the share of Colossus 2 involved is not stated.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"df6ae365-3303-5098-805a-fccbbb55eb8a","notes":"Anthropic's May 2026 funding announcement cites an agreement with SpaceX for GPU capacity in Colossus 1 and Colossus 2; the share of Colossus 2 involved is not stated.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"df6ae365-3303-5098-805a-fccbbb55eb8a","notes":"Listed as a user by Epoch AI (analyst); reported but not confirmed by Cursor, xAI or SpaceX in the sources reviewed.","party":"Cursor","relationship_scope":"unknown","role":"tenant","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"3dd97b1c-26ad-5403-99cb-2ed24b8f815f","notes":"xAI affiliate that bought the former Duke Energy site at 2875 Stanton Road South, Southaven, and holds the Mississippi air permit for the turbines that power Colossus 2.","party":"MZX Tech LLC","relationship_scope":"unknown","role":"power_supplier","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"7164895e-ef5e-50ae-a468-736371acfdf4","notes":"xAI affiliate that bought the former Duke Energy site at 2875 Stanton Road South, Southaven, and holds the Mississippi air permit for the turbines that power Colossus 2.","party":"MZX Tech LLC","relationship_scope":"unknown","role":"power_supplier","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"09b2d5a9-29d7-512d-84e2-65e09c2bfd97","notes":"xAI affiliate that bought the former Duke Energy site at 2875 Stanton Road South, Southaven, and holds the Mississippi air permit for the turbines that power Colossus 2.","party":"MZX Tech LLC","relationship_scope":"unknown","role":"power_supplier","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"206aff59-d746-56e5-af7e-4ce594a6af30","notes":"Serves the site with water and limited gas; as of May 2025 xAI had not filed a final request for grid power at Tulane Road.","party":"Memphis Light, Gas and Water","relationship_scope":"unknown","role":"utility","source_record_id":"xai-colossus-2-memphis"},{"evidence_id":"7164895e-ef5e-50ae-a468-736371acfdf4","notes":"Approved the Southaven turbine air permit on March 10, 2026.","party":"Mississippi Environmental Quality Permit Board","relationship_scope":"unknown","role":"government","source_record_id":"xai-colossus-2-memphis"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | SpaceX |  |  | Anthropic; Cursor |  | https://epoch.ai/data/ai-data-centers/directory/colossus-2 | https://www.mlgw.com/images/content/files/pdf/new/5-5-25%20xAI%20Update.pdf | [{"identity_decision":{"decision":"unique_site","flags":["source_site_point_not_surveyed_boundary"],"rationale":"No matching named development in the 201-project release. Preserve xAI Colossus 2 (Memphis) as an independent source record; its site locator does not itself establish a surveyed physical site.","source_record_id":"xai-colossus-2-memphis","source_relations":[{"reason":"Colossus 2 Memphis and MACROHARDRR Southaven are separately named facilities in Tennessee and Mississippi; nearby coordinates do not merge them.","relationship":"separate_nearby_facilities","source_id":"xai-macrohardrr-southaven"}]},"record":{"aliases":["Colossus II"],"id":"xai-colossus-2-memphis","last_reviewed":"2026-10-09","location":{"admin1":"Tennessee","country":"US","lat":34.998,"locality":"Memphis","lon":-90.0349,"note":"Center of the OpenStreetMap building tagged 'xAI Macrohard Colossus 2' at 5420 Tulane Road, taken from this project's OpenStreetMap data center layer (no geocoder call); Cleanview gives the same address. MLGW describes the facility as on Tulane Road very near the Tennessee-Mississippi line.","precision":"site","source_ids":["s2","s9"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-15","basis":"operational","metric":"power_capacity","note":"Epoch AI analyst estimate, not a company disclosure, from its June 15, 2026 satellite observation. Epoch projects about 1,531 MW of IT load in the first quarter of 2027, with a third building estimated to be complete in February 2027.","power_scope":"it_load","qualifier":"approximately","source_ids":["s8"],"unit":"MW","value":946},{"applies_to":"campus","as_of":"2026-05","basis":"operational","metric":"power_capacity","note":"Cleanview count of about 59 temporary turbines totaling about 1.3 GW in mid-May 2026 imagery of the Southaven generation site (analyst estimate, not a company disclosure). Cleanview reports no utility power at Colossus 2.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s9"],"unit":"MW","value":1300},{"applies_to":"campus","as_of":"2026-03-10","basis":"permitted","metric":"power_capacity","note":"41 permanent gas turbines permitted in March 2026 at the Southaven plant site. The 1.2 GW figure comes from Cleanview (analyst) and WMC; the permit coverage reviewed gives no capacity.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s9","s7","s4"],"unit":"MW","value":1200},{"applies_to":"campus","as_of":"2025-05-05","basis":"planned","metric":"power_capacity","note":"MLGW received an initial, unstudied request for 260 MW and had discussed options from 260 MW to 1.1 GW; xAI had not filed a final request as of May 2025.","power_scope":"grid_connection","qualifier":"range","source_ids":["s2"],"unit":"MW","value":260,"value_high":1100},{"accelerator_model":"NVIDIA GB200 and GB300","applies_to":"campus","as_of":"2026-05","basis":"installed","metric":"accelerators","note":"Cleanview figure (analyst estimate, not a company disclosure).","qualifier":"approximately","source_ids":["s9"],"unit":"count","value":550000},{"accelerator_model":"NVIDIA B200 and B300","applies_to":"campus","as_of":"2026-06-15","basis":"installed","metric":"accelerators","note":"Epoch AI analyst estimate, not a company disclosure: about 110,000 B200 and 330,000 B300 chips. It differs from Cleanview's figure; both are kept.","qualifier":"approximately","source_ids":["s8"],"unit":"count","value":440000},{"applies_to":"campus","as_of":"2026-10-05","basis":"reported","metric":"investment","note":"Epoch AI current capital cost estimate (analyst estimate, not a company disclosure); the page does not say what the figure includes.","qualifier":"approximately","source_ids":["s8"],"unit":"USD","value":35800000000}],"milestones":[{"date":"2025-02-28","event":"construction_started","kind":"actual","note":"Epoch AI dates land clearing next to the existing building from satellite imagery (analyst estimate, not a company disclosure).","source_ids":["s8"]},{"date":"2025-03","event":"site_acquired","kind":"actual","note":"WMC reported in March 2025 that xAI was buying about one million square feet of property in southwest Memphis; by May 2025 MLGW said xAI had secured the Tulane Road facility.","source_ids":["s1","s2"]},{"date":"2025-07","event":"other","kind":"actual","note":"xAI affiliate MZX Tech bought the former Duke Energy plant site in Southaven, Mississippi; Cleanview identifies it as the generation site for Colossus 2.","source_ids":["s3","s9"]},{"date":"2025-10","event":"first_operational","kind":"actual","note":"Approximate. Epoch AI's first nonzero compute estimate for the site, about 239 MW of IT load, is dated October 19, 2025 from satellite imagery (analyst estimate, not a company disclosure).","source_ids":["s8"]},{"date":"2026-03-10","event":"permit_approved","kind":"actual","note":"Mississippi permit board approved 41 gas turbines at the Southaven plant site.","source_ids":["s4"]},{"date":"2026-04-09","event":"other","kind":"actual","note":"SELC filed an appeal of the Southaven turbine air permit on behalf of the NAACP, Young Gifted & Green and the Safe and Sound Coalition.","source_ids":["s5"]},{"date":"2026-08","event":"other","kind":"planned","note":"Planned start of removing the 69 temporary Southaven turbines, to finish by July 2027 as a permanent 41-turbine plant replaces them.","source_ids":["s7"]}],"name":"xAI Colossus 2 (Memphis)","notes":"MACROHARDRR, the adjacent xAI building just across the state line in Southaven, is tracked separately as xai-macrohardrr-southaven. Some coverage labels it as part of Colossus 2, and the analyst sources cited here do not say whether their Colossus 2 estimates include it, so analyst figures for the two may overlap. Capacity, GPU and cost figures from Epoch AI and Cleanview are analyst estimates, not company disclosures.","parties":[{"name":"xAI","role":"developer","source_ids":["s1","s2"]},{"name":"SpaceX","note":"Epoch AI (analyst) lists the owner as SpaceXAI and WMC's July 2026 report refers to SpaceXAI; Anthropic describes its Colossus 2 capacity agreement as being with SpaceX. No company filing reviewed states ownership.","role":"owner","source_ids":["s8","s7","s6"]},{"name":"Anthropic","note":"Anthropic's May 2026 funding announcement cites an agreement with SpaceX for GPU capacity in Colossus 1 and Colossus 2; the share of Colossus 2 involved is not stated.","role":"tenant","source_ids":["s6","s8"]},{"name":"Cursor","note":"Listed as a user by Epoch AI (analyst); reported but not confirmed by Cursor, xAI or SpaceX in the sources reviewed.","role":"tenant","source_ids":["s8"]},{"name":"MZX Tech LLC","note":"xAI affiliate that bought the former Duke Energy site at 2875 Stanton Road South, Southaven, and holds the Mississippi air permit for the turbines that power Colossus 2.","role":"power_supplier","source_ids":["s3","s4","s5"]},{"name":"Memphis Light, Gas and Water","note":"Serves the site with water and limited gas; as of May 2025 xAI had not filed a final request for grid power at Tulane Road.","role":"utility","source_ids":["s2"]},{"name":"Mississippi Environmental Quality Permit Board","note":"Approved the Southaven turbine air permit on March 10, 2026.","role":"government","source_ids":["s4"]}],"power_sources":[{"description":"Behind-the-meter gas turbines at the former Duke Energy site in Southaven, Mississippi. Regulators permitted 41 permanent units in March 2026; WMC reported 69 turbines on site in July 2026, all to be removed by July 2027.","source_ids":["s4","s7","s9"],"type":"natural_gas_onsite"},{"description":"Epoch AI observed a battery facility connected to the building by September 2025 (analyst observation).","source_ids":["s8"],"type":"battery_storage"}],"related_ids":["xai-colossus-memphis","xai-macrohardrr-southaven"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-03-07","publisher":"WMC Action News 5","title":"xAI purchasing 1 million square feet of property in Southwest Memphis for expansion","type":"news","url":"https://www.actionnews5.com/2025/03/07/xai-purchasing-1-million-square-feet-property-southwest-memphis-expansion"},{"accessed":"2026-10-09","id":"s2","published":"2025-05-05","publisher":"Memphis Light, Gas and Water","title":"MLGW update regarding utility support for xAI","type":"utility","url":"https://www.mlgw.com/images/content/files/pdf/new/5-5-25%20xAI%20Update.pdf"},{"accessed":"2026-10-09","id":"s3","published":"2025-07-18","publisher":"DeSoto County News","title":"xAI buys Southaven property","type":"news","url":"https://desotocountynews.com/desoto-county-news/xai-buys-southaven-property/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260909173956/https://www.mississippifreepress.org/mississippi-permit-board-grants-xais-request-for-41-southaven-gas-turbines-to-power-memphis-data-center/","id":"s4","published":"2026-03-10","publisher":"Mississippi Free Press","title":"Mississippi permit board grants xAI's request for 41 Southaven gas turbines to power Memphis data center","type":"news","url":"https://www.mississippifreepress.org/mississippi-permit-board-grants-xais-request-for-41-southaven-gas-turbines-to-power-memphis-data-center/"},{"accessed":"2026-10-09","id":"s5","published":"2026-04-09","publisher":"Southern Environmental Law Center","title":"Groups appeal air permit for xAI's personal power plant in North Mississippi","type":"other","url":"https://www.selc.org/press-release/groups-appeal-air-permit-for-xais-personal-power-plant/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006212841/https://www.anthropic.com/news/series-h","id":"s6","published":"2026-05-28","publisher":"Anthropic","title":"Anthropic raises $65B in Series H funding at $965B post-money valuation","type":"company","url":"https://www.anthropic.com/news/series-h"},{"accessed":"2026-10-09","id":"s7","published":"2026-07-31","publisher":"WMC Action News 5","title":"xAI announces fourth data center; turbines to be removed from Southaven site","type":"news","url":"https://www.actionnews5.com/2026/07/31/xai-announces-fourth-data-center-turbines-be-removed-southaven-site/"},{"accessed":"2026-10-09","id":"s8","published":"2026-10-05","publisher":"Epoch AI","title":"Colossus 2 ¦ AI data centers","type":"analyst","url":"https://epoch.ai/data/ai-data-centers/directory/colossus-2"},{"accessed":"2026-10-09","id":"s9","published":null,"publisher":"Cleanview","title":"Colossus 1 & 2 ¦ Behind-the-Meter Data Centers","type":"analyst","url":"https://cleanview.co/reports/behind-the-meter-data-centers/full-report/colossus"}],"status":"partially_operational","status_as_of":"2026-10-05","status_source_ids":["s8","s7"],"summary":"Second xAI supercomputer campus, in a building of about one million square feet on Tulane Road in the Whitehaven area of Memphis, near the Mississippi line, which xAI bought in 2025. The site has drawn little or no grid power and runs mainly on gas turbines at a former Duke Energy plant site about 1.5 miles away in Southaven, Mississippi. Mississippi regulators permitted 41 permanent turbines there in March 2026, and environmental and civil rights groups appealed the permit in April 2026. Analyst estimates put its IT load near 1 GW by mid-2026. Anthropic says it has GPU capacity here under an agreement with SpaceX.","workloads":["ai_training"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"69c0a462-635f-5a28-a0fa-2addf0737441","s2":"206aff59-d746-56e5-af7e-4ce594a6af30","s3":"3dd97b1c-26ad-5403-99cb-2ed24b8f815f","s4":"7164895e-ef5e-50ae-a468-736371acfdf4","s5":"09b2d5a9-29d7-512d-84e2-65e09c2bfd97","s6":"e9d820a3-caef-54b1-85a9-fa80a43dae22","s7":"535d58bb-f29e-57f3-a441-be4e33a629eb","s8":"df6ae365-3303-5098-805a-fccbbb55eb8a","s9":"a44ea2fb-4ed6-5ed9-af9e-122343da2638"},"source_file":"datacenters/projects/xai-colossus-2-memphis.json","source_record_id":"xai-colossus-2-memphis","source_record_sha256":"a96b3341db0b72f4eeb487d50474903219c98fa2d20b32ec4e3af47c0c0a03d7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4cfe5b5baab4cd38ff3e09967cd3611e410e23f78f3009854145febbb02aef3b"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-62e42a722eab77bd5345/#project-9002afae-5b81-5c8c-a6f9-4504c91e8624 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9002afae-5b81-5c8c-a6f9-4504c91e8624.json
908ba9ce-1e84-567b-926f-8d47d4d2a7ed | imported:semiconductor-atlas:balico-pittsylvania-county | vcc-site-7b36022a26fba8770036 | imported:semiconductor-atlas:balico-pittsylvania-county | Balico gas-powered data center campus, Pittsylvania County | United States | US | 36.8256 | -79.3975 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of the town of Chatham (s5). Sources place the land near Chatham (s3, s4) in the county's Banister district (s1) but name no roads; the parcels were not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2b620414-745c-5b05-9ddb-a65fa6fe757a | cancelled | 2025-04-16 | 545 | imported_documented_status | 12674abe-1b54-563d-adbe-b2b32893468c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"818fe93d-c1ea-5599-a450-5f6c8ad85a46","notes":null,"party":"Balico LLC","relationship_scope":"unknown","role":"developer","source_record_id":"balico-pittsylvania-county"},{"evidence_id":"2f92b229-80ee-5009-9e0b-becd1fe7b293","notes":null,"party":"Balico LLC","relationship_scope":"unknown","role":"developer","source_record_id":"balico-pittsylvania-county"},{"evidence_id":"2b620414-745c-5b05-9ddb-a65fa6fe757a","notes":null,"party":"Balico LLC","relationship_scope":"unknown","role":"developer","source_record_id":"balico-pittsylvania-county"},{"evidence_id":"12674abe-1b54-563d-adbe-b2b32893468c","notes":null,"party":"Balico LLC","relationship_scope":"unknown","role":"developer","source_record_id":"balico-pittsylvania-county"},{"evidence_id":"2f92b229-80ee-5009-9e0b-becd1fe7b293","notes":"Denied the withdrawal request 5-2 and the rezoning 6-1.","party":"Pittsylvania County Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"balico-pittsylvania-county"},{"evidence_id":"12674abe-1b54-563d-adbe-b2b32893468c","notes":"Denied the withdrawal request 5-2 and the rezoning 6-1.","party":"Pittsylvania County Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"balico-pittsylvania-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://cardinalnews.org/2025/04/16/pittsylvania-rejects-data-center-project-that-has-dominated-county-conversation-for-6-months/ | https://www.wdbj7.com/2025/04/14/company-withdraws-data-center-proposal-residents-express-skepticism/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Balico gas-powered data center campus, Pittsylvania County as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"balico-pittsylvania-county","source_relations":[{"reason":"Rejected Balico Banister/Chatham plan and STACK Berry Hill megasite have distinct proponent and site descriptions; centroid proximity is not site overlap.","relationship":"separate_named_developments","source_id":"stack-berry-hill-pittsylvania-county"}]},"record":{"aliases":["Balico data center campus","Balico Chatham project"],"id":"balico-pittsylvania-county","last_reviewed":"2026-10-09","location":{"admin1":"Virginia","admin2":"Pittsylvania County","country":"US","lat":36.8256,"locality":"Chatham","lon":-79.3975,"note":"Coordinates are the Wikipedia centroid of the town of Chatham (s5). Sources place the land near Chatham (s3, s4) in the county's Banister district (s1) but name no roads; the parcels were not geocoded.","precision":"locality","source_ids":["s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-04-14","basis":"planned","metric":"power_capacity","note":"Planned natural gas power plant serving the campus; WDBJ reported the same plant size for the scaled-down 2025 application.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s1","s3","s4"],"unit":"MW","value":3500},{"applies_to":"campus","as_of":"2024-11-04","basis":"planned","metric":"land_area","note":"47 parcels to be rezoned to heavy industrial in the original application, withdrawn in November 2024 and superseded by the 750-acre plan.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":2233},{"applies_to":"campus","as_of":"2025-04-16","basis":"planned","metric":"land_area","note":"Scaled-down application rejected in April 2025.","qualifier":"approximately","source_ids":["s3","s4"],"unit":"acres","value":750},{"applies_to":"campus","as_of":"2024-11-04","basis":"planned","metric":"buildings","note":"Original application, withdrawn in November 2024 and superseded by the 12-building plan.","qualifier":"exact","source_ids":["s1","s4"],"unit":"count","value":84},{"applies_to":"campus","as_of":"2025-04-16","basis":"planned","metric":"buildings","note":"Each building planned at 396,000 square feet.","qualifier":"up_to","source_ids":["s2","s3","s4"],"unit":"count","value":12},{"applies_to":"campus","as_of":"2024-11-04","basis":"planned","metric":"jobs_permanent","note":"Company claim for the original application; residents questioned the job promises.","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":700}],"milestones":[{"date":"2024-10","event":"announced","kind":"actual","note":"Balico held community meetings on its rezoning application in late October 2024.","source_ids":["s1"]},{"date":"2024-11","event":"other","kind":"actual","note":"First application withdrawn before a planning commission hearing, with county staff recommending denial; Balico said it was revising, not abandoning, the project.","source_ids":["s1"]},{"date":"2025-01","event":"other","kind":"actual","note":"Planning commission voted unanimously to recommend denying the revised rezoning.","source_ids":["s2"]},{"date":"2025-04-15","event":"cancelled","kind":"actual","note":"Board of Supervisors denied Balico's request to withdraw and rejected the rezoning 6-1.","source_ids":["s4"]}],"name":"Balico gas-powered data center campus, Pittsylvania County","notes":"Recorded as cancelled because the county rejected the rezoning after refusing Balico's request to withdraw it; the sources reviewed report no appeal or new application. After the vote Balico's attorney said it was pursuing a joint venture with Dallas developer Hillwood and weighing other uses for the land, including another data center or housing. This project is separate from the Stack Infrastructure campus at the Berry Hill megasite in the same county.","parties":[{"name":"Balico LLC","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Pittsylvania County Board of Supervisors","note":"Denied the withdrawal request 5-2 and the rezoning 6-1.","role":"government","source_ids":["s2","s4"]}],"power_sources":[{"description":"A 3,500 MW natural gas power plant on the campus, described as the largest in Virginia; a public health study commissioned by the Southern Environmental Law Center estimated at least 326.53 tons of fine particulate emissions a year.","source_ids":["s1","s2","s3"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250418131331/https://cardinalnews.org/2024/11/04/data-center-proposal-in-pittsylvania-withdrawn-for-now/","id":"s1","published":"2024-11-04","publisher":"Cardinal News","title":"Data center proposal in Pittsylvania withdrawn, for now","type":"news","url":"https://cardinalnews.org/2024/11/04/data-center-proposal-in-pittsylvania-withdrawn-for-now/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260712161639/https://www.wvtf.org/news/2025-04-14/balico-withdraws-application-to-build-data-centers-in-pittsylvania-county","id":"s2","published":"2025-04-14","publisher":"Radio IQ (WVTF)","title":"Balico withdraws application to build data centers in Pittsylvania County","type":"news","url":"https://www.wvtf.org/news/2025-04-14/balico-withdraws-application-to-build-data-centers-in-pittsylvania-county"},{"accessed":"2026-10-09","id":"s3","published":"2025-04-14","publisher":"WDBJ7","title":"Company withdraws data center proposal, residents express skepticism","type":"news","url":"https://www.wdbj7.com/2025/04/14/company-withdraws-data-center-proposal-residents-express-skepticism/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260918072731/https://cardinalnews.org/2025/04/16/pittsylvania-rejects-data-center-project-that-has-dominated-county-conversation-for-6-months/","id":"s4","published":"2025-04-16","publisher":"Cardinal News","title":"Pittsylvania rejects data center project that has dominated county conversation for 6 months","type":"news","url":"https://cardinalnews.org/2025/04/16/pittsylvania-rejects-data-center-project-that-has-dominated-county-conversation-for-6-months/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003071231/https://en.wikipedia.org/wiki/Chatham,_Virginia","id":"s5","published":null,"publisher":"Wikipedia","title":"Chatham, Virginia","type":"other","url":"https://en.wikipedia.org/wiki/Chatham,_Virginia"}],"status":"cancelled","status_as_of":"2025-04-16","status_source_ids":["s4"],"summary":"Rejected plan by Herndon-based Balico for a data center campus with a 3,500 MW on-site natural gas power plant near Chatham in Pittsylvania County, Virginia. The first application, covering 47 parcels and about 2,233 acres with 84 data center buildings, was withdrawn in November 2024 after community meetings. A scaled-down version on about 750 acres with up to 12 buildings kept the 3,500 MW plant; the planning commission unanimously recommended denial in January 2025. On 15 April 2025 county supervisors refused Balico's request to withdraw it again and voted 6-1 against the rezoning, so a new filing had to wait a year.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"818fe93d-c1ea-5599-a450-5f6c8ad85a46","s2":"2f92b229-80ee-5009-9e0b-becd1fe7b293","s3":"2b620414-745c-5b05-9ddb-a65fa6fe757a","s4":"12674abe-1b54-563d-adbe-b2b32893468c","s5":"3b39030f-c2a8-583b-8198-cab46caaabcf"},"source_file":"datacenters/projects/balico-pittsylvania-county.json","source_record_id":"balico-pittsylvania-county","source_record_sha256":"9169c30b464bb8fd99931fce532ae356b7455ba9eb4e67c4c9c205374c151b21","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"187f5a2de7c8f9378e59d8a0fe49dce0518a84b249a609e39ddd2b81afddbb19"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7b36022a26fba8770036/#project-908ba9ce-1e84-567b-926f-8d47d4d2a7ed | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/908ba9ce-1e84-567b-926f-8d47d4d2a7ed.json
912a1942-9e25-5d1f-b3ce-7f39f60ca845 | imported:semiconductor-atlas:sdaia-hexagon-riyadh | vcc-site-ba5a5fcafa0e68a3bbc8 | imported:semiconductor-atlas:sdaia-hexagon-riyadh | Hexagon Data Center (Riyadh) | Saudi Arabia | SA | 24.633 | 46.717 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City coordinates from the Riyadh Wikipedia page; the sources do not name a district. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6627618c-e97b-5d09-b2b1-ccc30c1d176b | under_construction | 2026-05-01 | 165 | imported_documented_status | 6627618c-e97b-5d09-b2b1-ccc30c1d176b | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6627618c-e97b-5d09-b2b1-ccc30c1d176b","notes":null,"party":"Saudi Data and Artificial Intelligence Authority (SDAIA)","relationship_scope":"unknown","role":"developer","source_record_id":"sdaia-hexagon-riyadh"},{"evidence_id":"d2fe83ae-509a-5708-a7e2-3224a1e36e91","notes":null,"party":"Saudi Data and Artificial Intelligence Authority (SDAIA)","relationship_scope":"unknown","role":"developer","source_record_id":"sdaia-hexagon-riyadh"},{"evidence_id":"1da75167-6f75-52a8-8d5c-81dfd3d4b7bf","notes":null,"party":"Saudi Data and Artificial Intelligence Authority (SDAIA)","relationship_scope":"unknown","role":"developer","source_record_id":"sdaia-hexagon-riyadh"},{"evidence_id":"1da75167-6f75-52a8-8d5c-81dfd3d4b7bf","notes":"Named as main contractor in a trade project-tracking profile; not confirmed by SDAIA in sources reviewed.","party":"Albawani","relationship_scope":"unknown","role":"builder","source_record_id":"sdaia-hexagon-riyadh"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://w.media/sdaia-lays-foundation-stone-for-480mw-hexagon-government-data-center-in-riyadh/ | https://w.media/sdaia-lays-foundation-stone-for-480mw-hexagon-government-data-center-in-riyadh/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Hexagon Data Center (Riyadh) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"sdaia-hexagon-riyadh"},"record":{"aliases":["Hexagon Data Centre","SDAIA Hexagon"],"id":"sdaia-hexagon-riyadh","last_reviewed":"2026-10-09","location":{"admin1":"Riyadh Province","country":"SA","lat":24.633,"locality":"Riyadh","lon":46.717,"note":"City coordinates from the Riyadh Wikipedia page; the sources do not name a district.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-01","basis":"planned","metric":"power_capacity","note":"Announcement coverage gives capacity of up to 480 MW without a scope; the project-tracking profile labels it IT load capacity.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"MW","value":480},{"applies_to":"campus","as_of":"2026-05-01","basis":"reported","metric":"investment","note":"W.Media attributes this estimate to Gulf News; the project-tracking profile lists the same project value. No official SDAIA figure was found.","qualifier":"approximately","source_ids":["s1","s3"],"unit":"USD","value":2700000000}],"milestones":[{"date":"2026-01","event":"construction_started","kind":"actual","note":"Foundation stone laid at a ceremony at which SDAIA's president received senior officials.","source_ids":["s1","s2"]},{"date":"2029-Q1","event":"fully_operational","kind":"planned","note":"Completion target given in a trade project-tracking profile.","source_ids":["s3"]}],"name":"Hexagon Data Center (Riyadh)","notes":"Coverage published on 4 and 5 January 2026 reports the foundation stone as already laid without giving the ceremony date, so only the month is recorded. The 30 million square feet is described as the total or site area and is not recorded as a floor area metric. W.Media reports LEED Gold certification and the project-tracking profile mentions direct liquid and hybrid cooling; no source gives power supply details.","parties":[{"name":"Saudi Data and Artificial Intelligence Authority (SDAIA)","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Albawani","note":"Named as main contractor in a trade project-tracking profile; not confirmed by SDAIA in sources reviewed.","role":"builder","source_ids":["s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-05","publisher":"W.Media","title":"SDAIA lays foundation stone for 480MW Hexagon government data center in Riyadh","type":"trade_press","url":"https://w.media/sdaia-lays-foundation-stone-for-480mw-hexagon-government-data-center-in-riyadh/"},{"accessed":"2026-10-09","id":"s2","published":"2026-01-04","publisher":"Sharikat Mubasher","title":"Saudi Arabia lays cornerstone for Hexagon data center in Riyadh","type":"news","url":"https://en.sharikatmubasher.com/news/article/21526638/saudi-arabia-lays-cornerstone-for-hexagon-data-center-in-riyadh?lang=en"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260515174431/https://ognnews.com/ArticleOGN/461988/sdaia-hexagon-data-centre","id":"s3","published":"2026-05-01","publisher":"Oil & Gas News","title":"SDAIA Hexagon Data Centre (project profile)","type":"trade_press","url":"https://ognnews.com/ArticleOGN/461988/sdaia-hexagon-data-centre"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Riyadh","type":"other","url":"https://en.wikipedia.org/wiki/Riyadh"}],"status":"under_construction","status_as_of":"2026-05-01","status_source_ids":["s1","s3"],"summary":"Government data centre being built in Riyadh by the Saudi Data and Artificial Intelligence Authority (SDAIA), billed as the world's largest Tier IV government data centre. The foundation stone was laid in early January 2026 for a facility of up to 480 MW on a site of about 30 million square feet, designed to host more than 290 government systems and to seed a wider national network of centres. Reported project value is about USD 2.7 billion; a project-tracking profile names Albawani as main contractor, says construction was progressing in April 2026 and gives a Q1 2029 completion target.","workloads":["enterprise"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6627618c-e97b-5d09-b2b1-ccc30c1d176b","s2":"d2fe83ae-509a-5708-a7e2-3224a1e36e91","s3":"1da75167-6f75-52a8-8d5c-81dfd3d4b7bf","s4":"9153e8f1-0ad6-5b42-8df1-10076c85529c"},"source_file":"datacenters/projects/sdaia-hexagon-riyadh.json","source_record_id":"sdaia-hexagon-riyadh","source_record_sha256":"5a355aa9d4df550b443d510babcc5ebcbe3c271cec99a7f31673680ead44846b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"c76535396da4ab856da31ff6b384bcb216d08ef60a0c2c2784a500b93b51a445"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ba5a5fcafa0e68a3bbc8/#project-912a1942-9e25-5d1f-b3ce-7f39f60ca845 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/912a1942-9e25-5d1f-b3ce-7f39f60ca845.json
917342c6-069b-5678-bf52-e27fcf933a5a | imported:semiconductor-atlas:art-data-centres-ennis | vcc-site-a94efdae4ca44082dd5e | imported:semiconductor-atlas:art-data-centres-ennis | Art Data Centres Ennis campus | Ireland | IE | 52.8463 | -8.9807 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Ennis town centroid from its Wikipedia article. Clare FM places the site beside the Tulla Road on the town's eastern side near M18 junction 13, but no cited source gives coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 80ea5db6-fbbf-5202-8504-3c045fc73ac8 | announced | 2026-03-25 | 202 | imported_documented_status | 80ea5db6-fbbf-5202-8504-3c045fc73ac8 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"80ea5db6-fbbf-5202-8504-3c045fc73ac8","notes":null,"party":"Art Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"art-data-centres-ennis"},{"evidence_id":"ed14465a-9cf5-5035-8fb9-691fbbf9ab16","notes":null,"party":"Art Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"art-data-centres-ennis"},{"evidence_id":"465afa26-a69c-5dc2-a553-f12f46eff786","notes":null,"party":"Art Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"art-data-centres-ennis"},{"evidence_id":"80ea5db6-fbbf-5202-8504-3c045fc73ac8","notes":"Granted planning permission in April 2024.","party":"An Bord Pleanála (now An Coimisiún Pleanála)","relationship_scope":"unknown","role":"government","source_record_id":"art-data-centres-ennis"},{"evidence_id":"ed14465a-9cf5-5035-8fb9-691fbbf9ab16","notes":"Granted planning permission in April 2024.","party":"An Bord Pleanála (now An Coimisiún Pleanála)","relationship_scope":"unknown","role":"government","source_record_id":"art-data-centres-ennis"},{"evidence_id":"465afa26-a69c-5dc2-a553-f12f46eff786","notes":"Granted planning permission in April 2024.","party":"An Bord Pleanála (now An Coimisiún Pleanála)","relationship_scope":"unknown","role":"government","source_record_id":"art-data-centres-ennis"},{"evidence_id":"80ea5db6-fbbf-5202-8504-3c045fc73ac8","notes":"Working with the developer on diverting overhead power lines as the first enabling works.","party":"EirGrid","relationship_scope":"unknown","role":"utility","source_record_id":"art-data-centres-ennis"},{"evidence_id":"80ea5db6-fbbf-5202-8504-3c045fc73ac8","notes":"Working with the developer on diverting overhead power lines as the first enabling works.","party":"ESB Networks","relationship_scope":"unknown","role":"utility","source_record_id":"art-data-centres-ennis"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.clare.fm/news/high-court-clears-way-for-construction-of-e1-6bn-ennis-data-centre-project/ | https://www.clare.fm/news/high-court-clears-way-for-construction-of-e1-6bn-ennis-data-centre-project/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Art Data Centres Ennis campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"art-data-centres-ennis"},"record":{"aliases":["Ennis data centre campus","Art Data Centres Tulla Road campus"],"id":"art-data-centres-ennis","last_reviewed":"2026-10-09","location":{"admin1":"County Clare","country":"IE","lat":52.8463,"locality":"Ennis","lon":-8.9807,"note":"Ennis town centroid from its Wikipedia article. Clare FM places the site beside the Tulla Road on the town's eastern side near M18 junction 13, but no cited source gives coordinates.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-13","basis":"planned","metric":"power_capacity","note":"Industrial Info describes six data halls of slightly more than 33 MW each.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-03-13","basis":"reported","metric":"investment","note":"Across three phases.","qualifier":"more_than","source_ids":["s1","s2"],"unit":"EUR","value":1600000000},{"applies_to":"campus","as_of":"2025-03-21","basis":"reported","metric":"investment","note":"Earlier reported figure, superseded by the 2026 estimate of more than EUR 1.6 billion.","qualifier":"approximately","source_ids":["s3"],"unit":"EUR","value":1200000000},{"applies_to":"campus","as_of":"2026-03-13","basis":"planned","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"acres","value":145},{"applies_to":"phase","as_of":"2025-03-21","basis":"planned","metric":"floor_area","note":"Per-hall figure from the 2025 report; not summed into a campus total.","phase_label":"Each of six data halls","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":200000},{"applies_to":"campus","as_of":"2026-03-13","basis":"planned","metric":"buildings","note":"Six data halls built in three phases of two buildings each.","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2026-03-13","basis":"planned","metric":"jobs_construction","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2026-03-13","basis":"planned","metric":"jobs_permanent","note":"Developer figure reported by Clare FM.","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":1000}],"milestones":[{"date":"2024-04","event":"permit_approved","kind":"actual","note":"Planning permission from An Bord Pleanála; the 2025 report says permission was first granted in 2022.","source_ids":["s1","s2","s3"]},{"date":"2025-03","event":"other","kind":"actual","note":"The court found the judicial review grounds, including those concerning Leisler's bat, lacked merit; the remaining grounds were to be relisted later.","source_ids":["s3","s1"]},{"date":"2026-03","event":"other","kind":"actual","note":"High Court dismissed the remaining judicial review challenges, ending almost six years of legal challenges and clearing the way for enabling works.","source_ids":["s1","s2"]},{"date":"2028","event":"first_operational","kind":"planned","note":"Phase 1 (substation, data halls 2 and 3 and site works) due for completion and commissioning by the end of 2028; the 2025 report had targeted the first halls by the end of 2027.","source_ids":["s1","s2"]}],"name":"Art Data Centres Ennis campus","notes":"No construction start had been reported by the sources opened; Clare FM says enabling works can now begin. Investment figures have risen across reports (EUR 1.2 billion in 2025, more than EUR 1.6 billion in 2026). Clare FM and Industrial Info give the campus as 145 acres or 1.3 million sq ft, presenting the two as equivalent although 145 acres is about 6.3 million sq ft; because neither says what the 1.3 million sq ft measures, it is not recorded as floor area. Industrial Info's six halls of slightly more than 33 MW each are not summed. The judicial review was brought by Friends of the Irish Environment, Futureproof Clare and several individuals.","parties":[{"name":"Art Data Centres","role":"developer","source_ids":["s1","s2","s3"]},{"name":"An Bord Pleanála (now An Coimisiún Pleanála)","note":"Granted planning permission in April 2024.","role":"government","source_ids":["s1","s2","s3"]},{"name":"EirGrid","note":"Working with the developer on diverting overhead power lines as the first enabling works.","role":"utility","source_ids":["s1"]},{"name":"ESB Networks","note":"Working with the developer on diverting overhead power lines as the first enabling works.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"An 83 MVA connection to the Ennis substation, per Industrial Info.","source_ids":["s2"],"type":"grid"},{"description":"Industrial Info says an off-grid substation would be supplied by wind, solar and biogas.","source_ids":["s2"],"type":"wind"},{"description":"Solar is one of the sources Industrial Info lists for the off-grid substation.","source_ids":["s2"],"type":"solar"},{"description":"Biogas is one of the sources Industrial Info lists for the off-grid substation.","source_ids":["s2"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260420003426/https://www.clare.fm/news/high-court-clears-way-for-construction-of-e1-6bn-ennis-data-centre-project/","id":"s1","published":"2026-03-13","publisher":"Clare FM","title":"High Court Clears Way For Construction Of €1.6bn Ennis Data Centre Project","type":"news","url":"https://www.clare.fm/news/high-court-clears-way-for-construction-of-e1-6bn-ennis-data-centre-project/"},{"accessed":"2026-10-09","id":"s2","published":"2026-03-25","publisher":"Industrial Info Resources","title":"Court Clears Way for Major Irish Data Center","type":"trade_press","url":"https://www.industrialinfo.com/iirenergy/industry-news/article/court-clears-way-for-major-irish-data-center--355133"},{"accessed":"2026-10-09","id":"s3","published":"2025-03-21","publisher":"BeBeez International (republishing DCD)","title":"Art Data Centres Ennis campus judicial review gets dismissed","type":"trade_press","url":"https://bebeez.eu/en/news/art-data-centres-ennis-campus-judicial-review-gets-dismissed/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Ennis","type":"other","url":"https://en.wikipedia.org/wiki/Ennis"}],"status":"announced","status_as_of":"2026-03-25","status_source_ids":["s1","s2"],"summary":"Six-hall, 200 MW data center campus planned by Art Data Centres on about 145 acres beside the Tulla Road on the eastern edge of Ennis, County Clare, near junction 13 of the M18. The national planning board granted permission in April 2024, and in March 2026 the High Court dismissed the last judicial review challenges after years of litigation. Investment is now put at more than EUR 1.6 billion over three phases. Phase 1, with a substation and two data halls, is due for commissioning by the end of 2028; enabling works start with diverting overhead power lines.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"80ea5db6-fbbf-5202-8504-3c045fc73ac8","s2":"ed14465a-9cf5-5035-8fb9-691fbbf9ab16","s3":"465afa26-a69c-5dc2-a553-f12f46eff786","s4":"008ea865-8f97-5b92-ad7a-9b29569aa23a"},"source_file":"datacenters/projects/art-data-centres-ennis.json","source_record_id":"art-data-centres-ennis","source_record_sha256":"57f07bb943f4af27c537241facc42eb84e0b74a40b0fa009ae04b4cd34279386","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b211091ff27ae35941b0c37d43341e3df0fc68010f2f6c45b94fe17ebb8ace73"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a94efdae4ca44082dd5e/#project-917342c6-069b-5678-bf52-e27fcf933a5a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/917342c6-069b-5678-bf52-e27fcf933a5a.json
9217888a-3e78-5b75-ac86-bd32ef026084 | curated:portus-munich-data-center-campus:muc2 | vcc-site-5b9d2c3d36d5b5f40ab6 | curated:portus-munich-data-center-campus | Portus MUC2 | Germany | DE | 48.1585 | 11.7688 | Point | campus | provider_supplied_community_building_centroid_bound_to_exact_certified_constituent_site_address | preserve_Nominatim_lat_lon_for_OSM_way_571006394_and_match_MUC1_certificate_address_then_explicit_MUC1_MUC2_shared_campus | community_constituent_building_reference_point | community_source | campus_locator | The source-supplied centroid of the address-tagged Spacenet commercial building locates the MUC1/MUC2 campus through the exact MUC1 certificate address and explicit operator same-campus statement. It is not MUC2's building, active-work footprint, campus boundary, entrance, parcel centroid, verified current building-use assertion or survey-accuracy claim. The conflicting operator structured-data point is excluded. Source digits do not establish accuracy. |  | Neither OSM way 571006394 nor its Nominatim point gives quantitative positional accuracy. | 3e2be26d-bcc7-5313-a9d8-9886d2157402 | under_construction | 2026-05-28 | 138 | authoritative_physical_status_update | c4af69cb-30b1-5b71-83c0-6817895c74b6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.portusdatacenters.com/pressrelease/arcus-secures-inaugural-financing-for-portus-data-centers/ | https://nominatim.openstreetmap.org/search?q=Marsstrasse%205%20Kirchheim%20bei%20Munchen&format=jsonv2&addressdetails=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5b9d2c3d36d5b5f40ab6/#project-9217888a-3e78-5b75-ac86-bd32ef026084 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9217888a-3e78-5b75-ac86-bd32ef026084.json
9283d3fe-3789-54c7-abf4-8bb757e29835 | curated:jefferson-lab-newport-news-campus:jldc-building | vcc-site-2f392531ebec4705b0aa | curated:jefferson-lab-newport-news-campus | Jefferson Lab Data Center (JLDC) | United States | US | 37.0984 | -76.4897 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 34a0d6a4-02e3-57e3-8b39-6c7e64363b3a | under_construction | 2026-06-12 | 123 | authoritative_construction_start | 299ff180-d01b-5474-b229-12fed55b6f7c | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.jlab.org/news/releases/jefferson-lab-breaks-ground-new-building-power-next-generation-scientific-discovery | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2f392531ebec4705b0aa/#project-9283d3fe-3789-54c7-abf4-8bb757e29835 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9283d3fe-3789-54c7-abf4-8bb757e29835.json
938feeec-a323-56e0-b6ce-2590fe58e623 | curated:lancium-clean-campus-abilene-ai-data-center:remaining-six-building-expansion | vcc-site-85b3549bb55293336132 | curated:lancium-clean-campus-abilene-ai-data-center | Lancium Clean Campus Abilene Remaining Six-Building Expansion | United States | US | 32.5096 | -99.7748 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The municipal address binds Buildings 5 through 8 and the remaining campus development; the point is not any one of the six remaining building locations. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 6600dddb-f2d8-5458-8e71-b43f77cc5e01 | under_construction | 2026-06-04 | 131 | authoritative_physical_status_update | c721a602-e557-5a4d-8518-d5fce69a64d2 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.12 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.oracle.com/data-centers/ | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-85b3549bb55293336132/#project-938feeec-a323-56e0-b6ce-2590fe58e623 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/938feeec-a323-56e0-b6ce-2590fe58e623.json
93e5705d-3c86-524c-8089-0868d13bbd0d | imported:semiconductor-atlas:google-journey-haskell-county-texas | vcc-site-e348a191d95cf61970ae | imported:semiconductor-atlas:google-journey-haskell-county-texas | Google Journey data center campus (Haskell County) | United States | US | 33.1564 | -99.5683 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | OpenStreetMap geometry of Red Creek Road in Haskell County. The abatement exhibit places the 300-acre tract on the west side of Red Creek Road about two miles south of US Highway 380; the registered address is 1362 Red Creek Rd, which could not be resolved to a point. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | dfab1504-d44e-5ef1-b4c7-78e82a32d5b9 | under_construction | 2026-06-25 | 110 | imported_documented_status | 1f444679-4f9d-5dc3-952f-64a062473389 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"dfab1504-d44e-5ef1-b4c7-78e82a32d5b9","notes":"Delaware LLC named as project entity in the abatement and as owner in state building registrations.","party":"Homebound Group LLC","relationship_scope":"unknown","role":"owner","source_record_id":"google-journey-haskell-county-texas"},{"evidence_id":"1f444679-4f9d-5dc3-952f-64a062473389","notes":"Delaware LLC named as project entity in the abatement and as owner in state building registrations.","party":"Homebound Group LLC","relationship_scope":"unknown","role":"owner","source_record_id":"google-journey-haskell-county-texas"},{"evidence_id":"8ac5c431-f07e-5cd2-a6d2-c9744ff5eacb","notes":"Delaware LLC named as project entity in the abatement and as owner in state building registrations.","party":"Homebound Group LLC","relationship_scope":"unknown","role":"owner","source_record_id":"google-journey-haskell-county-texas"},{"evidence_id":"dfab1504-d44e-5ef1-b4c7-78e82a32d5b9","notes":null,"party":"Homebound Group LLC","relationship_scope":"unknown","role":"developer","source_record_id":"google-journey-haskell-county-texas"},{"evidence_id":"15c1ff4e-32e7-53f5-a6bf-9ec0b270f046","notes":"Haskell County's abatement listing labels the Journey agreement as a Google project, and Google announced new data center campuses in Haskell County. Neither source spells out Google's corporate relationship with Homebound Group LLC, and the state registrations list no tenant.","party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-journey-haskell-county-texas"},{"evidence_id":"7e8f06fe-75dc-5de0-9401-aa1c5dfc0c81","notes":"Haskell County's abatement listing labels the Journey agreement as a Google project, and Google announced new data center campuses in Haskell County. Neither source spells out Google's corporate relationship with Homebound Group LLC, and the state registrations list no tenant.","party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-journey-haskell-county-texas"},{"evidence_id":"dfab1504-d44e-5ef1-b4c7-78e82a32d5b9","notes":"Granted a 10-year, 100% county property tax abatement per phase (excluding the debt-service rate), with payments in lieu of taxes.","party":"Haskell County","relationship_scope":"unknown","role":"government","source_record_id":"google-journey-haskell-county-texas"},{"evidence_id":"7e8f06fe-75dc-5de0-9401-aa1c5dfc0c81","notes":"Granted a 10-year, 100% county property tax abatement per phase (excluding the debt-service rate), with payments in lieu of taxes.","party":"Haskell County","relationship_scope":"unknown","role":"government","source_record_id":"google-journey-haskell-county-texas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Homebound Group LLC |  |  |  |  | https://www.tdlr.texas.gov/TABS/Search/Print/TABS2026023821 | https://www.haskellcountytx.gov/upload/page/9220/docs/Homebound%20Group%20LLC.pdf | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Google Journey data center campus (Haskell County) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"google-journey-haskell-county-texas"},"record":{"aliases":["Journey campus","Haskell County Journey Reinvestment Zone"],"id":"google-journey-haskell-county-texas","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Haskell County","country":"US","lat":33.1564,"locality":"Haskell","lon":-99.5683,"note":"OpenStreetMap geometry of Red Creek Road in Haskell County. The abatement exhibit places the 300-acre tract on the west side of Red Creek Road about two miles south of US Highway 380; the registered address is 1362 Red Creek Rd, which could not be resolved to a point.","precision":"approximate_site","source_ids":["s2","s4","s5"]},"metrics":[{"applies_to":"phase","as_of":"2025-06-24","basis":"incentive_agreement","metric":"investment","note":"Anticipated initial capital cost of Phase 1; the agreement also sets a $1 billion minimum capital investment for the abatement.","phase_label":"Phase 1","qualifier":"approximately","source_ids":["s2"],"unit":"USD","value":1000000000},{"applies_to":"phase","as_of":"2026-06-25","basis":"reported","metric":"investment","note":"Estimated cost in the state building registration.","phase_label":"Building JNR1A","qualifier":"exact","source_ids":["s4"],"unit":"USD","value":400000000},{"applies_to":"phase","as_of":"2026-06-25","basis":"reported","metric":"investment","note":"Estimated cost in the state building registration.","phase_label":"Building JNR2A","qualifier":"exact","source_ids":["s5"],"unit":"USD","value":400000000},{"applies_to":"phase","as_of":"2026-06-25","basis":"under_construction","metric":"floor_area","phase_label":"Building JNR1A","qualifier":"exact","source_ids":["s4"],"unit":"sq_ft","value":285282},{"applies_to":"phase","as_of":"2026-06-25","basis":"under_construction","metric":"floor_area","phase_label":"Building JNR2A","qualifier":"exact","source_ids":["s5"],"unit":"sq_ft","value":210420},{"applies_to":"campus","as_of":"2025-06-24","basis":"reported","metric":"land_area","note":"Area of the reinvestment zone tract described in the abatement exhibit.","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":300},{"applies_to":"campus","as_of":"2025-06-24","basis":"planned","metric":"jobs_permanent","qualifier":"at_least","source_ids":["s2"],"unit":"count","value":50}],"milestones":[{"date":"2025-06-24","event":"other","kind":"actual","note":"Haskell County designated the Journey reinvestment zone and approved the tax abatement agreement with Homebound Group LLC.","source_ids":["s2","s3"]},{"date":"2025-11-14","event":"announced","kind":"actual","note":"Google announced new Haskell County campuses without naming the sites.","source_ids":["s1"]},{"date":"2026-04-01","event":"construction_started","kind":"actual","note":"Estimated start date for building JNR1A in a state registration filed on 2026-06-25, after that date had passed.","source_ids":["s4"]},{"date":"2026-06-23","event":"other","kind":"actual","note":"Estimated start date for building JNR2A in a state registration filed on 2026-06-25.","source_ids":["s5"]},{"date":"2027-08-21","event":"other","kind":"planned","note":"Registered construction completion date for building JNR1A.","source_ids":["s4"]},{"date":"2027-10-27","event":"other","kind":"planned","note":"Registered construction completion date for building JNR2A.","source_ids":["s5"]}],"name":"Google Journey data center campus (Haskell County)","notes":"Haskell County also lists Google-labelled abatements for Homebound's Thelma and Quest projects and for Ascendant Site Solutions' Ranger project; those are separate sites and are not part of this record. Google's $40 billion Texas figure is statewide and is not recorded as a campus investment. Status is inferred from the June 2026 state registrations, which list new construction with estimated start dates of April 1 and June 23, 2026; no opened source reports work on site directly.","parties":[{"name":"Homebound Group LLC","note":"Delaware LLC named as project entity in the abatement and as owner in state building registrations.","role":"owner","source_ids":["s2","s4","s5"]},{"name":"Homebound Group LLC","role":"developer","source_ids":["s2"]},{"name":"Google","note":"Haskell County's abatement listing labels the Journey agreement as a Google project, and Google announced new data center campuses in Haskell County. Neither source spells out Google's corporate relationship with Homebound Group LLC, and the state registrations list no tenant.","role":"developer","source_ids":["s1","s3"]},{"name":"Haskell County","note":"Granted a 10-year, 100% county property tax abatement per phase (excluding the debt-service rate), with payments in lieu of taxes.","role":"government","source_ids":["s2","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-14","publisher":"Google","title":"Google's investments run deep in the heart of Texas","type":"company","url":"https://blog.google/inside-google/company-announcements/google-american-innovation-texas/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260105124830/https://www.haskellcountytx.gov/upload/page/9220/docs/Homebound%20Group%20LLC.pdf","id":"s2","published":"2025-06","publisher":"Haskell County, Texas","title":"Tax Abatement Agreement between Haskell County and Homebound Group LLC (Journey)","type":"government","url":"https://www.haskellcountytx.gov/upload/page/9220/docs/Homebound%20Group%20LLC.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004093445/https://www.haskellcountytx.gov/page/haskell.Abatement","id":"s3","published":null,"publisher":"Haskell County, Texas","title":"Tax Abatement Information","type":"government","url":"https://www.haskellcountytx.gov/page/haskell.Abatement"},{"accessed":"2026-10-09","id":"s4","published":"2026-06-25","publisher":"Texas Department of Licensing and Regulation","title":"TABS project TABS2026023821: Journey 1A (JNR1A)","type":"regulatory_filing","url":"https://www.tdlr.texas.gov/TABS/Search/Print/TABS2026023821"},{"accessed":"2026-10-09","id":"s5","published":"2026-06-25","publisher":"Texas Department of Licensing and Regulation","title":"TABS project TABS2026023839: Journey 2A (JNR2A)","type":"regulatory_filing","url":"https://www.tdlr.texas.gov/TABS/Search/Print/TABS2026023839"}],"status":"under_construction","status_as_of":"2026-06-25","status_source_ids":["s4","s5"],"summary":"Data center campus on a 300-acre tract along Red Creek Road, south of US Highway 380 in Haskell County, Texas, owned by Homebound Group LLC. Haskell County labels the Journey abatement as a Google project, and Google named new Haskell County campuses in its November 2025 Texas program. The June 2025 county tax abatement expects Phase 1 capital costs of about $1 billion, allows up to four phases, and requires at least 50 permanent jobs. 2026 state registrations list two buildings at 1362 Red Creek Rd, JNR1A (285,282 sq ft) and JNR2A (210,420 sq ft), each estimated at $400 million, with completion targets in August and October 2027.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"15c1ff4e-32e7-53f5-a6bf-9ec0b270f046","s2":"dfab1504-d44e-5ef1-b4c7-78e82a32d5b9","s3":"7e8f06fe-75dc-5de0-9401-aa1c5dfc0c81","s4":"1f444679-4f9d-5dc3-952f-64a062473389","s5":"8ac5c431-f07e-5cd2-a6d2-c9744ff5eacb"},"source_file":"datacenters/projects/google-journey-haskell-county-texas.json","source_record_id":"google-journey-haskell-county-texas","source_record_sha256":"72e5be79448d9c10c235e6e58f736780f1941773120215f3afa2cd445bf665d7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4d6f9f730200b3e47c33ed49b417b5d32b0deaee99603b5012770896c4c87783"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e348a191d95cf61970ae/#project-93e5705d-3c86-524c-8089-0868d13bbd0d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/93e5705d-3c86-524c-8089-0868d13bbd0d.json
94562977-e3af-5f59-bee1-896ee8db20f6 | imported:semiconductor-atlas:fermi-america-hypergrid-amarillo | vcc-site-0fd145d30136b16a75ed | imported:semiconductor-atlas:fermi-america-hypergrid-amarillo | Fermi America Project Matador campus | United States | US | 35.3116 | -101.5597 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Coordinates of the Pantex Plant from Wikipedia (s5). Fermi says its campus is next to the Pantex complex (s2), in Carson County (s1, s4) and near Amarillo (s3); the campus covers thousands of acres, so the point is only approximate. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f6b4d9a4-f01a-5a71-beb8-621d552bdb95 | under_construction | 2026-09-28 | 15 | imported_documented_status | f6b4d9a4-f01a-5a71-beb8-621d552bdb95 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f6b4d9a4-f01a-5a71-beb8-621d552bdb95","notes":"Also styled Fermi America.","party":"Fermi Inc.","relationship_scope":"unknown","role":"developer","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"ca55d57d-d4a6-5149-8e73-f65d9370fc11","notes":"Also styled Fermi America.","party":"Fermi Inc.","relationship_scope":"unknown","role":"developer","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"f6b4d9a4-f01a-5a71-beb8-621d552bdb95","notes":"Lease dated August 9, 2026; closing was expected by September 30, 2026, subject to conditions.","party":"TensorWave","relationship_scope":"unknown","role":"tenant","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"ca55d57d-d4a6-5149-8e73-f65d9370fc11","notes":"Lease dated August 9, 2026; closing was expected by September 30, 2026, subject to conditions.","party":"TensorWave","relationship_scope":"unknown","role":"tenant","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"f6b4d9a4-f01a-5a71-beb8-621d552bdb95","notes":"Supplier of SGT-800 and SGT6-5000F gas turbines.","party":"Siemens Energy","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"25d95be5-0754-59ec-a7bb-b8a2d6c1c330","notes":"Supplier of SGT-800 and SGT6-5000F gas turbines.","party":"Siemens Energy","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"04fa5bd4-ae37-536c-abab-4c6c98747cf3","notes":"Selected to operate and maintain the natural gas generation fleet, which Fermi continues to own.","party":"NAES Corporation","relationship_scope":"unknown","role":"operator","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"04fa5bd4-ae37-536c-abab-4c6c98747cf3","notes":"Selected to operate and maintain Fermi's first data center on the campus.","party":"CBRE","relationship_scope":"unknown","role":"operator","source_record_id":"fermi-america-hypergrid-amarillo"},{"evidence_id":"f6b4d9a4-f01a-5a71-beb8-621d552bdb95","notes":"Expected to supply about 200 MW of grid power for the initial load.","party":"Southwestern Public Service Company","relationship_scope":"unknown","role":"utility","source_record_id":"fermi-america-hypergrid-amarillo"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | CBRE; NAES Corporation |  | TensorWave |  | https://www.sec.gov/Archives/edgar/data/2071778/000207177826000051/frmi-20260630.htm | https://www.sec.gov/Archives/edgar/data/2071778/000207177826000051/frmi-20260630.htm | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Fermi America Project Matador campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"fermi-america-hypergrid-amarillo"},"record":{"aliases":["Private Power HyperGrid","Project Matador"],"id":"fermi-america-hypergrid-amarillo","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Carson County","country":"US","lat":35.3116,"lon":-101.5597,"note":"Coordinates of the Pantex Plant from Wikipedia (s5). Fermi says its campus is next to the Pantex complex (s2), in Carson County (s1, s4) and near Amarillo (s3); the campus covers thousands of acres, so the point is only approximate.","precision":"approximate_site","source_ids":["s1","s2","s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-30","basis":"planned","metric":"power_capacity","note":"Private-grid generation planned for the campus.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":11000},{"applies_to":"campus","as_of":"2026-06-30","basis":"planned","metric":"power_capacity","note":"Expansion case, subject to pending land acquisitions and additional state air permits.","power_scope":"onsite_generation","qualifier":"up_to","source_ids":["s1","s2"],"unit":"MW","value":17000},{"applies_to":"campus","as_of":"2026-10-09","basis":"permitted","metric":"power_capacity","note":"Generation the company website describes as already permitted; the page is undated and was accessed on this date.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s2"],"unit":"MW","value":6000},{"applies_to":"phase","as_of":"2026-06-30","basis":"planned","metric":"power_capacity","note":"Grid power from Southwestern Public Service Company supporting the first gigawatt of load.","phase_label":"Initial 1 GW of load","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":200},{"applies_to":"phase","as_of":"2026-08-09","basis":"contracted","metric":"power_capacity","note":"Total facility power under the TensorWave lease, delivered in phases from late 2027 into early 2028.","phase_label":"TensorWave premises","power_scope":"facility","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":222},{"applies_to":"phase","as_of":"2026-08-09","basis":"planned","metric":"power_capacity","note":"Facility power if TensorWave exercises its option for two more buildings.","phase_label":"TensorWave premises with expansion option","power_scope":"facility","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":650},{"applies_to":"campus","as_of":"2026-06-30","basis":"reported","metric":"investment","note":"Construction in progress on Fermi's balance sheet, not a total project budget; the filing also expects about 2 billion US dollars of capital spending over the following twelve months for Phases 0 and 1.","qualifier":"approximately","source_ids":["s1"],"unit":"USD","value":1540000000},{"applies_to":"campus","as_of":"2026-06-30","basis":"reported","metric":"land_area","note":"Land held or to be held under a long-term lease from the Texas Tech University System.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":5236},{"applies_to":"campus","as_of":"2026-06-30","basis":"planned","metric":"land_area","note":"Expected total site including other acquired, contracted or optioned land, subject to closings.","qualifier":"approximately","source_ids":["s1","s2"],"unit":"acres","value":8400},{"applies_to":"campus","as_of":"2026-06-30","basis":"planned","metric":"floor_area","qualifier":"approximately","source_ids":["s1"],"unit":"sq_ft","value":15000000},{"applies_to":"phase","as_of":"2026-08-09","basis":"planned","metric":"floor_area","phase_label":"TensorWave premises","qualifier":"approximately","source_ids":["s1"],"unit":"sq_ft","value":311496}],"milestones":[{"date":"2025","event":"construction_started","kind":"actual","note":"Preliminary site development began in 2025; vertical construction was to follow the first tenant lease.","source_ids":["s1"]},{"date":"2026-08-09","event":"other","kind":"actual","note":"Lease signed with TensorWave for 222 MW of facility power over a 15-year initial term.","source_ids":["s1"]},{"date":"2026-09-18","event":"other","kind":"actual","note":"First Siemens Energy SGT6-5000F gas turbines reported delivered to the site.","source_ids":["s3"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Target year for commercial operations of the first campus; the company website says first power was planned for 2026.","source_ids":["s1","s2"]},{"date":"2033","event":"other","kind":"planned","note":"Target for the first of four planned Westinghouse nuclear units, one per year through 2036; the filing says the first unit slipped about a year.","source_ids":["s1"]}],"name":"Fermi America Project Matador campus","notes":"The June 2026 10-Q says only preliminary site development had begun and that vertical construction of data center facilities was to follow a definitive tenant lease; the status reflects site work and generation equipment arriving, not data center building construction. The TensorWave lease was subject to closing conditions, including project-level financing, with closing expected by September 30, 2026; no source confirming the closing was opened.","parties":[{"name":"Fermi Inc.","note":"Also styled Fermi America.","role":"developer","source_ids":["s1","s2"]},{"name":"TensorWave","note":"Lease dated August 9, 2026; closing was expected by September 30, 2026, subject to conditions.","role":"tenant","source_ids":["s1","s2"]},{"name":"Siemens Energy","note":"Supplier of SGT-800 and SGT6-5000F gas turbines.","role":"hardware_supplier","source_ids":["s1","s3"]},{"name":"NAES Corporation","note":"Selected to operate and maintain the natural gas generation fleet, which Fermi continues to own.","role":"operator","source_ids":["s4"]},{"name":"CBRE","note":"Selected to operate and maintain Fermi's first data center on the campus.","role":"operator","source_ids":["s4"]},{"name":"Southwestern Public Service Company","note":"Expected to supply about 200 MW of grid power for the initial load.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Siemens SGT-800 and SGT6-5000F gas turbines plus leased GE TM2500 mobile units forming a private grid.","source_ids":["s1","s3","s4"],"type":"natural_gas_onsite"},{"description":"Four Westinghouse reactor units planned for commissioning between 2033 and 2036.","source_ids":["s1"],"type":"nuclear"},{"description":"Solar described as bridge capacity alongside battery storage.","source_ids":["s2"],"type":"solar"},{"description":"Battery storage described as bridge capacity alongside solar.","source_ids":["s2"],"type":"battery_storage"},{"description":"About 200 MW of grid power from Southwestern Public Service Company for the initial load.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-08-14","publisher":"U.S. Securities and Exchange Commission (Fermi Inc. filing)","title":"Fermi Inc. Form 10-Q for the quarter ended June 30, 2026","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/2071778/000207177826000051/frmi-20260630.htm"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Fermi America","title":"Fermi America home page","type":"company","url":"https://fermiamerica.com/"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-18","publisher":"Fermi America","title":"First Power Generation Assets Arrive at Project Matador","type":"company","url":"https://fermiamerica.com/first-power-generation-assets-arrive-at-project-matador/"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-28","publisher":"Fermi America","title":"Fermi Selects NAES to Operate Project Matador's Natural Gas Fleet","type":"company","url":"https://fermiamerica.com/fermi-selects-naes-to-operate-project-matadors-natural-gas-fleet/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260601100312/https://en.wikipedia.org/wiki/Pantex_Plant","id":"s5","published":null,"publisher":"Wikipedia","title":"Pantex Plant","type":"other","url":"https://en.wikipedia.org/wiki/Pantex_Plant"}],"status":"under_construction","status_as_of":"2026-09-28","status_source_ids":["s1","s3","s4"],"summary":"Fermi Inc. is developing a private-power AI campus in Carson County, Texas, near Amarillo, mostly on land leased from the Texas Tech University System. Its filing describes about 11 GW of planned on-site generation, potentially expandable to about 17 GW, and about 15 million square feet of AI infrastructure space. Gas turbines come first, with nuclear units planned from 2033 and limited grid supply at the start. In August 2026 Fermi signed its first tenant lease, with TensorWave, for 222 MW of facility power. At mid-2026 it reported 1.54 billion US dollars of construction in progress and going-concern doubts that management said its plans alleviate.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f6b4d9a4-f01a-5a71-beb8-621d552bdb95","s2":"ca55d57d-d4a6-5149-8e73-f65d9370fc11","s3":"25d95be5-0754-59ec-a7bb-b8a2d6c1c330","s4":"04fa5bd4-ae37-536c-abab-4c6c98747cf3","s5":"0328fcce-2c60-5546-ac42-9f861ed8f9e1"},"source_file":"datacenters/projects/fermi-america-hypergrid-amarillo.json","source_record_id":"fermi-america-hypergrid-amarillo","source_record_sha256":"2784250e9a1dd9f679638c54fd185e63aec4254906feee0f129ab485698ebe1c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"6786d8491cf40bc05c7f858cd71723904c90a9d20f4f2f58191976ba20257d88"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0fd145d30136b16a75ed/#project-94562977-e3af-5f59-bee1-896ee8db20f6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/94562977-e3af-5f59-bee1-896ee8db20f6.json
94c0f50d-843b-57cd-bfcd-4bd3b7b9d9f0 | curated:start-campus-sines-data-campus:sin02-current-facility-build | vcc-site-fdb92bb99c36b43e6162 | epoch-ai:data-center:1fb39208-53bc-5714-80d2-881a5c944551 | Start Campus SIN02 Current Facility Build | Portugal | PT | 37.9384 | -8.8055 | Point | campus | official_georeferenced_drawing_shared_area_centroid_transformed_to_crs84 | apa_sin02_06_shared_multi_phase_area_centroid_as_campus_locator | official_shared_multi_phase_area_centroid_as_campus_locator | official_source | campus_locator | The point is an approximate centroid of the official shared SIN02-06 multi-phase area. It is not the SIN02 facility, an entrance, survey point, parcel, campus boundary, project footprint, building footprint, or current-work point or extent. | 25 |  | 26d88bed-8fc2-5e71-8683-68d3b9bb1ee3 | under_construction | 2026-06-23 | 112 | authoritative_physical_status_update | 4fa044ee-8801-5e39-96e9-3b41014d5a96 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.16 country-diversity batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/feed/update/urn:li:activity:7475104761256718337 | https://siaia.apambiente.pt/AIADOC/AIA3633/22045-ep-amb-des-001-01-a202382212930.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fdb92bb99c36b43e6162/#project-94c0f50d-843b-57cd-bfcd-4bd3b7b9d9f0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/94c0f50d-843b-57cd-bfcd-4bd3b7b9d9f0.json
9563b94b-4d68-5f38-b2b2-ce63346ebbe8 | curated:hut8-beacon-point-ai-data-center-campus:first-phase-352mw-critical-it-lease | vcc-site-a15d402305ed80ba8cba | curated:hut8-beacon-point-ai-data-center-campus | Hut 8 Beacon Point First Phase 352 MW Critical IT Lease | United States | US | 27.8345 | -97.6148 | Point | campus | Match direct campus page to the platform's same title and slug; dereference explicit geolocation fields; reproduce the site's six-decimal marker rounding; emit longitude then latitude. | operator_published_mapbox_campus_marker | operator_published_campus_reference_point | official_source | campus_locator | Exact operator-rendered named campus marker, not a survey, campus boundary, building centroid, construction footprint, or phase-specific location. |  | Publisher reports no bounded horizontal positional accuracy; decimal places and deterministic rounding do not establish site accuracy. | 68bba6b3-26b0-50d9-929f-570e39728681 | under_construction | 2026-08-04 | 70 | authoritative_physical_status_update | 56eddcf1-c98f-563c-9135-12ba2009edb3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.hut8.com/news-insights/press-releases/hut-8-reports-second-quarter-2026-results | https://www.hut8.com/data-centers/beacon-point | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a15d402305ed80ba8cba/#project-9563b94b-4d68-5f38-b2b2-ce63346ebbe8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9563b94b-4d68-5f38-b2b2-ce63346ebbe8.json
95b33a98-a85e-57af-b18d-6811a7fd3b20 | curated:nextdc-kl1-kuala-lumpur:incremental-in-progress-fit-out | vcc-site-355111878b17009b2503 | curated:nextdc-kl1-kuala-lumpur | NEXTDC KL1 Remaining In-Progress Fit-Out | Malaysia | MY | 3.0947 | 101.6284 | Point | campus | community_named_building_representative_point | preserve_Nominatim_way1026603690_lat_lon_and_bind_exact_NEXTDC_KL1_ref_operator_and_street | community_building_campus_reference_point | community_source | campus_locator | Representative point of the explicitly named NEXTDC KL1 data-center building, bound by operator/ref/address/URL tags and official contact address. Campus locator only, not the remaining fit-out hall, surveyed entrance or boundary. The same-named industrial-landuse result is not another campus; the operator's road-only directions destination is excluded. |  | No feature-specific quantitative positional-accuracy estimate is supplied by the selected point source. Coordinate digits are retained without asserting survey accuracy. | b420edee-9de9-5a3f-b6f7-0fe68eddf368 | mep_electrical | 2026-06-30 | 105 | authoritative_physical_status_update | c39d71f0-c36f-5942-85a8-d7c235f5ea32 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nextdc.com/hubfs/Financial%20Reports/FY26/FY26%20Results%20Announcement.pdf | https://nominatim.openstreetmap.org/search?q=NEXTDC%20KL1&format=jsonv2&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-355111878b17009b2503/#project-95b33a98-a85e-57af-b18d-6811a7fd3b20 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/95b33a98-a85e-57af-b18d-6811a7fd3b20.json
96848e3f-da64-53c8-be33-bf5c9cd2109a | imported:semiconductor-atlas:microsoft-mount-pleasant-international-drive | vcc-site-c5988379bc974f1f6240 | imported:semiconductor-atlas:microsoft-mount-pleasant-international-drive | Microsoft Mount Pleasant International Drive datacenter campus | United States | US | 42.7112 | -87.9339 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Nominatim point for International Drive in Mount Pleasant, the road the sources name for the campus; the parcel boundary is not published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 20fee728-51c4-598d-b3e8-3cf49887dbe3 | announced | 2026-01-27 | 259 | imported_documented_status | 17414c26-e568-5e54-ae88-13ac8e17f591 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"20fee728-51c4-598d-b3e8-3cf49887dbe3","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-mount-pleasant-international-drive"},{"evidence_id":"c93ccee2-05e4-50e5-b256-af4c2a614dd7","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-mount-pleasant-international-drive"},{"evidence_id":"20fee728-51c4-598d-b3e8-3cf49887dbe3","notes":"A Microsoft spokesperson said the land was bought in 2024; a village spokesperson said it came from the village or private owners.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-mount-pleasant-international-drive"},{"evidence_id":"4f5197a5-e9ca-5c03-81ba-881d66604cf7","notes":"A Microsoft spokesperson said the land was bought in 2024; a village spokesperson said it came from the village or private owners.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-mount-pleasant-international-drive"},{"evidence_id":"20fee728-51c4-598d-b3e8-3cf49887dbe3","notes":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","party":"Village of Mount Pleasant","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-mount-pleasant-international-drive"},{"evidence_id":"4f5197a5-e9ca-5c03-81ba-881d66604cf7","notes":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","party":"Village of Mount Pleasant","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-mount-pleasant-international-drive"},{"evidence_id":"17414c26-e568-5e54-ae88-13ac8e17f591","notes":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","party":"Village of Mount Pleasant","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-mount-pleasant-international-drive"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Microsoft |  |  |  |  | https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval | https://www.wpr.org/news/microsoft-15-more-data-centers-mount-pleasant | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Mount Pleasant International Drive datacenter campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-mount-pleasant-international-drive","source_relations":[{"reason":"County Road KR phases 1/2 and International Drive six-building campus occupy separately described development parcels.","relationship":"separate_campus_parcels","source_id":"microsoft-fairwater-mount-pleasant"},{"reason":"Distinct 791-acre nine-building Durand campus and 530-acre six-building International Drive campus.","relationship":"separate_campus_parcels","source_id":"microsoft-mount-pleasant-durand-avenue"}]},"record":{"aliases":[],"id":"microsoft-mount-pleasant-international-drive","last_reviewed":"2026-10-09","location":{"admin1":"Wisconsin","admin2":"Racine County","country":"US","lat":42.7112,"locality":"Mount Pleasant","lon":-87.9339,"note":"Nominatim point for International Drive in Mount Pleasant, the road the sources name for the campus; the parcel boundary is not published.","precision":"approximate_site","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-20","basis":"reported","metric":"investment","note":"The municipality's estimated taxable value for the development, from village planning documents reported by WPR; not a company investment figure.","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":5300000000},{"applies_to":"campus","as_of":"2026-01-27","basis":"planned","metric":"buildings","note":"Datacenter buildings only; an office and other buildings are additional.","qualifier":"exact","source_ids":["s1","s3","s4"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2026-01-20","basis":"planned","metric":"floor_area","note":"Total development size from village planning documents reported by WPR; the office and other buildings are not broken out.","qualifier":"more_than","source_ids":["s1"],"unit":"sq_ft","value":3500000},{"applies_to":"campus","as_of":"2026-01-21","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2"],"unit":"acres","value":530}],"milestones":[{"date":"2024","event":"site_acquired","kind":"actual","source_ids":["s1","s2"]},{"date":"2026-01-20","event":"announced","kind":"actual","note":"Site plans became public ahead of the plan commission meeting; Microsoft called them preliminary.","source_ids":["s1","s3"]},{"date":"2026-01-26","event":"zoning_approved","kind":"actual","note":"Plan commission recommended approval on 2026-01-21; the village board approved the site plan unanimously on 2026-01-26, allowing engineering plans and building permit applications to follow.","source_ids":["s2","s4"]}],"name":"Microsoft Mount Pleasant International Drive datacenter campus","notes":"Approved together with the nine-building Durand Avenue campus; the two campuses' combined estimated taxable value was reported as more than USD 13 billion. Microsoft told WPR that an energy-use estimate was not available.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s3"]},{"name":"Microsoft","note":"A Microsoft spokesperson said the land was bought in 2024; a village spokesperson said it came from the village or private owners.","role":"owner","source_ids":["s1","s2"]},{"name":"Village of Mount Pleasant","note":"The plan commission recommended and the village board approved the site plan; the campus sits in a tax increment financing district.","role":"government","source_ids":["s1","s2","s4"]}],"power_sources":[],"related_ids":["microsoft-fairwater-mount-pleasant","microsoft-mount-pleasant-durand-avenue"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-20","publisher":"Wisconsin Public Radio","title":"Microsoft wants to build 15 more data centers in Mount Pleasant","type":"news","url":"https://www.wpr.org/news/microsoft-15-more-data-centers-mount-pleasant"},{"accessed":"2026-10-09","id":"s2","published":"2026-01-21","publisher":"Wisconsin Public Radio","title":"Mount Pleasant commission approves Microsoft's plans for data center expansion","type":"news","url":"https://www.wpr.org/news/mount-pleasant-approves-microsoft-data-center-expansion"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260205013908/https://spectrumnews1.com/wi/milwaukee/news/2026/01/21/microsoft-to-expand-data-center-in-mount-pleasant-","id":"s3","published":"2026-01-21","publisher":"Spectrum News 1","title":"Microsoft to expand data center in Mount Pleasant","type":"news","url":"https://spectrumnews1.com/wi/milwaukee/news/2026/01/21/microsoft-to-expand-data-center-in-mount-pleasant-"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260223142131/https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval","id":"s4","published":"2026-01-27","publisher":"Spectrum News 1","title":"Mount Pleasant village board approves Microsoft data center expansion","type":"news","url":"https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval"}],"status":"announced","status_as_of":"2026-01-27","status_source_ids":["s4"],"summary":"Planned six-building Microsoft datacenter campus along International Drive in Mount Pleasant, Wisconsin, on about 530 acres Microsoft says it bought in 2024. Village planning documents reported by WPR describe more than 3.5 million sq ft of development, including a 74,000 sq ft office and other buildings, with an estimated taxable value of more than USD 5.3 billion. The plan commission recommended the site plan with conditions including a traffic impact analysis and water-use compliance, and the village board approved it unanimously in January 2026. Microsoft called the plans preliminary and gave no construction timeline or energy estimate."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"20fee728-51c4-598d-b3e8-3cf49887dbe3","s2":"4f5197a5-e9ca-5c03-81ba-881d66604cf7","s3":"c93ccee2-05e4-50e5-b256-af4c2a614dd7","s4":"17414c26-e568-5e54-ae88-13ac8e17f591"},"source_file":"datacenters/projects/microsoft-mount-pleasant-international-drive.json","source_record_id":"microsoft-mount-pleasant-international-drive","source_record_sha256":"2fc9140e0cc603e7e8d9d9b804a94e384834e7381c41e9a315d5d9adc4fd1354","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"43af0729feb6272f0be5d311a2eef5919b68162be01373e3449d95b38cce8061"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c5988379bc974f1f6240/#project-96848e3f-da64-53c8-be33-bf5c9cd2109a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/96848e3f-da64-53c8-be33-bf5c9cd2109a.json
96c80c6f-de7a-5e5c-b9b1-fc1bb7c738a6 | imported:semiconductor-atlas:adaniconnex-navi-mumbai | vcc-site-bb97e3ebf82c06ecfb2c | imported:semiconductor-atlas:adaniconnex-navi-mumbai | AdaniConneX Navi Mumbai data centre campus | India | IN | 19.0308 | 73.0199 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | The company names Navi Mumbai only. Coordinates are the OpenStreetMap Nominatim centroid of Navi Mumbai, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | e515e455-3532-5efd-a7b5-516691716bd7 | announced | 2026-10-09 | 4 | imported_documented_status | e515e455-3532-5efd-a7b5-516691716bd7 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e515e455-3532-5efd-a7b5-516691716bd7","notes":null,"party":"AdaniConneX","relationship_scope":"unknown","role":"developer","source_record_id":"adaniconnex-navi-mumbai"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.adaniconnex.com/data-centers | https://www.adaniconnex.com/data-centers | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AdaniConneX Navi Mumbai data centre campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"adaniconnex-navi-mumbai"},"record":{"aliases":[],"id":"adaniconnex-navi-mumbai","last_reviewed":"2026-10-09","location":{"admin1":"Maharashtra","country":"IN","lat":19.0308,"locality":"Navi Mumbai","lon":73.0199,"note":"The company names Navi Mumbai only. Coordinates are the OpenStreetMap Nominatim centroid of Navi Mumbai, not the site.","precision":"locality","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"power_capacity","note":"Listed by the company as potential capacity in IT load.","power_scope":"it_load","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":1000}],"milestones":[{"date":"2026-12","event":"first_operational","kind":"planned","note":"Company lists ready-for-service as December 2026 onwards.","source_ids":["s1"]}],"name":"AdaniConneX Navi Mumbai data centre campus","notes":"Single source: the status comes from the company's undated campus page, accessed on 2026-10-09, so status_as_of is that access date. Status is announced because the page calls the facility soon to be launched and gives no construction details.","parties":[{"name":"AdaniConneX","role":"developer","source_ids":["s1"]}],"power_sources":[{"description":"Company states up to 100% renewable energy; the supply arrangement is not described.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"AdaniConneX","title":"Data Centers","type":"company","url":"https://www.adaniconnex.com/data-centers"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s1"],"summary":"AdaniConneX lists a planned Navi Mumbai campus with a potential capacity of 1,000 MW of IT load, which the company says has not yet launched and will connect to the main internet exchanges over OPGW fibre. The company gives a ready-for-service date of December 2026 onwards and says the campus can use up to 100% renewable power. No address, investment figure, tenant or construction progress has been published in the sources reviewed.","workloads":["colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e515e455-3532-5efd-a7b5-516691716bd7"},"source_file":"datacenters/projects/adaniconnex-navi-mumbai.json","source_record_id":"adaniconnex-navi-mumbai","source_record_sha256":"3a6aa884cfc83d7ae8ea0b60217b27b5bf24328457b98137ca311f97f66040a2","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"193775fdbca5097dbd6c024a44e410dc247bfb83b30db731a1223388de798d11"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bb97e3ebf82c06ecfb2c/#project-96c80c6f-de7a-5e5c-b9b1-fc1bb7c738a6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/96c80c6f-de7a-5e5c-b9b1-fc1bb7c738a6.json
96d7988b-a1e7-517c-9218-462524058a80 | curated:israel-mega-dc-mdcil5-idan-hanegev-site:phase-a | vcc-site-166ec46634755791abc3 | curated:israel-mega-dc-mdcil5-idan-hanegev-site | Mega D.C. MDCIL-5 Idan HaNegev Phase A Current Build | Israel | IL | 31.3743 | 34.7899 | Polygon | campus | approved_plan_land_use_plot_ring_transformed_EPSG2039_to_WGS84 | Xplan_layer4_plot_query_native_ring_PROJ_Israel1993_to_WGS84_2_round7 | approved_statutory_plan_land_use_plot | official_source | campus_locator | Every native plot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. Plot 10 of plan 625-0866855 is bound to the campus by the issuer's own plot references; it is a planning plot, not a surveyed cadastral boundary, building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it. |  | The planning service states no positional accuracy and disclaims official status; the 0.5 m datum-operation figure is not a plot accuracy. | dae2e594-fb54-5b36-b83e-7a330026ca33 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 45c161db-5105-5885-9358-9d46a4861a63 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://megaor.co.il/wp-content/uploads/2026/08/דוח-רבעון-2-לשנת-2026.pdf | https://ags.iplan.gov.il/arcgisiplan/rest/services/PlanningPublic/Xplan/MapServer/4/query?where=num%3D%2710%27+AND+pl_number%3D%27625-0866855%27&outFields=*&returnGeometry=true&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-166ec46634755791abc3/#project-96d7988b-a1e7-517c-9218-462524058a80 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/96d7988b-a1e7-517c-9218-462524058a80.json
9753db27-dba7-5bba-933f-499d9b7ffa72 | imported:semiconductor-atlas:adaniconnex-hyderabad | vcc-site-42f06f3124352e4af817 | imported:semiconductor-atlas:adaniconnex-hyderabad | AdaniConneX Hyderabad data centre campus | India | IN | 17.3888 | 78.4611 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Hyderabad only. Coordinates are the OpenStreetMap Nominatim centroid of Hyderabad, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 9d576bb9-0637-5135-927f-62427dc5e634 | partially_operational | 2026-10-09 | 4 | imported_documented_status | 9d576bb9-0637-5135-927f-62427dc5e634 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9d576bb9-0637-5135-927f-62427dc5e634","notes":null,"party":"AdaniConneX","relationship_scope":"unknown","role":"developer","source_record_id":"adaniconnex-hyderabad"},{"evidence_id":"91046785-8eff-5626-9062-81343ddcc805","notes":null,"party":"AdaniConneX","relationship_scope":"unknown","role":"developer","source_record_id":"adaniconnex-hyderabad"},{"evidence_id":"9d576bb9-0637-5135-927f-62427dc5e634","notes":"Offers colocation and managed services at the campus.","party":"AdaniConneX","relationship_scope":"unknown","role":"operator","source_record_id":"adaniconnex-hyderabad"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | AdaniConneX |  |  |  | https://www.adaniconnex.com/data-centers | https://www.adaniconnex.com/data-centers | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AdaniConneX Hyderabad data centre campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"adaniconnex-hyderabad"},"record":{"aliases":[],"id":"adaniconnex-hyderabad","last_reviewed":"2026-10-09","location":{"admin1":"Telangana","country":"IN","lat":17.3888,"locality":"Hyderabad","lon":78.4611,"note":"Sources name Hyderabad only. Coordinates are the OpenStreetMap Nominatim centroid of Hyderabad, not the site.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"power_capacity","note":"Listed by the company as potential capacity in IT load.","power_scope":"it_load","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":600}],"milestones":[{"date":"2024-10","event":"first_operational","kind":"actual","note":"Company lists Phase 1 as live from October 2024; its capacity is not given.","source_ids":["s1"]}],"name":"AdaniConneX Hyderabad data centre campus","notes":"The status comes from the company's undated campus page, accessed on 2026-10-09, so status_as_of is that access date. Microsoft is not listed as a party because the Adani release does not state its role at the Hyderabad campus. The March 2024 safety-grading release confirms the Hyderabad site existed but gives no capacity or status.","parties":[{"name":"AdaniConneX","role":"developer","source_ids":["s1","s2"]},{"name":"AdaniConneX","note":"Offers colocation and managed services at the campus.","role":"operator","source_ids":["s1"]}],"power_sources":[{"description":"Company states up to 100% renewable energy; the supply arrangement is not described.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"AdaniConneX","title":"Data Centers","type":"company","url":"https://www.adaniconnex.com/data-centers"},{"accessed":"2026-10-09","id":"s2","published":"2024-03-13","publisher":"AdaniConneX","title":"AdaniConneX's Hyderabad Site Gets Five-Star Grading from British Safety Council","type":"company","url":"https://resources.adaniconnex.com/press-release/adaniconnexs-hyderabad-site-gets-five-star-grading-from-british-safety-council"},{"accessed":"2026-10-09","id":"s3","published":"2026-02-17","publisher":"Adani Group","title":"Adani Commits USD 100 Bn to Sovereign AI Infrastructure","type":"company","url":"https://www.adani.com/newsroom/media-releases/Adani-Commits-USD-100-Bn-to-Sovereign-AI-Infrastructure"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s1"],"summary":"AdaniConneX, the Adani group's data centre business, lists a Hyderabad campus with a potential capacity of 600 MW of IT load, of which a first phase went live in October 2024. The company says the campus can draw up to 100% renewable power and offers colocation, connectivity and managed services there. A February 2026 Adani group release links its Microsoft partnership to the Hyderabad and Pune campuses without describing the terms. The site address and the size of the live first phase have not been published.","workloads":["colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9d576bb9-0637-5135-927f-62427dc5e634","s2":"91046785-8eff-5626-9062-81343ddcc805","s3":"481f20f8-9c4b-5f9a-ac63-bf6d3b3d445f"},"source_file":"datacenters/projects/adaniconnex-hyderabad.json","source_record_id":"adaniconnex-hyderabad","source_record_sha256":"17a94d9c49e2094b59e61b04c231e4242f77cf0bdf7edef5589b966c20150cbb","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"508b7ad271f69810c514c007242d12f6a36e300dcd10a8788ecfbd34ed33a5ab"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-42f06f3124352e4af817/#project-9753db27-dba7-5bba-933f-499d9b7ffa72 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9753db27-dba7-5bba-933f-499d9b7ffa72.json
97f12a4b-6526-5c76-94b3-6562420ffe99 | curated:nscale-kvandal-narvik-ai-data-center-campus:initial-25mw-epc-current-build | vcc-site-2fb799e38497b94b3ed1 | curated:nscale-kvandal-narvik-ai-data-center-campus | Nscale Kvandal Initial 25 MW EPC Current Build | Norway | NO | 68.5753 | 17.5801 | Polygon | campus | cross_source_overlay | kartverket_official_cadastral_parcel_polygon_as_campus_locator | official_cadastral_parcel_as_campus_locator | official_source | campus_locator | Exact current Kartverket cadastral polygon for parcel 10/760, used only to locate the Nscale Kvandal campus and inherited by the 25 MW current-build project through the explicit v14 project_targets relationship. The parcel contains both officially mapped data-center buildings and is not the footprint or centroid of Data Center 1, the 25 MW EPC project, Data Center 2, or the complete campus. |  | The captured WFS publishes accuracy class “Grønt” but no numeric horizontal uncertainty in metres; the bridge does not convert that class into survey accuracy. | 7960e467-cbd7-52b6-9fe5-c0b3d905f1dd | under_construction | 2026-07-06 | 99 | authoritative_physical_status_update | 9f5522ca-0b7c-5b13-aa39-eeb8b5f704cb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.nscale.com/press-releases/nordscale | https://wfs.geonorge.no/skwms1/wfs.matrikkelen-eiendomskart-teig?service=WFS&version=2.0.0&request=GetFeature&typeNames=app%3ATeig&count=20&srsName=EPSG%3A4326&NAMESPACES=xmlns%28app%2Chttp%3A%2F%2Fskjema.geonorge.no%2FSOSI%2Fproduktspesifikasjon%2FMatrikkelen-Eiendomskart-Teig%2F20211101%29&FILTER=%3Cfes%3AFilter+xmlns%3Afes%3D%22http%3A%2F%2Fwww.opengis.net%2Ffes%2F2.0%22+xmlns%3Aapp%3D%22http%3A%2F%2Fskjema.geonorge.no%2FSOSI%2Fproduktspesifikasjon%2FMatrikkelen-Eiendomskart-Teig%2F20211101%22%3E%3Cfes%3AAnd%3E%3Cfes%3APropertyIsEqualTo%3E%3Cfes%3AValueReference%3Eapp%3Akommunenummer%3C%2Ffes%3AValueReference%3E%3Cfes%3ALiteral%3E1806%3C%2Ffes%3ALiteral%3E%3C%2Ffes%3APropertyIsEqualTo%3E%3Cfes%3APropertyIsEqualTo%3E%3Cfes%3AValueReference%3Eapp%3AmatrikkelnummerTekst%3C%2Ffes%3AValueReference%3E%3Cfes%3ALiteral%3E10%2F760%3C%2Ffes%3ALiteral%3E%3C%2Ffes%3APropertyIsEqualTo%3E%3C%2Ffes%3AAnd%3E%3C%2Ffes%3AFilter%3E | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2fb799e38497b94b3ed1/#project-97f12a4b-6526-5c76-94b3-6562420ffe99 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/97f12a4b-6526-5c76-94b3-6562420ffe99.json
987638c1-43b0-5075-a91a-f02ac2f007cc | imported:semiconductor-atlas:reliance-jamnagar-ai-data-center | vcc-site-7f644893d8685d1d4b44 | imported:semiconductor-atlas:reliance-jamnagar-ai-data-center | Reliance Jamnagar AI-enabled data centre for Meta | India | IN | 22.4732 | 70.0552 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | The release names Jamnagar, Gujarat only. Coordinates are the OpenStreetMap Nominatim centroid of Jamnagar city, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 12061b36-621f-5896-9816-570fc1e6d37f | announced | 2026-06-10 | 125 | imported_documented_status | 12061b36-621f-5896-9816-570fc1e6d37f | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"12061b36-621f-5896-9816-570fc1e6d37f","notes":null,"party":"Reliance Industries Limited","relationship_scope":"unknown","role":"developer","source_record_id":"reliance-jamnagar-ai-data-center"},{"evidence_id":"12061b36-621f-5896-9816-570fc1e6d37f","notes":"Responsible for design and construction.","party":"Reliance Industries Limited","relationship_scope":"unknown","role":"builder","source_record_id":"reliance-jamnagar-ai-data-center"},{"evidence_id":"12061b36-621f-5896-9816-570fc1e6d37f","notes":"To provide managed operational services, utilities management and network connectivity.","party":"Reliance Industries Limited","relationship_scope":"unknown","role":"operator","source_record_id":"reliance-jamnagar-ai-data-center"},{"evidence_id":"12061b36-621f-5896-9816-570fc1e6d37f","notes":"To manage the renewable power supply.","party":"Reliance Industries Limited","relationship_scope":"unknown","role":"power_supplier","source_record_id":"reliance-jamnagar-ai-data-center"},{"evidence_id":"12061b36-621f-5896-9816-570fc1e6d37f","notes":"Will lease capacity from the facility.","party":"Meta Platforms","relationship_scope":"unknown","role":"tenant","source_record_id":"reliance-jamnagar-ai-data-center"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Reliance Industries Limited |  | Meta Platforms |  | https://www.ril.com/sites/default/files/2026-06/10062026_MR_Reliance_and_Meta_to_Develop_AI-Enabled_Data_Centre_in_Jamnagar_Gujarat.pdf | https://www.ril.com/sites/default/files/2026-06/10062026_MR_Reliance_and_Meta_to_Develop_AI-Enabled_Data_Centre_in_Jamnagar_Gujarat.pdf | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Reliance Jamnagar AI-enabled data centre for Meta as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"reliance-jamnagar-ai-data-center"},"record":{"aliases":[],"id":"reliance-jamnagar-ai-data-center","last_reviewed":"2026-10-09","location":{"admin1":"Gujarat","admin2":"Jamnagar","country":"IN","lat":22.4732,"locality":"Jamnagar","lon":70.0552,"note":"The release names Jamnagar, Gujarat only. Coordinates are the OpenStreetMap Nominatim centroid of Jamnagar city, not the site.","precision":"locality","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-10","basis":"planned","metric":"power_capacity","note":"The release adds that there is an option to scale beyond this.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":168}],"milestones":[{"date":"2026-06-10","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2028","event":"first_operational","kind":"planned","note":"Reliance said the capacity would be delivered within two years of the June 2026 announcement.","source_ids":["s1"]}],"name":"Reliance Jamnagar AI-enabled data centre for Meta","notes":"Only the company release was available for this record; no construction progress had been reported in the sources reviewed. The power figure is not labelled as IT load or facility power.","parties":[{"name":"Reliance Industries Limited","role":"developer","source_ids":["s1"]},{"name":"Reliance Industries Limited","note":"Responsible for design and construction.","role":"builder","source_ids":["s1"]},{"name":"Reliance Industries Limited","note":"To provide managed operational services, utilities management and network connectivity.","role":"operator","source_ids":["s1"]},{"name":"Reliance Industries Limited","note":"To manage the renewable power supply.","role":"power_supplier","source_ids":["s1"]},{"name":"Meta Platforms","note":"Will lease capacity from the facility.","role":"tenant","source_ids":["s1"]}],"power_sources":[{"description":"To be powered by renewable energy managed by Reliance; the technology mix was not specified.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260831105528/https://www.ril.com/sites/default/files/2026-06/10062026_MR_Reliance_and_Meta_to_Develop_AI-Enabled_Data_Centre_in_Jamnagar_Gujarat.pdf","id":"s1","published":"2026-06-10","publisher":"Reliance Industries Limited","title":"Reliance and Meta to Develop AI-Enabled Data Centre in Jamnagar, Gujarat","type":"company","url":"https://www.ril.com/sites/default/files/2026-06/10062026_MR_Reliance_and_Meta_to_Develop_AI-Enabled_Data_Centre_in_Jamnagar_Gujarat.pdf"}],"status":"announced","status_as_of":"2026-06-10","status_source_ids":["s1"],"summary":"Reliance Industries agreed in June 2026 to develop a 168 MW AI-enabled data centre in Jamnagar, Gujarat, built to suit Meta, which will lease capacity there to support its global infrastructure and AI compute. Reliance is to handle design, construction, utilities, renewable power, network connectivity and managed operations, with delivery targeted within two years and an option to expand. The facility is to be cooled with desalinated seawater. Reliance described it as Meta's first built-to-suit data centre capacity in India.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"12061b36-621f-5896-9816-570fc1e6d37f"},"source_file":"datacenters/projects/reliance-jamnagar-ai-data-center.json","source_record_id":"reliance-jamnagar-ai-data-center","source_record_sha256":"8728624624506889a917efa504539545fa6de92360d5f39b83f3ac96b202431e","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"2a1bd57413bbf96d609c7d6ae3d95c3e5b0bf66dca12b87d235e350a9ba80fec"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7f644893d8685d1d4b44/#project-987638c1-43b0-5075-a91a-f02ac2f007cc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/987638c1-43b0-5075-a91a-f02ac2f007cc.json
98e47ac5-8576-53f7-ab71-9f3d683b5ec5 | curated:ast-janciems-dispatcher-control-data-center:fit-out-after-building-completion | vcc-site-fe9285f72381fc346e86 | curated:ast-janciems-dispatcher-control-data-center | AST Jāņciems Fit-out After Building Completion | Latvia | LV | 56.9331 | 24.1815 | Point | project | direct_geometry | authoritative_address_geocode | facility_address_point | official_source | reviewed_site_locator | Current Latvian State Land Service address-register point, facility-specific, with 20 metre stated uncertainty. | 20 |  | 458f3a8b-8978-5fa6-a7f9-35d2f1801375 | shell | 2026-06-27 | 108 | authoritative_physical_status_update | e0c26d7e-7fcb-5f72-8b46-02986a635772 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.ast.lv/en/events/commissioning-new-building-latvias-power-system-main-dispatcher-control-and-data-centre | https://geo-dpps.viss.gov.lv/api/DPPSPackage/client/Adresu_tel_418_k6gL2A/3d692785-0c95-44a8-816c-f2f91493c4ce?service=WFS&version=2.0.0&request=GetFeature&typeNames=ad%3AAddress&featureID=AD101873308 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fe9285f72381fc346e86/#project-98e47ac5-8576-53f7-ab71-9f3d683b5ec5 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/98e47ac5-8576-53f7-ab71-9f3d683b5ec5.json
99fa93f5-9f63-5576-b036-2ee8086032a3 | curated:goodman-syd01-macquarie-park-data-centre:current-single-building-development | vcc-site-37497f8175db87d92ef8 | curated:goodman-syd01-macquarie-park-data-centre | Goodman SYD01 Current Single-Building Development | Australia | AU | -33.8184 | 151.19 | Point | project | coordinates_to_point | nsw_planning_portal_applicant_project_coordinate_to_point | official_applicant_project_site_reference_point | official_source | project_locator | Applicant-reported State Significant Development project-site coordinate for SSD-66777221, whose project name, applicant, address, and lots bind the SYD01 development. It is a point locator, not any lot, parcel, campus, building, project, or current-work boundary. |  | The application supplies no datum, reference-feature definition, collection method, or numeric horizontal-accuracy statement. | 8f3069b1-7b32-5df4-9329-c365ae2a09bb | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | 1ad44bfe-736f-511c-91ea-89c64e5f5970 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.13 geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://au.goodman.com/en/our-properties/properties-for-lease/goodman-syd01 | https://majorprojects.planningportal.nsw.gov.au/prweb/PRRestService/mp/01/getContent?AttachRef=SSD-66777221%2120240606T082629.257+GMT | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-37497f8175db87d92ef8/#project-99fa93f5-9f63-5576-b036-2ee8086032a3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/99fa93f5-9f63-5576-b036-2ee8086032a3.json
9a4afe64-8789-5cee-8947-61a12f8966a8 | imported:semiconductor-atlas:beacon-ai-centers-heartland | vcc-site-5376b585718a989c8dc5 | imported:semiconductor-atlas:beacon-ai-centers-heartland | Beacon AI Centers Heartland campus (Sturgeon County) | Canada | CA | 53.8403 | -113.1922 | Point | project | imported_reference_point | imported_reference_point | site | compiled_reference | project_locator | Decimal coordinates stated in the federal project description summary, which places the project just north-northeast of Highway 643 and Range Road 223 (NW and SW quarters of Section 15-56-22-W4M). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 444bf1b1-03c1-5c00-8571-522390feeb7b | proposed | 2026-03-10 | 217 | imported_documented_status | 59a5285d-e8b2-5ec5-9b2e-c109009160bd | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"444bf1b1-03c1-5c00-8571-522390feeb7b","notes":null,"party":"Beacon AI Centers","relationship_scope":"unknown","role":"developer","source_record_id":"beacon-ai-centers-heartland"},{"evidence_id":"4b8016f6-a212-5cdf-a9ba-ea096f8e8754","notes":null,"party":"Beacon AI Centers","relationship_scope":"unknown","role":"developer","source_record_id":"beacon-ai-centers-heartland"},{"evidence_id":"444bf1b1-03c1-5c00-8571-522390feeb7b","notes":"Project-specific entity, with general partner Northbridge Power GPC Inc., that would build and operate the on-site gas plant.","party":"Heartland Power Generation LP","relationship_scope":"unknown","role":"power_supplier","source_record_id":"beacon-ai-centers-heartland"},{"evidence_id":"59a5285d-e8b2-5ec5-9b2e-c109009160bd","notes":"Project-specific entity, with general partner Northbridge Power GPC Inc., that would build and operate the on-site gas plant.","party":"Heartland Power Generation LP","relationship_scope":"unknown","role":"power_supplier","source_record_id":"beacon-ai-centers-heartland"},{"evidence_id":"4b8016f6-a212-5cdf-a9ba-ea096f8e8754","notes":"Project-specific entity, with general partner Northbridge Power GPC Inc., that would build and operate the on-site gas plant.","party":"Heartland Power Generation LP","relationship_scope":"unknown","role":"power_supplier","source_record_id":"beacon-ai-centers-heartland"},{"evidence_id":"444bf1b1-03c1-5c00-8571-522390feeb7b","notes":"Owner of the existing 240 kV transmission line the project would tap for its grid connection.","party":"AltaLink","relationship_scope":"unknown","role":"utility","source_record_id":"beacon-ai-centers-heartland"},{"evidence_id":"444bf1b1-03c1-5c00-8571-522390feeb7b","notes":"Municipality engaged on local planning and permitting; it completed the AUC municipal engagement form.","party":"Sturgeon County","relationship_scope":"unknown","role":"government","source_record_id":"beacon-ai-centers-heartland"},{"evidence_id":"4b8016f6-a212-5cdf-a9ba-ea096f8e8754","notes":"Municipality engaged on local planning and permitting; it completed the AUC municipal engagement form.","party":"Sturgeon County","relationship_scope":"unknown","role":"government","source_record_id":"beacon-ai-centers-heartland"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.iaac-aeic.gc.ca/050/evaluations/proj/90123 | https://iaac-aeic.gc.ca/050/documents/p90123/164350E.pdf | [{"identity_decision":{"decision":"unique_site","flags":["source_site_point_not_surveyed_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Beacon AI Centers Heartland campus (Sturgeon County) as an independent source record; its site locator does not itself establish a surveyed physical site.","source_record_id":"beacon-ai-centers-heartland"},"record":{"aliases":["Beacon AI Centers Heartland Project","Beacon Data Centers Heartland Project","Beacon Heartland AI Hub"],"id":"beacon-ai-centers-heartland","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","admin2":"Sturgeon County","country":"CA","lat":53.84032,"locality":"About 7 km east of Gibbons","lon":-113.192246,"note":"Decimal coordinates stated in the federal project description summary, which places the project just north-northeast of Highway 643 and Range Road 223 (NW and SW quarters of Section 15-56-22-W4M).","precision":"site","source_ids":["s1","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-12-28","basis":"planned","metric":"power_capacity","note":"Four planned data halls rated at 200 MWe each, matching the roughly 800 MWe of continuous supply the plant would deliver to them. The filings do not say whether this is IT or total facility load.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1","s4"],"unit":"MW","value":800},{"applies_to":"campus","as_of":"2025-12-28","basis":"planned","metric":"power_capacity","note":"Nominal capacity of 200 INNIO Jenbacher J624 gas engines of 4.6 MWe each, grouped in 40 modules.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s1","s2","s4"],"unit":"MW","value":920},{"applies_to":"campus","as_of":"2025-12-28","basis":"planned","metric":"land_area","note":"Data centre campus area; the power plant would occupy a 32-acre footprint within it.","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":317},{"applies_to":"campus","as_of":"2025-12-28","basis":"planned","metric":"buildings","note":"Separate data hall structures, still under design.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":4}],"milestones":[{"date":"2025-12-14","event":"other","kind":"actual","note":"Initial project description for the gas plant submitted to the Impact Assessment Agency of Canada.","source_ids":["s2"]},{"date":"2025-12-19","event":"other","kind":"actual","note":"Power plant application filed with the Alberta Utilities Commission.","source_ids":["s4"]},{"date":"2026-03-09","event":"other","kind":"actual","note":"Impact Assessment Agency of Canada decided that no further federal assessment of the power plant is required; the notice was posted on 10 March 2026.","source_ids":["s3"]},{"date":"2026-Q3","event":"construction_started","kind":"planned","note":"Civil works and foundations scheduled for Q3 2026 in the December 2025 filing; no source confirms a start.","source_ids":["s1"]},{"date":"2027-Q3","event":"first_operational","kind":"planned","note":"Targeted commercial operation date of the power plant.","source_ids":["s1"]}],"name":"Beacon AI Centers Heartland campus (Sturgeon County)","notes":"The federal filing includes data centre details for information only; the data centre is not part of the federally reviewed power project. No Alberta Utilities Commission decision on proceeding 30518 was found, and the AUC proceeding page could not be opened. The proponent said a federal impact assessment, had one been required, would have pushed in-service to about Q3 2030.","parties":[{"name":"Beacon AI Centers","role":"developer","source_ids":["s1","s4"]},{"name":"Heartland Power Generation LP","note":"Project-specific entity, with general partner Northbridge Power GPC Inc., that would build and operate the on-site gas plant.","role":"power_supplier","source_ids":["s1","s2","s4"]},{"name":"AltaLink","note":"Owner of the existing 240 kV transmission line the project would tap for its grid connection.","role":"utility","source_ids":["s1"]},{"name":"Sturgeon County","note":"Municipality engaged on local planning and permitting; it completed the AUC municipal engagement form.","role":"government","source_ids":["s1","s4"]}],"power_sources":[{"description":"About 920 MWe of on-site gas reciprocating engines in four generation pods, fuelled by a new lateral from the NGTL and ATCO pipeline system about 0.5 km east, running as a microgrid for the campus.","source_ids":["s1","s4"],"type":"natural_gas_onsite"},{"description":"The plant would also connect to Alberta's grid through a new on-site substation (initially listed at 400 MW) T-tapped to an existing AltaLink 240 kV line; the connection design was not finalised when the AUC application was filed.","source_ids":["s1","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-12-28","publisher":"Heartland Power Generation LP (filed with the Impact Assessment Agency of Canada)","title":"Beacon AI Centers - Heartland Project: Initial Project Description Summary","type":"regulatory_filing","url":"https://iaac-aeic.gc.ca/050/documents/p90123/164350E.pdf"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Impact Assessment Agency of Canada","title":"Beacon AI Centers Heartland Project (Canadian Impact Assessment Registry, reference 90123)","type":"government","url":"https://www.iaac-aeic.gc.ca/050/evaluations/proj/90123"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-10","publisher":"Impact Assessment Agency of Canada","title":"Notice of Early Decision with Reasons: Beacon AI Centers Heartland Project","type":"government","url":"https://iaac-aeic.gc.ca/050/evaluations/document/165326?culture=en-CA"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260606010642/https://media.auc.ab.ca/prd-wp-uploads/Shared%20Documents/Projects/30518-BeaconAICentersHeartlandProject.pdf","id":"s4","published":"2025-12-19","publisher":"Heartland Power Generation LP (filed with the Alberta Utilities Commission)","title":"Beacon AI Centers - Heartland Project Thermal Power Plant Application (cover letter)","type":"regulatory_filing","url":"https://media.auc.ab.ca/prd-wp-uploads/Shared%20Documents/Projects/30518-BeaconAICentersHeartlandProject.pdf"}],"status":"proposed","status_as_of":"2026-03-10","status_source_ids":["s2","s3"],"summary":"Beacon AI Centers proposes a 317-acre AI data centre campus about 7 km east of Gibbons in Sturgeon County, Alberta, inside the Alberta Industrial Heartland heavy industrial zone. Filings describe four data halls rated at 200 MW each, supplied by an on-site plant of 200 gas engines totalling about 920 MW, built by the project entity Heartland Power. The federal agency decided in March 2026 that no further federal assessment was needed; the plant application filed with the Alberta Utilities Commission in December 2025 had no decision found. The proponent targeted commercial operation in Q3 2027.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"444bf1b1-03c1-5c00-8571-522390feeb7b","s2":"59a5285d-e8b2-5ec5-9b2e-c109009160bd","s3":"2845fdef-aa69-5234-99c2-694474e06566","s4":"4b8016f6-a212-5cdf-a9ba-ea096f8e8754"},"source_file":"datacenters/projects/beacon-ai-centers-heartland.json","source_record_id":"beacon-ai-centers-heartland","source_record_sha256":"3fa20de3718e9272491cd51627f812d8541cc3638c62724375f137b02b6e33f9","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"472c330bc6e95626a2ae8848324378d0552a0e8ad176bf05a030ee210ad939f7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5376b585718a989c8dc5/#project-9a4afe64-8789-5cee-8947-61a12f8966a8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9a4afe64-8789-5cee-8947-61a12f8966a8.json
9be0ab88-c727-5dbc-8a12-e2443878b69f | curated:atnorth-ice02-reykjanesbaer-campus:phase-2-expansion | vcc-site-17f7ed745e789e79ad69 | curated:atnorth-ice02-reykjanesbaer-campus | atNorth ICE02 Phase 2 Expansion | Iceland | IS | 63.9636 | -22.5385 | Polygon | campus | cross_source_overlay | openstreetmap_named_campus_fence_boundary | reviewed_openstreetmap_named_campus_fence | community_mapped | campus_locator | The frozen global-open-v3 Polygon is a reviewed named ICE02 campus fence/site locator inherited by the phase-two project through the explicit project_targets relationship. It is not an official, cadastral, or survey boundary; a complete current campus extent; a building footprint; or a Phase 2 footprint. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | 6aa2c3ec-e7cc-59f0-8cd1-4b6e68a51fef | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | 5d2dd8ab-e30c-5a8d-816e-6b5b744cc665 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.mannverk.is/allprojects/atnorth2 | https://www.openstreetmap.org/way/1223207434 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-17f7ed745e789e79ad69/#project-9be0ab88-c727-5dbc-8a12-e2443878b69f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9be0ab88-c727-5dbc-8a12-e2443878b69f.json
9c34c305-5149-5961-b88f-648da82351f7 | curated:cdc-beard-campus:be1-current-build | vcc-site-61f9e739f63e5c96092e | curated:cdc-beard-campus | CDC Beard BE1 Current Data Center Build | Australia | AU | -35.3402 | 149.2092 | Polygon | project | direct_geometry | act_official_retired_block_polygon_as_be1_historical_project_locator | official_historical_cadastral_parcel_as_project_locator | official_source | project_locator | ACT Block 24 Section 11 polygon cross-identified to the BE1 DA plan. The source marks the block RETIRED, so the exact polygon is published only as a historical project locator; it is never a current parcel, present legal boundary, campus boundary, project footprint, building footprint, or current-work extent. |  | The ACT feature supplies no bounded numeric horizontal-accuracy value, and its retired lifecycle makes it unsuitable as a present legal-boundary claim. | 9677a40a-6a16-59e3-b098-3bf415f47dfd | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | c6cc7f23-5fd6-5f6a-9efb-af631204f5c3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.15 global geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.cdc.com.au/locations/canberra/ | https://services1.arcgis.com/E5n4f1VY84i0xSjy/ArcGIS/rest/services/ACTGOV_BLOCKS/FeatureServer/0/query?where=DIVISION_NAME%3D%27BEARD%27%20AND%20SECTION_NUMBER%3D11%20AND%20BLOCK_NUMBER%3D24&outFields=%2A&returnGeometry=true&outSR=4326&f=geojson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-61f9e739f63e5c96092e/#project-9c34c305-5149-5961-b88f-648da82351f7 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9c34c305-5149-5961-b88f-648da82351f7.json
9cceddca-71bc-52f2-a417-e9fdf0d7faa3 | curated:cdc-laverton-melbourne-campus:current-build | vcc-site-0f9ffed73b02dd75c9a5 | curated:cdc-laverton-melbourne-campus | CDC Laverton Current Build | Australia | AU | -37.8416 | 144.7754 | Polygon | facility | cross_source_geometry | openstreetmap_cdc_laverton_named_development_polygon_as_parent_campus_locator | reviewed_openstreetmap_cdc_laverton_named_development_polygon | community_mapped | campus_locator | Contributor-mapped named development/address polygon used only to locate the parent Laverton campus. It is not the current-build project boundary, a complete campus boundary, an official parcel or planning boundary, a building footprint, a security fence, or a current construction-progress extent. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | e07bd94a-9734-5f78-a7b6-d69e757357c2 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | d05112cf-0117-5f1a-9b7a-4087ec4f5c8f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"d05112cf-0117-5f1a-9b7a-4087ec4f5c8f","party":"CDC Data Centres","relationship_scope":"intended","role":"operator"}] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | CDC Data Centres |  |  |  | https://www.cdc.com.au/locations/melbourne/ | https://www.openstreetmap.org/way/263915226 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0f9ffed73b02dd75c9a5/#project-9cceddca-71bc-52f2-a417-e9fdf0d7faa3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9cceddca-71bc-52f2-a417-e9fdf0d7faa3.json
9d173225-d19b-5566-ab43-b319b0434236 | imported:semiconductor-atlas:sify-chennai-02-siruseri | vcc-site-dc7beeb061c0e039f4cf | imported:semiconductor-atlas:sify-chennai-02-siruseri | Sify Chennai 02 data center campus, Siruseri | India | IN | 12.835 | 80.2 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Siruseri, Chennai, without an address. The point is the Siruseri coordinate from its Wikipedia article (which also gives the district), so it marks the locality rather than the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ac5b7466-58d3-5166-a4b9-6156d63c66d9 | partially_operational | 2025-10-16 | 362 | imported_documented_status | dd4c722d-2527-58da-8f7d-44631da38bdb | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ac5b7466-58d3-5166-a4b9-6156d63c66d9","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"developer","source_record_id":"sify-chennai-02-siruseri"},{"evidence_id":"dd4c722d-2527-58da-8f7d-44631da38bdb","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"developer","source_record_id":"sify-chennai-02-siruseri"},{"evidence_id":"dd4c722d-2527-58da-8f7d-44631da38bdb","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"operator","source_record_id":"sify-chennai-02-siruseri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Sify Infinit Spaces Limited |  |  |  | https://nsearchives.nseindia.com/corporate/Registration_17102025141743_DRHP_Fillingversion.pdf | https://w.media/sify-and-partners-to-invest-rs-10000-crores-in-chennai-dc-over-next-five-years-mp-vijaykumar/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Sify Chennai 02 data center campus, Siruseri as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"sify-chennai-02-siruseri"},"record":{"aliases":["Chennai 02","Sify Siruseri campus"],"id":"sify-chennai-02-siruseri","last_reviewed":"2026-10-09","location":{"admin1":"Tamil Nadu","admin2":"Chengalpattu district","country":"IN","lat":12.835,"locality":"Siruseri","lon":80.2,"note":"Sources name Siruseri, Chennai, without an address. The point is the Siruseri coordinate from its Wikipedia article (which also gives the district), so it marks the locality rather than the site.","precision":"locality","source_ids":["s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-04-30","basis":"planned","metric":"power_capacity","note":"Eventual IT power of the three-tower campus as given on Sify's website (130+ MW). W.Media (s2) reported an eventual capacity of 130 MW without stating the scope.","power_scope":"it_load","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":130},{"applies_to":"phase","as_of":"2025-06-30","basis":"operational","metric":"power_capacity","note":"Installed IT capacity of Tower B at 30 June 2025; none was installed at 31 March 2025. The prospectus defines built capacity as the maximum IT load a facility is engineered to support on its present design, and installed capacity as the part that is equipped, powered and commissioned.","phase_label":"Tower B (installed capacity)","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":4.32},{"applies_to":"phase","as_of":"2025-06-30","basis":"planned","metric":"power_capacity","note":"Built IT capacity of Tower B at 30 June 2025. The prospectus defines built capacity as the maximum IT load a facility is engineered to support on its present design, and installed capacity as the part that is equipped, powered and commissioned. Only 4.32 MW was installed, so this figure is recorded as planned rather than operational.","phase_label":"Tower B (built capacity)","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":25.92},{"applies_to":"phase","as_of":"2025-10-16","basis":"planned","metric":"power_capacity","note":"Additional built IT capacity planned by the financial year ending March 2028.","phase_label":"Completion of Tower B (additional capacity)","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":26},{"applies_to":"campus","as_of":"2025-04-30","basis":"announced","metric":"investment","note":"INR 10,000 crore planned over five years by Sify together with partners (hyperscalers, enterprises and public sector companies), up from an original INR 2,500 crore commitment.","qualifier":"exact","source_ids":["s2"],"unit":"INR","value":100000000000},{"applies_to":"phase","as_of":"2025-04-30","basis":"announced","metric":"investment","note":"W.Media reports that the first phase was developed at a cost of INR 1,882 crore; how this relates to the prospectus estimate for Tower B is not explained.","phase_label":"Initial phase","qualifier":"exact","source_ids":["s2"],"unit":"INR","value":18820000000},{"applies_to":"phase","as_of":"2025-10-16","basis":"announced","metric":"investment","note":"Estimated cost of Tower B excluding land, certified by an independent chartered engineer; about INR 4.41 billion had been spent by 31 August 2025.","phase_label":"Tower B","qualifier":"exact","source_ids":["s3"],"unit":"INR","value":12020070000},{"applies_to":"campus","as_of":"2025-10-16","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"count","value":3}],"milestones":[{"date":"2025-04","event":"first_operational","kind":"actual","note":"Inauguration of the first tower by Tamil Nadu's chief minister, reported on 2025-04-30 without an event date. The prospectus shows no installed capacity at 31 March 2025 and 4.32 MW at 30 June 2025.","source_ids":["s2","s3"]},{"date":"2028","event":"other","kind":"planned","note":"Completion of Tower B, adding 26 MW of built IT capacity, targeted by the financial year ending March 2028; towers A and C had not started.","source_ids":["s3"]}],"name":"Sify Chennai 02 data center campus, Siruseri","notes":"Sify's undated website (s1) still describes the Siruseri campus as becoming operational soon, which is older than the prospectus position; the status rests on the October 2025 prospectus, and no 2026 campus-level update was found. The prospectus places Tower B on a 4.90-acre plot in the SIPCOT Industrial Park, Siruseri, leased from SIPCOT. The INR 10,000 crore figure includes partners' spending and is a five-year plan, not Sify's own committed budget. Tamil Nadu's chief minister inaugurated the first tower; the state has no other stated role, so it is not listed as a party. Siruseri coordinates and the district come from Wikipedia (s4), used only for the location.","parties":[{"name":"Sify Infinit Spaces Limited","role":"developer","source_ids":["s2","s3"]},{"name":"Sify Infinit Spaces Limited","role":"operator","source_ids":["s3"]}],"power_sources":[{"description":"On-site 230 kV GIS substation.","source_ids":["s3"],"type":"grid"},{"description":"About 60% of power came from renewable sources in April 2025, with a stated aim of 80-90% and eventually fully renewable supply; the generation types were not given.","source_ids":["s2"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Sify Technologies","title":"Data centre","type":"company","url":"https://www.sifytechnologies.com/europe/data-centre/"},{"accessed":"2026-10-09","id":"s2","published":"2025-04-30","publisher":"W.Media","title":"Sify and partners to invest Rs 10,000 crores in Chennai DC over next five years: MP Vijaykumar","type":"trade_press","url":"https://w.media/sify-and-partners-to-invest-rs-10000-crores-in-chennai-dc-over-next-five-years-mp-vijaykumar/"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-16","publisher":"Sify Infinit Spaces Limited (filed with SEBI; hosted by National Stock Exchange of India)","title":"Sify Infinit Spaces Limited: Draft Red Herring Prospectus (filing version)","type":"regulatory_filing","url":"https://nsearchives.nseindia.com/corporate/Registration_17102025141743_DRHP_Fillingversion.pdf"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Siruseri","type":"other","url":"https://en.wikipedia.org/wiki/Siruseri"}],"status":"partially_operational","status_as_of":"2025-10-16","status_source_ids":["s3"],"summary":"Sify Infinit Spaces' hyperscale and AI-ready campus at Siruseri, Chennai, is planned as three towers over a shared basement, with an on-site subsea cable landing station and a 230 kV GIS substation. Tamil Nadu's chief minister inaugurated the first tower in April 2025, when Sify said the campus would eventually reach 130 MW and that it and its partners planned to invest INR 10,000 crore over five years. Sify's October 2025 prospectus reported 25.92 MW of built IT capacity in Tower B, of which 4.32 MW was installed, planned another 26 MW there by the year to March 2028, and said work on towers A and C had not begun.","workloads":["colocation","cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"fe5b75a7-bddd-5e21-bf9c-a48236387dd4","s2":"ac5b7466-58d3-5166-a4b9-6156d63c66d9","s3":"dd4c722d-2527-58da-8f7d-44631da38bdb","s4":"89650fad-c134-580c-983c-6f5794dcf265"},"source_file":"datacenters/projects/sify-chennai-02-siruseri.json","source_record_id":"sify-chennai-02-siruseri","source_record_sha256":"170ba28a751e64c53e17b26ae9c52ee55b7d914376056eebf8b052bcd8c64285","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1c5b10951d644b597903819d7720293e0aaebd1c10ae4c460b60f4872b1692f7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dc7beeb061c0e039f4cf/#project-9d173225-d19b-5566-ab43-b319b0434236 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9d173225-d19b-5566-ab43-b319b0434236.json
9dbfd718-7b41-58b1-bb46-0138b96aeca8 | imported:semiconductor-atlas:terawulf-justified-data-hawesville | vcc-site-dbe568d910290db51ead | imported:semiconductor-atlas:terawulf-justified-data-hawesville | TeraWulf Justified Data campus (Hawesville) | United States | US | 37.9011 | -86.7494 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City coordinates from Wikipedia. TeraWulf places the campus at the former Century Aluminum Hawesville facility in Hancock County, whose exact position is not given in the sources. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 30a8faac-6bf4-5f82-80b3-159eed56720e | announced | 2026-08-24 | 50 | imported_documented_status | 01b458cf-d4e4-5032-bd65-3afdc46856b8 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"30a8faac-6bf4-5f82-80b3-159eed56720e","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"7765458b-3843-5a7a-b6c0-6188e7ae143f","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"01b458cf-d4e4-5032-bd65-3afdc46856b8","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"30a8faac-6bf4-5f82-80b3-159eed56720e","notes":"Announced on February 2, 2026 that it had acquired the site.","party":"TeraWulf","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"7765458b-3843-5a7a-b6c0-6188e7ae143f","notes":"20-year lease for about 401 MW of critical IT load signed in July 2026.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"83a7245e-347c-5b30-a1ed-04dfa6146efb","notes":"20-year lease for about 401 MW of critical IT load signed in July 2026.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"01b458cf-d4e4-5032-bd65-3afdc46856b8","notes":"The Kentucky PSC authorized Big Rivers and Kenergy to implement the retail electric service agreement for the campus.","party":"Big Rivers Electric Corporation","relationship_scope":"unknown","role":"utility","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"01b458cf-d4e4-5032-bd65-3afdc46856b8","notes":"The Kentucky PSC authorized Kenergy and Big Rivers to implement the retail electric service agreement for the campus.","party":"Kenergy Corp.","relationship_scope":"unknown","role":"utility","source_record_id":"terawulf-justified-data-hawesville"},{"evidence_id":"01b458cf-d4e4-5032-bd65-3afdc46856b8","notes":"Approved the retail electric service agreement in an order dated August 21, 2026.","party":"Kentucky Public Service Commission","relationship_scope":"unknown","role":"government","source_record_id":"terawulf-justified-data-hawesville"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | TeraWulf |  |  | Anthropic |  | https://investors.terawulf.com/news-events/press-releases/detail/145/kentucky-psc-approves-482-mw-power-agreement-for-terawulfs-justified-data-campus | https://investors.terawulf.com/news-events/press-releases/detail/129/terawulf-expands-digital-and-power-infrastructure-portfolio-with-strategic-acquisitions-in-kentucky-and-maryland | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve TeraWulf Justified Data campus (Hawesville) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"terawulf-justified-data-hawesville"},"record":{"aliases":["Justified Data Campus"],"id":"terawulf-justified-data-hawesville","last_reviewed":"2026-10-09","location":{"admin1":"Kentucky","admin2":"Hancock County","country":"US","lat":37.9011,"locality":"Hawesville","lon":-86.7494,"note":"City coordinates from Wikipedia. TeraWulf places the campus at the former Century Aluminum Hawesville facility in Hancock County, whose exact position is not given in the sources.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-06","basis":"contracted","metric":"power_capacity","power_scope":"it_load","qualifier":"approximately","source_ids":["s2","s3"],"unit":"MW","value":401},{"applies_to":"campus","as_of":"2026-08-21","basis":"contracted","metric":"power_capacity","note":"Electric service under the agreement approved by the Kentucky PSC; TeraWulf earlier described about 480 MW of existing power availability at the site.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s4"],"unit":"MW","value":482},{"applies_to":"phase","as_of":"2026-08-24","basis":"announced","metric":"investment","note":"TeraWulf estimate based on $10 million to $12 million per MW of critical IT load; excludes customer investment in computing equipment.","phase_label":"Site development and initial data halls","qualifier":"range","source_ids":["s4"],"unit":"USD","value":4000000000,"value_high":4500000000},{"applies_to":"campus","as_of":"2026-02-02","basis":"acquired","metric":"land_area","note":"Buildable acres.","qualifier":"more_than","source_ids":["s1","s3"],"unit":"acres","value":250}],"milestones":[{"date":"2026-02","event":"site_acquired","kind":"actual","note":"TeraWulf announced on February 2, 2026 that it had acquired the Hawesville site.","source_ids":["s1"]},{"date":"2026-07-06","event":"other","kind":"actual","note":"Anthropic lease announced.","source_ids":["s2"]},{"date":"2026-08-21","event":"other","kind":"actual","note":"Kentucky PSC approved the up-to-482 MW retail electric service agreement.","source_ids":["s4"]},{"date":"2027-H2","event":"first_operational","kind":"planned","note":"Initial capacity expected in service.","source_ids":["s2","s3"]},{"date":"2028-H1","event":"fully_operational","kind":"planned","note":"TeraWulf expects the full 401 MW by early 2028.","source_ids":["s2","s3"]}],"name":"TeraWulf Justified Data campus (Hawesville)","parties":[{"name":"TeraWulf","role":"developer","source_ids":["s1","s2","s4"]},{"name":"TeraWulf","note":"Announced on February 2, 2026 that it had acquired the site.","role":"owner","source_ids":["s1"]},{"name":"Anthropic","note":"20-year lease for about 401 MW of critical IT load signed in July 2026.","role":"tenant","source_ids":["s2","s3"]},{"name":"Big Rivers Electric Corporation","note":"The Kentucky PSC authorized Big Rivers and Kenergy to implement the retail electric service agreement for the campus.","role":"utility","source_ids":["s4"]},{"name":"Kenergy Corp.","note":"The Kentucky PSC authorized Kenergy and Big Rivers to implement the retail electric service agreement for the campus.","role":"utility","source_ids":["s4"]},{"name":"Kentucky Public Service Commission","note":"Approved the retail electric service agreement in an order dated August 21, 2026.","role":"government","source_ids":["s4"]}],"power_sources":[{"description":"Up to 482 MW of retail electric service under a PSC-approved agreement implemented by Kenergy and Big Rivers, using the site's energized on-site substation and existing high-voltage transmission lines.","source_ids":["s1","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260901033739/https://investors.terawulf.com/news-events/press-releases/detail/129/terawulf-expands-digital-and-power-infrastructure-portfolio-with-strategic-acquisitions-in-kentucky-and-maryland","id":"s1","published":"2026-02-02","publisher":"TeraWulf","title":"TeraWulf Expands Digital and Power Infrastructure Portfolio with Strategic Acquisitions in Kentucky and Maryland","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/129/terawulf-expands-digital-and-power-infrastructure-portfolio-with-strategic-acquisitions-in-kentucky-and-maryland"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-06","publisher":"TeraWulf","title":"TeraWulf Announces Anthropic Lease at Justified Data Campus and Sale of Majority Interest in Abernathy Joint Venture to Fluidstack","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/142/terawulf-announces-anthropic-lease-at-justified-data-campus-and-sale-of-majority-interest-in-abernathy-joint-venture-to-fluidstack"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-05","publisher":"TeraWulf","title":"TeraWulf Reports Second Quarter 2026 Results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004051014/https://investors.terawulf.com/news-events/press-releases/detail/145/kentucky-psc-approves-482-mw-power-agreement-for-terawulfs-justified-data-campus","id":"s4","published":"2026-08-24","publisher":"TeraWulf","title":"Kentucky PSC Approves 482 MW Power Agreement for TeraWulf's Justified Data Campus","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/145/kentucky-psc-approves-482-mw-power-agreement-for-terawulfs-justified-data-campus"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Hawesville, Kentucky","type":"other","url":"https://en.wikipedia.org/wiki/Hawesville,_Kentucky"}],"status":"announced","status_as_of":"2026-08-24","status_source_ids":["s4","s2"],"summary":"TeraWulf is redeveloping the former Century Aluminum facility at Hawesville, Kentucky, acquired in early 2026, into an AI data center campus with more than 250 buildable acres, an energized on-site substation and about 480 MW of available power. In July 2026 Anthropic signed a 20-year lease for about 401 MW of critical IT load, expected to bring about $19 billion of rent over the initial term. Kentucky regulators approved a retail electric service agreement of up to 482 MW in August 2026. TeraWulf targets initial capacity in the second half of 2027 and the full 401 MW by early 2028.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"30a8faac-6bf4-5f82-80b3-159eed56720e","s2":"7765458b-3843-5a7a-b6c0-6188e7ae143f","s3":"83a7245e-347c-5b30-a1ed-04dfa6146efb","s4":"01b458cf-d4e4-5032-bd65-3afdc46856b8","s5":"c55d4b60-b32e-5e6a-af0d-2caee573d40e"},"source_file":"datacenters/projects/terawulf-justified-data-hawesville.json","source_record_id":"terawulf-justified-data-hawesville","source_record_sha256":"7db40d44894208f4e792a562ea9403ac682100e2515b0c7715e1d07e0ca4a4e7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"27278e58daf1a0c3569e9dbb95f6fd7bc301c50777ef215c520c7574637006a7"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dbe568d910290db51ead/#project-9dbfd718-7b41-58b1-bb46-0138b96aeca8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9dbfd718-7b41-58b1-bb46-0138b96aeca8.json
9ddf0df3-e40c-515f-9468-ed78f063513b | curated:ntt-dallas-data-center-campus:tx4 | vcc-site-86c96db92481ee74998d | curated:ntt-dallas-data-center-campus | NTT Dallas TX4 Data Center | United States | US | 32.9825 | -96.6544 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The current NTT page supplies 2060 Lookout Drive and controls the locator; the Texas TDLR record supplies conflicting 2008 Lookout Drive. Both remain disclosed, and neither point is a TX4 footprint or parcel. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 6600dddb-f2d8-5458-8e71-b43f77cc5e01 | under_construction | 2026-05-31 | 135 | authoritative_physical_status_update | 077a6629-8396-549b-92c0-cdec324067f3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.12 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/posts/ntt-global-data-centers_time-lapse-video-tx4-garland-tx-activity-7473147125938147328-uZsM | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-86c96db92481ee74998d/#project-9ddf0df3-e40c-515f-9468-ed78f063513b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9ddf0df3-e40c-515f-9468-ed78f063513b.json
9ed96427-8138-552b-9f88-3b1fbeaa341b | imported:semiconductor-atlas:bitdeer-shalersville-portage-county | vcc-site-43a4fd4202a0c1c9518f | imported:semiconductor-atlas:bitdeer-shalersville-portage-county | Bitdeer and Geis Shalersville AI data center campus | United States | US | 41.2456 | -81.2603 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the site at the Turnpike Commerce Center just north of the Ohio Turnpike in Shalersville Township, without coordinates. The point is the township coordinate from its Wikipedia article, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 54ab57f7-416c-52ec-8ca1-9b7762480ab9 | proposed | 2026-10-07 | 6 | imported_documented_status | 995d3afb-4a08-560a-85b4-bece8430c74c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"54ab57f7-416c-52ec-8ca1-9b7762480ab9","notes":"Reported in May 2026 to be under contract to buy about 257 acres for the campus.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"394f235e-1d3c-51f7-8c30-388921536a8d","notes":"Reported in May 2026 to be under contract to buy about 257 acres for the campus.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"a549f6ca-53f0-5ed4-ba69-561848dcd5dd","notes":"Reported in May 2026 to be under contract to buy about 257 acres for the campus.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"195bbfbf-9214-5087-ad56-e9c5c31c307c","notes":"Reported in May 2026 to be under contract to buy about 257 acres for the campus.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"995d3afb-4a08-560a-85b4-bece8430c74c","notes":"Reported in May 2026 to be under contract to buy about 257 acres for the campus.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"54ab57f7-416c-52ec-8ca1-9b7762480ab9","notes":"Streetsboro-based business park developer partnering with Bitdeer.","party":"Geis Development","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"394f235e-1d3c-51f7-8c30-388921536a8d","notes":"Streetsboro-based business park developer partnering with Bitdeer.","party":"Geis Development","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"a549f6ca-53f0-5ed4-ba69-561848dcd5dd","notes":"Streetsboro-based business park developer partnering with Bitdeer.","party":"Geis Development","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"995d3afb-4a08-560a-85b4-bece8430c74c","notes":"Streetsboro-based business park developer partnering with Bitdeer.","party":"Geis Development","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"195bbfbf-9214-5087-ad56-e9c5c31c307c","notes":"Geis affiliate described as owning the land in August 2026; the October 2026 report also calls it Geis-owned land.","party":"Shalersville Holdings (Geis Companies)","relationship_scope":"unknown","role":"owner","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"995d3afb-4a08-560a-85b4-bece8430c74c","notes":"Geis affiliate described as owning the land in August 2026; the October 2026 report also calls it Geis-owned land.","party":"Shalersville Holdings (Geis Companies)","relationship_scope":"unknown","role":"owner","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"54ab57f7-416c-52ec-8ca1-9b7762480ab9","notes":"Has a data center moratorium in place and in October 2026 redefined its industrial zoning categories.","party":"Shalersville Township","relationship_scope":"unknown","role":"government","source_record_id":"bitdeer-shalersville-portage-county"},{"evidence_id":"995d3afb-4a08-560a-85b4-bece8430c74c","notes":"Has a data center moratorium in place and in October 2026 redefined its industrial zoning categories.","party":"Shalersville Township","relationship_scope":"unknown","role":"government","source_record_id":"bitdeer-shalersville-portage-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Shalersville Holdings (Geis Companies) |  |  |  |  | https://theportager.com/shalersville-redefines-industrial-zoning-adding-obstacles-to-data-center-proposal | https://www.news5cleveland.com/news/local-news/local-developer-global-tech-firm-plan-major-data-center-project-in-portage-county | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bitdeer and Geis Shalersville AI data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"bitdeer-shalersville-portage-county"},"record":{"aliases":["Turnpike Commerce Center data center","Bitdeer Shalersville"],"id":"bitdeer-shalersville-portage-county","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Portage County","country":"US","lat":41.2456,"locality":"Shalersville Township","lon":-81.2603,"note":"Sources place the site at the Turnpike Commerce Center just north of the Ohio Turnpike in Shalersville Township, without coordinates. The point is the township coordinate from its Wikipedia article, not the site.","precision":"locality","source_ids":["s1","s2","s4","s5","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-07","basis":"planned","metric":"power_capacity","note":"Potential capacity if the full campus is built; the sources do not say whether this is IT or facility load.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s3","s5"],"unit":"MW","value":750},{"applies_to":"phase","as_of":"2026-05","basis":"planned","metric":"power_capacity","phase_label":"Initial capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2026-05","basis":"reported","metric":"investment","note":"Construction cost excluding the company's computing equipment.","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":300000000},{"applies_to":"campus","as_of":"2026-08-14","basis":"reported","metric":"land_area","note":"The October 2026 Portager report instead describes the campus as sitting on just over 150 acres of Geis-owned land.","qualifier":"approximately","source_ids":["s1","s3","s4"],"unit":"acres","value":257},{"applies_to":"campus","as_of":"2026-08-14","basis":"planned","metric":"buildings","note":"Phase 1 is two data halls plus a 51,500 sq ft office building; phase 2 adds 12 data halls.","qualifier":"exact","source_ids":["s1","s3","s4"],"unit":"count","value":15},{"applies_to":"phase","as_of":"2026-05","basis":"planned","metric":"floor_area","phase_label":"Each phase 1 data hall","qualifier":"approximately","source_ids":["s1","s3"],"unit":"sq_ft","value":48000},{"applies_to":"campus","as_of":"2026-06-17","basis":"planned","metric":"jobs_construction","note":"Local construction jobs over five years, as presented at the June 2026 public meeting.","qualifier":"approximately","source_ids":["s3"],"unit":"count","value":400},{"applies_to":"campus","as_of":"2026-06-17","basis":"planned","metric":"jobs_permanent","note":"At full build-out; phase 1 alone was put at 30 to 50 long-term jobs.","qualifier":"range","source_ids":["s1","s3"],"unit":"count","value":150,"value_high":200}],"milestones":[{"date":"2026-05","event":"announced","kind":"actual","note":"Plans became public in late May 2026, ahead of a township residents' open house that the article links to 29 May.","source_ids":["s1"]},{"date":"2026-06-16","event":"other","kind":"actual","note":"Public meeting at Shalersville Town Hall drew about 200 people inside and dozens more outside.","source_ids":["s3"]},{"date":"2026-10-06","event":"other","kind":"actual","note":"Trustees amended zoning definitions so that uses of 25 MW or more belong on heavy industrial land, which the township lacks; Geis's lawyer called the change unlawful and said the firm would sue unless it was tabled or rejected. The moratorium runs to the first week of November, and trustees said they would extend it if needed.","source_ids":["s5"]}],"name":"Bitdeer and Geis Shalersville AI data center campus","notes":"The News 5 Cleveland article (s1) shows no publication date; its images are dated 27 May 2026 and it links to a 29 May 2026 open house, so its figures are dated 2026-05. The Portager's June report (s2) relays the land-contract detail from News 5. Bitdeer says it is not seeking tax abatements and put phase 1 property tax revenue at about USD 2.17 million a year. The first buildings would use closed-loop liquid cooling with about 350 gallons of water a day and no wells. The August 2026 Portager article is partly paywalled; only its opening could be read. Further planning commission, zoning commission and trustee meetings were scheduled for 14 to 20 October 2026.","parties":[{"name":"Bitdeer Technologies Group","note":"Reported in May 2026 to be under contract to buy about 257 acres for the campus.","role":"developer","source_ids":["s1","s2","s3","s4","s5"]},{"name":"Geis Development","note":"Streetsboro-based business park developer partnering with Bitdeer.","role":"developer","source_ids":["s1","s2","s3","s5"]},{"name":"Shalersville Holdings (Geis Companies)","note":"Geis affiliate described as owning the land in August 2026; the October 2026 report also calls it Geis-owned land.","role":"owner","source_ids":["s4","s5"]},{"name":"Shalersville Township","note":"Has a data center moratorium in place and in October 2026 redefined its industrial zoning categories.","role":"government","source_ids":["s1","s5"]}],"power_sources":[{"description":"Bitdeer said it would pay for the electricity it needs and for any transmission and distribution upgrades; the utility is not named.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260819033708/https://www.news5cleveland.com/news/local-news/local-developer-global-tech-firm-plan-major-data-center-project-in-portage-county","id":"s1","published":null,"publisher":"News 5 Cleveland (WEWS)","title":"Local developer, global tech firm plan major data center project in Portage County","type":"news","url":"https://www.news5cleveland.com/news/local-news/local-developer-global-tech-firm-plan-major-data-center-project-in-portage-county"},{"accessed":"2026-10-09","id":"s2","published":"2026-06-05","publisher":"The Portager","title":"Asian crypto mining company and Geis partner to bring data center to Shalersville","type":"news","url":"https://theportager.com/asian-crypto-mining-company-and-geis-partner-to-bring-data-center-to-shalersville"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260927132914/https://theenergymag.com/news/2026-06-17/bitdeer-ohio-ai-pushback","id":"s3","published":"2026-06-17","publisher":"TheEnergyMag","title":"Bitdeer's 750MW Ohio AI Data Center Plan Draws Local Scrutiny","type":"trade_press","url":"https://theenergymag.com/news/2026-06-17/bitdeer-ohio-ai-pushback"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-14","publisher":"The Portager","title":"Shalersville weighs zoning changes to block data center","type":"news","url":"https://theportager.com/shalersville-holds-off-on-zoning-changes-to-allow-a-data-center"},{"accessed":"2026-10-09","id":"s5","published":"2026-10-07","publisher":"The Portager","title":"Shalersville redefines industrial zoning, adding obstacles to data center proposal","type":"news","url":"https://theportager.com/shalersville-redefines-industrial-zoning-adding-obstacles-to-data-center-proposal"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Shalersville Township, Portage County, Ohio","type":"other","url":"https://en.wikipedia.org/wiki/Shalersville_Township,_Portage_County,_Ohio"}],"status":"proposed","status_as_of":"2026-10-07","status_source_ids":["s5"],"summary":"Proposed 15-building AI data center campus by Bitdeer Technologies Group and Geis Development at the Turnpike Commerce Center, just north of the Ohio Turnpike in Shalersville Township, Portage County, Ohio. Plans made public in May 2026 start with two data halls of about 48,000 sq ft each plus an office building and 150 MW of initial power capacity, with a potential 750 MW at full build-out over about five years; construction was put at more than USD 300 million, excluding computing equipment. A township moratorium is in place, and on 6 October 2026 trustees required uses of 25 MW or more to sit on heavy industrial land, which the township lacks; Geis's lawyers threatened to sue.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"54ab57f7-416c-52ec-8ca1-9b7762480ab9","s2":"394f235e-1d3c-51f7-8c30-388921536a8d","s3":"a549f6ca-53f0-5ed4-ba69-561848dcd5dd","s4":"195bbfbf-9214-5087-ad56-e9c5c31c307c","s5":"995d3afb-4a08-560a-85b4-bece8430c74c","s6":"59512401-af15-503c-86a8-263547d75e81"},"source_file":"datacenters/projects/bitdeer-shalersville-portage-county.json","source_record_id":"bitdeer-shalersville-portage-county","source_record_sha256":"3bf4ed692033cd5d7788a796df21f16156be296573a4b008414791a303564b37","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"c79a8d515bddd387e67e885356fb497b4310ca7ff7253ea3108e5ff7afa1ac00"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-43a4fd4202a0c1c9518f/#project-9ed96427-8138-552b-9f88-3b1fbeaa341b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9ed96427-8138-552b-9f88-3b1fbeaa341b.json
9fe862f6-ace2-5f5d-9c90-486fa4622982 | curated:nxtra-eko-atlantic-lagos-data-center:current-facility-build | vcc-site-f5c004356599de3efed9 | curated:nxtra-eko-atlantic-lagos-data-center | Nxtra Eko Atlantic Lagos Current Facility Build | Nigeria | NG | 6.4175 | 3.4214 | Point | campus | copy_literal_operator_LOS1_latitude_longitude_to_GeoJSON_longitude_latitude | copy_literal_operator_LOS1_latitude_longitude_to_GeoJSON_longitude_latitude | operator_published_campus_reference_point | official_source | campus_locator | Operator-authored point tied to the named Lagos Eko Atlantic LOS1 campus. It is not a campus boundary, footprint, entrance or surveyed work-area center. Source digits are preserved. |  | The operator provides no positional accuracy or survey metadata. Numeric precision does not establish accuracy. | a7227b84-a250-530e-bee8-51edf1231237 | under_construction | 2026-07-23 | 82 | authoritative_physical_status_update | c51133f6-ec11-5fe2-9d6e-949a94150bf8 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://cdn-webportal.airtelstream.net/website/investor/main/pdf/Q1-2027/Airtel_Africa_Q12027_results_transcript.pdf | https://www.nxtraafrica.com/sites/default/files/images/image-gallery/data-center-africa1.html?locations=nigeria | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f5c004356599de3efed9/#project-9fe862f6-ace2-5f5d-9c90-486fa4622982 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/9fe862f6-ace2-5f5d-9c90-486fa4622982.json
a072994f-1b7d-5cc8-98b7-bc79c666c6c3 | curated:pure-dc-ams01-amsterdam-westpoort-campus:data-hall-development | vcc-site-e4874e06dbb0a951c91d | curated:pure-dc-ams01-amsterdam-westpoort-campus | Pure DC AMS01 Data Hall Development | Netherlands | NL | 52.3953 | 4.8346 | Point | campus | official_bag_address_record_to_point | pdok_bag_tower_1_address_point_as_broad_campus_locator | official_constituent_address_point_as_campus_locator | official_source | campus_locator | Plimsollweg 3 is the official BAG address used for one AMS01 constituent permit. It is only a broad campus locator, not a project point, entrance, parcel, complete campus, building footprint, or current-work extent. |  | BAG/PDOK publishes no bounded numeric horizontal accuracy applicable to this selected address point. | 2f4528c3-705c-5b59-95c2-1b4a37661ccf | under_construction | 2026-05-27 | 139 | authoritative_physical_status_update | d1fe732e-4201-53e9-a9b8-cf57e9150699 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.16 country-diversity batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://puredc.com/2026/05/27/pure-dc-secures-2-7-billion-to-accelerate-ai-infrastructure-growth-across-europe-and-the-middle-east | https://api.pdok.nl/bzk/locatieserver/search/v3_1/lookup?id=adr-26c03da8f403dfbe0de863d7b9cff485&fl=%2A | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e4874e06dbb0a951c91d/#project-a072994f-1b7d-5cc8-98b7-bc79c666c6c3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a072994f-1b7d-5cc8-98b7-bc79c666c6c3.json
a0ee0f70-6708-5a9c-8b50-a61e93a5e501 | imported:semiconductor-atlas:k2-zibido-san-giacomo-lacchiarella | vcc-site-4cde3223014097681c99 | imported:semiconductor-atlas:k2-zibido-san-giacomo-lacchiarella | K2 hyperscale data center campus, Zibido San Giacomo and Lacchiarella | Italy | IT | 45.317 | 9.133 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Lacchiarella municipal centroid from its Wikipedia article. The campus spans Zibido San Giacomo and Lacchiarella; no cited source gives site coordinates, so the point only marks one of the two municipalities. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 678ee678-24bb-5cee-bce9-0f8e0bd74c28 | announced | 2026-08-18 | 56 | imported_documented_status | 678ee678-24bb-5cee-bce9-0f8e0bd74c28 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"678ee678-24bb-5cee-bce9-0f8e0bd74c28","notes":"Held by K2 Strategic Pte. Ltd., per MondoMobileWeb.","party":"K2 Strategic Infrastructure Italy","relationship_scope":"unknown","role":"developer","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},{"evidence_id":"64e47a79-1a83-5f01-b165-3b37123f2765","notes":"Held by K2 Strategic Pte. Ltd., per MondoMobileWeb.","party":"K2 Strategic Infrastructure Italy","relationship_scope":"unknown","role":"developer","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},{"evidence_id":"72f80b5e-70b8-5a1a-9618-b6167664d200","notes":"Held by K2 Strategic Pte. Ltd., per MondoMobileWeb.","party":"K2 Strategic Infrastructure Italy","relationship_scope":"unknown","role":"developer","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},{"evidence_id":"678ee678-24bb-5cee-bce9-0f8e0bd74c28","notes":"Declared the programme of preeminent national strategic interest on a proposal from the Ministry of Enterprises and Made in Italy.","party":"Italian Council of Ministers","relationship_scope":"unknown","role":"government","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},{"evidence_id":"64e47a79-1a83-5f01-b165-3b37123f2765","notes":"Declared the programme of preeminent national strategic interest on a proposal from the Ministry of Enterprises and Made in Italy.","party":"Italian Council of Ministers","relationship_scope":"unknown","role":"government","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},{"evidence_id":"72f80b5e-70b8-5a1a-9618-b6167664d200","notes":"Declared the programme of preeminent national strategic interest on a proposal from the Ministry of Enterprises and Made in Italy.","party":"Italian Council of Ministers","relationship_scope":"unknown","role":"government","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},{"evidence_id":"678ee678-24bb-5cee-bce9-0f8e0bd74c28","notes":"Consulted on compliance with its new data center law; the commissioner is to be appointed in agreement with the region.","party":"Lombardy Region","relationship_scope":"unknown","role":"government","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},{"evidence_id":"64e47a79-1a83-5f01-b165-3b37123f2765","notes":"Consulted on compliance with its new data center law; the commissioner is to be appointed in agreement with the region.","party":"Lombardy Region","relationship_scope":"unknown","role":"government","source_record_id":"k2-zibido-san-giacomo-lacchiarella"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.ilgiorno.it/milano/economia/data-center-lacchiarella-zibido-cz1ai1qn | https://www.ilgiorno.it/milano/economia/data-center-lacchiarella-zibido-cz1ai1qn | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve K2 hyperscale data center campus, Zibido San Giacomo and Lacchiarella as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"k2-zibido-san-giacomo-lacchiarella"},"record":{"aliases":["K2 Strategic Infrastructure Italy campus"],"id":"k2-zibido-san-giacomo-lacchiarella","last_reviewed":"2026-10-09","location":{"admin1":"Lombardy","admin2":"Metropolitan City of Milan","country":"IT","lat":45.317,"locality":"Lacchiarella","lon":9.133,"note":"Lacchiarella municipal centroid from its Wikipedia article. The campus spans Zibido San Giacomo and Lacchiarella; no cited source gives site coordinates, so the point only marks one of the two municipalities.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-05","basis":"planned","metric":"power_capacity","note":"Figure communicated by the Ministry of Enterprises and Made in Italy (MIMIT), as reported by the press; described as total capacity of up to about 400 MW, scope not stated.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"MW","value":400},{"applies_to":"campus","as_of":"2026-08-05","basis":"announced","metric":"investment","note":"Figure communicated by the Ministry of Enterprises and Made in Italy (MIMIT), as reported by the press; Il Sole 24 Ore does not attribute it.","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"EUR","value":5300000000},{"applies_to":"campus","as_of":"2026-08-05","basis":"planned","metric":"jobs_construction","note":"Figure communicated by the Ministry of Enterprises and Made in Italy (MIMIT), as reported by the press: average workers per year over the four-year development and construction period.","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"count","value":2000},{"applies_to":"campus","as_of":"2026-08-05","basis":"planned","metric":"jobs_permanent","note":"Figure communicated by the Ministry of Enterprises and Made in Italy (MIMIT), as reported by the press: direct jobs once operating, plus about 1,300 permanent jobs in related businesses.","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"count","value":200}],"milestones":[{"date":"2026-08-04","event":"other","kind":"actual","note":"Council of Ministers declared the programme of preeminent national strategic interest, with a government commissioner to coordinate the single authorisation.","source_ids":["s2","s3"]}],"name":"K2 hyperscale data center campus, Zibido San Giacomo and Lacchiarella","notes":"The official government or ministry communiqué was not opened; capacity, investment and job figures come from press coverage attributing them to the ministry. No site area, tenant or construction start has been published. Il Giorno reports objections from residents and groups linked to the Parco Agricolo Sud Milano to the new data center projects in the area, over farmland loss, water use, grid strain, local heating and noise.","parties":[{"name":"K2 Strategic Infrastructure Italy","note":"Held by K2 Strategic Pte. Ltd., per MondoMobileWeb.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Italian Council of Ministers","note":"Declared the programme of preeminent national strategic interest on a proposal from the Ministry of Enterprises and Made in Italy.","role":"government","source_ids":["s1","s2","s3"]},{"name":"Lombardy Region","note":"Consulted on compliance with its new data center law; the commissioner is to be appointed in agreement with the region.","role":"government","source_ids":["s1","s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260810220341/https://www.ilgiorno.it/milano/economia/data-center-lacchiarella-zibido-cz1ai1qn","id":"s1","published":"2026-08-05","publisher":"Il Giorno","title":"Data Center, avanti tutta: interesse nazionale anche per Lacchiarella-Zibido. La mappa in Lombardia","type":"news","url":"https://www.ilgiorno.it/milano/economia/data-center-lacchiarella-zibido-cz1ai1qn"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-18","publisher":"MondoMobileWeb","title":"Data center, in Italia 7 investimenti strategici per oltre 25 miliardi di euro","type":"trade_press","url":"https://www.mondomobileweb.it/?p=325209"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-10","publisher":"Il Sole 24 Ore","title":"Data centres: EU gives the green light to the Eni-Khazna joint venture. Lombardy hub set to accelerate","type":"news","url":"https://en.ilsole24ore.com/art/data-centre-eu-gives-green-light-to-eni-khazna-joint-venture-lombardy-hub-to-be-accelerated-AJl2Zcj"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260101045140/https://en.wikipedia.org/wiki/Lacchiarella","id":"s4","published":null,"publisher":"Wikipedia","title":"Lacchiarella","type":"other","url":"https://en.wikipedia.org/wiki/Lacchiarella"}],"status":"announced","status_as_of":"2026-08-18","status_source_ids":["s1","s2"],"summary":"Hyperscale data center campus proposed by K2 Strategic Infrastructure Italy, a company held by K2 Strategic Pte. Ltd., across the municipalities of Zibido San Giacomo and Lacchiarella in the Metropolitan City of Milan. On 4 August 2026 Italy's Council of Ministers declared it a programme of preeminent national strategic interest. Press reports attribute to the Ministry of Enterprises and Made in Italy figures of up to about 400 MW and an estimated EUR 5.3 billion of investment over four years of development and construction. A government commissioner is to coordinate permits. Local groups have raised concerns about new data centers in the area over farmland, water, grid strain and noise.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"678ee678-24bb-5cee-bce9-0f8e0bd74c28","s2":"64e47a79-1a83-5f01-b165-3b37123f2765","s3":"72f80b5e-70b8-5a1a-9618-b6167664d200","s4":"d81f3e7c-33e0-5e5f-bd08-e5d8797c4d11"},"source_file":"datacenters/projects/k2-zibido-san-giacomo-lacchiarella.json","source_record_id":"k2-zibido-san-giacomo-lacchiarella","source_record_sha256":"e6c18fdd8c93267b9f8677c73883923f913dc248cc7222c37d82145c91ec195b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"65e323793e800cbf2f4bf4e14ca9a4a3119900b41a4eb935c6246f4598f0125d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4cde3223014097681c99/#project-a0ee0f70-6708-5a9c-8b50-a61e93a5e501 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a0ee0f70-6708-5a9c-8b50-a61e93a5e501.json
a1390e66-5b95-568b-869b-b9413c56f8ce | curated:noris-network-nbg6-nuremberg-south-campus:ba3-modular-expansion | vcc-site-2d8fde06f5151b5ae93b | curated:noris-network-nbg6-nuremberg-south-campus | noris network NBG6 BA3 Modular Expansion | Germany | DE | 49.41 | 11.1315 | Point | campus | provider_supplied_community_named_BA3_building_centroid_bound_to_operator_project_code_and_campus | preserve_Nominatim_lat_lon_for_OSM_way_1445218606_match_literal_NBG6_BA3_name_to_operator_code_and_campus_then_corroborate_modular_400_square_metre_units | community_constituent_building_reference_point | community_source | campus_locator | Exact returned representative point of a community feature named NBG6 BA3. The operator explicitly binds that code to Nürnberg Süd; separate modular-unit identity connects the August work report. Only a locator for the one campus is proposed, not an official parcel, campus boundary, surveyed entrance, active-work extent, quantitative accuracy claim, or independently verified imagery. Adjacent BA1/BA2 share the campus; the office map point is excluded. |  | Neither selected community response supplies quantified positional accuracy; seven decimal digits do not establish accuracy. | 9e7bcd9e-1b16-55c5-86ac-b3b91b931a00 | under_construction | 2026-08-13 | 61 | authoritative_physical_status_update | 8a58de29-c30d-5e2c-9827-44cad3dd0a70 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/feed/update/urn:li:activity:7493585204314554368/ | https://nominatim.openstreetmap.org/search?q=noris%20network%20N%C3%BCrnberg&format=jsonv2&addressdetails=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2d8fde06f5151b5ae93b/#project-a1390e66-5b95-568b-869b-b9413c56f8ce | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a1390e66-5b95-568b-869b-b9413c56f8ce.json
a1696719-0fe3-52ce-ad37-43e6d2215f4f | imported:semiconductor-atlas:compass-hoffman-estates | vcc-site-b2e02b9541ac2f2a5b20 | imported:semiconductor-atlas:compass-hoffman-estates | Compass Datacenters Hoffman Estates campus | United States | US | 42.0639 | -88.1469 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Hoffman Estates. The campus occupies the former Sears headquarters site in the village; no cited source gives site coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 2099b779-9d76-5a88-a84f-0c239664a1e0 | under_construction | 2026-10-06 | 7 | imported_documented_status | ce79a4bd-0948-573a-8e71-da87943a9cf7 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2099b779-9d76-5a88-a84f-0c239664a1e0","notes":null,"party":"Compass Datacenters","relationship_scope":"unknown","role":"developer","source_record_id":"compass-hoffman-estates"},{"evidence_id":"b0caefab-938f-56be-9a4e-7877fb2c64aa","notes":null,"party":"Compass Datacenters","relationship_scope":"unknown","role":"developer","source_record_id":"compass-hoffman-estates"},{"evidence_id":"ce79a4bd-0948-573a-8e71-da87943a9cf7","notes":null,"party":"Compass Datacenters","relationship_scope":"unknown","role":"developer","source_record_id":"compass-hoffman-estates"},{"evidence_id":"2099b779-9d76-5a88-a84f-0c239664a1e0","notes":"Named as a partner at the 2024 kickoff; the release does not describe its role further.","party":"ComEd","relationship_scope":"unknown","role":"utility","source_record_id":"compass-hoffman-estates"},{"evidence_id":"2099b779-9d76-5a88-a84f-0c239664a1e0","notes":"Host municipality, named as a partner at the 2024 kickoff.","party":"Village of Hoffman Estates","relationship_scope":"unknown","role":"government","source_record_id":"compass-hoffman-estates"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.compassdatacenters.com/news/village-of-hoffman-estates/ | https://www.compassdatacenters.com/news/compass-kicks-off-development-of-its-first-hyperscale-campus-in-illinois/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Compass Datacenters Hoffman Estates campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"compass-hoffman-estates"},"record":{"aliases":["Compass Chicago campus","Former Sears headquarters data center campus"],"id":"compass-hoffman-estates","last_reviewed":"2026-10-09","location":{"admin1":"Illinois","admin2":"Cook County","country":"US","lat":42.0639,"locality":"Hoffman Estates","lon":-88.1469,"note":"Wikipedia coordinates for Hoffman Estates. The campus occupies the former Sears headquarters site in the village; no cited source gives site coordinates.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Figure on Compass's undated markets page as viewed on the access date.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2024-06-13","basis":"announced","metric":"investment","note":"Local investment once the campus is operational; the village mayor said the investment was still preliminary.","qualifier":"approximately","source_ids":["s1"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2024-06-13","basis":"acquired","metric":"land_area","note":"Described as nearly 200 acres.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":200},{"applies_to":"campus","as_of":"2024-06-13","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1"],"unit":"count","value":5},{"applies_to":"campus","as_of":"2024-06-13","basis":"planned","metric":"jobs_construction","note":"Local construction jobs cited at the 2024 kickoff.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":1000}],"milestones":[{"date":"2023-09","event":"site_acquired","kind":"actual","source_ids":["s1"]},{"date":"2024-06-13","event":"construction_started","kind":"actual","note":"Kickoff ceremony celebrating the start of work to redevelop the site; structural demolition of the Sears buildings was to begin that summer and take more than a year.","source_ids":["s1"]},{"date":"2025","event":"other","kind":"planned","note":"Start of data center construction after demolition, as planned in June 2024; no cited source confirms that it began.","source_ids":["s1"]}],"name":"Compass Datacenters Hoffman Estates campus","notes":"Status rests on the start of site work (demolition) announced at the June 2024 kickoff and on Compass's October 2026 statement that it is developing the campus; no cited source confirms that vertical data center construction has begun.","parties":[{"name":"Compass Datacenters","role":"developer","source_ids":["s1","s2","s3"]},{"name":"ComEd","note":"Named as a partner at the 2024 kickoff; the release does not describe its role further.","role":"utility","source_ids":["s1"]},{"name":"Village of Hoffman Estates","note":"Host municipality, named as a partner at the 2024 kickoff.","role":"government","source_ids":["s1"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260510090040/https://www.compassdatacenters.com/news/compass-kicks-off-development-of-its-first-hyperscale-campus-in-illinois/","id":"s1","published":"2024-06-13","publisher":"Compass Datacenters","title":"Compass Kicks Off Development Of Its First Hyperscale Data Center Campus in Illinois","type":"company","url":"https://www.compassdatacenters.com/news/compass-kicks-off-development-of-its-first-hyperscale-campus-in-illinois/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Compass Datacenters","title":"Data Center Markets - Compass Datacenters","type":"company","url":"https://www.compassdatacenters.com/data-center-markets/"},{"accessed":"2026-10-09","id":"s3","published":"2026-10-06","publisher":"Compass Datacenters","title":"Compass Datacenters Funds New Community Wellness Space at Hoffman Estates Health and Human Services","type":"company","url":"https://www.compassdatacenters.com/news/village-of-hoffman-estates/"}],"status":"under_construction","status_as_of":"2026-10-06","status_source_ids":["s3","s1"],"summary":"Compass Datacenters is redeveloping the former Sears headquarters site, nearly 200 acres in Hoffman Estates about 30 miles west of Chicago, into a hyperscale campus of five data centers. Compass closed on the site in September 2023 and held a kickoff in June 2024, saying demolition of the old Sears buildings would start that summer and data center construction would follow in 2025. Compass put local investment at about USD 10 billion once operational, a figure the village mayor called preliminary, and its markets page lists the campus at 200 MW. In October 2026 Compass still described the campus as being developed."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"2099b779-9d76-5a88-a84f-0c239664a1e0","s2":"b0caefab-938f-56be-9a4e-7877fb2c64aa","s3":"ce79a4bd-0948-573a-8e71-da87943a9cf7"},"source_file":"datacenters/projects/compass-hoffman-estates.json","source_record_id":"compass-hoffman-estates","source_record_sha256":"919e4cab350dccba044b29137ae2d07da2c687d60d24fff80a509beb085c84d2","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1d62a6f63aaab6fadf204a5ca1b338fd573dc7a9b53aabcfda4c99edea4b850d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b2e02b9541ac2f2a5b20/#project-a1696719-0fe3-52ce-ad37-43e6d2215f4f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a1696719-0fe3-52ce-ad37-43e6d2215f4f.json
a203f1e3-768b-5094-b606-9c494490e0a6 | imported:semiconductor-atlas:meta-gallatin-tennessee | vcc-site-beb10377588af430b5a6 | imported:semiconductor-atlas:meta-gallatin-tennessee | Meta Gallatin Data Center | United States | US | 36.4085 | -86.3716 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Centroid of the area named Gallatin Data Center and tagged as Meta-operated in the local OpenStreetMap layer (way 1213758201); Meta-tagged data center buildings lie within about 500 m of it. Sources name only the city and county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | dfa60568-7e3e-5a91-b7e4-a8639c511983 | partially_operational | 2024-11-15 | 697 | imported_documented_status | 696d725a-6761-5023-9d87-ba433e1c9839 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"dfa60568-7e3e-5a91-b7e4-a8639c511983","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-gallatin-tennessee"},{"evidence_id":"549f8de1-c51b-5204-b9c8-bf42a67dbf2d","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-gallatin-tennessee"},{"evidence_id":"696d725a-6761-5023-9d87-ba433e1c9839","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"meta-gallatin-tennessee"},{"evidence_id":"549f8de1-c51b-5204-b9c8-bf42a67dbf2d","notes":null,"party":"DPR Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-gallatin-tennessee"},{"evidence_id":"5850e427-e206-5684-967c-9b1bf4abf1b5","notes":null,"party":"DPR Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-gallatin-tennessee"},{"evidence_id":"dfa60568-7e3e-5a91-b7e4-a8639c511983","notes":null,"party":"Tennessee Valley Authority","relationship_scope":"unknown","role":"utility","source_record_id":"meta-gallatin-tennessee"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Meta Platforms |  |  |  | https://www.gallatingetsit.com/newsroom/metas-data-centers-in-gallatin-are-up-and-running | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Gallatin-Data-Center.pdf | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Meta Gallatin Data Center as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"meta-gallatin-tennessee"},"record":{"aliases":["Gallatin Data Center"],"id":"meta-gallatin-tennessee","last_reviewed":"2026-10-09","location":{"admin1":"Tennessee","admin2":"Sumner County","country":"US","lat":36.4085,"locality":"Gallatin","lon":-86.3716,"note":"Centroid of the area named Gallatin Data Center and tagged as Meta-operated in the local OpenStreetMap layer (way 1213758201); Meta-tagged data center buildings lie within about 500 m of it. Sources name only the city and county.","precision":"approximate_site","source_ids":["s1","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2020","basis":"announced","metric":"investment","note":"Initial commitment made when Meta was still Facebook.","qualifier":"exact","source_ids":["s4"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2022-09-23","basis":"reported","metric":"investment","note":"Described in September 2022 as a nearly USD 1 billion investment, with about USD 1 billion spent to date.","qualifier":"approximately","source_ids":["s2"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2024-11-15","basis":"announced","metric":"investment","note":"Meta said the total would exceed this once the fourth data center is complete.","qualifier":"more_than","source_ids":["s1","s4"],"unit":"USD","value":1500000000},{"applies_to":"campus","as_of":"2024-11-15","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s3","s4"],"unit":"acres","value":800},{"applies_to":"campus","as_of":"2024-04-15","basis":"planned","metric":"floor_area","note":"About 1.6 million sq ft operating or under construction plus the 278,000 sq ft building filed in 2024, including some office space.","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":1900000},{"applies_to":"campus","as_of":"2024-11-15","basis":"planned","metric":"buildings","note":"Data center buildings; the fourth was under construction in November 2024.","qualifier":"at_least","source_ids":["s4"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2022-09-23","basis":"reported","metric":"jobs_construction","note":"Peak skilled trade workforce reported in 2022, up from an earlier peak of 1,200.","qualifier":"exact","source_ids":["s2"],"unit":"count","value":1700},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"jobs_construction","note":"Skilled trade workers on site at peak construction, per Meta's undated fact sheet; differs from the 2022 report.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":1100},{"applies_to":"campus","as_of":"2024-11-15","basis":"reported","metric":"jobs_permanent","qualifier":"more_than","source_ids":["s1","s4"],"unit":"count","value":100}],"milestones":[{"date":"2020-08","event":"construction_started","kind":"actual","source_ids":["s1","s2"]},{"date":"2022-09","event":"expansion_announced","kind":"actual","note":"W.Media reported two new structures, one for cold storage of older data, with completion then expected in late 2023.","source_ids":["s2"]},{"date":"2024-04","event":"expansion_announced","kind":"actual","note":"Plans for a further 278,000 sq ft data center went to the Gallatin planning commission.","source_ids":["s3"]},{"date":"2024-11","event":"other","kind":"actual","note":"Meta formally presented the operating campus to state and local officials.","source_ids":["s4"]}],"name":"Meta Gallatin Data Center","notes":"In November 2024 the campus was described as operating while its fourth data center was still under construction; no later report on that building was found. Reported site size differs: about 800 acres (Nashville Business Journal, 2024) versus more than 900 acres (W.Media, 2022). Peak construction workforce also differs: 1,700 in W.Media's 2022 report versus 1,100 on Meta's fact sheet. Meta's fact sheet (s1) shows no publication date (embedded file creation date 2026-09-02), so figures that rest on it alone are dated to the access date, 2026-10-09. The Nashville Business Journal articles are cited from reposts on the Gallatin Economic Development Agency site.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Meta Platforms","role":"operator","source_ids":["s4"]},{"name":"DPR Construction","role":"builder","source_ids":["s2","s3"]},{"name":"Tennessee Valley Authority","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Meta says it planned the campus's energy needs with the Tennessee Valley Authority and pays the full cost of the energy used; an on-site electrical substation was finished by 2022.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Meta Platforms","title":"Meta Gallatin Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Gallatin-Data-Center.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2022-09-23","publisher":"W.Media","title":"Meta Expands Gallatin Data Center with $1B Investment","type":"trade_press","url":"https://w.media/meta-expands-gallatin-data-center-with-nearly-1b-total-investment/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260509224526/https://www.gallatingetsit.com/newsroom/meta-formerly-known-as-facebook-tees-up-another-data-center-in-gallatin","id":"s3","published":"2024-04-15","publisher":"Nashville Business Journal (via Gallatin Economic Development Agency)","title":"Meta, formerly known as Facebook, tees up another data center in Gallatin","type":"news","url":"https://www.gallatingetsit.com/newsroom/meta-formerly-known-as-facebook-tees-up-another-data-center-in-gallatin"},{"accessed":"2026-10-09","id":"s4","published":"2024-11-15","publisher":"Nashville Business Journal (via Gallatin Economic Development Agency)","title":"Meta's data centers in Gallatin are up and running","type":"news","url":"https://www.gallatingetsit.com/newsroom/metas-data-centers-in-gallatin-are-up-and-running"}],"status":"partially_operational","status_as_of":"2024-11-15","status_source_ids":["s4"],"summary":"Multi-building Meta campus on roughly 800 acres in Gallatin, Tennessee. Construction began in August 2020 on what was first a USD 800 million commitment; by September 2022 the project was described as a nearly USD 1 billion investment, and in 2024 Meta filed plans for a further 278,000 sq ft data center that would take the campus to almost 1.9 million sq ft. In November 2024 Meta formally presented the operating campus to officials and said total investment would exceed USD 1.5 billion once the fourth data center is finished. DPR Construction is building the campus, and Meta says it planned its energy needs with the Tennessee Valley Authority.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"dfa60568-7e3e-5a91-b7e4-a8639c511983","s2":"549f8de1-c51b-5204-b9c8-bf42a67dbf2d","s3":"5850e427-e206-5684-967c-9b1bf4abf1b5","s4":"696d725a-6761-5023-9d87-ba433e1c9839"},"source_file":"datacenters/projects/meta-gallatin-tennessee.json","source_record_id":"meta-gallatin-tennessee","source_record_sha256":"9c9888451e66faeabdfac7734cb798e2a21dbcbfe5d6305de9e87d48f9351e8d","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"6e125273de54ce3b1289c2a306cc0123f7b97628ada0ccfb1d3a290960d7d315"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-beb10377588af430b5a6/#project-a203f1e3-768b-5094-b606-9c494490e0a6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a203f1e3-768b-5094-b606-9c494490e0a6.json
a225d046-5d72-5a1f-bf4b-ba454f713a49 | curated:estructure-cal3-rocky-view-campus:initial-build | vcc-site-0660c8cc500011957a7b | curated:estructure-cal3-rocky-view-campus | eStruxture CAL-3 Initial Build | Canada | CA | 51.2108 | -113.9147 | Point | facility | coordinates_to_point | first_party_published_decimal_coordinate_to_point | first_party_facility_reference_point | official_source | project_locator | First-party CAL-3 datasheet coordinate bound to the named facility. It is a project locator, not a parcel, campus, building, entrance, survey point, centroid, or current-work boundary. |  | The datasheet supplies coordinate digits but no datum, collection method, reference-feature definition, or bounded numeric horizontal-accuracy value. | 89aab19e-2eb3-59f5-a3c3-71366d5cb026 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | 6b7abcb5-6acc-5e16-8801-672021c4f9a3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.15 global geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.estruxture.com/data-centers/calgary/cal-3 | https://www.estruxture.com/hubfs/eStruxture_Datasheet_CAL3%20EN%20V1%202024.pdf?hsLang=en | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0660c8cc500011957a7b/#project-a225d046-5d72-5a1f-bf4b-ba454f713a49 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a225d046-5d72-5a1f-bf4b-ba454f713a49.json
a2de1edb-c874-5d78-902a-e174a5ecd03e | imported:semiconductor-atlas:mihta-askiy-data-centre-peace-river | vcc-site-499a1602728034c6a587 | imported:semiconductor-atlas:mihta-askiy-data-centre-peace-river | Mihta Askiy Data Centre | Canada | CA | 56.3814 | -116.7479 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Point from the Government of Alberta major projects inventory, which notes its map location is not exact; rounded to four decimals. The federal notice places the project about 40 km northeast of Peace River. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 1b01daad-275d-5d85-8065-33576847e484 | proposed | 2026-10-09 | 4 | imported_documented_status | 35b4997b-e1c8-5437-8d10-b716e4012f8f | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e0583de9-8652-5fe2-b21e-215b45f015f2","notes":"Federal proponent; the Alberta inventory describes it as a wholly owned subsidiary of Sovereign Digital Infrastructure.","party":"Cree Ative Datacenter Corp GP","relationship_scope":"unknown","role":"developer","source_record_id":"mihta-askiy-data-centre-peace-river"},{"evidence_id":"9591980c-1978-5e44-bcad-3236ec6c8b74","notes":"Federal proponent; the Alberta inventory describes it as a wholly owned subsidiary of Sovereign Digital Infrastructure.","party":"Cree Ative Datacenter Corp GP","relationship_scope":"unknown","role":"developer","source_record_id":"mihta-askiy-data-centre-peace-river"},{"evidence_id":"1b01daad-275d-5d85-8065-33576847e484","notes":"Federal proponent; the Alberta inventory describes it as a wholly owned subsidiary of Sovereign Digital Infrastructure.","party":"Cree Ative Datacenter Corp GP","relationship_scope":"unknown","role":"developer","source_record_id":"mihta-askiy-data-centre-peace-river"},{"evidence_id":"1b01daad-275d-5d85-8065-33576847e484","notes":"Listed as developer in the Alberta major projects inventory.","party":"Mihta Askiy Datacenter LP","relationship_scope":"unknown","role":"developer","source_record_id":"mihta-askiy-data-centre-peace-river"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://iaac-aeic.gc.ca/050/evaluations/document/165286?culture=en-CA | https://majorprojects.alberta.ca/details/Mihta-Askiy-Data-Centre/12097 | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Mihta Askiy Data Centre as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"mihta-askiy-data-centre-peace-river"},"record":{"aliases":["Mihta Askiy Data Center Project"],"id":"mihta-askiy-data-centre-peace-river","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","admin2":"Northern Sunrise County","country":"CA","lat":56.3814,"locality":"Peace River (about 40 km northeast)","lon":-116.7479,"note":"Point from the Government of Alberta major projects inventory, which notes its map location is not exact; rounded to four decimals. The federal notice places the project about 40 km northeast of Peace River.","precision":"approximate_site","source_ids":["s4","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-02","basis":"planned","metric":"power_capacity","note":"Production capacity of the gas-fired facility that would support the data centre; no separate data centre IT load was published in the sources opened.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"MW","value":650}],"milestones":[{"date":"2025-12-11","event":"other","kind":"actual","note":"Initial project description and its summary posted on the Impact Assessment Agency of Canada registry (reference 90036).","source_ids":["s1"]},{"date":"2026-03-03","event":"other","kind":"actual","note":"Federal agency decided no further assessment under the Impact Assessment Act was required; notice posted March 4, 2026.","source_ids":["s3"]},{"date":"2027","event":"construction_started","kind":"planned","note":"Alberta inventory lists the schedule as commencing in 2027.","source_ids":["s4"]}],"name":"Mihta Askiy Data Centre","notes":"Status rests partly on the undated Government of Alberta major projects entry, which lists the stage as proposed, so status_as_of is the date it was read (2026-10-09). No data centre IT load or cost estimate was published in the sources opened.","parties":[{"name":"Cree Ative Datacenter Corp GP","note":"Federal proponent; the Alberta inventory describes it as a wholly owned subsidiary of Sovereign Digital Infrastructure.","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Mihta Askiy Datacenter LP","note":"Listed as developer in the Alberta major projects inventory.","role":"developer","source_ids":["s4"]}],"power_sources":[{"description":"Dedicated 650 MW gas plant built in two stages: simple-cycle turbines first, later converted to combined cycle; planned 30-year operating life.","source_ids":["s1","s2"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Impact Assessment Agency of Canada","title":"Mihta Askiy Data Center Project (reference 90036)","type":"government","url":"https://iaac-aeic.gc.ca/050/evaluations/proj/90036"},{"accessed":"2026-10-09","id":"s2","published":"2026-01-02","publisher":"Impact Assessment Agency of Canada","title":"Public notice: Mihta Askiy Data Center Project, comments invited on the summary of the initial project description","type":"government","url":"https://iaac-aeic.gc.ca/050/evaluations/document/164258"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-04","publisher":"Impact Assessment Agency of Canada","title":"Notice of early decision with reasons: Mihta Askiy Data Center Project","type":"government","url":"https://iaac-aeic.gc.ca/050/evaluations/document/165286?culture=en-CA"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Government of Alberta, Major Projects","title":"Mihta Askiy Data Centre","type":"government","url":"https://majorprojects.alberta.ca/details/Mihta-Askiy-Data-Centre/12097"}],"status":"proposed","status_as_of":"2026-10-09","status_source_ids":["s3","s4"],"summary":"Proposed gas-powered data centre about 40 km northeast of Peace River in Northern Sunrise County, Alberta. Alberta's project inventory says the plan involves acquiring a partially completed power plant and converting it into a natural-gas-powered data centre. The proponent, Cree Ative Datacenter Corp GP, filed a federal project description for a 650 MW gas plant to serve the data centre, starting with simple-cycle turbines and later converting to combined cycle. The federal agency decided in March 2026 that no further federal assessment was required; Alberta's inventory lists the project as proposed, with work commencing in 2027.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e0583de9-8652-5fe2-b21e-215b45f015f2","s2":"9591980c-1978-5e44-bcad-3236ec6c8b74","s3":"35b4997b-e1c8-5437-8d10-b716e4012f8f","s4":"1b01daad-275d-5d85-8065-33576847e484"},"source_file":"datacenters/projects/mihta-askiy-data-centre-peace-river.json","source_record_id":"mihta-askiy-data-centre-peace-river","source_record_sha256":"472b8f227e3fd0409f1e131ff9a41c0886bdf5f70ed37d3c1a38e42c34cb2913","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"dd0a7cfef6137c5abc692fe4c038fbc892ff099589f9d381518962a07637ddcf"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-499a1602728034c6a587/#project-a2de1edb-c874-5d78-902a-e174a5ecd03e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a2de1edb-c874-5d78-902a-e174a5ecd03e.json
a31a1552-7be0-58e9-8097-4083d11175dd | imported:semiconductor-atlas:vantage-kul2-cyberjaya | vcc-site-54113ebec20f61dd4a6e | imported:semiconductor-atlas:vantage-kul2-cyberjaya | Vantage Data Centers Cyberjaya II campus (KUL2) | Malaysia | MY | 2.9225 | 101.655 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Vantage places KUL2 next to its KUL1 campus in Cyberjaya without an address. The point is the Cyberjaya coordinate from its Wikipedia article (which also gives the district), so it marks the township rather than the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 89571c26-d4c1-5923-adbf-ee81b0b8b068 | under_construction | 2024-08-06 | 798 | imported_documented_status | c2f6b1cb-3bb4-58d9-b2f6-b09a18e1245e | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"89571c26-d4c1-5923-adbf-ee81b0b8b068","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-kul2-cyberjaya"},{"evidence_id":"c2f6b1cb-3bb4-58d9-b2f6-b09a18e1245e","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-kul2-cyberjaya"},{"evidence_id":"da552195-033d-5bc9-806d-2d3a98a1361b","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-kul2-cyberjaya"},{"evidence_id":"c2f6b1cb-3bb4-58d9-b2f6-b09a18e1245e","notes":"Electricity supply agreement for 500 MVA via a dedicated 275 kV substation.","party":"Tenaga Nasional Berhad (TNB)","relationship_scope":"unknown","role":"utility","source_record_id":"vantage-kul2-cyberjaya"},{"evidence_id":"da552195-033d-5bc9-806d-2d3a98a1361b","notes":"Electricity supply agreement for 500 MVA via a dedicated 275 kV substation.","party":"Tenaga Nasional Berhad (TNB)","relationship_scope":"unknown","role":"utility","source_record_id":"vantage-kul2-cyberjaya"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://vantage-dc.com/news/vantage-data-centers-breaks-ground-on-256mw-cyberjaya-campus/ | https://vietnamnews.vn/media-outreach/1536601/vantage-data-centers-announces-second-campus-in-cyberjaya.html | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Vantage Data Centers Cyberjaya II campus (KUL2) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"vantage-kul2-cyberjaya"},"record":{"aliases":["KUL2","Cyberjaya II Data Center Campus"],"id":"vantage-kul2-cyberjaya","last_reviewed":"2026-10-09","location":{"admin1":"Selangor","admin2":"Sepang District","country":"MY","lat":2.9225,"locality":"Cyberjaya","lon":101.655,"note":"Vantage places KUL2 next to its KUL1 campus in Cyberjaya without an address. The point is the Cyberjaya coordinate from its Wikipedia article (which also gives the district), so it marks the township rather than the parcel.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2024-08-06","basis":"planned","metric":"power_capacity","note":"IT capacity at full build-out as announced in 2023 and restated at groundbreaking.","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":256},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Critical IT load once fully developed, from Vantage's undated campus page viewed on the access date; it supersedes the 256 MW plan without an announced explanation.","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":436},{"applies_to":"campus","as_of":"2024-08-06","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2"],"unit":"acres","value":35},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"Campus page figure (21 hectares), larger than the 35 acres given in 2023 and 2024.","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":52},{"applies_to":"campus","as_of":"2023-05-16","basis":"planned","metric":"floor_area","note":"Given as 2.75 million square feet.","qualifier":"exact","source_ids":["s1"],"unit":"sq_m","value":256000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Given as 4.8 million square feet (445,000 square metres) once fully developed.","qualifier":"approximately","source_ids":["s3"],"unit":"sq_m","value":445000},{"applies_to":"campus","as_of":"2023-05-16","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1"],"unit":"count","value":10},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"Campus page count of data centers once fully developed.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":6}],"milestones":[{"date":"2023-05-16","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024-08-06","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony, at which the TNB supply agreement was disclosed.","source_ids":["s2"]},{"date":"2025-Q4","event":"first_operational","kind":"planned","note":"Target set in the May 2023 announcement; no source found confirms whether it was met.","source_ids":["s1"]}],"name":"Vantage Data Centers Cyberjaya II campus (KUL2)","notes":"Vantage's May 2023 release presented an additional US$3 billion for building the campus, but its 2024 release calls the same sum investment into Malaysia, so it is kept out of the metrics as a country-level figure. Vantage signed an agreement with Cyberview Sdn Bhd, Cyberjaya's tech-hub developer, to secure the land; its formal role is not stated. The undated campus page (s3), read on 2026-10-09, gives the 436 MW plan in future tense without saying which buildings are live, so the status rests on the 2024 groundbreaking. KUL1 next door is a separate campus; in 2023 Vantage said both together would deliver 287 MW of IT capacity. Coordinates and district come from Wikipedia (s4).","parties":[{"name":"Vantage Data Centers","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Tenaga Nasional Berhad (TNB)","note":"Electricity supply agreement for 500 MVA via a dedicated 275 kV substation.","role":"utility","source_ids":["s2","s3"]}],"power_sources":[{"description":"Electricity supply agreement with TNB for 500 MVA through a dedicated 275 kV high-voltage substation on campus; the campus page lists a 500 MVA on-campus substation.","source_ids":["s2","s3"],"type":"grid"},{"description":"Vantage's campus page says solar panels will power non-critical areas such as offices and amenity spaces.","source_ids":["s3"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2023-05-16","publisher":"Vantage Data Centers (press release via Media OutReach, Viet Nam News)","title":"Vantage Data Centers Announces Second Campus in Cyberjaya","type":"company","url":"https://vietnamnews.vn/media-outreach/1536601/vantage-data-centers-announces-second-campus-in-cyberjaya.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260511172529/https://vantage-dc.com/news/vantage-data-centers-breaks-ground-on-256mw-cyberjaya-campus/","id":"s2","published":"2024-08-06","publisher":"Vantage Data Centers","title":"Vantage Data Centers Breaks Ground on 256MW Cyberjaya Campus","type":"company","url":"https://vantage-dc.com/news/vantage-data-centers-breaks-ground-on-256mw-cyberjaya-campus/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Vantage Data Centers","title":"Cyberjaya II, Malaysia Campus","type":"company","url":"https://vantage-dc.com/data-center-locations/apac/cyberjaya-ii-malaysia/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Cyberjaya","type":"other","url":"https://en.wikipedia.org/wiki/Cyberjaya"}],"status":"under_construction","status_as_of":"2024-08-06","status_source_ids":["s2"],"summary":"Vantage Data Centers' second hyperscale campus in Cyberjaya, Selangor, next to its existing KUL1 campus. Announced in May 2023 as a 256 MW IT campus of 10 facilities on nearly 35 acres, with the first facility planned for Q4 2025, it broke ground in August 2024 alongside a supply agreement with Tenaga Nasional Berhad for 500 MVA through a dedicated 275 kV substation. Vantage's campus page, viewed in October 2026, now describes a larger plan of 436 MW of critical IT load in six data centers on 52 acres. No source found confirms whether the first facility has opened.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"89571c26-d4c1-5923-adbf-ee81b0b8b068","s2":"c2f6b1cb-3bb4-58d9-b2f6-b09a18e1245e","s3":"da552195-033d-5bc9-806d-2d3a98a1361b","s4":"19c00ba6-d671-5c9a-811d-d7911af9b674"},"source_file":"datacenters/projects/vantage-kul2-cyberjaya.json","source_record_id":"vantage-kul2-cyberjaya","source_record_sha256":"a5368f23664126d38af865d9bb7fb6cf59a1e4af284c3d0160de0ca0ed90aae8","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4ea59882a900006b0a3b49ebadc701ea7b5d03b2fc4c600ab783ce866f92c00c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-54113ebec20f61dd4a6e/#project-a31a1552-7be0-58e9-8097-4083d11175dd | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a31a1552-7be0-58e9-8097-4083d11175dd.json
a490f00a-8b75-5547-b0e9-5fb3b6e5f616 | imported:semiconductor-atlas:quantum-frederick | vcc-site-bf298971fe1dec3fc0ac | imported:semiconductor-atlas:quantum-frederick | Quantum Frederick data center park | United States | US | 39.4311 | -77.3972 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of the city of Frederick (s5). Baxtel's listing beside the 2021 article (s1) gives a Manor Woods Road, Frederick address for the former Eastalco site, which lies outside the city; the park was not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a690b130-039f-5489-af4c-cc5ffc583b78 | under_construction | 2026-03-12 | 215 | imported_documented_status | 1cf26270-52c3-5e65-b4bb-92c10a00d4f9 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a690b130-039f-5489-af4c-cc5ffc583b78","notes":"TPG Real Estate Partners joined Quantum Loophole in a 2021 joint venture whose investment helped fund the site purchase; it took full control in December 2024 and trade press now calls the park TPG's.","party":"TPG Real Estate","relationship_scope":"unknown","role":"owner","source_record_id":"quantum-frederick"},{"evidence_id":"b23b1961-f34c-5183-95b6-6433cfabcd03","notes":"TPG Real Estate Partners joined Quantum Loophole in a 2021 joint venture whose investment helped fund the site purchase; it took full control in December 2024 and trade press now calls the park TPG's.","party":"TPG Real Estate","relationship_scope":"unknown","role":"owner","source_record_id":"quantum-frederick"},{"evidence_id":"1cf26270-52c3-5e65-b4bb-92c10a00d4f9","notes":"TPG Real Estate Partners joined Quantum Loophole in a 2021 joint venture whose investment helped fund the site purchase; it took full control in December 2024 and trade press now calls the park TPG's.","party":"TPG Real Estate","relationship_scope":"unknown","role":"owner","source_record_id":"quantum-frederick"},{"evidence_id":"b23b1961-f34c-5183-95b6-6433cfabcd03","notes":"Described as the park's sole developer by March 2026.","party":"TPG Real Estate","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"1cf26270-52c3-5e65-b4bb-92c10a00d4f9","notes":"Described as the park's sole developer by March 2026.","party":"TPG Real Estate","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"a690b130-039f-5489-af4c-cc5ffc583b78","notes":"Original developer and manager of the master-planned park; after TPG sought a court order in 2024 to remove it as manager, it ended any active involvement in December 2024.","party":"Quantum Loophole","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"3a1470e0-70e9-542b-8e57-545ea6b11011","notes":"Original developer and manager of the master-planned park; after TPG sought a court order in 2024 to remove it as manager, it ended any active involvement in December 2024.","party":"Quantum Loophole","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"b23b1961-f34c-5183-95b6-6433cfabcd03","notes":"Original developer and manager of the master-planned park; after TPG sought a court order in 2024 to remove it as manager, it ended any active involvement in December 2024.","party":"Quantum Loophole","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"3a1470e0-70e9-542b-8e57-545ea6b11011","notes":"Develops its own buildings within the park; named as a first mover in 2022. It paused development in mid-2023 over Maryland's backup generator rules and said in May 2024 that it would resume.","party":"Aligned Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"1cf26270-52c3-5e65-b4bb-92c10a00d4f9","notes":"Develops its own buildings within the park; named as a first mover in 2022. It paused development in mid-2023 over Maryland's backup generator rules and said in May 2024 that it would resume.","party":"Aligned Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"1cf26270-52c3-5e65-b4bb-92c10a00d4f9","notes":"Reported to be developing 11 buildings across three sites within the park.","party":"Rowan Digital Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"quantum-frederick"},{"evidence_id":"1cf26270-52c3-5e65-b4bb-92c10a00d4f9","notes":"Builder of Aligned's IAD-06 building.","party":"Turner Construction Company","relationship_scope":"unknown","role":"builder","source_record_id":"quantum-frederick"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | TPG Real Estate |  |  |  |  | https://baxtel.com/news/aligned-tops-out-new-maryland-data-center | https://baxtel.com/news/tpg-teams-up-with-quantum-loophole-to-redevelop-old-alcoa-plant | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry","master_park_with_multiple_subcampuses_not_individual_facility"],"rationale":"No matching named development in the 201-project release. Preserve Quantum Frederick data center park as an independent source record; its locality locator does not itself establish a surveyed physical site. Source encompasses a single explicitly bounded master park with multiple development subcampuses; retain that park-level scope.","source_record_id":"quantum-frederick"},"record":{"aliases":["Quantum Frederick","Quantum Park","Quantum Loophole Frederick campus"],"id":"quantum-frederick","last_reviewed":"2026-10-09","location":{"admin1":"Maryland","admin2":"Frederick County","country":"US","lat":39.4311,"locality":"Frederick","lon":-77.3972,"note":"Coordinates are the Wikipedia centroid of the city of Frederick (s5). Baxtel's listing beside the 2021 article (s1) gives a Manor Woods Road, Frederick address for the former Eastalco site, which lies outside the city; the park was not geocoded.","precision":"locality","source_ids":["s1","s5"]},"metrics":[{"applies_to":"campus","as_of":"2021-06-28","basis":"planned","metric":"power_capacity","note":"The 2021 announcement said the park would start with 1 GW of transmission power capacity.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-03-12","basis":"planned","metric":"power_capacity","phase_label":"Aligned Data Centers parcel (four buildings)","power_scope":"unspecified","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":264},{"applies_to":"phase","as_of":"2026-03-12","basis":"under_construction","metric":"power_capacity","note":"Two-story, 450,000 sq ft building whose structural phase was completed in March 2026.","phase_label":"Aligned IAD-06 building","power_scope":"unspecified","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":72},{"applies_to":"campus","as_of":"2024-12-27","basis":"reported","metric":"investment","note":"Trade press refers to the park as a USD 5 billion project when TPG took full control.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":5000000000},{"applies_to":"campus","as_of":"2021-06-28","basis":"acquired","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2","s3","s4"],"unit":"acres","value":2100},{"applies_to":"phase","as_of":"2026-03-12","basis":"reported","metric":"land_area","note":"Campus on which the IAD-06 building sits; the source does not say whether it covers all four planned Aligned buildings.","phase_label":"Aligned IAD-06 site","qualifier":"approximately","source_ids":["s4"],"unit":"acres","value":75},{"applies_to":"phase","as_of":"2026-03-12","basis":"planned","metric":"floor_area","note":"Aligned's original plan for the park, as reported in March 2026.","phase_label":"Aligned Data Centers parcel (four buildings)","qualifier":"approximately","source_ids":["s4"],"unit":"sq_ft","value":3300000},{"applies_to":"phase","as_of":"2026-03-12","basis":"planned","metric":"buildings","phase_label":"Aligned Data Centers parcel (four buildings)","qualifier":"exact","source_ids":["s4"],"unit":"count","value":4},{"applies_to":"phase","as_of":"2026-03-12","basis":"planned","metric":"buildings","phase_label":"Rowan Digital Infrastructure sites","qualifier":"exact","source_ids":["s4"],"unit":"count","value":11}],"milestones":[{"date":"2021","event":"site_acquired","kind":"actual","note":"Quantum Loophole had recently closed the purchase of the former Alcoa plant site when it announced the TPG Real Estate Partners joint venture in June 2021.","source_ids":["s1"]},{"date":"2022-06","event":"construction_started","kind":"actual","note":"Quantum Loophole announced on 22 June 2022 that it had broken ground on park infrastructure: power distribution, water and sewer, fiber ducts and roads.","source_ids":["s2"]},{"date":"2024-12","event":"other","kind":"actual","note":"TPG Real Estate took full control and Quantum Loophole ended its active involvement.","source_ids":["s3"]},{"date":"2025","event":"other","kind":"actual","note":"Aligned broke ground on its IAD-04 building in the park.","source_ids":["s4"]},{"date":"2026-Q1","event":"other","kind":"actual","note":"Turner and Aligned completed the structural phase of the 72 MW IAD-06 building, as reported on 12 March 2026.","source_ids":["s4"]}],"name":"Quantum Frederick data center park","notes":"This record covers the whole park; buildings by Aligned, Rowan and other developers inside it are tracked here as phases rather than separate records. The site was bought in 2021 but qualifies through the June 2022 infrastructure groundbreaking and later construction. No source found states that any data center building in the park is operating, so status stays under construction. No campus-wide MW total beyond the 2021 transmission figure was found.","parties":[{"name":"TPG Real Estate","note":"TPG Real Estate Partners joined Quantum Loophole in a 2021 joint venture whose investment helped fund the site purchase; it took full control in December 2024 and trade press now calls the park TPG's.","role":"owner","source_ids":["s1","s3","s4"]},{"name":"TPG Real Estate","note":"Described as the park's sole developer by March 2026.","role":"developer","source_ids":["s3","s4"]},{"name":"Quantum Loophole","note":"Original developer and manager of the master-planned park; after TPG sought a court order in 2024 to remove it as manager, it ended any active involvement in December 2024.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Aligned Data Centers","note":"Develops its own buildings within the park; named as a first mover in 2022. It paused development in mid-2023 over Maryland's backup generator rules and said in May 2024 that it would resume.","role":"developer","source_ids":["s2","s4"]},{"name":"Rowan Digital Infrastructure","note":"Reported to be developing 11 buildings across three sites within the park.","role":"developer","source_ids":["s4"]},{"name":"Turner Construction Company","note":"Builder of Aligned's IAD-06 building.","role":"builder","source_ids":["s4"]}],"power_sources":[{"description":"The park was planned around 1 GW of transmission power capacity, with power distribution and underground ducts among the first infrastructure works.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2021-06-28","publisher":"Baxtel","title":"TPG teams up with Quantum Loophole to redevelop Old Alcoa Plant","type":"trade_press","url":"https://baxtel.com/news/tpg-teams-up-with-quantum-loophole-to-redevelop-old-alcoa-plant"},{"accessed":"2026-10-09","id":"s2","published":"2022-07-05","publisher":"Cabling Installation & Maintenance","title":"Quantum Loophole begins construction on massive Frederick, Md. data center campus","type":"trade_press","url":"https://www.cablinginstall.com/data-center/article/14279126/quantum-loophole-begins-construction-on-massive-frederick-md-data-center-campus"},{"accessed":"2026-10-09","id":"s3","published":"2024-12-27","publisher":"Baxtel","title":"TPG Real Estate takes full control of Quantum Frederick Project","type":"trade_press","url":"https://baxtel.com/news/tpg-real-estate-takes-full-control-of-quantum-frederick-project"},{"accessed":"2026-10-09","id":"s4","published":"2026-03-12","publisher":"Baxtel","title":"Aligned Tops out New Maryland Data Center","type":"trade_press","url":"https://baxtel.com/news/aligned-tops-out-new-maryland-data-center"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001150817/https://en.wikipedia.org/wiki/Frederick,_Maryland","id":"s5","published":null,"publisher":"Wikipedia","title":"Frederick, Maryland","type":"other","url":"https://en.wikipedia.org/wiki/Frederick,_Maryland"}],"status":"under_construction","status_as_of":"2026-03-12","status_source_ids":["s4"],"summary":"Master-planned data center park of about 2,100 acres on the former Alcoa Eastalco Works site near Frederick, Maryland. Quantum Loophole bought the land in 2021 with backing from a joint venture with TPG Real Estate, planned to start with 1 GW of transmission capacity, and announced in June 2022 that it had broken ground on shared power, water and fiber infrastructure. TPG took full control at the end of 2024 of a project reported at USD 5 billion. Aligned Data Centers plans four buildings totaling 264 MW in the park, including a 72 MW building reported topped out in March 2026, and Rowan Digital Infrastructure is developing 11 buildings on three sites.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a690b130-039f-5489-af4c-cc5ffc583b78","s2":"3a1470e0-70e9-542b-8e57-545ea6b11011","s3":"b23b1961-f34c-5183-95b6-6433cfabcd03","s4":"1cf26270-52c3-5e65-b4bb-92c10a00d4f9","s5":"cc32245b-4b2a-51ac-8d2c-13cc74884c56"},"source_file":"datacenters/projects/quantum-frederick.json","source_record_id":"quantum-frederick","source_record_sha256":"98a19a570fec7492c5695c7b8bfda0e04f30819df89668cd9a89dcebba4c7f12","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"9aca781ae31db58f1a6986ccd5855d5e73741016fe013058dac666203171704d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bf298971fe1dec3fc0ac/#project-a490f00a-8b75-5547-b0e9-5fb3b6e5f616 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a490f00a-8b75-5547-b0e9-5fb3b6e5f616.json
a5618437-38a6-5fd0-a340-56ab10f1e97b | imported:semiconductor-atlas:cyrusone-freestone-county | vcc-site-4776103546341c240223 | imported:semiconductor-atlas:cyrusone-freestone-county | CyrusOne Freestone County data center campus | United States | US | 31.7183 | -96.1697 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of Fairfield (s3). CyrusOne gives the Freestone Energy Center's Fairfield address (on FM 488) as the reference point and has no address for the data center itself; the site was not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 1d917775-0af3-5219-98e1-39146778e43a | announced | 2026-10-09 | 4 | imported_documented_status | 9835b74e-ae0f-574b-8811-f7d628e64cdb | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"1d917775-0af3-5219-98e1-39146778e43a","notes":null,"party":"CyrusOne","relationship_scope":"unknown","role":"developer","source_record_id":"cyrusone-freestone-county"},{"evidence_id":"9835b74e-ae0f-574b-8811-f7d628e64cdb","notes":null,"party":"CyrusOne","relationship_scope":"unknown","role":"developer","source_record_id":"cyrusone-freestone-county"},{"evidence_id":"1d917775-0af3-5219-98e1-39146778e43a","notes":"Calpine LLC, a business unit of Constellation, supplies power from its Freestone Energy Center.","party":"Calpine","relationship_scope":"unknown","role":"power_supplier","source_record_id":"cyrusone-freestone-county"},{"evidence_id":"9835b74e-ae0f-574b-8811-f7d628e64cdb","notes":"Calpine LLC, a business unit of Constellation, supplies power from its Freestone Energy Center.","party":"Calpine","relationship_scope":"unknown","role":"power_supplier","source_record_id":"cyrusone-freestone-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.cyrusone.com/data-centers/north-america/freestone-county-texas | https://www.cyrusone.com/resources/press-releases/constellation-and-cyrusone-announce-agreement-to-support-new-data-center-facility-at-freestone-energy-center-in-texas | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve CyrusOne Freestone County data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"cyrusone-freestone-county"},"record":{"aliases":["Freestone County Data Center","Freestone Energy Center data center"],"id":"cyrusone-freestone-county","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Freestone County","country":"US","lat":31.7183,"locality":"Fairfield","lon":-96.1697,"note":"Coordinates are the Wikipedia centroid of Fairfield (s3). CyrusOne gives the Freestone Energy Center's Fairfield address (on FM 488) as the reference point and has no address for the data center itself; the site was not geocoded.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"phase","as_of":"2026-02-09","basis":"contracted","metric":"power_capacity","note":"The release does not name this tranche phase 1; it describes the second 380 MW block as phase 2.","phase_label":"First phase (initial 380 MW agreement)","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":380},{"applies_to":"phase","as_of":"2026-02-09","basis":"contracted","metric":"power_capacity","note":"Calpine entered an exclusive agreement to provide power, grid connectivity and site infrastructure for this phase; the release counts it within more than 1,100 MW under contract for CyrusOne in Texas.","phase_label":"Phase 2","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":380},{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"Stated across multiple phases on CyrusOne's undated campus page.","qualifier":"more_than","source_ids":["s2"],"unit":"USD","value":500000000}],"milestones":[{"date":"2026-02-09","event":"announced","kind":"actual","source_ids":["s1"]}],"name":"CyrusOne Freestone County data center campus","notes":"The campus page is an undated living page (it mentions events in June 2026), so status_as_of is the access date. It says the project still needs approval and gives no capacity, building count or delivery dates. Only company sources were found; no independent coverage was opened. Constellation's release puts CyrusOne's contracted Texas capacity across sites at over 1,100 MW, including 400 MW at the separate Bosque County campus.","parties":[{"name":"CyrusOne","role":"developer","source_ids":["s1","s2"]},{"name":"Calpine","note":"Calpine LLC, a business unit of Constellation, supplies power from its Freestone Energy Center.","role":"power_supplier","source_ids":["s1","s2"]}],"power_sources":[{"description":"Supply and grid connection through the Calpine agreement at the Freestone Energy Center.","source_ids":["s1","s2"],"type":"grid"},{"description":"CyrusOne says the campus will also use on-site generation; its type and size are not stated.","source_ids":["s2"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-02-09","publisher":"CyrusOne","title":"Constellation and CyrusOne Announce Agreement to Support New Data Center Facility at Freestone Energy Center in Texas","type":"company","url":"https://www.cyrusone.com/resources/press-releases/constellation-and-cyrusone-announce-agreement-to-support-new-data-center-facility-at-freestone-energy-center-in-texas"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"CyrusOne","title":"Freestone County Data Center","type":"company","url":"https://www.cyrusone.com/data-centers/north-america/freestone-county-texas"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260925231547/https://en.wikipedia.org/wiki/Fairfield,_Texas","id":"s3","published":null,"publisher":"Wikipedia","title":"Fairfield, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Fairfield,_Texas"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s2"],"summary":"Multiphase data center campus planned by CyrusOne next to Calpine's Freestone Energy Center in Freestone County, Texas, about 80 miles southeast of Dallas near Fairfield. In February 2026 Calpine, by then part of Constellation, signed a 380 MW agreement providing power, grid connectivity and site infrastructure, plus an exclusive agreement to serve a second 380 MW phase. CyrusOne's campus page lists the project as in development and still awaiting county approval, with more than USD 500 million of investment across phases, power from both the grid and on-site generation, and closed-loop cooling.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"1d917775-0af3-5219-98e1-39146778e43a","s2":"9835b74e-ae0f-574b-8811-f7d628e64cdb","s3":"a19c9491-1e5b-554d-80af-5a23af78251a"},"source_file":"datacenters/projects/cyrusone-freestone-county.json","source_record_id":"cyrusone-freestone-county","source_record_sha256":"6a4ceb3cac6ddc4faecfc7a89809b4861740596566c42b6a9ceaee9af91a1642","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"22c351fc2b421eadbc333afa86249fe4f8d42edb299ae8e7f126ad5eabef25e8"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4776103546341c240223/#project-a5618437-38a6-5fd0-a340-56ab10f1e97b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a5618437-38a6-5fd0-a340-56ab10f1e97b.json
a5b2cd4f-b857-573e-82b8-6edc1e776eec | imported:semiconductor-atlas:aws-project-rainier-new-carlisle | vcc-site-6835cf832163c1403b4e | imported:semiconductor-atlas:aws-project-rainier-new-carlisle | AWS New Carlisle data center campus (Project Rainier) | United States | US | 41.7006 | -86.4964 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the campus in the Indiana Enterprise Center near New Carlisle but give no parcel or address; coordinates are the New Carlisle town point from its Wikipedia article (Nominatim was unavailable). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | b24d6eb3-c5c8-574f-ae34-b54e0c7dd6b0 | partially_operational | 2026-07-23 | 82 | imported_documented_status | 760f6122-f93d-5471-bb3a-911441ab9a16 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"b24d6eb3-c5c8-574f-ae34-b54e0c7dd6b0","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-project-rainier-new-carlisle"},{"evidence_id":"7c2fd4d8-0120-57be-899a-2772b1aef6d2","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-project-rainier-new-carlisle"},{"evidence_id":"760f6122-f93d-5471-bb3a-911441ab9a16","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-project-rainier-new-carlisle"},{"evidence_id":"7c2fd4d8-0120-57be-899a-2772b1aef6d2","notes":"Amazon says Anthropic uses Project Rainier, which spans several US data centers including this one, to build and deploy Claude; trade press says the site's chips are dedicated to Anthropic's models.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"aws-project-rainier-new-carlisle"},{"evidence_id":"a39ceab7-e423-5efa-b0f9-42a0ad254673","notes":"Amazon says Anthropic uses Project Rainier, which spans several US data centers including this one, to build and deploy Claude; trade press says the site's chips are dedicated to Anthropic's models.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"aws-project-rainier-new-carlisle"},{"evidence_id":"fd2ca835-05d0-5417-b795-c96ba31fd5e4","notes":null,"party":"Indiana Michigan Power","relationship_scope":"unknown","role":"utility","source_record_id":"aws-project-rainier-new-carlisle"},{"evidence_id":"7c2fd4d8-0120-57be-899a-2772b1aef6d2","notes":null,"party":"Indiana Michigan Power","relationship_scope":"unknown","role":"utility","source_record_id":"aws-project-rainier-new-carlisle"},{"evidence_id":"b24d6eb3-c5c8-574f-ae34-b54e0c7dd6b0","notes":"Offered performance-based tax credits, training grants and a 50-year data center sales tax exemption.","party":"Indiana Economic Development Corporation","relationship_scope":"unknown","role":"government","source_record_id":"aws-project-rainier-new-carlisle"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | Anthropic |  | https://www.wndu.com/2026/07/23/amazon-web-services-investment-st-joseph-county-data-center-campus-surpasses-138-billion/ | https://www.iedc.in.gov/events/news/details/2024/04/25/gov.-holcomb-announces-amazon-web-services-plans-to-invest-11b-to-create-a-new-data-center-campus-in-northern-indiana | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AWS New Carlisle data center campus (Project Rainier) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"aws-project-rainier-new-carlisle"},"record":{"aliases":["Project Rainier","AWS Indiana Enterprise Center campus"],"id":"aws-project-rainier-new-carlisle","last_reviewed":"2026-10-09","location":{"admin1":"Indiana","admin2":"St. Joseph County","country":"US","lat":41.7006,"locality":"New Carlisle","lon":-86.4964,"note":"Sources place the campus in the Indiana Enterprise Center near New Carlisle but give no parcel or address; coordinates are the New Carlisle town point from its Wikipedia article (Nominatim was unavailable).","precision":"locality","source_ids":["s1","s5","s6"]},"metrics":[{"applies_to":"campus","as_of":"2024-04-25","basis":"announced","metric":"investment","note":"Original announced plan, described by the state as its largest capital investment announcement.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":11000000000},{"applies_to":"campus","as_of":"2026-07-23","basis":"reported","metric":"investment","note":"Amount an AWS director said had been invested by July 2026, above the original $11 billion goal, while construction continued.","qualifier":"approximately","source_ids":["s6"],"unit":"USD","value":13800000000},{"applies_to":"campus","as_of":"2025-04-23","basis":"planned","metric":"power_capacity","note":"Capacity stated in Amazon filings with the Indiana Utility Regulatory Commission as reported by The Times; the filings also cite a possible 90% load factor. Whether this is IT or total load is not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":2250},{"applies_to":"campus","as_of":"2025-10-29","basis":"planned","metric":"power_capacity","note":"Trade press figure for the expected draw of the full site at build-out.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s3"],"unit":"MW","value":2200},{"applies_to":"campus","as_of":"2026-07-23","basis":"planned","metric":"buildings","qualifier":"approximately","source_ids":["s3","s6"],"unit":"count","value":30},{"applies_to":"campus","as_of":"2025-10-29","basis":"operational","metric":"buildings","note":"Buildings complete and in use at the October 2025 activation.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":7},{"applies_to":"campus","as_of":"2026-07-23","basis":"operational","metric":"buildings","qualifier":"approximately","source_ids":["s6"],"unit":"count","value":18},{"applies_to":"campus","as_of":"2025-10-29","basis":"reported","metric":"land_area","note":"Trade press figure; a June 2026 local TV report gives 800 acres. The sources do not explain the difference.","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":1200},{"applies_to":"campus","as_of":"2026-06-03","basis":"reported","metric":"land_area","note":"Conflicts with the 1,200-acre trade press figure.","qualifier":"exact","source_ids":["s5"],"unit":"acres","value":800},{"applies_to":"campus","as_of":"2024-04-25","basis":"planned","metric":"jobs_permanent","qualifier":"at_least","source_ids":["s1"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2026-07-23","basis":"reported","metric":"jobs_permanent","note":"People hired to date as of July 2026, per the South Bend chamber president.","qualifier":"more_than","source_ids":["s6"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2026-07-23","basis":"reported","metric":"jobs_construction","note":"Peak on-site construction workforce cited by the South Bend chamber president.","qualifier":"up_to","source_ids":["s6"],"unit":"count","value":4000},{"applies_to":"campus","as_of":"2025-10-29","basis":"reported","metric":"jobs_construction","note":"Trade press total for construction jobs; not comparable to the peak on-site headcount.","qualifier":"approximately","source_ids":["s3"],"unit":"count","value":9000}],"milestones":[{"date":"2024-04-25","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024","event":"construction_started","kind":"actual","note":"Local TV said in July 2026 that construction had begun about two years earlier; no exact date given.","source_ids":["s6"]},{"date":"2025","event":"first_operational","kind":"actual","note":"Trade press reported AWS's activation of Project Rainier on 29 October 2025, with seven buildings at this site complete and in use; Amazon called the cluster fully operational. Earlier partial use is not dated in the sources.","source_ids":["s3","s4"]},{"date":"2026-06-03","event":"other","kind":"actual","note":"Campus administration building opened, housing workforce development programs.","source_ids":["s5"]}],"name":"AWS New Carlisle data center campus (Project Rainier)","notes":"Amazon describes Project Rainier as spread across several US data centers and names St. Joseph County as one of them, so the cluster-wide chip counts are not recorded here.","parties":[{"name":"Amazon Web Services","role":"developer","source_ids":["s1","s3","s6"]},{"name":"Anthropic","note":"Amazon says Anthropic uses Project Rainier, which spans several US data centers including this one, to build and deploy Claude; trade press says the site's chips are dedicated to Anthropic's models.","role":"tenant","source_ids":["s3","s4"]},{"name":"Indiana Michigan Power","role":"utility","source_ids":["s2","s3"]},{"name":"Indiana Economic Development Corporation","note":"Offered performance-based tax credits, training grants and a 50-year data center sales tax exemption.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Served by Indiana Michigan Power, which expects new data center load to double its demand by 2030; a consumer group says the utility has proposed adding gas-fired generation.","source_ids":["s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007105124/https://iedc.in.gov/events/news/details/2024/04/25/gov.-holcomb-announces-amazon-web-services-plans-to-invest-11b-to-create-a-new-data-center-campus-in-northern-indiana","id":"s1","published":"2024-04-25","publisher":"Indiana Economic Development Corporation","title":"Gov. Holcomb announces Amazon Web Services plans to invest $11B to create a new data center campus in Northern Indiana","type":"government","url":"https://www.iedc.in.gov/events/news/details/2024/04/25/gov.-holcomb-announces-amazon-web-services-plans-to-invest-11b-to-create-a-new-data-center-campus-in-northern-indiana"},{"accessed":"2026-10-09","id":"s2","published":"2025-04-23","publisher":"GovTech (The Times, Munster, via Tribune Content Agency)","title":"Indiana data center could bring significant power use","type":"news","url":"https://www.govtech.com/artificial-intelligence/indiana-data-center-could-bring-significant-power-use"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-29","publisher":"Converge Digest","title":"AWS activates Project Rainier data center campus","type":"trade_press","url":"https://convergedigest.com/aws-activates-project-rainier-data-center-campus/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Amazon","title":"AWS activates Project Rainier: One of the world's largest AI compute clusters comes online","type":"company","url":"https://www.aboutamazon.com/news/aws/aws-project-rainier-ai-trainium-chips-compute-cluster"},{"accessed":"2026-10-09","id":"s5","published":"2026-06-03","publisher":"WSBT","title":"First look at Amazon's New Carlisle data center's administration building, campus","type":"news","url":"https://wsbt.com/news/local/first-look-at-amazons-new-carlisle-data-centers-administration-building-campus-11-billion-dollar-investment-recruit-workers-technical-careers-multiple-buildings"},{"accessed":"2026-10-09","id":"s6","published":"2026-07-23","publisher":"WNDU","title":"Amazon Web Services investment in St. Joseph County data center campus surpasses $13.8 billion","type":"news","url":"https://www.wndu.com/2026/07/23/amazon-web-services-investment-st-joseph-county-data-center-campus-surpasses-138-billion/"}],"status":"partially_operational","status_as_of":"2026-07-23","status_source_ids":["s6"],"summary":"Amazon Web Services campus in the Indiana Enterprise Center near New Carlisle, St. Joseph County, announced in April 2024 as an $11 billion build over roughly a decade. It is one of the sites of Project Rainier, the Trainium2 cluster Anthropic uses to build and deploy Claude, which AWS activated in October 2025. Amazon's utility filings describe a 2,250 MW load. In July 2026 AWS said it had invested $13.8 billion, with about 18 of a planned 30 or so buildings running and construction continuing.","workloads":["ai_training","ai_inference","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"b24d6eb3-c5c8-574f-ae34-b54e0c7dd6b0","s2":"fd2ca835-05d0-5417-b795-c96ba31fd5e4","s3":"7c2fd4d8-0120-57be-899a-2772b1aef6d2","s4":"a39ceab7-e423-5efa-b0f9-42a0ad254673","s5":"1ae19b56-f226-5eb6-b673-041e0d86c005","s6":"760f6122-f93d-5471-bb3a-911441ab9a16"},"source_file":"datacenters/projects/aws-project-rainier-new-carlisle.json","source_record_id":"aws-project-rainier-new-carlisle","source_record_sha256":"9e019ae4b414feaed73344d8d3bddbdaf009ce19c6a6d17e8cf32708910e178a","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3b7a34a1562fe2d14287f8706f517b88b84b80c42b6c7373b0d0cf97e261546d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6835cf832163c1403b4e/#project-a5b2cd4f-b857-573e-82b8-6edc1e776eec | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a5b2cd4f-b857-573e-82b8-6edc1e776eec.json
a7a29c6e-70aa-5f7b-b172-d1abe208715e | imported:semiconductor-atlas:cloudhq-queretaro | vcc-site-9209936dfd95900f78c3 | imported:semiconductor-atlas:cloudhq-queretaro | CloudHQ QRO Campus (Querétaro) | Mexico | MX | 20.6198 | -100.1474 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Coordinates are the point published on CloudHQ's campus page. News reports place the 52-hectare site on the west side of the airport; the published point was not checked against a parcel boundary. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | eb3a316f-cdae-55ad-b88b-08ed42e7c6ed | announced | 2025-09-30 | 378 | imported_documented_status | 240ff090-6815-5cab-942c-af184e725d45 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"eb3a316f-cdae-55ad-b88b-08ed42e7c6ed","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-queretaro"},{"evidence_id":"284caabe-4de1-56e5-af68-2dad3ffdba21","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-queretaro"},{"evidence_id":"240ff090-6815-5cab-942c-af184e725d45","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-queretaro"},{"evidence_id":"0cb2d25c-611d-5bdf-9af0-71547a3b740e","notes":null,"party":"CloudHQ","relationship_scope":"unknown","role":"developer","source_record_id":"cloudhq-queretaro"},{"evidence_id":"284caabe-4de1-56e5-af68-2dad3ffdba21","notes":"Reported as supporting CloudHQ with land acquisition and permits; CloudHQ has worked with the state since 2021.","party":"Government of the State of Querétaro","relationship_scope":"unknown","role":"government","source_record_id":"cloudhq-queretaro"},{"evidence_id":"8c6396a6-ca07-52f9-a0fc-f730347ffb4e","notes":"Reported as supporting CloudHQ with land acquisition and permits; CloudHQ has worked with the state since 2021.","party":"Government of the State of Querétaro","relationship_scope":"unknown","role":"government","source_record_id":"cloudhq-queretaro"},{"evidence_id":"284caabe-4de1-56e5-af68-2dad3ffdba21","notes":"CloudHQ says it worked with CFE and the grid operator CENACE to secure the initial power supply.","party":"Comisión Federal de Electricidad (CFE)","relationship_scope":"unknown","role":"utility","source_record_id":"cloudhq-queretaro"},{"evidence_id":"8c6396a6-ca07-52f9-a0fc-f730347ffb4e","notes":"CloudHQ says it worked with CFE and the grid operator CENACE to secure the initial power supply.","party":"Comisión Federal de Electricidad (CFE)","relationship_scope":"unknown","role":"utility","source_record_id":"cloudhq-queretaro"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.telecomreviewamericas.com/articles/wholesale-and-capacity/cloudhq-to-build-mexicos-largest-hyperscale-data-hub-in-queretaro/ | https://cloudhq.com/campus/qro-campus/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve CloudHQ QRO Campus (Querétaro) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"cloudhq-queretaro"},"record":{"aliases":["QRO Campus","CloudHQ Querétaro"],"id":"cloudhq-queretaro","last_reviewed":"2026-10-09","location":{"admin1":"Querétaro","country":"MX","lat":20.61983,"locality":"Querétaro (beside Querétaro Intercontinental Airport)","lon":-100.1474,"note":"Coordinates are the point published on CloudHQ's campus page. News reports place the 52-hectare site on the west side of the airport; the published point was not checked against a parcel boundary.","precision":"approximate_site","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-09-25","basis":"planned","metric":"power_capacity","note":"Described as critical IT load at full build-out across six buildings.","power_scope":"it_load","qualifier":"up_to","source_ids":["s2","s3","s5"],"unit":"MW","value":900},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total critical IT load on CloudHQ's undated campus page (read 2026-10-09; its footer shows 2023). The same page lists six buildings of 48 MW each, which totals 288 MW.","power_scope":"it_load","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":360},{"applies_to":"phase","as_of":"2025-09-26","basis":"planned","metric":"power_capacity","note":"Reported as the initial power allocation CloudHQ has secured.","phase_label":"First phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s5"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2025-09-25","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s2","s3","s4","s5"],"unit":"USD","value":4800000000},{"applies_to":"campus","as_of":"2025-09-25","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s2","s3","s5"],"unit":"hectares","value":52},{"applies_to":"campus","as_of":"2025-09-26","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2025-09-26","basis":"planned","metric":"jobs_construction","qualifier":"approximately","source_ids":["s2","s3","s4"],"unit":"count","value":7200},{"applies_to":"campus","as_of":"2025-09-26","basis":"planned","metric":"jobs_permanent","note":"Por Esto instead reported about 600 direct operating jobs, while quoting a post that cited 900.","qualifier":"approximately","source_ids":["s2","s3","s4"],"unit":"count","value":900}],"milestones":[{"date":"2025-09-25","event":"announced","kind":"actual","note":"Presented at the president's morning press conference by Economy Secretary Marcelo Ebrard and CloudHQ executives.","source_ids":["s2","s5"]},{"date":"2027","event":"first_operational","kind":"planned","note":"CloudHQ targets readiness for service within 2027; heise reported operation planned for the first half of 2027.","source_ids":["s1","s3","s4"]}],"name":"CloudHQ QRO Campus (Querétaro)","notes":"Status rests on September 2025 announcement coverage; no 2026 construction or tenant update was found. Por Esto reported a lease already signed with an unnamed global technology tenant and works under way, Xataka reported that CloudHQ had invested USD 250 million so far and was still pursuing a long-term lease, while heise described construction as planned and Telecom Review Americas said CloudHQ was still finalising permits, site preparation and tenant contracts. CloudHQ's undated campus page lists 360 MW and six 48 MW buildings, figures that neither add up nor match the 900 MW announced in 2025.","parties":[{"name":"CloudHQ","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Government of the State of Querétaro","note":"Reported as supporting CloudHQ with land acquisition and permits; CloudHQ has worked with the state since 2021.","role":"government","source_ids":["s2","s5"]},{"name":"Comisión Federal de Electricidad (CFE)","note":"CloudHQ says it worked with CFE and the grid operator CENACE to secure the initial power supply.","role":"utility","source_ids":["s2","s5"]}],"power_sources":[{"description":"CloudHQ's page describes an on-site substation fed by 400 kV transmission; the company says it worked with CFE and CENACE on the initial supply and plans a larger switching substation of about 2 GW.","source_ids":["s1","s2","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260920080345/https://cloudhq.com/campus/qro-campus/","id":"s1","published":null,"publisher":"CloudHQ","title":"QRO Campus","type":"company","url":"https://cloudhq.com/campus/qro-campus/"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-26","publisher":"Xataka México","title":"Inversión millonaria en Querétaro: CloudHQ construirá 6 centros de datos de hiperescala para potenciar la Inteligencia Artificial","type":"news","url":"https://www.xataka.com.mx/servicios/inversion-millonaria-queretaro-cloudhq-construira-6-centros-datos-hiperescala-para-potenciar-inteligencia-artificial"},{"accessed":"2026-10-09","id":"s3","published":"2025-09-30","publisher":"Telecom Review Americas","title":"CloudHQ to Build Mexico's Largest Hyperscale Data Hub in Querétaro","type":"trade_press","url":"https://www.telecomreviewamericas.com/articles/wholesale-and-capacity/cloudhq-to-build-mexicos-largest-hyperscale-data-hub-in-queretaro/"},{"accessed":"2026-10-09","id":"s4","published":"2025-09-29","publisher":"heise online","title":"New data centres: CloudHQ invests USD 4.8 billion in Mexico","type":"news","url":"https://heise.de/-10678892"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250928102318/https://www.poresto.com/mexico/2025/9/25/cloudhq-invertira-4800-mdd-en-6-centros-de-datos-en-queretaro-900-mw-para-ia-dentro-del-plan-mexico.html","id":"s5","published":"2025-09-25","publisher":"Por Esto","title":"CloudHQ invertirá 4,800 mdd en 6 centros de datos en Querétaro: 900 MW para IA dentro del Plan México","type":"news","url":"https://www.poresto.com/mexico/2025/9/25/cloudhq-invertira-4800-mdd-en-6-centros-de-datos-en-queretaro-900-mw-para-ia-dentro-del-plan-mexico.html"}],"status":"announced","status_as_of":"2025-09-30","status_source_ids":["s3","s4"],"summary":"CloudHQ, a US data centre developer, plans a six-building hyperscale campus on about 52 hectares next to Querétaro's international airport in central Mexico. Presented at the Mexican president's morning press conference in September 2025, it carries USD 4.8 billion of planned investment and up to 900 MW of critical IT load, with initial power secured for a first 200 MW. CloudHQ's own campus page lists a smaller 360 MW and readiness within 2027. Reports disagree on whether a tenant lease is signed and whether building work has begun, and no 2026 progress report was found.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"eb3a316f-cdae-55ad-b88b-08ed42e7c6ed","s2":"284caabe-4de1-56e5-af68-2dad3ffdba21","s3":"240ff090-6815-5cab-942c-af184e725d45","s4":"0cb2d25c-611d-5bdf-9af0-71547a3b740e","s5":"8c6396a6-ca07-52f9-a0fc-f730347ffb4e"},"source_file":"datacenters/projects/cloudhq-queretaro.json","source_record_id":"cloudhq-queretaro","source_record_sha256":"e5fc1c4b95552e1f066ffad711ea763302ef3b9f31617b210adb0554fb9d29f9","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5fd2c88c37f9c7bee7bffdc8b8a21dea3b560a1ceaf3fbdb0c169bd91f2e3224"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9209936dfd95900f78c3/#project-a7a29c6e-70aa-5f7b-b172-d1abe208715e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a7a29c6e-70aa-5f7b-b172-d1abe208715e.json
a848e771-2e45-55fb-8d43-db0885bb824f | curated:qscale-q01-levis-campus:building-b | vcc-site-0ecf05307f91c1e40479 | curated:qscale-q01-levis-campus | QScale Q01 Building B | Canada | CA | 46.6762 | -71.3251 | Polygon | campus | cross_source_overlay | openstreetmap_named_addressed_facility_polygon_as_campus_locator | reviewed_openstreetmap_named_addressed_qscale_facility_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for one named QScale data-centre building at Q01's exact first-party address, used only to locate the Q01 campus. It is not the Building B footprint or centroid, the Q01 campus boundary, a parcel, a construction extent, or a survey-accuracy claim. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | 8dff3085-994d-5629-b19b-7f2f88c44967 | under_construction | 2026-06-04 | 131 | authoritative_physical_status_update | 43eab287-205f-5205-ac24-2c93dca605bd | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-06-04","base":60.0,"confidence":0.99,"evidence_id":"43eab287-205f-5205-ac24-2c93dca605bd","high":60.0,"low":60.0,"method":"reported","metric":"critical_it_mw","notes":"Directly labeled IT-capacity design figure; no present-load or operational-capacity claim.","stage":"design","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.qscale.com/news/q01-building-b-60mw-ai-ready-infrastructure | https://www.openstreetmap.org/way/1171439340 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ecf05307f91c1e40479/#project-a848e771-2e45-55fb-8d43-db0885bb824f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a848e771-2e45-55fb-8d43-db0885bb824f.json
a8c0727c-ed59-5641-8856-e4eac08a5cf0 | imported:semiconductor-atlas:vantage-villanueva-de-gallego | vcc-site-028ea637886484fbc894 | imported:semiconductor-atlas:vantage-villanueva-de-gallego | Vantage Data Centers Villanueva de Gállego campus | Spain | ES | 41.767 | -0.817 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from the Villanueva de Gállego Wikipedia article. Sources place the site south of the town along the A-23 (Huesca motorway), opposite the San Miguel industrial estate and close to the Universidad San Jorge campus; no parcel boundary is published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 25e8d6e9-275e-55fb-ad03-97523dd3b542 | announced | 2026-03-20 | 207 | imported_documented_status | c49f287a-0e2b-5d26-becc-7d6e0116c6f5 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"62db032c-a09e-54f1-8002-e497e12b40bb","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-villanueva-de-gallego"},{"evidence_id":"25e8d6e9-275e-55fb-ad03-97523dd3b542","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-villanueva-de-gallego"},{"evidence_id":"c49f287a-0e2b-5d26-becc-7d6e0116c6f5","notes":null,"party":"Vantage Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-villanueva-de-gallego"},{"evidence_id":"62db032c-a09e-54f1-8002-e497e12b40bb","notes":"Aragonese partner company promoting the project with Vantage; elDiario.es says it is made up of Atalaya Generación Eólica and Posidonia Inversiones, and Libertad Digital describes the campus as part of an eco-industrial park it promotes.","party":"Desarrollos Ecoindustriales La Cartuja","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-villanueva-de-gallego"},{"evidence_id":"25e8d6e9-275e-55fb-ad03-97523dd3b542","notes":"Aragonese partner company promoting the project with Vantage; elDiario.es says it is made up of Atalaya Generación Eólica and Posidonia Inversiones, and Libertad Digital describes the campus as part of an eco-industrial park it promotes.","party":"Desarrollos Ecoindustriales La Cartuja","relationship_scope":"unknown","role":"developer","source_record_id":"vantage-villanueva-de-gallego"},{"evidence_id":"25e8d6e9-275e-55fb-ad03-97523dd3b542","notes":"Reported to have granted 90 MW of electricity supply for the project.","party":"Endesa","relationship_scope":"unknown","role":"utility","source_record_id":"vantage-villanueva-de-gallego"},{"evidence_id":"62db032c-a09e-54f1-8002-e497e12b40bb","notes":"Received the general-interest request in May 2025 and approved a Declaración de Interés General de Aragón (DIGA) for the project in September 2025.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"vantage-villanueva-de-gallego"},{"evidence_id":"25e8d6e9-275e-55fb-ad03-97523dd3b542","notes":"Received the general-interest request in May 2025 and approved a Declaración de Interés General de Aragón (DIGA) for the project in September 2025.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"vantage-villanueva-de-gallego"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.elespanol.com/aragon/economia/20260320/sacara-vantage-metros-cubicos-agua-necesita-centros-datos-villanueva-gallego/1003744176774_0.html | https://www.libertaddigital.com/espana/2025-09-12/azcon-anuncia-una-inversion-de-3-200-millones-para-un-centro-de-datos-de-vantage-en-aragon-7294927/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Vantage Data Centers Villanueva de Gállego campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"vantage-villanueva-de-gallego"},"record":{"aliases":["Vantage Zaragoza"],"id":"vantage-villanueva-de-gallego","last_reviewed":"2026-10-09","location":{"admin1":"Aragón","admin2":"Zaragoza","country":"ES","lat":41.767,"locality":"Villanueva de Gállego","lon":-0.817,"note":"Town coordinates from the Villanueva de Gállego Wikipedia article. Sources place the site south of the town along the A-23 (Huesca motorway), opposite the San Miguel industrial estate and close to the Universidad San Jorge campus; no parcel boundary is published.","precision":"locality","source_ids":["s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-09-12","basis":"announced","metric":"investment","note":"Announced by the president of Aragón when the DIGA was approved; elDiario.es had reported in May 2025 a joint investment above this amount.","qualifier":"exact","source_ids":["s1","s2"],"unit":"EUR","value":3200000000},{"applies_to":"campus","as_of":"2025-09-12","basis":"contracted","metric":"power_capacity","note":"Electricity supply reported as already granted through Endesa; no planned full build-out capacity in MW was found.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":90},{"applies_to":"campus","as_of":"2025-09-12","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2"],"unit":"hectares","value":40},{"applies_to":"campus","as_of":"2026-03-20","basis":"reported","metric":"land_area","note":"Later figure from El Español's account of the environmental filing; it differs from the 40 hectares reported in 2025.","qualifier":"approximately","source_ids":["s3"],"unit":"hectares","value":48},{"applies_to":"campus","as_of":"2026-03-20","basis":"planned","metric":"buildings","note":"Data buildings; work would begin with site urbanisation, the substation and the first building, with the rest in later phases.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":8},{"applies_to":"phase","as_of":"2025-09-12","basis":"planned","metric":"jobs_construction","note":"Libertad Digital adds 600 to 750 workers a year from the fourth year to the end of the decade.","phase_label":"First three years of construction","qualifier":"exact","source_ids":["s2"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2025-09-12","basis":"planned","metric":"jobs_permanent","note":"Direct jobs at full operation, starting from about 180 in the first three years.","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":520}],"milestones":[{"date":"2025-05","event":"announced","kind":"actual","note":"The project became public in May 2025, when the promoters asked the Aragón government on 14 May to declare it of general interest.","source_ids":["s1"]},{"date":"2025-09","event":"other","kind":"actual","note":"The Aragón Governing Council approved a DIGA (declaration of general interest) for the project.","source_ids":["s2"]},{"date":"2026","event":"construction_started","kind":"planned","note":"In May 2025 elDiario.es reported construction was planned to start in summer 2026; in March 2026 the project was still awaiting authorisation.","source_ids":["s1"]}],"name":"Vantage Data Centers Villanueva de Gállego campus","notes":"Accounts of the layout differ: elDiario.es (May 2025) described three data centers, while El Español (March 2026) describes one campus of eight data buildings to reach full operation in about a decade. El Español reports the initial filing estimates about 5,000 cubic metres of water a year, mostly for staff, with closed-loop cooling. Amazon Web Services already runs a campus in the same town. No Vantage or government primary release was opened; the DIGA should be checked in the Boletín Oficial de Aragón.","parties":[{"name":"Vantage Data Centers","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Desarrollos Ecoindustriales La Cartuja","note":"Aragonese partner company promoting the project with Vantage; elDiario.es says it is made up of Atalaya Generación Eólica and Posidonia Inversiones, and Libertad Digital describes the campus as part of an eco-industrial park it promotes.","role":"developer","source_ids":["s1","s2"]},{"name":"Endesa","note":"Reported to have granted 90 MW of electricity supply for the project.","role":"utility","source_ids":["s2"]},{"name":"Gobierno de Aragón","note":"Received the general-interest request in May 2025 and approved a Declaración de Interés General de Aragón (DIGA) for the project in September 2025.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"90 MW of supply reported as granted through Endesa.","source_ids":["s2"],"type":"grid"},{"description":"The promoters plan to integrate local wind generation.","source_ids":["s2"],"type":"wind"},{"description":"The promoters plan to integrate local photovoltaic generation.","source_ids":["s2"],"type":"solar"},{"description":"Energy storage systems are part of the stated plan.","source_ids":["s2"],"type":"battery_storage"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260211144613/https://www.eldiario.es/aragon/politica/gigante-data-centers-amigo-trump-desembarca-zaragoza-aliado-empresarios-aragoneses_1_12301095.html","id":"s1","published":"2025-05-15","publisher":"elDiario.es","title":"Un gigante de los 'data centers' ligado a un amigo de Trump desembarca en Zaragoza aliado con empresarios aragoneses","type":"news","url":"https://www.eldiario.es/aragon/politica/gigante-data-centers-amigo-trump-desembarca-zaragoza-aliado-empresarios-aragoneses_1_12301095.html"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-12","publisher":"Libertad Digital","title":"Vantage levantará un centro de datos de hiperescala en Aragón con 3.200 millones de inversión","type":"news","url":"https://www.libertaddigital.com/espana/2025-09-12/azcon-anuncia-una-inversion-de-3-200-millones-para-un-centro-de-datos-de-vantage-en-aragon-7294927/"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-20","publisher":"El Español","title":"¿De dónde sacará Vantage los 5.000 metros cúbicos de agua que necesita para sus centros de datos en Villanueva de Gállego?","type":"news","url":"https://www.elespanol.com/aragon/economia/20260320/sacara-vantage-metros-cubicos-agua-necesita-centros-datos-villanueva-gallego/1003744176774_0.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003063012/https://en.wikipedia.org/wiki/Villanueva_de_G%C3%A1llego","id":"s4","published":null,"publisher":"Wikipedia","title":"Villanueva de Gállego","type":"other","url":"https://en.wikipedia.org/wiki/Villanueva_de_G%C3%A1llego"}],"status":"announced","status_as_of":"2026-03-20","status_source_ids":["s3"],"summary":"Planned hyperscale data center campus by US operator Vantage Data Centers with the Aragonese company Desarrollos Ecoindustriales La Cartuja, on roughly 40 to 48 hectares of industrial land south of Villanueva de Gállego (Zaragoza), beside the A-23 motorway near Universidad San Jorge. The partners asked for regional general-interest status in May 2025, and the Aragón government approved it in September 2025 for a EUR 3.2 billion investment over ten years in five phases, with 90 MW of supply already granted through Endesa. In March 2026 the project was still seeking authorisation, with initial documents filed with the regional environmental agency (Inaga) and eight data buildings planned.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"62db032c-a09e-54f1-8002-e497e12b40bb","s2":"25e8d6e9-275e-55fb-ad03-97523dd3b542","s3":"c49f287a-0e2b-5d26-becc-7d6e0116c6f5","s4":"f98ab74b-8bbd-58d6-8a40-1c521c23f305"},"source_file":"datacenters/projects/vantage-villanueva-de-gallego.json","source_record_id":"vantage-villanueva-de-gallego","source_record_sha256":"0e2845a71c98adb1675b74a6066bea2e001875aea020628c790e01910e33e9b7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"c78936918e73e197adf4b09e48719063801a700d4cc4e2226281758b9fdc36de"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-028ea637886484fbc894/#project-a8c0727c-ed59-5641-8856-e4eac08a5cf0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a8c0727c-ed59-5641-8856-e4eac08a5cf0.json
a95db60b-fb99-5f16-ad4a-c763e4714041 | imported:semiconductor-atlas:lambda-kansas-city | vcc-site-e305b394a907f57f2639 | imported:semiconductor-atlas:lambda-kansas-city | Lambda Kansas City AI factory | United States | US | 39.0997 | -94.5783 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City centroid from Wikipedia (s2). The announcement places the facility in the Northland part of Kansas City but gives no address, so the point is not at the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6846ad0f-2ca2-53a2-a083-33bef62ed168 | announced | 2025-10-28 | 350 | imported_documented_status | 6846ad0f-2ca2-53a2-a083-33bef62ed168 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6846ad0f-2ca2-53a2-a083-33bef62ed168","notes":null,"party":"Lambda","relationship_scope":"unknown","role":"developer","source_record_id":"lambda-kansas-city"},{"evidence_id":"6846ad0f-2ca2-53a2-a083-33bef62ed168","notes":null,"party":"Lambda","relationship_scope":"unknown","role":"operator","source_record_id":"lambda-kansas-city"},{"evidence_id":"6846ad0f-2ca2-53a2-a083-33bef62ed168","notes":"Described as the sole tenant; the capacity serves one unnamed Lambda customer.","party":"Lambda","relationship_scope":"unknown","role":"tenant","source_record_id":"lambda-kansas-city"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Lambda |  | Lambda |  | https://lambda.ai/blog/lambda-to-build-a-100mw-ai-factory-in-kansas-city-mo | https://lambda.ai/blog/lambda-to-build-a-100mw-ai-factory-in-kansas-city-mo | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Lambda Kansas City AI factory as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"lambda-kansas-city","source_relations":[{"reason":"Separate Lambda AI factory and Meta campus; coordinates are the same Kansas City civic location, not facility evidence.","relationship":"separate_named_developments","source_id":"meta-kansas-city"}]},"record":{"aliases":[],"id":"lambda-kansas-city","last_reviewed":"2026-10-09","location":{"admin1":"Missouri","country":"US","lat":39.0997,"locality":"Kansas City","lon":-94.5783,"note":"City centroid from Wikipedia (s2). The announcement places the facility in the Northland part of Kansas City but gives no address, so the point is not at the site.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"phase","as_of":"2025-10-28","basis":"planned","metric":"power_capacity","phase_label":"Initial launch","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":24},{"applies_to":"campus","as_of":"2025-10-28","basis":"planned","metric":"power_capacity","note":"Described as potential future scale.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":100},{"accelerator_model":"NVIDIA Blackwell Ultra","applies_to":"phase","as_of":"2025-10-28","basis":"planned","metric":"accelerators","note":"The footprint was expected to double over time.","phase_label":"Initial launch","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":10000}],"milestones":[{"date":"2025-10-28","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2026","event":"first_operational","kind":"planned","note":"Launch was expected in early 2026; no confirmation of opening was found.","source_ids":["s1"]}],"name":"Lambda Kansas City AI factory","parties":[{"name":"Lambda","role":"developer","source_ids":["s1"]},{"name":"Lambda","role":"operator","source_ids":["s1"]},{"name":"Lambda","note":"Described as the sole tenant; the capacity serves one unnamed Lambda customer.","role":"tenant","source_ids":["s1"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-10-28","publisher":"Lambda","title":"Lambda Doubles Down on Midwest Expansion, To Build AI Factory in Kansas City, MO","type":"company","url":"https://lambda.ai/blog/lambda-to-build-a-100mw-ai-factory-in-kansas-city-mo"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004233043/https://en.wikipedia.org/wiki/Kansas_City,_Missouri","id":"s2","published":null,"publisher":"Wikipedia","title":"Kansas City, Missouri","type":"other","url":"https://en.wikipedia.org/wiki/Kansas_City,_Missouri"}],"status":"announced","status_as_of":"2025-10-28","status_source_ids":["s1"],"summary":"Lambda announced in October 2025 that it would redevelop a vacant facility built in 2009 in the Northland area of Kansas City, Missouri, into an AI factory, as developer, operator and sole tenant. The site was to launch in early 2026 with 24 MW and more than 10,000 NVIDIA Blackwell Ultra GPUs serving one unnamed customer under a multi-year contract for AI training and inference, with potential to grow beyond 100 MW. No investment figure or street address was disclosed, and no later update on the site's opening was found.","workloads":["ai_training","ai_inference"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6846ad0f-2ca2-53a2-a083-33bef62ed168","s2":"31471ce2-024f-586a-9689-ede2521339fd"},"source_file":"datacenters/projects/lambda-kansas-city.json","source_record_id":"lambda-kansas-city","source_record_sha256":"06a230bf76ea131b0cc128f6fbd6ab1c196fffdbc6c4dafe3e65d10695f74a6f","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"cd25d4a17c604d3f2f290c09e8314a008e2475ea9db2f828366e5bc71b204ee1"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e305b394a907f57f2639/#project-a95db60b-fb99-5f16-ad4a-c763e4714041 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a95db60b-fb99-5f16-ad4a-c763e4714041.json
a9ca22ae-d872-5122-a052-e5c9ec410abd | imported:semiconductor-atlas:microsoft-aragon-la-muela | vcc-site-155a753d051b04508b1c | imported:semiconductor-atlas:microsoft-aragon-la-muela | Microsoft La Muela datacenter campus (Aragón) | Spain | ES | 41.6068 | -1.0832 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Nominatim point for the Polígono Industrial Centrovía in La Muela, which sources name as the site area (the campus involves an expansion of the estate); the 146-hectare boundary is not published in the sources. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | aeaecec7-38ef-58cd-888d-4c1a9f97d17c | announced | 2026-09-04 | 39 | imported_documented_status | a7ef4557-e00f-511f-bd0b-6c2e3fb29344 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"aeaecec7-38ef-58cd-888d-4c1a9f97d17c","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-la-muela"},{"evidence_id":"2c514e1e-08fd-5e9d-b21d-14694ef236cc","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-la-muela"},{"evidence_id":"16bd796f-400b-51f9-be5b-59149c0107cc","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-la-muela"},{"evidence_id":"aeaecec7-38ef-58cd-888d-4c1a9f97d17c","notes":"Declared the project of general interest and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-la-muela"},{"evidence_id":"2c514e1e-08fd-5e9d-b21d-14694ef236cc","notes":"Declared the project of general interest and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-la-muela"},{"evidence_id":"16bd796f-400b-51f9-be5b-59149c0107cc","notes":"Declared the project of general interest and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-la-muela"},{"evidence_id":"a7ef4557-e00f-511f-bd0b-6c2e3fb29344","notes":"Agreed to sell Microsoft the land needed to complete the expansion of the Centrovía industrial estate.","party":"Ayuntamiento de La Muela","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-la-muela"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.eldiario.es/aragon/economia/prioridad-extranjera-pp-vox-aragon-expropian-suelo-centro-datos-microsoft-2-euros-metro_1_13417031.html | https://www.vozpopuli.com/economia/aragon-centro-datos-microsoft-inversion-2000-millones.html | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft La Muela datacenter campus (Aragón) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-aragon-la-muela"},"record":{"aliases":["Microsoft Centrovía La Muela campus"],"id":"microsoft-aragon-la-muela","last_reviewed":"2026-10-09","location":{"admin1":"Aragón","admin2":"Zaragoza","country":"ES","lat":41.6068,"locality":"La Muela","lon":-1.0832,"note":"Nominatim point for the Polígono Industrial Centrovía in La Muela, which sources name as the site area (the campus involves an expansion of the estate); the 146-hectare boundary is not published in the sources.","precision":"approximate_site","source_ids":["s1","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-14","basis":"reported","metric":"investment","note":"Per-site figure in the PIGA as reported by elDiario.es; program-level totals are described in the record notes.","qualifier":"exact","source_ids":["s2"],"unit":"EUR","value":2179000000},{"applies_to":"phase","as_of":"2025-11-14","basis":"planned","metric":"power_capacity","note":"elDiario.es says Microsoft has this power secured for the first phase at each campus.","phase_label":"First phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":50},{"applies_to":"campus","as_of":"2025-11-14","basis":"planned","metric":"power_capacity","note":"Second-phase aspiration per campus in the PIGA, as reported by elDiario.es; Forbes gives 250-300 MW per campus over about ten years.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s2","s3"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-11-14","basis":"planned","metric":"land_area","qualifier":"exact","source_ids":["s2"],"unit":"hectares","value":146}],"milestones":[{"date":"2023","event":"other","kind":"actual","note":"Vozpópuli and EFE report that the Centrovía site in La Muela received general-interest status in the final months of 2023.","source_ids":["s1"]},{"date":"2025-11-14","event":"other","kind":"actual","note":"Initial approval of the PIGA Región MSFT plan covering La Muela, Villamayor de Gállego and Zaragoza, opening a public information period.","source_ids":["s2","s3"]},{"date":"2026-07-30","event":"other","kind":"actual","note":"A modification of the PIGA was published in the Boletín Oficial de Aragón for public comment.","source_ids":["s5"]},{"date":"2030","event":"first_operational","kind":"planned","note":"Forbes reported the first phase was expected to operate from 2030.","source_ids":["s3"]}],"name":"Microsoft La Muela datacenter campus (Aragón)","notes":"Program-level figures differ by scope and date: EUR 6.6 billion across three sites in 2024 (La Cartuja, Centrovía and Villamayor de Gállego), EUR 5.356 billion across the three PIGA campuses and a wider EUR 10 billion plan including land and servers (November 2025), and EUR 2.9 billion across three campuses (August 2026). Only the per-site PIGA figure is recorded as a metric. No government primary source was opened; Boletín Oficial de Aragón entries should be added when available.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Gobierno de Aragón","note":"Declared the project of general interest and is processing the PIGA regional plan.","role":"government","source_ids":["s1","s2","s3"]},{"name":"Ayuntamiento de La Muela","note":"Agreed to sell Microsoft the land needed to complete the expansion of the Centrovía industrial estate.","role":"government","source_ids":["s4"]}],"power_sources":[{"description":"Grid supply through a new substation (named Plaza) starting at 132 kV with a later upgrade to 220 kV.","source_ids":["s2"],"type":"grid"}],"related_ids":["microsoft-aragon-villamayor-de-gallego","microsoft-aragon-zaragoza-puerto-venecia"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-07-03","publisher":"Vozpópuli","title":"Aragón da luz verde a un centro de datos de Microsoft con una inversión de 2.000 millones","type":"news","url":"https://www.vozpopuli.com/economia/aragon-centro-datos-microsoft-inversion-2000-millones.html"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-14","publisher":"elDiario.es","title":"Microsoft avanza con su red de centros de datos en Zaragoza, donde proyecta una de sus mayores regiones en Europa","type":"news","url":"https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-14","publisher":"Forbes España","title":"Microsoft obtiene luz verde para su ambicioso proyecto de centros de datos en Aragón","type":"news","url":"https://forbes.es/empresas/828243/microsoft-obtiene-luz-verde-para-su-ambicioso-proyecto-de-centros-de-datos-en-aragon/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006005223/https://www.eldiario.es/aragon/economia/prioridad-extranjera-pp-vox-aragon-expropian-suelo-centro-datos-microsoft-2-euros-metro_1_13417031.html","id":"s4","published":"2026-08-02","publisher":"elDiario.es","title":"La 'prioridad extranjera' para PP y Vox en Aragón: expropian suelo para un centro de datos de Microsoft a 2 euros el metro","type":"news","url":"https://www.eldiario.es/aragon/economia/prioridad-extranjera-pp-vox-aragon-expropian-suelo-centro-datos-microsoft-2-euros-metro_1_13417031.html"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-04","publisher":"elDiario.es","title":"ZeC presenta 25 alegaciones al plan de Microsoft y exige a la alcaldesa de Zaragoza paralizar un centro de datos","type":"news","url":"https://www.eldiario.es/aragon/politica/zec-presenta-25-alegaciones-plan-microsoft-exige-alcaldesa-zaragoza-paralizar-centro-datos_1_13487405.html"}],"status":"announced","status_as_of":"2026-09-04","status_source_ids":["s4","s5"],"summary":"Planned Microsoft datacenter campus at the Centrovía industrial estate in La Muela, west of Zaragoza, the largest by area and investment of the three campuses in Microsoft's Aragón plan. The site was declared of general interest in late 2023. The regional plan (PIGA Región MSFT), given initial approval in November 2025, assigns it 146 hectares and about EUR 2.18 billion, with 50 MW secured for a first phase and up to 300 MW sought later through a new substation. The plan still lacked final approval in August 2026, and a modified version went out for public comment in July 2026. Forbes reported first operation was expected from 2030.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"aeaecec7-38ef-58cd-888d-4c1a9f97d17c","s2":"2c514e1e-08fd-5e9d-b21d-14694ef236cc","s3":"16bd796f-400b-51f9-be5b-59149c0107cc","s4":"a7ef4557-e00f-511f-bd0b-6c2e3fb29344","s5":"8973fdca-8650-59ad-a4a6-72644fd4ee3c"},"source_file":"datacenters/projects/microsoft-aragon-la-muela.json","source_record_id":"microsoft-aragon-la-muela","source_record_sha256":"6b52e7ee1fc0d0bf161b9378e47ebccbfedbc6afc0fbcb18c225c7fcc32a53b3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"efd0447e6f6308425b1d0a4001efc814f2cfaba03698f5b737d43c892ce434e4"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-155a753d051b04508b1c/#project-a9ca22ae-d872-5122-a052-e5c9ec410abd | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/a9ca22ae-d872-5122-a052-e5c9ec410abd.json
aa2dc8a4-52d8-5519-b23a-2ff0313db9e3 | curated:merlin-edged-madrid-getafe-ii-campus:mad02-site-preparation | vcc-site-5c9b661562b39e724fe6 | curated:merlin-edged-madrid-getafe-ii-campus | MERLIN Edged MAD02 Site Preparation | Spain | ES | 40.3114 | -3.7068 | Point | campus | literal_operator_specification_site_point | preserve_MAD02_specification_latitude_longitude_bound_to_Fundidores2_and_Getafe2_parent_page | operator_campus_reference_point | official_source | campus_locator | Exact operator-published MAD02 site-coordinate point at Fundidores2. Campus locator only, not an entrance, surveyed boundary, building footprint or active-demolition extent. Distinct from Getafe1 at Fundidores40. The MAD-GETII report code match is explicit analyst identity inference. |  | Neither selected source supplies quantitative positional accuracy or survey provenance. Decimal digits do not establish accuracy. | 2bd9d01f-b34d-5ac0-94b8-8dd17c9543cf | site_preparation | 2026-06-30 | 105 | authoritative_physical_status_update | 1c80fcc9-5d29-5196-9ecf-9ed583c6f1f4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ir.merlinproperties.com/wp-content/uploads/2026/07/RI-6M26-MERLIN-Properties_eng.pdf | https://cdn.prod.website-files.com/612d5118cc3229538b508294/68bf2b6a1186eb51f6c433e8_MAD02_Spec%20Sheet_250730_Digital.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5c9b661562b39e724fe6/#project-aa2dc8a4-52d8-5519-b23a-2ff0313db9e3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/aa2dc8a4-52d8-5519-b23a-2ff0313db9e3.json
aa93c84a-17d6-5092-bf57-686f7e1ab4a4 | curated:stt-jakarta-data-centre-campus:stt-jakarta-3 | vcc-site-57a103a9de718a95ae14 | curated:stt-jakarta-data-centre-campus | STT Jakarta 3 | Indonesia | ID | -6.374 | 107.2011 | Polygon | campus | cross_source_overlay | openstreetmap_exactly_named_stt_jakarta_1_facility_polygon_as_shared_campus_locator | reviewed_openstreetmap_stt_jakarta_1_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for STT Jakarta 1, used only as one known-building anchor for the shared campus targeted by STT Jakarta 3. It is not the Jakarta 3 location or footprint, the campus boundary, a parcel, a construction extent, or a survey-accuracy claim. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral or survey geometry. | f16b034b-60d8-5826-841a-1acaa849a930 | shell | 2026-06-10 | 125 | authoritative_physical_status_update | a251b3bb-e0bc-56d3-b89a-97914d692f5d | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-16","base":24.0,"confidence":0.99,"evidence_id":"09530596-5c39-5d1c-881f-6993227a10d1","high":24.0,"low":24.0,"method":"reported","metric":"critical_it_mw","notes":"Planned STT Jakarta 3 critical-IT design capacity, preserving the factsheet’s ‘Up to 24MW of IT Load’ maximum scope. It is not current load, gross facility power, grid draw, generation, annual energy, or measured consumption.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.sttelemediagdc.com/newsroom/stt-gdc-accelerates-jakarta-campus-expansion-power-indonesia-ai-and-digital-ambitions | https://www.openstreetmap.org/way/1533569836 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-57a103a9de718a95ae14/#project-aa93c84a-17d6-5092-bf57-686f7e1ab4a4 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/aa93c84a-17d6-5092-bf57-686f7e1ab4a4.json
abb5573d-8211-5781-be5c-50c8b27d4fe8 | imported:semiconductor-atlas:airtrunk-jhb1-johor | vcc-site-b83e933ca77e513685ed | imported:semiconductor-atlas:airtrunk-jhb1-johor | AirTrunk JHB1 | Malaysia | MY | 1.5367 | 103.7206 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | AirTrunk places JHB1 in Johor Bahru without an address; coordinates are the OpenStreetMap Nominatim centroid of the Johor Bahru administrative area, which includes Iskandar Puteri. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d520bc9c-46a1-5e00-8e7a-5cc2803873fd | partially_operational | 2024-08-09 | 795 | imported_documented_status | d520bc9c-46a1-5e00-8e7a-5cc2803873fd | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d520bc9c-46a1-5e00-8e7a-5cc2803873fd","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb1-johor"},{"evidence_id":"446b8893-6618-5fbf-a993-a81dc7449ed2","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb1-johor"},{"evidence_id":"d2ee237b-6973-5394-b481-af5b95406e38","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb1-johor"},{"evidence_id":"d520bc9c-46a1-5e00-8e7a-5cc2803873fd","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"operator","source_record_id":"airtrunk-jhb1-johor"},{"evidence_id":"d520bc9c-46a1-5e00-8e7a-5cc2803873fd","notes":"Counterparty to a 30 MW renewable virtual power purchase agreement cited in the opening announcement.","party":"ib vogt","relationship_scope":"unknown","role":"power_supplier","source_record_id":"airtrunk-jhb1-johor"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | AirTrunk |  |  |  | https://airtrunk.com/airtrunk-opens-ai-ready-data-centre-in-malaysia-accelerating-innovation-and-the-energy-transition/ | https://airtrunk.com/airtrunk-opens-ai-ready-data-centre-in-malaysia-accelerating-innovation-and-the-energy-transition/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AirTrunk JHB1 as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"airtrunk-jhb1-johor"},"record":{"aliases":["JHB1 Johor"],"id":"airtrunk-jhb1-johor","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Johor Bahru District","country":"MY","lat":1.5367,"lon":103.7206,"note":"AirTrunk places JHB1 in Johor Bahru without an address; coordinates are the OpenStreetMap Nominatim centroid of the Johor Bahru administrative area, which includes Iskandar Puteri.","precision":"admin2","source_ids":["s1"]},"metrics":[{"applies_to":"phase","as_of":"2024-07-30","basis":"operational","metric":"power_capacity","phase_label":"Initial phases at opening","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":50},{"applies_to":"phase","as_of":"2024-08-09","basis":"under_construction","metric":"power_capacity","note":"Remaining phases to be delivered over about 18 months, with an initial tranche by mid-2025.","phase_label":"2024 expansion","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2024-07-30","basis":"planned","metric":"power_capacity","note":"The opening announcement describes JHB1 as a 150 MW campus; later releases say more than 150 MW.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2025-02-12","basis":"planned","metric":"power_capacity","note":"Given as total campus capacity after the 100 MW expansion; AirTrunk does not say whether it is IT load.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s2","s3"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2024-07-30","basis":"reported","metric":"land_area","qualifier":"more_than","source_ids":["s1"],"unit":"hectares","value":10.3}],"milestones":[{"date":"2024-07","event":"first_operational","kind":"actual","note":"Opening ceremony announced 30 July 2024.","source_ids":["s1","s3"]},{"date":"2024-08-09","event":"expansion_announced","kind":"actual","note":"100 MW expansion underway.","source_ids":["s2"]},{"date":"2026-04-30","event":"other","kind":"actual","note":"AirTrunk said JHB1 and JHB2 were almost 100% contracted; it did not say whether all JHB1 phases were complete.","source_ids":["s4"]}],"name":"AirTrunk JHB1","parties":[{"name":"AirTrunk","role":"developer","source_ids":["s1","s2","s3"]},{"name":"AirTrunk","role":"operator","source_ids":["s1"]},{"name":"ib vogt","note":"Counterparty to a 30 MW renewable virtual power purchase agreement cited in the opening announcement.","role":"power_supplier","source_ids":["s1"]}],"power_sources":[{"description":"Solar-ready roof able to provide over 1 MW for the opening phase.","source_ids":["s1"],"type":"solar"},{"description":"30 MW renewable virtual power purchase agreement with ib vogt under Malaysia's Corporate Green Power Programme.","source_ids":["s1","s3"],"type":"other"}],"related_ids":["airtrunk-jhb2-iskandar-puteri"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260611075647/https://airtrunk.com/airtrunk-opens-ai-ready-data-centre-in-malaysia-accelerating-innovation-and-the-energy-transition/","id":"s1","published":"2024-07-30","publisher":"AirTrunk","title":"AirTrunk opens AI-ready data centre in Malaysia, accelerating innovation and the energy transition","type":"company","url":"https://airtrunk.com/airtrunk-opens-ai-ready-data-centre-in-malaysia-accelerating-innovation-and-the-energy-transition/"},{"accessed":"2026-10-09","id":"s2","published":"2024-08-09","publisher":"AirTrunk","title":"100MW expansion underway at AirTrunk JHB1","type":"company","url":"https://airtrunk.com/airtrunk-jhb1100mw-expansion-underway/"},{"accessed":"2026-10-09","id":"s3","published":"2025-02-12","publisher":"AirTrunk","title":"AirTrunk grows Malaysia platform with second cloud and AI-ready data centre in Johor","type":"company","url":"https://airtrunk.com/airtrunk-scales-up-in-malaysia-with-announcement-of-second-malaysia-hyperscale-data-centre-jhb2/"},{"accessed":"2026-10-09","id":"s4","published":"2026-04-30","publisher":"AirTrunk","title":"AirTrunk doubles down in Malaysia with two new hyperscale campuses in Johor Bahru","type":"company","url":"https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/"}],"status":"partially_operational","status_as_of":"2024-08-09","status_source_ids":["s1","s2"],"summary":"JHB1 is AirTrunk's first hyperscale data center campus in Malaysia, located in Johor Bahru on more than 10 hectares. It opened in July 2024 with initial phases of over 50 MW for large technology customers, and the following month AirTrunk began a 100 MW expansion to take the campus past 150 MW, with remaining phases due over about 18 months. AirTrunk said in April 2026 that JHB1 and its sister campus JHB2 were almost fully contracted. Renewable supply includes a solar-ready roof and a 30 MW virtual power purchase agreement with ib vogt.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d520bc9c-46a1-5e00-8e7a-5cc2803873fd","s2":"446b8893-6618-5fbf-a993-a81dc7449ed2","s3":"d2ee237b-6973-5394-b481-af5b95406e38","s4":"c154a158-2c46-5534-8b0b-aa846cb05b1c"},"source_file":"datacenters/projects/airtrunk-jhb1-johor.json","source_record_id":"airtrunk-jhb1-johor","source_record_sha256":"55ea527fa7e6faaf7264cdee8b164b00422f68c71f0e95130c76c3d51367468d","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5b578168c8367fe8d6fe866aaa05ffd0ece5be1a9e4a67e907ed93babaeab172"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b83e933ca77e513685ed/#project-abb5573d-8211-5781-be5c-50c8b27d4fe8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/abb5573d-8211-5781-be5c-50c8b27d4fe8.json
acf9eda7-3b44-5e9b-8c40-62783a7e0aa0 | curated:cra-prague-gateway-data-center-campus:current-campus-build | vcc-site-418907144d1bd1426055 | curated:cra-prague-gateway-data-center-campus | CRA Prague Gateway DC Current Campus Build | Czechia | CZ | 49.9482 | 14.3678 | Point | campus | official_parcel_union_point_on_surface | cuzk_permit_named_parcel_union_as_campus_locator | official_parcels_as_campus_locator | official_source | campus_locator | A deterministic point on the union of two current official parcel geometries named by the permit. It locates the wider CRA site only and is not an official campus boundary, building or work footprint, entrance, surveyed project point, or horizontal-accuracy claim. |  | No project-applicable bounded horizontal accuracy was selected from CUZK. | 956fa5bf-63d8-55e6-80f8-60eeeeca386d | under_construction | 2026-08-20 | 54 | authoritative_physical_status_update | 3cb5d028-a110-558f-b9c3-69f22e0c699a | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/embed/feed/update/urn:li:activity:7496145983718969344 | https://ags.cuzk.gov.cz/arcgis/rest/services/RUIAN/MapServer/5/query?where=katastralniuzemi%3d660175+AND+%28%28cisloparcely%3d%27505%2f2%27+AND+druhcislovanikod%3d2%29+OR+%28cisloparcely%3d%27379%27+AND+druhcislovanikod%3d1%29%29&outFields=id%2ccisloparcely%2ckatastralniuzemi%2ckmenovecislo%2cpoddelenicisla%2cdruhcislovanikod%2cvymeraparcely%2cplatiod%2cplatido%2czdroj&returnGeometry=true&outSR=4326&f=geojson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-418907144d1bd1426055/#project-acf9eda7-3b44-5e9b-8c40-62783a7e0aa0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/acf9eda7-3b44-5e9b-8c40-62783a7e0aa0.json
ad57807a-f6b6-55f9-b26f-acd194e12880 | curated:flexential-hillsboro-starr-campus:hillsboro-5-current-build | vcc-site-45292d327405c32357bc | curated:flexential-hillsboro-starr-campus | Flexential Hillsboro 5 Current Build | United States | US | 45.5565 | -122.9394 | Point | campus | source_community_representative_point | exact_OSM_way1080170580_Nominatim_representative_lon_lat | named_community_building_reference_point | community_source | campus_locator | Exact H5-named, operator/address-bound OSM building representative point. Not a surveyed building footprint, campus boundary, construction extent, entrance or whole-campus centre. Neighboring H4/H3 and restricted municipal points unselected. |  | No source-specific numeric positional accuracy for community geometry/representative point. | f3fccadb-e01f-5545-9b50-2e655093f641 | under_construction | 2026-08-18 | 56 | authoritative_physical_status_update | 2a3a54fe-bcf3-5e51-ac21-8791ecef42ae | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.prnewswire.com/news-releases/flexential-secures-800-million-to-fund-data-center-development-across-four-high-growth-markets-302853453.html | https://nominatim.openstreetmap.org/lookup?osm_ids=W1080170580&format=jsonv2&addressdetails=1&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-45292d327405c32357bc/#project-ad57807a-f6b6-55f9-b26f-acd194e12880 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ad57807a-f6b6-55f9-b26f-acd194e12880.json
ad5f9b2b-80bf-5580-92f2-0f53473c882d | curated:nextdc-m2-melbourne:incremental-in-progress-fit-out | vcc-site-6c4336501258c6139275 | curated:nextdc-m2-melbourne | NEXTDC M2 Incremental In-Progress Fit-Out | Australia | AU | -37.708 | 144.8757 | Point | campus | operator_published_destination_coordinate | copy_M2_facility_href_destination_not_viewport | operator_campus_reference_point | official_source | campus_locator | The M2 facility's own operator-published directions URL supplies the destination at 75 Sharps Road. No Google page or third-party search result is selected. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate. |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | 69f903c5-00c1-557f-a61e-d7eaadb9ad04 | mep_electrical | 2026-06-30 | 105 | authoritative_physical_status_update | 43bd6a30-6bac-5500-afd1-74b0e425d6b0 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nextdc.com/hubfs/Financial%20Reports/FY26/FY26%20Results%20Announcement.pdf | https://www.nextdc.com/contact | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6c4336501258c6139275/#project-ad5f9b2b-80bf-5580-92f2-0f53473c882d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ad5f9b2b-80bf-5580-92f2-0f53473c882d.json
adc32529-cea1-5d06-86de-334e63433be6 | curated:borealis-blonduos-data-center-campus:expansion-current-build | vcc-site-0ed3e2f5c48bfda417a3 | curated:borealis-blonduos-data-center-campus | Borealis Blönduós Expansion Current Build | Iceland | IS | 65.6473 | -20.243 | Polygon | facility | cross_source_geometry | openstreetmap_borealis_blonduos_named_building_polygon_as_parent_campus_locator | reviewed_openstreetmap_borealis_blonduos_named_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for a named Borealis building at Blönduós, used only to locate the parent campus. It is not the 2026 expansion boundary, a complete campus boundary, an official parcel or planning boundary, or a current construction-progress extent. A first-party map link that resolves only to the Blönduós town/place is rejected as site geometry. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | b24c0246-2488-55e4-9022-3609124fd8c8 | under_construction | 2026-06-23 | 112 | authoritative_physical_status_update | bd494c0b-3936-5cc0-844a-67cd0db22812 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.landsvirkjun.com/news/borealis-and-landsvirkjun-sign-a-12-mw-power-purchasing-agreement | https://www.openstreetmap.org/way/1227173411 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ed3e2f5c48bfda417a3/#project-adc32529-cea1-5d06-86de-334e63433be6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/adc32529-cea1-5d06-86de-334e63433be6.json
ade90a9a-b55b-503e-a8b9-d2f8340a81d6 | imported:semiconductor-atlas:cipher-black-pearl | vcc-site-6bedc032f2f6fb914715 | curated:cipher-digital-black-pearl-wink-texas-data-center-campus | Cipher Black Pearl data center | United States | US | 31.7545 | -103.1541 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Filings place the facility in or near Wink but give no street address. Coordinates are the Wink town point from its Wikipedia article, which also gives the county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 4c64ca35-7a18-5662-ad69-696665683807 | partially_operational | 2026-08-04 | 70 | imported_documented_status | 5bc7254b-53ee-55b1-b5ec-22bc5a3e07d0 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"4c64ca35-7a18-5662-ad69-696665683807","notes":"Formerly Cipher Mining; develops the site through wholly owned subsidiaries Cipher Black Pearl LLC and Black Pearl Compute LLC.","party":"Cipher Digital (formerly Cipher Mining)","relationship_scope":"unknown","role":"developer","source_record_id":"cipher-black-pearl"},{"evidence_id":"5bc7254b-53ee-55b1-b5ec-22bc5a3e07d0","notes":"Formerly Cipher Mining; develops the site through wholly owned subsidiaries Cipher Black Pearl LLC and Black Pearl Compute LLC.","party":"Cipher Digital (formerly Cipher Mining)","relationship_scope":"unknown","role":"developer","source_record_id":"cipher-black-pearl"},{"evidence_id":"5c940a57-17e2-5adf-b1bb-cfb444c03cda","notes":"Formerly Cipher Mining; develops the site through wholly owned subsidiaries Cipher Black Pearl LLC and Black Pearl Compute LLC.","party":"Cipher Digital (formerly Cipher Mining)","relationship_scope":"unknown","role":"developer","source_record_id":"cipher-black-pearl"},{"evidence_id":"4c64ca35-7a18-5662-ad69-696665683807","notes":"The land is owned by a wholly owned Cipher subsidiary and the facility is described as wholly owned.","party":"Cipher Digital (formerly Cipher Mining)","relationship_scope":"unknown","role":"owner","source_record_id":"cipher-black-pearl"},{"evidence_id":"4c64ca35-7a18-5662-ad69-696665683807","notes":"Named as the Black Pearl lessee only in the 10-K (s1), which dates the 15-year lease of about 300 gross MW to both October and November 2025. The November 2025 release (s2) announces the AWS lease without naming the site, and the August 2026 updates refer to an unnamed investment-grade hyperscale tenant.","party":"Amazon Web Services","relationship_scope":"unknown","role":"tenant","source_record_id":"cipher-black-pearl"},{"evidence_id":"841a8da1-9f19-501b-9cb7-da7b2d2dc0ce","notes":"Named as the Black Pearl lessee only in the 10-K (s1), which dates the 15-year lease of about 300 gross MW to both October and November 2025. The November 2025 release (s2) announces the AWS lease without naming the site, and the August 2026 updates refer to an unnamed investment-grade hyperscale tenant.","party":"Amazon Web Services","relationship_scope":"unknown","role":"tenant","source_record_id":"cipher-black-pearl"},{"evidence_id":"4c64ca35-7a18-5662-ad69-696665683807","notes":"Cipher names Quanta as an engineering, construction and procurement partner for sites such as Black Pearl.","party":"Quanta Services","relationship_scope":"unknown","role":"builder","source_record_id":"cipher-black-pearl"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Cipher Digital (formerly Cipher Mining) |  |  | Amazon Web Services |  | https://www.sec.gov/Archives/edgar/data/1819989/000181998926000038/q226_earningsxprxdraftxvf.htm | https://www.sec.gov/Archives/edgar/data/1819989/000181998926000009/cifr-20251231.htm | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Cipher Black Pearl facility near Wink, with mining conversion, operating phase I and phase II. Existing record specifically selects AWS phase II current construction; campus partial operation does not complete phase II.","source_record_id":"cipher-black-pearl","target_physical_site_stable_key":"curated:cipher-digital-black-pearl-wink-texas-data-center-campus"},"record":{"aliases":["Black Pearl Facility","Black Pearl campus"],"id":"cipher-black-pearl","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Winkler County","country":"US","lat":31.7545,"locality":"Wink","lon":-103.1541,"note":"Filings place the facility in or near Wink but give no street address. Coordinates are the Wink town point from its Wikipedia article, which also gives the county.","precision":"locality","source_ids":["s1","s5","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-02-24","basis":"contracted","metric":"power_capacity","note":"Gross turnkey data center capacity leased to AWS, per the 10-K; the November 2025 release gives 300 MW. Cipher does not separate IT and facility load.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1","s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-02-24","basis":"permitted","metric":"power_capacity","note":"Approved interconnection capacity on the ERCOT grid.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2025-09","basis":"operational","metric":"power_capacity","note":"Mining capacity reached by September 2025; mining stopped in February 2026 for the AWS conversion.","phase_label":"Former bitcoin mining operation (2025 to February 2026)","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2026-02-24","basis":"acquired","metric":"land_area","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":75}],"milestones":[{"date":"2025-06","event":"first_operational","kind":"actual","note":"Bitcoin mining began at the site; this predates the AI/HPC conversion.","source_ids":["s1"]},{"date":"2025","event":"construction_started","kind":"actual","note":"Retrofit and development of the 300 MW data center began in 2025.","source_ids":["s1"]},{"date":"2025-11-03","event":"announced","kind":"actual","note":"Cipher announced the 15-year, roughly USD 5.5 billion AWS lease for 300 MW, without naming the site in the release.","source_ids":["s2"]},{"date":"2026-02","event":"other","kind":"actual","note":"Bitcoin mining at the site ceased, and the USD 2.0 billion Black Pearl notes offering closed on 2026-02-11.","source_ids":["s1","s5"]},{"date":"2026-08","event":"other","kind":"actual","note":"First data center capacity delivered to the tenant and rent began, about two months ahead of the original schedule after a lease amendment.","source_ids":["s3","s4"]},{"date":"2027-Q1","event":"fully_operational","kind":"planned","note":"Rent was expected to fully ramp by Q1 2027 when the final subphase is complete.","source_ids":["s1"]}],"name":"Cipher Black Pearl data center","notes":"The 10-K is the only source opened that names AWS as the Black Pearl lessee; the August 2026 releases refer to an unnamed investment-grade hyperscale tenant. Delivery moved forward: the 10-K targeted first rent by Q4 2026, and an amended lease brought first delivery to August 2026. In February 2026 subsidiary Black Pearl Compute LLC issued USD 2.0 billion of senior secured notes to fund the remaining facility cost, repay about USD 232.5 million of Cipher equity and fund reserves and fees; this is debt financing, not a disclosed project cost. The crypto_mining tag reflects the former 2025 mining use only.","parties":[{"name":"Cipher Digital (formerly Cipher Mining)","note":"Formerly Cipher Mining; develops the site through wholly owned subsidiaries Cipher Black Pearl LLC and Black Pearl Compute LLC.","role":"developer","source_ids":["s1","s3","s5"]},{"name":"Cipher Digital (formerly Cipher Mining)","note":"The land is owned by a wholly owned Cipher subsidiary and the facility is described as wholly owned.","role":"owner","source_ids":["s1"]},{"name":"Amazon Web Services","note":"Named as the Black Pearl lessee only in the 10-K (s1), which dates the 15-year lease of about 300 gross MW to both October and November 2025. The November 2025 release (s2) announces the AWS lease without naming the site, and the August 2026 updates refer to an unnamed investment-grade hyperscale tenant.","role":"tenant","source_ids":["s1","s2"]},{"name":"Quanta Services","note":"Cipher names Quanta as an engineering, construction and procurement partner for sites such as Black Pearl.","role":"builder","source_ids":["s1"]}],"power_sources":[{"description":"Approved for 300 MW of interconnection and set up to take part in the ERCOT market.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260918143824/https://www.sec.gov/Archives/edgar/data/1819989/000181998926000009/cifr-20251231.htm","id":"s1","published":"2026-02-24","publisher":"Cipher Mining Inc. (now Cipher Digital Inc.) via SEC EDGAR","title":"Cipher annual report on Form 10-K for fiscal year 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1819989/000181998926000009/cifr-20251231.htm"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-03","publisher":"Cipher Mining Inc. via SEC EDGAR","title":"Cipher Mining provides third quarter 2025 business update (Form 8-K, Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1819989/000181998925000110/nov3_earningspressreleasex.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-04","publisher":"Cipher Digital Inc. via SEC EDGAR","title":"Cipher Digital Provides Second Quarter 2026 Business Update (Form 8-K Exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1819989/000181998926000038/q226_earningsxprxdraftxvf.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006075929/https://www.sec.gov/Archives/edgar/data/1819989/000181998926000038/cipherdigital_businessup.htm","id":"s4","published":"2026-08-04","publisher":"Cipher Digital Inc. via SEC EDGAR","title":"Cipher Digital business update presentation (Form 8-K Exhibit 99.2)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1819989/000181998926000038/cipherdigital_businessup.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261005185914/https://www.sec.gov/Archives/edgar/data/1819989/000095010326001966/dp241421_8k.htm","id":"s5","published":"2026-02-11","publisher":"Cipher Mining Inc. via SEC EDGAR","title":"Cipher Mining Form 8-K: Black Pearl Compute LLC 6.125% senior secured notes due 2031","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1819989/000095010326001966/dp241421_8k.htm"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Wink, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Wink,_Texas"}],"status":"partially_operational","status_as_of":"2026-08-04","status_source_ids":["s3","s4"],"summary":"Cipher Digital (formerly Cipher Mining) facility on about 75 company-owned acres near Wink, Texas, with 300 MW of approved ERCOT interconnection. Cipher began bitcoin mining there in June 2025, signed a 15-year lease with Amazon Web Services for about 300 gross MW of turnkey data center capacity, which it valued at about USD 5.5 billion, and stopped mining in February 2026. Cipher said it delivered the first data center capacity and rent began in August 2026, two months ahead of the original schedule, while the remaining phase I halls were in fit-out and phase II was still being built.","workloads":["ai_unspecified","hpc","crypto_mining"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"4c64ca35-7a18-5662-ad69-696665683807","s2":"841a8da1-9f19-501b-9cb7-da7b2d2dc0ce","s3":"5bc7254b-53ee-55b1-b5ec-22bc5a3e07d0","s4":"e783aa50-048c-5a24-a978-935b81008e55","s5":"5c940a57-17e2-5adf-b1bb-cfb444c03cda","s6":"e6a7bc2c-db8e-551f-a7a7-c796bf8f1bde"},"source_file":"datacenters/projects/cipher-black-pearl.json","source_record_id":"cipher-black-pearl","source_record_sha256":"3f9721d3988a2090aaf77c85c80c95f20be223460a8838ab884ee62d8e0414d2","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"124821f366946a55c69c9521d4b42d0003c2b861addb05b39bc4d74530ce1d02"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6bedc032f2f6fb914715/#project-ade90a9a-b55b-503e-a8b9-d2f8340a81d6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ade90a9a-b55b-503e-a8b9-d2f8340a81d6.json
ae484949-f575-5553-ad33-bc1f96eab345 | curated:sabey-sdc-austin-round-rock-campus:building-b-current-build | vcc-site-be615a0bc019c0f6d350 | curated:sabey-sdc-austin-round-rock-campus | Sabey SDC Austin Building B Current Build | United States | US | 30.4858 | -97.651 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | b4bdfbf2-b320-5186-8978-0076403b94c3 | shell | 2026-06-16 | 119 | authoritative_physical_status_update | ed8d1d3a-d3bf-5121-99f1-8da8caaebd1e | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://sabeydatacenters.com/news/sdc-austin-progress-q2-2026 | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-be615a0bc019c0f6d350/#project-ae484949-f575-5553-ad33-bc1f96eab345 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ae484949-f575-5553-ad33-bc1f96eab345.json
ae6f1b86-660b-54e9-bdb0-d29bfeedc551 | curated:qts-cedar-rapids-data-center-campus:current-campus-development | vcc-site-d60291ccffe6616c33cc | curated:qts-cedar-rapids-data-center-campus | QTS Cedar Rapids Current Campus Development | United States | US | 41.9073 | -91.7543 | Point | campus | first_party_published_map_pin | qts_first_party_cdr1_dc1_page_map_pin_as_shared_campus_locator | first_party_facility_page_point_as_broad_campus_locator | official_source | campus_locator | QTS-published page map pin attached to the CDR1 DC1 address at the shared 6200 76th Avenue SW campus. It is used only as a broad campus locator, not as DC1, DC2, DC3, current-development, sewer-work, building, parcel, or 612-acre campus boundary geometry. |  | The QTS page publishes coordinate digits but no collection method, reference-feature definition, or bounded numeric horizontal-accuracy value; the map pin is not asserted to fall on any specific building or work extent. | 7f58e6cc-7e09-55a4-8202-38d31f72d03d | under_construction | 2026-07-15 | 90 | authoritative_physical_status_update | e2169f4d-f349-5a9c-8e37-03a4ee09aa49 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://q.com/data-centers/cedar-rapids/ | https://q.com/data-centers/cedar-rapids/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d60291ccffe6616c33cc/#project-ae6f1b86-660b-54e9-bdb0-d29bfeedc551 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ae6f1b86-660b-54e9-bdb0-d29bfeedc551.json
b02620fe-58af-53a3-91fc-855e2454512c | imported:semiconductor-atlas:bitdeer-weathersfield-ohio | vcc-site-755524c9fd6de6eed9f2 | imported:semiconductor-atlas:bitdeer-weathersfield-ohio | Bitdeer Weathersfield (Niles) development site | United States | US | 41.1783 | -80.7578 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Bitdeer names the site Niles and later Weathersfield, Ohio, without an address. The point is the Weathersfield Township coordinate from its Wikipedia article, which lists much of the city of Niles among the township's populated places; it is not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 854437f1-bd50-583c-9b5a-aeb46572a5cf | announced | 2026-08-10 | 64 | imported_documented_status | 03d2d93d-6216-5214-a952-7c6399432079 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"854437f1-bd50-583c-9b5a-aeb46572a5cf","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-weathersfield-ohio"},{"evidence_id":"82c10057-5c86-56a3-9310-fe1326cd2618","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-weathersfield-ohio"},{"evidence_id":"03d2d93d-6216-5214-a952-7c6399432079","notes":null,"party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"developer","source_record_id":"bitdeer-weathersfield-ohio"},{"evidence_id":"854437f1-bd50-583c-9b5a-aeb46572a5cf","notes":"Owns the 41.8 acres of land.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"owner","source_record_id":"bitdeer-weathersfield-ohio"},{"evidence_id":"82c10057-5c86-56a3-9310-fe1326cd2618","notes":"Owns the 41.8 acres of land.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"owner","source_record_id":"bitdeer-weathersfield-ohio"},{"evidence_id":"03d2d93d-6216-5214-a952-7c6399432079","notes":"Owns the 41.8 acres of land.","party":"Bitdeer Technologies Group","relationship_scope":"unknown","role":"owner","source_record_id":"bitdeer-weathersfield-ohio"},{"evidence_id":"854437f1-bd50-583c-9b5a-aeb46572a5cf","notes":"Party to the interconnection agreement and set the original energization schedule. The 2026 results refer only to a transmission line extension agreement with an unnamed local utility company.","party":"FirstEnergy","relationship_scope":"unknown","role":"utility","source_record_id":"bitdeer-weathersfield-ohio"},{"evidence_id":"82c10057-5c86-56a3-9310-fe1326cd2618","notes":"Party to the interconnection agreement and set the original energization schedule. The 2026 results refer only to a transmission line extension agreement with an unnamed local utility company.","party":"FirstEnergy","relationship_scope":"unknown","role":"utility","source_record_id":"bitdeer-weathersfield-ohio"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Bitdeer Technologies Group |  |  |  |  | https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm | https://www.sec.gov/Archives/edgar/data/0001899123/000121390025098957/ea026118901ex99-1_bitdeer.htm | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bitdeer Weathersfield (Niles) development site as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"bitdeer-weathersfield-ohio"},"record":{"aliases":["Bitdeer Niles","Niles, Ohio site"],"id":"bitdeer-weathersfield-ohio","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Trumbull County","country":"US","lat":41.1783,"locality":"Weathersfield Township (Niles)","lon":-80.7578,"note":"Bitdeer names the site Niles and later Weathersfield, Ohio, without an address. The point is the Weathersfield Township coordinate from its Wikipedia article, which lists much of the city of Niles among the township's populated places; it is not the site.","precision":"locality","source_ids":["s1","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-31","basis":"planned","metric":"power_capacity","note":"Listed as the capacity of a grid-interconnected development site in Bitdeer's power pipeline. Bitdeer's 2025 updates footnote their capacity figures as total available electrical capacity.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-07-31","basis":"acquired","metric":"land_area","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"acres","value":41.8}],"milestones":[{"date":"2025-09","event":"announced","kind":"actual","note":"Bitdeer said it officially launched the 300 MW Niles power pipeline in September 2025.","source_ids":["s1"]},{"date":"2028-Q4","event":"other","kind":"planned","note":"Target energization (ready-for-service) as of July 2026. The 2025 updates gave Q1 2029 as scheduled by FirstEnergy.","source_ids":["s3"]}],"name":"Bitdeer Weathersfield (Niles) development site","notes":"The September and October 2025 updates do not state an intended use; the Q2 2026 results list planned usage as colocation and AI cloud. Bitdeer's separate 570 MW Clarington, Ohio site (planned for colocation and crypto) and its Massillon, Ohio mining site are different builds.","parties":[{"name":"Bitdeer Technologies Group","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Bitdeer Technologies Group","note":"Owns the 41.8 acres of land.","role":"owner","source_ids":["s1","s2","s3"]},{"name":"FirstEnergy","note":"Party to the interconnection agreement and set the original energization schedule. The 2026 results refer only to a transmission line extension agreement with an unnamed local utility company.","role":"utility","source_ids":["s1","s2"]}],"power_sources":[{"description":"Grid interconnection under an agreement with FirstEnergy, plus a transmission line extension agreement with a local utility.","source_ids":["s1","s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-10-14","publisher":"Bitdeer Technologies Group via SEC EDGAR","title":"Bitdeer Announces September 2025 Production and Operations Update (Form 6-K exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001899123/000121390025098957/ea026118901ex99-1_bitdeer.htm"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-10","publisher":"Bitdeer Technologies Group via SEC EDGAR","title":"Bitdeer Announces October 2025 Production and Operations Update (Form 6-K exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001899123/000121390025107866/ea026473802ex99-1_bitdeer.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-10","publisher":"Bitdeer Technologies Group via SEC EDGAR","title":"Bitdeer Reports Unaudited Financial Results for the Second Quarter of 2026 (Form 6-K exhibit 99.1)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Weathersfield Township, Trumbull County, Ohio","type":"other","url":"https://en.wikipedia.org/wiki/Weathersfield_Township,_Trumbull_County,_Ohio"}],"status":"announced","status_as_of":"2026-08-10","status_source_ids":["s3"],"summary":"Bitdeer development site on 41.8 owned acres at the former Niles Generating Station, demolished in 2013, in Weathersfield, Ohio, near Niles. Bitdeer launched it in September 2025 as a 300 MW grid-interconnected power pipeline under an interconnection agreement with FirstEnergy, which first scheduled energization for Q1 2029. Bitdeer's Q2 2026 results, with data as of 31 July 2026, target energization in Q4 2028, cite a transmission line extension agreement with a local utility, and list planned usage as colocation and AI cloud; the site is still described as a development site.","workloads":["colocation","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"854437f1-bd50-583c-9b5a-aeb46572a5cf","s2":"82c10057-5c86-56a3-9310-fe1326cd2618","s3":"03d2d93d-6216-5214-a952-7c6399432079","s4":"a535c63a-b506-5947-ba5c-5bb2ba66ee66"},"source_file":"datacenters/projects/bitdeer-weathersfield-ohio.json","source_record_id":"bitdeer-weathersfield-ohio","source_record_sha256":"6873998ecf110e750fa0194050d1a7f43fadc62158d613faef7b8fe7d3b8dc9b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1f44177ccd7d8c6879a60f226ec4bfbc0a373b0278fd2eceee51165abf471a07"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-755524c9fd6de6eed9f2/#project-b02620fe-58af-53a3-91fc-855e2454512c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b02620fe-58af-53a3-91fc-855e2454512c.json
b0588082-53ae-577a-b989-667b8f9f171d | curated:digital-realty-fra20-frankfurt:uw04-substation-current-build | vcc-site-f98926ffb5ad45066954 | curated:digital-realty-fra20-frankfurt | Digital Park Fechenheim UW04 Substation | Germany | DE | 50.1259 | 8.7528 | Point | campus | literal_operator_facility_latitude_longitude_reordered_without_numeric_transform | first_party_named_constituent_facility_marker_with_static_frontend_and_wgs84_contract | official_operator_published_constituent_campus_reference_point | official_source | campus_locator | FRA20 constituent facility marker at Hugo-Junkers-Strasse 5a, used solely to locate the physical Digital Park Fechenheim campus shared with UW04. Not the UW04 building, its entrance/address, a transformer position, cadastral parcel, campus boundary, active work extent or quantified survey location. |  | Operator publishes no positional accuracy; six decimal places and a documented datum do not establish survey accuracy. | de30d8ff-1dd6-500b-b538-0704dd5ae94e | under_construction | 2026-07-02 | 103 | authoritative_physical_status_update | d4a9d3ee-4746-51bc-90f4-1428feb96d93 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.lupp.de/spatenstich-fuer-das-umspannwerk-im-digitalpark-fechenheim | https://www.digitalrealty.com/de/data-centers/emea/frankfurt/fra20 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f98926ffb5ad45066954/#project-b0588082-53ae-577a-b989-667b8f9f171d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b0588082-53ae-577a-b989-667b8f9f171d.json
b0be5071-aff0-5470-a041-a0be3cc8385a | curated:goodman-mad01-madrid-data-centre-campus:current-development | vcc-site-d00d83a0549fcc042174 | curated:goodman-mad01-madrid-data-centre-campus | Goodman MAD01 Current Development | Spain | ES | 40.4441 | -3.5464 | Point | campus | first_party_brochure_published_map_coordinate_query | resolve_exact_PDF_URI_annotation_and_preserve_published_coordinate_query | official_operator_published_campus_reference_point | official_source | campus_locator | The exact MAD01 brochure map query locates the campus at C/ Provisional Iveco-Pegaso Cinco 2. No survey, boundary, building footprint or current-work extent is asserted; secured future campus expansion is not another site. |  | No numeric accuracy or surveyed-feature description accompanies the owner's coordinate query. | c874fcec-0c4d-5dec-b277-0c338369d9c7 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 11e06062-9188-5c5b-8df8-8f557f27c7e6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | https://maps.app.goo.gl/27oe2osrJoEjN5eB8 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d00d83a0549fcc042174/#project-b0be5071-aff0-5470-a041-a0be3cc8385a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b0be5071-aff0-5470-a041-a0be3cc8385a.json
b10fbc1b-2689-5864-989c-b36b13abb9ad | imported:semiconductor-atlas:teton-digital-black-bear-swan-hills | vcc-site-50ba6e2d0f69faaff629 | imported:semiconductor-atlas:teton-digital-black-bear-swan-hills | Teton Digital Black Bear power and data centre campus (Swan Hills) | Canada | CA | 54.5325 | -115.5732 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Coordinates of the south end of the power plant project area as stated in the 2024 federal project description (SW and SE quarters of Section 15-64-11-W5M). The data centre land is described only as adjacent Crown land, so its centre may differ. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d5c22c5a-1956-5498-9c09-94a18e16251b | proposed | 2026-09-23 | 20 | imported_documented_status | b034592b-6022-5934-8b5a-f9924626f394 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"b034592b-6022-5934-8b5a-f9924626f394","notes":null,"party":"Teton Digital","relationship_scope":"unknown","role":"developer","source_record_id":"teton-digital-black-bear-swan-hills"},{"evidence_id":"1e2e5d54-724b-5882-8b4b-8dbd2350b253","notes":null,"party":"Teton Digital","relationship_scope":"unknown","role":"developer","source_record_id":"teton-digital-black-bear-swan-hills"},{"evidence_id":"9a3d7740-336f-582c-ae46-5fa8fe7d4be2","notes":null,"party":"Teton Digital","relationship_scope":"unknown","role":"developer","source_record_id":"teton-digital-black-bear-swan-hills"},{"evidence_id":"d5c22c5a-1956-5498-9c09-94a18e16251b","notes":"Original 2024 proponent of the power plant; DeSmog reports it exited the power business in 2025 and cancelled its planned AESO grid connection in December 2025.","party":"Kiwetinohk Energy Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"teton-digital-black-bear-swan-hills"},{"evidence_id":"b904a8ae-d243-5f8c-84a4-4ada16f0adf6","notes":"Original 2024 proponent of the power plant; DeSmog reports it exited the power business in 2025 and cancelled its planned AESO grid connection in December 2025.","party":"Kiwetinohk Energy Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"teton-digital-black-bear-swan-hills"},{"evidence_id":"1e2e5d54-724b-5882-8b4b-8dbd2350b253","notes":"Original 2024 proponent of the power plant; DeSmog reports it exited the power business in 2025 and cancelled its planned AESO grid connection in December 2025.","party":"Kiwetinohk Energy Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"teton-digital-black-bear-swan-hills"},{"evidence_id":"9a3d7740-336f-582c-ae46-5fa8fe7d4be2","notes":"Original 2024 proponent of the power plant; DeSmog reports it exited the power business in 2025 and cancelled its planned AESO grid connection in December 2025.","party":"Kiwetinohk Energy Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"teton-digital-black-bear-swan-hills"},{"evidence_id":"9a3d7740-336f-582c-ae46-5fa8fe7d4be2","notes":"Reported in July 2026 to be amending bylaws to fast-track the project; the Sucker Creek First Nation asked council to wait until environmental and water questions were answered.","party":"Big Lakes County","relationship_scope":"unknown","role":"government","source_record_id":"teton-digital-black-bear-swan-hills"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://tetondigital.io/black-bear | https://iaac-aeic.gc.ca/050/documents/p88747/158276E.pdf | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Teton Digital Black Bear power and data centre campus (Swan Hills) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"teton-digital-black-bear-swan-hills"},"record":{"aliases":["Black Bear Power Project","Black Bear Power Plant Project","Black Bear"],"id":"teton-digital-black-bear-swan-hills","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","admin2":"Big Lakes County","country":"CA","lat":54.532535,"locality":"About 19 km south of Swan Hills","lon":-115.57319,"note":"Coordinates of the south end of the power plant project area as stated in the 2024 federal project description (SW and SE quarters of Section 15-64-11-W5M). The data centre land is described only as adjacent Crown land, so its centre may differ.","precision":"approximate_site","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2024-07","basis":"planned","metric":"power_capacity","note":"Net output of the plant's single combustion turbine generator in Kiwetinohk's 2024 federal filing, before a data centre was attached.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s1","s2"],"unit":"MW","value":460},{"applies_to":"phase","as_of":"2026-09-23","basis":"planned","metric":"power_capacity","note":"Teton's figure for the natural gas combined-cycle plant.","phase_label":"Phase I","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s3","s4","s5"],"unit":"MW","value":466},{"applies_to":"campus","as_of":"2026-09-23","basis":"planned","metric":"power_capacity","note":"Teton's stated long-term pathway, split as about 2 GW behind the meter and 1 GW grid-connected, across one or more data centre campuses.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3","s4"],"unit":"MW","value":3000},{"applies_to":"campus","as_of":"2026-09-23","basis":"planned","metric":"land_area","note":"Adjacent Crown land being developed for data centre use.","qualifier":"approximately","source_ids":["s3","s4"],"unit":"acres","value":1500}],"milestones":[{"date":"2024-07-18","event":"other","kind":"actual","note":"Kiwetinohk filed the initial project description for the Black Bear power plant with the Impact Assessment Agency of Canada.","source_ids":["s2"]},{"date":"2024-12-23","event":"other","kind":"actual","note":"Federal agency decided that an impact assessment of the power plant is not required.","source_ids":["s2"]},{"date":"2026-04","event":"other","kind":"actual","note":"Teton says it filed an AESO Cluster 3 grid interconnection application.","source_ids":["s3","s5"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Compute could begin as early as 2027 using temporary grid power before the plant is complete.","source_ids":["s3","s4"]},{"date":"2028-Q3","event":"other","kind":"planned","note":"Target for full 466 MW commercial operation of the power plant.","source_ids":["s3"]}],"name":"Teton Digital Black Bear power and data centre campus (Swan Hills)","notes":"Status rests on Daily Hive's September 2026 report that Alberta Major Projects lists the project as proposed, plus Teton's undated project page (read 2026-10-09), which says provincial and federal permits are in hand and an AESO interconnection application was filed in April 2026. DeSmog reported Teton's federal permitting claim without verifying it, raised questions about the developer's background, and reported that the 2024 carbon capture design no longer appears in Teton's materials. Both news outlets describe it as a $1.3 billion project without stating the currency, so no investment figure is recorded.","parties":[{"name":"Teton Digital","role":"developer","source_ids":["s3","s4","s5"]},{"name":"Kiwetinohk Energy Corp.","note":"Original 2024 proponent of the power plant; DeSmog reports it exited the power business in 2025 and cancelled its planned AESO grid connection in December 2025.","role":"developer","source_ids":["s1","s2","s4","s5"]},{"name":"Big Lakes County","note":"Reported in July 2026 to be amending bylaws to fast-track the project; the Sucker Creek First Nation asked council to wait until environmental and water questions were answered.","role":"government","source_ids":["s5"]}],"power_sources":[{"description":"A natural gas combined-cycle plant of 466 MW in its first phase; Kiwetinohk's 2024 design included CO2 capture with pipeline transport to a storage hub, which Teton's materials do not mention.","source_ids":["s1","s2","s3","s5"],"type":"natural_gas_onsite"},{"description":"Teton plans bridge power from the grid from 2027 and has applied to AESO for an interconnection; it puts roughly 1 GW of the long-term pathway on the grid.","source_ids":["s3","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-07","publisher":"Kiwetinohk Energy Corp. (filed with the Impact Assessment Agency of Canada)","title":"Black Bear Power Plant: Summary of the Initial Project Description","type":"regulatory_filing","url":"https://iaac-aeic.gc.ca/050/documents/p88747/158276E.pdf"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Impact Assessment Agency of Canada","title":"Black Bear Power Plant Project (Canadian Impact Assessment Registry, reference 88747)","type":"government","url":"https://iaac-aeic.gc.ca/050/evaluations/proj/88747"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Teton Digital","title":"Black Bear","type":"company","url":"https://tetondigital.io/black-bear"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-23","publisher":"Daily Hive","title":"A $1.3B power plant and data centre is in the works northwest of Edmonton","type":"news","url":"https://dailyhive.com/edmonton/power-plant-data-centre-swan-hills"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260729123620/https://www.desmog.com/2026/07/27/u-s-developer-tied-to-failed-bitcoin-venture-is-proposing-major-alberta-data-centre/","id":"s5","published":"2026-07-27","publisher":"DeSmog","title":"U.S. Developer Tied to Failed Bitcoin Venture Is Proposing Major Alberta Data Centre","type":"news","url":"https://www.desmog.com/2026/07/27/u-s-developer-tied-to-failed-bitcoin-venture-is-proposing-major-alberta-data-centre/"}],"status":"proposed","status_as_of":"2026-09-23","status_source_ids":["s3","s4"],"summary":"Proposed gas-powered data centre campus on Crown land about 19 km south of Swan Hills, Alberta, in Big Lakes County. Kiwetinohk Energy first proposed the roughly 460 MW Black Bear combined-cycle plant in 2024 and received a federal decision that no impact assessment was needed; Teton Digital has since taken it up as the power source for about 1,500 acres of adjacent data centre land. Teton describes a 466 MW first phase with a path to about 3 GW, compute online as early as 2027 using grid power, and the full plant running in Q3 2028. Alberta's project inventory lists it as proposed."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d5c22c5a-1956-5498-9c09-94a18e16251b","s2":"b904a8ae-d243-5f8c-84a4-4ada16f0adf6","s3":"b034592b-6022-5934-8b5a-f9924626f394","s4":"1e2e5d54-724b-5882-8b4b-8dbd2350b253","s5":"9a3d7740-336f-582c-ae46-5fa8fe7d4be2"},"source_file":"datacenters/projects/teton-digital-black-bear-swan-hills.json","source_record_id":"teton-digital-black-bear-swan-hills","source_record_sha256":"d01e8fafc2f8a182ec3539b2223aeaa9076b7c425026e60538d9904df7100d82","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"c2aca4c0fdd215dfd7a5856135bf9fcf51bdab2c75b6a0fc3163f68167ea252c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-50ba6e2d0f69faaff629/#project-b10fbc1b-2689-5864-989c-b36b13abb9ad | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b10fbc1b-2689-5864-989c-b36b13abb9ad.json
b19d5d3a-c2cc-5cea-9698-fe07ac125c8e | imported:semiconductor-atlas:qts-vimercate | vcc-site-e6669b76221d6e79fd89 | imported:semiconductor-atlas:qts-vimercate | QTS Vimercate data center campus | Italy | IT | 45.617 | 9.367 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from the Vimercate Wikipedia article. Sources place the site on the former IBM area at Velasca, a frazione of Vimercate, near the boundary with Burago; the site is not mapped in the local OpenStreetMap layer. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | e4ddd93d-c079-503a-8fb4-c050901d33db | announced | 2026-10-09 | 4 | imported_documented_status | e4ddd93d-c079-503a-8fb4-c050901d33db | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e4ddd93d-c079-503a-8fb4-c050901d33db","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-vimercate"},{"evidence_id":"2e44a0cd-e620-53d7-afa6-1e7a4e88411c","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-vimercate"},{"evidence_id":"770bb9d2-a4ef-5546-b2c3-d68273de5c76","notes":null,"party":"QTS Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"qts-vimercate"},{"evidence_id":"770bb9d2-a4ef-5546-b2c3-d68273de5c76","notes":"Il Giorno names Kryalos alongside QTS; Cloudnews says Blackstone holds a stake in Kryalos and that it is linked to the project, without describing its role.","party":"Kryalos SGR","relationship_scope":"unknown","role":"developer","source_record_id":"qts-vimercate"},{"evidence_id":"aeae6b21-c409-5b76-8063-1554a8502985","notes":"Il Giorno names Kryalos alongside QTS; Cloudnews says Blackstone holds a stake in Kryalos and that it is linked to the project, without describing its role.","party":"Kryalos SGR","relationship_scope":"unknown","role":"developer","source_record_id":"qts-vimercate"},{"evidence_id":"2e44a0cd-e620-53d7-afa6-1e7a4e88411c","notes":"Is to build a new electrical station near the Burago boundary that would serve this and two other planned Vimercate data centers.","party":"Terna","relationship_scope":"unknown","role":"utility","source_record_id":"qts-vimercate"},{"evidence_id":"aeae6b21-c409-5b76-8063-1554a8502985","notes":"Is to build a new electrical station near the Burago boundary that would serve this and two other planned Vimercate data centers.","party":"Terna","relationship_scope":"unknown","role":"utility","source_record_id":"qts-vimercate"},{"evidence_id":"2e44a0cd-e620-53d7-afa6-1e7a4e88411c","notes":"Expects about EUR 5 million in development charges plus refurbishment of the Oreno sports ground; objections were also lodged on its planning-code revision.","party":"Comune di Vimercate","relationship_scope":"unknown","role":"government","source_record_id":"qts-vimercate"},{"evidence_id":"770bb9d2-a4ef-5546-b2c3-d68273de5c76","notes":"Expects about EUR 5 million in development charges plus refurbishment of the Oreno sports ground; objections were also lodged on its planning-code revision.","party":"Comune di Vimercate","relationship_scope":"unknown","role":"government","source_record_id":"qts-vimercate"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://q.com/data-centers/vimercate-en/ | https://q.com/data-centers/vimercate-en/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve QTS Vimercate data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"qts-vimercate"},"record":{"aliases":["QTS Vimercate/Milan","Velasca data center"],"id":"qts-vimercate","last_reviewed":"2026-10-09","location":{"admin1":"Lombardia","admin2":"Monza e Brianza","country":"IT","lat":45.617,"locality":"Vimercate","lon":9.367,"note":"Town coordinates from the Vimercate Wikipedia article. Sources place the site on the former IBM area at Velasca, a frazione of Vimercate, near the boundary with Burago; the site is not mapped in the local OpenStreetMap layer.","precision":"locality","source_ids":["s1","s2","s7"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"Inward investment figure on QTS's undated campus page, read on 2026-10-09.","qualifier":"up_to","source_ids":["s1","s5"],"unit":"EUR","value":2300000000},{"applies_to":"campus","as_of":"2026-07-12","basis":"planned","metric":"power_capacity","note":"Reported after QTS's open day as two buildings of 60 MW and one of 36 MW.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":156},{"applies_to":"campus","as_of":"2026-06-24","basis":"planned","metric":"power_capacity","note":"Undated trade article written after the 24 June 2026 presentation; it describes three buildings.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s5"],"unit":"MW","value":220},{"applies_to":"campus","as_of":"2026-07-11","basis":"planned","metric":"power_capacity","note":"Il Giorno reports 300 MW of electrical power in its account of residents' objections.","power_scope":"unspecified","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-07-12","basis":"reported","metric":"land_area","note":"QTS's page and Il Giorno give a 277,800 square metre site instead.","qualifier":"exact","source_ids":["s2","s3"],"unit":"hectares","value":19},{"applies_to":"campus","as_of":"2026-07-12","basis":"planned","metric":"floor_area","note":"Buildable area reported as a little under 100,000 square metres.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"sq_m","value":100000},{"applies_to":"campus","as_of":"2026-07-12","basis":"planned","metric":"buildings","note":"Data center buildings; annex buildings and a substation are also planned.","qualifier":"exact","source_ids":["s2","s3","s4"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2026-07-12","basis":"planned","metric":"jobs_construction","qualifier":"approximately","source_ids":["s2","s3"],"unit":"count","value":600},{"applies_to":"campus","as_of":"2026-07-12","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s2","s4"],"unit":"count","value":100}],"milestones":[{"date":"2025-07","event":"other","kind":"actual","note":"QTS's executive vice-president said the approval process began in July of the previous year.","source_ids":["s2"]},{"date":"2026-06-24","event":"other","kind":"actual","note":"Public open day at which QTS presented the project to residents, businesses and local officials.","source_ids":["s3","s5"]},{"date":"2026","event":"construction_started","kind":"planned","note":"Site preparation planned by the end of 2026, after the environmental assessment and building permit.","source_ids":["s2","s3"]},{"date":"2028-H2","event":"first_operational","kind":"planned","note":"First building expected in the second half of 2028; the report places the formal opening between then and 2029.","source_ids":["s2","s3"]}],"name":"QTS Vimercate data center campus","notes":"Capacity figures conflict: 156 MW (Prima Monza, Giornale di Vimercate), about 220 MW (Cloudnews, citing Il Cittadino) and 300 MW (Il Giorno); site size is 19 hectares in local press but 277,800 square metres on QTS's undated page, which calls the development proposed (status_as_of is the access date). Giornale di Vimercate was read as a PDF clipping hosted by CIAI, a charity QTS sponsors; Prima Monza's own site carries the same text. A sponsored MBNews piece, also hosted by CIAI, said old sheds were being demolished; this is unconfirmed and not recorded. Opponents asked for heat recovery, generator-test limits and buried power lines. No ministry environmental decision was found.","parties":[{"name":"QTS Data Centers","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Kryalos SGR","note":"Il Giorno names Kryalos alongside QTS; Cloudnews says Blackstone holds a stake in Kryalos and that it is linked to the project, without describing its role.","role":"developer","source_ids":["s4","s5"]},{"name":"Terna","note":"Is to build a new electrical station near the Burago boundary that would serve this and two other planned Vimercate data centers.","role":"utility","source_ids":["s2","s5"]},{"name":"Comune di Vimercate","note":"Expects about EUR 5 million in development charges plus refurbishment of the Oreno sports ground; objections were also lodged on its planning-code revision.","role":"government","source_ids":["s2","s4"]}],"power_sources":[{"description":"On-site substation linked by underground cable to a new station Terna is to build near the Burago boundary.","source_ids":["s2"],"type":"grid"},{"description":"133 emergency generators are planned (fuel not stated), which Il Giorno puts at about 1,000 MW thermal in total.","source_ids":["s4","s5"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"QTS Data Centers","title":"Vimercate","type":"company","url":"https://q.com/data-centers/vimercate-en/"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-12","publisher":"Prima Monza","title":"Il primo data center della città si svela","type":"news","url":"https://primamonza.it/attualita/il-primo-data-center-della-citta-si-svela/"},{"accessed":"2026-10-09","id":"s3","published":"2026-06-30","publisher":"Giornale di Vimercate (press clipping hosted by CIAI)","title":"Su il sipario sul nuovo Data center","type":"news","url":"https://www.ciai.it/wp-content/uploads/2026/07/Giornale-Vimercate-30-6-26.pdf"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-11","publisher":"Il Giorno","title":"Il Campus Data Center fa paura: \"Diciamo no al deserto di cemento\"","type":"news","url":"https://www.ilgiorno.it/monza-brianza/cronaca/il-campus-data-center-fa-6bad3cb1"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Cloudnews.tech","title":"QTS prepares a 220 MW campus near Milan and accelerates its expansion","type":"trade_press","url":"https://cloudnews.tech/qts-prepares-a-220-mw-campus-near-milan-and-accelerates-its-expansion/"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Wikipedia","title":"Vimercate","type":"other","url":"https://en.wikipedia.org/wiki/Vimercate"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s1","s2","s4"],"summary":"Proposed first Italian campus of Blackstone-owned QTS Data Centers on the former IBM industrial site at Velasca in Vimercate (Monza and Brianza). QTS's page calls it a proposed development of up to EUR 2.3 billion. At a June 2026 open day QTS presented three buildings and an on-site substation linked to a planned Terna station; local press reported 156 MW (two 60 MW buildings and one of 36 MW), while other reports give about 220 MW or 300 MW. In July 2026 QTS awaited the national environmental assessment before a building permit, aiming to prepare the site by end-2026 and open the first building in the second half of 2028.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e4ddd93d-c079-503a-8fb4-c050901d33db","s2":"2e44a0cd-e620-53d7-afa6-1e7a4e88411c","s3":"efd0bf68-9446-5dbd-a64c-bf8cde4f298b","s4":"770bb9d2-a4ef-5546-b2c3-d68273de5c76","s5":"aeae6b21-c409-5b76-8063-1554a8502985","s7":"82ca9162-6f69-5624-937e-c32e3fdfc557"},"source_file":"datacenters/projects/qts-vimercate.json","source_record_id":"qts-vimercate","source_record_sha256":"2eab43957ef241c6d48d076e0bf4c83579582967c2f8daf95df70b38410c03dd","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"f4d79141779165657969abaac643332fe9136caee03246c72acbb244add3eb09"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e6669b76221d6e79fd89/#project-b19d5d3a-c2cc-5cea-9698-fe07ac125c8e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b19d5d3a-c2cc-5cea-9698-fe07ac125c8e.json
b284fbeb-8cd9-5448-860d-b4f69bb8bd7a | curated:equinix-mu4-munich-data-center:phase-3 | vcc-site-3867ebd8648d7b1a2b65 | curated:equinix-mu4-munich-data-center | Equinix MU4 Phase 3 | Germany | DE | 48.147 | 11.6825 | Polygon | facility | cross_source_geometry | openstreetmap_mu4_construction_landuse_polygon_as_parent_campus_locator | reviewed_openstreetmap_mu4_construction_landuse_polygon | community_mapped | campus_locator | Contributor-mapped MU4 construction-landuse polygon, used only to locate the parent MU4 campus. It is not a Phase 3 point or boundary, the complete current campus extent, an official parcel or planning boundary, a building footprint, or a current construction-progress extent. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | efe5b5c9-7394-5f0c-951b-051197168c49 | shell | 2026-07-16 | 89 | authoritative_physical_status_update | 4302b7fb-1bf4-5dc7-abf5-9ba24f4556fa | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.mercuryeng.com/2026/07/16/mercury-marks-significant-milestone-at-equinixs-mu4-3-data-centre-delivery-in-munich-germany/ | https://www.openstreetmap.org/way/899514480 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3867ebd8648d7b1a2b65/#project-b284fbeb-8cd9-5448-860d-b4f69bb8bd7a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b284fbeb-8cd9-5448-860d-b4f69bb8bd7a.json
b2e4945f-3d75-5d9b-b2bb-d65deb74c405 | curated:digital-edge-cgk-campus-bekasi:cgk1 | vcc-site-f42f9f22874b1766554e | curated:digital-edge-cgk-campus-bekasi | Digital Edge CGK1 | Indonesia | ID | -6.3868 | 107.1871 | Polygon | host_estate | osm_way_nodes_to_polygon | osm_giic_way_568349989_v13_retained_as_host_estate_context_not_campus_locator | community_host_estate_polygon_context_only | community_source | host_estate_context | Entire Greenland International Industrial Center (GIIC) host estate as mapped by OSM way 568349989 version 13: a 458-vertex community polygon (a closed way of 459 node references) of about 2,113.63 ha (WGS84 geodesic, diagnostic). Digital Edge places CGK Campus only in the GIIC Industrial Estate; no reviewed source places CGK or CGK1 at any position within, or confirms containment in, this polygon. It also wholly contains the selected STT Jakarta Data Centre Campus geometry and, in the 2026-10-08 OSM snapshot, named data-centre buildings of AWS (ref CGK Sukamahi), Princeton Digital (JC3), Microsoft (JKT05, JKT11) and Digital Hyperspace. Host-estate locality context only: not a CGK or CGK1 locator, parcel, boundary, footprint or work extent. The display anchor is the planar centroid of the estate's longitude/latitude ring, kept unchanged only because the row schema requires a point; it is not a CGK position. |  | CGK's position relative to this host-estate outline is unknown and no source bounds it; OpenStreetMap states no positional accuracy for the outline. No numeric uncertainty is asserted. | 60324cce-b743-571c-ace0-813e7ae281bc | shell | 2026-06-08 | 127 | authoritative_physical_status_update | f1f4c429-166d-5a2f-9757-669775b964a8 | recent_authoritative_physical_observation_plus_host_estate_context_only | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.16 country-diversity batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://id.digitaledgedc.com/news/digital-edge-tops-out-cgk1-secures-largest-indonesia-power-deal | https://api.openstreetmap.org/api/0.6/way/568349989/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f42f9f22874b1766554e/#project-b2e4945f-3d75-5d9b-b2bb-d65deb74c405 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b2e4945f-3d75-5d9b-b2bb-d65deb74c405.json
b3656b35-f3ad-5119-8918-ac5237bf2a7f | osm:way/1383040174:development-project | vcc-site-3cd7dd9c786c855c1820 | osm:way/1383040174 | Microsoft Lévis Charny Development Project | Canada | CA | 46.7079 | -71.2587 | Point | campus | point_on_named_community_polygon | Shapely_Polygon_representative_point | named_community_site_locator | community_source | campus_locator | Interior representative point of an explicitly named OSM Microsoft campus polygon. Not official boundary, current work footprint or surveyed position. |  | OSM mapping accuracy is not quantified; node decimal precision does not establish positional accuracy. | ac662b5d-3d31-52ed-be5a-8b1f6f8d7589 | under_construction | 2026-06-08 | 127 | authoritative_physical_status_update | d7ac9af1-1de8-5ecd-b7f4-06e7bafc6579 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.ccq.org/-/media/Project/Ccq/Ccq-Website/PDF/Recherche/ChantiersImportants/Juin2026/Quebec.pdf?rev=f6c6681d730744f7bf856c79a7b114a0&sc_lang=fr-CA | https://api.openstreetmap.org/api/0.6/way/1383040174/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3cd7dd9c786c855c1820/#project-b3656b35-f3ad-5119-8918-ac5237bf2a7f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b3656b35-f3ad-5119-8918-ac5237bf2a7f.json
b3b98301-a692-5790-88e7-656d77e8fb69 | curated:ntt-frankfurt-1-campus:7-3mw-expansion | vcc-site-fbb0a56d0fdb8284922c | curated:ntt-frankfurt-1-campus | NTT Frankfurt 1 7.3MW Expansion | Germany | DE | 50.1293 | 8.602 | Polygon | facility | cross_source_geometry | openstreetmap_named_ntt_global_data_centers_campus_polygon_with_exact_contained_address_objects_as_parent_campus_locator | reviewed_openstreetmap_named_ntt_global_data_centers_campus_polygon | community_mapped | campus_locator | Contributor-mapped named NTT campus polygon used only to locate the parent Frankfurt 1 campus. It is not the 7.3MW expansion point or footprint, a complete current or legal campus extent, an official parcel, cadastral, planning, or survey boundary, a building footprint, or a current construction-progress extent. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry and address objects are not cadastral, planning-authority, or survey geometry. | eb188ade-b0ff-5b98-bbd4-83cee821ca4b | under_construction | 2026-07-19 | 86 | authoritative_construction_start | 603f155d-0c9d-5428-8e24-36a685af8aa7 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-19","base":7.3,"confidence":0.99,"evidence_id":"603f155d-0c9d-5428-8e24-36a685af8aa7","high":7.3,"low":7.3,"method":"reported","metric":"critical_it_mw","notes":"Additional critical IT load for the distinct expansion that the current page says is under construction; planned capacity stage does not itself assert energization or operation.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://services.global.ntt/en-us/services-and-products/global-data-centers/global-locations/emea/frankfurt-1-data-center | https://www.openstreetmap.org/way/697501723 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fbb0a56d0fdb8284922c/#project-b3b98301-a692-5790-88e7-656d77e8fb69 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b3b98301-a692-5790-88e7-656d77e8fb69.json
b3d41aee-bf24-5299-97dd-2e16bc40012e | imported:semiconductor-atlas:cavour-trino | vcc-site-a4bfb4274cc4e48492b6 | imported:semiconductor-atlas:cavour-trino | Cavour Hyperscale Campus (Trino) | Italy | IT | 45.2521 | 8.1939 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Coordinates of the former Galileo Ferraris thermoelectric plant (frazione Leri Cavour, Trino) from its Italian Wikipedia article; the campus boundary has not been published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | b6f06cee-d9d3-5814-9501-bf553666503b | announced | 2026-07-27 | 78 | imported_documented_status | b6f06cee-d9d3-5814-9501-bf553666503b | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"b6f06cee-d9d3-5814-9501-bf553666503b","notes":"ItaliaOggi names TechBau as the group behind the project; the regional government says it worked with TechBau on the investment.","party":"TechBau","relationship_scope":"unknown","role":"developer","source_record_id":"cavour-trino"},{"evidence_id":"c6801a71-4f70-5d17-96bf-4c6c468508e9","notes":"ItaliaOggi names TechBau as the group behind the project; the regional government says it worked with TechBau on the investment.","party":"TechBau","relationship_scope":"unknown","role":"developer","source_record_id":"cavour-trino"},{"evidence_id":"b6f06cee-d9d3-5814-9501-bf553666503b","notes":"Declared the programme of preeminent national strategic interest on a proposal from the industry minister, allowing an extraordinary commissioner to coordinate the single authorisation.","party":"Government of Italy (Council of Ministers)","relationship_scope":"unknown","role":"government","source_record_id":"cavour-trino"},{"evidence_id":"be62f15d-f7e1-500b-a87e-b00082d8c2fb","notes":"Declared the programme of preeminent national strategic interest on a proposal from the industry minister, allowing an extraordinary commissioner to coordinate the single authorisation.","party":"Government of Italy (Council of Ministers)","relationship_scope":"unknown","role":"government","source_record_id":"cavour-trino"},{"evidence_id":"b6f06cee-d9d3-5814-9501-bf553666503b","notes":null,"party":"Regione Piemonte","relationship_scope":"unknown","role":"government","source_record_id":"cavour-trino"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.regione.piemonte.it/web/node/22790 | https://www.regione.piemonte.it/web/node/22790 | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Cavour Hyperscale Campus (Trino) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"cavour-trino"},"record":{"aliases":["Cavour Hyperscale Campus"],"id":"cavour-trino","last_reviewed":"2026-10-09","location":{"admin1":"Piemonte","admin2":"Vercelli","country":"IT","lat":45.25206,"locality":"Trino","lon":8.19393,"note":"Coordinates of the former Galileo Ferraris thermoelectric plant (frazione Leri Cavour, Trino) from its Italian Wikipedia article; the campus boundary has not been published.","precision":"approximate_site","source_ids":["s1","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-24","basis":"announced","metric":"investment","qualifier":"approximately","source_ids":["s1","s2","s4"],"unit":"EUR","value":4000000000},{"applies_to":"campus","as_of":"2026-07-24","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"range","source_ids":["s2","s3","s4"],"unit":"MW","value":300,"value_high":400},{"applies_to":"campus","as_of":"2026-07-24","basis":"planned","metric":"jobs_construction","note":"Average construction workforce, with peaks above 2,000.","qualifier":"approximately","source_ids":["s1","s2","s4"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2026-07-24","basis":"planned","metric":"jobs_permanent","note":"Highly qualified operating jobs; sources add about 1,000 indirect jobs, and ItaliaOggi speaks of more than 2,000 jobs at full operation.","qualifier":"range","source_ids":["s1","s2","s4"],"unit":"count","value":300,"value_high":350}],"milestones":[{"date":"2026-07-24","event":"other","kind":"actual","note":"Council of Ministers declared the programme of preeminent national strategic interest under article 13 of the Decreto Asset.","source_ids":["s1","s2"]},{"date":"2026","event":"other","kind":"planned","note":"Services conference for permitting to begin by the end of 2026.","source_ids":["s1","s2"]},{"date":"2027","event":"permit_approved","kind":"planned","note":"Target for the single authorisation (autorizzazione unica).","source_ids":["s1","s2","s4"]},{"date":"2028","event":"first_operational","kind":"planned","note":"First lot to enter service.","source_ids":["s1","s2","s4"]}],"name":"Cavour Hyperscale Campus (Trino)","notes":"The Council of Ministers decision covered two programmes totalling about EUR 8 billion; the other is an Equinix programme in Lombardy and is not part of this record. No Council of Ministers or ministry release was opened, and no later report on the permitting conference or the appointment of a commissioner was found. ItaliaOggi attributes the EUR 4 billion figure to La Stampa. The regional release describes the campus as a hub for data processing and artificial intelligence; none of the opened sources states cloud workloads. The Italian Wikipedia article on the former plant is used for coordinates only.","parties":[{"name":"TechBau","note":"ItaliaOggi names TechBau as the group behind the project; the regional government says it worked with TechBau on the investment.","role":"developer","source_ids":["s1","s4"]},{"name":"Government of Italy (Council of Ministers)","note":"Declared the programme of preeminent national strategic interest on a proposal from the industry minister, allowing an extraordinary commissioner to coordinate the single authorisation.","role":"government","source_ids":["s1","s2"]},{"name":"Regione Piemonte","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"Use of an existing 380 kV substation at the former power station site.","source_ids":["s3"],"type":"grid"},{"description":"An 87.5 MW photovoltaic plant already in operation would be used.","source_ids":["s3"],"type":"solar"},{"description":"Electrochemical storage of 100 to 120 MW and 200 to 240 MWh.","source_ids":["s3"],"type":"battery_storage"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-07-24","publisher":"Regione Piemonte (Piemonteinforma)","title":"Un data center nell'ex centrale di Trino","type":"government","url":"https://www.regione.piemonte.it/web/node/22790"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-24","publisher":"CorCom (Corriere Comunicazioni)","title":"Data center, dal Cdm ok a investimenti per 8 miliardi. Urso: \"Italia hub europeo del digitale\"","type":"trade_press","url":"https://corrierecomunicazioni.it/digital-economy/data-center-dal-cdm-ok-a-investimenti-per-8-miliardi-urso-italia-hub-europeo-del-digitale"},{"accessed":"2026-10-09","id":"s3","published":"2026-07-27","publisher":"Punto Informatico","title":"Data center in Lombardia e Piemonte: via libera dal Cdm","type":"trade_press","url":"https://www.punto-informatico.it/data-center-lombardia-piemonte-via-libera-cdm/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260728004340/https://www.italiaoggi.it/economia-e-politica/economia-e-finanza/piemonte-4-miliardi-per-il-nuovo-cavour-hyperscale-campus-norkj7yw","id":"s4","published":"2026-07-27","publisher":"ItaliaOggi","title":"Piemonte, 4 miliardi per il nuovo Cavour Hyperscale Campus","type":"news","url":"https://www.italiaoggi.it/economia-e-politica/economia-e-finanza/piemonte-4-miliardi-per-il-nuovo-cavour-hyperscale-campus-norkj7yw"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Centrale termoelettrica \"Galileo Ferraris\"","type":"other","url":"https://it.wikipedia.org/wiki/Centrale_termoelettrica_Galileo_Ferraris"}],"status":"announced","status_as_of":"2026-07-27","status_source_ids":["s1","s4"],"summary":"Proposed data processing and AI campus on the site of the former Galileo Ferraris power station at Trino in the province of Vercelli, Piedmont, associated with the Italian engineering and construction group TechBau. On 24 July 2026 Italy's Council of Ministers declared it a programme of preeminent national strategic interest, citing about EUR 4 billion of investment and 300 to 400 MW of power. The site would reuse an existing 380 kV substation and an operating 87.5 MW solar plant, with 100 to 120 MW of battery storage. The timetable calls for the permitting conference to open by the end of 2026, a single authorisation in 2027 and a first lot in service in 2028.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"b6f06cee-d9d3-5814-9501-bf553666503b","s2":"be62f15d-f7e1-500b-a87e-b00082d8c2fb","s3":"5f79092a-e377-5c0e-b067-73c78cc8a6c3","s4":"c6801a71-4f70-5d17-96bf-4c6c468508e9","s5":"9b48f02d-3f1c-5397-889a-144889f3715a"},"source_file":"datacenters/projects/cavour-trino.json","source_record_id":"cavour-trino","source_record_sha256":"6f1f1f35d6c4d412bf41db689101e52ca1298003703fa9928013c7195b5c2411","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"becea76bc83c8fcb0caaf6e4f33f3647ae803303e606ee3f5a0a4e775e3c4681"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a4bfb4274cc4e48492b6/#project-b3d41aee-bf24-5299-97dd-2e16bc40012e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b3d41aee-bf24-5299-97dd-2e16bc40012e.json
b4349487-1879-5b90-9064-d1b86cb49850 | curated:greenergy-huuru-data-center-campus:data-hall-expansion | vcc-site-695cedb1c24a33253685 | curated:greenergy-huuru-data-center-campus | Greenergy Hüüru Data-Hall Expansion | Estonia | EE | 59.3861 | 24.562 | Point | campus | representative_point_of_exact_named_OSM_enclosure | OSM_way_1043819046_full_ordered_nodes_WGS84_Shapely_representative_point | community_named_enclosure_representative_point | community_source | campus_locator | Interior representative point of exact named community-mapped Greenergy enclosure. Not a surveyed or official boundary, building footprint, entrance, work extent or inferred office locator. The underlying enclosure's name, address, phone and website match the operator data-center page. |  | No source quantifies positional accuracy. Seven-decimal source coordinates and extra derived decimals are not survey accuracy. | 892c8445-2e50-5df3-b6a3-cb78285accd2 | site_preparation | 2026-07-30 | 75 | authoritative_physical_status_update | b3ee85bd-b902-5459-b3c0-510bee0b23e5 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://tensor.estate/news/mcf-group-100m-expansion | https://api.openstreetmap.org/api/0.6/way/1043819046/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-695cedb1c24a33253685/#project-b4349487-1879-5b90-9064-d1b86cb49850 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b4349487-1879-5b90-9064-d1b86cb49850.json
b4ff75a2-9d55-54ad-bf27-4c60b096eb0f | curated:riot-rockdale-site:amd-expansion-phases-3-4 | vcc-site-3dedcd29014f493a2abb | curated:riot-rockdale-site | Riot Rockdale AMD Expansion Phases 3 and 4 | United States | US | 30.5759 | -97.0789 | Point | campus | official_named_address_point | native_EPSG3857_to_EPSG4326_inverse_Web_Mercator | official_address_reference_point | official_source | campus_locator | One official state-aggregated site/structure address reference point matched to the exact facility address. Not a campus boundary, parcel, surveyed point, active AMD work footprint, entrance or precise building marker. Decimal places preserve calculation only. |  | Originating point placement and numeric positional accuracy are unspecified. Projection operation accuracy is also unavailable; no precision inferred. | 97d5f7f7-eccb-525f-8b01-7fe9559fc9b6 | under_construction | 2026-08-10 | 64 | authoritative_physical_status_update | d520228f-acc4-5a5a-98d8-291265e6a5f1 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.riotplatforms.com/riot-platforms-reports-second-quarter-2026-financial-results-and-strategic-highlights/ | https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0/query?objectIds=8633415&outFields=objectid,full_addr,add_number,st_name,post_comm,post_code,county,source,date_acq&returnGeometry=true&outSR=3857&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3dedcd29014f493a2abb/#project-b4ff75a2-9d55-54ad-bf27-4c60b096eb0f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b4ff75a2-9d55-54ad-bf27-4c60b096eb0f.json
b5625b8f-5e00-5fbe-b313-ba7adb980583 | curated:scala-praia-do-futuro-campus:sforpf01 | vcc-site-b12dddd73cb490c6bb64 | curated:scala-praia-do-futuro-campus | Scala SFORPF01 | Brazil | BR | -3.7515 | -38.458 | Polygon | project | direct_geometry | authoritative_surveyed_project_boundary | surveyed_project_boundary | official_source | official_boundary | Polygon transformed from the four surveyed project-boundary vertices in the official municipal plan; 5 metre stated uncertainty. | 5 |  | 295b555a-ca97-5752-b525-24ab75f62a71 | under_construction | 2026-08-04 | 70 | authoritative_physical_status_update | 985f5a20-bebc-584f-822f-7cbedc22858c | recent_authoritative_physical_observation_plus_official_boundary | FALSE | tracked_blind_ambiguous_locally_unsealed_identity_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-21","base":7.2,"confidence":0.99,"evidence_id":"62b2a499-44a6-59c1-b956-78abbbc1b8d5","high":7.2,"low":7.2,"method":"reported","metric":"critical_it_mw","notes":"Current first-party IT-capacity card value, retained at design stage. It is not installed, energized, operationally available, current load, gross facility demand, grid connection, generation, consumption, annual energy, or measured PUE.","stage":"design","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://filemanager-cdn.mziq.com/published/eacf948d-b138-408b-a8b7-1d6db21f3e84/6352b3fe-1887-43c5-be82-dbf4c54255d3_67224342000166-OPD07082026V01-001280434.pdf | https://urbanismoemeioambiente.fortaleza.ce.gov.br/images/urbanismo-e-meio-ambiente/infocidade/cppd/PROJETO_ARQUITETONICO_FL01-02.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b12dddd73cb490c6bb64/#project-b5625b8f-5e00-5fbe-b313-ba7adb980583 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b5625b8f-5e00-5fbe-b313-ba7adb980583.json
b649f6b4-e5be-5d52-9b44-0273c14cbea3 | imported:semiconductor-atlas:aws-fayette-county-ohio | vcc-site-04c2489b55d49bcb5ef5 | imported:semiconductor-atlas:aws-fayette-county-ohio | AWS Fayette County data center site | United States | US | 39.56 | -83.45 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Amazon names only the county; coordinates are the Fayette County point from its Wikipedia article (Nominatim was unavailable). |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | e5bdd89d-ddf9-528d-869d-0a61c6492cc2 | announced | 2024-12-24 | 658 | imported_documented_status | e5bdd89d-ddf9-528d-869d-0a61c6492cc2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e5bdd89d-ddf9-528d-869d-0a61c6492cc2","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-fayette-county-ohio"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.aboutamazon.com/news/aws/aws-continues-to-invest-in-ohio | https://www.aboutamazon.com/news/aws/aws-continues-to-invest-in-ohio | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AWS Fayette County data center site as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"aws-fayette-county-ohio"},"record":{"aliases":[],"id":"aws-fayette-county-ohio","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Fayette County","country":"US","lat":39.56,"lon":-83.45,"note":"Amazon names only the county; coordinates are the Fayette County point from its Wikipedia article (Nominatim was unavailable).","precision":"admin2","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2024-12-24","basis":"announced","metric":"investment","note":"Amazon's estimate for new data centers in Fayette County, within a $10 billion Ohio plan that could add up to eight new sites by the end of 2030.","qualifier":"approximately","source_ids":["s1"],"unit":"USD","value":5000000000}],"milestones":[{"date":"2024-12-24","event":"announced","kind":"actual","note":"Date Amazon updated its Ohio page with the $10 billion plan naming Fayette County.","source_ids":["s1"]}],"name":"AWS Fayette County data center site","notes":"The only source is Amazon's own page; no independent or later source on progress, land or power was found, so the record is thinly sourced.","parties":[{"name":"Amazon Web Services","role":"developer","source_ids":["s1"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-12-24","publisher":"Amazon","title":"AWS plans $10 billion infrastructure investment in Ohio, advancing the future of AI","type":"company","url":"https://www.aboutamazon.com/news/aws/aws-continues-to-invest-in-ohio"}],"status":"announced","status_as_of":"2024-12-24","status_source_ids":["s1"],"summary":"Amazon Web Services named Fayette County, Ohio, in December 2024 as the first new site in a $10 billion Ohio investment plan, estimating $5 billion for new data centers in the county. Amazon said its Ohio expansion could reach up to eight new sites by the end of 2030. It gave no address, power figure, job count or schedule for the Fayette County site.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e5bdd89d-ddf9-528d-869d-0a61c6492cc2"},"source_file":"datacenters/projects/aws-fayette-county-ohio.json","source_record_id":"aws-fayette-county-ohio","source_record_sha256":"219f67c5695f0c6dde0838b80d267da9b907d78f43726c4614922ba48207c891","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"85ad47d479b5f28757e0d4c6497199eb478e8eb90dbff4149207dc31c317c713"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-04c2489b55d49bcb5ef5/#project-b649f6b4-e5be-5d52-9b44-0273c14cbea3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b649f6b4-e5be-5d52-9b44-0273c14cbea3.json
b6d175dc-d92a-56ca-a1a7-85306c9de22a | imported:semiconductor-atlas:virtus-wustermark | vcc-site-dba81c9003e655831d45 | imported:semiconductor-atlas:virtus-wustermark | VIRTUS Wustermark campus | Germany | DE | 52.5463 | 12.9404 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Nominatim centroid of the municipality of Wustermark; sources name the municipality and the 50Hertz Wustermark substation but give no address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 8df23ef2-bd9e-5794-9b1e-e8c46ce5a4c5 | under_construction | 2026-06-01 | 134 | imported_documented_status | fe5e0d1a-24cf-5eca-9600-b08191632cdd | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8df23ef2-bd9e-5794-9b1e-e8c46ce5a4c5","notes":null,"party":"VIRTUS Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"virtus-wustermark"},{"evidence_id":"fe5e0d1a-24cf-5eca-9600-b08191632cdd","notes":null,"party":"VIRTUS Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"virtus-wustermark"},{"evidence_id":"1bf21fc1-2ca5-5f90-b1da-4cb3ca6f4e77","notes":null,"party":"VIRTUS Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"virtus-wustermark"},{"evidence_id":"8df23ef2-bd9e-5794-9b1e-e8c46ce5a4c5","notes":"Parent group of VIRTUS.","party":"ST Telemedia Global Data Centres","relationship_scope":"unknown","role":"owner","source_record_id":"virtus-wustermark"},{"evidence_id":"8df23ef2-bd9e-5794-9b1e-e8c46ce5a4c5","notes":"Holds a significant minority stake via Macquarie European Infrastructure Fund 7, per the 2023 release.","party":"Macquarie Asset Management","relationship_scope":"unknown","role":"investor","source_record_id":"virtus-wustermark"},{"evidence_id":"fe5e0d1a-24cf-5eca-9600-b08191632cdd","notes":"Transmission operator; dual direct 380 kV connections integrated with its Wustermark substation.","party":"50Hertz","relationship_scope":"unknown","role":"utility","source_record_id":"virtus-wustermark"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | ST Telemedia Global Data Centres |  |  |  |  | https://virtusdatacentres.com/press-releases/virtus-installs-two-of-europes-largest-super-grid-transformers-at-wustermark-campus-in-brandenburg | https://virtusdatacentres.com/press-releases/virtus-unveils-3bn-300mw-wustermark-megacampus-project | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve VIRTUS Wustermark campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"virtus-wustermark"},"record":{"aliases":["Berlin Data Centres Wustermark Campus","Wustermark Megacampus"],"id":"virtus-wustermark","last_reviewed":"2026-10-09","location":{"admin1":"Brandenburg","admin2":"Havelland","country":"DE","lat":52.5463,"locality":"Wustermark","lon":12.9404,"note":"Nominatim centroid of the municipality of Wustermark; sources name the municipality and the 50Hertz Wustermark substation but give no address.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2023-09-04","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1"],"unit":"EUR","value":3000000000},{"applies_to":"campus","as_of":"2026-06-01","basis":"planned","metric":"power_capacity","note":"Initial capacity, designed to scale; the 2023 release described 300 MW of incoming power across two campus locations in Wustermark.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Undated company campus page; as_of is the access date.","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":204},{"applies_to":"campus","as_of":"2026-06-01","basis":"under_construction","metric":"power_capacity","note":"Rating of the dedicated substation delivering power to the campus.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2023-09-04","basis":"reported","metric":"land_area","note":"Sources state more than 350,000 square metres.","qualifier":"more_than","source_ids":["s1","s3"],"unit":"hectares","value":35},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","qualifier":"up_to","source_ids":["s3"],"unit":"count","value":9}],"milestones":[{"date":"2023-09-04","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2026-H1","event":"other","kind":"actual","note":"VIRTUS announced on 2026-06-01 that two 185 MVA super-grid transformers for the 380 kV connection had been delivered and installed.","source_ids":["s2"]},{"date":"2026","event":"first_operational","kind":"planned","note":"Original 2023 target for Phase I; superseded by the later target below.","source_ids":["s1"]},{"date":"2028-H1","event":"first_operational","kind":"planned","note":"Company page projects operations in early 2028.","source_ids":["s3"]}],"name":"VIRTUS Wustermark campus","notes":"All sources are developer materials; no independent coverage could be opened this session. The 2023 release covered two campus locations within Wustermark, treated here as one record because they share the name and power arrangement.","parties":[{"name":"VIRTUS Data Centres","role":"developer","source_ids":["s1","s2","s3"]},{"name":"ST Telemedia Global Data Centres","note":"Parent group of VIRTUS.","role":"owner","source_ids":["s1"]},{"name":"Macquarie Asset Management","note":"Holds a significant minority stake via Macquarie European Infrastructure Fund 7, per the 2023 release.","role":"investor","source_ids":["s1"]},{"name":"50Hertz","note":"Transmission operator; dual direct 380 kV connections integrated with its Wustermark substation.","role":"utility","source_ids":["s2"]}],"power_sources":[{"description":"Dual direct connections to the 50Hertz 380 kV transmission network through a dedicated substation at the Wustermark grid node.","source_ids":["s2"],"type":"grid"},{"description":"The developer describes an electrical coupling to some of Germany's largest contiguous onshore wind farms beside the site.","source_ids":["s1","s3"],"type":"wind"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2023-09-04","publisher":"VIRTUS Data Centres","title":"VIRTUS Unveils €3BN, 300MW Wustermark Megacampus Project","type":"company","url":"https://virtusdatacentres.com/press-releases/virtus-unveils-3bn-300mw-wustermark-megacampus-project"},{"accessed":"2026-10-09","id":"s2","published":"2026-06-01","publisher":"VIRTUS Data Centres","title":"VIRTUS installs two of Europe's largest super-grid transformers at Wustermark campus in Brandenburg","type":"company","url":"https://virtusdatacentres.com/press-releases/virtus-installs-two-of-europes-largest-super-grid-transformers-at-wustermark-campus-in-brandenburg"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"VIRTUS Data Centres","title":"Berlin Data Centres ¦ Wustermark Campus","type":"company","url":"https://virtusdatacentres.com/locations/germany/berlin-data-centres-wustermark-campus"}],"status":"under_construction","status_as_of":"2026-06-01","status_source_ids":["s2","s3"],"summary":"VIRTUS Data Centres, part of ST Telemedia Global Data Centres, is developing a EUR 3 billion data center megacampus on more than 35 hectares in Wustermark, Havelland, about 12 km from Berlin's city limits. The campus is planned for up to nine data centers and 204 MW of IT load, with an initial 300 MW of power delivered through a dedicated substation with dual direct connections to the 50Hertz 380 kV grid, the first such connection for a Berlin-Brandenburg data center campus. Two 185 MVA super-grid transformers had been installed by June 2026; VIRTUS now projects operations from early 2028.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8df23ef2-bd9e-5794-9b1e-e8c46ce5a4c5","s2":"fe5e0d1a-24cf-5eca-9600-b08191632cdd","s3":"1bf21fc1-2ca5-5f90-b1da-4cb3ca6f4e77"},"source_file":"datacenters/projects/virtus-wustermark.json","source_record_id":"virtus-wustermark","source_record_sha256":"2280f1936acf26cd5cb763e4d09d8dc103abd5d9fcfa88388580dffb2d4a5649","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"91aa18b5ffa4d381faa2d0925636228f1d3da1e5e19cfb9c6ed32d0b2066c683"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dba81c9003e655831d45/#project-b6d175dc-d92a-56ca-a1a7-85306c9de22a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b6d175dc-d92a-56ca-a1a7-85306c9de22a.json
b6f0ed21-2ab2-51e2-971e-4e9512279101 | imported:semiconductor-atlas:terawulf-fluidstack-abernathy | vcc-site-8ea405601b72e53a6661 | imported:semiconductor-atlas:terawulf-fluidstack-abernathy | Abernathy HPC campus (TeraWulf and Fluidstack joint venture) | United States | US | 33.8322 | -101.8431 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town coordinates from Wikipedia; the sources name Abernathy but give no address. The town spans Hale and Lubbock counties, so no county is recorded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 9160242e-d5c4-5428-b55d-9234947b7f01 | under_construction | 2026-02-27 | 228 | imported_documented_status | 83750040-3c48-5887-a3c7-fac81d9ab36f | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9160242e-d5c4-5428-b55d-9234947b7f01","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"1f3e196a-da54-548c-8d11-d91607c3cae3","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"9160242e-d5c4-5428-b55d-9234947b7f01","notes":"Joint venture partner; expected to continue leading the project after its investor group buys TeraWulf's stake.","party":"Fluidstack","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"7ace9139-658c-5289-bbd4-259c07aad802","notes":"Joint venture partner; expected to continue leading the project after its investor group buys TeraWulf's stake.","party":"Fluidstack","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"9160242e-d5c4-5428-b55d-9234947b7f01","notes":"Holds a 50.1% interest per the 10-K and July 2026 release (the October 2025 announcement said 51%); agreed in July 2026 to sell it to a Fluidstack-led investor group for about $530 million, with closing not reported by August 2026.","party":"TeraWulf","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"1f3e196a-da54-548c-8d11-d91607c3cae3","notes":"Holds a 50.1% interest per the 10-K and July 2026 release (the October 2025 announcement said 51%); agreed in July 2026 to sell it to a Fluidstack-led investor group for about $530 million, with closing not reported by August 2026.","party":"TeraWulf","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"7ace9139-658c-5289-bbd4-259c07aad802","notes":"Holds a 50.1% interest per the 10-K and July 2026 release (the October 2025 announcement said 51%); agreed in July 2026 to sell it to a Fluidstack-led investor group for about $530 million, with closing not reported by August 2026.","party":"TeraWulf","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"455d2370-9bc6-5192-921d-f25e2226335d","notes":"Holds a 50.1% interest per the 10-K and July 2026 release (the October 2025 announcement said 51%); agreed in July 2026 to sell it to a Fluidstack-led investor group for about $530 million, with closing not reported by August 2026.","party":"TeraWulf","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"1f3e196a-da54-548c-8d11-d91607c3cae3","notes":"Fluidstack CS I holds the other joint venture interest.","party":"Fluidstack","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"7ace9139-658c-5289-bbd4-259c07aad802","notes":"Fluidstack CS I holds the other joint venture interest.","party":"Fluidstack","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"9160242e-d5c4-5428-b55d-9234947b7f01","notes":"Fluidstack USA III pre-leased the full 168 MW under a 25-year lease that can be shortened to 20 or 15 years; Google backstops about $1.3 billion of the lease obligations.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-fluidstack-abernathy"},{"evidence_id":"1f3e196a-da54-548c-8d11-d91607c3cae3","notes":"Fluidstack USA III pre-leased the full 168 MW under a 25-year lease that can be shortened to 20 or 15 years; Google backstops about $1.3 billion of the lease obligations.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-fluidstack-abernathy"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Fluidstack; TeraWulf |  |  | Fluidstack |  | https://investors.terawulf.com/news-events/press-releases/detail/128/terawulf-and-fluidstack-announce-successful-pricing-of-project-financing-for-168-mw-hpc-compute-joint-venture | https://investors.terawulf.com/news-events/press-releases/detail/121/terawulf-expands-strategic-partnership-with-fluidstack-through-new-168-mw-ai-compute-joint-venture | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Abernathy HPC campus (TeraWulf and Fluidstack joint venture) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"terawulf-fluidstack-abernathy"},"record":{"aliases":["Abernathy HPC Campus"],"id":"terawulf-fluidstack-abernathy","last_reviewed":"2026-10-09","location":{"admin1":"Texas","country":"US","lat":33.8322,"locality":"Abernathy","lon":-101.8431,"note":"Town coordinates from Wikipedia; the sources name Abernathy but give no address. The town spans Hale and Lubbock counties, so no county is recorded.","precision":"locality","source_ids":["s1","s3","s6"]},"metrics":[{"applies_to":"campus","as_of":"2025-10-28","basis":"contracted","metric":"power_capacity","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":168},{"applies_to":"campus","as_of":"2025-12-18","basis":"planned","metric":"power_capacity","note":"Gross power capacity.","power_scope":"facility","qualifier":"up_to","source_ids":["s1","s2"],"unit":"MW","value":240}],"milestones":[{"date":"2025-10-28","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-12-18","event":"other","kind":"actual","note":"Project-level construction financing priced.","source_ids":["s2"]},{"date":"2026-H2","event":"first_operational","kind":"planned","note":"Targeted commissioning and delivery.","source_ids":["s2","s3"]},{"date":"2026-07-06","event":"other","kind":"actual","note":"TeraWulf agreed to sell its entire 50.1% interest to a Fluidstack-led investor group; the August 2026 results still described it as an agreement.","source_ids":["s4","s5"]}],"name":"Abernathy HPC campus (TeraWulf and Fluidstack joint venture)","parties":[{"name":"TeraWulf","role":"developer","source_ids":["s1","s3"]},{"name":"Fluidstack","note":"Joint venture partner; expected to continue leading the project after its investor group buys TeraWulf's stake.","role":"developer","source_ids":["s1","s4"]},{"name":"TeraWulf","note":"Holds a 50.1% interest per the 10-K and July 2026 release (the October 2025 announcement said 51%); agreed in July 2026 to sell it to a Fluidstack-led investor group for about $530 million, with closing not reported by August 2026.","role":"owner","source_ids":["s1","s3","s4","s5"]},{"name":"Fluidstack","note":"Fluidstack CS I holds the other joint venture interest.","role":"owner","source_ids":["s3","s4"]},{"name":"Fluidstack","note":"Fluidstack USA III pre-leased the full 168 MW under a 25-year lease that can be shortened to 20 or 15 years; Google backstops about $1.3 billion of the lease obligations.","role":"tenant","source_ids":["s1","s3"]}],"power_sources":[{"description":"Campus is located within the Southwest Power Pool market.","source_ids":["s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-10-28","publisher":"TeraWulf","title":"TeraWulf Expands Strategic Partnership with Fluidstack Through New 168 MW AI Compute Joint Venture","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/121/terawulf-expands-strategic-partnership-with-fluidstack-through-new-168-mw-ai-compute-joint-venture"},{"accessed":"2026-10-09","id":"s2","published":"2025-12-18","publisher":"TeraWulf","title":"TeraWulf and Fluidstack Announce Successful Pricing of Project Financing for 168 MW HPC Compute Joint Venture","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/128/terawulf-and-fluidstack-announce-successful-pricing-of-project-financing-for-168-mw-hpc-compute-joint-venture"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929023534/https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm","id":"s3","published":"2026-02-27","publisher":"U.S. Securities and Exchange Commission (TeraWulf filing)","title":"TeraWulf Inc. Form 10-K for the fiscal year ended December 31, 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-06","publisher":"TeraWulf","title":"TeraWulf Announces Anthropic Lease at Justified Data Campus and Sale of Majority Interest in Abernathy Joint Venture to Fluidstack","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/142/terawulf-announces-anthropic-lease-at-justified-data-campus-and-sale-of-majority-interest-in-abernathy-joint-venture-to-fluidstack"},{"accessed":"2026-10-09","id":"s5","published":"2026-08-05","publisher":"TeraWulf","title":"TeraWulf Reports Second Quarter 2026 Results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Abernathy, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Abernathy,_Texas"}],"status":"under_construction","status_as_of":"2026-02-27","status_source_ids":["s2","s3"],"summary":"AI data center campus in Abernathy, Texas, developed by a joint venture of TeraWulf and Fluidstack announced in October 2025. It is designed for 168 MW of critical IT load (up to 240 MW gross) and is fully pre-leased to a Fluidstack entity for up to 25 years, with Google backstopping about $1.3 billion of the lease obligations; the end user is described only as a global hyperscale AI platform. Project financing was priced in December 2025 and commissioning was targeted for the second half of 2026. In July 2026 TeraWulf agreed to sell its 50.1% stake to a Fluidstack-led investor group, with Fluidstack to keep leading the project.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9160242e-d5c4-5428-b55d-9234947b7f01","s2":"83750040-3c48-5887-a3c7-fac81d9ab36f","s3":"1f3e196a-da54-548c-8d11-d91607c3cae3","s4":"7ace9139-658c-5289-bbd4-259c07aad802","s5":"455d2370-9bc6-5192-921d-f25e2226335d","s6":"415364a5-823e-574c-bef4-748bb34d2356"},"source_file":"datacenters/projects/terawulf-fluidstack-abernathy.json","source_record_id":"terawulf-fluidstack-abernathy","source_record_sha256":"c78e69781f5e1182302f758390b03e4b52f85cc85c10d9fbb82d5c157135f5a3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"f237216344f2a9bdc1f81adb9e25380882befa51cfd73d5971cc152953f61607"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8ea405601b72e53a6661/#project-b6f0ed21-2ab2-51e2-971e-4e9512279101 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b6f0ed21-2ab2-51e2-971e-4e9512279101.json
b74385b8-0724-5b4d-b192-4aa5a1c45885 | imported:semiconductor-atlas:iren-childress | vcc-site-b80c969b486b2844a8d9 | imported:semiconductor-atlas:iren-childress | IREN Childress data center campus | United States | US | 34.4281 | -100.215 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City coordinates from Wikipedia; IREN names the site after Childress but publishes no street address or county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a6ebeceb-ddd9-5507-b6d7-40f1189162b4 | partially_operational | 2026-08-27 | 47 | imported_documented_status | 3464cc5f-4960-5039-a630-b4fdca2f4fed | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a6ebeceb-ddd9-5507-b6d7-40f1189162b4","notes":null,"party":"IREN","relationship_scope":"unknown","role":"developer","source_record_id":"iren-childress"},{"evidence_id":"3464cc5f-4960-5039-a630-b4fdca2f4fed","notes":null,"party":"IREN","relationship_scope":"unknown","role":"developer","source_record_id":"iren-childress"},{"evidence_id":"a6ebeceb-ddd9-5507-b6d7-40f1189162b4","notes":"IREN describes the site as freehold and states that it owns its data centers, including the land, grid connections and substations.","party":"IREN","relationship_scope":"unknown","role":"owner","source_record_id":"iren-childress"},{"evidence_id":"3464cc5f-4960-5039-a630-b4fdca2f4fed","notes":"IREN describes the site as freehold and states that it owns its data centers, including the land, grid connections and substations.","party":"IREN","relationship_scope":"unknown","role":"owner","source_record_id":"iren-childress"},{"evidence_id":"3464cc5f-4960-5039-a630-b4fdca2f4fed","notes":"IREN states that it develops, owns and operates its data centers.","party":"IREN","relationship_scope":"unknown","role":"operator","source_record_id":"iren-childress"},{"evidence_id":"3464cc5f-4960-5039-a630-b4fdca2f4fed","notes":"Customer for GPU cloud services delivered from the four Horizon facilities under a five-year agreement of about $9.7 billion.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"iren-childress"},{"evidence_id":"87972be2-72f1-5de6-a7aa-d28633e61f65","notes":"Customer for GPU cloud services delivered from the four Horizon facilities under a five-year agreement of about $9.7 billion.","party":"Microsoft","relationship_scope":"unknown","role":"tenant","source_record_id":"iren-childress"},{"evidence_id":"3464cc5f-4960-5039-a630-b4fdca2f4fed","notes":"Horizon 1 runs NVIDIA GB300 NVL72 systems, which NVIDIA tested for its Exemplar Cloud status.","party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"iren-childress"},{"evidence_id":"87972be2-72f1-5de6-a7aa-d28633e61f65","notes":"Horizon 1 runs NVIDIA GB300 NVL72 systems, which NVIDIA tested for its Exemplar Cloud status.","party":"NVIDIA","relationship_scope":"unknown","role":"hardware_supplier","source_record_id":"iren-childress"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | IREN | IREN |  | Microsoft |  | https://www.sec.gov/Archives/edgar/data/1878848/000187884826000052/iren-20260630.htm | https://iren.com/data-centers/childress | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve IREN Childress data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"iren-childress","source_relations":[{"reason":"Crusoe/Lancium newly announced campus and IREN mining/HPC conversion campus are separately described operators/developments, sharing only the Childress town centroid.","relationship":"separate_named_developments","source_id":"crusoe-lancium-childress-texas"}]},"record":{"aliases":["Horizon data centers (Childress)"],"id":"iren-childress","last_reviewed":"2026-10-09","location":{"admin1":"Texas","country":"US","lat":34.4281,"locality":"Childress","lon":-100.215,"note":"City coordinates from Wikipedia; IREN names the site after Childress but publishes no street address or county.","precision":"locality","source_ids":["s1","s2","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-30","basis":"planned","metric":"power_capacity","note":"IREN's 10-K lists Childress at 750 MW of total planned power capacity in gross MW.","power_scope":"facility","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":750},{"applies_to":"phase","as_of":"2026-08","basis":"operational","metric":"power_capacity","phase_label":"Horizon 1","power_scope":"it_load","qualifier":"exact","source_ids":["s3","s4"],"unit":"MW","value":50},{"applies_to":"phase","as_of":"2026-08-27","basis":"under_construction","metric":"power_capacity","note":"Three 50 MW (IT) deployments; Horizon 2 in commissioning and Horizons 3 and 4 in late-stage construction in August 2026.","phase_label":"Horizons 2-4","power_scope":"it_load","qualifier":"exact","source_ids":["s3","s4"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2026-06-30","basis":"acquired","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":576}],"milestones":[{"date":"2025-11","event":"other","kind":"actual","note":"Five-year Microsoft agreement announced, covering the Horizon 1-4 facilities at Childress.","source_ids":["s2"]},{"date":"2026-08","event":"other","kind":"actual","note":"Horizon 1 delivered to and accepted by Microsoft.","source_ids":["s2","s3"]},{"date":"2026-Q4","event":"other","kind":"planned","note":"Targeted phased delivery of Horizons 2-4; grace periods under the Microsoft agreement run from mid-Q4 2026 to the beginning of Q2 2027.","source_ids":["s2","s4"]}],"name":"IREN Childress data center campus","parties":[{"name":"IREN","role":"developer","source_ids":["s1","s2"]},{"name":"IREN","note":"IREN describes the site as freehold and states that it owns its data centers, including the land, grid connections and substations.","role":"owner","source_ids":["s1","s2"]},{"name":"IREN","note":"IREN states that it develops, owns and operates its data centers.","role":"operator","source_ids":["s2"]},{"name":"Microsoft","note":"Customer for GPU cloud services delivered from the four Horizon facilities under a five-year agreement of about $9.7 billion.","role":"tenant","source_ids":["s2","s3"]},{"name":"NVIDIA","note":"Horizon 1 runs NVIDIA GB300 NVL72 systems, which NVIDIA tested for its Exemplar Cloud status.","role":"hardware_supplier","source_ids":["s2","s3"]}],"power_sources":[{"description":"Direct connection to the ERCOT grid via on-site substations owned by IREN; IREN bought renewable energy certificates covering all of the site's consumption through June 2026.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"IREN","title":"Childress Data Center ¦ 750MW AI-Optimised Facility","type":"company","url":"https://iren.com/data-centers/childress"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260912074420/https://www.sec.gov/Archives/edgar/data/1878848/000187884826000052/iren-20260630.htm","id":"s2","published":"2026-08-27","publisher":"U.S. Securities and Exchange Commission (IREN filing)","title":"IREN Ltd Form 10-K for the fiscal year ended June 30, 2026","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1878848/000187884826000052/iren-20260630.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-13","publisher":"IREN","title":"IREN Delivers Horizon 1 to Microsoft and Achieves NVIDIA Exemplar Cloud Status on GB300 NVL72","type":"company","url":"https://www.sec.gov/Archives/edgar/data/1878848/000114036126032638/ef20080141_ex99-1.htm"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-27","publisher":"IREN","title":"IREN Reports FY26 Results","type":"company","url":"https://www.sec.gov/Archives/edgar/data/1878848/000187884826000051/irenreportsfy26results.htm"},{"accessed":"2026-10-09","id":"s5","published":"2026-03-04","publisher":"IREN","title":"IREN Expands AI Cloud Capacity to 150,000 GPUs","type":"company","url":"https://www.sec.gov/Archives/edgar/data/1878848/000114036126007905/ny20064909x3_ex99-1.htm"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Childress, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Childress,_Texas"}],"status":"partially_operational","status_as_of":"2026-08-27","status_source_ids":["s2","s4","s5"],"summary":"IREN campus at Childress in the Texas Panhandle with 750 MW of planned gross power capacity on a 576-acre freehold site, connected to the ERCOT grid through IREN-owned on-site substations. It hosts IREN's liquid-cooled Horizon AI cloud buildings, which serve Microsoft under a five-year contract of about $9.7 billion announced in November 2025. Horizon 1, a 50 MW (IT) deployment of NVIDIA GB300 NVL72 systems, was delivered to and accepted by Microsoft in August 2026; Horizon 2 was in commissioning and Horizons 3 and 4 in late-stage construction, with delivery targeted for the fourth quarter of 2026.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a6ebeceb-ddd9-5507-b6d7-40f1189162b4","s2":"3464cc5f-4960-5039-a630-b4fdca2f4fed","s3":"87972be2-72f1-5de6-a7aa-d28633e61f65","s4":"b1119eb9-3fd9-506e-9354-8fe940376027","s5":"686ddcd6-693c-5b99-8f0a-6975485e19ff","s6":"37a32cc5-39a0-5b1b-910b-3ebd913fa3c5"},"source_file":"datacenters/projects/iren-childress.json","source_record_id":"iren-childress","source_record_sha256":"2e84178afc0deb7b62de37b97e373907adbcd669801951165b008127658131de","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"ec58905442d037bd132f45a7b3b3ba14f7d327d7290df9045cef7f2bfee9aad9"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b80c969b486b2844a8d9/#project-b74385b8-0724-5b4d-b192-4aa5a1c45885 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b74385b8-0724-5b4d-b192-4aa5a1c45885.json
b75695b9-38e3-58ec-baf2-039179ab353a | curated:coreweave-chirisa-lancaster-greenfield-road-campus:phase-1-adaptive-reuse | vcc-site-9b9b5ef71cedda52fd47 | curated:coreweave-chirisa-lancaster-greenfield-road-campus | CoreWeave/Chirisa Lancaster Greenfield Phase 1 Adaptive-Reuse Project | United States | US | 40.0487 | -76.2561 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The address identifies the adaptive-reuse property, but the Census point is not the existing shell or Phase 1 footprint. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 6600dddb-f2d8-5458-8e71-b43f77cc5e01 | under_construction | 2026-07-22 | 83 | authoritative_physical_status_update | 0eb488ab-3c0c-5223-86d8-2b47a96e7476 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.12 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://chirisatechnologyparks.com/ | https://geocoding.geo.census.gov/geocoder/ | [{"identity_decision":{"decision":"multi_site_program","flags":["administrative_locator_not_project_geometry","multiple_sites_no_single_map_point"],"rationale":"Source explicitly bundles Greenfield Road phase 1/phase 2 and a planned Harrisburg Pike site. Only the Greenfield Phase 1 adaptive-reuse project is in the current release; attach the broad source as program context, retain Harrisburg Pike as an unmapped component, and do not treat a Lancaster city centroid as either site.","related_project_stable_keys":["curated:coreweave-chirisa-lancaster-greenfield-road-campus:phase-1-adaptive-reuse"],"source_record_id":"coreweave-lancaster-pennsylvania","unmapped_components":[{"name":"1375 Harrisburg Pike planned site","reason":"Explicit separate address in source summary; not geocoded and no matching current release project."}]},"record":{"aliases":["Lancaster AI Hub","Lancaster East data center"],"id":"coreweave-lancaster-pennsylvania","last_reviewed":"2026-10-09","location":{"admin1":"Pennsylvania","admin2":"Lancaster County","country":"US","lat":40.0397,"locality":"Lancaster","lon":-76.3044,"note":"City centroid from Wikipedia (s5). Sources give addresses at 216 Greenfield Road and 1375 Harrisburg Pike, but these were not geocoded, so the point is the city centroid rather than either site.","precision":"locality","source_ids":["s1","s2","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-07-15","basis":"announced","metric":"investment","note":"CoreWeave's intent to commit funds to equip the data center, as worded in its newsroom copy of the announcement.","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":6000000000},{"applies_to":"campus","as_of":"2025-07-15","basis":"announced","metric":"investment","note":"The investor-relations copy of the same July 15, 2025 announcement words the commitment as up to 6 billion US dollars rather than more than 6 billion.","qualifier":"up_to","source_ids":["s6"],"unit":"USD","value":6000000000},{"applies_to":"campus","as_of":"2025-09-16","basis":"reported","metric":"investment","note":"Joint venture funding from Blue Owl-managed funds and affiliates of Chirisa Technology Parks and Machine Investment Group.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":4000000000},{"applies_to":"campus","as_of":"2025-10-19","basis":"reported","metric":"investment","note":"Total cost of the Lancaster AI Hub across the Greenfield Road and Harrisburg Pike sites as reported by LNP.","qualifier":"exact","source_ids":["s4"],"unit":"USD","value":10000000000},{"applies_to":"phase","as_of":"2025-10-19","basis":"reported","metric":"investment","note":"Cost to build and equip, including computer equipment.","phase_label":"Phase two","qualifier":"up_to","source_ids":["s4"],"unit":"USD","value":2500000000},{"applies_to":"phase","as_of":"2025-07-15","basis":"planned","metric":"power_capacity","phase_label":"Initial capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2025-07-15","basis":"planned","metric":"power_capacity","note":"Potential expansion.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2025-08-08","basis":"planned","metric":"floor_area","phase_label":"Phase one (216 Greenfield Road)","qualifier":"exact","source_ids":["s2"],"unit":"sq_ft","value":450000},{"applies_to":"phase","as_of":"2025-10-19","basis":"planned","metric":"floor_area","note":"Two-story new building.","phase_label":"Phase two","qualifier":"exact","source_ids":["s4"],"unit":"sq_ft","value":735128},{"applies_to":"campus","as_of":"2025-07-15","basis":"planned","metric":"jobs_construction","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":600},{"applies_to":"campus","as_of":"2025-07-15","basis":"planned","metric":"jobs_permanent","note":"About 70 at launch, growing to about 175 over time.","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":175}],"milestones":[{"date":"2025-07-15","event":"announced","kind":"actual","note":"Announced at the Pennsylvania Energy and Innovation Summit in Pittsburgh.","source_ids":["s1"]},{"date":"2025","event":"construction_started","kind":"actual","note":"Demolition at the Greenfield Road phase one site was underway by early August 2025, and phase one was described as under construction in October 2025; it needed no land development plan because it reuses an existing building footprint.","source_ids":["s2","s4"]},{"date":"2025-09-16","event":"other","kind":"actual","note":"4 billion US dollar joint venture with Blue Owl-managed funds announced.","source_ids":["s3"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Phase one completion targeted for summer 2027.","source_ids":["s2"]},{"date":"2027","event":"other","kind":"planned","note":"Developer said phase two could be online by mid to late 2027, pending city planning commission land development approval.","source_ids":["s4"]}],"name":"CoreWeave Lancaster AI data center (Lancaster AI Hub)","notes":"CoreWeave's two published copies of its July 15, 2025 announcement differ: the newsroom copy says more than 6 billion US dollars and the investor-relations copy says up to 6 billion; both are recorded. LNP puts the whole Lancaster AI Hub at 10 billion US dollars, a figure that may include equipment and both sites.","parties":[{"name":"Chirisa Technology Parks","role":"developer","source_ids":["s1","s3","s4"]},{"name":"Machine Investment Group","note":"Named as co-developer in CoreWeave's announcement.","role":"developer","source_ids":["s1","s4"]},{"name":"Machine Investment Group","note":"Joint venture partner in the 4 billion US dollar funding.","role":"investor","source_ids":["s3"]},{"name":"Blue Owl Capital","note":"Funds managed by Blue Owl are joint venture partners.","role":"investor","source_ids":["s3"]},{"name":"CoreWeave","role":"tenant","source_ids":["s1","s3","s4"]},{"name":"CoreWeave","note":"Described as having invested in the campus.","role":"investor","source_ids":["s3"]},{"name":"PPL","note":"A new PPL substation and switchyard are proposed next to the phase two building.","role":"utility","source_ids":["s4"]}],"power_sources":[{"description":"Grid supply from PPL with a proposed new substation and switchyard; the developer says it is spending 200 million US dollars on grid upgrades.","source_ids":["s4"],"type":"grid"},{"description":"Backup generators for power outages, located mainly between the two Greenfield Road buildings; the fuel is not stated.","source_ids":["s4"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-07-15","publisher":"CoreWeave","title":"CoreWeave Announces Multi-Billion Dollar Commitment to AI Infrastructure in Pennsylvania","type":"company","url":"https://coreweave.com/news/coreweave-announces-multi-billion-dollar-commitment-to-ai-infrastructure-in-pennsylvania"},{"accessed":"2026-10-09","id":"s2","published":"2025-08-08","publisher":"Government Technology (LNP via Tribune Content Agency)","title":"Lancaster, Pa., Hearing to Revisit Data Center Zoning Decision","type":"news","url":"https://www.govtech.com/products/lancaster-pa-hearing-to-revisit-data-center-zoning-decision"},{"accessed":"2026-10-09","id":"s3","published":"2025-09-16","publisher":"Holland & Knight","title":"Holland & Knight Advises Chirisa Technology Parks in $4 Billion Joint Venture Partnership for Lancaster Campus","type":"other","url":"https://www.hklaw.com/en/news/pressreleases/2025/09/hk-advises-chirisa-technology-parks-in-4-billion-joint-venture"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260911180724/https://www.witf.org/2025/10/19/data-centers-second-phase-expected-to-cost-up-to-2-5-billion-in-lancaster-county/","id":"s4","published":"2025-10-19","publisher":"WITF (LNP ¦ LancasterOnline)","title":"Data center's second phase expected to cost up to $2.5 billion in Lancaster County","type":"news","url":"https://www.witf.org/2025/10/19/data-centers-second-phase-expected-to-cost-up-to-2-5-billion-in-lancaster-county/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Lancaster, Pennsylvania","type":"other","url":"https://en.wikipedia.org/wiki/Lancaster,_Pennsylvania"},{"accessed":"2026-10-09","id":"s6","published":"2025-07-15","publisher":"CoreWeave","title":"CoreWeave Announces Multi-Billion Dollar Commitment to AI Infrastructure in Pennsylvania","type":"company","url":"https://investors.coreweave.com/news/news-details/2025/CoreWeave-Announces-Multi-Billion-Dollar-Commitment-to-AI-Infrastructure-in-Pennsylvania/default.aspx"}],"status":"under_construction","status_as_of":"2025-10-19","status_source_ids":["s4"],"summary":"AI data center development in Lancaster, Pennsylvania, on former LSC Communications printing plant sites, co-developed by Chirisa Technology Parks and Machine Investment Group with CoreWeave as tenant. In July 2025 CoreWeave said it intended to commit about 6 billion US dollars to equip an initial 100 MW facility expandable to 300 MW. Phase one reuses the plant at 216 Greenfield Road and was under construction by October 2025, targeting summer 2027. A new-build phase two of about 735,000 sq ft needed city land development approval; a site at 1375 Harrisburg Pike is also planned. A 4 billion US dollar joint venture with Blue Owl funds the campus.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3d8d0c3d-24da-5903-a27e-3ace4ec4925f","s2":"5342973f-d3b5-594a-a7b3-6444d43094b8","s3":"b5d3e30a-4c1d-55a6-a4a7-fe480b54fcbd","s4":"2ddfa1d8-0a27-58a7-bc6a-1086d024ffa7","s5":"6185f0c2-f590-51d1-ab06-be2e0377a546","s6":"3055e2e6-d496-5e2a-9537-aa0e26047f25"},"source_file":"datacenters/projects/coreweave-lancaster-pennsylvania.json","source_record_id":"coreweave-lancaster-pennsylvania","source_record_sha256":"3da7b985dea6aab54b6d7610b08c127892b84b6825d60e166f63e4d3b65a78de","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a356ca1ca775478ada1545334dce0cb31ac058488deb6e1e43780d99e5f75f91"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9b9b5ef71cedda52fd47/#project-b75695b9-38e3-58ec-baf2-039179ab353a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b75695b9-38e3-58ec-baf2-039179ab353a.json
b75df57e-ef16-50f9-b1d8-ae13bae596a5 | imported:semiconductor-atlas:stt-gdc-fairview-quezon-city | vcc-site-78bd59a55f0376662286 | imported:semiconductor-atlas:stt-gdc-fairview-quezon-city | STT Fairview data center campus | Philippines | PH | 14.65 | 121.0475 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | STT's factsheet gives the address as Regalado Avenue, Fairview, Quezon City. The point is the Quezon City coordinate from its Wikipedia article, so it marks the city centre, several kilometres south of the Fairview area; precision is therefore given at city level. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 9adc2e4b-72ef-566e-bf9f-4008c8f42a92 | under_construction | 2026-04-20 | 176 | imported_documented_status | 9004580a-303b-52dc-adb3-4c3642ecda48 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9adc2e4b-72ef-566e-bf9f-4008c8f42a92","notes":"Joint venture of Globe Telecom, Ayala Corporation and ST Telemedia Global Data Centres.","party":"STT GDC Philippines (Globe STT GDC Inc.)","relationship_scope":"unknown","role":"developer","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"4a885e19-5d83-5bdc-8f9d-2b2e7e50bfab","notes":"Joint venture of Globe Telecom, Ayala Corporation and ST Telemedia Global Data Centres.","party":"STT GDC Philippines (Globe STT GDC Inc.)","relationship_scope":"unknown","role":"developer","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9004580a-303b-52dc-adb3-4c3642ecda48","notes":"Joint venture of Globe Telecom, Ayala Corporation and ST Telemedia Global Data Centres.","party":"STT GDC Philippines (Globe STT GDC Inc.)","relationship_scope":"unknown","role":"developer","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"860d3eb0-ae8e-514f-b13d-fcfcad984ded","notes":"STT GDC Philippines presents STT Fairview 1 as its flagship data centre.","party":"STT GDC Philippines (Globe STT GDC Inc.)","relationship_scope":"unknown","role":"operator","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9adc2e4b-72ef-566e-bf9f-4008c8f42a92","notes":"Joint venture partner in STT GDC Philippines.","party":"Globe Telecom","relationship_scope":"unknown","role":"investor","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9004580a-303b-52dc-adb3-4c3642ecda48","notes":"Joint venture partner in STT GDC Philippines.","party":"Globe Telecom","relationship_scope":"unknown","role":"investor","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9adc2e4b-72ef-566e-bf9f-4008c8f42a92","notes":"Joint venture partner in STT GDC Philippines.","party":"Ayala Corporation","relationship_scope":"unknown","role":"investor","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9004580a-303b-52dc-adb3-4c3642ecda48","notes":"Joint venture partner in STT GDC Philippines.","party":"Ayala Corporation","relationship_scope":"unknown","role":"investor","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9adc2e4b-72ef-566e-bf9f-4008c8f42a92","notes":"Singapore-based joint venture partner in STT GDC Philippines.","party":"ST Telemedia Global Data Centres","relationship_scope":"unknown","role":"investor","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9004580a-303b-52dc-adb3-4c3642ecda48","notes":"Singapore-based joint venture partner in STT GDC Philippines.","party":"ST Telemedia Global Data Centres","relationship_scope":"unknown","role":"investor","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"bfaea9b5-88e3-55f4-8016-000bc863d7bc","notes":"Awarded the contract for the first phase of STT Fairview 1 in November 2023, together with First Balfour.","party":"Leighton Asia","relationship_scope":"unknown","role":"builder","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"bfaea9b5-88e3-55f4-8016-000bc863d7bc","notes":null,"party":"First Balfour","relationship_scope":"unknown","role":"builder","source_record_id":"stt-gdc-fairview-quezon-city"},{"evidence_id":"9004580a-303b-52dc-adb3-4c3642ecda48","notes":"Meralco's retail electricity arm; 10-year deal for up to 40.5 MW of clean energy covering the Fairview and Cavite data centers.","party":"MPower (Meralco)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"stt-gdc-fairview-quezon-city"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | STT GDC Philippines (Globe STT GDC Inc.) |  |  |  | https://www.philstar.com/business/2026/04/20/2522112/ayala-led-data-center-builder-inks-supply-deal-meralco | https://w.media/stt-gdc-announces-plans-to-build-sustainable-carrier-neutral-data-center-in-the-philippines/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve STT Fairview data center campus as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"stt-gdc-fairview-quezon-city"},"record":{"aliases":["STT Fairview","STT Fairview 1"],"id":"stt-gdc-fairview-quezon-city","last_reviewed":"2026-10-09","location":{"admin1":"Metro Manila","admin2":"Quezon City","country":"PH","lat":14.65,"locality":"Fairview (Regalado Avenue)","lon":121.0475,"note":"STT's factsheet gives the address as Regalado Avenue, Fairview, Quezon City. The point is the Quezon City coordinate from its Wikipedia article, so it marks the city centre, several kilometres south of the Fairview area; precision is therefore given at city level.","precision":"admin2","source_ids":["s1","s3","s6"]},"metrics":[{"applies_to":"campus","as_of":"2024-10","basis":"planned","metric":"power_capacity","note":"IT load at full build-out across four buildings. The power section of STT's 2024 factsheet gives a campus total of 128 MW instead, without explanation. STT's October 2025 release and the April 2026 Philippine Star report also give 124 MW, without saying whether it is IT load.","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":124},{"applies_to":"phase","as_of":"2024-10","basis":"planned","metric":"power_capacity","phase_label":"STT Fairview 1 (first building)","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":28},{"applies_to":"phase","as_of":"2026-04-20","basis":"planned","metric":"power_capacity","note":"Initial capacity the Philippine Star said would open during 2026.","phase_label":"Initial opening capacity (2026)","power_scope":"unspecified","qualifier":"exact","source_ids":["s5"],"unit":"MW","value":12},{"applies_to":"campus","as_of":"2026-04-20","basis":"reported","metric":"investment","note":"Single news source: the Philippine Star states the project costs USD 1 billion without attributing the figure, and does not say whether it covers only Fairview. No company source opened for this record gives it.","qualifier":"exact","source_ids":["s5"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2024-10","basis":"planned","metric":"floor_area","note":"Gross floor area across four buildings.","qualifier":"more_than","source_ids":["s1","s3"],"unit":"sq_m","value":83000},{"applies_to":"phase","as_of":"2024-10","basis":"planned","metric":"floor_area","note":"Gross floor area; the factsheet gives 8,619 square metres of net lettable area.","phase_label":"STT Fairview 1 (first building)","qualifier":"exact","source_ids":["s3"],"unit":"sq_m","value":24918},{"applies_to":"campus","as_of":"2024-10","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s3"],"unit":"count","value":4}],"milestones":[{"date":"2023-05-19","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2023-11","event":"other","kind":"actual","note":"Leighton Asia and First Balfour awarded the contract for the first phase of STT Fairview 1.","source_ids":["s2"]},{"date":"2026","event":"first_operational","kind":"planned","note":"Earlier targets slipped: the 2024 factsheet gave ready-for-service in Q2 2025 and STT said in October 2025 that Fairview 1 was on track for full operations in Q4 2025; in April 2026 the Philippine Star said the campus would partly open during 2026 with 12 MW.","source_ids":["s3","s4","s5"]}],"name":"STT Fairview data center campus","notes":"Whether STT Fairview 1 was operating by October 2026 is unconfirmed: STT said in October 2025 that it was on track for full operations in Q4 2025, but the April 2026 Philippine Star report described the campus as only partly opening during 2026. The USD 1 billion cost comes from that single news report. A third-party report that Fairview 1 opened in 2025 could not be opened and is not used. The factsheet file sits in a 2024-11 folder and is labelled October 2024. Quezon City coordinates come from Wikipedia (s6), used only for the map point.","parties":[{"name":"STT GDC Philippines (Globe STT GDC Inc.)","note":"Joint venture of Globe Telecom, Ayala Corporation and ST Telemedia Global Data Centres.","role":"developer","source_ids":["s1","s3","s5"]},{"name":"STT GDC Philippines (Globe STT GDC Inc.)","note":"STT GDC Philippines presents STT Fairview 1 as its flagship data centre.","role":"operator","source_ids":["s4"]},{"name":"Globe Telecom","note":"Joint venture partner in STT GDC Philippines.","role":"investor","source_ids":["s1","s5"]},{"name":"Ayala Corporation","note":"Joint venture partner in STT GDC Philippines.","role":"investor","source_ids":["s1","s5"]},{"name":"ST Telemedia Global Data Centres","note":"Singapore-based joint venture partner in STT GDC Philippines.","role":"investor","source_ids":["s1","s5"]},{"name":"Leighton Asia","note":"Awarded the contract for the first phase of STT Fairview 1 in November 2023, together with First Balfour.","role":"builder","source_ids":["s2"]},{"name":"First Balfour","role":"builder","source_ids":["s2"]},{"name":"MPower (Meralco)","note":"Meralco's retail electricity arm; 10-year deal for up to 40.5 MW of clean energy covering the Fairview and Cavite data centers.","role":"power_supplier","source_ids":["s5"]}],"power_sources":[{"description":"STT Fairview 1 is designed with two diverse 115 kV utility feeds and up to 48 hours of on-site fuel storage for backup.","source_ids":["s3"],"type":"grid"},{"description":"Renewable electricity bought under a 10-year retail supply deal with MPower for up to 40.5 MW across the Fairview and Cavite data centers; STT described Fairview 1 as powered by 100% renewable energy. The generation types were not disclosed.","source_ids":["s4","s5"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2023-05-19","publisher":"W.Media","title":"STT GDC Announces Plans to Build Sustainable Carrier-Neutral Data Center in the Philippines","type":"trade_press","url":"https://w.media/stt-gdc-announces-plans-to-build-sustainable-carrier-neutral-data-center-in-the-philippines/"},{"accessed":"2026-10-09","id":"s2","published":"2023-11-14","publisher":"W.Media","title":"STT GDC Selects Leighton Asia and First Balfour for Hyperscale DC Development in the Philippines","type":"trade_press","url":"https://w.media/sttgdc-awards-contract-for-stt-fairview-1-data-center-development-the-philippines/"},{"accessed":"2026-10-09","id":"s3","published":"2024-10","publisher":"ST Telemedia Global Data Centres","title":"STT Fairview 1 factsheet (version October 2024)","type":"company","url":"https://assets.sttelemediagdc.com/sttgdc/global_en/public/2024-11/STT_Fairview_1_Factsheet_vOct2024.pdf"},{"accessed":"2026-10-09","id":"s4","published":"2025-10-15","publisher":"ST Telemedia Global Data Centres (Philippines)","title":"STT GDC Philippines Advances the Country's Digital Readiness, Welcomes Globe, Radius and Source Telecoms as Connectivity Partners","type":"company","url":"https://www.sttgdc.com/ph-en/newsroom/stt-gdc-philippines-advances-country-digital-readiness-welcomes-globe-radius-source-telecoms-connectivity-partners"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260420180559/https://www.philstar.com/business/2026/04/20/2522112/ayala-led-data-center-builder-inks-supply-deal-meralco","id":"s5","published":"2026-04-20","publisher":"The Philippine Star","title":"Ayala-led data center builder inks supply deal with Meralco","type":"news","url":"https://www.philstar.com/business/2026/04/20/2522112/ayala-led-data-center-builder-inks-supply-deal-meralco"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261005010001/https://en.wikipedia.org/wiki/Quezon_City","id":"s6","published":null,"publisher":"Wikipedia","title":"Quezon City","type":"other","url":"https://en.wikipedia.org/wiki/Quezon_City"}],"status":"under_construction","status_as_of":"2026-04-20","status_source_ids":["s5"],"summary":"STT GDC Philippines, a joint venture of Globe Telecom, Ayala Corporation and ST Telemedia Global Data Centres, is building a four-building carrier-neutral campus on Regalado Avenue in Fairview, Quezon City. Announced in May 2023, it is planned at 124 MW of IT load and over 83,000 square metres of floor space. The first building, STT Fairview 1, was designed for 28 MW of IT load and targeted for service in 2025, but in April 2026 the Philippine Star reported the campus would partly open during 2026 with an initial 12 MW and put the project's cost at USD 1 billion. A 10-year MPower renewable supply deal signed in April 2026 covers Fairview and the Cavite data center.","workloads":["colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9adc2e4b-72ef-566e-bf9f-4008c8f42a92","s2":"bfaea9b5-88e3-55f4-8016-000bc863d7bc","s3":"4a885e19-5d83-5bdc-8f9d-2b2e7e50bfab","s4":"860d3eb0-ae8e-514f-b13d-fcfcad984ded","s5":"9004580a-303b-52dc-adb3-4c3642ecda48","s6":"c4726d75-eadd-591e-99b2-4cca63c38187"},"source_file":"datacenters/projects/stt-gdc-fairview-quezon-city.json","source_record_id":"stt-gdc-fairview-quezon-city","source_record_sha256":"71f0b470d87b8a447ef876145c1929c20e520cff1632064b538e6fedf873c941","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1017bee96f9c625520384df90fc72c7790f26218103f962eb7719f56dba49e2f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-78bd59a55f0376662286/#project-b75df57e-ef16-50f9-b1d8-ae13bae596a5 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b75df57e-ef16-50f9-b1d8-ae13bae596a5.json
b7744ad5-aa48-5977-a70e-3d6a588f468d | curated:applied-digital-delta-forge-1-alexandria:current-build | vcc-site-60a52daa24c85edeb3a2 | curated:applied-digital-delta-forge-1-alexandria | Delta Forge 1 Current Construction | United States | US | 31.3826 | -92.6862 | Point | campus | representative_point_of_OSM_named_construction_enclosure | OSM_way1545345944_v2_WGS84_nodes_in_provider_order_ShAPely_representative_point | open_mapping_named_construction_enclosure_representative_point | community_source | campus_locator | A point inside the provider-mapped Applied Digital construction-fence enclosure. Not a project centroid, footprint, building, parcel or legal campus boundary; independent authoritative well/address bridge is corroborative only. Source positional accuracy is unknown. |  | Neither mapping provider nor source record publishes source-specific survey accuracy. Map decimals, local-knowledge notes and coordinate agreement do not establish accuracy. | ea663d84-8e4a-55d8-bd1e-007e7851f8b3 | under_construction | 2026-07-27 | 78 | authoritative_physical_status_update | 9a4d444e-8164-542a-b644-b21d948d12fb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"76fb62d0-9f70-5915-8e2b-23a2100e110f","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-delta-forge-1"},{"evidence_id":"be88f178-34c5-5b57-8d1e-0d1a4684e783","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-delta-forge-1"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year | https://api.openstreetmap.org/api/0.6/way/1545345944/full.json | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same named Delta Forge 1 development in Boyce near Alexandria; source and release share the issuer July 2026 results URL. Existing current build and source initial two-facility development describe the same project.","source_record_id":"applied-digital-delta-forge-1","target_project_stable_key":"curated:applied-digital-delta-forge-1-alexandria:current-build"},"record":{"aliases":["Delta Forge 1 AI Factory Campus"],"id":"applied-digital-delta-forge-1","last_reviewed":"2026-10-09","location":{"admin1":"Louisiana","admin2":"Rapides Parish","country":"US","lat":31.3906,"locality":"Boyce","lon":-92.67,"note":"Town centroid of Boyce from its Wikipedia coordinates (s5), which also places Boyce in Rapides Parish. The July 2026 results release (s3) names Boyce, Louisiana; earlier releases described only a southern US state. No parcel found.","precision":"locality","source_ids":["s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-22","basis":"planned","metric":"power_capacity","note":"Described as the initial total utility power for the campus.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":430},{"applies_to":"campus","as_of":"2026-04-23","basis":"contracted","metric":"power_capacity","note":"Critical IT load leased to an unnamed US high investment-grade hyperscaler, about 7.5 billion US dollars over an estimated 15-year term.","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2026-01-22","basis":"planned","metric":"buildings","note":"Two 150 MW facilities, with room to scale in 2028 and beyond.","phase_label":"Initial build","qualifier":"exact","source_ids":["s1"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2026-01-22","basis":"reported","metric":"land_area","qualifier":"more_than","source_ids":["s1","s2"],"unit":"acres","value":500},{"applies_to":"campus","as_of":"2026-01-22","basis":"planned","metric":"jobs_permanent","note":"Full-time employees expected at full operation, plus long-term contractors.","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":200}],"milestones":[{"date":"2026-01-22","event":"construction_started","kind":"actual","note":"Groundbreaking announced on this date; the release gives no separate groundbreaking date.","source_ids":["s1"]},{"date":"2026-04-23","event":"other","kind":"actual","note":"Lease of 300 MW of critical IT load to an unnamed hyperscaler announced.","source_ids":["s2"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Earlier releases said mid-2027; the July 2026 results release says calendar 2027.","source_ids":["s1","s2","s3"]}],"name":"Applied Digital Delta Forge 1","parties":[{"name":"Applied Digital","role":"developer","source_ids":["s1","s2"]}],"power_sources":[{"description":"Initial 430 MW of total utility power; the utility is not named in the cited sources.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261008211451/https://ir.applieddigital.com/news-events/press-releases/detail/144/applied-digital-breaks-ground-on-delta-forge-1-a-430-mw-ai","id":"s1","published":"2026-01-22","publisher":"Applied Digital","title":"Applied Digital Breaks Ground on Delta Forge 1, a 430 MW AI Factory Campus in a Southern U.S. State","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/144/applied-digital-breaks-ground-on-delta-forge-1-a-430-mw-ai"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260721210555/https://ir.applieddigital.com/news-events/press-releases/detail/149/applied-digital-announces-new-u-s-based-high","id":"s2","published":"2026-04-23","publisher":"Applied Digital","title":"Applied Digital Announces New U.S. Based High Investment-Grade Hyperscaler Tenant at Delta Forge 1, a 430 MW AI Factory Campus","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/149/applied-digital-announces-new-u-s-based-high"},{"accessed":"2026-10-09","id":"s3","published":"2026-07-27","publisher":"Applied Digital","title":"Applied Digital Reports Fiscal Fourth Quarter and Full Year 2026 Results","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/159/applied-digital-reports-fiscal-fourth-quarter-and-full-year"},{"accessed":"2026-10-09","id":"s4","published":"2026-10-07","publisher":"U.S. Securities and Exchange Commission (Applied Digital filing)","title":"Applied Digital Reports Fiscal First Quarter 2027 Results (Form 8-K exhibit)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001144879/000114487926000057/apldq127earningsrelease.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260115055604/https://en.wikipedia.org/wiki/Boyce,_Louisiana","id":"s5","published":null,"publisher":"Wikipedia","title":"Boyce, Louisiana","type":"other","url":"https://en.wikipedia.org/wiki/Boyce,_Louisiana"}],"status":"under_construction","status_as_of":"2026-10-07","status_source_ids":["s3","s4"],"summary":"Applied Digital AI factory campus in Boyce, Louisiana, on more than 500 acres, designed for an initial 430 MW of total utility power and up to 300 MW of critical IT load in two 150 MW facilities. Ground was broken in January 2026 with the state undisclosed. In April 2026 an unnamed US high investment-grade hyperscaler leased the 300 MW for about 15 years, worth about 7.5 billion US dollars. The company's July 2026 results release names Boyce, Louisiana. Initial operations are targeted for mid-2027.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"76fb62d0-9f70-5915-8e2b-23a2100e110f","s2":"be88f178-34c5-5b57-8d1e-0d1a4684e783","s3":"72c75125-9706-5a1e-832b-50bb239df07c","s4":"f08861a9-7b3d-5bca-958b-5d00b4194aa6","s5":"2584dc11-92bc-5311-b669-832d0c1daec9"},"source_file":"datacenters/projects/applied-digital-delta-forge-1.json","source_record_id":"applied-digital-delta-forge-1","source_record_sha256":"10214256785a9b6414201e99b67e33b4d86cc025f37ec2646022215dc0d7c5f7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"683e94b0ef0d2a832d315284bdbcbe096c8934d7431d72e9b99e4e5b3eb466e8"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-60a52daa24c85edeb3a2/#project-b7744ad5-aa48-5977-a70e-3d6a588f468d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b7744ad5-aa48-5977-a70e-3d6a588f468d.json
b7d85afa-fbc0-53d6-b19c-6e00c6639642 | imported:semiconductor-atlas:google-armstrong-county-texas | vcc-site-9da1382c1df4f319ef97 | imported:semiconductor-atlas:google-armstrong-county-texas | Google Armstrong County data center campus (Crusoe Goodnight) | United States | US | 35.1081 | -101.3627 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid of Claude via Nominatim. Sources place the roughly 1,300-acre site near Claude but give no street address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ed446beb-064d-5891-bbfb-502f3438c893 | under_construction | 2026-10-01 | 12 | imported_documented_status | aeea7f42-4fac-59bd-b8b4-d1450000e9bb | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ed446beb-064d-5891-bbfb-502f3438c893","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"aeea7f42-4fac-59bd-b8b4-d1450000e9bb","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"4f42a20e-1e5c-5115-8ef5-df80760dabe7","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"48027b42-f0c8-5325-adfe-bbb6f550e307","notes":null,"party":"Crusoe","relationship_scope":"unknown","role":"developer","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"aeea7f42-4fac-59bd-b8b4-d1450000e9bb","notes":"Crusoe affiliate listed as owner in 2026 Texas Department of Licensing and Regulation filings for two new buildings; those filings name no tenant.","party":"GN DC1 LLC","relationship_scope":"unknown","role":"owner","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"9c8656c4-0869-5925-9cac-19532dbf05b9","notes":"Described as the tenant or end user. Google names Armstrong County as a new campus location in its Texas investment program. New Project Media reported that Crusoe agreed to sell the project to Google; Google did not respond and Crusoe declined to comment, so the sale is unconfirmed.","party":"Google","relationship_scope":"unknown","role":"tenant","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"ed446beb-064d-5891-bbfb-502f3438c893","notes":"Described as the tenant or end user. Google names Armstrong County as a new campus location in its Texas investment program. New Project Media reported that Crusoe agreed to sell the project to Google; Google did not respond and Crusoe declined to comment, so the sale is unconfirmed.","party":"Google","relationship_scope":"unknown","role":"tenant","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"c405c84e-2372-5bc8-9028-a06ce4e97111","notes":"Described as the tenant or end user. Google names Armstrong County as a new campus location in its Texas investment program. New Project Media reported that Crusoe agreed to sell the project to Google; Google did not respond and Crusoe declined to comment, so the sale is unconfirmed.","party":"Google","relationship_scope":"unknown","role":"tenant","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"4f42a20e-1e5c-5115-8ef5-df80760dabe7","notes":"Described as the tenant or end user. Google names Armstrong County as a new campus location in its Texas investment program. New Project Media reported that Crusoe agreed to sell the project to Google; Google did not respond and Crusoe declined to comment, so the sale is unconfirmed.","party":"Google","relationship_scope":"unknown","role":"tenant","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"48027b42-f0c8-5325-adfe-bbb6f550e307","notes":"Described as the tenant or end user. Google names Armstrong County as a new campus location in its Texas investment program. New Project Media reported that Crusoe agreed to sell the project to Google; Google did not respond and Crusoe declined to comment, so the sale is unconfirmed.","party":"Google","relationship_scope":"unknown","role":"tenant","source_record_id":"google-armstrong-county-texas"},{"evidence_id":"4f42a20e-1e5c-5115-8ef5-df80760dabe7","notes":"Owner of the operating Goodnight 1 wind farm, one of the two adjacent wind farms the campus is linked to.","party":"Serena","relationship_scope":"unknown","role":"power_supplier","source_record_id":"google-armstrong-county-texas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | GN DC1 LLC |  |  | Google |  | https://theenergymag.com/news/2026-07-31/crusoe-texas-ai-data-center-goodnight | https://www.abc7amarillo.com/news/local/google-announces-new-data-center-in-armstrong-county-texas-judge-adam-ensey-crusoe-energy-ercot-southwest-power-pool-claude-texas | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Google Armstrong County data center campus (Crusoe Goodnight) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"google-armstrong-county-texas"},"record":{"aliases":["Goodnight campus","Project Goodnight"],"id":"google-armstrong-county-texas","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Armstrong County","country":"US","lat":35.1081,"locality":"Claude","lon":-101.3627,"note":"Town centroid of Claude via Nominatim. Sources place the roughly 1,300-acre site near Claude but give no street address.","precision":"locality","source_ids":["s2","s4"]},"metrics":[{"applies_to":"phase","as_of":"2026-07-31","basis":"planned","metric":"power_capacity","note":"From an Armstrong County tax abatement agreement, which also describes four 25 MW data halls per building.","phase_label":"Phase 1 (four buildings)","power_scope":"unspecified","qualifier":"up_to","source_ids":["s3","s4"],"unit":"MW","value":530},{"applies_to":"phase","as_of":"2025-12-15","basis":"planned","metric":"power_capacity","note":"From earlier tax abatement materials as summarized by New Project Media; newer amended filings omit project details.","phase_label":"Phase 2 (three buildings)","power_scope":"unspecified","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2025-12-15","basis":"planned","metric":"power_capacity","note":"Two-phase campus total from earlier tax abatement materials as summarized by New Project Media; the layout may be redrawn.","power_scope":"unspecified","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":1030},{"applies_to":"campus","as_of":"2025-12-15","basis":"reported","metric":"investment","note":"Figure from earlier tax abatement materials and prior New Project Media reporting, not from the amended filings.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":29000000000},{"applies_to":"phase","as_of":"2026-07-31","basis":"reported","metric":"investment","note":"Estimated construction cost of about $500 million per building, each roughly 805,000 sq ft; estimates may change.","phase_label":"Two new buildings (Buildings 3 and 4) in 2026 state filings","qualifier":"approximately","source_ids":["s4"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2026-07-31","basis":"planned","metric":"buildings","qualifier":"at_least","source_ids":["s4"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2025-11-24","basis":"reported","metric":"land_area","qualifier":"approximately","source_ids":["s2"],"unit":"acres","value":1300},{"applies_to":"campus","as_of":"2025-11-24","basis":"planned","metric":"jobs_permanent","note":"The county judge said the facility is expected to employ 80 to 100 people once running.","qualifier":"range","source_ids":["s2"],"unit":"count","value":80,"value_high":100},{"applies_to":"campus","as_of":"2026-10-01","basis":"reported","metric":"jobs_construction","note":"Workers on site daily, per Crusoe.","qualifier":"more_than","source_ids":["s5"],"unit":"count","value":5500}],"milestones":[{"date":"2025-05","event":"construction_started","kind":"actual","note":"Local TV reported that Crusoe had been building since May 2025.","source_ids":["s2"]},{"date":"2025-06","event":"construction_started","kind":"actual","note":"Crusoe's account dates the groundbreaking to June 2025, a month later than the local report.","source_ids":["s5"]},{"date":"2025-11-14","event":"announced","kind":"actual","note":"Google named Armstrong County as a new campus location in its Texas investment announcement.","source_ids":["s1"]},{"date":"2026-01","event":"other","kind":"actual","note":"Permit application for a 933 MW natural gas plant to serve two buildings behind the meter; Google said it had not agreed to buy the plant's output.","source_ids":["s5"]},{"date":"2026-09-28","event":"other","kind":"actual","note":"Crusoe publicly confirmed Google as the campus end user.","source_ids":["s5"]},{"date":"2028-Q4","event":"fully_operational","kind":"planned","note":"Completion expected in late 2028 or early 2029 per the county judge.","source_ids":["s2"]}],"name":"Google Armstrong County data center campus (Crusoe Goodnight)","notes":"Google's $40 billion Texas figure runs through 2027 and covers new campuses in Armstrong and Haskell Counties among other spending; it is not recorded here as a campus investment. Phase and campus MW figures come from tax abatement materials and are not added together. One state filing gave Building 3 an August 1 completion date (year not stated, presumably 2026) and Building 4 a March 2027 date. New Project Media's article was first published for subscribers; the date used is that of its public posting.","parties":[{"name":"Crusoe","role":"developer","source_ids":["s2","s4","s5","s6"]},{"name":"GN DC1 LLC","note":"Crusoe affiliate listed as owner in 2026 Texas Department of Licensing and Regulation filings for two new buildings; those filings name no tenant.","role":"owner","source_ids":["s4"]},{"name":"Google","note":"Described as the tenant or end user. Google names Armstrong County as a new campus location in its Texas investment program. New Project Media reported that Crusoe agreed to sell the project to Google; Google did not respond and Crusoe declined to comment, so the sale is unconfirmed.","role":"tenant","source_ids":["s1","s2","s3","s5","s6"]},{"name":"Serena","note":"Owner of the operating Goodnight 1 wind farm, one of the two adjacent wind farms the campus is linked to.","role":"power_supplier","source_ids":["s5"]}],"power_sources":[{"description":"Linked to the adjacent Goodnight wind farms: Goodnight 1 (265.5 MW, operating) and Goodnight 2 (similar size, under construction), about 531 MW combined; surplus output returns to the grid.","source_ids":["s5","s6"],"type":"wind"},{"description":"Amended abatement filings added gas turbines; a January 2026 application sought a 933 MW gas plant serving two buildings without a grid tie. It is a proposal, and Google has not agreed to buy its power.","source_ids":["s3","s5"],"type":"natural_gas_onsite"},{"description":"Battery storage was added to the power plan in amended Armstrong County tax abatement filings.","source_ids":["s3"],"type":"battery_storage"},{"description":"The county judge said the data center would draw from the ERCOT grid, although the county itself is served through the Southwest Power Pool.","source_ids":["s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-14","publisher":"Google","title":"Google's investments run deep in the heart of Texas","type":"company","url":"https://blog.google/inside-google/company-announcements/google-american-innovation-texas/"},{"accessed":"2026-10-09","id":"s2","published":"2025-11-24","publisher":"ABC 7 Amarillo","title":"Google announces new data center in Armstrong County, Texas","type":"news","url":"https://www.abc7amarillo.com/news/local/google-announces-new-data-center-in-armstrong-county-texas-judge-adam-ensey-crusoe-energy-ercot-southwest-power-pool-claude-texas"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260514080205/https://newprojectmedia.com/origination-crusoe-adds-natural-gas-storage-to-texas-panhandle-energy-mix-as-project-shifts-to-google-ownership/","id":"s3","published":"2025-12-15","publisher":"New Project Media","title":"ORIGINATION: Crusoe adds natural gas, storage to Texas Panhandle energy mix as project shifts to Google ownership","type":"trade_press","url":"https://newprojectmedia.com/origination-crusoe-adds-natural-gas-storage-to-texas-panhandle-energy-mix-as-project-shifts-to-google-ownership/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260927131459/https://theenergymag.com/news/2026-07-31/crusoe-texas-ai-data-center-goodnight","id":"s4","published":"2026-07-31","publisher":"TheEnergyMag","title":"Crusoe Plans $1B Texas AI Data Center Expansion, Pursues Nuclear Power","type":"trade_press","url":"https://theenergymag.com/news/2026-07-31/crusoe-texas-ai-data-center-goodnight"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003152915/https://baxtel.com/news/crusoe-confirms-google-ai-campus-in-texas-with-531mw-wind-link","id":"s5","published":"2026-10-01","publisher":"Baxtel","title":"Crusoe Confirms Google AI Campus In Texas With 531MW Wind Link","type":"trade_press","url":"https://baxtel.com/news/crusoe-confirms-google-ai-campus-in-texas-with-531mw-wind-link"},{"accessed":"2026-10-09","id":"s6","published":"2026-10-01","publisher":"The Tech Capital","title":"Google taps Crusoe for new Texas AI data centre campus","type":"trade_press","url":"https://thetechcapital.com/google-taps-crusoe-for-new-texas-ai-data-centre-campus/"}],"status":"under_construction","status_as_of":"2026-10-01","status_source_ids":["s4","s5"],"summary":"AI data center campus near Claude, Armstrong County, in the Texas Panhandle, being developed by Crusoe on about 1,300 acres beside the Goodnight wind farms. Google named Armstrong County as a new campus site in its November 2025 Texas program ($40 billion statewide through 2027), and Crusoe confirmed Google as the end user in September 2026. County tax abatement materials described a first phase of four buildings drawing up to 530 MW, within a two-phase 1,030 MW design. State filings in 2026 added two buildings of about 805,000 sq ft each, together estimated at $1 billion. Amended filings added gas turbines and battery storage, and one report says Crusoe agreed to sell the project to Google.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9c8656c4-0869-5925-9cac-19532dbf05b9","s2":"ed446beb-064d-5891-bbfb-502f3438c893","s3":"c405c84e-2372-5bc8-9028-a06ce4e97111","s4":"aeea7f42-4fac-59bd-b8b4-d1450000e9bb","s5":"4f42a20e-1e5c-5115-8ef5-df80760dabe7","s6":"48027b42-f0c8-5325-adfe-bbb6f550e307"},"source_file":"datacenters/projects/google-armstrong-county-texas.json","source_record_id":"google-armstrong-county-texas","source_record_sha256":"f55a3707ea4ac75a2f9b631f23417f0a5f6df89437b652668172d0934fa4e412","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0c7f0624ec1a0b34a9cc12a70a1d339937093460edf1399776a95394fe95aa87"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9da1382c1df4f319ef97/#project-b7d85afa-fbc0-53d6-b19c-6e00c6639642 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b7d85afa-fbc0-53d6-b19c-6e00c6639642.json
b8399bc6-5c72-5627-a035-4fea208cd287 | curated:edged-chicago-aurora-campus:ord01-2 | vcc-site-9369a9dbb7d04a9e1327 | curated:edged-chicago-aurora-campus | Edged Chicago ORD01-2 | United States | US | 41.807 | -88.241 | Point | project | direct_geometry | authoritative_address_geocode | campus_address_point | official_source | reviewed_site_locator | Exact City of Aurora address point for 2835 Bilter Road on the Edged Chicago LLC-owned parcel; not an ORD01-2 footprint. |  | official source does not state positional accuracy | 98fcd750-ba33-537e-8669-fe8d1db1a6c6 | shell | 2026-06-04 | 131 | authoritative_physical_status_update | 781c461b-14cf-53e1-9e40-5c39a3d589b5 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [{"as_of_date":"2026-06-04","confidence":0.99,"deployment_scope":"intended","evidence_id":"781c461b-14cf-53e1-9e40-5c39a3d589b5","method":"company_disclosure","workload":"ai_inference"},{"as_of_date":"2026-06-04","confidence":0.99,"deployment_scope":"intended","evidence_id":"781c461b-14cf-53e1-9e40-5c39a3d589b5","method":"company_disclosure","workload":"ai_training"}] |  | [{"evidence_id":"781c461b-14cf-53e1-9e40-5c39a3d589b5","party":"Edged US","relationship_scope":"intended","role":"operator"}] | [{"as_of_date":"2026-07-20","base":72.0,"confidence":0.99,"evidence_id":"5e1b3dfc-046d-5289-bcce-08208107f1bf","high":72.0,"low":72.0,"method":"reported","metric":"critical_it_mw","notes":"Planned critical capacity for ORD01-2, nested within the Chicago campus's 96 MW total. It is not current load, installed or energized capacity, gross demand, grid connection, generation, annual energy, or measured consumption.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | Edged US |  |  |  | https://edged.us/news/edged-us-tops-out-second-sustainable-data-center-on-edged-chicago-campus | https://services1.arcgis.com/79UxTxnBeBW8JHY4/arcgis/rest/services/Address_Points/FeatureServer/0/query?where=LOCATIONID%3D85050%20AND%20PIN%3D%2707-05-105-006%27&outFields=OBJECTID%2CLOCATIONID%2CPIN%2CADDRESS%2CCITY%2CZIPCODE%2CCOUNTY%2CZONING%2CLANDUSE%2COWNERNAME&returnGeometry=true&outSR=4326&f=geojson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9369a9dbb7d04a9e1327/#project-b8399bc6-5c72-5627-a035-4fea208cd287 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b8399bc6-5c72-5627-a035-4fea208cd287.json
b91d994d-0f59-5ed8-ad74-20e4ba2251f3 | curated:procergs-porto-alegre-praca-dos-acorianos-campus:new-substation-6033 | vcc-site-900b1508d570a2f4253f | curated:procergs-porto-alegre-praca-dos-acorianos-campus | Procergs Porto Alegre New Substation 6033-00 | Brazil | BR | -30.0386 | -51.2308 | Point | campus | provider_supplied_named_Procergs_building_centroid_bound_to_explicit_datacenter_address_and_substation_contract6033 | copy_exact_Nominatim_lat_lon_for_OSM_way112410783_corroborate_canonical_website_short_name_historic_name_and_official_DC_address | community_constituent_building_reference_point | community_source | campus_locator | Only a locator for the Procergs campus from its named existing headquarters/datacenter constituent. New substation is alongside that same building, not asserted at this exact point. No work-footprint containment, official parcel, exact entrance, surveyed location or quantitative positional accuracy claim. OSM/Nominatim address labels differ from the official address; identity rests on the literal company name, short_name, canonical website and independent datacenter-address record. |  | Neither OSM nor Nominatim provides a quantified positional accuracy. Decimal digits and point-in-building containment do not establish survey accuracy. | a019a821-4ecd-59b8-a01e-ffb7df16a1dd | under_construction | 2026-07-01 | 104 | authoritative_physical_status_update | 73bfac37-2316-515a-bae1-3bfb4d24c292 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.procergs.rs.gov.br/upload/arquivos/202608/20132929-aporte2025-prestacaocontas-jul2026.pdf | https://nominatim.openstreetmap.org/search?format=jsonv2&q=PROCERGS%20Porto%20Alegre&addressdetails=1&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-900b1508d570a2f4253f/#project-b91d994d-0f59-5ed8-ad74-20e4ba2251f3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b91d994d-0f59-5ed8-ad74-20e4ba2251f3.json
b9ccc1e7-c2da-5822-82bc-b20be7d43dfe | curated:nebius-pajarila-lappeenranta-campus:first-phase-current-build | vcc-site-80fb287847eab3cd8bf9 | curated:nebius-pajarila-lappeenranta-campus | Nebius Pajarila First Phase Current Build | Finland | FI | 61.0559 | 28.2855 | Point | campus | municipal_exact_address_result_transformed_by_same_municipal_service_to_EPSG4326 | municipal_exact_address_result_transformed_by_same_municipal_service_to_EPSG4326 | government_site_address_reference_point | official_source | campus_locator | Municipal point for the exact address printed in Fira's project-bound data-center piling notice. It identifies the first-phase campus parcel at Pajarilanväylä24, not the whole 41ha boundary, a building footprint or a current work-area centroid. |  | The source provides no survey accuracy or quantitative positional uncertainty; coordinate digits do not establish accuracy. | 1396cf0e-0de1-5c51-ab78-5e027fd4a6e8 | under_construction | 2026-08-11 | 63 | authoritative_physical_status_update | b09547d7-5388-566f-87ad-0f911a8b49db | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://fira.fi/en/news/construction-and-project-development-company-fira-selected-as-main-contractor-for-one-of-europes-largest-ai-data-center-projects/ | https://kartta.lappeenranta.fi/IMS/fi/Transform?north=6771752&east=28515420&targetSystem=EPSG%3A4326&decimalCount=8 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-80fb287847eab3cd8bf9/#project-b9ccc1e7-c2da-5822-82bc-b20be7d43dfe | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b9ccc1e7-c2da-5822-82bc-b20be7d43dfe.json
b9f9191a-1f90-551d-a8b9-44e6f8833e96 | imported:semiconductor-atlas:qscale-q01-levis | vcc-site-0ecf05307f91c1e40479 | curated:qscale-q01-levis-campus | QScale Q01 campus (Lévis) | Canada | CA | 46.6761 | -71.3251 | Point | project | imported_reference_point | imported_reference_point | site | compiled_reference | project_locator | QScale's Q01 campus page gives the address 2280 Albert-Dion St, Lévis; coordinates were geocoded from that address to an OpenStreetMap building tagged QScale. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 79ba5ea0-689a-5af4-ba14-30784e107890 | partially_operational | 2026-10-09 | 4 | imported_documented_status | bba8372d-6941-50b4-ac42-93b948f99605 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"bd1b7da7-ad64-5106-8974-9e6a18e59762","notes":null,"party":"QScale","relationship_scope":"unknown","role":"developer","source_record_id":"qscale-q01-levis"},{"evidence_id":"183ba80f-eeac-5e5f-a13d-f1640eb9e217","notes":null,"party":"QScale","relationship_scope":"unknown","role":"developer","source_record_id":"qscale-q01-levis"},{"evidence_id":"bba8372d-6941-50b4-ac42-93b948f99605","notes":null,"party":"QScale","relationship_scope":"unknown","role":"developer","source_record_id":"qscale-q01-levis"},{"evidence_id":"47843290-f57d-5b78-bd5b-80bdbcd4692a","notes":null,"party":"QScale","relationship_scope":"unknown","role":"operator","source_record_id":"qscale-q01-levis"},{"evidence_id":"79ba5ea0-689a-5af4-ba14-30784e107890","notes":null,"party":"QScale","relationship_scope":"unknown","role":"operator","source_record_id":"qscale-q01-levis"},{"evidence_id":"47843290-f57d-5b78-bd5b-80bdbcd4692a","notes":"Announced as first anchor tenant in May 2023; deployed its AI cloud at the campus.","party":"Hewlett Packard Enterprise","relationship_scope":"unknown","role":"tenant","source_record_id":"qscale-q01-levis"},{"evidence_id":"79ba5ea0-689a-5af4-ba14-30784e107890","notes":"Announced as first anchor tenant in May 2023; deployed its AI cloud at the campus.","party":"Hewlett Packard Enterprise","relationship_scope":"unknown","role":"tenant","source_record_id":"qscale-q01-levis"},{"evidence_id":"1a572902-495e-5d09-85d2-f9148814a902","notes":"Its infrastructure business acquired QScale; founders and management reinvested.","party":"Goldman Sachs Alternatives","relationship_scope":"unknown","role":"owner","source_record_id":"qscale-q01-levis"},{"evidence_id":"bd1b7da7-ad64-5106-8974-9e6a18e59762","notes":"Provided a loan and bought shares for the first phase in 2021.","party":"Government of Quebec","relationship_scope":"unknown","role":"investor","source_record_id":"qscale-q01-levis"},{"evidence_id":"bd1b7da7-ad64-5106-8974-9e6a18e59762","notes":"Agreement for the use of 140 MW reported at the 2021 launch.","party":"Hydro-Québec","relationship_scope":"unknown","role":"utility","source_record_id":"qscale-q01-levis"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Goldman Sachs Alternatives | QScale |  | Hewlett Packard Enterprise |  | https://www.qscale.com/news/q01-building-b-60mw-ai-ready-infrastructure | https://www.qscale.com/q01-campus | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["source_site_point_not_surveyed_boundary","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same QScale Q01 campus at 2280 Albert-Dion Street; coordinates agree within about 7 metres and the Building B issuer source is shared. Source spans operating campus and expansion; existing record is only Building B.","source_record_id":"qscale-q01-levis","target_physical_site_stable_key":"curated:qscale-q01-levis-campus"},"record":{"aliases":["Q01","QScale Q01"],"id":"qscale-q01-levis","last_reviewed":"2026-10-09","location":{"admin1":"Quebec","country":"CA","lat":46.6761,"locality":"Lévis","lon":-71.3251,"note":"QScale's Q01 campus page gives the address 2280 Albert-Dion St, Lévis; coordinates were geocoded from that address to an OpenStreetMap building tagged QScale.","precision":"site","source_ids":["s7"]},"metrics":[{"applies_to":"campus","as_of":"2023-05-22","basis":"planned","metric":"power_capacity","note":"Power capacity listed on the campus page; the 2023 release says the campus is powered by 142 MW of renewable energy. Neither says whether the figure is contracted or how it relates to the 114 MW IT load.","power_scope":"unspecified","qualifier":"exact","source_ids":["s3","s7"],"unit":"MW","value":142},{"applies_to":"campus","as_of":"2021-07-13","basis":"contracted","metric":"power_capacity","note":"Agreement with Hydro-Québec for the use of 140 MW, reported at the 2021 launch.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":140},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Protected customer IT load stated on the undated campus page.","power_scope":"it_load","qualifier":"exact","source_ids":["s7"],"unit":"MW","value":114},{"applies_to":"phase","as_of":"2026-06-04","basis":"under_construction","metric":"power_capacity","note":"Second building; the release gives its cost as 700 million dollars without a currency code.","phase_label":"Building B","power_scope":"it_load","qualifier":"exact","source_ids":["s6"],"unit":"MW","value":60},{"applies_to":"campus","as_of":"2022-09-21","basis":"announced","metric":"investment","note":"Total for all eight phases. The 2021 launch release gave 867 million dollars, with 195 million for phase 1.","qualifier":"exact","source_ids":["s2"],"unit":"CAD","value":1050000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Total building space on the undated campus page; white space about 313,000 sq ft.","qualifier":"approximately","source_ids":["s7"],"unit":"sq_ft","value":930000}],"milestones":[{"date":"2021-07-13","event":"announced","kind":"actual","note":"Launch and financing of the first phase; phase 1 backbone infrastructure was targeted for completion by the end of 2022.","source_ids":["s1"]},{"date":"2022-09-21","event":"other","kind":"actual","note":"Phase 2 construction reported well underway, a year ahead of schedule.","source_ids":["s2"]},{"date":"2023-05-22","event":"other","kind":"actual","note":"Hewlett Packard Enterprise announced as first anchor tenant.","source_ids":["s3"]},{"date":"2024-11-20","event":"other","kind":"actual","note":"Credit facility of up to 320 million dollars arranged to fund phases 3 and 4.","source_ids":["s4"]},{"date":"2026-05-13","event":"other","kind":"actual","note":"Goldman Sachs Alternatives announced that it had closed its acquisition of QScale.","source_ids":["s5"]},{"date":"2026-06-04","event":"expansion_announced","kind":"actual","note":"Construction of Building B (60 MW IT) reported well underway.","source_ids":["s6"]}],"name":"QScale Q01 campus (Lévis)","notes":"Status rests on the June 2026 release, which describes the existing campus in operation while Building B is built, and on QScale's undated campus page, which reports HPE's deployment; status_as_of is the date that page was read (2026-10-09), as are the as_of dates of figures taken from it. Building B's 700 million dollar cost is given without a currency and is not recorded as a metric.","parties":[{"name":"QScale","role":"developer","source_ids":["s1","s2","s6"]},{"name":"QScale","role":"operator","source_ids":["s3","s7"]},{"name":"Hewlett Packard Enterprise","note":"Announced as first anchor tenant in May 2023; deployed its AI cloud at the campus.","role":"tenant","source_ids":["s3","s7"]},{"name":"Goldman Sachs Alternatives","note":"Its infrastructure business acquired QScale; founders and management reinvested.","role":"owner","source_ids":["s5"]},{"name":"Government of Quebec","note":"Provided a loan and bought shares for the first phase in 2021.","role":"investor","source_ids":["s1"]},{"name":"Hydro-Québec","note":"Agreement for the use of 140 MW reported at the 2021 launch.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Supplied by Hydro-Québec through a QScale-owned 120 kV substation; the company describes the supply as 100% renewable.","source_ids":["s1","s7"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2021-07-13","publisher":"QScale","title":"QScale: From Data Processing to Food Self-Sufficiency","type":"company","url":"https://www.qscale.com/news/from-data-processing-to-food-self-sufficiency-financing"},{"accessed":"2026-10-09","id":"s2","published":"2022-09-21","publisher":"QScale","title":"QScale Accelerates Its Expansion and Growth","type":"company","url":"https://www.qscale.com/news/qscale-accelerates-its-expansion-and-growth"},{"accessed":"2026-10-09","id":"s3","published":"2023-05-22","publisher":"QScale","title":"QScale Welcomes Hewlett Packard Enterprise as First Anchor Tenant at Q01 Campus","type":"company","url":"https://www.qscale.com/news/hewlett-packard-enterprise-hpe-q01-campus"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260514194651/https://www.qscale.com/news/320m-financing-growth","id":"s4","published":"2024-11-20","publisher":"QScale","title":"QScale Secures Up to $320 Million Funding to Accelerate Growth","type":"company","url":"https://www.qscale.com/news/320m-financing-growth"},{"accessed":"2026-10-09","id":"s5","published":"2026-05-13","publisher":"QScale","title":"Goldman Sachs Alternatives to Acquire QScale, a Leading Canadian Data Center Platform","type":"company","url":"https://www.qscale.com/news/goldman-sachs-alternatives-to-acquire-qscale"},{"accessed":"2026-10-09","id":"s6","published":"2026-06-04","publisher":"QScale","title":"QScale Begins Construction of Its Second Building at the Q01 Campus, Adding 60 MW of AI-Ready Infrastructure in Quebec","type":"company","url":"https://www.qscale.com/news/q01-building-b-60mw-ai-ready-infrastructure"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"QScale","title":"Q01 Campus","type":"company","url":"https://www.qscale.com/q01-campus"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s6","s7"],"summary":"QScale's Q01 campus in Lévis, in the Quebec City area, is a liquid- and air-cooled colocation and AI campus that the company says is powered by 142 MW of renewable energy. Launched in 2021 as an eight-phase project, it was later costed at CAD 1.05 billion; Hewlett Packard Enterprise became its first anchor tenant in 2023. Goldman Sachs Alternatives closed its acquisition of QScale in May 2026, and in June 2026 QScale said construction of a second building adding 60 MW of IT capacity was well underway.","workloads":["colocation","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"bd1b7da7-ad64-5106-8974-9e6a18e59762","s2":"183ba80f-eeac-5e5f-a13d-f1640eb9e217","s3":"47843290-f57d-5b78-bd5b-80bdbcd4692a","s4":"c56477fa-b646-5d68-8657-1b5e25fc2f12","s5":"1a572902-495e-5d09-85d2-f9148814a902","s6":"bba8372d-6941-50b4-ac42-93b948f99605","s7":"79ba5ea0-689a-5af4-ba14-30784e107890"},"source_file":"datacenters/projects/qscale-q01-levis.json","source_record_id":"qscale-q01-levis","source_record_sha256":"88ec25d50c62b593691517ad815b73e1bc3d81f12e4e437b5e05f6b866166882","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"cc92eb90d7af016cc498a6233f3acd0d2a81a360c55904229d55fd6f73ffc170"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0ecf05307f91c1e40479/#project-b9f9191a-1f90-551d-a8b9-44e6f8833e96 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/b9f9191a-1f90-551d-a8b9-44e6f8833e96.json
ba5ddf33-10ec-5fb8-b880-98a04df096b8 | curated:trg-spring-cypress-campus:hou2 | vcc-site-77fa0d95d9c7ed1b2168 | curated:trg-spring-cypress-campus | TRG HOU2 | United States | US | 30.066 | -95.4557 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. The brochure places HOU1 and HOU2 on one two-data-center campus. The address point locates that campus and is not an HOU2 building footprint. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 6600dddb-f2d8-5458-8e71-b43f77cc5e01 | under_construction | 2026-07-20 | 85 | authoritative_physical_status_update | 209c7f3e-18eb-533c-bb99-0b302fc22d7b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.12 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.trgdatacenters.com/wp-content/uploads/2026/01/TRG-Campus-HOU2-Brochure.pdf | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-77fa0d95d9c7ed1b2168/#project-ba5ddf33-10ec-5fb8-b880-98a04df096b8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ba5ddf33-10ec-5fb8-b880-98a04df096b8.json
baa5ddbb-3439-5e4f-a03f-265b844b4460 | imported:semiconductor-atlas:airtrunk-jhb3-iskandar-puteri | vcc-site-492efa6e8a99e32cfb93 | imported:semiconductor-atlas:airtrunk-jhb3-iskandar-puteri | AirTrunk JHB3 Johor Bahru | Malaysia | MY | 1.4222 | 103.65 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | AirTrunk and W.Media name Iskandar Puteri without an address; the point is the Iskandar Puteri coordinate from its Wikipedia article, so it marks the city rather than the campus. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 9a88e6c1-7d4b-5b22-96b2-7c13e495e1a7 | announced | 2026-04-30 | 166 | imported_documented_status | 9a88e6c1-7d4b-5b22-96b2-7c13e495e1a7 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9a88e6c1-7d4b-5b22-96b2-7c13e495e1a7","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb3-iskandar-puteri"},{"evidence_id":"db6735a0-3e97-52f3-94e9-e5fa1eb3430a","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb3-iskandar-puteri"},{"evidence_id":"3e139db5-f1a0-566e-9f40-383df947e1ea","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb3-iskandar-puteri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/ | https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AirTrunk JHB3 Johor Bahru as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"airtrunk-jhb3-iskandar-puteri","source_relations":[{"reason":"AirTrunk names separate JHB3 and JHB4 campuses, different site areas and 138/142 MW scopes; shared city centroid is not a shared site.","relationship":"separate_nearby_campuses","source_id":"airtrunk-jhb4-iskandar-puteri"},{"reason":"AirTrunk names separate campuses; shared JHB2 electrical supply does not merge JHB3 physical identity.","relationship":"separate_nearby_campuses","source_id":"airtrunk-jhb2-iskandar-puteri"}]},"record":{"aliases":["AirTrunk JHB3","JHB3 Johor Bahru"],"id":"airtrunk-jhb3-iskandar-puteri","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Johor Bahru District","country":"MY","lat":1.4222,"locality":"Iskandar Puteri","lon":103.65,"note":"AirTrunk and W.Media name Iskandar Puteri without an address; the point is the Iskandar Puteri coordinate from its Wikipedia article, so it marks the city rather than the campus.","precision":"locality","source_ids":["s1","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total capacity on AirTrunk's undated JHB3 page. The April 2026 announcement gives more than 280 MW of IT load for JHB3 and JHB4 together.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s2"],"unit":"MW","value":138},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s2"],"unit":"hectares","value":5.4034},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Technical data hall area across eight halls; office and storage space of 3,300 square metres is listed separately.","qualifier":"exact","source_ids":["s2"],"unit":"sq_m","value":11150}],"milestones":[{"date":"2026-04-30","event":"announced","kind":"actual","source_ids":["s1","s3"]}],"name":"AirTrunk JHB3 Johor Bahru","notes":"The more than 280 MW of IT load, the MYR12 billion (USD3 billion) investment and the 3,000-plus construction jobs were announced for JHB3 and JHB4 together, so they are not recorded as metrics for this campus alone. AirTrunk's site page states a total capacity without saying whether it is IT load. No construction start or status update after the announcement was found. Related records: airtrunk-jhb1-johor and airtrunk-jhb2-iskandar-puteri. Wikipedia is cited only for the city coordinate.","parties":[{"name":"AirTrunk","role":"developer","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"Permanent 275 kV dual feed from the neighbouring JHB2 campus, per AirTrunk's site page.","source_ids":["s2"],"type":"grid"}],"related_ids":["airtrunk-jhb4-iskandar-puteri"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001022558/https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/","id":"s1","published":"2026-04-30","publisher":"AirTrunk","title":"AirTrunk doubles down in Malaysia with two new hyperscale campuses in Johor Bahru","type":"company","url":"https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"AirTrunk","title":"JHB3 Johor Bahru","type":"company","url":"https://airtrunk.com/location/jhb3-johor-bahru/"},{"accessed":"2026-10-09","id":"s3","published":"2026-04-30","publisher":"W.Media","title":"AirTrunk to invest US$ 3 billion in Johor to build two hyperscale campuses totaling 280MW capacity","type":"trade_press","url":"https://w.media/airtrunk-to-invest-us-3-billion-in-johor-to-build-two-hyperscale-campuses-totaling-280mw-capacity/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Iskandar Puteri","type":"other","url":"https://en.wikipedia.org/wiki/Iskandar_Puteri"}],"status":"announced","status_as_of":"2026-04-30","status_source_ids":["s1","s3"],"summary":"JHB3 is one of two new AirTrunk hyperscale campuses announced on 30 April 2026 in Iskandar Puteri, Johor, next to its JHB1 and JHB2 campuses. AirTrunk lists JHB3 at more than 138 MW across multiple buildings with eight data halls on about 5.4034 hectares, fed at 275 kV from JHB2 and cooled with recycled water, aimed at high-density cloud and AI customers. AirTrunk put the combined investment for JHB3 and JHB4 at MYR12 billion (USD3 billion), with more than 3,000 construction jobs; no construction or opening dates were given.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9a88e6c1-7d4b-5b22-96b2-7c13e495e1a7","s2":"db6735a0-3e97-52f3-94e9-e5fa1eb3430a","s3":"3e139db5-f1a0-566e-9f40-383df947e1ea","s4":"dd647655-de7a-52e7-8de2-fd9d6142c761"},"source_file":"datacenters/projects/airtrunk-jhb3-iskandar-puteri.json","source_record_id":"airtrunk-jhb3-iskandar-puteri","source_record_sha256":"53ca2c2a255790080b0498d64eaaeb2494166033ef54efda8388e43fd03a5744","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7c1fb46f123ac4e328ad4bc084ccc8eae3e11bb13329500ccce4da6872f63da1"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-492efa6e8a99e32cfb93/#project-baa5ddbb-3439-5e4f-a03f-265b844b4460 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/baa5ddbb-3439-5e4f-a03f-265b844b4460.json
bb1b28fd-610b-5739-b928-e44f21cb6f1b | imported:semiconductor-atlas:wonder-valley-alberta | vcc-site-0a62731022d2820e105f | imported:semiconductor-atlas:wonder-valley-alberta | Wonder Valley AI data centre park (Alberta) | Canada | CA | 54.8119 | -118.6834 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Point taken from the Government of Alberta major projects inventory entry for Phase 1 and rounded; the developer's FAQ places the site in the Greenview Industrial Gateway about 42 km south of Grande Prairie. Parcel boundaries were not published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d43b045c-1fff-5626-9644-8a866d075e46 | announced | 2026-10-09 | 4 | imported_documented_status | 65288924-cdc7-59d4-ba64-e37a3cf58398 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d43b045c-1fff-5626-9644-8a866d075e46","notes":"Named proponent in the Alberta inventory and in the February 2026 release.","party":"O'Leary Digital Limited","relationship_scope":"unknown","role":"developer","source_record_id":"wonder-valley-alberta"},{"evidence_id":"65288924-cdc7-59d4-ba64-e37a3cf58398","notes":"Named proponent in the Alberta inventory and in the February 2026 release.","party":"O'Leary Digital Limited","relationship_scope":"unknown","role":"developer","source_record_id":"wonder-valley-alberta"},{"evidence_id":"0e3f5300-2d80-546c-86ee-7e8cb231b86a","notes":"Named proponent in the Alberta inventory and in the February 2026 release.","party":"O'Leary Digital Limited","relationship_scope":"unknown","role":"developer","source_record_id":"wonder-valley-alberta"},{"evidence_id":"b60c7297-7fb2-552b-9442-1b871cf657c2","notes":"Named as the lead company when the project was announced in December 2024; later materials use O'Leary Digital.","party":"O'Leary Ventures","relationship_scope":"unknown","role":"developer","source_record_id":"wonder-valley-alberta"},{"evidence_id":"06c0bcf8-7abe-5ced-aad8-d754a6a570ba","notes":"Named as the lead company when the project was announced in December 2024; later materials use O'Leary Digital.","party":"O'Leary Ventures","relationship_scope":"unknown","role":"developer","source_record_id":"wonder-valley-alberta"},{"evidence_id":"b60c7297-7fb2-552b-9442-1b871cf657c2","notes":"Host municipality and partner; it owns the industrial gateway land and holds the area's Water Act licence.","party":"Municipal District of Greenview No. 16","relationship_scope":"unknown","role":"government","source_record_id":"wonder-valley-alberta"},{"evidence_id":"06c0bcf8-7abe-5ced-aad8-d754a6a570ba","notes":"Host municipality and partner; it owns the industrial gateway land and holds the area's Water Act licence.","party":"Municipal District of Greenview No. 16","relationship_scope":"unknown","role":"government","source_record_id":"wonder-valley-alberta"},{"evidence_id":"037f649a-0355-578e-b423-6ce6f1d6d63c","notes":"Host municipality and partner; it owns the industrial gateway land and holds the area's Water Act licence.","party":"Municipal District of Greenview No. 16","relationship_scope":"unknown","role":"government","source_record_id":"wonder-valley-alberta"},{"evidence_id":"65288924-cdc7-59d4-ba64-e37a3cf58398","notes":"Named as construction manager for the Alberta site.","party":"PCL Construction","relationship_scope":"unknown","role":"builder","source_record_id":"wonder-valley-alberta"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://tools.prnewswire.com/en-us/live/20823/release/20260217EN90212 | https://majorprojects.alberta.ca/details/Wonder-Valley-AI-Data-Centre-Park/11477 | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Wonder Valley AI data centre park (Alberta) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"wonder-valley-alberta"},"record":{"aliases":["Wonder Valley","Wonder Valley AI Data Centre Park","Wonder Valley Alberta"],"id":"wonder-valley-alberta","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","admin2":"Municipal District of Greenview No. 16","country":"CA","lat":54.8119,"locality":"Greenview Industrial Gateway (south of Grande Prairie)","lon":-118.6834,"note":"Point taken from the Government of Alberta major projects inventory entry for Phase 1 and rounded; the developer's FAQ places the site in the Greenview Industrial Gateway about 42 km south of Grande Prairie. Parcel boundaries were not published.","precision":"approximate_site","source_ids":["s3","s1","s8"]},"metrics":[{"applies_to":"campus","as_of":"2026-02-18","basis":"planned","metric":"power_capacity","note":"Described as off-grid generation to be delivered to hyperscale data centres over roughly a decade; the 2026 release calls it power generation capacity.","power_scope":"onsite_generation","qualifier":"up_to","source_ids":["s1","s2","s4"],"unit":"MW","value":7500},{"applies_to":"phase","as_of":"2024-12-09","basis":"planned","metric":"power_capacity","note":"First-phase off-grid power system using natural gas and geothermal resources.","phase_label":"Phase 1","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":1400},{"applies_to":"phase","as_of":"2026","basis":"planned","metric":"power_capacity","note":"Undated developer FAQ (2026 copyright) gives a larger Phase 1 figure than the 2024 announcement and says it would support up to ten facilities of roughly 100 MW of IT load each.","phase_label":"Phase 1","power_scope":"onsite_generation","qualifier":"up_to","source_ids":["s8"],"unit":"MW","value":2000},{"applies_to":"phase","as_of":"2024-12-09","basis":"announced","metric":"investment","note":"Cost cited for the first 1.4 GW of power. Lifetime spending above 70 billion dollars was also cited without a currency, and the Alberta inventory lists a 12.0 billion dollar Phase 1 estimate without a currency code; neither is recorded as a metric.","phase_label":"Phase 1","qualifier":"approximately","source_ids":["s1"],"unit":"USD","value":2000000000},{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"land_area","note":"Developer FAQ figure. The December 2024 announcement referred to a letter of intent for thousands of acres within and south of the gateway.","qualifier":"approximately","source_ids":["s8"],"unit":"acres","value":13000},{"applies_to":"campus","as_of":"2024-12-09","basis":"planned","metric":"floor_area","note":"Full build-out figure reported at announcement.","qualifier":"exact","source_ids":["s2"],"unit":"sq_ft","value":35000000}],"milestones":[{"date":"2024-12-09","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2025-04-07","event":"other","kind":"actual","note":"Alberta issued the Municipal District of Greenview a Water Act licence for up to 6 million cubic metres a year from the Smoky River for industrial use in the gateway; the developer FAQ cites this licence as the project's water access.","source_ids":["s6","s8"]},{"date":"2026-04-17","event":"other","kind":"actual","note":"Alberta's Environmental Appeals Board dismissed Sturgeon Lake Cree Nation's appeal of the gateway water licence, finding the Nation not directly affected.","source_ids":["s6","s7"]},{"date":"2027","event":"first_operational","kind":"planned","note":"Original target for a first phase, as described in December 2025 reporting; the schedule has since slipped.","source_ids":["s5"]},{"date":"2028-H2","event":"construction_started","kind":"planned","note":"A Greenview official said in late 2025 that construction might start in late 2028, versus an original plan to start by 2026.","source_ids":["s5"]},{"date":"2026-08","event":"other","kind":"actual","note":"Western Standard reported on 2026-08-14 that a judge rejected a bid backed by the O'Leary data centre side to halt a Sturgeon Lake Cree Nation challenge; the court, ruling date and subject of the challenge were not stated.","source_ids":["s9"]}],"name":"Wonder Valley AI data centre park (Alberta)","notes":"Status rests partly on two undated pages, the Government of Alberta major projects entry (stage: proposed) and the developer's FAQ (pre-construction, development stage), so status_as_of is the date they were read (2026-10-09).","parties":[{"name":"O'Leary Digital Limited","note":"Named proponent in the Alberta inventory and in the February 2026 release.","role":"developer","source_ids":["s3","s4","s8"]},{"name":"O'Leary Ventures","note":"Named as the lead company when the project was announced in December 2024; later materials use O'Leary Digital.","role":"developer","source_ids":["s1","s5"]},{"name":"Municipal District of Greenview No. 16","note":"Host municipality and partner; it owns the industrial gateway land and holds the area's Water Act licence.","role":"government","source_ids":["s1","s5","s6"]},{"name":"PCL Construction","note":"Named as construction manager for the Alberta site.","role":"builder","source_ids":["s4"]}],"power_sources":[{"description":"Off-grid generation fuelled by local natural gas is the primary planned supply.","source_ids":["s1","s2","s3"],"type":"natural_gas_onsite"},{"description":"Geothermal energy is named as a complementary or backstop supply for the off-grid system.","source_ids":["s1","s3","s5"],"type":"geothermal"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260421012811/https://calgary.tech/2024/12/09/kevin-oleary-leads-visionary-70-billion-ai-data-centre-project-in-alberta/","id":"s1","published":"2024-12-09","publisher":"Calgary.Tech","title":"Kevin O'Leary leads visionary $70 billion AI data centre project in Alberta","type":"news","url":"https://calgary.tech/2024/12/09/kevin-oleary-leads-visionary-70-billion-ai-data-centre-project-in-alberta/"},{"accessed":"2026-10-09","id":"s2","published":"2024-12-09","publisher":"Natural Gas World","title":"VC unveils plan for 7.5 GW data centre in Alberta","type":"trade_press","url":"https://www.naturalgasworld.com/vc-unveils-plan-for-7.5-gw-data-centre-in-alberta-118787"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929183026/https://majorprojects.alberta.ca/details/Wonder-Valley-AI-Data-Centre-Park/11477","id":"s3","published":null,"publisher":"Government of Alberta, Major Projects","title":"Wonder Valley AI Data Centre Park (Phase 1)","type":"government","url":"https://majorprojects.alberta.ca/details/Wonder-Valley-AI-Data-Centre-Park/11477"},{"accessed":"2026-10-09","id":"s4","published":"2026-02-18","publisher":"O'Leary Digital Limited via PR Newswire","title":"O'Leary Digital Forms Joint Venture to Advance 7.5 GW Wonder Valley Utah Campus; Alberta Permitting Underway","type":"company","url":"https://tools.prnewswire.com/en-us/live/20823/release/20260217EN90212"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260706172634/https://www.geothermalcanada.org/news/2025/12/17/the-truth-about-wonder-valley","id":"s5","published":"2025-12-10","publisher":"The Logic (republished by Geothermal Canada)","title":"The truth about Wonder Valley, Kevin O'Leary's data-centre dream","type":"news","url":"https://www.geothermalcanada.org/news/2025/12/17/the-truth-about-wonder-valley"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260518035010/https://www.eab.gov.ab.ca/media/r2slqi1d/eab-25-014-md-of-greenview-final.pdf","id":"s6","published":"2026-04-17","publisher":"Alberta Environmental Appeals Board","title":"Standing Decision: Sturgeon Lake Cree Nation v Designated Director under the Water Act, re: Municipal District of Greenview No. 16, 2026 ABEAB 9","type":"government","url":"https://www.eab.gov.ab.ca/media/r2slqi1d/eab-25-014-md-of-greenview-final.pdf"},{"accessed":"2026-10-09","id":"s7","published":"2026-05-15","publisher":"Hamilton Spectator (republished by Canada WaterPortal)","title":"First Nation's appeal on Wonder Valley water dismissed","type":"news","url":"https://waterportal.ca/water-news/wonder-valley-licence/"},{"accessed":"2026-10-09","id":"s8","published":null,"publisher":"O'Leary Digital","title":"Wonder Valley FAQ","type":"company","url":"https://www.olearydigital.ai/faq"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260816183217/https://www.westernstandard.news/news/judge-rejects-kevin-oleary-backed-data-centre-bid-to-halt-first-nation-challenge/75984","id":"s9","published":"2026-08-14","publisher":"Western Standard","title":"Judge rejects Kevin O'Leary-backed data centre bid to halt First Nation challenge","type":"news","url":"https://www.westernstandard.news/news/judge-rejects-kevin-oleary-backed-data-centre-bid-to-halt-first-nation-challenge/75984"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s4","s7","s3","s8"],"summary":"Proposed off-grid AI data centre park in the Greenview Industrial Gateway south of Grande Prairie, Alberta, announced in December 2024 by O'Leary Ventures with the Municipal District of Greenview and now led by O'Leary Digital. Backers describe up to 7.5 GW of on-site gas and geothermal generation built in phases, starting with 1.4 GW. O'Leary Digital said in February 2026 that Alberta permitting was underway; a December 2025 report said the site was undeveloped and construction might not start until late 2028. Sturgeon Lake Cree Nation lost an appeal of the gateway's water licence in April 2026; in August 2026 a judge refused an O'Leary-backed bid to halt a Nation challenge.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"b60c7297-7fb2-552b-9442-1b871cf657c2","s2":"0e2ea4ee-748a-5425-ba47-816efc6112b4","s3":"d43b045c-1fff-5626-9644-8a866d075e46","s4":"65288924-cdc7-59d4-ba64-e37a3cf58398","s5":"06c0bcf8-7abe-5ced-aad8-d754a6a570ba","s6":"037f649a-0355-578e-b423-6ce6f1d6d63c","s7":"fcdfd317-774e-55d1-9e1d-eb0a0c2002ad","s8":"0e3f5300-2d80-546c-86ee-7e8cb231b86a","s9":"42927f21-8267-59be-9df8-a322807aefd1"},"source_file":"datacenters/projects/wonder-valley-alberta.json","source_record_id":"wonder-valley-alberta","source_record_sha256":"8362b04814249174419268d40122ca73605913dfcf84412d960be5265857e94c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"35d730bb27d84824a53aab3fece2704ebbe9fabd9ef69e02b4c6cd792cd24d9d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0a62731022d2820e105f/#project-bb1b28fd-610b-5739-b928-e44f21cb6f1b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/bb1b28fd-610b-5739-b928-e44f21cb6f1b.json
bb2a6c51-4439-5bda-aa65-a5f7f9e14e98 | curated:china-telecom-shaotang-shaoguan:announced-campus-development | vcc-site-efe797bc04a70a7ce5bb | curated:china-telecom-shaotang-shaoguan | China Telecom Shaotang Campus Development | China | CN | 24.7875 | 113.6619 | Point | campus | direct_geometry | official_eia_geographic_dms_point_transcription | official_eia_on_campus_substation_locator | official_source | campus_locator | Reported center point of the campus 220kV substation in its northwest corner. Locates the campus through named on-campus support infrastructure; not a data-hall center, parcel centroid, or construction boundary. |  | No positional accuracy or coordinate datum stated. Numeric precision is source transcription precision, not positional accuracy; offset to individual data halls is unknown. | ba904be8-28ae-59dc-9fda-afca852eb5d9 | announced | 2026-09-21 | 22 | authoritative_project_announcement | 1a38543f-df6d-5aed-8878-b4bd2cf46893 | authoritative_project_record_plus_scoped_location | FALSE | not_reviewed | unknown | not established by selected evidence | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"ba904be8-28ae-59dc-9fda-afca852eb5d9","party":"China Telecom","relationship_scope":"intended","role":"operator"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | China Telecom |  |  |  | https://www.sg.gov.cn/smsg/sgqmshggn/content/post_2883361.html | https://www.sg.gov.cn/attachment/0/315/315394/2880917.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-efe797bc04a70a7ce5bb/#project-bb2a6c51-4439-5bda-aa65-a5f7f9e14e98 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/bb2a6c51-4439-5bda-aa65-a5f7f9e14e98.json
bb8ba3ad-d563-5f84-a543-079a10264640 | curated:cdc-maddington-perth-campus:current-build | vcc-site-e7cbc915d8b179b3017f | curated:cdc-maddington-perth-campus | CDC Maddington Current Build | Australia | AU | -32.0342 | 116.0052 | Polygon | campus | official_coordinate_transform | official_property_polygon | one_constituent_campus_lot | official_source | campus_locator | Exact transformed polygon for one of four officially identified Maddington campus lots; not the complete campus, an individual building, or current work area. |  | The public property service states no survey-grade horizontal accuracy after transformation. | 04eb4e29-b035-5d4f-b6dc-ababe98ba94e | shell | 2026-06-25 | 110 | authoritative_physical_status_update | 7f5a79ea-9dc0-574f-ae63-e00fe77d34ab | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/embed/feed/update/urn:li:activity:7475736271517286400 | https://maps.gosnells.wa.gov.au/intramaps22A/?project=Gosnells | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e7cbc915d8b179b3017f/#project-bb8ba3ad-d563-5f84-a543-079a10264640 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/bb8ba3ad-d563-5f84-a543-079a10264640.json
bc344b80-1656-5a9a-a788-a5f7cb59131e | imported:semiconductor-atlas:huntley-page-arizona | vcc-site-09a8ea20931b50e7a218 | imported:semiconductor-atlas:huntley-page-arizona | Page, Arizona data center site (Huntley LLC) | United States | US | 36.9142 | -111.5033 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of Page (s6). The city says the land lies on the southwest side of Page near Highway 98, about two miles from Horseshoe Bend, and that the exact building location is undetermined; other reports describe it as next to Horseshoe Bend. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 8f755fe0-608b-580c-a6fb-767c4d8df930 | proposed | 2026-10-09 | 4 | imported_documented_status | dafa4f8a-9cc6-5bb8-85ea-ed2ed15ef8ac | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8f755fe0-608b-580c-a6fb-767c4d8df930","notes":"Buyer of the city land under the sale agreement. Hoodline, citing filings and industry reporting, links it to UK real estate interests and a developer called Rooskey, with Arup as engineering partner; the city does not confirm those ties.","party":"Huntley LLC","relationship_scope":"unknown","role":"developer","source_record_id":"huntley-page-arizona"},{"evidence_id":"a1b1d4d6-cc0a-5616-8c4d-a97c6da90cc1","notes":"Buyer of the city land under the sale agreement. Hoodline, citing filings and industry reporting, links it to UK real estate interests and a developer called Rooskey, with Arup as engineering partner; the city does not confirm those ties.","party":"Huntley LLC","relationship_scope":"unknown","role":"developer","source_record_id":"huntley-page-arizona"},{"evidence_id":"dafa4f8a-9cc6-5bb8-85ea-ed2ed15ef8ac","notes":"The land is city-owned and subject to the sale agreement and its buy-back terms.","party":"City of Page","relationship_scope":"unknown","role":"owner","source_record_id":"huntley-page-arizona"},{"evidence_id":"8f755fe0-608b-580c-a6fb-767c4d8df930","notes":"Approved the land sale ordinance; two council members voted against it.","party":"Page City Council","relationship_scope":"unknown","role":"government","source_record_id":"huntley-page-arizona"},{"evidence_id":"066affc1-b93b-502b-92b6-a030a9f63198","notes":"Approved the land sale ordinance; two council members voted against it.","party":"Page City Council","relationship_scope":"unknown","role":"government","source_record_id":"huntley-page-arizona"},{"evidence_id":"a1b1d4d6-cc0a-5616-8c4d-a97c6da90cc1","notes":"Approved the land sale ordinance; two council members voted against it.","party":"Page City Council","relationship_scope":"unknown","role":"government","source_record_id":"huntley-page-arizona"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | City of Page |  |  |  |  | https://cityofpage.org/departments/economic-development/page-data-center-faq/ | https://azcir.org/news/2025/11/21/did-page-az-city-council-approve-the-sale-of-500-acres-for-a-data-center-yes/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Page, Arizona data center site (Huntley LLC) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"huntley-page-arizona"},"record":{"aliases":["Page data center","Horseshoe Bend data center proposal"],"id":"huntley-page-arizona","last_reviewed":"2026-10-09","location":{"admin1":"Arizona","country":"US","lat":36.9142,"locality":"Page","lon":-111.5033,"note":"Coordinates are the Wikipedia centroid of Page (s6). The city says the land lies on the southwest side of Page near Highway 98, about two miles from Horseshoe Bend, and that the exact building location is undetermined; other reports describe it as next to Horseshoe Bend.","precision":"locality","source_ids":["s1","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-21","basis":"planned","metric":"power_capacity","note":"Campus size described in filings and industry reporting, as relayed by Hoodline; the city FAQ gives no capacity.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-05-21","basis":"reported","metric":"investment","note":"Hoodline attributes this figure, which includes on-site energy work, to filings and industry reporting; Arizona's Family calls it a USD 10 billion proposal without a source. Not confirmed by the city or the company.","qualifier":"up_to","source_ids":["s2","s3"],"unit":"USD","value":10000000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"incentive_agreement","metric":"investment","note":"Minimum spending the land sale agreement requires within two years of closing, failing which the city may buy the land back.","qualifier":"at_least","source_ids":["s4"],"unit":"USD","value":20000000},{"applies_to":"campus","as_of":"2025-11-21","basis":"reported","metric":"land_area","note":"Agreed price of USD 14,000 an acre, about USD 7 million in total; the city says the sale cannot close until zoning and related issues are resolved.","qualifier":"approximately","source_ids":["s1","s3","s4"],"unit":"acres","value":500}],"milestones":[{"date":"2025-10-22","event":"other","kind":"actual","note":"City council passed Ordinance 744-25 approving the land sale agreement and a feasibility period.","source_ids":["s1","s3"]},{"date":"2025-Q4","event":"other","kind":"actual","note":"The city rejected a resident referendum petition against the sale over paperwork defects; reported by 17 December 2025.","source_ids":["s2","s3"]},{"date":"2026-09-17","event":"other","kind":"actual","note":"The city announced public hearings in September and October 2026 on a Data Center Overlay District text amendment.","source_ids":["s5"]}],"name":"Page, Arizona data center site (Huntley LLC)","notes":"Status is proposed: the city FAQ, an undated living page labelled September 2026 and dated here by access, says no construction, zoning, utility or development approvals have been granted and no water source has been approved. The developer must secure its own water and power. The FAQ puts the full timeline at six to eight years and lists further hearings on 28 October and 17 November 2026. Capacity and investment figures come from press accounts of filings, not from the city.","parties":[{"name":"Huntley LLC","note":"Buyer of the city land under the sale agreement. Hoodline, citing filings and industry reporting, links it to UK real estate interests and a developer called Rooskey, with Arup as engineering partner; the city does not confirm those ties.","role":"developer","source_ids":["s1","s3"]},{"name":"City of Page","note":"The land is city-owned and subject to the sale agreement and its buy-back terms.","role":"owner","source_ids":["s4"]},{"name":"Page City Council","note":"Approved the land sale ordinance; two council members voted against it.","role":"government","source_ids":["s1","s2","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-21","publisher":"Arizona Center for Investigative Reporting","title":"Did the Page City Council approve the sale of 500 acres for a data center?","type":"news","url":"https://azcir.org/news/2025/11/21/did-page-az-city-council-approve-the-sale-of-500-acres-for-a-data-center-yes/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260211095322/https://www.azfamily.com/2025/12/18/page-residents-push-back-10b-data-center-proposal-near-horseshoe-bend/","id":"s2","published":"2025-12-17","publisher":"Arizona's Family (KTVK/KPHO)","title":"Page residents push back on $10B data center proposal near Horseshoe Bend","type":"news","url":"https://www.azfamily.com/2025/12/18/page-residents-push-back-10b-data-center-proposal-near-horseshoe-bend/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260522044502/https://hoodline.com/2026/05/horseshoe-bend-uproar-page-locals-rage-over-1gw-data-hub-deal/","id":"s3","published":"2026-05-21","publisher":"Hoodline","title":"Horseshoe Bend Uproar, Page Locals Rage Over 1GW Data Hub Deal","type":"news","url":"https://hoodline.com/2026/05/horseshoe-bend-uproar-page-locals-rage-over-1gw-data-hub-deal/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260915004309/https://cityofpage.org/departments/economic-development/page-data-center-faq/","id":"s4","published":null,"publisher":"City of Page","title":"Page Data Center FAQ","type":"government","url":"https://cityofpage.org/departments/economic-development/page-data-center-faq/"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-17","publisher":"City of Page","title":"Proposed Data Center Overlay District Text Amendment","type":"government","url":"https://cityofpage.org/proposed-data-center-overlay-district-text-amendment/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006125909/https://en.wikipedia.org/wiki/Page,_Arizona","id":"s6","published":null,"publisher":"Wikipedia","title":"Page, Arizona","type":"other","url":"https://en.wikipedia.org/wiki/Page,_Arizona"}],"status":"proposed","status_as_of":"2026-10-09","status_source_ids":["s4","s5"],"summary":"Proposed data center campus on about 500 acres of city-owned recreational land on the southwest side of Page, Arizona, near Highway 98 and Horseshoe Bend. In October 2025 the city council passed Ordinance 744-25, a land sale agreement with Huntley LLC at USD 14,000 an acre with a feasibility period, milestones and a city buy-back right; it approves no construction, zoning or utilities. Press accounts of filings describe a campus of about 1 GW worth up to USD 10 billion including on-site energy work. A resident referendum petition was rejected on paperwork grounds in late 2025, and in autumn 2026 the city was holding hearings on data center zoning rules.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8f755fe0-608b-580c-a6fb-767c4d8df930","s2":"066affc1-b93b-502b-92b6-a030a9f63198","s3":"a1b1d4d6-cc0a-5616-8c4d-a97c6da90cc1","s4":"dafa4f8a-9cc6-5bb8-85ea-ed2ed15ef8ac","s5":"4337e1f9-4237-569b-9d1a-a1baefbd48b2","s6":"410cc30c-454d-5a44-97a4-6aa2abccfa87"},"source_file":"datacenters/projects/huntley-page-arizona.json","source_record_id":"huntley-page-arizona","source_record_sha256":"97f36630761d76604a66ebb99d8f270114cf82e816eff5b78d0570cacf0af6d6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5ffdef31fd7f5c480616237bf78c6d912d7c2c7fa1e9e8bb1aea2fb910570a10"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-09a8ea20931b50e7a218/#project-bc344b80-1656-5a9a-a788-a5f7cb59131e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/bc344b80-1656-5a9a-a788-a5f7cb59131e.json
bdfd522f-2d7e-5d1f-8e00-3c43b462ed27 | curated:amazon-falls-township-innovation-campus:active-buildout | vcc-site-138d436c47cc25fa668a | curated:amazon-falls-township-innovation-campus | Amazon Falls Township Active Campus Buildout | United States | US | 40.1555 | -74.75 | Polygon | campus | official_parcel_polygon | county_service_outSR_4326_rings_to_geojson_without_boundary_inference | official_tax_parcel_constituent_campus_locator | official_source | campus_locator | Exact county tax parcel 13-051-001-034 for reused building six only. This locates a constituent of the Amazon Falls Township campus, not its full 250-acre development, individual new halls or construction footprint. Display anchor is the coordinate-envelope midpoint used only for rendering; it is not an observed center. |  | No source provides a numeric horizontal-accuracy guarantee or a surveyed campus reference feature. | 4f2ffb6c-d4e6-51d6-8105-3deea9fb32e1 | under_construction | 2026-07-19 | 86 | authoritative_construction_start | 5f1bf174-99c0-55f0-bf94-b496cb6230fb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.amazoninnovationinpa.com/falls-township-innovation-campus/ | https://services3.arcgis.com/SP47Tddf7RK32lBU/ArcGIS/rest/services/Bucks_County_Parcels/FeatureServer/0/query?where=PARCEL_NUM%3D%2713-051-001-034%27&outFields=OBJECTID,PARCEL_NUM,ADDRESS,MUNICIPALITY,DEED_AREA,OWNER1,OWNER2,LAND_USE_CODE,MODIFY_DATE&returnGeometry=true&outSR=4326&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-138d436c47cc25fa668a/#project-bdfd522f-2d7e-5d1f-8e00-3c43b462ed27 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/bdfd522f-2d7e-5d1f-8e00-3c43b462ed27.json
be6d721d-f632-5c86-a057-78774604bc6c | curated:goodman-par01-paris-data-centre-campus:phase-1-current-development | vcc-site-5adc03aabe03531ee95f | curated:goodman-par01-paris-data-centre-campus | Goodman PAR01 Phase 1 Current Development | France | FR | 48.9676 | 2.5694 | Point | campus | official_exact_house_number_geocode | exact_named_address_feature_to_point_without_centroiding | official_address_campus_locator | official_source | campus_locator | The exact house-number point locates the reviewed Goodman campus address, not any specific phase, building, campus boundary or observed-work extent. Multiple buildings on this campus remain one physical site. |  | The service supplies a house-number address point without a numeric horizontal-accuracy statement. Match score is not positional uncertainty. | 17a1d516-33f6-5108-9c04-806f94890963 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 388f30b8-8e1e-537c-a590-14a13c4a4e0b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | https://data.geopf.fr/geocodage/search?q=13%20Rue%20Charles%20Cros%2093290%20Tremblay-en-France&index=address&limit=5 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5adc03aabe03531ee95f/#project-be6d721d-f632-5c86-a057-78774604bc6c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/be6d721d-f632-5c86-a057-78774604bc6c.json
be874ef3-dd3e-54dd-be06-f01895ac6992 | curated:china-telecom-cloud-computing-guizhou-information-park:phase-2-1-b5-b6-data-center-build | vcc-site-03a8f52a32b90569e4e1 | curated:china-telecom-cloud-computing-guizhou-information-park | China Telecom Guizhou Information Park B5/B6 Civil Works | China | CN | 26.38 | 106.54 | Point | campus | direct_geometry | literal_reported_campus_coordinates_no_transformation | institutional_report_approximate_campus_reference_point | official_source | campus_locator | The SASAC official account names the China Telecom Guizhou Information Park and publishes 26.38 N, 106.54 E to two decimal places. This is an approximate campus reference, not a B5/B6 building, parcel, entrance or work-extent locator. The original datum is not stated; values are retained literally without a claimed CRS conversion. |  | Coordinates published to 0.01 degree; datum, surveyed reference feature and measured horizontal accuracy are unknown. Rounding alone is roughly kilometre scale, and no precise building position or accuracy radius is inferred. | b29dd16b-b07a-5737-9570-ee1a8811fca2 | completed | 2026-09-20 | 23 | authoritative_physical_status_update | b0a029a2-77ac-57a8-b770-0d1c41dfd0a7 | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed | unknown | not established by selected evidence | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://5bur.cscec.com/oa/dtxw/202609/3960801.html | https://m.thepaper.cn/newsDetail_forward_32634480 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-03a8f52a32b90569e4e1/#project-be874ef3-dd3e-54dd-be06-f01895ac6992 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/be874ef3-dd3e-54dd-be06-f01895ac6992.json
bf8d11a2-72a6-500d-a532-98fb73958c84 | curated:iron-mountain-madrid-data-center-campus:mad-2-mad-3-20mw-development | vcc-site-0baa18deeb394aec986b | curated:iron-mountain-madrid-data-center-campus | Iron Mountain MAD-2 and MAD-3 20 MW Development | Spain | ES | 40.4582 | -3.4985 | Point | campus | official_exact_street_number_address_point | select_exact_CartoCiudad_portal_result_and_preserve_service_WGS84_coordinates | official_address_point_campus_locator | official_source | campus_locator | The operator names Calle Mar Egeo 4 for its whole Madrid campus. The selected government result locates that address, not an individual data hall, parcel boundary, active works or a surveyed building point. The two current components count as one physical campus. |  | The exact returned address point has no published source-specific numeric horizontal accuracy; decimal precision is not accuracy. | 71e329e6-eaa7-5cff-8740-459fd32d5449 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | f672b5f3-72b9-5d29-9683-b3b2fbbd9999 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1020569/000102056926000068/q22026srpfinal.htm | https://www.cartociudad.es/geocoder/api/geocoder/candidates?q=Calle%20Mar%20Egeo%204%20San%20Fernando%20de%20Henares&limit=5 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0baa18deeb394aec986b/#project-bf8d11a2-72a6-500d-a532-98fb73958c84 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/bf8d11a2-72a6-500d-a532-98fb73958c84.json
c01906b8-f76a-5afe-ae86-ea56184443f3 | imported:semiconductor-atlas:nebius-independence-missouri | vcc-site-acf731facf63970bd84b | imported:semiconductor-atlas:nebius-independence-missouri | Nebius Independence AI factory | United States | US | 39.0925 | -94.4139 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City centroid from the Wikipedia infobox for Independence (s3). The groundbreaking release places the roughly 400-acre site in eastern Independence and the project page puts it at Route 78 and Little Blue Parkway, but no geocoder was used, so the point is the city centroid rather than the site. The city spans Jackson and Clay counties, so no county is given. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c | under_construction | 2026-10-09 | 4 | imported_documented_status | 3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c","notes":null,"party":"Nebius","relationship_scope":"unknown","role":"developer","source_record_id":"nebius-independence-missouri"},{"evidence_id":"276230cb-6f75-55ca-9fe4-81acaf55bb82","notes":null,"party":"Nebius","relationship_scope":"unknown","role":"developer","source_record_id":"nebius-independence-missouri"},{"evidence_id":"276230cb-6f75-55ca-9fe4-81acaf55bb82","notes":"The project page says Nebius bought the land from Northpoint in December 2025.","party":"Nebius","relationship_scope":"unknown","role":"owner","source_record_id":"nebius-independence-missouri"},{"evidence_id":"3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c","notes":"General contractor for phase 1.","party":"ARCO National Construction","relationship_scope":"unknown","role":"builder","source_record_id":"nebius-independence-missouri"},{"evidence_id":"276230cb-6f75-55ca-9fe4-81acaf55bb82","notes":"General contractor for phase 1.","party":"ARCO National Construction","relationship_scope":"unknown","role":"builder","source_record_id":"nebius-independence-missouri"},{"evidence_id":"276230cb-6f75-55ca-9fe4-81acaf55bb82","notes":"To supply 800 MW through the Southwest Power Pool grid and deliver initial power in the second half of 2026.","party":"Independence Power & Light","relationship_scope":"unknown","role":"utility","source_record_id":"nebius-independence-missouri"},{"evidence_id":"276230cb-6f75-55ca-9fe4-81acaf55bb82","notes":"City Council approved the Chapter 100 industrial development incentive in March 2026.","party":"City of Independence","relationship_scope":"unknown","role":"government","source_record_id":"nebius-independence-missouri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Nebius |  |  |  |  | https://nebius.com/newsroom/nebius-breaks-ground-on-gigawatt-scale-ai-factory-in-independence-missouri | https://nebius.com/newsroom/nebius-breaks-ground-on-gigawatt-scale-ai-factory-in-independence-missouri | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Nebius Independence AI factory as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"nebius-independence-missouri"},"record":{"aliases":["Nebius Independence, Missouri AI factory"],"id":"nebius-independence-missouri","last_reviewed":"2026-10-09","location":{"admin1":"Missouri","country":"US","lat":39.0925,"locality":"Independence","lon":-94.4139,"note":"City centroid from the Wikipedia infobox for Independence (s3). The groundbreaking release places the roughly 400-acre site in eastern Independence and the project page puts it at Route 78 and Little Blue Parkway, but no geocoder was used, so the point is the city centroid rather than the site. The city spans Jackson and Clay counties, so no county is given.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total capacity on the undated project page, accessed on this date; the groundbreaking release calls the project gigawatt-scale without a figure.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s2"],"unit":"MW","value":1200},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Share of the 1.2 GW the project FAQ attributes to Independence Power & Light; a further study for additional utility power is expected in early 2029.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":800},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"On-site generation share in the FAQ; the same page says on-site generation is still being evaluated for a future phase.","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":400},{"applies_to":"campus","as_of":"2026-05-12","basis":"acquired","metric":"land_area","qualifier":"approximately","source_ids":["s1","s2"],"unit":"acres","value":400},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s2"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2026-05-12","basis":"planned","metric":"jobs_construction","note":"The project page says more than 1,000.","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2026-05-12","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s1","s2"],"unit":"count","value":130}],"milestones":[{"date":"2025-12","event":"site_acquired","kind":"actual","note":"Land purchased from Northpoint.","source_ids":["s2"]},{"date":"2026-03","event":"other","kind":"actual","note":"Independence City Council approved the Chapter 100 industrial development incentive application.","source_ids":["s2"]},{"date":"2026-05-12","event":"construction_started","kind":"actual","note":"Groundbreaking; construction of the first phase underway.","source_ids":["s1","s2"]},{"date":"2026-H2","event":"other","kind":"planned","note":"Independence Power & Light expected to deliver initial power.","source_ids":["s2"]}],"name":"Nebius Independence AI factory","notes":"The Independence project page is undated; status_as_of and the as_of dates of figures taken only from it are the date it was accessed, when it said construction had begun.","parties":[{"name":"Nebius","role":"developer","source_ids":["s1","s2"]},{"name":"Nebius","note":"The project page says Nebius bought the land from Northpoint in December 2025.","role":"owner","source_ids":["s2"]},{"name":"ARCO National Construction","note":"General contractor for phase 1.","role":"builder","source_ids":["s1","s2"]},{"name":"Independence Power & Light","note":"To supply 800 MW through the Southwest Power Pool grid and deliver initial power in the second half of 2026.","role":"utility","source_ids":["s2"]},{"name":"City of Independence","note":"City Council approved the Chapter 100 industrial development incentive in March 2026.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"Power from Independence Power & Light, a city utility in the Southwest Power Pool, with Nebius paying full costs; a privately financed plant by Independence Power Partners at the retired Blue Valley plant site is described as part of the supply plan.","source_ids":["s2"],"type":"grid"},{"description":"Possible on-site generation of about 400 MW for a future phase, technology not specified and still under evaluation.","source_ids":["s2"],"type":"other"},{"description":"Two diesel emergency generators per building.","source_ids":["s2"],"type":"diesel_backup"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-05-12","publisher":"Nebius","title":"Nebius breaks ground on gigawatt-scale AI factory in Independence, Missouri","type":"company","url":"https://nebius.com/newsroom/nebius-breaks-ground-on-gigawatt-scale-ai-factory-in-independence-missouri"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260806031252/https://nebius.com/independencemo","id":"s2","published":null,"publisher":"Nebius","title":"Nebius in Independence, Missouri project page","type":"company","url":"https://nebius.com/independencemo"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Wikipedia","title":"Independence, Missouri","type":"other","url":"https://en.wikipedia.org/wiki/Independence,_Missouri"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s1","s2"],"summary":"Nebius is building what it calls its first gigawatt-scale AI infrastructure project in the US on about 400 acres in eastern Independence, Missouri, near Route 78 and Little Blue Parkway. The project page describes up to 1.2 GW across four buildings built over five to seven years, with 800 MW from Independence Power & Light and 400 MW of possible on-site generation still under evaluation. Nebius bought the land in December 2025, the City Council approved a Chapter 100 incentive in March 2026, and ground was broken in May 2026 with ARCO as general contractor.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c","s2":"276230cb-6f75-55ca-9fe4-81acaf55bb82","s3":"5ef8dbfb-f2a9-5734-ac71-94a3ee1824b7"},"source_file":"datacenters/projects/nebius-independence-missouri.json","source_record_id":"nebius-independence-missouri","source_record_sha256":"520960b450397b2cfae36eb12989945f7e799ceb6836cefd2f9542e954ffef16","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1b9ccbaaf57cd5c5e551035623b45f974f59cb70ae4edeabd2e8373c17083989"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-acf731facf63970bd84b/#project-c01906b8-f76a-5afe-ae86-ea56184443f3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c01906b8-f76a-5afe-ae86-ea56184443f3.json
c01f2073-5c23-511c-9d85-80ad9345987a | imported:semiconductor-atlas:nebius-birmingham-alabama | vcc-site-8cdb2274a5a7f5abf1c9 | imported:semiconductor-atlas:nebius-birmingham-alabama | Nebius Birmingham AI factory (Lakeshore Parkway) | United States | US | 33.5175 | -86.8094 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City centroid from the Wikipedia infobox for Birmingham (s3). The report places the site off Lakeshore Parkway without an address, so the point is the city centroid, not the site. Birmingham spans Jefferson and Shelby counties, so no county is given. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 8039fb20-c919-5864-948c-86bd8da72cdd | proposed | 2026-02-10 | 245 | imported_documented_status | 8039fb20-c919-5864-948c-86bd8da72cdd | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8039fb20-c919-5864-948c-86bd8da72cdd","notes":null,"party":"Nebius","relationship_scope":"unknown","role":"developer","source_record_id":"nebius-birmingham-alabama"},{"evidence_id":"0e272cde-13f1-5c9e-91d4-877af3058c04","notes":null,"party":"Nebius","relationship_scope":"unknown","role":"developer","source_record_id":"nebius-birmingham-alabama"},{"evidence_id":"8039fb20-c919-5864-948c-86bd8da72cdd","notes":"Reported to own about 80 acres off Lakeshore Parkway.","party":"Nebius","relationship_scope":"unknown","role":"owner","source_record_id":"nebius-birmingham-alabama"},{"evidence_id":"8039fb20-c919-5864-948c-86bd8da72cdd","notes":"WBRC said it was told Alabama Power would serve the facility; the source of that statement is not named.","party":"Alabama Power","relationship_scope":"unknown","role":"utility","source_record_id":"nebius-birmingham-alabama"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Nebius |  |  |  |  | https://www.wbrc.com/2026/02/11/ai-factory-being-proposed-along-lakeshore-parkway-birmingham/ | https://www.wbrc.com/2026/02/11/ai-factory-being-proposed-along-lakeshore-parkway-birmingham/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Nebius Birmingham AI factory (Lakeshore Parkway) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"nebius-birmingham-alabama"},"record":{"aliases":[],"id":"nebius-birmingham-alabama","last_reviewed":"2026-10-09","location":{"admin1":"Alabama","country":"US","lat":33.5175,"locality":"Birmingham","lon":-86.8094,"note":"City centroid from the Wikipedia infobox for Birmingham (s3). The report places the site off Lakeshore Parkway without an address, so the point is the city centroid, not the site. Birmingham spans Jefferson and Shelby counties, so no county is given.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-02-10","basis":"planned","metric":"power_capacity","note":"Unattributed figure: WBRC reported it as information it was told without naming the source; Nebius is not quoted on it.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-02-10","basis":"acquired","metric":"land_area","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":80},{"applies_to":"campus","as_of":"2026-02-10","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1"],"unit":"count","value":2}],"milestones":[{"date":"2026-02-10","event":"other","kind":"actual","note":"WBRC reported the proposal and an early-phase permit application with the city.","source_ids":["s1"]}],"name":"Nebius Birmingham AI factory (Lakeshore Parkway)","parties":[{"name":"Nebius","role":"developer","source_ids":["s1","s2"]},{"name":"Nebius","note":"Reported to own about 80 acres off Lakeshore Parkway.","role":"owner","source_ids":["s1"]},{"name":"Alabama Power","note":"WBRC said it was told Alabama Power would serve the facility; the source of that statement is not named.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Reported to be served by Alabama Power.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-02-10","publisher":"WBRC","title":"'AI factory' being proposed along Lakeshore Parkway in Birmingham","type":"news","url":"https://www.wbrc.com/2026/02/11/ai-factory-being-proposed-along-lakeshore-parkway-birmingham/"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-10","publisher":"Nebius","title":"Nebius x Vineland, NJ fact sheet","type":"company","url":"https://assets.nebius.com/assets/729154ac-8d55-459f-9dd6-8f85a40da15b/NEW%20Vineland%20NJ%20Fact%20Sheet_7.10.26.pdf?cache-buster=2026-07-10T18:45:11.445Z"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Wikipedia","title":"Birmingham, Alabama","type":"other","url":"https://en.wikipedia.org/wiki/Birmingham,_Alabama"}],"status":"proposed","status_as_of":"2026-02-10","status_source_ids":["s1"],"summary":"Nebius has proposed a two-building AI factory on about 80 acres it owns off Lakeshore Parkway in Birmingham, Alabama, reusing a former bank back-office building. Local television reported in February 2026, without naming who supplied the figure, that Alabama Power would serve the 300 MW facility; it also reported an early-phase permit application with the city and a proposed six-month pause on new data centers. Nebius listed Birmingham among its US data center locations in July 2026. No investment figure, job count or schedule appears in the cited sources.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8039fb20-c919-5864-948c-86bd8da72cdd","s2":"0e272cde-13f1-5c9e-91d4-877af3058c04","s3":"142ec0fd-0dbf-5254-a749-9111129a6f73"},"source_file":"datacenters/projects/nebius-birmingham-alabama.json","source_record_id":"nebius-birmingham-alabama","source_record_sha256":"0aab4bda32e1c1b74b9110271f1466bebe21f707042341167cb2d486459c1505","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"815d32dbd9fa778b0e8a34c8bc358d75d8df7eb8fe861b6f652544f90f75ccff"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8cdb2274a5a7f5abf1c9/#project-c01f2073-5c23-511c-9d85-80ad9345987a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c01f2073-5c23-511c-9d85-80ad9345987a.json
c04bedc0-51b3-5d4d-996c-1d1e56de96c0 | curated:goodman-hkg09-kwai-chung-data-centre:current-redevelopment | vcc-site-0bec2abc5fdac2e0fcf6 | curated:goodman-hkg09-kwai-chung-data-centre | Goodman HKG09 Current Redevelopment | Hong Kong | HK | 22.3679 | 114.1363 | Point | campus | cross_source_overlay | official_company_exact_address_to_lands_department_location_search_and_official_hk80_wgs84_transform | official_lands_department_address_building_reference_point | official_source | campus_locator | Official address/building reference point used only to locate the HKG09 campus inherited by the current redevelopment. It is not a parcel, building footprint or centroid, redevelopment extent, construction extent, campus boundary, or survey-accuracy claim. |  | The Location Search API and transformation API do not publish numeric horizontal accuracy for this selected result; the transformation service warns against precise-point applications. | 9f4c707b-692b-5d29-b1df-3db4259967cc | under_construction | 2026-07-15 | 90 | authoritative_construction_start | 3cdab590-3e47-5972-8a2a-f164a6a59916 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-20","base":28.0,"confidence":0.99,"evidence_id":"68917683-63f2-5256-90ed-6b310d354ebc","high":28.0,"low":28.0,"method":"reported","metric":"critical_it_mw","notes":"Source-explicit approximately 28 MW of planned HKG09 IT power. The approximation interval is not quantified. This is distinct from, and non-additive with, the 50 MW secured-primary-power row and is not current load, measured consumption, gross facility demand, generation, or annual energy.","stage":"planned","target_date":null,"unit":"MW"},{"as_of_date":"2026-07-20","base":50.0,"confidence":0.99,"evidence_id":"68917683-63f2-5256-90ed-6b310d354ebc","high":50.0,"low":50.0,"method":"reported","metric":"grid_connection_mw","notes":"Source-explicit 50 MW of HKG09 primary power secured, normalized conservatively as contracted grid connection. This is distinct from, and non-additive with, approximately 28 MW IT power and is not installed or energized capacity, current draw, gross facility demand, generation, annual energy, or measured consumption.","stage":"contracted","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://hk.goodman.com/en/about-goodman/media-centre/news/2026/20260716-goodman-advances-hkg09-groundbreaking | https://www.geodetic.gov.hk/transform/v2/?inSys=hkgrid&outSys=wgsgeog&e=832091&n=825415 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0bec2abc5fdac2e0fcf6/#project-c04bedc0-51b3-5d4d-996c-1d1e56de96c0 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c04bedc0-51b3-5d4d-996c-1d1e56de96c0.json
c0f8dadf-2c3d-5176-b649-85363c06e1fa | imported:semiconductor-atlas:meta-montgomery | vcc-site-4905a5572ec5f3fc6e2d | imported:semiconductor-atlas:meta-montgomery | Meta Montgomery data center | United States | US | 32.3777 | -86.3091 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City point from OpenStreetMap Nominatim; Meta gives no site address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 26e820ae-0d05-593e-9d5f-794caa26f215 | under_construction | 2026-10-09 | 4 | imported_documented_status | a422880d-f1ff-5477-9149-87a2bafa08f0 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"26e820ae-0d05-593e-9d5f-794caa26f215","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-montgomery"},{"evidence_id":"cd5ba844-f6e3-5f69-b795-75ac11188ffb","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-montgomery"},{"evidence_id":"26e820ae-0d05-593e-9d5f-794caa26f215","notes":"Meta refers readers to Hensel Phelps for construction information.","party":"Hensel Phelps","relationship_scope":"unknown","role":"builder","source_record_id":"meta-montgomery"},{"evidence_id":"a422880d-f1ff-5477-9149-87a2bafa08f0","notes":"Named in Meta's fact sheet as its energy-planning partner.","party":"Alabama Power","relationship_scope":"unknown","role":"utility","source_record_id":"meta-montgomery"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Montgomery-Data-Center.pdf | https://datacenters.atmeta.com/2024/05/hello-montgomery/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Montgomery data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-montgomery"},"record":{"aliases":["Montgomery Data Center"],"id":"meta-montgomery","last_reviewed":"2026-10-09","location":{"admin1":"Alabama","country":"US","lat":32.3777,"locality":"Montgomery","lon":-86.3091,"note":"City point from OpenStreetMap Nominatim; Meta gives no site address.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2024-05-02","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2025-09-23","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s2","s3","s4"],"unit":"USD","value":1500000000},{"applies_to":"phase","as_of":"2024-05-02","basis":"planned","metric":"floor_area","phase_label":"Original campus","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":715000},{"applies_to":"campus","as_of":"2025-09-23","basis":"planned","metric":"floor_area","note":"Described as nearly 1.3 million square feet after the expansion.","qualifier":"approximately","source_ids":["s2"],"unit":"sq_ft","value":1300000},{"applies_to":"campus","as_of":"2025-09-23","basis":"planned","metric":"jobs_construction","qualifier":"more_than","source_ids":["s1","s2","s4"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_construction","note":"From Meta's undated fact sheet, read 2026-10-09; conflicts with the more than 1,000 given in Meta's posts and location list.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":4000},{"applies_to":"campus","as_of":"2025-09-23","basis":"planned","metric":"jobs_permanent","qualifier":"more_than","source_ids":["s2","s4"],"unit":"count","value":100},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_permanent","note":"From Meta's undated fact sheet, read 2026-10-09; conflicts with the more than 100 given in Meta's 2025 post and location list.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":300}],"milestones":[{"date":"2024-05-02","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024","event":"construction_started","kind":"actual","note":"Meta's location list gives 2024 as the groundbreaking year.","source_ids":["s4"]},{"date":"2025-09-23","event":"expansion_announced","kind":"actual","note":"Two additional buildings, nearly doubling the investment.","source_ids":["s2"]}],"name":"Meta Montgomery data center","notes":"The status rests on two undated Meta pages: the U.S. location list, which gives 2024 as the groundbreaking year, and the fact sheet, which describes the data center in the future tense. status_as_of is therefore the date both were read (2026-10-09). The fact sheet PDF shows no publication date; its embedded file creation date is 2026-09-02.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Hensel Phelps","note":"Meta refers readers to Hensel Phelps for construction information.","role":"builder","source_ids":["s1"]},{"name":"Alabama Power","note":"Named in Meta's fact sheet as its energy-planning partner.","role":"utility","source_ids":["s3"]}],"power_sources":[{"description":"Meta says it planned its energy needs with Alabama Power, pays the full cost of the energy used and matches its use with clean and renewable energy; its 2025 post cites Meta-supported clean energy projects adding 227 MW in Alabama.","source_ids":["s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260616180446/https://datacenters.atmeta.com/2024/05/hello-montgomery/","id":"s1","published":"2024-05-02","publisher":"Meta Platforms","title":"Hello, Montgomery!","type":"company","url":"https://datacenters.atmeta.com/2024/05/hello-montgomery/"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-23","publisher":"Meta Platforms","title":"Montgomery, we're growing!","type":"company","url":"https://datacenters.atmeta.com/2025/09/montgomery-were-growing/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Meta Platforms","title":"Meta Montgomery Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Montgomery-Data-Center.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007122559/https://datacenters.atmeta.com/us-locations/","id":"s4","published":null,"publisher":"Meta Platforms","title":"United States - Meta Data Centers","type":"company","url":"https://datacenters.atmeta.com/us-locations/"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s3","s4"],"summary":"Meta data center campus in Montgomery, Alabama. Announced in May 2024 as a 715,000-square-foot campus worth more than USD 800 million, it was expanded in September 2025 with two more buildings, bringing the campus to nearly 1.3 million square feet and the investment to more than USD 1.5 billion; Meta says it will be optimized for AI workloads. Meta's location list gives 2024 as the groundbreaking year. Meta names Alabama Power as its energy-planning partner and refers readers to Hensel Phelps for construction information. Meta's undated fact sheet gives job estimates well above those in its earlier posts.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"26e820ae-0d05-593e-9d5f-794caa26f215","s2":"cd5ba844-f6e3-5f69-b795-75ac11188ffb","s3":"a422880d-f1ff-5477-9149-87a2bafa08f0","s4":"bea9cdd6-497f-5ee8-905a-08953042f84f"},"source_file":"datacenters/projects/meta-montgomery.json","source_record_id":"meta-montgomery","source_record_sha256":"ca356acb7d71bb8501b5d2bfa601c1dcc4bce58c72de4e9ab7349dd3af9a18e1","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7dd60b5baf9ed99f11101e2450870cf030b35efe48cf582b94f66282faa15b24"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4905a5572ec5f3fc6e2d/#project-c0f8dadf-2c3d-5176-b649-85363c06e1fa | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c0f8dadf-2c3d-5176-b649-85363c06e1fa.json
c1016e49-7b45-52ff-8938-0bd01e78a7ad | curated:dvz-schwerin-luebecker-strasse-campus:new-modular-data-center-current-build | vcc-site-f616a1fa427698a3ecec | curated:dvz-schwerin-luebecker-strasse-campus | DVZ Schwerin New Modular Data Center Current Build | Germany | DE | 53.647 | 11.3811 | Point | campus | copy_Overpass_center_for_named_DVZ_data_center_campus_way1545965488 | copy_Overpass_center_for_named_DVZ_data_center_campus_way1545965488 | community_mapped_campus_reference_point | community_source | campus_locator | A representative point for the entire named DVZ campus. The operator's plot description and TED exact-address clause bind the new building to this campus. The point is not claimed to locate the new building footprint or its active work extent; individual office centers are not selected. |  | No source states survey accuracy or quantitative positional uncertainty. | 123278b3-cec1-5c38-b035-facda8b70f25 | under_construction | 2026-07-31 | 74 | authoritative_physical_status_update | ad5920da-5084-504e-8d8a-3d6d2a6b0348 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.dvz-mv.de/sites/default/files/2026-07/community-01-2026_BF-final.pdf | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bnwr%5B%22name%22~%22DVZ%7CDatenverarbeitungszentrum%22%2Ci%5D%2853.6%2C11.3%2C53.7%2C11.45%29%3Bout%20meta%20center%3B | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f616a1fa427698a3ecec/#project-c1016e49-7b45-52ff-8938-0bd01e78a7ad | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c1016e49-7b45-52ff-8938-0bd01e78a7ad.json
c160d8d5-7572-53c2-8051-cd7990b1f771 | curated:odata-dc-sp04-osasco-campus:phase-2-expansion | vcc-site-c2fa5b54c32ada55d1e4 | curated:odata-dc-sp04-osasco-campus | ODATA DC SP04 Phase 2 Expansion | Brazil | BR | -23.4832 | -46.776 | Point | campus | first_party_published_map_pin | first_party_published_map_pin | operator_facility_pin | official_source | campus_locator | Operator-embedded terminal place-pin values, not the map viewport center and not a parcel or Phase 2 work footprint; decimal digits are not an accuracy claim. |  | The embedded Google place pin carries no publisher-stated accuracy. | ec98aabb-2dd1-5a20-813a-cb4682042aa2 | under_construction | 2026-06-18 | 117 | authoritative_physical_status_update | 31feb8fa-3920-5576-aa53-b7ac0b67e434 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/embed/feed/update/urn:li:activity:7473377620018077696 | https://odatacolocation.com/blog/data-center/dc-sp04/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c2fa5b54c32ada55d1e4/#project-c160d8d5-7572-53c2-8051-cd7990b1f771 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c160d8d5-7572-53c2-8051-cd7990b1f771.json
c1af62b5-b9a2-5c15-a8a4-717e1a65ac05 | curated:microsoft-finland-espoo-hepokorpi-campus:second-building | vcc-site-81f27673b0960b9da911 | curated:microsoft-finland-espoo-hepokorpi-campus | Microsoft Espoo Second Datacenter Building | Finland | FI | 60.2378 | 24.6875 | Polygon | project | official_registered_parcel_coordinate_transform | exact_parcel_49-65-3-1_EPSG3879_to_EPSG4326_with_planar_area_centroid_anchor | official_registered_parcel_containing_selected_project | official_source | project_locator | Registered parcel 49-65-3-1 contains the selected second building and the first-building project. It is a parcel locator, not a data-center campus boundary or building footprint. The planar area-weighted centroid is a derived display anchor, not an official building-center coordinate; third-building parcel 49-65-2-1 is excluded. |  | The selected property-unit response states no numeric horizontal accuracy for this parcel geometry. | 9ba2902e-39d3-51fc-abcb-9a36d3a66d72 | under_construction | 2026-06-11 | 124 | authoritative_physical_status_update | b80a4916-7cc6-5898-9269-3b84ae424785 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://espoo.oncloudos.com/cgi/DREQUEST.PHP?id=20261687-10&page=meetingitem | https://kartat.espoo.fi/teklaogcweb/wfs.ashx?SERVICE=WFS&REQUEST=GetFeature&VERSION=1.1.0&TYPENAME=GIS%3AKiinteistot_karsittu&OUTPUTFORMAT=GML2&SRSNAME=EPSG%3A3879&MAXFEATURES=10&FILTER=%3Cogc%3AFilter%20xmlns%3Aogc%3D%22http%3A%2F%2Fwww.opengis.net%2Fogc%22%3E%3Cogc%3APropertyIsEqualTo%3E%3Cogc%3APropertyName%3EKiinteistotunnus%3C%2Fogc%3APropertyName%3E%3Cogc%3ALiteral%3E49-65-3-1%3C%2Fogc%3ALiteral%3E%3C%2Fogc%3APropertyIsEqualTo%3E%3C%2Fogc%3AFilter%3E | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-81f27673b0960b9da911/#project-c1af62b5-b9a2-5c15-a8a4-717e1a65ac05 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c1af62b5-b9a2-5c15-a8a4-717e1a65ac05.json
c23fe40c-0685-5cee-8fab-9c08575e6b27 | curated:qts-aurora-den1-campus:dc2-current-fit-out | vcc-site-98db91806e7e60522076 | curated:qts-aurora-den1-campus | QTS Aurora DEN1 DC2 Current Fit-Out | United States | US | 39.7338 | -104.7124 | Point | campus | official_address_point | Official_ArcGIS_address_geometry_EPSG2232_to_EPSG4326_explicit_datum1188_independently_checked | official_constituent_address_reference_point | official_source | campus_locator | City address point for exact DEN1 DC2 constituent at1140 N Gun Club Road. It is not a campus boundary, centroid, entrance, surveyed building location or actual drywall-work footprint; unknown real-world positional accuracy. |  | The city supplies no numerical source feature accuracy and expressly disclaims accuracy warranties. Coordinate digits and four-metre transformation-operation accuracy are not measured locator accuracy. | 7270537c-36c5-56e3-8dc2-e01b4e99cc17 | under_construction | 2026-08-19 | 55 | authoritative_physical_status_update | efe9fe73-a0be-549f-93b8-ddf0559817b4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://amandacommerce.auroragov.org/BuildingPlanReviewPub/MyProjects/Inspections.aspx | https://ags.auroragov.org/aurora/rest/services/OpenData/MapServer/9/query?f=json&where=ADDRESS+IN+%28%271160+N+GUN+CLUB+RD%27%2C%271140+N+GUN+CLUB+RD%27%2C%271100+N+GUN+CLUB+RD%27%29&outFields=OBJECTID%2CADDRESS%2CADDRESS_ID%2CPROPERTYRSN&returnGeometry=true&outSR=4326&datumTransformation=1188 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-98db91806e7e60522076/#project-c23fe40c-0685-5cee-8fab-9c08575e6b27 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c23fe40c-0685-5cee-8fab-9c08575e6b27.json
c2ec8d08-3436-5bbc-af4e-4eb553297fe2 | curated:northc-frankfurt-fra01:current-facility-build | vcc-site-ece79fca728f9d94dc00 | curated:northc-frankfurt-fra01 | NorthC Frankfurt1 (FRA01) Current Facility Build | Germany | DE | 50.0996 | 8.581 | Point | campus | direct_geometry | official_municipal_address_point_crs_transform | official_building_address_point | official_source | project_locator | Official municipal building-address point for exact street and house number695. Binds the operator-published project address; does not delineate the new data-centre building, parcel or works boundary. |  | Address source provides no positional accuracy. Transformation operation accuracy of1m is not site-location uncertainty. | 8a94810f-0243-582c-b684-10791ec2a193 | site_preparation | 2026-09-18 | 25 | authoritative_physical_status_update | 7a8a11aa-4979-5f4a-a997-335f0636ad57 | authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed | unknown | not established by selected evidence | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"3ae304e7-a74f-522e-8b9b-df93664fbd17","party":"NorthC Datacenters","relationship_scope":"intended","role":"operator"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation |  | NorthC Datacenters |  |  |  | https://www.linkedin.com/posts/northc-group_preparatory-work-has-started-on-our-fra01-activity-7506698388931821568-UW3t | https://geoportal.frankfurt.de/elastic/basisgis/_search?source_content_type=application%2Fjson&source=%7B%22query%22%3A%7B%22match_phrase%22%3A%7B%22properties.searchField%22%3A%22Mainzer+Landstra%C3%9Fe+695%22%7D%7D%2C%22size%22%3A5%7D | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ece79fca728f9d94dc00/#project-c2ec8d08-3436-5bbc-af4e-4eb553297fe2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c2ec8d08-3436-5bbc-af4e-4eb553297fe2.json
c30aeadf-c2f6-58a5-a8b1-227868f477c1 | curated:bitzero-namsskogan-data-center-campus:2026-power-infrastructure-expansion | vcc-site-2d9846dc358cfee26779 | curated:bitzero-namsskogan-data-center-campus | Bitzero Namsskogan 2026 Power Infrastructure Expansion | Norway | NO | 64.7143 | 12.8341 | Polygon | campus | cross_source_geometry | kartverket_official_cadastral_parcel_polygon_as_campus_locator | official_cadastral_parcel_as_campus_locator | official_source | campus_locator | Exact reviewed Kartverket cadastral polygon for property 5044-50/44, used only to locate the source-linked Bitzero Namsskogan parent campus and inherited by its current power-infrastructure project. It is not a transformer-foundation location, data-hall or building footprint, current-work extent, verified complete campus boundary, security boundary, or survey-accuracy claim. |  | Kartverket supplies only the coarse green parcel-accuracy class here, warns that property maps may be incomplete or imprecise, and does not expose boundary-line quality or a numeric horizontal uncertainty in this response. | 90d3590f-be24-5554-809a-36313784fe51 | foundations | 2026-06-15 | 120 | authoritative_physical_status_update | 3c85c95a-5036-5cf2-b9b8-c15070c6aaea | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.13 geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.newsfilecorp.com/release/301582 | https://api.kartverket.no/eiendom/v1/geokoding?matrikkelnummer=5044-50%2F44&omrade=true&utkoordsys=4258 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2d9846dc358cfee26779/#project-c30aeadf-c2f6-58a5-a8b1-227868f477c1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c30aeadf-c2f6-58a5-a8b1-227868f477c1.json
c400f10b-b4a6-5824-987b-3ff8657fb0d3 | imported:semiconductor-atlas:nightpeak-old-ocean | vcc-site-88d9a98c0d66b0ceae9f | imported:semiconductor-atlas:nightpeak-old-ocean | Old Ocean Data Center (Nightpeak Energy) | United States | US | 29.0797 | -95.7494 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Bisnow, citing county meeting documents, places the 158-acre site outside Sweeny, and the campus is named after Old Ocean, an unincorporated community about 5 miles northwest of Sweeny. The point is Old Ocean's coordinate from its Wikipedia article, not the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f3c72526-743a-54a9-be8a-a843c26bfe76 | proposed | 2026-03-11 | 216 | imported_documented_status | f3c72526-743a-54a9-be8a-a843c26bfe76 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f3c72526-743a-54a9-be8a-a843c26bfe76","notes":"Developer of the data center campus; Public Citizen spells the name Night Peak Energy. Bisnow cites Nightpeak's website for the timelines of both the campus and the co-located Bulldog Power turbine plant but does not state who develops the plant.","party":"Nightpeak Energy","relationship_scope":"unknown","role":"developer","source_record_id":"nightpeak-old-ocean"},{"evidence_id":"23df5ccc-860a-557c-a60c-11a7a4c08fea","notes":"Developer of the data center campus; Public Citizen spells the name Night Peak Energy. Bisnow cites Nightpeak's website for the timelines of both the campus and the co-located Bulldog Power turbine plant but does not state who develops the plant.","party":"Nightpeak Energy","relationship_scope":"unknown","role":"developer","source_record_id":"nightpeak-old-ocean"},{"evidence_id":"f3c72526-743a-54a9-be8a-a843c26bfe76","notes":"Rejected the reinvestment zone and tax abatements in March 2026.","party":"Brazoria County Commissioners Court","relationship_scope":"unknown","role":"government","source_record_id":"nightpeak-old-ocean"},{"evidence_id":"23df5ccc-860a-557c-a60c-11a7a4c08fea","notes":"Rejected the reinvestment zone and tax abatements in March 2026.","party":"Brazoria County Commissioners Court","relationship_scope":"unknown","role":"government","source_record_id":"nightpeak-old-ocean"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.citizen.org/news/public-citizen-applauds-brazoria-county-for-rejecting-tax-break-for-massive-data-center/ | https://www.citizen.org/news/public-citizen-applauds-brazoria-county-for-rejecting-tax-break-for-massive-data-center/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Old Ocean Data Center (Nightpeak Energy) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"nightpeak-old-ocean"},"record":{"aliases":["Old Ocean Datacenter"],"id":"nightpeak-old-ocean","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Brazoria County","country":"US","lat":29.0797,"locality":"Old Ocean (near Sweeny)","lon":-95.7494,"note":"Bisnow, citing county meeting documents, places the 158-acre site outside Sweeny, and the campus is named after Old Ocean, an unincorporated community about 5 miles northwest of Sweeny. The point is Old Ocean's coordinate from its Wikipedia article, not the parcel.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"phase","as_of":"2026-03-11","basis":"planned","metric":"power_capacity","note":"Bisnow, citing county meeting documents, describes two 310 MW data centers; Public Citizen describes a single 310 MW data center. No campus total is recorded.","phase_label":"Each planned hyperscale data center","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":310},{"applies_to":"phase","as_of":"2026-03-11","basis":"planned","metric":"power_capacity","note":"Bisnow, citing county meeting documents, reports two 310 MW turbine plants; Public Citizen describes one 310 MW gas plant built to power the data center. No campus total is recorded.","phase_label":"Each planned combustion turbine plant (Bulldog Power)","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":310},{"applies_to":"campus","as_of":"2026-03-11","basis":"reported","metric":"investment","note":"Bisnow's own headline total for the data centers and power plants together; it is not attributed to a document and matches the per-facility figures Bisnow attributes to county meeting documents. Public Citizen describes only one data center and one plant, so this total is uncertain.","qualifier":"exact","source_ids":["s2"],"unit":"USD","value":3500000000},{"applies_to":"phase","as_of":"2026-03-11","basis":"reported","metric":"investment","note":"From county meeting documents as reported by Bisnow; each turbine plant was put at USD 250 million.","phase_label":"Each planned hyperscale data center","qualifier":"exact","source_ids":["s2"],"unit":"USD","value":1500000000},{"applies_to":"campus","as_of":"2026-03-11","basis":"reported","metric":"land_area","note":"From county meeting documents as reported by Bisnow.","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":158},{"applies_to":"campus","as_of":"2026-03-11","basis":"planned","metric":"jobs_permanent","note":"Reported by Bisnow alongside figures it attributes to meeting documents; several hundred construction jobs were also expected.","qualifier":"approximately","source_ids":["s2"],"unit":"count","value":30}],"milestones":[{"date":"2026-03-10","event":"other","kind":"actual","note":"Brazoria County commissioners unanimously rejected a reinvestment zone for the site and power plant and denied four ten-year, 100% tax abatements, amid concerns about noise, water and power use and the small number of permanent jobs.","source_ids":["s1","s2"]},{"date":"2027","event":"other","kind":"planned","note":"Nightpeak's website, as quoted by Bisnow, said the campus could energize beginning in 2027.","source_ids":["s2"]}],"name":"Old Ocean Data Center (Nightpeak Energy)","notes":"Public Citizen, an advocacy group that opposed the incentives, put the requested tax break at USD 10.5 million. The county judge said he expected the project to proceed regardless of the vote; Bisnow attributes the point that the county has little power to stop it to reporting by The Facts. Nightpeak's own website could not be opened, so its claims are recorded only as relayed by Bisnow. No later 2026 status update was found in an openable source. A smaller data center that recently opened in the nearby city of Brazoria, mentioned at the same meeting, is a different build.","parties":[{"name":"Nightpeak Energy","note":"Developer of the data center campus; Public Citizen spells the name Night Peak Energy. Bisnow cites Nightpeak's website for the timelines of both the campus and the co-located Bulldog Power turbine plant but does not state who develops the plant.","role":"developer","source_ids":["s1","s2"]},{"name":"Brazoria County Commissioners Court","note":"Rejected the reinvestment zone and tax abatements in March 2026.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"Co-located Bulldog Power combustion turbine plant, which Bisnow, citing Nightpeak's website, says has been in development since 2023 and targets operation in 2028 or earlier; sources differ on whether one or two 310 MW plants are planned.","source_ids":["s1","s2"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-03-10","publisher":"Public Citizen","title":"Public Citizen Applauds Brazoria County for Rejecting Tax Break for Massive Data Center","type":"other","url":"https://www.citizen.org/news/public-citizen-applauds-brazoria-county-for-rejecting-tax-break-for-massive-data-center/"},{"accessed":"2026-10-09","id":"s2","published":"2026-03-11","publisher":"Bisnow","title":"Houston-Area County Rejects Tax Break For $3.5B Data Center Project","type":"trade_press","url":"https://www.bisnow.com/houston/news/data-center-development/houston-area-county-rejects-tax-abatement-for-35b-data-center-development-133616"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Wikipedia","title":"Old Ocean, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Old_Ocean,_Texas"}],"status":"proposed","status_as_of":"2026-03-11","status_source_ids":["s1","s2"],"summary":"Nightpeak Energy proposes a hyperscale data center campus with co-located gas turbine generation on a 158-acre site outside Sweeny in Brazoria County, Texas, about 65 miles southwest of Houston. County meeting documents, as reported by Bisnow, describe two 310 MW data centers at USD 1.5 billion each and two 310 MW combustion turbine plants at USD 250 million each, while Public Citizen describes one data center and one gas plant. On 10 March 2026 the commissioners court unanimously rejected a reinvestment zone and four ten-year, 100% tax abatements; the county judge expected the project to proceed anyway. Nightpeak's website, as quoted by Bisnow, said the campus could energize from 2027.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f3c72526-743a-54a9-be8a-a843c26bfe76","s2":"23df5ccc-860a-557c-a60c-11a7a4c08fea","s3":"918925da-38a8-5836-839a-88e01174b802"},"source_file":"datacenters/projects/nightpeak-old-ocean.json","source_record_id":"nightpeak-old-ocean","source_record_sha256":"5878487ce27a64c97206ce1a137a67a4ba60cd6bf2884d1aa54a1f4fe3d80f15","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"aae418f9117b06832c493a7904a452ee9123ad2a0c3e4b8234ec8e08733b7a8a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88d9a98c0d66b0ceae9f/#project-c400f10b-b4a6-5824-987b-3ff8657fb0d3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c400f10b-b4a6-5824-987b-3ff8657fb0d3.json
c42e542c-bee8-54bc-9f79-9f03d98979ea | imported:semiconductor-atlas:aws-king-george-county-virginia | vcc-site-9c23979ae731456903ea | imported:semiconductor-atlas:aws-king-george-county-virginia | Amazon Web Services King George County campus (Birchwood site) | United States | US | 38.2614 | -77.3319 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Sealston community coordinates from its Wikipedia page. Sources place the campus at the former Birchwood power plant on State Route 3 in the Sealston area but give no parcel coordinates. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 77cb3c3a-e777-5b92-80e3-e42a09b8002f | proposed | 2026-10-09 | 4 | imported_documented_status | 6d65f7f2-40a4-54a9-b179-63df6f9eef5e | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3f4ffb24-1067-5a97-9faa-e98a13a966c8","notes":"Named as Amazon Data Center Services by its rezoning counsel and as Amazon Web Services (AWS) in local press.","party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"4ee8c224-d4f2-518c-9bc8-43de4e913323","notes":"Named as Amazon Data Center Services by its rezoning counsel and as Amazon Web Services (AWS) in local press.","party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"4ee8c224-d4f2-518c-9bc8-43de4e913323","notes":"Bought nine parcels for USD 168.8 million in December 2023, per Baxtel; a county supervisor said AWS owns the land.","party":"Amazon Web Services","relationship_scope":"unknown","role":"owner","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"6d65f7f2-40a4-54a9-b179-63df6f9eef5e","notes":"Bought nine parcels for USD 168.8 million in December 2023, per Baxtel; a county supervisor said AWS owns the land.","party":"Amazon Web Services","relationship_scope":"unknown","role":"owner","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"77cb3c3a-e777-5b92-80e3-e42a09b8002f","notes":"Subsidiary of J-Power that first proposed the campus at the former power plant site in July 2023.","party":"Birchwood Power Partners","relationship_scope":"unknown","role":"developer","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"6cbef912-e76f-5fae-8331-76b91b575a48","notes":"Subsidiary of J-Power that first proposed the campus at the former power plant site in July 2023.","party":"Birchwood Power Partners","relationship_scope":"unknown","role":"developer","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"6cbef912-e76f-5fae-8331-76b91b575a48","notes":"Approved the rezoning and a December 2023 performance agreement; a reconstituted board voted in January 2024 to renegotiate it.","party":"King George County Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"4ee8c224-d4f2-518c-9bc8-43de4e913323","notes":"Approved the rezoning and a December 2023 performance agreement; a reconstituted board voted in January 2024 to renegotiate it.","party":"King George County Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"aws-king-george-county-virginia"},{"evidence_id":"4ee8c224-d4f2-518c-9bc8-43de4e913323","notes":"Said new substations and transmission lines would be needed but it was not proposing power plants in the county.","party":"Dominion Energy","relationship_scope":"unknown","role":"utility","source_record_id":"aws-king-george-county-virginia"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Amazon Web Services |  |  |  |  | https://baxtel.com/data-center/amazon-king-george-va | https://www.bisnow.com/news/national/data-center/amazon-data-center-campus-planned-for-king-george-county-va-as-project-clears-key-hurdle-120212 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Amazon Web Services King George County campus (Birchwood site) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"aws-king-george-county-virginia"},"record":{"aliases":["Birchwood data center campus","Amazon Birchwood"],"id":"aws-king-george-county-virginia","last_reviewed":"2026-10-09","location":{"admin1":"Virginia","admin2":"King George County","country":"US","lat":38.2614,"locality":"Sealston","lon":-77.3319,"note":"Coordinates are the Sealston community coordinates from its Wikipedia page. Sources place the campus at the former Birchwood power plant on State Route 3 in the Sealston area but give no parcel coordinates.","precision":"locality","source_ids":["s1","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2024-01-08","basis":"reported","metric":"investment","note":"Proposed investment reported when the county approved tax incentives in December 2023 and in later local coverage; the sources do not describe it as a commitment in the performance agreement.","qualifier":"approximately","source_ids":["s3","s4","s5"],"unit":"USD","value":6000000000},{"applies_to":"campus","as_of":"2024-01-08","basis":"reported","metric":"land_area","note":"Site area; the rezoning counsel gives about 870 acres.","qualifier":"approximately","source_ids":["s1","s2","s3","s4","s5"],"unit":"acres","value":869},{"applies_to":"campus","as_of":"2024-01-08","basis":"planned","metric":"floor_area","note":"Full build-out over about 15 years.","qualifier":"up_to","source_ids":["s1","s3","s5"],"unit":"sq_ft","value":7500000},{"applies_to":"campus","as_of":"2024-03-23","basis":"planned","metric":"floor_area","note":"Figure given by the rezoning counsel and local press.","qualifier":"exact","source_ids":["s2","s4"],"unit":"sq_ft","value":7250000},{"applies_to":"phase","as_of":"2024-01-08","basis":"planned","metric":"floor_area","phase_label":"Phase 1","qualifier":"approximately","source_ids":["s1","s3"],"unit":"sq_ft","value":4000000},{"applies_to":"phase","as_of":"2024-01-08","basis":"planned","metric":"buildings","note":"Data center buildings, plus two electrical substations.","phase_label":"Phase 1","qualifier":"up_to","source_ids":["s1","s3"],"unit":"count","value":8},{"applies_to":"phase","as_of":"2023-08-14","basis":"planned","metric":"buildings","note":"Later phases on neighbouring parcels, adding about 3.5 million sq ft.","phase_label":"Later phases","qualifier":"exact","source_ids":["s1","s5"],"unit":"count","value":9}],"milestones":[{"date":"2023-07","event":"announced","kind":"actual","note":"Birchwood Power Partners proposed the campus; Amazon was identified as the intended user soon after.","source_ids":["s1","s3"]},{"date":"2023-09","event":"zoning_approved","kind":"actual","source_ids":["s2","s3"]},{"date":"2023-12-19","event":"other","kind":"actual","note":"The outgoing Board of Supervisors approved a performance agreement with tax incentives for the campus.","source_ids":["s3","s4"]},{"date":"2023-12","event":"site_acquired","kind":"actual","note":"Amazon bought nine parcels for USD 168.8 million, per Baxtel.","source_ids":["s5"]},{"date":"2024-01","event":"other","kind":"actual","note":"A reconstituted board voted on 2 January to renegotiate the performance agreement; a letter from Amazon's lawyer argued the vote did not affect the agreement's enforceability.","source_ids":["s3","s4"]},{"date":"2025-04","event":"other","kind":"actual","note":"Amazon filed a court petition seeking a vested rights review; the county Board of Zoning Appeals denied its request in mid-2025 and the case was pending in circuit court as of March 2026, per Baxtel.","source_ids":["s5"]}],"name":"Amazon Web Services King George County campus (Birchwood site)","notes":"Status comes from Baxtel's undated third-party listing (accessed 2026-10-09), which labels the project in doubt; its latest entry, for March 2026, says the case was pending in King George County Circuit Court with no ruling. No later ruling was found. Total floor area is reported as 7.5 million sq ft by Bisnow and Baxtel and 7.25 million sq ft by the rezoning counsel and local press. Baxtel gives a total of 19 buildings, which does not match its own phase breakdown of eight plus nine, so no campus building total is recorded. The site was the 258 MW Birchwood coal plant, decommissioned in 2021.","parties":[{"name":"Amazon Web Services","note":"Named as Amazon Data Center Services by its rezoning counsel and as Amazon Web Services (AWS) in local press.","role":"developer","source_ids":["s2","s4"]},{"name":"Amazon Web Services","note":"Bought nine parcels for USD 168.8 million in December 2023, per Baxtel; a county supervisor said AWS owns the land.","role":"owner","source_ids":["s4","s5"]},{"name":"Birchwood Power Partners","note":"Subsidiary of J-Power that first proposed the campus at the former power plant site in July 2023.","role":"developer","source_ids":["s1","s3"]},{"name":"King George County Board of Supervisors","note":"Approved the rezoning and a December 2023 performance agreement; a reconstituted board voted in January 2024 to renegotiate it.","role":"government","source_ids":["s3","s4"]},{"name":"Dominion Energy","note":"Said new substations and transmission lines would be needed but it was not proposing power plants in the county.","role":"utility","source_ids":["s4"]}],"power_sources":[{"description":"Dominion Energy said new substations and transmission lines would be needed to support data center growth in the county and that it was not proposing power plants there; the first phase plans include two on-site electrical substations.","source_ids":["s3","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2023-08-14","publisher":"Bisnow","title":"Amazon Data Center Campus Planned For King George County, Virginia, As Project Clears Key Hurdle","type":"trade_press","url":"https://www.bisnow.com/news/national/data-center/amazon-data-center-campus-planned-for-king-george-county-va-as-project-clears-key-hurdle-120212"},{"accessed":"2026-10-09","id":"s2","published":"2023-09","publisher":"Hirschler","title":"Hirschler Secures Historic Rezoning for Massive Data Center Campus in King George County, Virginia","type":"other","url":"https://www.hirschlerlaw.com/newsroom-news-historic-rezoning-massive-data-center-king-george-county"},{"accessed":"2026-10-09","id":"s3","published":"2024-01-08","publisher":"Bisnow","title":"Amazon Dealt Setback In Plan For $6B Virginia Data Center Campus","type":"trade_press","url":"https://www.bisnow.com/news/national/data-center/virginia-county-backtracks-on-agreement-with-amazon-for-6b-data-center-campus-122327"},{"accessed":"2026-10-09","id":"s4","published":"2024-03-23","publisher":"Fredericksburg Free Press","title":"King George supervisors ready to 'go to war' with Amazon","type":"news","url":"https://www.fredericksburgfreepress.com/?p=107200"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Baxtel","title":"Amazon: King George, VA Data Center","type":"other","url":"https://baxtel.com/data-center/amazon-king-george-va"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Sealston, Virginia","type":"other","url":"https://en.wikipedia.org/wiki/Sealston,_Virginia"}],"status":"proposed","status_as_of":"2026-10-09","status_source_ids":["s5"],"summary":"Proposed Amazon Web Services data center campus on about 869 acres at the former Birchwood coal power plant on State Route 3 in the Sealston area of King George County, Virginia. Rezoned in September 2023, it is planned at 7.25 to 7.5 million sq ft, with a first phase of up to eight buildings and about 4 million sq ft and nine more buildings in later phases, and is reported as a USD 6 billion project. The county approved tax incentives in December 2023, but a new board voted in January 2024 to renegotiate them; Amazon sought a vested rights review in 2025, and as of March 2026 the case was pending in circuit court with no construction reported.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"77cb3c3a-e777-5b92-80e3-e42a09b8002f","s2":"3f4ffb24-1067-5a97-9faa-e98a13a966c8","s3":"6cbef912-e76f-5fae-8331-76b91b575a48","s4":"4ee8c224-d4f2-518c-9bc8-43de4e913323","s5":"6d65f7f2-40a4-54a9-b179-63df6f9eef5e","s6":"d91f9bc4-4a22-5b1c-8d11-b65b5f4ae27c"},"source_file":"datacenters/projects/aws-king-george-county-virginia.json","source_record_id":"aws-king-george-county-virginia","source_record_sha256":"62591200ca59b25c6df7e986d69c90c48de9b225a81de81358247c804fc75884","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"46efdd86f1bee352e35c0512fed5126aa422d0e62080316c1b1b464761c54c0c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9c23979ae731456903ea/#project-c42e542c-bee8-54bc-9f79-9f03d98979ea | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c42e542c-bee8-54bc-9f79-9f03d98979ea.json
c4cf35bd-5452-551f-8b1c-bb88d2f2b35b | imported:semiconductor-atlas:softbank-tomakomai | vcc-site-6fc591eaf0edc175a75c | imported:semiconductor-atlas:softbank-tomakomai | SoftBank Hokkaido Tomakomai AI Data Center | Japan | JP | 42.6341 | 141.6055 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Tomakomai City only; coordinates are the OpenStreetMap Nominatim centroid of the city boundary. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | d00b5a09-e567-5c82-9aaf-df71b5f87d92 | under_construction | 2026-08-04 | 70 | authoritative_physical_status_update | 5d3d9ccb-c460-5418-9031-8dd22aecca92 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d00b5a09-e567-5c82-9aaf-df71b5f87d92","notes":null,"party":"SoftBank Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-tomakomai"},{"evidence_id":"632852c2-37ac-5865-a1e0-f1dc8194b01b","notes":null,"party":"SoftBank Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-tomakomai"},{"evidence_id":"fc76f541-11a1-591d-81c9-ab51f1a96bd1","notes":null,"party":"SoftBank Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-tomakomai"},{"evidence_id":"f563155b-3553-53d5-9133-c6523341f108","notes":null,"party":"SoftBank Corp.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-tomakomai"},{"evidence_id":"d00b5a09-e567-5c82-9aaf-df71b5f87d92","notes":"SoftBank subsidiary; co-selected with SoftBank as development operator under the subsidy program and named as co-builder at groundbreaking.","party":"IDC Frontier Inc.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-tomakomai"},{"evidence_id":"632852c2-37ac-5865-a1e0-f1dc8194b01b","notes":"SoftBank subsidiary; co-selected with SoftBank as development operator under the subsidy program and named as co-builder at groundbreaking.","party":"IDC Frontier Inc.","relationship_scope":"unknown","role":"developer","source_record_id":"softbank-tomakomai"},{"evidence_id":"aff59ec7-86fe-5451-8100-89ec85a970d5","notes":"Provides a subsidy under its FY2023 regional data center program; trade press reported a maximum of 30 billion yen, about half the project cost.","party":"Ministry of Economy, Trade and Industry (Japan)","relationship_scope":"unknown","role":"government","source_record_id":"softbank-tomakomai"},{"evidence_id":"7a38daa4-627c-57b8-8305-b0d22ccb8a8f","notes":"Provides a subsidy under its FY2023 regional data center program; trade press reported a maximum of 30 billion yen, about half the project cost.","party":"Ministry of Economy, Trade and Industry (Japan)","relationship_scope":"unknown","role":"government","source_record_id":"softbank-tomakomai"},{"evidence_id":"fc76f541-11a1-591d-81c9-ab51f1a96bd1","notes":"Provides a subsidy under its FY2023 regional data center program; trade press reported a maximum of 30 billion yen, about half the project cost.","party":"Ministry of Economy, Trade and Industry (Japan)","relationship_scope":"unknown","role":"government","source_record_id":"softbank-tomakomai"},{"evidence_id":"d00b5a09-e567-5c82-9aaf-df71b5f87d92","notes":null,"party":"SB Power Corp.","relationship_scope":"unknown","role":"power_supplier","source_record_id":"softbank-tomakomai"},{"evidence_id":"d00b5a09-e567-5c82-9aaf-df71b5f87d92","notes":null,"party":"Hokkaido Electric Power Company","relationship_scope":"unknown","role":"power_supplier","source_record_id":"softbank-tomakomai"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.softbank.jp/sbnews/entry/20260804_02 | https://www.softbank.jp/corp/news/press/sbkk/2023/20231107_01/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve SoftBank Hokkaido Tomakomai AI Data Center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"softbank-tomakomai"},"record":{"aliases":["Core Brain","Hokkaido Tomakomai Data Center"],"id":"softbank-tomakomai","last_reviewed":"2026-10-09","location":{"admin1":"Hokkaido","country":"JP","lat":42.6341,"locality":"Tomakomai","lon":141.6055,"note":"Sources name Tomakomai City only; coordinates are the OpenStreetMap Nominatim centroid of the city boundary.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"phase","as_of":"2023-11-07","basis":"planned","metric":"power_capacity","note":"SoftBank describes the first stage as a data center of about 50 MW scale, without saying whether this is receiving capacity or IT load.","phase_label":"Initial phase targeted for FY2026","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":50},{"applies_to":"phase","as_of":"2025-04-30","basis":"planned","metric":"power_capacity","note":"Trade press figure at groundbreaking; scope not stated.","phase_label":"Phase 1 (completion scheduled 2026)","power_scope":"unspecified","qualifier":"exact","source_ids":["s5"],"unit":"MW","value":50},{"applies_to":"phase","as_of":"2023-11-07","basis":"planned","metric":"power_capacity","note":"Dempa reported 10 MW of total initial receiving power; SoftBank's own release describes the first stage as a 50 MW-scale data center, and the reason for the difference was not found.","phase_label":"Initial receiving capacity (trade press)","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":10},{"applies_to":"campus","as_of":"2023-11-07","basis":"planned","metric":"power_capacity","note":"Projected future receiving capacity; SoftBank's 2025 groundbreaking article repeats a capacity expected to exceed 300 MW.","power_scope":"grid_connection","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2023-11-07","basis":"reported","metric":"investment","note":"Total project cost reported by trade press at the subsidy announcement; the government subsidy covers about half.","qualifier":"more_than","source_ids":["s2"],"unit":"JPY","value":65000000000},{"applies_to":"campus","as_of":"2025-04-30","basis":"reported","metric":"investment","qualifier":"approximately","source_ids":["s5"],"unit":"JPY","value":65000000000},{"applies_to":"campus","as_of":"2025-05-01","basis":"planned","metric":"land_area","note":"Reported as about 700,000 square meters at full build-out.","qualifier":"approximately","source_ids":["s1","s3","s4"],"unit":"hectares","value":70}],"milestones":[{"date":"2023-11-07","event":"announced","kind":"actual","note":"Plan announced as SoftBank and IDC Frontier were selected for the government subsidy.","source_ids":["s1","s2"]},{"date":"2025-04-15","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony.","source_ids":["s4","s5"]},{"date":"2027-03","event":"first_operational","kind":"planned","note":"SoftBank targets opening in fiscal 2026, which ends in March 2027; the date shown is the end of that window.","source_ids":["s1","s4","s6"]}],"name":"SoftBank Hokkaido Tomakomai AI Data Center","parties":[{"name":"SoftBank Corp.","role":"developer","source_ids":["s1","s4","s6","s7"]},{"name":"IDC Frontier Inc.","note":"SoftBank subsidiary; co-selected with SoftBank as development operator under the subsidy program and named as co-builder at groundbreaking.","role":"developer","source_ids":["s1","s4"]},{"name":"Ministry of Economy, Trade and Industry (Japan)","note":"Provides a subsidy under its FY2023 regional data center program; trade press reported a maximum of 30 billion yen, about half the project cost.","role":"government","source_ids":["s2","s5","s6"]},{"name":"SB Power Corp.","role":"power_supplier","source_ids":["s1"]},{"name":"Hokkaido Electric Power Company","role":"power_supplier","source_ids":["s1"]}],"power_sources":[{"description":"Electricity to be supplied through SoftBank's retail subsidiary SB Power and Hokkaido Electric Power.","source_ids":["s1"],"type":"grid"},{"description":"SoftBank plans to run the facility on 100% renewable electricity procured within Hokkaido.","source_ids":["s1","s3","s4"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260926175912/https://www.softbank.jp/corp/news/press/sbkk/2023/20231107_01/","id":"s1","published":"2023-11-07","publisher":"SoftBank Corp.","title":"次世代社会インフラ構想の要となる大規模な計算基盤を備えたデータセンター「Core Brain」を構築","type":"company","url":"https://www.softbank.jp/corp/news/press/sbkk/2023/20231107_01/"},{"accessed":"2026-10-09","id":"s2","published":"2023-11-07","publisher":"Dempa Digital (Dempa Shimbun)","title":"経産省、北海道苫小牧市のデータセンターに300億円補助 ソフトバンクが建設予定","type":"trade_press","url":"https://dempa-digital.com/?p=492112"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260922002656/https://www.softbank.jp/business/service/platform/datacenter/tomakomai","id":"s3","published":null,"publisher":"SoftBank Corp.","title":"北海道苫小牧データセンター","type":"company","url":"https://www.softbank.jp/business/service/platform/datacenter/tomakomai"},{"accessed":"2026-10-09","id":"s4","published":"2025-05-01","publisher":"SoftBank Corp. (SoftBank News)","title":"Laying the Foundation for the AI Era: Construction Begins on \"Hokkaido Tomakomai AI Data Center\"","type":"company","url":"https://www.softbank.jp/en/sbnews/entry/20250501_01"},{"accessed":"2026-10-09","id":"s5","published":"2025-04-30","publisher":"W.Media","title":"SoftBank breaks ground for AI data center in Hokkaido","type":"trade_press","url":"https://w.media/softbank-breaks-ground-for-ai-data-center-in-hokkaido/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260806004530/https://www.softbank.jp/en/sbnews/entry/20260225_01","id":"s6","published":"2026-02-25","publisher":"SoftBank Corp. (SoftBank News)","title":"Building for the AI Era: An Inside Look at SoftBank Corp.'s Next-generation AI Data Center in Hokkaido","type":"company","url":"https://www.softbank.jp/en/sbnews/entry/20260225_01"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260922125049/https://www.softbank.jp/en/sbnews/entry/20260623_01","id":"s7","published":"2026-06-23","publisher":"SoftBank Corp. (SoftBank News)","title":"SoftBank Corp.'s 40th Annual General Meeting of Shareholders: Building on Telecommunications Foundation to Unlock Potential of AI","type":"company","url":"https://www.softbank.jp/en/sbnews/entry/20260623_01"}],"status":"under_construction","status_as_of":"2026-06-23","status_source_ids":["s6","s7"],"summary":"SoftBank Corp. and its subsidiary IDC Frontier are building a large AI data center in Tomakomai, Hokkaido, as the core site of SoftBank's Brain DataCenter concept. The plan, selected for a Japanese government regional data center subsidy in 2023, starts with a data center of about 50 MW, with receiving capacity expected to grow past 300 MW on a site of about 700,000 square meters. Ground was broken in April 2025 and SoftBank targets opening in fiscal 2026. The company intends to run the facility on renewable electricity sourced within Hokkaido.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d00b5a09-e567-5c82-9aaf-df71b5f87d92","s2":"aff59ec7-86fe-5451-8100-89ec85a970d5","s3":"fc90dcfc-dc18-57e1-9ace-fbee124696aa","s4":"632852c2-37ac-5865-a1e0-f1dc8194b01b","s5":"7a38daa4-627c-57b8-8305-b0d22ccb8a8f","s6":"fc76f541-11a1-591d-81c9-ab51f1a96bd1","s7":"f563155b-3553-53d5-9133-c6523341f108"},"source_file":"datacenters/projects/softbank-tomakomai.json","source_record_id":"softbank-tomakomai","source_record_sha256":"5ac7faf40fa30f74785a70cbb690430ecb00e38dc1ebc8e64e0c190bcd91bc0d","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"87f8282937aee10c7fce6886f9f2f9a117b38090f43f09ef236bae73fa629846"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6fc591eaf0edc175a75c/#project-c4cf35bd-5452-551f-8b1c-bb88d2f2b35b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c4cf35bd-5452-551f-8b1c-bb88d2f2b35b.json
c4ffa53e-bb43-5af1-9e07-aa5045ea480b | curated:microsoft-etobicoke-ontario-campus:first-building | vcc-site-12d6215837c6451ab8a3 | curated:microsoft-etobicoke-ontario-campus | Microsoft Etobicoke First Building Current Build | Canada | CA | 43.7087 | -79.5482 | Point | project | official_municipal_land_address_point | exact_city_address_point_id_30029368_preserved_without_atlas_centroiding | official_project_address_land_locator | official_source | project_locator | City OAR Land address point for exact 48 Lowe's Place, independently bound to Microsoft ownership and the Etobicoke datacentre. Not the new building footprint, full campus boundary, entrance, active-work extent or a surveyed building-centre claim. |  | No numeric positional accuracy published for the selected municipal address point. | c5cf08ec-c05c-54ab-86b1-f9ba72b1e068 | under_construction | 2026-08-05 | 69 | authoritative_physical_status_update | e1b4ef61-0f27-5a02-9786-de0bb85acf79 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://local.microsoft.com/blog/etobicoke-construction-update/ | https://ckan0.cf.opendata.inter.prod-toronto.ca/api/3/action/datastore_search?resource_id=0b3756af-9caf-4f0f-ac28-9c6617adede4&filters=%7B%22LINEAR_NAME_FULL%22:%22Lowe%27s%20Pl%22%7D&limit=100 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-12d6215837c6451ab8a3/#project-c4ffa53e-bb43-5af1-9e07-aa5045ea480b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c4ffa53e-bb43-5af1-9e07-aa5045ea480b.json
c52dcc98-dfd2-5012-8703-5d9e24de51b2 | imported:semiconductor-atlas:sify-rabale-navi-mumbai | vcc-site-2088ce1cae4288c3f3a1 | imported:semiconductor-atlas:sify-rabale-navi-mumbai | Sify Rabale data center campus (Mumbai 03), Navi Mumbai | India | IN | 19.1442 | 73.0086 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sify gives the address as Plot R-847, TTC Industrial Area, Rabale, Navi Mumbai, and the prospectus places towers 11 and 12 on Plot R-978 in the same industrial area. The point is the Rabale coordinate from its Wikipedia article (which also gives Thane district), so it marks the neighbourhood rather than the plots. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3ca04bf3-2438-554c-8f7a-ac8c8167e22c | partially_operational | 2026-10-09 | 4 | imported_documented_status | 3ca04bf3-2438-554c-8f7a-ac8c8167e22c | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ebdd68d0-d340-59ab-bcf5-f7d24aae8ac6","notes":"Data center subsidiary of Sify Technologies, which is one of its promoters.","party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"developer","source_record_id":"sify-rabale-navi-mumbai"},{"evidence_id":"3ca04bf3-2438-554c-8f7a-ac8c8167e22c","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"operator","source_record_id":"sify-rabale-navi-mumbai"},{"evidence_id":"ebdd68d0-d340-59ab-bcf5-f7d24aae8ac6","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"operator","source_record_id":"sify-rabale-navi-mumbai"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Sify Infinit Spaces Limited |  |  |  | https://www.sifytechnologies.com/data-center/mumbai-data-center/ | https://www.sifytechnologies.com/data-center/mumbai-data-center/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Sify Rabale data center campus (Mumbai 03), Navi Mumbai as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"sify-rabale-navi-mumbai"},"record":{"aliases":["Rabale Data Center campus","Mumbai 03","MUM03"],"id":"sify-rabale-navi-mumbai","last_reviewed":"2026-10-09","location":{"admin1":"Maharashtra","admin2":"Thane district","country":"IN","lat":19.14417,"locality":"Rabale, Navi Mumbai (TTC Industrial Area)","lon":73.00861,"note":"Sify gives the address as Plot R-847, TTC Industrial Area, Rabale, Navi Mumbai, and the prospectus places towers 11 and 12 on Plot R-978 in the same industrial area. The point is the Rabale coordinate from its Wikipedia article (which also gives Thane district), so it marks the neighbourhood rather than the plots.","precision":"locality","source_ids":["s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Design capacity across 12 towers from Sify's undated website, read on the access date.","power_scope":"it_load","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":377},{"applies_to":"phase","as_of":"2026-10-09","basis":"operational","metric":"power_capacity","note":"Sify's undated campus page, read on the access date, gives 96.94 MW of IT power with five of 12 towers fully operational. The prospectus gives the same figure as the built capacity of towers 1-5 at 30 June 2025, when Tower 5 had only 30.24 MW of its 43.2 MW installed, so commissioned capacity at that date was lower.","phase_label":"Towers 1-5","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":96.94},{"applies_to":"phase","as_of":"2025-06-30","basis":"planned","metric":"power_capacity","note":"Sify's campus page says Tower 5 is designed for 43.2 MW of IT power; the prospectus gives the same figure as its built capacity. The prospectus defines built capacity as the maximum IT load a facility is engineered to support on its present design, and installed capacity as the part that is equipped, powered and commissioned.","phase_label":"Tower 5 (design / built capacity)","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":43.2},{"applies_to":"phase","as_of":"2025-06-30","basis":"operational","metric":"power_capacity","note":"Installed IT capacity of Tower 5 at 30 June 2025, up from 6.48 MW at 31 March 2024.","phase_label":"Tower 5 (installed capacity)","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":30.24},{"applies_to":"phase","as_of":"2025-10-16","basis":"under_construction","metric":"power_capacity","note":"19.44 MW in each tower, with operations targeted by the financial year ending March 2028.","phase_label":"Towers 11 and 12","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":38.88},{"applies_to":"phase","as_of":"2025-10-16","basis":"announced","metric":"investment","note":"Estimated cost of towers 11 and 12 excluding land, certified by an independent chartered engineer; INR 8.6 billion was to come from IPO proceeds and the rest from borrowing.","phase_label":"Towers 11 and 12","qualifier":"exact","source_ids":["s3"],"unit":"INR","value":11276930000},{"applies_to":"campus","as_of":"2025-10-16","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"count","value":12},{"applies_to":"campus","as_of":"2025-06-30","basis":"operational","metric":"buildings","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":5}],"milestones":[{"date":"2025-10-16","event":"other","kind":"actual","note":"Prospectus reports towers 11 and 12 under construction, to be part-funded by the planned IPO of Sify Infinit Spaces.","source_ids":["s3"]},{"date":"2026","event":"other","kind":"planned","note":"Sify's campus page says towers 6, 7, 11 and 12 are slated to be operational by 2026; the October 2025 prospectus targets towers 11 and 12 for the year ending March 2028.","source_ids":["s2"]}],"name":"Sify Rabale data center campus (Mumbai 03), Navi Mumbai","notes":"The partially operational status and the 2026 tower schedule come from Sify's undated campus page (s2), read on 2026-10-09; it says towers 6, 7, 11 and 12 are slated for 2026 and towers 8 to 10 are in planning, while the October 2025 prospectus targets towers 11 and 12 for the year ending March 2028. The prospectus shows no Tower 5 capacity in the year to March 2023 and 43.2 MW built by March 2024. Towers 11 and 12 stand on Plot R-978, sub-leased from Gargantuan Industrial Space Solutions, which is to deliver the buildings built-to-suit. Rabale coordinates and the district come from Wikipedia (s4), used only for the location.","parties":[{"name":"Sify Infinit Spaces Limited","note":"Data center subsidiary of Sify Technologies, which is one of its promoters.","role":"developer","source_ids":["s3"]},{"name":"Sify Infinit Spaces Limited","role":"operator","source_ids":["s2","s3"]}],"power_sources":[{"description":"Towers 1 to 3 are served by an on-site 110 kV substation and the later towers by an on-site 220 kV GIS substation (towers 4 and 5 in the prospectus, towers 4 to 6 on Sify's campus page).","source_ids":["s2","s3"],"type":"grid"},{"description":"Renewable power from solar and wind, bought through power purchase agreements, covers up to 70% of campus operations; Sify's campus page cites 99 MW of green power.","source_ids":["s2","s3"],"type":"solar"},{"description":"Wind generation is part of the renewable supply bought through power purchase agreements.","source_ids":["s2","s3"],"type":"wind"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Sify Technologies","title":"Data centre","type":"company","url":"https://www.sifytechnologies.com/europe/data-centre/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Sify Technologies","title":"Mumbai data center","type":"company","url":"https://www.sifytechnologies.com/data-center/mumbai-data-center/"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-16","publisher":"Sify Infinit Spaces Limited (filed with SEBI; hosted by National Stock Exchange of India)","title":"Sify Infinit Spaces Limited: Draft Red Herring Prospectus (filing version)","type":"regulatory_filing","url":"https://nsearchives.nseindia.com/corporate/Registration_17102025141743_DRHP_Fillingversion.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260720155305/https://en.wikipedia.org/wiki/Rabale","id":"s4","published":null,"publisher":"Wikipedia","title":"Rabale","type":"other","url":"https://en.wikipedia.org/wiki/Rabale"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s2","s3"],"summary":"Sify Infinit Spaces' Rabale campus in the TTC Industrial Area, Navi Mumbai, one of its largest, is designed for 12 towers, of which five are operating. Sify's campus page gives 96.94 MW of IT power for them, the figure its October 2025 prospectus reports as built capacity at mid-2025. The hyperscale and AI-ready Tower 5, designed for 43.2 MW, came into service in the 2023-24 financial year and had 30.24 MW installed by June 2025. Sify's website gives more than 377 MW of IT power for the full campus. Towers 11 and 12 (38.88 MW together) were under construction in October 2025 at an estimated INR 11.3 billion, targeted for the year to March 2028.","workloads":["colocation","cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"62607d81-7c58-586f-ad65-8ed10982e797","s2":"3ca04bf3-2438-554c-8f7a-ac8c8167e22c","s3":"ebdd68d0-d340-59ab-bcf5-f7d24aae8ac6","s4":"f7516d2b-28aa-5a58-b8d9-0861ee4a7b9c"},"source_file":"datacenters/projects/sify-rabale-navi-mumbai.json","source_record_id":"sify-rabale-navi-mumbai","source_record_sha256":"f90080b82ee86a1325331b42b98916e8af2adb26691fc1b4b755ddf2a1092cd7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"6347e247ca845b8953b09fc8ece3ee8b9f14d8b7b04671491f40153486848a0f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2088ce1cae4288c3f3a1/#project-c52dcc98-dfd2-5012-8703-5d9e24de51b2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c52dcc98-dfd2-5012-8703-5d9e24de51b2.json
c53b72b6-ff87-58eb-b74f-7082b159a513 | imported:semiconductor-atlas:data4-hanau | vcc-site-4a5d5083c6a8b110c612 | imported:semiconductor-atlas:data4-hanau | Data4 Hanau campus | Germany | DE | 50.1 | 8.95 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Centroid of the Großauheim district of Hanau from its Wikipedia article. Data4 places the campus on the former Großauheim military base but no cited source gives coordinates for the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ce89216d-e227-5e79-944a-25d62f4fc66c | under_construction | 2026-03-11 | 216 | imported_documented_status | c69188d3-f2b9-5b58-81a5-c09f32c31249 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ce89216d-e227-5e79-944a-25d62f4fc66c","notes":null,"party":"Data4","relationship_scope":"unknown","role":"developer","source_record_id":"data4-hanau"},{"evidence_id":"2e09b450-ac25-5670-a9cf-3a4e0a434bc5","notes":null,"party":"Data4","relationship_scope":"unknown","role":"developer","source_record_id":"data4-hanau"},{"evidence_id":"ce89216d-e227-5e79-944a-25d62f4fc66c","notes":"Data4 says it finances, designs, builds and operates its own data centers.","party":"Data4","relationship_scope":"unknown","role":"operator","source_record_id":"data4-hanau"},{"evidence_id":"ce89216d-e227-5e79-944a-25d62f4fc66c","notes":"Acquired the site.","party":"Data4","relationship_scope":"unknown","role":"owner","source_record_id":"data4-hanau"},{"evidence_id":"2e09b450-ac25-5670-a9cf-3a4e0a434bc5","notes":"Owner of Data4, per trade press.","party":"Brookfield","relationship_scope":"unknown","role":"investor","source_record_id":"data4-hanau"},{"evidence_id":"c69188d3-f2b9-5b58-81a5-c09f32c31249","notes":"Owner of Data4, per trade press.","party":"Brookfield","relationship_scope":"unknown","role":"investor","source_record_id":"data4-hanau"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Data4 | Data4 |  |  |  | https://capacityglobal.com/news/data4-hanau-data-centre-germany-data-centre-of-the-month/ | https://www.data4group.com/wp-content/uploads/2025/09/FINAL_ENG_Press-Release-_Data4_Event_Hanau-1.pdf | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Data4 Hanau campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"data4-hanau"},"record":{"aliases":["Data4 Großauheim campus"],"id":"data4-hanau","last_reviewed":"2026-10-09","location":{"admin1":"Hesse","admin2":"Main-Kinzig-Kreis","country":"DE","lat":50.1,"locality":"Hanau (Großauheim)","lon":8.95,"note":"Centroid of the Großauheim district of Hanau from its Wikipedia article. Data4 places the campus on the former Großauheim military base but no cited source gives coordinates for the site.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-09-15","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":180},{"applies_to":"campus","as_of":"2025-09-15","basis":"announced","metric":"investment","note":"Data4's release headline calls this the campus investment, doubled from EUR 1 billion to EUR 2 billion; the body says planned investment for its German location rose to over EUR 2 billion. Trade press gives EUR 2 billion (Capacity) or up to EUR 2 billion (DCD via BeBeez).","qualifier":"more_than","source_ids":["s1"],"unit":"EUR","value":2000000000},{"applies_to":"campus","as_of":"2025-09-15","basis":"acquired","metric":"land_area","note":"Data4's own figure. Trade press reports 25 acres instead.","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":25},{"applies_to":"campus","as_of":"2026-03-11","basis":"reported","metric":"land_area","note":"Trade press figure, which conflicts with Data4's 25 hectares.","qualifier":"exact","source_ids":["s2","s3"],"unit":"acres","value":25}],"milestones":[{"date":"2023","event":"site_acquired","kind":"actual","note":"Trade press gives 2023; Data4's September 2025 release says it bought the site 18 months earlier, which would point to early 2024.","source_ids":["s2","s3"]},{"date":"2025-09-15","event":"construction_started","kind":"actual","note":"Foundation-laying ceremony attended by Hesse's digital minister and Hanau's mayor.","source_ids":["s1","s2"]}],"name":"Data4 Hanau campus","notes":"Data4's release names no tenants and gives no phase schedule or operating date. Land area sources conflict (25 hectares from Data4, 25 acres from trade press), so both are kept.","parties":[{"name":"Data4","role":"developer","source_ids":["s1","s2"]},{"name":"Data4","note":"Data4 says it finances, designs, builds and operates its own data centers.","role":"operator","source_ids":["s1"]},{"name":"Data4","note":"Acquired the site.","role":"owner","source_ids":["s1"]},{"name":"Brookfield","note":"Owner of Data4, per trade press.","role":"investor","source_ids":["s2","s3"]}],"power_sources":[{"description":"Data4 plans an on-site combined heat and power plant (fuel not stated) and a substation, and says the campus will run on 100% decarbonised energy; waste heat is to serve local district heating.","source_ids":["s1","s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-09-15","publisher":"Data4","title":"Data4 lays the foundations on its first mega campus in Germany: a new gateway to AI, Cloud and Digital Sovereignty","type":"company","url":"https://www.data4group.com/wp-content/uploads/2025/09/FINAL_ENG_Press-Release-_Data4_Event_Hanau-1.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2025-09-17","publisher":"BeBeez International (republishing DCD)","title":"Data4 breaks ground on data center project in Hanau, Germany","type":"trade_press","url":"https://bebeez.eu/en/news/data4-breaks-ground-on-data-center-project-in-hanau-germany/"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-11","publisher":"Capacity","title":"Data centre of the month: Data4’s site in Hanau, Germany","type":"trade_press","url":"https://capacityglobal.com/news/data4-hanau-data-centre-germany-data-centre-of-the-month/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251129092158/https://en.wikipedia.org/wiki/Gro%C3%9Fauheim","id":"s4","published":null,"publisher":"Wikipedia","title":"Großauheim","type":"other","url":"https://en.wikipedia.org/wiki/Gro%C3%9Fauheim"}],"status":"under_construction","status_as_of":"2026-03-11","status_source_ids":["s3"],"summary":"Data4's first German campus, on a former military base in the Großauheim district of Hanau, about 30 minutes from central Frankfurt. Data4, owned by Brookfield, plans 180 MW of power capacity for cloud and AI customers and in September 2025 doubled its planned investment from EUR 1 billion to more than EUR 2 billion when it laid the foundations. The plan includes a combined heat and power plant, a substation, decarbonised energy and waste heat for local district heating. Trade press described the campus as under construction in March 2026; no operating date has been published.","workloads":["cloud","ai_unspecified","colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"ce89216d-e227-5e79-944a-25d62f4fc66c","s2":"2e09b450-ac25-5670-a9cf-3a4e0a434bc5","s3":"c69188d3-f2b9-5b58-81a5-c09f32c31249","s4":"866a1d6b-194f-55be-8129-f3efa462e151"},"source_file":"datacenters/projects/data4-hanau.json","source_record_id":"data4-hanau","source_record_sha256":"0ded64a8f2c490b254e02fe884f19b185b57310e137175a2ae8a3af63ce99372","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"791d141e25245bcc7d686f47847df75d56210d60a0775c795417c0b531aaf6e4"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4a5d5083c6a8b110c612/#project-c53b72b6-ff87-58eb-b74f-7082b159a513 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c53b72b6-ff87-58eb-b74f-7082b159a513.json
c62aed61-a87f-57ab-b1a4-76d1867f73b9 | imported:semiconductor-atlas:core-scientific-denton | vcc-site-dadea001f97aa8058f7a | imported:semiconductor-atlas:core-scientific-denton | Core Scientific Denton data center (CoreWeave) | United States | US | 33.2164 | -97.1292 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City coordinates from Wikipedia. Core Scientific gives the address 8171 Jim Christal Rd, Denton, TX 76207, but it was not geocoded in this review. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3877ce56-44bc-5417-b82c-46b731aa3cf8 | under_construction | 2026-10-09 | 4 | imported_documented_status | 565c5f5d-bb37-5202-b15b-24d35285f349 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"cec8410c-6766-584c-afb5-2e1b9742b3f8","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-denton"},{"evidence_id":"565c5f5d-bb37-5202-b15b-24d35285f349","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-denton"},{"evidence_id":"3877ce56-44bc-5417-b82c-46b731aa3cf8","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"operator","source_record_id":"core-scientific-denton"},{"evidence_id":"565c5f5d-bb37-5202-b15b-24d35285f349","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"operator","source_record_id":"core-scientific-denton"},{"evidence_id":"cec8410c-6766-584c-afb5-2e1b9742b3f8","notes":"Colocation customer for about 260 MW of critical IT load at Denton. The release cites 12-year contract terms across Core Scientific's CoreWeave agreements and two five-year renewal options for the added 70 MW.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-denton"},{"evidence_id":"3877ce56-44bc-5417-b82c-46b731aa3cf8","notes":null,"party":"Denton Municipal Electric","relationship_scope":"unknown","role":"utility","source_record_id":"core-scientific-denton"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Core Scientific |  | CoreWeave |  | https://corescientific.com/high-density-data-centers/denton-texas/ | https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Core Scientific Denton data center (CoreWeave) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"core-scientific-denton"},"record":{"aliases":["Denton 1"],"id":"core-scientific-denton","last_reviewed":"2026-10-09","location":{"admin1":"Texas","country":"US","lat":33.2164,"locality":"Denton","lon":-97.1292,"note":"City coordinates from Wikipedia. Core Scientific gives the address 8171 Jim Christal Rd, Denton, TX 76207, but it was not geocoded in this review.","precision":"locality","source_ids":["s2","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-12-31","basis":"contracted","metric":"power_capacity","note":"Gross utility power capacity from Denton Municipal Electric per the 10-K; the company site lists 394 MW of total power capacity.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2","s4"],"unit":"MW","value":394},{"applies_to":"campus","as_of":"2025-02-26","basis":"contracted","metric":"power_capacity","note":"Critical IT load for CoreWeave after the February 2025 expansion of 70 MW of contracted power.","power_scope":"it_load","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":260},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"From Core Scientific's undated Denton page, as accessed.","qualifier":"exact","source_ids":["s4"],"unit":"acres","value":78}],"milestones":[{"date":"2025-02-26","event":"expansion_announced","kind":"actual","note":"Core Scientific and CoreWeave announced a $1.2 billion contracted-revenue expansion at Denton; Core Scientific funds $104 million of the added capex and CoreWeave the rest.","source_ids":["s1"]},{"date":"2027-H1","event":"other","kind":"planned","note":"Company-wide target to deliver about 590 MW to CoreWeave by early 2027; Denton-specific timing is not stated.","source_ids":["s3"]}],"name":"Core Scientific Denton data center (CoreWeave)","notes":"Status date is the access date of Core Scientific's undated Denton page, which still describes the supercomputer as expected. The sources reviewed do not state how much of the Denton conversion is energized. In March 2026 Core Scientific reported about 350 MW energized across its CoreWeave sites, and its 10-K says a portion of the converted facilities was operating at the end of 2025 without naming them, so the site may already be partly operational.","parties":[{"name":"Core Scientific","role":"developer","source_ids":["s1","s4"]},{"name":"Core Scientific","role":"operator","source_ids":["s2","s4"]},{"name":"CoreWeave","note":"Colocation customer for about 260 MW of critical IT load at Denton. The release cites 12-year contract terms across Core Scientific's CoreWeave agreements and two five-year renewal options for the added 70 MW.","role":"tenant","source_ids":["s1"]},{"name":"Denton Municipal Electric","role":"utility","source_ids":["s2"]}],"power_sources":[{"description":"Denton Municipal Electric supplies 394 MW of gross utility power capacity.","source_ids":["s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-02-26","publisher":"Core Scientific","title":"Core Scientific and CoreWeave Announce $1.2 Billion Expansion at Denton, TX Site","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/110/core-scientific-and-coreweave-announce-1-2-billion-expansion-at-denton-tx-site"},{"accessed":"2026-10-09","id":"s2","published":"2026-03-02","publisher":"U.S. Securities and Exchange Commission (Core Scientific filing)","title":"Core Scientific, Inc. Form 10-K for the fiscal year ended December 31, 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm"},{"accessed":"2026-10-09","id":"s3","published":"2026-03-02","publisher":"Core Scientific","title":"Core Scientific Announces Fourth Quarter Fiscal Year 2025 Results","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/127/core-scientific-announces-fourth-quarter-fiscal-year-2025-results"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929001323/https://corescientific.com/high-density-data-centers/denton-texas/","id":"s4","published":null,"publisher":"Core Scientific","title":"Denton, TX Data Center ¦ High-Density at Scale","type":"company","url":"https://corescientific.com/high-density-data-centers/denton-texas/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Denton, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Denton,_Texas"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s4","s1","s3"],"summary":"Core Scientific campus at 8171 Jim Christal Road in Denton, Texas, with 394 MW of gross utility power capacity from Denton Municipal Electric, being fitted out as high-density colocation for CoreWeave as Core Scientific converts its facilities from digital asset mining to HPC colocation. A February 2025 expansion added 70 MW of contracted power and raised CoreWeave's critical IT load at the site to about 260 MW, adding $1.2 billion of contracted revenue. The campus covers 78 acres, and Core Scientific says it is expected to host one of North America's largest supercomputers.","workloads":["hpc","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"cec8410c-6766-584c-afb5-2e1b9742b3f8","s2":"3877ce56-44bc-5417-b82c-46b731aa3cf8","s3":"fe68a3b2-539a-520d-a3f0-3cedd8bef19e","s4":"565c5f5d-bb37-5202-b15b-24d35285f349","s5":"4aaab43d-5c69-5737-aca9-5e52606ee2ec"},"source_file":"datacenters/projects/core-scientific-denton.json","source_record_id":"core-scientific-denton","source_record_sha256":"91a53158a43d538f9b348f473ca1b8746bd8d181d2d3a8473af455cd7ea27b0b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3b4b3bed3d3924cd80354b7fe4e8046dc61b921015c350a1addc79cb1de64371"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dadea001f97aa8058f7a/#project-c62aed61-a87f-57ab-b1a4-76d1867f73b9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c62aed61-a87f-57ab-b1a4-76d1867f73b9.json
c71872a1-fc95-5d5b-8ee8-6b5082e974df | curated:datagrid-makarewa-ai-factory:initial-horizontal-works | vcc-site-f72817dc402c9746aa98 | curated:datagrid-makarewa-ai-factory | Datagrid Makarewa Initial Horizontal Works | New Zealand | NZ | -46.3369 | 168.3875 | Polygon | campus | official_primary_parcel_union | linz_title_matched_primary_parcels_deterministic_union | official_cadastral_union_as_core_campus_locator | official_source | campus_locator | Current LINZ cadastral union for the four exact title-matched parcels making up about 49.2 hectares. It is not an asserted official project boundary, work extent, building footprint, as-built survey, or the full six-parcel consent property. |  | LINZ publishes broad nominal urban and rural ranges but no bounded project-specific horizontal accuracy for this dissolved four-parcel locator. | e7f25be7-7451-526c-b584-30468a12afe5 | under_construction | 2026-08-18 | 56 | authoritative_construction_start | 21f09e98-2096-55c8-a0a7-41be03842204 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.datagrid.nz/pr1-rc/horizontal-works-begin-on-datagrids-ai-data-centre-campus-in-makarewa | https://services.arcgis.com/xdsHIIxuCWByZiCB/ArcGIS/rest/services/LINZ_NZ_Primary_Parcels/FeatureServer/0/query?where=appellation+IN+%28%27Lot+1+DP+595572%27%2c%27Lot+2+DP+595572%27%2c%27Lot+3+DP+595572%27%2c%27Lot+2+DP+526953%27%29&outFields=OBJECTID%2cid%2cappellation%2cparcel_intent%2ctopology_type%2cland_district%2ctitles%2csurvey_area%2ccalc_area%2cShape__Area%2cShape__Length&returnGeometry=true&outSR=4326&orderByFields=appellation+ASC&f=geojson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f72817dc402c9746aa98/#project-c71872a1-fc95-5d5b-8ee8-6b5082e974df | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c71872a1-fc95-5d5b-8ee8-6b5082e974df.json
c73ac912-e44d-5477-84f5-c5beb4813518 | curated:amazon-salem-township-innovation-campus:active-buildout | vcc-site-b065c16b51237fbb767f | curated:amazon-salem-township-innovation-campus | Amazon Salem Township Active Campus Buildout | United States | US | 41.084 | -76.1434 | Polygon | campus | cross_source_overlay | openstreetmap_named_addressed_aws_building_polygon_as_campus_locator | reviewed_openstreetmap_named_addressed_aws_data_centre_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for one named and addressed Amazon AWS data-centre building, used only to locate the Salem Township innovation campus. It is not an official campus boundary, the complete campus extent, a parcel, the active-buildout footprint or centroid, a construction extent, a current-building count, or a survey-accuracy claim. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | 13a65a07-1b3a-58a3-9ca7-b98723686f7c | under_construction | 2026-07-19 | 86 | authoritative_construction_start | 4197607a-032d-53c9-9fb8-681a6311e78a | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | tracked_identity_bound_uncertain_unsuperseded_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [{"as_of_date":"2026-07-19","confidence":0.95,"deployment_scope":"intended","evidence_id":"4197607a-032d-53c9-9fb8-681a6311e78a","method":"company_disclosure","workload":"mixed"}] |  | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.amazoninnovationinpa.com/salem-township-innovation-campus/ | https://www.openstreetmap.org/way/1334234458 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b065c16b51237fbb767f/#project-c73ac912-e44d-5477-84f5-c5beb4813518 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c73ac912-e44d-5477-84f5-c5beb4813518.json
c7671f1b-16fb-5d22-b002-93f28cea5585 | imported:semiconductor-atlas:pdg-jc3-bekasi | vcc-site-99d9ae40e299f5a9f017 | imported:semiconductor-atlas:pdg-jc3-bekasi | Princeton Digital Group JC3 Greater Jakarta | Indonesia | ID | -6.3836 | 107.1911 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | PDG places JC3 in the Greenland International Industrial Center (GIIC), Bekasi Regency, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the GIIC industrial estate. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 701fe2a3-dc28-5cef-81d2-9c7a67259df8 | under_construction | 2026-05-07 | 159 | imported_documented_status | 701fe2a3-dc28-5cef-81d2-9c7a67259df8 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"701fe2a3-dc28-5cef-81d2-9c7a67259df8","notes":null,"party":"Princeton Digital Group","relationship_scope":"unknown","role":"developer","source_record_id":"pdg-jc3-bekasi"},{"evidence_id":"c6195d0a-a4f4-5781-901e-4d9cd7deabe0","notes":null,"party":"Princeton Digital Group","relationship_scope":"unknown","role":"developer","source_record_id":"pdg-jc3-bekasi"},{"evidence_id":"701fe2a3-dc28-5cef-81d2-9c7a67259df8","notes":null,"party":"Princeton Digital Group","relationship_scope":"unknown","role":"operator","source_record_id":"pdg-jc3-bekasi"},{"evidence_id":"701fe2a3-dc28-5cef-81d2-9c7a67259df8","notes":"Provides dual grid feeds.","party":"PT Perusahaan Listrik Negara (PLN)","relationship_scope":"unknown","role":"utility","source_record_id":"pdg-jc3-bekasi"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Princeton Digital Group |  |  |  | https://princetondg.com/press-releases/princeton-digital-group-breaks-ground-on-milestone-usd-1-billion-120-mw-greater-jakarta-campus/ | https://princetondg.com/press-releases/princeton-digital-group-breaks-ground-on-milestone-usd-1-billion-120-mw-greater-jakarta-campus/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Princeton Digital Group JC3 Greater Jakarta as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"pdg-jc3-bekasi","source_relations":[{"reason":"PDG describes JC4 about 1.7 km from JC3; both use the GIIC estate centroid. Preserve independent campus identities.","relationship":"separate_nearby_campuses","source_id":"pdg-jc4-bekasi"}]},"record":{"aliases":["JC3","PDG JC3"],"id":"pdg-jc3-bekasi","last_reviewed":"2026-10-09","location":{"admin1":"West Java","admin2":"Bekasi Regency","country":"ID","lat":-6.3836,"lon":107.1911,"note":"PDG places JC3 in the Greenland International Industrial Center (GIIC), Bekasi Regency, without a street address; coordinates are the OpenStreetMap Nominatim centroid of the GIIC industrial estate.","precision":"approximate_site","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-07","basis":"under_construction","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":120},{"applies_to":"campus","as_of":"2025-11-19","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1000000000}],"milestones":[{"date":"2025-11-19","event":"construction_started","kind":"actual","note":"Groundbreaking.","source_ids":["s1"]},{"date":"2026-Q4","event":"first_operational","kind":"planned","note":"First phase targeted to be ready for service.","source_ids":["s1"]},{"date":"2026-05-07","event":"other","kind":"actual","note":"PDG announced about USD 856 million of debt (a USD 456 million underwritten syndicated loan plus an accordion of about USD 400 million in progress) for the JC3 build-out.","source_ids":["s2"]}],"name":"Princeton Digital Group JC3 Greater Jakarta","parties":[{"name":"Princeton Digital Group","role":"developer","source_ids":["s1","s2"]},{"name":"Princeton Digital Group","role":"operator","source_ids":["s1"]},{"name":"PT Perusahaan Listrik Negara (PLN)","note":"Provides dual grid feeds.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Dual grid feeds from PLN.","source_ids":["s1"],"type":"grid"}],"related_ids":["pdg-jc4-bekasi"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-19","publisher":"Princeton Digital Group","title":"Princeton Digital Group Breaks Ground on Milestone USD 1 Billion, 120 MW Greater Jakarta Campus","type":"company","url":"https://princetondg.com/press-releases/princeton-digital-group-breaks-ground-on-milestone-usd-1-billion-120-mw-greater-jakarta-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004132014/https://princetondg.com/press-releases/pdg-raising-usd-856-million-debt-for-its-hyperscale-data-center-expansion-in-indonesia/","id":"s2","published":"2026-05-07","publisher":"Princeton Digital Group","title":"PDG Raising ~USD 856 Million Debt for its Hyperscale Data Center Expansion in Indonesia","type":"company","url":"https://princetondg.com/press-releases/pdg-raising-usd-856-million-debt-for-its-hyperscale-data-center-expansion-in-indonesia/"},{"accessed":"2026-10-09","id":"s3","published":"2026-04-30","publisher":"Princeton Digital Group","title":"PDG Acquires 240 MW of Powered Land in Jakarta, Advancing Its Rapid Expansion Across Asia","type":"company","url":"https://princetondg.com/press-releases/pdg-acquires-240-mw-of-powered-land-in-jakarta-advancing-its-rapid-expansion-across-asia/"}],"status":"under_construction","status_as_of":"2026-05-07","status_source_ids":["s1","s2"],"summary":"Princeton Digital Group broke ground in November 2025 on JC3, a USD 1 billion, 120 MW AI-ready hyperscale campus in the Greenland International Industrial Center in Bekasi Regency, Greater Jakarta, about 25 km from its JC2 campus in Cibitung. The campus offers direct-to-chip liquid cooling alongside conventional cooling and dual grid feeds from state utility PLN, with a first phase targeted to be ready for service in the fourth quarter of 2026. In May 2026 PDG said it was raising about USD 856 million of debt to fund the ongoing build-out.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"701fe2a3-dc28-5cef-81d2-9c7a67259df8","s2":"c6195d0a-a4f4-5781-901e-4d9cd7deabe0","s3":"166840f7-6620-5ddb-ae24-c2b8a1f011de"},"source_file":"datacenters/projects/pdg-jc3-bekasi.json","source_record_id":"pdg-jc3-bekasi","source_record_sha256":"fb1513fb62dcd655204b9379590ede9da417a35626575c38b1e116e557e866f4","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b5a881b948f3ef9e8b8676da5680503c9f8c7d5b6901345b60f63d73fd208662"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-99d9ae40e299f5a9f017/#project-c7671f1b-16fb-5d22-b002-93f28cea5585 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c7671f1b-16fb-5d22-b002-93f28cea5585.json
c789668b-ecf3-53b2-b23c-44151e199317 | curated:nextdc-m3-melbourne:incremental-in-progress-fit-out | vcc-site-dec24d7a34a6a816e35b | curated:nextdc-m3-melbourne | NEXTDC M3 Incremental In-Progress Fit-Out | Australia | AU | -37.8049 | 144.8638 | Point | campus | community_named_campus_representative_point | preserve_Nominatim_way1431074202_lat_lon_and_bind_exact_NEXTDC_M3_name_to_operator_West_Footscray_entry | community_campus_reference_point | community_source | campus_locator | OSM way1431074202 is named NEXTDC M3 in West Footscray, matching the operator campus entry at 25 Indwe Street. It has no OSM address tag; the street address is operator evidence, not a synthesized OSM property. This is a source-specific campus locator, not a construction footprint, campus boundary, surveyed entrance or location of the selected remaining fit-out. No coordinate decimal count is an accuracy estimate. |  | The source supplies no quantitative horizontal positional-accuracy estimate; the original coordinate digits are retained without a survey-precision claim. | 944d20c6-1f9a-503d-857d-951b8336071c | mep_electrical | 2026-06-30 | 105 | authoritative_physical_status_update | 43bd6a30-6bac-5500-afd1-74b0e425d6b0 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nextdc.com/hubfs/Financial%20Reports/FY26/FY26%20Results%20Announcement.pdf | https://nominatim.openstreetmap.org/search?q=NEXTDC%20M3&format=jsonv2&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-dec24d7a34a6a816e35b/#project-c789668b-ecf3-53b2-b23c-44151e199317 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c789668b-ecf3-53b2-b23c-44151e199317.json
c794c146-24e6-5cb8-8cd9-a12a266bba83 | curated:digipowerx-columbiana-ai-data-center-campus:purpose-built-flagship-vertical-build | vcc-site-c1a0f58564147c78c139 | curated:digipowerx-columbiana-ai-data-center-campus | Digi Power X Columbiana Purpose-Built Flagship Vertical Build | United States | US | 33.1828 | -86.6185 | Point | campus | official_address_geocode | official_address_geocode | address_range_geocode | official_source | campus_locator | Exact returned Census coordinate for the project-linked street address; digits are not positional accuracy and the point is not parcel, rooftop, building, or work-area geometry. |  | Census supplies an address-range geocode without a bounded horizontal error for this match. | 8e34c085-5ca7-50e1-b460-ac5132c8439a | shell | 2026-07-07 | 98 | authoritative_physical_status_update | 25d30d41-6ee8-521c-a8d5-5fc372370ebb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://thankful-miracle-1ed8bdfdaf.media.strapiapp.com/Digi_Power_X_Provides_Operations_and_Financial_Update_4a179c433b.pdf | https://geocoding.geo.census.gov/geocoder/geographies/onelineaddress?address=130%20Industrial%20Pkwy%2C%20Columbiana%2C%20AL&benchmark=Public_AR_Current&vintage=Current_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c1a0f58564147c78c139/#project-c794c146-24e6-5cb8-8cd9-a12a266bba83 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c794c146-24e6-5cb8-8cd9-a12a266bba83.json
c7adcc1a-b5ed-5df0-b28b-572b6d9dbc4b | imported:semiconductor-atlas:galaxy-helios | vcc-site-43bf6c7b8c9e9dfc51d0 | curated:galaxy-helios-data-center-campus | Galaxy Helios data center campus | United States | US | 33.62 | -100.78 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | County coordinates from Wikipedia; Galaxy names Dickens County but gives no street address. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | fdcb5993-0964-542a-836c-12f1a74bf919 | partially_operational | 2026-08-12 | 62 | imported_documented_status | fdcb5993-0964-542a-836c-12f1a74bf919 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a7aeea58-842a-518b-85d0-f035420feeb1","notes":null,"party":"Galaxy Digital","relationship_scope":"unknown","role":"developer","source_record_id":"galaxy-helios"},{"evidence_id":"50f3cc80-73a3-5465-a007-cf94dd0d0382","notes":null,"party":"Galaxy Digital","relationship_scope":"unknown","role":"developer","source_record_id":"galaxy-helios"},{"evidence_id":"50f3cc80-73a3-5465-a007-cf94dd0d0382","notes":"Galaxy says it acquired Helios in 2022.","party":"Galaxy Digital","relationship_scope":"unknown","role":"owner","source_record_id":"galaxy-helios"},{"evidence_id":"a7aeea58-842a-518b-85d0-f035420feeb1","notes":"Leases for the initial 133 MW of critical IT (15 years, April 2025), Phase II (260 MW, August 2025) and Phase III (133 MW, January 2026).","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"galaxy-helios"},{"evidence_id":"50f3cc80-73a3-5465-a007-cf94dd0d0382","notes":"Leases for the initial 133 MW of critical IT (15 years, April 2025), Phase II (260 MW, August 2025) and Phase III (133 MW, January 2026).","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"galaxy-helios"},{"evidence_id":"fdcb5993-0964-542a-836c-12f1a74bf919","notes":"Leases for the initial 133 MW of critical IT (15 years, April 2025), Phase II (260 MW, August 2025) and Phase III (133 MW, January 2026).","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"galaxy-helios"},{"evidence_id":"fdcb5993-0964-542a-836c-12f1a74bf919","notes":"Named by Galaxy as the new general contractor for Phase II in August 2026.","party":"HITT","relationship_scope":"unknown","role":"builder","source_record_id":"galaxy-helios"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Galaxy Digital |  |  | CoreWeave |  | https://www.galaxy.com/newsroom/q226-unwrapped | https://www.galaxy.com/newsroom/q226-unwrapped | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same Galaxy Helios campus in Dickens County. Source includes operating phase I and three-phase CoreWeave leases; existing record selects phase II 260 MW critical-IT construction.","source_record_id":"galaxy-helios","target_physical_site_stable_key":"curated:galaxy-helios-data-center-campus"},"record":{"aliases":["Helios"],"id":"galaxy-helios","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Dickens County","country":"US","lat":33.62,"lon":-100.78,"note":"County coordinates from Wikipedia; Galaxy names Dickens County but gives no street address.","precision":"admin2","source_ids":["s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-01","basis":"permitted","metric":"power_capacity","note":"Gross power capacity approved by ERCOT, combining the original 800 MW and 830 MW approved in January 2026.","power_scope":"grid_connection","qualifier":"more_than","source_ids":["s1","s2"],"unit":"MW","value":1600},{"applies_to":"phase","as_of":"2026-04-08","basis":"contracted","metric":"power_capacity","note":"Gross power leased to CoreWeave, stated by Galaxy as the first 800 MW; the 10-K gives about 200 MW for the initial lease and 600 MW for the Phase II and III leases.","phase_label":"CoreWeave Phases I-III","power_scope":"facility","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":800},{"applies_to":"phase","as_of":"2026-01","basis":"contracted","metric":"power_capacity","phase_label":"CoreWeave Phases I-III","power_scope":"it_load","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":526},{"applies_to":"phase","as_of":"2026-08-12","basis":"operational","metric":"power_capacity","phase_label":"Phase I","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":133},{"applies_to":"phase","as_of":"2026-08-12","basis":"under_construction","metric":"power_capacity","note":"Earthwork complete and foundation work under way in August 2026. Galaxy's update does not report construction status for Phase III.","phase_label":"Phase II","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":260},{"applies_to":"phase","as_of":"2026-01","basis":"permitted","metric":"power_capacity","note":"Not yet leased; Galaxy had committed more than $180 million to long-lead equipment by August 2026.","phase_label":"Expansion approved January 2026","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":830},{"applies_to":"phase","as_of":"2026-04-08","basis":"announced","metric":"investment","note":"Capital investment Galaxy associates with the first 800 MW leased to CoreWeave.","phase_label":"CoreWeave Phases I-III","qualifier":"more_than","source_ids":["s2"],"unit":"USD","value":7500000000},{"applies_to":"campus","as_of":"2026-04-08","basis":"reported","metric":"investment","note":"Galaxy CEO's estimate of long-term digital infrastructure investment at Helios.","qualifier":"more_than","source_ids":["s2"],"unit":"USD","value":15000000000}],"milestones":[{"date":"2022","event":"site_acquired","kind":"actual","source_ids":["s2"]},{"date":"2025-04","event":"other","kind":"actual","note":"15-year CoreWeave lease for the first 133 MW of critical IT load.","source_ids":["s1"]},{"date":"2025-08","event":"expansion_announced","kind":"actual","note":"CoreWeave Phase II lease for 260 MW of additional critical IT.","source_ids":["s1"]},{"date":"2026-01","event":"expansion_announced","kind":"actual","note":"CoreWeave Phase III lease for 133 MW of additional critical IT; ERCOT approved 830 MW more.","source_ids":["s1"]},{"date":"2026","event":"first_operational","kind":"actual","note":"Galaxy's Q2 2026 update reported the first 133 MW of critical IT load delivered to CoreWeave and in service.","source_ids":["s3"]},{"date":"2027-Q2","event":"other","kind":"planned","note":"First of eight Phase II data halls expected online; seven by year-end and the last in early 2028.","source_ids":["s3"]}],"name":"Galaxy Helios data center campus","parties":[{"name":"Galaxy Digital","role":"developer","source_ids":["s1","s2"]},{"name":"Galaxy Digital","note":"Galaxy says it acquired Helios in 2022.","role":"owner","source_ids":["s2"]},{"name":"CoreWeave","note":"Leases for the initial 133 MW of critical IT (15 years, April 2025), Phase II (260 MW, August 2025) and Phase III (133 MW, January 2026).","role":"tenant","source_ids":["s1","s2","s3"]},{"name":"HITT","note":"Named by Galaxy as the new general contractor for Phase II in August 2026.","role":"builder","source_ids":["s3"]}],"power_sources":[{"description":"ERCOT has approved more than 1.6 GW of gross capacity for the campus; six main power transformers are installed at the project substation.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260501171759/https://www.sec.gov/Archives/edgar/data/1859392/000185939226000016/glxy-20251231.htm","id":"s1","published":"2026-02-26","publisher":"U.S. Securities and Exchange Commission (Galaxy Digital filing)","title":"Galaxy Digital Inc. Form 10-K for the fiscal year ended December 31, 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1859392/000185939226000016/glxy-20251231.htm"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-08","publisher":"Galaxy","title":"A Letter from the Founder & CEO (GLXY 2025 Annual Report)","type":"company","url":"https://www.galaxy.com/newsroom/2025-annual-report-and-ceo-letter"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-12","publisher":"Galaxy","title":"Galaxy Q2 2026 Unwrapped: The Code Economy Delivers","type":"company","url":"https://www.galaxy.com/newsroom/q226-unwrapped"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-27","publisher":"Galaxy","title":"Galaxy Announces On-Campus Emergency Services Partnership with Total Safety at Helios Data Center Campus","type":"company","url":"https://www.galaxy.com/newsroom/galaxy-announces-on-campus-emergency-services-partnership-with-total-safety-at-helios"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260804033539/https://en.wikipedia.org/wiki/Dickens_County,_Texas","id":"s5","published":null,"publisher":"Wikipedia","title":"Dickens County, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Dickens_County,_Texas"}],"status":"partially_operational","status_as_of":"2026-08-12","status_source_ids":["s3"],"summary":"Mining campus in Dickens County, in the West Texas panhandle, that Galaxy acquired in 2022 and is converting into AI and HPC data centers. CoreWeave has leased the first 800 MW of gross power in three phases totaling 526 MW of critical IT load, starting with a 15-year lease signed in April 2025. Galaxy delivered the first 133 MW of critical IT load to CoreWeave in 2026, and the eight Phase II data halls are expected online from the second quarter of 2027 into early 2028. ERCOT approved another 830 MW in January 2026, taking approved capacity above 1.6 GW, and Galaxy plans to develop that capacity on a build-to-suit basis.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a7aeea58-842a-518b-85d0-f035420feeb1","s2":"50f3cc80-73a3-5465-a007-cf94dd0d0382","s3":"fdcb5993-0964-542a-836c-12f1a74bf919","s4":"f318a6fd-2039-503e-a4a9-8269d59b70fe","s5":"5bc59bd6-db35-5157-b6d7-cbf30f94f53d"},"source_file":"datacenters/projects/galaxy-helios.json","source_record_id":"galaxy-helios","source_record_sha256":"fb7062a8fab776e6721a45fc5ed166567bb5a5383511e86566b63610f5a5bf3f","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"576000b87be4d233c49e6a85f4fd2ae5cd2af4523170cf71c15b7b097f6711e3"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-43bf6c7b8c9e9dfc51d0/#project-c7adcc1a-b5ed-5df0-b28b-572b6d9dbc4b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c7adcc1a-b5ed-5df0-b28b-572b6d9dbc4b.json
c7eebc15-358c-5985-9a48-16f53bdd4726 | curated:digital-edge-edge2-jakarta:phase-3-electrical-mechanical-build | vcc-site-afb6c00afe427fdacc70 | curated:digital-edge-edge2-jakarta | Digital Edge EDGE2 Phase 3 Electrical and Mechanical Development | Indonesia | ID | -6.214 | 106.8351 | Polygon | campus | Exact OSM way1230327255 ordered node ring; display-only anchor is the mean of four unique corners of this parallelogram. | copy_named_community_building_source_nodes_in_way_order_without_digitizing_or_geocoding | community_mapped_constituent_building_outline | community_source | campus_locator | Source node coordinates retain seven decimal places. The mapped existing EDGE2 building locates one physical campus with phase3 electrical/mechanical construction; it is not an official cadastral or campus boundary, a surveyed footprint or the current work extent. Separate EDGE1, CGK, DGE1 and DGE2 are not merged. The brochure point remains rejected and source-map precision is not measured accuracy. |  | OSM does not supply a survey method or quantitative positional accuracy for this feature. Numeric precision and agreement with earlier snapshots do not establish accuracy. | 60295470-6e35-5151-ae6c-7ff84481ab48 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 11086c9d-4b87-5828-8aa8-8bc8dce80f2c | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://indonet.id/wp-content/uploads/2026/08/FS-Indonet-30-June-2026.pdf | https://www.openstreetmap.org/api/0.6/way/1230327255/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-afb6c00afe427fdacc70/#project-c7eebc15-358c-5985-9a48-16f53bdd4726 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c7eebc15-358c-5985-9a48-16f53bdd4726.json
c9b6bff7-09a3-599b-9c8c-49243461c0fb | curated:flexbase-technologiezentrum-laufenburg-campus:new-technology-centre-current-build | vcc-site-30de35a29d7b36fc6ef8 | curated:flexbase-technologiezentrum-laufenburg-campus | FlexBase New Technology Centre Current Build | Switzerland | CH | 47.5536 | 8.0511 | Point | campus | copy_Overpass_center_of_explicitly_named_Technologiezentrum_Laufenburg_way1160708952 | copy_Overpass_center_of_explicitly_named_Technologiezentrum_Laufenburg_way1160708952 | community_mapped_campus_reference_point | community_source | campus_locator | Representative center of the named new construction feature. It is not a survey, building centroid, legal boundary, existing-office location or a claim that all mixed-use floor area is data-center space. |  | Community map metadata does not provide survey accuracy or quantitative positional uncertainty. | 0348daa4-b3cf-562b-97d3-9a49949647d2 | under_construction | 2026-06-18 | 117 | authoritative_physical_status_update | 832dc37a-5254-5be4-b0c9-4b4b24fcd3e9 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.erne-gruppe.ch/de/bauprojekte/neubau-flexbase-technologiezentrum-laufenburg/ | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bnwr%5B%22name%22~%22FlexBase%7CTechnologiezentrum%7CSwissgrid%22%2Ci%5D%2847.52%2C8.03%2C47.59%2C8.1%29%3Bout%20meta%20center%3B | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-30de35a29d7b36fc6ef8/#project-c9b6bff7-09a3-599b-9c8c-49243461c0fb | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/c9b6bff7-09a3-599b-9c8c-49243461c0fb.json
ca9b7a8f-2f71-5996-8ef1-66d4a2bfe2fa | imported:semiconductor-atlas:microsoft-skelton-grange-leeds | vcc-site-307be41074d784035ee5 | imported:semiconductor-atlas:microsoft-skelton-grange-leeds | Microsoft Skelton Grange datacentre campus, Leeds | United Kingdom | GB | 53.7758 | -1.4978 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Nominatim point on Skelton Grange Road, Stourton (LS10 1RS), next to the former power station land the sources name; the exact plot boundaries are not published in the sources. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 72dad65d-f126-519a-a2dd-bfbd080c5b9a | announced | 2026-04-27 | 169 | imported_documented_status | 72dad65d-f126-519a-a2dd-bfbd080c5b9a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"d573a930-a412-5fcf-9f8b-1949e6c51e80","notes":"Harworth names the applicant as Microsoft entity MSFT MCIO Limited.","party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-skelton-grange-leeds"},{"evidence_id":"72dad65d-f126-519a-a2dd-bfbd080c5b9a","notes":"Harworth names the applicant as Microsoft entity MSFT MCIO Limited.","party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-skelton-grange-leeds"},{"evidence_id":"72dad65d-f126-519a-a2dd-bfbd080c5b9a","notes":"Owns Plot 1 (27 acres) since June 2024; purchase of Plot 2 (21 acres) was still to complete as of April 2026.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-skelton-grange-leeds"},{"evidence_id":"57ec8b60-3112-55c7-a657-d09b655e62c2","notes":"Owns Plot 1 (27 acres) since June 2024; purchase of Plot 2 (21 acres) was still to complete as of April 2026.","party":"Microsoft","relationship_scope":"unknown","role":"owner","source_record_id":"microsoft-skelton-grange-leeds"},{"evidence_id":"72dad65d-f126-519a-a2dd-bfbd080c5b9a","notes":"Sold the land to Microsoft and is carrying out site remediation and enabling works for it; retains an adjoining 16-acre plot for industrial and logistics space.","party":"Harworth Group","relationship_scope":"unknown","role":"builder","source_record_id":"microsoft-skelton-grange-leeds"},{"evidence_id":"57ec8b60-3112-55c7-a657-d09b655e62c2","notes":"Sold the land to Microsoft and is carrying out site remediation and enabling works for it; retains an adjoining 16-acre plot for industrial and logistics space.","party":"Harworth Group","relationship_scope":"unknown","role":"builder","source_record_id":"microsoft-skelton-grange-leeds"},{"evidence_id":"72dad65d-f126-519a-a2dd-bfbd080c5b9a","notes":null,"party":"Leeds City Council","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-skelton-grange-leeds"},{"evidence_id":"1259e6c5-d7bd-5b59-bd22-95b2f92da07c","notes":null,"party":"Leeds City Council","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-skelton-grange-leeds"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Microsoft |  |  |  |  | https://harworthgroup.com/2026/04/27/harworth-and-microsoft-receive-resolution-to-grant-planning-consent-for-hyperscale-data-centre-and-il-space-at-skelton-grange-leeds/ | https://harworthgroup.com/2026/04/27/harworth-and-microsoft-receive-resolution-to-grant-planning-consent-for-hyperscale-data-centre-and-il-space-at-skelton-grange-leeds/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Skelton Grange datacentre campus, Leeds as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-skelton-grange-leeds"},"record":{"aliases":["Skelton Grange (Leeds) datacentre"],"id":"microsoft-skelton-grange-leeds","last_reviewed":"2026-10-09","location":{"admin1":"England","admin2":"Leeds","country":"GB","lat":53.7758,"locality":"Stourton","lon":-1.4978,"note":"Nominatim point on Skelton Grange Road, Stourton (LS10 1RS), next to the former power station land the sources name; the exact plot boundaries are not published in the sources.","precision":"approximate_site","source_ids":["s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-27","basis":"reported","metric":"investment","note":"Harworth's estimate of inward investment once the development completes; Construction Enquirer uses the figure in its headline. Microsoft has not published a figure.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"GBP","value":4000000000},{"applies_to":"campus","as_of":"2026-04-27","basis":"planned","metric":"buildings","note":"Construction Enquirer reports three buildings; Harworth and The Construction Index describe three data centre halls plus auxiliary buildings.","qualifier":"exact","source_ids":["s2","s3","s4"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2026-04-27","basis":"planned","metric":"floor_area","note":"Three data centre buildings, per Construction Enquirer.","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":424000},{"applies_to":"campus","as_of":"2026-04-27","basis":"planned","metric":"floor_area","note":"Harworth's figure for three data centre halls plus auxiliary buildings on Plots 1 and 2.","qualifier":"approximately","source_ids":["s2","s4"],"unit":"sq_ft","value":500000},{"applies_to":"phase","as_of":"2024-06","basis":"acquired","metric":"land_area","note":"Bought for GBP 51.2 million gross; Plot 2 (21 acres) adds GBP 53.2 million on completion.","phase_label":"Plot 1","qualifier":"exact","source_ids":["s2","s4"],"unit":"acres","value":27},{"applies_to":"campus","as_of":"2026-04-27","basis":"reported","metric":"land_area","note":"Site of the whole hybrid application, which also includes industrial space on land retained by Harworth outside the Microsoft plots.","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":65},{"applies_to":"campus","as_of":"2026-04-27","basis":"planned","metric":"jobs_construction","note":"Over a build programme described as six years.","qualifier":"approximately","source_ids":["s3"],"unit":"count","value":740},{"applies_to":"campus","as_of":"2026-04-27","basis":"planned","metric":"jobs_permanent","note":"Operational roles across the data centre campus and the industrial and logistics element.","qualifier":"more_than","source_ids":["s3"],"unit":"count","value":350}],"milestones":[{"date":"2024-06","event":"site_acquired","kind":"actual","note":"Plot 1 purchase completed; Plot 2 still pending in April 2026.","source_ids":["s2","s4"]},{"date":"2025-06-11","event":"other","kind":"actual","note":"Microsoft held a two-day public consultation on 11-12 June 2025 while preparing its planning application (later registered as 25/06139/FU).","source_ids":["s1","s2"]},{"date":"2026-04","event":"zoning_approved","kind":"actual","note":"Leeds City Council planners resolved to grant the hybrid application, delegating final approval to the Chief Planning Officer subject to conditions and a Section 106 agreement.","source_ids":["s2","s3","s4"]},{"date":"2027","event":"construction_started","kind":"planned","note":"Construction Enquirer reported a start on site was likely within 12 to 18 months of the April 2026 approval.","source_ids":["s3"]}],"name":"Microsoft Skelton Grange datacentre campus, Leeds","notes":"No power capacity figure for the campus was found in the cited sources; Harworth's 0.8 GW figure refers to its wider powered-land portfolio, not this campus. Harworth's release footnote dates the plans panel to 23/04/2027, apparently a typo for 2026. The Construction Index page shows only day and month; the year is taken from its context alongside the same-day Harworth release.","parties":[{"name":"Microsoft","note":"Harworth names the applicant as Microsoft entity MSFT MCIO Limited.","role":"developer","source_ids":["s1","s2"]},{"name":"Microsoft","note":"Owns Plot 1 (27 acres) since June 2024; purchase of Plot 2 (21 acres) was still to complete as of April 2026.","role":"owner","source_ids":["s2","s4"]},{"name":"Harworth Group","note":"Sold the land to Microsoft and is carrying out site remediation and enabling works for it; retains an adjoining 16-acre plot for industrial and logistics space.","role":"builder","source_ids":["s2","s4"]},{"name":"Leeds City Council","role":"government","source_ids":["s2","s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260916155404/https://local.microsoft.com/blog/skelton-grange-leeds-datacentre-planning-application/","id":"s1","published":null,"publisher":"Microsoft Local","title":"Skelton Grange (Leeds) Datacentre Planning Application","type":"company","url":"https://local.microsoft.com/blog/skelton-grange-leeds-datacentre-planning-application/"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-27","publisher":"Harworth Group","title":"Harworth and Microsoft receive resolution to grant planning consent for hyperscale data centre and I&L space at Skelton Grange, Leeds","type":"company","url":"https://harworthgroup.com/2026/04/27/harworth-and-microsoft-receive-resolution-to-grant-planning-consent-for-hyperscale-data-centre-and-il-space-at-skelton-grange-leeds/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003184249/https://www.constructionenquirer.com/2026/04/27/go-ahead-for-microsofts-4bn-leeds-data-hub-push/","id":"s3","published":"2026-04-27","publisher":"Construction Enquirer","title":"Go-ahead for Microsoft's £4bn Leeds data hub push","type":"trade_press","url":"https://www.constructionenquirer.com/2026/04/27/go-ahead-for-microsofts-4bn-leeds-data-hub-push/"},{"accessed":"2026-10-09","id":"s4","published":"2026-04-27","publisher":"The Construction Index","title":"Data centre approved in Leeds","type":"trade_press","url":"https://www.theconstructionindex.co.uk/news/view/data-centre-approved-in-leeds"}],"status":"announced","status_as_of":"2026-04-27","status_source_ids":["s2","s3","s4"],"summary":"Planned Microsoft hyperscale datacentre campus on the former Skelton Grange power station land at Stourton, Leeds, beside the River Aire. Microsoft bought the first 27-acre plot from Harworth Group in 2024, and a second 21-acre plot is due to transfer. The application covers three data centre buildings of about 424,000 sq ft (about 500,000 sq ft with auxiliary buildings) plus power, water and energy infrastructure. Leeds planners resolved to grant consent in April 2026, subject to conditions and a Section 106 agreement. Harworth estimates about GBP 4 billion of inward investment at completion; a start on site was expected within 12 to 18 months."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"d573a930-a412-5fcf-9f8b-1949e6c51e80","s2":"72dad65d-f126-519a-a2dd-bfbd080c5b9a","s3":"1259e6c5-d7bd-5b59-bd22-95b2f92da07c","s4":"57ec8b60-3112-55c7-a657-d09b655e62c2"},"source_file":"datacenters/projects/microsoft-skelton-grange-leeds.json","source_record_id":"microsoft-skelton-grange-leeds","source_record_sha256":"9060bb11a242aa6d4b736bffada87ddb9a23ac1c4462581a4aa1aea25874a7b5","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b82fadf68164fb6e8c94dbab887d58ac27d54e0e1b8f7680f42944caef1a52c1"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-307be41074d784035ee5/#project-ca9b7a8f-2f71-5996-8ef1-66d4a2bfe2fa | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ca9b7a8f-2f71-5996-8ef1-66d4a2bfe2fa.json
cb66229f-70db-5cfc-95b3-f5a05a3e73bc | imported:semiconductor-atlas:kasi-cloud-lekki | vcc-site-94afbf6dc84e8a88fc00 | imported:semiconductor-atlas:kasi-cloud-lekki | Kasi Cloud LOS campus (Lekki, Lagos) | Nigeria | NG | 6.4934 | 3.7207 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates of Lekki from its Wikipedia article. Capacity Media places the site in the Maiyegun area of Lekki, ThisDay along the Lagos-Calabar coastal highway, and Kasi's website lists the campus in Lekki, Lagos; no exact point is published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6bd0fd8d-5b0f-51c9-a6cd-55c87d0a291b | partially_operational | 2026-05-19 | 147 | imported_documented_status | 29483830-227d-5f2c-9552-ea7a8e4a2018 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6bd0fd8d-5b0f-51c9-a6cd-55c87d0a291b","notes":null,"party":"Kasi Cloud","relationship_scope":"unknown","role":"developer","source_record_id":"kasi-cloud-lekki"},{"evidence_id":"20040910-3ae7-5291-981e-139492623469","notes":null,"party":"Kasi Cloud","relationship_scope":"unknown","role":"developer","source_record_id":"kasi-cloud-lekki"},{"evidence_id":"29483830-227d-5f2c-9552-ea7a8e4a2018","notes":null,"party":"Kasi Cloud","relationship_scope":"unknown","role":"developer","source_record_id":"kasi-cloud-lekki"},{"evidence_id":"29483830-227d-5f2c-9552-ea7a8e4a2018","notes":null,"party":"Kasi Cloud","relationship_scope":"unknown","role":"operator","source_record_id":"kasi-cloud-lekki"},{"evidence_id":"6bd0fd8d-5b0f-51c9-a6cd-55c87d0a291b","notes":"Capacity Media names the authority's chief executive among Kasi's key investors attending the groundbreaking.","party":"Nigeria Sovereign Investment Authority","relationship_scope":"unknown","role":"investor","source_record_id":"kasi-cloud-lekki"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Kasi Cloud |  |  |  | https://brandspurng.com/?p=191649 | https://capacityglobal.com/article/29zq9ki6a4ua8k9zv0q9s/data-economy/kasi-cloud-breaks-ground-on-first-nigeria-campus | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Kasi Cloud LOS campus (Lekki, Lagos) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"kasi-cloud-lekki"},"record":{"aliases":["Kasi LOS1","Kasi Cloud Lagos campus"],"id":"kasi-cloud-lekki","last_reviewed":"2026-10-09","location":{"admin1":"Lagos State","country":"NG","lat":6.493394,"locality":"Lekki","lon":3.720668,"note":"Coordinates of Lekki from its Wikipedia article. Capacity Media places the site in the Maiyegun area of Lekki, ThisDay along the Lagos-Calabar coastal highway, and Kasi's website lists the campus in Lekki, Lagos; no exact point is published.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-19","basis":"planned","metric":"power_capacity","note":"The dedicated substation can scale to about 100 MW of IT load; the campus is to grow progressively to this size.","power_scope":"it_load","qualifier":"approximately","source_ids":["s3"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2026-05-18","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":100},{"applies_to":"phase","as_of":"2026-05-18","basis":"planned","metric":"power_capacity","note":"ThisDay gives 8 MW per floor and 32 MW for the four floors; Brand Spur says each floor is designed for up to 8 MW of critical load and that a single building could scale beyond 30 MW.","phase_label":"LOS1 building (four floors)","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":32},{"applies_to":"campus","as_of":"2026-05-19","basis":"announced","metric":"investment","qualifier":"approximately","source_ids":["s1","s3"],"unit":"USD","value":250000000},{"applies_to":"campus","as_of":"2022-04-20","basis":"acquired","metric":"land_area","qualifier":"approximately","source_ids":["s1"],"unit":"hectares","value":4},{"applies_to":"campus","as_of":"2026-05-18","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s2"],"unit":"hectares","value":4.2},{"applies_to":"campus","as_of":"2026-05-18","basis":"planned","metric":"buildings","note":"LOS1 is described as the first of four facilities.","qualifier":"exact","source_ids":["s2"],"unit":"count","value":4}],"milestones":[{"date":"2022-04-19","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony with the Lagos State governor as guest of honour; Capacity Media, published on 20 April 2022, dates it to the previous day.","source_ids":["s1"]},{"date":"2023-Q2","event":"other","kind":"actual","note":"Major construction works began.","source_ids":["s3"]},{"date":"2026-05","event":"first_operational","kind":"actual","note":"Brand Spur reports the first phase of LOS1 as commissioned: a 5.5 MW data hall and a 7.5 MW ecosystem floor where customers can lease from a single server to a full aisle. Kasi's website still showed the campus as coming soon in October 2026.","source_ids":["s3"]}],"name":"Kasi Cloud LOS campus (Lekki, Lagos)","notes":"Sources conflict on whether the campus is in service. Brand Spur (19 May 2026) reports that Kasi commissioned the first phase of LOS1, ThisDay (18 May 2026) only said the launch was due the next day, and Kasi's own website still listed the LOS campus (LOS1 and LOS5) under coming soon when read on 2026-10-09. The partially operational status therefore rests on a single press report. ThisDay's publication date comes from its URL. The 5.5 MW and 7.5 MW first-phase figures are kept separate and not added together.","parties":[{"name":"Kasi Cloud","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Kasi Cloud","role":"operator","source_ids":["s3"]},{"name":"Nigeria Sovereign Investment Authority","note":"Capacity Media names the authority's chief executive among Kasi's key investors attending the groundbreaking.","role":"investor","source_ids":["s1"]}],"power_sources":[{"description":"Dedicated 132 kV substation for the campus.","source_ids":["s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2022-04-20","publisher":"Capacity Media","title":"Kasi Cloud breaks ground on first Nigeria campus","type":"trade_press","url":"https://capacityglobal.com/article/29zq9ki6a4ua8k9zv0q9s/data-economy/kasi-cloud-breaks-ground-on-first-nigeria-campus"},{"accessed":"2026-10-09","id":"s2","published":"2026-05-18","publisher":"ThisDay","title":"Kasi Set to Launch Hyperscale AI-ready Data Centres in Lagos","type":"news","url":"https://www.thisdaylive.com/2026/05/18/kasi-set-to-launch-hyperscale-ai-ready-data-centres-in-lagos/"},{"accessed":"2026-10-09","id":"s3","published":"2026-05-19","publisher":"Brand Spur Nigeria","title":"Kasi Cloud Commissions First Phase Of 100MW AI-Ready Hyperscale Data Centre In Lagos","type":"news","url":"https://brandspurng.com/?p=191649"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Kasi Cloud","title":"Kasi Cloud","type":"company","url":"https://www.kasicloud.com/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Lekki","type":"other","url":"https://en.wikipedia.org/wiki/Lekki"}],"status":"partially_operational","status_as_of":"2026-05-19","status_source_ids":["s3"],"summary":"Hyperscale, AI-ready data centre campus of Kasi Cloud on about 4 hectares in the Maiyegun area of Lekki, Lagos, Nigeria, along the Lagos-Calabar coastal highway. Kasi broke ground in April 2022 on the USD 250 million project and major construction began in the second quarter of 2023. A May 2026 press report says Kasi commissioned the first phase, a 5.5 MW data hall and a 7.5 MW shared ecosystem floor in LOS1, the first of four planned buildings, although Kasi's own website still listed the campus as coming soon in October 2026. LOS1 has four floors of up to 8 MW of critical load each, and a dedicated 132 kV substation can scale the campus to about 100 MW of IT load.","workloads":["ai_unspecified","cloud","colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6bd0fd8d-5b0f-51c9-a6cd-55c87d0a291b","s2":"20040910-3ae7-5291-981e-139492623469","s3":"29483830-227d-5f2c-9552-ea7a8e4a2018","s4":"4bdd34dc-089d-59c4-83b3-32a95d278bc3","s5":"9f45e3cb-e4f5-533b-a970-c0ebb718d877"},"source_file":"datacenters/projects/kasi-cloud-lekki.json","source_record_id":"kasi-cloud-lekki","source_record_sha256":"f28323f52114c0517e3c60722514b6397a3c39996bc56c6cdaaf9597fa545f91","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"994ea8e104afde12c65f813d40d155ca02a8c101e0bc1c913dc8351b5ba5abb3"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-94afbf6dc84e8a88fc00/#project-cb66229f-70db-5cfc-95b3-f5a05a3e73bc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/cb66229f-70db-5cfc-95b3-f5a05a3e73bc.json
cbe074bd-68d8-59cb-aaf7-e21fa82b193f | curated:stack-bossier-highway-3-technology-park-campus:current-campus-build | vcc-site-b414ed2a7f2e60f4b886 | curated:stack-bossier-highway-3-technology-park-campus | STACK Bossier Highway 3 Technology Park Current Campus Build | United States | US | 32.7556 | -93.7357 | Point | campus | Extract the named smaller Project Site path from the government-published applicant map; interpolate its PDF positions through the four embedded source-CRS controls, explicitly normalize the self-touching ring, take an interior representative point in source projected units, transform without ballpark operations and round the locator to five decimals. | interior_point_of_named_project_map_vector_path_using_embedded_geospatial_pdf_controls | derived_point_within_named_applicant_project_area | official_source | campus_locator | Five-decimal longitude/latitude locator derived from the specifically named Project Site, not from the larger landholding or viewport. Official source means the government-published applicant submission, not Corps survey certification. This is not a surveyed building, entrance, parcel centroid, campus boundary, verified construction footprint or observed work location. Extra intermediate digits are computational precision; the two-metre datum-operation accuracy is not source positional accuracy. |  | The applicant drawing provides no quantitative survey or positional-accuracy estimate. Embedded five-decimal geographic controls, vector-page precision, interpolation consistency and datum-operation accuracy do not establish the accuracy of the drawing or derived locator. | 2990174e-9cc5-5129-9c06-7fd46477a9b0 | under_construction | 2026-06-10 | 125 | authoritative_physical_status_update | 53b4020a-a8d0-54b6-8fe4-b3fbe48a2b21 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.stackinfra.com/about/news-press/press-releases/stack-infrastructure-partners-with-amazon-to-invest-in-northwest-louisiana-communities/ | https://www.mvk.usace.army.mil/Portals/58/docs/regulatory/publicnotices/Public%20Notice%20MVK-2025-00855%20WP%20Signed.pdf?ver=D2NPrQzn2XfolicLUj62YA%3D%3D | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b414ed2a7f2e60f4b886/#project-cbe074bd-68d8-59cb-aaf7-e21fa82b193f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/cbe074bd-68d8-59cb-aaf7-e21fa82b193f.json
cbe9c330-13a3-5d1f-a9ba-c981c31585a7 | curated:cloud4y-marfino-data-center-campus:main-building-current-build | vcc-site-1295b8a3ae3b2543ec97 | curated:cloud4y-marfino-data-center-campus | Cloud4Y Marfino Main Building Current Construction | Russia | RU | 56.0741 | 37.5663 | Point | campus | operator_card_coordinate_pair_axis_reorder_only | first_party_named_datacenter_card_yandex_placemark | operator_published_campus_reference_point | official_source | campus_locator | Exact operator-supplied numeric precision retained; actual positional accuracy unknown. Campus marker only, not construction boundary, main-building footprint, energy-center footprint, entrance, parcel centroid or land extent. |  | Operator supplies no positional accuracy or survey statement; many decimal places are not measured accuracy. | 9b3dada3-b68b-5658-b9cb-f304c02dadb5 | under_construction | 2026-06-01 | 134 | authoritative_physical_status_update | b621ebef-cf6c-50a0-92aa-034354ef746b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://habr.com/ru/companies/cloud4y/articles/1058450/ | https://www.cloud4y.ru/contacts/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-1295b8a3ae3b2543ec97/#project-cbe9c330-13a3-5d1f-a9ba-c981c31585a7 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/cbe9c330-13a3-5d1f-a9ba-c981c31585a7.json
ccb7fe0e-f94d-58ca-8d36-695a9cd48d56 | curated:microsoft-mount-pleasant-datacenter-campus:second-facility | vcc-site-fcc06643c640f5d8cce2 | curated:microsoft-mount-pleasant-datacenter-campus | Microsoft Mount Pleasant Second Datacenter Facility | United States | US | 42.6765 | -87.9103 | Polygon | campus | cross_source_overlay | openstreetmap_named_construction_area_polygon_as_campus_locator | reviewed_openstreetmap_named_microsoft_fairwater_phase_2_construction_area_polygon | community_mapped | campus_locator | Contributor-mapped polygon for a named Microsoft Fairwater Phase 2 construction area, used only to locate the Mount Pleasant datacenter campus. It is not an official campus boundary, the complete campus extent, a parcel, a building footprint, the official second-facility footprint, a construction-progress extent, or a survey-accuracy claim. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not a cadastral or survey product. | ab38ac59-f17b-5f63-b060-392d2bebd078 | under_construction | 2026-06-23 | 112 | authoritative_construction_start | d7e6bc2e-63fd-5cb3-a118-03bec050c1e6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | tracked_identity_bound_uncertain_unsuperseded_no_construction_claim | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://news.microsoft.com/source/2026/06/23/microsoft-completes-construction-on-first-datacenter-facility-in-mount-pleasant-wisconsin/ | https://www.openstreetmap.org/way/1528490094 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fcc06643c640f5d8cce2/#project-ccb7fe0e-f94d-58ca-8d36-695a9cd48d56 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ccb7fe0e-f94d-58ca-8d36-695a9cd48d56.json
ce6cee07-15ea-56c9-83d5-c0cdb18aa695 | imported:semiconductor-atlas:atnorth-haugaland-nor01 | vcc-site-7b9b287883c887b86116 | imported:semiconductor-atlas:atnorth-haugaland-nor01 | atNorth NOR01 Haugaland mega site | Norway | NO | 59.3154 | 5.4252 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | atNorth names Haugaland Business Park in Tysvær; the business park was geocoded with OpenStreetMap, but the specific plot within it was not identified. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a66d9703-a215-5f0f-affb-7f70b07b491d | announced | 2026-06-09 | 126 | imported_documented_status | a66d9703-a215-5f0f-affb-7f70b07b491d | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a66d9703-a215-5f0f-affb-7f70b07b491d","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-haugaland-nor01"},{"evidence_id":"c6d01366-3477-5823-9314-6e6ff00b9436","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-haugaland-nor01"},{"evidence_id":"50f24591-2031-503f-ab5f-ad6cda332cac","notes":null,"party":"atNorth","relationship_scope":"unknown","role":"developer","source_record_id":"atnorth-haugaland-nor01"},{"evidence_id":"a66d9703-a215-5f0f-affb-7f70b07b491d","notes":"Transmission system operator building one of the substations serving the site.","party":"Statnett","relationship_scope":"unknown","role":"utility","source_record_id":"atnorth-haugaland-nor01"},{"evidence_id":"50f24591-2031-503f-ab5f-ad6cda332cac","notes":"Transmission system operator building one of the substations serving the site.","party":"Statnett","relationship_scope":"unknown","role":"utility","source_record_id":"atnorth-haugaland-nor01"},{"evidence_id":"a66d9703-a215-5f0f-affb-7f70b07b491d","notes":"Regional grid company building the other substation.","party":"Fagne","relationship_scope":"unknown","role":"utility","source_record_id":"atnorth-haugaland-nor01"},{"evidence_id":"50f24591-2031-503f-ab5f-ad6cda332cac","notes":"Regional grid company building the other substation.","party":"Fagne","relationship_scope":"unknown","role":"utility","source_record_id":"atnorth-haugaland-nor01"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.atnorth.com/news/atnorth-expands-to-norway-with-new-mega-site-in-haugaland/ | https://www.atnorth.com/news/atnorth-expands-to-norway-with-new-mega-site-in-haugaland/ | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve atNorth NOR01 Haugaland mega site as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"atnorth-haugaland-nor01"},"record":{"aliases":["NOR01","Haugaland mega site"],"id":"atnorth-haugaland-nor01","last_reviewed":"2026-10-09","location":{"admin1":"Rogaland","admin2":"Tysvær Municipality","country":"NO","lat":59.3154,"locality":"Haugaland Business Park","lon":5.4252,"note":"atNorth names Haugaland Business Park in Tysvær; the business park was geocoded with OpenStreetMap, but the specific plot within it was not identified.","precision":"approximate_site","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-03","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":350},{"applies_to":"phase","as_of":"2026-06-03","basis":"planned","metric":"power_capacity","phase_label":"Initial phases","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":120},{"applies_to":"campus","as_of":"2026-06-03","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1","s2"],"unit":"hectares","value":36},{"applies_to":"campus","as_of":"2026-06-03","basis":"planned","metric":"jobs_permanent","note":"People expected on site once the campus reaches full capacity.","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":200}],"milestones":[{"date":"2026-06-03","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2028","event":"other","kind":"planned","note":"Power availability for the site is projected for 2028.","source_ids":["s1","s3"]}],"name":"atNorth NOR01 Haugaland mega site","parties":[{"name":"atNorth","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Statnett","note":"Transmission system operator building one of the substations serving the site.","role":"utility","source_ids":["s1","s3"]},{"name":"Fagne","note":"Regional grid company building the other substation.","role":"utility","source_ids":["s1","s3"]}],"power_sources":[{"description":"Grid supply via new substations being built by Statnett and Fagne; atNorth's site page says renewable supply will be backed by certificates of origin from the energy provider.","source_ids":["s1","s2","s3"],"type":"grid"},{"description":"Standby generators fuelled with hydrotreated vegetable oil (HVO), with fuel storage for at least 24 hours of operation.","source_ids":["s2"],"type":"diesel_backup"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-06-03","publisher":"atNorth","title":"atNorth expands to Norway with new mega site in Haugaland","type":"company","url":"https://www.atnorth.com/news/atnorth-expands-to-norway-with-new-mega-site-in-haugaland/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260915051455/https://www.atnorth.com/nordic-data-centers/norway-data-centers/haugaland-nor01/","id":"s2","published":null,"publisher":"atNorth","title":"Haugaland mega site (NOR01)","type":"company","url":"https://www.atnorth.com/nordic-data-centers/norway-data-centers/haugaland-nor01/"},{"accessed":"2026-10-09","id":"s3","published":"2026-06-09","publisher":"RCRTech (RCR Wireless News)","title":"atNorth sees growing AI demand driving 350MW Norway DC campus","type":"trade_press","url":"https://rcrtech.com/ai-infrastructure-news/atnorth-ai-demand-norway/"}],"status":"announced","status_as_of":"2026-06-09","status_source_ids":["s1","s3"],"summary":"Nordic data center operator atNorth announced in June 2026 its first Norwegian campus, NOR01, on a 36-hectare plot in Haugaland Business Park in Tysvær, western Norway. Initial phases are planned at 120 MW, ramping up to 350 MW, with power availability projected for 2028 once Statnett and regional grid company Fagne complete new substations. atNorth markets the site for high-density AI, machine learning, cloud and HPC workloads, including build-to-suit projects, and expects about 200 people to work there at full capacity. No investment figure or customers have been disclosed.","workloads":["ai_training","ai_inference","cloud","hpc","colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a66d9703-a215-5f0f-affb-7f70b07b491d","s2":"c6d01366-3477-5823-9314-6e6ff00b9436","s3":"50f24591-2031-503f-ab5f-ad6cda332cac"},"source_file":"datacenters/projects/atnorth-haugaland-nor01.json","source_record_id":"atnorth-haugaland-nor01","source_record_sha256":"12639e844d7f54ef73aadb4f463f6b23855963c6f42938e98f9d11f1bdcde636","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0e23df66801d383feec8e86c8dc5fcceccfd0906ed6b26d498cadd6b6c7dd286"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7b9b287883c887b86116/#project-ce6cee07-15ea-56c9-83d5-c0cdb18aa695 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ce6cee07-15ea-56c9-83d5-c0cdb18aa695.json
cf028790-cea6-555d-a3bb-48e08ff78f3b | curated:cyrusone-aurora-diehl-road-campus:chi2-sound-mitigation-capital-retrofit | vcc-site-d5d70748e492c5e2278a | curated:cyrusone-aurora-diehl-road-campus | CyrusOne Aurora CHI2 Permanent Sound-Mitigation Capital Retrofit | United States | US | 41.7981 | -88.2434 | Point | campus | official_census_street_address_range_interpolation | exact_state_named_campus_address_Census_NAD83_to_WGS84_pyproj_3_8_0 | official_campus_street_address_locator | official_source | campus_locator | Exact source-bound campus address interpolated along Diehl Road. This is not the CHI2 rooftop work site, surveyed building position, campus interior, parcel boundary or construction footprint. The state campus address locates the shared CHI1-CHI3 campus once. |  | Census supplies no site-specific accuracy for this address-range interpolation. | f1342044-d585-5e7f-8596-2af4ecf75928 | under_construction | 2026-08-20 | 54 | authoritative_physical_status_update | d4e9cd1f-158c-59ab-808a-20ede57c862b | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.cyrusone.com/data-centers/north-america/aurora-il-back-up-generator-schedule | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=2905%20Diehl%20Road%2C%20Aurora%2C%20IL%2060502&benchmark=Public_AR_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d5d70748e492c5e2278a/#project-cf028790-cea6-555d-a3bb-48e08ff78f3b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/cf028790-cea6-555d-a3bb-48e08ff78f3b.json
d024514a-30a3-514d-b65e-2743133f6800 | curated:hyperco-loviisa-data-center-campus:current-development | vcc-site-2205657258ac3679cfaa | curated:hyperco-loviisa-data-center-campus | Hyperco Loviisa Current Data Center Development | Finland | FI | 60.4744 | 26.2681 | Point | building | direct_geometry | ryhti_official_permit_building_point_as_project_locator | official_permit_building_reference_point | official_source | project_locator | Ryhti point for permanent building 104259934N cross-identified to the Hyperco permit by permanent permit, property, decision date, and gross floor area. It is a project locator, not a building footprint, parcel, campus, entrance, survey point, or work-at-point claim. |  | Ryhti supplies no collection method, reference-feature definition, or bounded numeric horizontal-accuracy value for the building point. | a1f1c613-7606-5e9d-baf9-31cdb38d34f0 | under_construction | 2026-07-02 | 103 | authoritative_physical_status_update | 6a06bae8-a0c9-59d5-8c19-e82b2dc4e1eb | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.15 global geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.loviisa.fi/ajankohtaista/meluavat-tyot-datakeskuksen-tyomaalla-jatkuvat/ | https://paikkatiedot.ymparisto.fi/geoserver/ryhti_permit/ogc/features/v1/collections/open_permit_building/items?f=application%2Fgeo%2Bjson&filter=permanent_permit_identifier%3D%27302396994R%27%20AND%20gross_floor_area%3D24145&limit=10 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2205657258ac3679cfaa/#project-d024514a-30a3-514d-b65e-2743133f6800 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d024514a-30a3-514d-b65e-2743133f6800.json
d1538d73-e301-5203-9e49-924b20051374 | curated:meta-sturgeon-county-alberta-data-center:current-campus-build | vcc-site-b8522efc1a60fe3072e4 | curated:meta-sturgeon-county-alberta-data-center | Meta Sturgeon County Alberta Current Campus Build | Canada | CA | 53.8181 | -113.1867 | Point | project | official_parcel_union | official_permit_units_representative_point | representative_point_of_partial_permit_envelope | official_source | project_locator | Representative point of the deterministic union of 11 official ATS quarter sections named by DP-26-0028; Shapely 2.1.2/GEOS 3.13.1 unary_union followed by representative_point. It is a partial permit-envelope locator, not the full project boundary, parcel survey, building, or work area. |  | The selected permit units include road allowances and non-quarter cadastral identifiers that are not represented by the 11 queried quarter-section polygons. | e049970c-d467-5fc5-9e5c-6660606eb9be | under_construction | 2026-07-08 | 97 | authoritative_construction_start | 420301bd-49ca-5323-8bea-6109ff72a96f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"51ec093e-0bd2-51f0-8340-cd824b4756ff","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-sturgeon-county"},{"evidence_id":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-sturgeon-county"},{"evidence_id":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","notes":"General contractor; a joint venture of Clark Builders and PCL Construction.","party":"Frost Collective","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"8b8340df-2be1-5be2-9dab-567c1d87b23d","notes":"General contractor; a joint venture of Clark Builders and PCL Construction.","party":"Frost Collective","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","notes":null,"party":"Clark Builders","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"8b8340df-2be1-5be2-9dab-567c1d87b23d","notes":null,"party":"Clark Builders","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"d45eeb39-18f9-52cf-8f67-052ed8d11a2c","notes":null,"party":"Clark Builders","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","notes":null,"party":"PCL Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"8b8340df-2be1-5be2-9dab-567c1d87b23d","notes":null,"party":"PCL Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"d45eeb39-18f9-52cf-8f67-052ed8d11a2c","notes":null,"party":"PCL Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-sturgeon-county"},{"evidence_id":"51ec093e-0bd2-51f0-8340-cd824b4756ff","notes":"Named by Meta as an energy-planning partner; supply terms not disclosed.","party":"AltaLink","relationship_scope":"unknown","role":"utility","source_record_id":"meta-sturgeon-county"},{"evidence_id":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","notes":"Named by Meta as an energy-planning partner; supply terms not disclosed.","party":"AltaLink","relationship_scope":"unknown","role":"utility","source_record_id":"meta-sturgeon-county"},{"evidence_id":"8b8340df-2be1-5be2-9dab-567c1d87b23d","notes":"Named by Meta as an energy-planning partner; supply terms not disclosed.","party":"AltaLink","relationship_scope":"unknown","role":"utility","source_record_id":"meta-sturgeon-county"},{"evidence_id":"51ec093e-0bd2-51f0-8340-cd824b4756ff","notes":"Named by Meta as an energy-planning partner; supply terms not disclosed.","party":"Greenlight Limited Partnership","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-sturgeon-county"},{"evidence_id":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","notes":"Named by Meta as an energy-planning partner; supply terms not disclosed.","party":"Greenlight Limited Partnership","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-sturgeon-county"},{"evidence_id":"8b8340df-2be1-5be2-9dab-567c1d87b23d","notes":"Named by Meta as an energy-planning partner; supply terms not disclosed.","party":"Greenlight Limited Partnership","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-sturgeon-county"},{"evidence_id":"51ec093e-0bd2-51f0-8340-cd824b4756ff","notes":"Named by Meta as an energy-planning partner (spelled Capitol Power in the newsroom post); supply terms not disclosed.","party":"Capital Power","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-sturgeon-county"},{"evidence_id":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","notes":"Named by Meta as an energy-planning partner (spelled Capitol Power in the newsroom post); supply terms not disclosed.","party":"Capital Power","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-sturgeon-county"},{"evidence_id":"8b8340df-2be1-5be2-9dab-567c1d87b23d","notes":"Named by Meta as an energy-planning partner (spelled Capitol Power in the newsroom post); supply terms not disclosed.","party":"Capital Power","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-sturgeon-county"},{"evidence_id":"8b8340df-2be1-5be2-9dab-567c1d87b23d","notes":"Meta says it pays the county the full cost of water and wastewater service.","party":"Sturgeon County","relationship_scope":"unknown","role":"government","source_record_id":"meta-sturgeon-county"}] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://about.fb.com/news/2026/07/breaking-ground-on-metas-first-data-center-in-canada/ | https://geospatial.alberta.ca/titan/rest/services/ags_apps/ags_apps_alberta_township_system/MapServer/2/query | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same Meta first Canadian campus in Sturgeon County; the exact Meta groundbreaking URL is shared. The source county centroid is not the permit-located site. Nearby Beacon Heartland is a separate project.","source_record_id":"meta-sturgeon-county","target_project_stable_key":"curated:meta-sturgeon-county-alberta-data-center:current-campus-build"},"record":{"aliases":["Sturgeon Data Centre"],"id":"meta-sturgeon-county","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","admin2":"Sturgeon County","country":"CA","lat":53.8422,"lon":-113.5407,"note":"County point from OpenStreetMap Nominatim; Meta names Sturgeon County but no specific site, and the project website places it in the Edmonton region.","precision":"admin2","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-08","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Appears only in the project website's page description metadata, not its visible text, as read on 2026-10-09; conflicts with Meta's 1 GW announcement.","power_scope":"unspecified","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":1600},{"applies_to":"campus","as_of":"2026-07-08","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"CAD","value":13000000000},{"applies_to":"campus","as_of":"2026-07-08","basis":"planned","metric":"jobs_construction","note":"Peak construction workforce. The fact sheet also says the general contractor will manage more than 3,000 workers at peak, and the project website gives more than 3,000.","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"count","value":3000},{"applies_to":"campus","as_of":"2026-07-08","basis":"planned","metric":"jobs_permanent","note":"Meta's fact sheet gives about 300.","qualifier":"more_than","source_ids":["s1","s2"],"unit":"count","value":300}],"milestones":[{"date":"2026-07-08","event":"announced","kind":"actual","note":"Meta described it as its first data center in Canada.","source_ids":["s1","s2"]},{"date":"2026-07","event":"construction_started","kind":"actual","note":"Meta announced the groundbreaking on 2026-07-08; the exact start of site works is not given.","source_ids":["s1"]}],"name":"Meta Sturgeon data centre","notes":"Meta's fact sheet PDF (s3) shows no publication date; its embedded file creation date is in early September 2026. The project website (s4) is undated; its 1.6 GW figure carries the date it was read (2026-10-09).","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Frost Collective","note":"General contractor; a joint venture of Clark Builders and PCL Construction.","role":"builder","source_ids":["s2","s3"]},{"name":"Clark Builders","role":"builder","source_ids":["s2","s3","s4"]},{"name":"PCL Construction","role":"builder","source_ids":["s2","s3","s4"]},{"name":"AltaLink","note":"Named by Meta as an energy-planning partner; supply terms not disclosed.","role":"utility","source_ids":["s1","s2","s3"]},{"name":"Greenlight Limited Partnership","note":"Named by Meta as an energy-planning partner; supply terms not disclosed.","role":"power_supplier","source_ids":["s1","s2","s3"]},{"name":"Capital Power","note":"Named by Meta as an energy-planning partner (spelled Capitol Power in the newsroom post); supply terms not disclosed.","role":"power_supplier","source_ids":["s1","s2","s3"]},{"name":"Sturgeon County","note":"Meta says it pays the county the full cost of water and wastewater service.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"Meta says it planned its energy needs with Greenlight Limited Partnership, AltaLink, Capital Power and the Alberta Electric System Operator, is fully funding new generation and grid infrastructure in Alberta, and will match the site's electricity use with clean energy. The generation type is not specified.","source_ids":["s1","s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004070212/https://about.fb.com/news/2026/07/breaking-ground-on-metas-first-data-center-in-canada/","id":"s1","published":"2026-07-08","publisher":"Meta Platforms","title":"Breaking Ground on Meta's First Data Center in Canada","type":"company","url":"https://about.fb.com/news/2026/07/breaking-ground-on-metas-first-data-center-in-canada/"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-08","publisher":"Meta Platforms","title":"Hello, Sturgeon County!","type":"company","url":"https://datacenters.atmeta.com/2026/07/hello-sturgeon-county/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Meta Platforms","title":"Meta Sturgeon Data Centre fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Metas-Sturgeon-Data-Center.pdf"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Sturgeon Data Centre project website","title":"Sturgeon Data Centre","type":"company","url":"https://sturgeondatacentre.com"}],"status":"under_construction","status_as_of":"2026-07-08","status_source_ids":["s1"],"summary":"Meta's first data centre in Canada, a 1 GW campus optimized for its AI workloads in Sturgeon County, Alberta, in the Edmonton region, with more than CA$13 billion of planned investment. Meta announced the groundbreaking in July 2026. Meta says it is fully funding new generation and grid infrastructure in Alberta and names Greenlight Limited Partnership, AltaLink, Capital Power and the Alberta Electric System Operator as energy-planning partners. Frost Collective, a joint venture of Clark Builders and PCL Construction, is the general contractor. The project website's page description cites 1.6 GW, which differs from Meta's 1 GW figure.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"51ec093e-0bd2-51f0-8340-cd824b4756ff","s2":"0702ec92-61c9-595f-a8dc-bb25e0186aa1","s3":"8b8340df-2be1-5be2-9dab-567c1d87b23d","s4":"d45eeb39-18f9-52cf-8f67-052ed8d11a2c"},"source_file":"datacenters/projects/meta-sturgeon-county.json","source_record_id":"meta-sturgeon-county","source_record_sha256":"b5f2331db09e9949bd4b7edfc68469145bbe29ee0ecd55917d535b96345275e1","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d0ae668e45f579791ab709030d30b6d4fe85af0b8eb74a9c96bd855c9a6a23eb"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b8522efc1a60fe3072e4/#project-d1538d73-e301-5203-9e49-924b20051374 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d1538d73-e301-5203-9e49-924b20051374.json
d2915b77-394c-5202-8c38-cbd3277121c7 | curated:digital-edge-seoul-bupyeong-campus:sel3-phase-2 | vcc-site-5750ea0ecd6d7c900211 | curated:digital-edge-seoul-bupyeong-campus | Digital Edge SEL3 Phase 2 | Korea, Republic of | KR | 37.518 | 126.7109 | Point | campus | cross_source_geometry | first_party_sel2_specification_point_to_cross_source_shared_sel2_sel3_campus_locator | official_source_reported_adjacent_facility_point_used_as_shared_campus_locator | official_source | campus_locator | The point is the first-party SEL2 facility coordinate and may be spatially offset from SEL3. It is a shared-campus locator only, not a SEL3 project point, campus centroid, footprint, parcel, building outline, construction extent, or boundary. |  | The specification does not state datum, reference feature, collection method, or horizontal accuracy. | adac0b2c-575b-5ec5-a0d8-bed593fc3c20 | under_construction | 2026-07-09 | 96 | authoritative_physical_status_update | 4319b4ff-25cd-51ce-bf9b-e17197ff1fbf | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-07-09","base":60.0,"confidence":0.99,"evidence_id":"4319b4ff-25cd-51ce-bf9b-e17197ff1fbf","high":60.0,"low":60.0,"method":"reported","metric":"critical_it_mw","notes":"Reported 60 MW IT capacity for the current SEL3/Bupyeong phase-2 project, normalized once as planned critical IT capacity. The nested 96 MW SEL2-plus-SEL3 campus total is not added. This is not grid capacity, gross facility demand, generation, energized or current load, annual energy, consumption, or PUE, and no conversion is made.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://news.skecoplant.com/board/19247 | https://www.digitaledgedc.com/wp-content/uploads/2023/06/SEL2_Specsheet_EN.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5750ea0ecd6d7c900211/#project-d2915b77-394c-5202-8c38-cbd3277121c7 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d2915b77-394c-5202-8c38-cbd3277121c7.json
d2bf7339-8e09-50df-8229-96ad3f8fa358 | imported:semiconductor-atlas:applied-digital-delta-forge-2 | vcc-site-8d354596ddb2508a0eda | imported:semiconductor-atlas:applied-digital-delta-forge-2 | Applied Digital Delta Forge 2 | United States | US | 33.2397 | -87.3278 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Local reports place the campus north of the 17000 block of Brookwood Parkway. No geocoder was used; coordinates are the Brookwood city point from its Wikipedia article. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ab72ef7f-022c-58c6-87fb-9002d3f55b74 | under_construction | 2026-10-07 | 6 | imported_documented_status | 9742cc25-a6af-549d-ac0a-6d1f3d33f499 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"59ac7964-e31e-5810-bb0f-5cc411d54e0c","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-delta-forge-2"},{"evidence_id":"9742cc25-a6af-549d-ac0a-6d1f3d33f499","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-delta-forge-2"},{"evidence_id":"ab72ef7f-022c-58c6-87fb-9002d3f55b74","notes":null,"party":"Applied Digital","relationship_scope":"unknown","role":"developer","source_record_id":"applied-digital-delta-forge-2"},{"evidence_id":"ab72ef7f-022c-58c6-87fb-9002d3f55b74","notes":"Signed off on the project in September 2026; Applied Digital committed USD 270 million in community benefit payments to the authority over 20 years.","party":"Tuscaloosa County Economic Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"applied-digital-delta-forge-2"},{"evidence_id":"28f7a83e-130e-5334-b341-8165c439b288","notes":"Signed off on the project in September 2026; Applied Digital committed USD 270 million in community benefit payments to the authority over 20 years.","party":"Tuscaloosa County Economic Development Authority","relationship_scope":"unknown","role":"government","source_record_id":"applied-digital-delta-forge-2"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.sec.gov/Archives/edgar/data/0001144879/000114487926000057/apldq127earningsrelease.htm | https://abc3340.com/news/local/alabama-32-billion-ai-data-center-campus-announced-in-brookwood-brookwood-mayor-joe-barger-september-2026 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Applied Digital Delta Forge 2 as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"applied-digital-delta-forge-2"},"record":{"aliases":["Delta Forge 2 AI Factory"],"id":"applied-digital-delta-forge-2","last_reviewed":"2026-10-09","location":{"admin1":"Alabama","admin2":"Tuscaloosa County","country":"US","lat":33.2397,"locality":"Brookwood","lon":-87.3278,"note":"Local reports place the campus north of the 17000 block of Brookwood Parkway. No geocoder was used; coordinates are the Brookwood city point from its Wikipedia article.","precision":"locality","source_ids":["s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-08","basis":"contracted","metric":"power_capacity","note":"Critical IT load leased for 15 years to an unnamed US high investment-grade hyperscaler; the release puts base-term revenue at about USD 5.2 billion.","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":210},{"applies_to":"campus","as_of":"2026-09-24","basis":"incentive_agreement","metric":"investment","note":"Initial capital investment figure reported with the local incentive package; reports also round it to more than USD 3.2 billion from Applied Digital and its tenant.","qualifier":"approximately","source_ids":["s3","s4"],"unit":"USD","value":3286500000},{"applies_to":"campus","as_of":"2026-09-24","basis":"planned","metric":"floor_area","note":"An earlier state environmental permit application had described about 2 million square feet.","qualifier":"approximately","source_ids":["s3","s4"],"unit":"sq_ft","value":1260000},{"applies_to":"campus","as_of":"2026-09-24","basis":"planned","metric":"land_area","note":"Campus footprint within a site of nearly 1,300 acres.","qualifier":"approximately","source_ids":["s3","s4"],"unit":"acres","value":160},{"applies_to":"campus","as_of":"2026-09-24","basis":"planned","metric":"jobs_construction","note":"Expected peak construction workforce.","qualifier":"more_than","source_ids":["s3","s4"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2026-09-24","basis":"planned","metric":"jobs_permanent","qualifier":"exact","source_ids":["s3"],"unit":"count","value":101}],"milestones":[{"date":"2026-06-08","event":"announced","kind":"actual","note":"Applied Digital announced the 210 MW lease at Delta Forge 2 in an unnamed southern state.","source_ids":["s1"]},{"date":"2026-07-20","event":"permit_approved","kind":"actual","note":"Alabama's Department of Environmental Management approved a permit application for a data center in Brookwood, later confirmed as this project.","source_ids":["s4"]},{"date":"2026-09-24","event":"other","kind":"actual","note":"Applied Digital confirmed the Brookwood location and the county economic development authority approved the incentive package.","source_ids":["s3","s4"]},{"date":"2026-10-01","event":"construction_started","kind":"planned","note":"Scheduled construction start reported with the incentive terms; the company's 7 October 2026 results list the campus as under construction.","source_ids":["s3","s2"]},{"date":"2028-Q1","event":"first_operational","kind":"planned","note":"Anticipated start of initial operations; local reporting gives completion by the end of 2028.","source_ids":["s1","s3"]}],"name":"Applied Digital Delta Forge 2","notes":"The tenant is not named; Applied Digital says it is the same US high investment-grade hyperscaler as two of its other leases. Renewal options could lift lease revenue to about USD 12.7 billion over a 30-year total term. The June 2026 release describes proprietary waterless cooling for the campus. No source opened names the utility or a dedicated power arrangement for the campus. Local reports put 20-year taxes and community payments at about USD 440.7 million, against about USD 314.5 million in tax abatements.","parties":[{"name":"Applied Digital","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Tuscaloosa County Economic Development Authority","note":"Signed off on the project in September 2026; Applied Digital committed USD 270 million in community benefit payments to the authority over 20 years.","role":"government","source_ids":["s3","s4"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006090244/https://ir.applieddigital.com/news-events/press-releases/detail/154/applied-digital-signs-210-mw-lease-at-delta-forge-2","id":"s1","published":"2026-06-08","publisher":"Applied Digital","title":"Applied Digital signs 210 MW lease at Delta Forge 2, expanding its AI factory franchise model to a fifth campus","type":"company","url":"https://ir.applieddigital.com/news-events/press-releases/detail/154/applied-digital-signs-210-mw-lease-at-delta-forge-2"},{"accessed":"2026-10-09","id":"s2","published":"2026-10-07","publisher":"Applied Digital via SEC EDGAR","title":"Applied Digital reports fiscal first quarter 2027 results (Form 8-K exhibit)","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/0001144879/000114487926000057/apldq127earningsrelease.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004090303/https://abc3340.com/news/local/alabama-32-billion-ai-data-center-campus-announced-in-brookwood-brookwood-mayor-joe-barger-september-2026","id":"s3","published":"2026-09-24","publisher":"ABC 33/40","title":"$3.2 billion AI data center campus announced in Brookwood","type":"news","url":"https://abc3340.com/news/local/alabama-32-billion-ai-data-center-campus-announced-in-brookwood-brookwood-mayor-joe-barger-september-2026"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-24","publisher":"FOX10 News","title":"Applied Digital confirms $3.2 billion data center campus in Brookwood","type":"news","url":"https://www.fox10tv.com/2026/09/25/applied-digital-confirms-32-billion-data-center-campus-brookwood/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260910031829/https://en.wikipedia.org/wiki/Brookwood,_Alabama","id":"s5","published":null,"publisher":"Wikipedia","title":"Brookwood, Alabama","type":"other","url":"https://en.wikipedia.org/wiki/Brookwood,_Alabama"}],"status":"under_construction","status_as_of":"2026-10-07","status_source_ids":["s2","s3"],"summary":"Applied Digital's fifth AI factory campus, on about 160 acres of a nearly 1,300-acre site north of Brookwood Parkway in Brookwood, Tuscaloosa County, Alabama. In June 2026 the company announced a 15-year lease of 210 MW of critical IT load to an unnamed US high investment-grade hyperscaler, worth about USD 5.2 billion in base-term revenue, naming only a southern state. Applied Digital confirmed the Brookwood site in September 2026; local reports gave an initial capital investment of about USD 3.29 billion and about 1.26 million square feet of data center space. Construction was set to begin on 1 October 2026, with initial operations expected in Q1 2028.","workloads":["ai_training","ai_inference"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"59ac7964-e31e-5810-bb0f-5cc411d54e0c","s2":"9742cc25-a6af-549d-ac0a-6d1f3d33f499","s3":"ab72ef7f-022c-58c6-87fb-9002d3f55b74","s4":"28f7a83e-130e-5334-b341-8165c439b288","s5":"ced17f4a-2e44-55a4-915d-64c16ed1cfd1"},"source_file":"datacenters/projects/applied-digital-delta-forge-2.json","source_record_id":"applied-digital-delta-forge-2","source_record_sha256":"3f77543f5729096edee3c5ffc6f3c7c95c63e56ffc896f2abb25148735d8af6c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b03b12cab07c4066e18d739678497dce456d5b49fe18a96ae318d911486a5d5d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8d354596ddb2508a0eda/#project-d2bf7339-8e09-50df-8229-96ad3f8fa358 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d2bf7339-8e09-50df-8229-96ad3f8fa358.json
d2db6863-886a-5c16-b819-7f2cd95cd87e | imported:semiconductor-atlas:xai-colossus-memphis | vcc-site-837c77c61e73b3c11714 | imported:semiconductor-atlas:xai-colossus-memphis | xAI Colossus 1 (Memphis) | United States | US | 35.0599 | -90.1563 | Point | project | imported_reference_point | imported_reference_point | site | compiled_reference | project_locator | Center of the OpenStreetMap building tagged 'xAI Colossus' at 3231 Paul R. Lowery Road, taken from this project's OpenStreetMap data center layer (no geocoder call). The address comes from Cleanview and from Memphis Business Journal reporting cited by WMC; MLGW places the facility in the former Electrolux plant in Frank C. Pidgeon Industrial Park. Shelby County is the jurisdiction of the health department that permitted the site's turbines. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f683c140-2c68-543f-bc1a-5b12f7daf9b1 | operational | 2026-10-05 | 8 | imported_documented_status | 7cf2e42d-a04c-5b5d-836e-ad424e0a8ae2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f683c140-2c68-543f-bc1a-5b12f7daf9b1","notes":null,"party":"xAI","relationship_scope":"unknown","role":"developer","source_record_id":"xai-colossus-memphis"},{"evidence_id":"df2e369e-60d0-59f2-935a-60748757247c","notes":null,"party":"xAI","relationship_scope":"unknown","role":"developer","source_record_id":"xai-colossus-memphis"},{"evidence_id":"15bf3257-b23b-5081-8705-5882f10baedb","notes":null,"party":"xAI","relationship_scope":"unknown","role":"developer","source_record_id":"xai-colossus-memphis"},{"evidence_id":"7cf2e42d-a04c-5b5d-836e-ad424e0a8ae2","notes":"Anthropic's May 2026 announcement refers to Colossus 1 as SpaceX's data center, and Epoch AI (analyst) lists the owner as SpaceXAI; no company filing reviewed states ownership.","party":"SpaceX","relationship_scope":"unknown","role":"owner","source_record_id":"xai-colossus-memphis"},{"evidence_id":"645ec7d3-9369-5624-9eb3-c4c9e3c39c99","notes":"Anthropic's May 2026 announcement refers to Colossus 1 as SpaceX's data center, and Epoch AI (analyst) lists the owner as SpaceXAI; no company filing reviewed states ownership.","party":"SpaceX","relationship_scope":"unknown","role":"owner","source_record_id":"xai-colossus-memphis"},{"evidence_id":"7cf2e42d-a04c-5b5d-836e-ad424e0a8ae2","notes":"Agreed in May 2026 to use all of the compute capacity at Colossus 1.","party":"Anthropic","relationship_scope":"unknown","role":"tenant","source_record_id":"xai-colossus-memphis"},{"evidence_id":"df2e369e-60d0-59f2-935a-60748757247c","notes":null,"party":"Memphis Light, Gas and Water","relationship_scope":"unknown","role":"utility","source_record_id":"xai-colossus-memphis"},{"evidence_id":"df2e369e-60d0-59f2-935a-60748757247c","notes":"TVA's board approved the first 150 MW of grid service; MLGW said a decision on a second 150 MW was pending in May 2025.","party":"Tennessee Valley Authority","relationship_scope":"unknown","role":"power_supplier","source_record_id":"xai-colossus-memphis"},{"evidence_id":"d6e9775e-6cfe-5712-bd65-c6fe3b73db0d","notes":"Approved the July 2025 air permit for 15 permanent on-site gas turbines.","party":"Shelby County Health Department","relationship_scope":"unknown","role":"government","source_record_id":"xai-colossus-memphis"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | SpaceX |  |  | Anthropic |  | https://www.anthropic.com/news/higher-limits-spacex | https://www.actionnews5.com/2024/06/05/elon-musk-build-multi-billion-dollar-ai-supercomputer-project-memphis/ | [{"identity_decision":{"decision":"unique_site","flags":["source_site_point_not_surveyed_boundary"],"rationale":"No matching named development in the 201-project release. Preserve xAI Colossus 1 (Memphis) as an independent source record; its site locator does not itself establish a surveyed physical site.","source_record_id":"xai-colossus-memphis"},"record":{"aliases":["Colossus","Colossus 1","Gigafactory of Compute"],"id":"xai-colossus-memphis","last_reviewed":"2026-10-09","location":{"admin1":"Tennessee","admin2":"Shelby County","country":"US","lat":35.0599,"locality":"Memphis","lon":-90.1563,"note":"Center of the OpenStreetMap building tagged 'xAI Colossus' at 3231 Paul R. Lowery Road, taken from this project's OpenStreetMap data center layer (no geocoder call). The address comes from Cleanview and from Memphis Business Journal reporting cited by WMC; MLGW places the facility in the former Electrolux plant in Frank C. Pidgeon Industrial Park. Shelby County is the jurisdiction of the health department that permitted the site's turbines.","precision":"site","source_ids":["s1","s2","s3","s7"]},"metrics":[{"applies_to":"campus","as_of":"2025-05-05","basis":"operational","metric":"power_capacity","note":"Delivered through an existing MLGW substation (8 MW) and a new substation funded by xAI (142 MW).","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":150},{"applies_to":"campus","as_of":"2025-05-05","basis":"planned","metric":"power_capacity","note":"Total of two successive 150 MW requests; MLGW expected to supply the second 150 MW by December 2025 if TVA approved it.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-05-06","basis":"contracted","metric":"power_capacity","note":"Capacity covered by Anthropic's agreement; the announcement does not say whether this is IT load or total power.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s5"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2026-06-15","basis":"operational","metric":"power_capacity","note":"Epoch AI analyst estimate, not a company disclosure, based on satellite imagery and public information. Epoch shows this level from July 22, 2025 through its latest observation on June 15, 2026.","power_scope":"it_load","qualifier":"approximately","source_ids":["s6"],"unit":"MW","value":340},{"applies_to":"campus","as_of":"2026-05","basis":"operational","metric":"power_capacity","note":"Cleanview count of 12 Solar SMT-130 gas turbines of about 16.5 MW each in May 2026 imagery; Cleanview says temporary turbines are being removed. This is an analyst estimate, not a company disclosure.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s7"],"unit":"MW","value":198},{"accelerator_model":"NVIDIA GPUs (models not specified)","applies_to":"campus","as_of":"2026-05-06","basis":"installed","metric":"accelerators","note":"Count from Anthropic. Epoch AI estimates about 230,000 chips: 150,000 H100, 50,000 H200 and 30,000 B200 in GB200 configuration (analyst estimate, not a company disclosure).","qualifier":"more_than","source_ids":["s5","s6"],"unit":"count","value":220000},{"applies_to":"campus","as_of":"2026-10-05","basis":"reported","metric":"investment","note":"Epoch AI capital cost estimate (analyst estimate, not a company disclosure); the page does not say what the figure includes.","qualifier":"approximately","source_ids":["s6"],"unit":"USD","value":12900000000}],"milestones":[{"date":"2024-04","event":"construction_started","kind":"actual","note":"Epoch AI dates the start of work at the former Electrolux building, when a road was added on site, to April 24, 2024 from satellite imagery (analyst estimate, not a company disclosure).","source_ids":["s6"]},{"date":"2024-06-05","event":"announced","kind":"actual","note":"The Greater Memphis Chamber announced the project without naming the site.","source_ids":["s1"]},{"date":"2024-08","event":"first_operational","kind":"actual","note":"Epoch AI reports the first training workload, on about 25,000 H100 GPUs, on August 11, 2024 (analyst estimate, not a company disclosure).","source_ids":["s6"]},{"date":"2025-07","event":"permit_approved","kind":"actual","note":"Shelby County Health Department approved an air permit for 15 permanent natural gas turbines; WMC reported it on July 2, 2025 without an exact approval date, and Cleanview confirms the site was permitted for 15 turbines.","source_ids":["s3","s7"]},{"date":"2026-05-06","event":"other","kind":"actual","note":"Anthropic announced an agreement to use all of the compute capacity at Colossus 1.","source_ids":["s5"]}],"name":"xAI Colossus 1 (Memphis)","parties":[{"name":"xAI","role":"developer","source_ids":["s1","s2","s4"]},{"name":"SpaceX","note":"Anthropic's May 2026 announcement refers to Colossus 1 as SpaceX's data center, and Epoch AI (analyst) lists the owner as SpaceXAI; no company filing reviewed states ownership.","role":"owner","source_ids":["s5","s6"]},{"name":"Anthropic","note":"Agreed in May 2026 to use all of the compute capacity at Colossus 1.","role":"tenant","source_ids":["s5"]},{"name":"Memphis Light, Gas and Water","role":"utility","source_ids":["s2"]},{"name":"Tennessee Valley Authority","note":"TVA's board approved the first 150 MW of grid service; MLGW said a decision on a second 150 MW was pending in May 2025.","role":"power_supplier","source_ids":["s2"]},{"name":"Shelby County Health Department","note":"Approved the July 2025 air permit for 15 permanent on-site gas turbines.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"MLGW and TVA grid service of 150 MW in May 2025 via an existing and a new xAI-funded substation, with a second 150 MW requested; xAI agreed to curtail grid use during peak demand.","source_ids":["s2"],"type":"grid"},{"description":"Shelby County permitted 15 permanent gas turbines in July 2025; Cleanview estimated about 198 MW from 12 turbines in May 2026 imagery (analyst estimate).","source_ids":["s3","s7"],"type":"natural_gas_onsite"},{"description":"Cleanview counts roughly 119 Tesla Megapack units, about 120 MW, from satellite imagery (analyst estimate).","source_ids":["s7"],"type":"battery_storage"}],"related_ids":["xai-colossus-2-memphis","xai-macrohardrr-southaven"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260708100208/https://www.actionnews5.com/2024/06/05/elon-musk-build-multi-billion-dollar-ai-supercomputer-project-memphis/","id":"s1","published":"2024-06-05","publisher":"WMC Action News 5","title":"Elon Musk's xAI to build multi-billion-dollar supercomputer project in Memphis","type":"news","url":"https://www.actionnews5.com/2024/06/05/elon-musk-build-multi-billion-dollar-ai-supercomputer-project-memphis/"},{"accessed":"2026-10-09","id":"s2","published":"2025-05-05","publisher":"Memphis Light, Gas and Water","title":"MLGW update regarding utility support for xAI","type":"utility","url":"https://www.mlgw.com/images/content/files/pdf/new/5-5-25%20xAI%20Update.pdf"},{"accessed":"2026-10-09","id":"s3","published":"2025-07-02","publisher":"WMC Action News 5","title":"Health dept. grants permit for xAI turbines","type":"news","url":"https://www.actionnews5.com/2025/07/02/health-dept-grants-permit-xai-turbines/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260228134904/https://www.actionnews5.com/2026/01/07/xai-raises-billions-dollars-expansion-amid-rapid-growth-memphis-metro/","id":"s4","published":"2026-01-07","publisher":"WMC Action News 5","title":"xAI raises billions of dollars for expansion amid rapid growth in Memphis metro","type":"news","url":"https://www.actionnews5.com/2026/01/07/xai-raises-billions-dollars-expansion-amid-rapid-growth-memphis-metro"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003122220/https://www.anthropic.com/news/higher-limits-spacex","id":"s5","published":"2026-05-06","publisher":"Anthropic","title":"Higher usage limits for Claude and a compute deal with SpaceX","type":"company","url":"https://www.anthropic.com/news/higher-limits-spacex"},{"accessed":"2026-10-09","id":"s6","published":"2026-10-05","publisher":"Epoch AI","title":"Colossus 1 ¦ AI data centers","type":"analyst","url":"https://epoch.ai/data/ai-data-centers/directory/colossus-1"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Cleanview","title":"Colossus 1 & 2 ¦ Behind-the-Meter Data Centers","type":"analyst","url":"https://cleanview.co/reports/behind-the-meter-data-centers/full-report/colossus"}],"status":"operational","status_as_of":"2026-10-05","status_source_ids":["s5","s6"],"summary":"AI supercomputer that xAI built in 2024 inside the former Electrolux manufacturing plant on Paul R. Lowry Road in southwest Memphis. Grid power comes from MLGW and TVA through an existing MLGW substation and a new one paid for by xAI, supplemented by permitted on-site gas turbines and battery storage. Anthropic now describes Colossus 1 as SpaceX's data center, and in May 2026 it agreed to use all of the site's compute capacity, stated as more than 300 MW and over 220,000 NVIDIA GPUs.","workloads":["ai_training","ai_inference"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f683c140-2c68-543f-bc1a-5b12f7daf9b1","s2":"df2e369e-60d0-59f2-935a-60748757247c","s3":"d6e9775e-6cfe-5712-bd65-c6fe3b73db0d","s4":"15bf3257-b23b-5081-8705-5882f10baedb","s5":"7cf2e42d-a04c-5b5d-836e-ad424e0a8ae2","s6":"645ec7d3-9369-5624-9eb3-c4c9e3c39c99","s7":"14729585-bde5-5c16-96e9-f008242638d7"},"source_file":"datacenters/projects/xai-colossus-memphis.json","source_record_id":"xai-colossus-memphis","source_record_sha256":"dfb2757770260ccf50149a6e04c556018f960324cd194a80d5c5cf347be8f974","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"48c95e4a44b8f4dbae5819de5f7056cdd6ee6aae1c540f087c3d07df103e6305"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-837c77c61e73b3c11714/#project-d2db6863-886a-5c16-b819-7f2cd95cd87e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d2db6863-886a-5c16-b819-7f2cd95cd87e.json
d2e988cd-e878-5061-817e-0c1cda87f372 | curated:bulk-dk01-esbjerg-campus:current-new-building-construction | vcc-site-8a182a091b75047cadab | curated:bulk-dk01-esbjerg-campus | Bulk DK01 Current New Building Construction | Denmark | DK | 55.5092 | 8.4955 | Point | campus | source_attribute_decimal_coordinates_to_point_without_centroiding | first_party_schema_org_geocoordinates_literal_point | official_operator_published_campus_reference_point | official_source | campus_locator | Campus reference point only, associated by canonical site URL and postal address. The new construction project is on this campus but is not asserted at the exact point. No parcel boundary, work footprint, surveyed entrance or quantified accuracy is claimed. |  | Publisher supplies no positional accuracy. Decimal precision and supporting map containment do not establish survey accuracy. | 8e346666-c072-5c99-9322-d0e3257bdcde | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | d72c7f46-599a-551b-a27c-98c8bcc8fd9c | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://bulkinfrastructure.com/uploads/Financial-report/Quarterly-Report/Bulk-Infrastructure-Group-Financial-statements-Q2-2026.pdf | https://bulkinfrastructure.com/data-centers/locations/dk01 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-8a182a091b75047cadab/#project-d2e988cd-e878-5061-817e-0c1cda87f372 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d2e988cd-e878-5061-817e-0c1cda87f372.json
d31725a8-2753-5d70-963d-320d4f6fbb61 | imported:semiconductor-atlas:sify-noida-02 | vcc-site-37108b4d9d3683d6451d | imported:semiconductor-atlas:sify-noida-02 | Sify Noida 02 data center campus | India | IN | 28.57 | 77.32 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sify says Noida 02 is within 1 km of Noida 01, whose address is Plot B7, Sector 132, Noida; no address is given for Noida 02 itself. The point is the Noida city coordinate from its Wikipedia article, so it marks the city rather than the site near Sector 132. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 5a5fd34a-45cf-5da0-8871-2e26a40fc5f2 | partially_operational | 2025-10-16 | 362 | imported_documented_status | 90ecf099-fc6a-570d-b178-dacf0854499b | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"5a5fd34a-45cf-5da0-8871-2e26a40fc5f2","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"developer","source_record_id":"sify-noida-02"},{"evidence_id":"90ecf099-fc6a-570d-b178-dacf0854499b","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"developer","source_record_id":"sify-noida-02"},{"evidence_id":"90ecf099-fc6a-570d-b178-dacf0854499b","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"operator","source_record_id":"sify-noida-02"},{"evidence_id":"c724ea6f-d5d6-5da6-8c29-2218b7fe8c1a","notes":null,"party":"Sify Infinit Spaces Limited","relationship_scope":"unknown","role":"operator","source_record_id":"sify-noida-02"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Sify Infinit Spaces Limited |  |  |  | https://nsearchives.nseindia.com/corporate/Registration_17102025141743_DRHP_Fillingversion.pdf | https://indianinfrastructure.com/2025/03/11/sify-launches-north-indias-largest-ai-ready-data-centre-campus-in-noida/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Sify Noida 02 data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"sify-noida-02","source_relations":[{"reason":"Distinct AdaniConneX and Sify named developments; exactly shared coordinates are Noida city locators.","relationship":"separate_named_developments","source_id":"adaniconnex-noida"}]},"record":{"aliases":["Noida 02"],"id":"sify-noida-02","last_reviewed":"2026-10-09","location":{"admin1":"Uttar Pradesh","admin2":"Gautam Buddha Nagar district","country":"IN","lat":28.57,"locality":"Noida","lon":77.32,"note":"Sify says Noida 02 is within 1 km of Noida 01, whose address is Plot B7, Sector 132, Noida; no address is given for Noida 02 itself. The point is the Noida city coordinate from its Wikipedia article, so it marks the city rather than the site near Sector 132.","precision":"locality","source_ids":["s1","s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-03-11","basis":"planned","metric":"power_capacity","note":"Launch coverage gives total capacity above 130 MW without a scope; Sify's website calls it more than 130 MW of IT power.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1","s2"],"unit":"MW","value":130},{"applies_to":"phase","as_of":"2025-06-30","basis":"operational","metric":"power_capacity","note":"Installed IT capacity of Tower B, the same at 31 March and 30 June 2025. The prospectus defines built capacity as the maximum IT load a facility is engineered to support on its present design, and installed capacity as the part that is equipped, powered and commissioned.","phase_label":"Tower B (installed capacity)","power_scope":"it_load","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":4.32},{"applies_to":"phase","as_of":"2025-06-30","basis":"planned","metric":"power_capacity","note":"Built IT capacity of Tower B at 30 June 2025, also listed on Sify's Noida page. The prospectus defines built capacity as the maximum IT load a facility is engineered to support on its present design, and installed capacity as the part that is equipped, powered and commissioned. Only 4.32 MW was installed, so this figure is recorded as planned rather than operational.","phase_label":"Tower B (built capacity)","power_scope":"it_load","qualifier":"exact","source_ids":["s3","s4"],"unit":"MW","value":25.92},{"applies_to":"campus","as_of":"2025-10-16","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1","s3"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2025-10-16","basis":"operational","metric":"buildings","qualifier":"exact","source_ids":["s3"],"unit":"count","value":1}],"milestones":[{"date":"2024-07-04","event":"other","kind":"actual","note":"Term loan obtained for development works at Noida 02.","source_ids":["s3"]},{"date":"2025-03","event":"first_operational","kind":"actual","note":"Inaugurated by Uttar Pradesh's chief minister, reported on 2025-03-11 without an event date; the industry report in the prospectus says Sify launched Noida 02 in March 2025.","source_ids":["s1","s3"]}],"name":"Sify Noida 02 data center campus","notes":"The prospectus (s3) describes the campus as located in 'Noida, Delhi'; Uttar Pradesh is the state given elsewhere in the same filing. No 2026 campus-level status update was found. Sify's Noida page cites 130+ MW of IT capacity while listing Noida 01 at 10.96 MW and Noida 02 at 25.92 MW, so the larger figure describes planned build-out. Uttar Pradesh's chief minister inaugurated the campus; the state has no other stated role, so it is not listed as a party. Noida coordinates and the district come from Wikipedia (s5), used only for the location.","parties":[{"name":"Sify Infinit Spaces Limited","role":"developer","source_ids":["s1","s3"]},{"name":"Sify Infinit Spaces Limited","role":"operator","source_ids":["s3","s4"]}],"power_sources":[{"description":"Dedicated on-site 220 kV substation.","source_ids":["s1","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001011356/https://indianinfrastructure.com/2025/03/11/sify-launches-north-indias-largest-ai-ready-data-centre-campus-in-noida/","id":"s1","published":"2025-03-11","publisher":"Indian Infrastructure","title":"Sify launches North India's largest AI-ready data centre campus in Noida","type":"trade_press","url":"https://indianinfrastructure.com/2025/03/11/sify-launches-north-indias-largest-ai-ready-data-centre-campus-in-noida/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Sify Technologies","title":"Data centre","type":"company","url":"https://www.sifytechnologies.com/europe/data-centre/"},{"accessed":"2026-10-09","id":"s3","published":"2025-10-16","publisher":"Sify Infinit Spaces Limited (filed with SEBI; hosted by National Stock Exchange of India)","title":"Sify Infinit Spaces Limited: Draft Red Herring Prospectus (filing version)","type":"regulatory_filing","url":"https://nsearchives.nseindia.com/corporate/Registration_17102025141743_DRHP_Fillingversion.pdf"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Sify Technologies","title":"Noida data center","type":"company","url":"https://www.sifytechnologies.com/data-center/noida-data-center/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Noida","type":"other","url":"https://en.wikipedia.org/wiki/Noida"}],"status":"partially_operational","status_as_of":"2025-10-16","status_source_ids":["s3"],"summary":"Sify Infinit Spaces' second campus in Noida, Uttar Pradesh, within a kilometre of its Noida 01 facility, is planned as three towers with a dedicated on-site 220 kV substation. Uttar Pradesh's chief minister inaugurated it in March 2025 as North India's largest AI-ready data center campus, with total capacity of more than 130 MW. Sify's October 2025 prospectus said only Tower B was operating, with 25.92 MW of built IT capacity of which 4.32 MW was installed at 30 June 2025; a July 2024 term loan funded development work.","workloads":["colocation","cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"5a5fd34a-45cf-5da0-8871-2e26a40fc5f2","s2":"13fd9433-c937-5d15-83df-0615d0f5d23e","s3":"90ecf099-fc6a-570d-b178-dacf0854499b","s4":"c724ea6f-d5d6-5da6-8c29-2218b7fe8c1a","s5":"1b7988e6-fae3-537c-8a4a-7702622c0195"},"source_file":"datacenters/projects/sify-noida-02.json","source_record_id":"sify-noida-02","source_record_sha256":"de2cd649d7b533c3c76ce23f61f0aafb9a8f5ea874df5d8d2c5d72dce0096611","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8ccf5eca5f59e0e0c7a4bcf1c073a3bc4ada69df67946582006fda41b699990d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-37108b4d9d3683d6451d/#project-d31725a8-2753-5d70-963d-320d4f6fbb61 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d31725a8-2753-5d70-963d-320d4f6fbb61.json
d3694f4b-3497-5f87-88aa-de8e9449c754 | imported:semiconductor-atlas:meta-dekalb-illinois | vcc-site-560ea7139f27238b7ea1 | imported:semiconductor-atlas:meta-dekalb-illinois | Meta DeKalb Data Center | United States | US | 41.8894 | -88.7265 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Mean of three building outlines tagged as Meta-operated data centers in the local OpenStreetMap layer (ways 1312792611, 1312792612, 1312792613) on DeKalb's south side, consistent with the cited address on Metaverse Way off I-88. The point is a building centroid average, not a surveyed parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 0ad1d56c-aa25-535d-82b8-275d8a38b87c | partially_operational | 2023-12-01 | 1047 | imported_documented_status | c7e0b45a-dd55-5ce8-a84e-5a19744afa75 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"0ad1d56c-aa25-535d-82b8-275d8a38b87c","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-dekalb-illinois"},{"evidence_id":"c7e0b45a-dd55-5ce8-a84e-5a19744afa75","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-dekalb-illinois"},{"evidence_id":"4f2b3bf2-1ac8-5ac3-ac94-137011720b32","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"meta-dekalb-illinois"},{"evidence_id":"c7e0b45a-dd55-5ce8-a84e-5a19744afa75","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"meta-dekalb-illinois"},{"evidence_id":"0ad1d56c-aa25-535d-82b8-275d8a38b87c","notes":null,"party":"ComEd","relationship_scope":"unknown","role":"utility","source_record_id":"meta-dekalb-illinois"},{"evidence_id":"4f2b3bf2-1ac8-5ac3-ac94-137011720b32","notes":null,"party":"ComEd","relationship_scope":"unknown","role":"utility","source_record_id":"meta-dekalb-illinois"},{"evidence_id":"0ad1d56c-aa25-535d-82b8-275d8a38b87c","notes":"Partnered with Meta and ComEd on serving the campus; Meta says it pays the full cost of city water and wastewater service.","party":"City of DeKalb","relationship_scope":"unknown","role":"government","source_record_id":"meta-dekalb-illinois"},{"evidence_id":"4f2b3bf2-1ac8-5ac3-ac94-137011720b32","notes":"Partnered with Meta and ComEd on serving the campus; Meta says it pays the full cost of city water and wastewater service.","party":"City of DeKalb","relationship_scope":"unknown","role":"government","source_record_id":"meta-dekalb-illinois"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Meta Platforms |  |  |  | https://www.shawlocal.com/daily-chronicle/2023/11/30/meta-takes-dekalb-data-center-online | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-DeKalb-Data-Center.pdf | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Meta DeKalb Data Center as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"meta-dekalb-illinois"},"record":{"aliases":["DeKalb Data Center"],"id":"meta-dekalb-illinois","last_reviewed":"2026-10-09","location":{"admin1":"Illinois","admin2":"DeKalb County","country":"US","lat":41.8894,"locality":"DeKalb","lon":-88.7265,"note":"Mean of three building outlines tagged as Meta-operated data centers in the local OpenStreetMap layer (ways 1312792611, 1312792612, 1312792613) on DeKalb's south side, consistent with the cited address on Metaverse Way off I-88. The point is a building centroid average, not a surveyed parcel.","precision":"approximate_site","source_ids":["s1","s3"]},"metrics":[{"applies_to":"campus","as_of":"2023-11-29","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2023-12-01","basis":"planned","metric":"floor_area","qualifier":"more_than","source_ids":["s2","s3","s4"],"unit":"sq_ft","value":2300000},{"applies_to":"phase","as_of":"2023-11-29","basis":"operational","metric":"floor_area","note":"Space reported as built at the November 2023 opening, when two of the five planned buildings were serving traffic.","phase_label":"Built by November 2023","qualifier":"approximately","source_ids":["s4"],"unit":"sq_ft","value":1000000},{"applies_to":"campus","as_of":"2023-12-01","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s3"],"unit":"count","value":5},{"applies_to":"phase","as_of":"2023-12-01","basis":"operational","metric":"buildings","phase_label":"First two buildings","qualifier":"exact","source_ids":["s3"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2023-11-29","basis":"reported","metric":"jobs_construction","note":"Skilled trade workers during construction; Meta's fact sheet gives 1,200 at peak.","qualifier":"more_than","source_ids":["s1","s2"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2023-11-29","basis":"planned","metric":"jobs_permanent","note":"Once fully operational; about 80 people were employed at the opening.","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"count","value":200}],"milestones":[{"date":"2020","event":"construction_started","kind":"actual","source_ids":["s1","s3"]},{"date":"2023-11-29","event":"first_operational","kind":"actual","note":"Opening ceremony; the first two buildings began carrying live traffic that week.","source_ids":["s2","s3","s4"]}],"name":"Meta DeKalb Data Center","notes":"At the November 2023 opening, the state release called the campus fully operational, while local reports said two of five planned buildings were serving traffic and about 1 million of 2.3 million sq ft had been built; the status follows the building-level reporting. No later report on the remaining buildings was found. Meta's fact sheet (s1) shows no publication date; its embedded file creation date is 2026-09-02.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s3"]},{"name":"Meta Platforms","role":"operator","source_ids":["s2","s3"]},{"name":"ComEd","role":"utility","source_ids":["s1","s2"]},{"name":"City of DeKalb","note":"Partnered with Meta and ComEd on serving the campus; Meta says it pays the full cost of city water and wastewater service.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"Served by ComEd, which partnered with Meta and the City of DeKalb to power the campus; Meta says it planned its energy needs with the utility and pays the full cost of the energy used, and the state release says the data center is supported by 100% renewable energy.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Meta Platforms","title":"Meta DeKalb Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-DeKalb-Data-Center.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2023-11-29","publisher":"Office of the Governor of Illinois","title":"Gov. Pritzker Celebrates Opening of Meta's DeKalb Data Center","type":"government","url":"https://gov.illinois.gov/news/press-release.28370.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260828024302/https://www.shawlocal.com/daily-chronicle/2023/11/30/meta-takes-dekalb-data-center-online/","id":"s3","published":"2023-12-01","publisher":"Daily Chronicle (Shaw Local)","title":"Meta takes DeKalb Data Center online","type":"news","url":"https://www.shawlocal.com/daily-chronicle/2023/11/30/meta-takes-dekalb-data-center-online"},{"accessed":"2026-10-09","id":"s4","published":"2023-11-29","publisher":"FOX 32 Chicago","title":"Meta's new Illinois data center now operational","type":"news","url":"https://www.fox32chicago.com/news/meta-new-illinois-data-center-operational"}],"status":"partially_operational","status_as_of":"2023-12-01","status_source_ids":["s3","s4"],"summary":"Meta campus at 2050 Metaverse Way on the south side of DeKalb, Illinois, off Interstate 88. Meta broke ground in 2020 on a planned five-building campus of more than 2.3 million sq ft and more than USD 1 billion of investment. It came online in late November 2023, when the Illinois governor attended the opening; local reports said two buildings were serving traffic and about 1 million sq ft had been built. Meta says it planned its energy needs with ComEd and pays the full cost of the energy the campus uses.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"0ad1d56c-aa25-535d-82b8-275d8a38b87c","s2":"4f2b3bf2-1ac8-5ac3-ac94-137011720b32","s3":"c7e0b45a-dd55-5ce8-a84e-5a19744afa75","s4":"51ed270f-9f90-5011-8842-d25254b4f344"},"source_file":"datacenters/projects/meta-dekalb-illinois.json","source_record_id":"meta-dekalb-illinois","source_record_sha256":"83f6ef171748fe2d9828ddcc471e268a595f3828207a358113ba59290c39dc6e","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"86b8ee006c2da6114811df03b2f7b0f09c2c87026810f557fa1c4624a1b8468d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-560ea7139f27238b7ea1/#project-d3694f4b-3497-5f87-88aa-de8e9449c754 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d3694f4b-3497-5f87-88aa-de8e9449c754.json
d461c464-bedc-555a-a582-c6f96a0a2acc | imported:semiconductor-atlas:scala-ai-city-eldorado-do-sul | vcc-site-a1239f397b785f28fd31 | imported:semiconductor-atlas:scala-ai-city-eldorado-do-sul | Scala AI City (Eldorado do Sul) | Brazil | BR | -30.0839 | -51.6158 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Municipal reference point for Eldorado do Sul (Wikipedia infobox); the releases name the municipality but not the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | bb426ea9-cd82-5aec-a66e-9a11374b7be7 | announced | 2025-05-14 | 517 | imported_documented_status | ef800797-7851-5561-ad75-a6b917f27c17 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"bb426ea9-cd82-5aec-a66e-9a11374b7be7","notes":null,"party":"Scala Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"scala-ai-city-eldorado-do-sul"},{"evidence_id":"af73cfff-cf62-518d-9e0a-0a03142c3325","notes":null,"party":"Scala Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"scala-ai-city-eldorado-do-sul"},{"evidence_id":"ef800797-7851-5561-ad75-a6b917f27c17","notes":null,"party":"Scala Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"scala-ai-city-eldorado-do-sul"},{"evidence_id":"bb426ea9-cd82-5aec-a66e-9a11374b7be7","notes":"Signed a letter of intent with Scala through its economic development department.","party":"Government of Rio Grande do Sul","relationship_scope":"unknown","role":"government","source_record_id":"scala-ai-city-eldorado-do-sul"},{"evidence_id":"af73cfff-cf62-518d-9e0a-0a03142c3325","notes":"Enacted Municipal Law 5.949/2024 expanding the urban perimeter to include the site.","party":"Municipality of Eldorado do Sul","relationship_scope":"unknown","role":"government","source_record_id":"scala-ai-city-eldorado-do-sul"},{"evidence_id":"ef800797-7851-5561-ad75-a6b917f27c17","notes":"Authorized a phased connection of up to 5 GW to the national grid.","party":"Brazil Ministry of Mines and Energy","relationship_scope":"unknown","role":"government","source_record_id":"scala-ai-city-eldorado-do-sul"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.prnewswire.com/news-releases/scala-ai-city-brazils-ministry-of-mines-and-energy-approves-5-gw-power-connection-for-data-center-city-in-rio-grande-do-sul-302455610.html | https://www.prnewswire.com/news-releases/with-an-initial-investment-of-usd-500-million-scala-data-centers-and-rio-grande-do-sul-government-sign-agreement-for-largest-digital-infrastructure-project-in-the-state-of-southern-brazil-302245667.html | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Scala AI City (Eldorado do Sul) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"scala-ai-city-eldorado-do-sul"},"record":{"aliases":["Scala AI City"],"id":"scala-ai-city-eldorado-do-sul","last_reviewed":"2026-10-09","location":{"admin1":"Rio Grande do Sul","country":"BR","lat":-30.0839,"locality":"Eldorado do Sul","lon":-51.6158,"note":"Municipal reference point for Eldorado do Sul (Wikipedia infobox); the releases name the municipality but not the parcel.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"phase","as_of":"2025-05-14","basis":"planned","metric":"power_capacity","phase_label":"Phase 1","power_scope":"it_load","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":54},{"applies_to":"campus","as_of":"2025-05-14","basis":"planned","metric":"power_capacity","note":"Described as potential capacity at full build-out; the releases do not say whether it is IT load.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"MW","value":4750},{"applies_to":"campus","as_of":"2025-05-14","basis":"permitted","metric":"power_capacity","note":"Ramp-up connection to the national interconnected system authorized by the Ministry of Mines and Energy.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s3"],"unit":"MW","value":5000},{"applies_to":"phase","as_of":"2024-12-18","basis":"announced","metric":"investment","note":"The September 2024 release gave the same phase as USD 500 million.","phase_label":"Phase 1","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"BRL","value":3000000000},{"applies_to":"campus","as_of":"2025-05-14","basis":"announced","metric":"investment","note":"Potential total at full build-out. The releases also cite USD figures that differ (USD 90 billion in September 2024, USD 80 billion in December 2024).","qualifier":"up_to","source_ids":["s2","s3"],"unit":"BRL","value":500000000000},{"applies_to":"campus","as_of":"2024-09-11","basis":"planned","metric":"land_area","note":"Later releases give the site as more than 7 million square metres (December 2024) and 10 million square metres (May 2025), so stated areas vary.","qualifier":"more_than","source_ids":["s1"],"unit":"acres","value":1730}],"milestones":[{"date":"2024-09-11","event":"announced","kind":"actual","note":"Letter of intent signed with the Rio Grande do Sul government.","source_ids":["s1"]},{"date":"2024-12-18","event":"zoning_approved","kind":"actual","note":"Mayor signed Municipal Law 5.949/2024 bringing the site into the urban perimeter; date is the release date.","source_ids":["s2"]},{"date":"2025-05-14","event":"permit_approved","kind":"actual","note":"Federal authorization for a phased grid connection of up to 5 GW; date is the release date.","source_ids":["s3"]}],"name":"Scala AI City (Eldorado do Sul)","parties":[{"name":"Scala Data Centers","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Government of Rio Grande do Sul","note":"Signed a letter of intent with Scala through its economic development department.","role":"government","source_ids":["s1"]},{"name":"Municipality of Eldorado do Sul","note":"Enacted Municipal Law 5.949/2024 expanding the urban perimeter to include the site.","role":"government","source_ids":["s2"]},{"name":"Brazil Ministry of Mines and Energy","note":"Authorized a phased connection of up to 5 GW to the national grid.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"Connection to Brazil's national interconnected system; Scala says the campus will use 100% renewable, certified energy.","source_ids":["s1","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-09-11","publisher":"Scala Data Centers via PR Newswire","title":"With an initial investment of USD 500 million, Scala Data Centers and Rio Grande do Sul government sign agreement for largest digital infrastructure project in the state of southern Brazil","type":"company","url":"https://www.prnewswire.com/news-releases/with-an-initial-investment-of-usd-500-million-scala-data-centers-and-rio-grande-do-sul-government-sign-agreement-for-largest-digital-infrastructure-project-in-the-state-of-southern-brazil-302245667.html"},{"accessed":"2026-10-09","id":"s2","published":"2024-12-18","publisher":"Scala Data Centers via PR Newswire","title":"Mayor of Eldorado do Sul, Brazil, Approves Law Enabling the Construction of Latin America's First Data Center City","type":"company","url":"https://www.prnewswire.com/news-releases/mayor-of-eldorado-do-sul-brazil-approves-law-enabling-the-construction-of-latin-americas-first-data-center-city-302335569.html"},{"accessed":"2026-10-09","id":"s3","published":"2025-05-14","publisher":"Scala Data Centers via PR Newswire","title":"Scala AI City: Brazil's Ministry of Mines and Energy approves 5 GW power connection for data center city in Rio Grande do Sul","type":"company","url":"https://www.prnewswire.com/news-releases/scala-ai-city-brazils-ministry-of-mines-and-energy-approves-5-gw-power-connection-for-data-center-city-in-rio-grande-do-sul-302455610.html"}],"status":"announced","status_as_of":"2025-05-14","status_source_ids":["s3"],"summary":"Scala Data Centers plans a data centre city in Eldorado do Sul, in the Porto Alegre metropolitan region of Rio Grande do Sul, Brazil. It signed an agreement with the state government in September 2024 for a first phase of 54 MW of IT capacity, about BRL 3 billion, with potential growth to 4,750 MW and total investment the company puts as high as BRL 500 billion. Eldorado do Sul passed a law in December 2024 adding the site to the urban perimeter, and in May 2025 Brazil's Ministry of Mines and Energy authorized a phased grid connection of up to 5 GW. No construction start had been reported in the sources reviewed.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"bb426ea9-cd82-5aec-a66e-9a11374b7be7","s2":"af73cfff-cf62-518d-9e0a-0a03142c3325","s3":"ef800797-7851-5561-ad75-a6b917f27c17"},"source_file":"datacenters/projects/scala-ai-city-eldorado-do-sul.json","source_record_id":"scala-ai-city-eldorado-do-sul","source_record_sha256":"103d344a42eb7961581f8eb5ddb159a0a96bf6206972db1e371492bec63c0c57","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7c9051a8b3c2a79777dcfdf3020a9a420711a7c8d4cace9dd7cab6fae1492262"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a1239f397b785f28fd31/#project-d461c464-bedc-555a-a582-c6f96a0a2acc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d461c464-bedc-555a-a582-c6f96a0a2acc.json
d5b84301-4f54-5958-a0d1-fd2c5a72cc5b | curated:dc-blox-palm-coast-cls-campus:approved-first-building-current-build | vcc-site-98db1c10877fca784aba | curated:dc-blox-palm-coast-cls-campus | DC BLOX Palm Coast Approved First Building Current Construction | United States | US | 29.4954 | -81.1973 | Point | campus | official_named_address_point | native_EPSG2881_to_EPSG4326_pyproj_NAD83_HARN_to_WGS84_3 | official_address_reference_point | official_source | campus_locator | Literal municipal address reference point inside the exact approved Lot 7B parcel, transformed from its stored-source NAD83(HARN) Florida East coordinates. Not a parcel centroid, surveyed boundary, entrance, building outline or precise active-work position; digits preserve computational precision only. |  | The city supplies no numeric positional-accuracy estimate and warns of generalized map error and scale limitations. The one-metre selected transformation-operation accuracy is not source feature accuracy. | e5855643-474a-5e69-ab89-f951302a58dd | under_construction | 2026-06-19 | 116 | authoritative_physical_status_update | f9bc2a0b-a7ea-546b-bb5a-ec9f419c19a5 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.palmcoast.gov/newsroom/home/details/approved-scope-of-dc-blox | https://gis.palmcoast.gov/hosting/rest/services/External/FlaglerCountyParcels/MapServer/0/query?f=json&objectIds=93663&outFields=OBJECTID%2CPT_ID%2CADDRESS%2CPARCEL_ID%2CCONF%2CStatus&returnGeometry=true&outSR=2881 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-98db1c10877fca784aba/#project-d5b84301-4f54-5958-a0d1-fd2c5a72cc5b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d5b84301-4f54-5958-a0d1-fd2c5a72cc5b.json
d63cbbf2-d501-5bf8-83d4-befc76c4bb39 | imported:semiconductor-atlas:datavita-lanarkshire-ai-growth-zone | vcc-site-ad58c35abfe93060c2c2 | imported:semiconductor-atlas:datavita-lanarkshire-ai-growth-zone | DataVita Lanarkshire AI Growth Zone campus (Chapelhall) | United Kingdom | GB | 55.835 | -3.9444 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | The UK government places the site in Airdrie; DataVita locates the DV4 expansion at Lancaster Avenue, Chapelhall, next to its existing DV1 and DV3. Coordinates are an approximate point near Lancaster Avenue; individual building plots were not identified. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 63c621be-5d2c-562b-80ca-84dd7a6d2ca5 | under_construction | 2026-09-02 | 41 | imported_documented_status | 33149068-8232-51ab-9404-1ce6278b8750 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"63c621be-5d2c-562b-80ca-84dd7a6d2ca5","notes":null,"party":"DataVita","relationship_scope":"unknown","role":"developer","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"5764c649-8696-5ed9-86f7-259d32798228","notes":null,"party":"DataVita","relationship_scope":"unknown","role":"developer","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"33149068-8232-51ab-9404-1ce6278b8750","notes":null,"party":"DataVita","relationship_scope":"unknown","role":"developer","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"c43ff3e3-0835-5d0e-912d-e99c9b8301b5","notes":"DataVita says it built, owns and runs DV1 at Chapelhall; DataVita is part of HFD Group.","party":"DataVita","relationship_scope":"unknown","role":"owner","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"c43ff3e3-0835-5d0e-912d-e99c9b8301b5","notes":"DataVita says it has run the Chapelhall campus for more than ten years.","party":"DataVita","relationship_scope":"unknown","role":"operator","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"9f270ed4-454c-5309-b244-bbba6597e021","notes":"Full capacity of the DV1 expansion and DV3 contracted to CoreWeave under a 15-year agreement.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"33149068-8232-51ab-9404-1ce6278b8750","notes":"Full capacity of the DV1 expansion and DV3 contracted to CoreWeave under a 15-year agreement.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"33149068-8232-51ab-9404-1ce6278b8750","notes":"Provided a GBP 202m guarantee supporting a roughly GBP 300m debt facility from ING, ABN AMRO, Santander, the Scottish National Investment Bank and Siemens Financial Services.","party":"National Wealth Fund","relationship_scope":"unknown","role":"investor","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"63c621be-5d2c-562b-80ca-84dd7a6d2ca5","notes":"Designated the site an AI Growth Zone, conditional on delivery against agreed milestones.","party":"UK Government","relationship_scope":"unknown","role":"government","source_record_id":"datavita-lanarkshire-ai-growth-zone"},{"evidence_id":"c43ff3e3-0835-5d0e-912d-e99c9b8301b5","notes":"Planning authority for the DV4 application.","party":"North Lanarkshire Council","relationship_scope":"unknown","role":"government","source_record_id":"datavita-lanarkshire-ai-growth-zone"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | DataVita | DataVita |  | CoreWeave |  | https://blog.datavita.co.uk/blog/datavita-secures-funding-data-centre-expansion | https://www.gov.uk/government/news/more-than-3400-jobs-and-targeted-support-for-local-communities-to-help-tackle-the-cost-of-living-as-lanarkshire-named-latest-ai-growth-zone | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve DataVita Lanarkshire AI Growth Zone campus (Chapelhall) as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"datavita-lanarkshire-ai-growth-zone"},"record":{"aliases":["Lanarkshire AI Growth Zone","SAIZ Project","DataVita Chapelhall campus"],"id":"datavita-lanarkshire-ai-growth-zone","last_reviewed":"2026-10-09","location":{"admin1":"Scotland","admin2":"North Lanarkshire","country":"GB","lat":55.835,"locality":"Chapelhall","lon":-3.9444,"note":"The UK government places the site in Airdrie; DataVita locates the DV4 expansion at Lancaster Avenue, Chapelhall, next to its existing DV1 and DV3. Coordinates are an approximate point near Lancaster Avenue; individual building plots were not identified.","precision":"approximate_site","source_ids":["s1","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-29","basis":"planned","metric":"power_capacity","note":"UK government says DataVita plans more than 500 MW of on-site power generation within four years; no IT load figure is given.","power_scope":"onsite_generation","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-01-29","basis":"announced","metric":"investment","note":"Private investment attached to the AI Growth Zone designation.","qualifier":"exact","source_ids":["s1","s2"],"unit":"GBP","value":8200000000},{"applies_to":"phase","as_of":"2025-09-17","basis":"announced","metric":"investment","note":"Investment in AI infrastructure at the Lanarkshire campus announced by DataVita with CoreWeave; the release does not say who provides the funds.","phase_label":"CoreWeave AI deployment","qualifier":"exact","source_ids":["s3"],"unit":"GBP","value":1500000000},{"applies_to":"phase","as_of":"2026-09-02","basis":"announced","metric":"investment","note":"Construction investment over two years cited in the DV4 planning announcement.","phase_label":"DV4","qualifier":"exact","source_ids":["s5"],"unit":"GBP","value":849600000},{"applies_to":"phase","as_of":"2026-08-18","basis":"planned","metric":"jobs_construction","phase_label":"DV1 expansion and DV3","qualifier":"approximately","source_ids":["s4"],"unit":"count","value":600},{"applies_to":"phase","as_of":"2026-08-18","basis":"planned","metric":"jobs_permanent","phase_label":"DV1 expansion and DV3","qualifier":"approximately","source_ids":["s4"],"unit":"count","value":100},{"applies_to":"phase","as_of":"2026-09-02","basis":"planned","metric":"jobs_permanent","note":"Permanent skilled roles on site, including apprenticeships.","phase_label":"DV4","qualifier":"exact","source_ids":["s5"],"unit":"count","value":120}],"milestones":[{"date":"2025-09-17","event":"announced","kind":"actual","note":"DataVita and CoreWeave announced a GBP 1.5bn renewable-powered AI infrastructure deployment at the Lanarkshire campus.","source_ids":["s3"]},{"date":"2026-01-29","event":"other","kind":"actual","note":"UK government named the North Lanarkshire site an AI Growth Zone.","source_ids":["s1"]},{"date":"2026-08-18","event":"other","kind":"actual","note":"DataVita secured a roughly GBP 300m debt facility to expand DV1 and build DV3; its managing director said work was well advanced on site.","source_ids":["s4"]},{"date":"2026","event":"other","kind":"planned","note":"DataVita's managing director said the first of the two funded facilities would complete in 2026; DV1 itself has operated for more than a decade.","source_ids":["s4"]},{"date":"2026-09-02","event":"other","kind":"actual","note":"DataVita announced it had submitted an application for planning permission in principle for DV4 to North Lanarkshire Council.","source_ids":["s5"]}],"name":"DataVita Lanarkshire AI Growth Zone campus (Chapelhall)","parties":[{"name":"DataVita","role":"developer","source_ids":["s1","s2","s4"]},{"name":"DataVita","note":"DataVita says it built, owns and runs DV1 at Chapelhall; DataVita is part of HFD Group.","role":"owner","source_ids":["s5"]},{"name":"DataVita","note":"DataVita says it has run the Chapelhall campus for more than ten years.","role":"operator","source_ids":["s5"]},{"name":"CoreWeave","note":"Full capacity of the DV1 expansion and DV3 contracted to CoreWeave under a 15-year agreement.","role":"tenant","source_ids":["s3","s4"]},{"name":"National Wealth Fund","note":"Provided a GBP 202m guarantee supporting a roughly GBP 300m debt facility from ING, ABN AMRO, Santander, the Scottish National Investment Bank and Siemens Financial Services.","role":"investor","source_ids":["s4"]},{"name":"UK Government","note":"Designated the site an AI Growth Zone, conditional on delivery against agreed milestones.","role":"government","source_ids":["s1"]},{"name":"North Lanarkshire Council","note":"Planning authority for the DV4 application.","role":"government","source_ids":["s5"]}],"power_sources":[{"description":"On-site renewable generation planned, more than 500 MW within four years per the UK government; the technology mix is not specified, though nearby land is described as suitable for solar and wind.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261005164117/https://www.gov.uk/government/news/more-than-3400-jobs-and-targeted-support-for-local-communities-to-help-tackle-the-cost-of-living-as-lanarkshire-named-latest-ai-growth-zone","id":"s1","published":"2026-01-29","publisher":"UK Government","title":"More than 3,400 jobs and targeted support for local communities to help tackle the cost of living as Lanarkshire named latest AI Growth Zone","type":"government","url":"https://www.gov.uk/government/news/more-than-3400-jobs-and-targeted-support-for-local-communities-to-help-tackle-the-cost-of-living-as-lanarkshire-named-latest-ai-growth-zone"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260901124808/https://www.datavita.co.uk/lanarkshire-ai-growth-zone","id":"s2","published":null,"publisher":"DataVita","title":"Lanarkshire AI Growth Zone","type":"company","url":"https://www.datavita.co.uk/lanarkshire-ai-growth-zone"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260711122150/https://blog.datavita.co.uk/blog/datavita-and-coreweave-to-launch-ai-infrastructure-in-scotland-powered-by-renewable-energy-as-part-of-ps1-5bn-investment","id":"s3","published":"2025-09-17","publisher":"DataVita","title":"DataVita, CoreWeave launch £1.5bn renewable AI infrastructure in Scotland","type":"company","url":"https://blog.datavita.co.uk/blog/datavita-and-coreweave-to-launch-ai-infrastructure-in-scotland-powered-by-renewable-energy-as-part-of-ps1-5bn-investment"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-18","publisher":"DataVita","title":"DataVita secures £300 million for data centre rollout in Scotland's AI Growth Zone, with backing from National Wealth Fund and major lenders","type":"company","url":"https://blog.datavita.co.uk/blog/datavita-secures-funding-data-centre-expansion"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260917083924/https://blog.datavita.co.uk/blog/datavita-submits-plans-dv4-data-centre-chapelhall","id":"s5","published":"2026-09-02","publisher":"DataVita","title":"DataVita submits plans for DV4, its third data centre at Chapelhall","type":"company","url":"https://blog.datavita.co.uk/blog/datavita-submits-plans-dv4-data-centre-chapelhall"}],"status":"under_construction","status_as_of":"2026-09-02","status_source_ids":["s4","s5"],"summary":"DataVita, part of HFD Group, is expanding its data centre campus at Chapelhall near Airdrie, North Lanarkshire, which the UK government named an AI Growth Zone in January 2026, Scotland's first, with GBP 8.2bn of private investment and plans for more than 500 MW of on-site power generation within four years. CoreWeave partnered with DataVita on a GBP 1.5bn AI deployment in 2025 and has contracted the full capacity of an expanded DV1 and a new DV3 building for 15 years. DV3 was under construction in 2026, backed by a roughly GBP 300m debt facility, and in September 2026 DataVita said it had applied for planning permission in principle for a further building, DV4.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"63c621be-5d2c-562b-80ca-84dd7a6d2ca5","s2":"5764c649-8696-5ed9-86f7-259d32798228","s3":"9f270ed4-454c-5309-b244-bbba6597e021","s4":"33149068-8232-51ab-9404-1ce6278b8750","s5":"c43ff3e3-0835-5d0e-912d-e99c9b8301b5"},"source_file":"datacenters/projects/datavita-lanarkshire-ai-growth-zone.json","source_record_id":"datavita-lanarkshire-ai-growth-zone","source_record_sha256":"e50f7a7877930b30a9f0bf4dd7d58e55b956794c069b49ab3b9dd7d0aece56cb","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"071c683461798ce72e22d218da92316080ce8de85d1bf4c142586431880b5440"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ad58c35abfe93060c2c2/#project-d63cbbf2-d501-5bf8-83d4-befc76c4bb39 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d63cbbf2-d501-5bf8-83d4-befc76c4bb39.json
d654ea2a-ea8e-564e-a1df-67f35d52ebbc | imported:semiconductor-atlas:project-blue-tucson | vcc-site-18500c4557e6b208669d | imported:semiconductor-atlas:project-blue-tucson | Project Blue | United States | US | 32.2219 | -110.9714 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Tucson. The site is in unincorporated Pima County immediately north of the Pima County Fairgrounds and west of Houghton Road in the Southeast Employment and Logistics Center, southeast of this point; no coordinates were found in a cited source. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 27cd40f2-5183-5f51-a749-737dcb1e93a5 | under_construction | 2026-04-24 | 172 | imported_documented_status | 3d965061-2afb-5201-b178-6690a45d1f18 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"27cd40f2-5183-5f51-a749-737dcb1e93a5","notes":null,"party":"Beale Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"project-blue-tucson"},{"evidence_id":"65a107df-b44a-57ed-abc1-baab6a67dcb8","notes":null,"party":"Beale Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"project-blue-tucson"},{"evidence_id":"68c46307-ea04-59d1-b4ec-b6dc039e13c5","notes":null,"party":"Beale Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"project-blue-tucson"},{"evidence_id":"eddf2016-2f98-57a5-bb20-2ed4afc06a37","notes":"Arizona Luminaria names it as the purchaser in the county land sale contract, and the county's binding memorandum of agreement is with it; AZ Capitol Times refers to the developers as Beale Infrastructure and Humphrey's Peak Power.","party":"Humphrey's Peak Properties, LLC","relationship_scope":"unknown","role":"owner","source_record_id":"project-blue-tucson"},{"evidence_id":"27cd40f2-5183-5f51-a749-737dcb1e93a5","notes":"Arizona Luminaria names it as the purchaser in the county land sale contract, and the county's binding memorandum of agreement is with it; AZ Capitol Times refers to the developers as Beale Infrastructure and Humphrey's Peak Power.","party":"Humphrey's Peak Properties, LLC","relationship_scope":"unknown","role":"owner","source_record_id":"project-blue-tucson"},{"evidence_id":"eddf2016-2f98-57a5-bb20-2ed4afc06a37","notes":null,"party":"Tucson Electric Power","relationship_scope":"unknown","role":"utility","source_record_id":"project-blue-tucson"},{"evidence_id":"65a107df-b44a-57ed-abc1-baab6a67dcb8","notes":null,"party":"Tucson Electric Power","relationship_scope":"unknown","role":"utility","source_record_id":"project-blue-tucson"},{"evidence_id":"27cd40f2-5183-5f51-a749-737dcb1e93a5","notes":"Sold the land and approved a binding community-benefits agreement with Beale.","party":"Pima County","relationship_scope":"unknown","role":"government","source_record_id":"project-blue-tucson"},{"evidence_id":"68c46307-ea04-59d1-b4ec-b6dc039e13c5","notes":"Sold the land and approved a binding community-benefits agreement with Beale.","party":"Pima County","relationship_scope":"unknown","role":"government","source_record_id":"project-blue-tucson"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Humphrey's Peak Properties, LLC |  |  |  |  | https://www.kold.com/2026/04/25/construction-begins-first-hyper-scale-data-center-pima-county/ | https://www.pima.gov/3552/Project-Blue-FAQ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Project Blue as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"project-blue-tucson"},"record":{"aliases":["Beale Infrastructure Pima County data center campus"],"id":"project-blue-tucson","last_reviewed":"2026-10-09","location":{"admin1":"Arizona","admin2":"Pima County","country":"US","lat":32.2219,"locality":"Tucson","lon":-110.9714,"note":"Wikipedia coordinates for Tucson. The site is in unincorporated Pima County immediately north of the Pima County Fairgrounds and west of Houghton Road in the Southeast Employment and Logistics Center, southeast of this point; no coordinates were found in a cited source.","precision":"locality","source_ids":["s1","s6"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"Total capital investment planned over a multi-year build, per the county's undated Project Blue FAQ page as viewed on the access date; its newest listed document is dated April 2026.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":3600000000},{"applies_to":"campus","as_of":"2025-12-04","basis":"contracted","metric":"power_capacity","note":"Capacity TEP is to provide by 2028 under the energy supply agreement approved by the Arizona Corporation Commission; any expansion would need a new agreement.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2","s4"],"unit":"MW","value":286},{"applies_to":"campus","as_of":"2026-04-24","basis":"acquired","metric":"land_area","qualifier":"approximately","source_ids":["s1","s6"],"unit":"acres","value":290},{"applies_to":"campus","as_of":"2026-04-24","basis":"planned","metric":"buildings","qualifier":"up_to","source_ids":["s1","s6"],"unit":"count","value":10},{"applies_to":"phase","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"Undated county FAQ page as viewed on the access date.","phase_label":"Initial phase","qualifier":"exact","source_ids":["s1"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2025-12-16","basis":"planned","metric":"jobs_permanent","note":"The county FAQ expects these jobs by the third year of operations.","qualifier":"approximately","source_ids":["s1","s5"],"unit":"count","value":180},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_construction","note":"Direct construction jobs expected between 2026 and 2028, per the undated county FAQ page as viewed on the access date.","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":3000}],"milestones":[{"date":"2025-06-17","event":"other","kind":"actual","note":"Pima County Board of Supervisors approved the sale of the county parcel to the developer.","source_ids":["s2"]},{"date":"2025-08","event":"other","kind":"actual","note":"Tucson City Council voted against the project, ending annexation negotiations.","source_ids":["s2","s3"]},{"date":"2025-12-03","event":"other","kind":"actual","note":"Arizona Corporation Commission approved the TEP energy supply agreement by a four-to-one vote.","source_ids":["s4"]},{"date":"2025-12-16","event":"other","kind":"actual","note":"County board approved a binding agreement with Beale by a three-to-two vote.","source_ids":["s5"]},{"date":"2025-12","event":"site_acquired","kind":"actual","note":"County lists land sale closing updates dated late December 2025.","source_ids":["s1"]},{"date":"2027","event":"first_operational","kind":"planned","note":"County FAQ says the first building could be operational as soon as 2027.","source_ids":["s1"]},{"date":"2028","event":"first_operational","kind":"planned","note":"April 2026 local coverage says the campus is expected to be running by 2028, later than the county's earliest target.","source_ids":["s6"]}],"name":"Project Blue","notes":"AZ Capitol Times reported in December 2025 that Amazon Web Services, which public records first obtained by Arizona Luminaria had tied to the project, would no longer use it after the switch to air cooling, and that no replacement user had been named.","parties":[{"name":"Beale Infrastructure","role":"developer","source_ids":["s1","s4","s5"]},{"name":"Humphrey's Peak Properties, LLC","note":"Arizona Luminaria names it as the purchaser in the county land sale contract, and the county's binding memorandum of agreement is with it; AZ Capitol Times refers to the developers as Beale Infrastructure and Humphrey's Peak Power.","role":"owner","source_ids":["s2","s1"]},{"name":"Tucson Electric Power","role":"utility","source_ids":["s2","s4"]},{"name":"Pima County","note":"Sold the land and approved a binding community-benefits agreement with Beale.","role":"government","source_ids":["s1","s5"]}],"power_sources":[{"description":"Tucson Electric Power supply under a special energy supply agreement that TEP says uses existing resources; Beale has pledged to match all of its consumption with independently verified renewable energy.","source_ids":["s4","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Pima County","title":"Project Blue FAQ","type":"government","url":"https://www.pima.gov/3552/Project-Blue-FAQ"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261008060825/https://azluminaria.org/2025/08/27/project-blue-data-center-pima-county-beale-infrastructure-tep/","id":"s2","published":"2025-08-27","publisher":"Arizona Luminaria","title":"Project Blue is back: Beale moving ahead with data center on county land","type":"news","url":"https://azluminaria.org/2025/08/27/project-blue-data-center-pima-county-beale-infrastructure-tep/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251004134431/https://www.azfamily.com/2025/08/09/tucson-rejects-amazon-linked-data-center-amid-water-energy-concerns/","id":"s3","published":"2025-08-08","publisher":"Arizona's Family (KTVK/KPHO)","title":"Tucson rejects Amazon-linked data center amid water, energy concerns","type":"news","url":"https://www.azfamily.com/2025/08/09/tucson-rejects-amazon-linked-data-center-amid-water-energy-concerns/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260629231758/https://azcapitoltimes.com/news/2025/12/04/acc-greenlights-energy-agreement-for-tep-to-power-project-blue-data-center/","id":"s4","published":"2025-12-04","publisher":"Arizona Capitol Times","title":"ACC greenlights energy agreement for TEP to power Project Blue data center","type":"news","url":"https://azcapitoltimes.com/news/2025/12/04/acc-greenlights-energy-agreement-for-tep-to-power-project-blue-data-center/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260304105222/https://www.kold.com/2025/12/16/pima-county-votes-move-forward-with-project-blue/","id":"s5","published":"2025-12-16","publisher":"KOLD News 13","title":"Pima County Board of Supervisors gives green light to Project Blue","type":"news","url":"https://www.kold.com/2025/12/16/pima-county-votes-move-forward-with-project-blue"},{"accessed":"2026-10-09","id":"s6","published":"2026-04-24","publisher":"KOLD News 13","title":"Construction begins on first hyper-scale data center in Pima County","type":"news","url":"https://www.kold.com/2026/04/25/construction-begins-first-hyper-scale-data-center-pima-county/"}],"status":"under_construction","status_as_of":"2026-04-24","status_source_ids":["s6"],"summary":"Beale Infrastructure is building a data center campus on about 290 acres of former county land just north of the Pima County Fairgrounds, in unincorporated Pima County outside Tucson's city limits. Tucson's council voted against the project in August 2025, ending annexation talks, so it went ahead under county jurisdiction with a redesigned air-cooled plan. The county puts total investment at USD 3.6 billion, with four buildings in the first phase and up to ten at full build-out. State regulators approved a Tucson Electric Power supply agreement for 286 MW in December 2025, and work on site was reported under way in April 2026."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"27cd40f2-5183-5f51-a749-737dcb1e93a5","s2":"eddf2016-2f98-57a5-bb20-2ed4afc06a37","s3":"0760610d-7367-5c5f-ba60-ecabca22a5e4","s4":"65a107df-b44a-57ed-abc1-baab6a67dcb8","s5":"68c46307-ea04-59d1-b4ec-b6dc039e13c5","s6":"3d965061-2afb-5201-b178-6690a45d1f18"},"source_file":"datacenters/projects/project-blue-tucson.json","source_record_id":"project-blue-tucson","source_record_sha256":"36e90bd020e0cf912c30f63d71e0c1efd8ce8bbc328218d5e7860d7c1996c304","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"9f1b32cb9ddbbf307e29039d7363f7d2cad9828ba5f410f8f04e197c9d4def92"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-18500c4557e6b208669d/#project-d654ea2a-ea8e-564e-a1df-67f35d52ebbc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d654ea2a-ea8e-564e-a1df-67f35d52ebbc.json
d6a6d399-4580-54f8-80de-1dc0854e4699 | curated:prologis-trenton-project-mila-campus:current-campus-build | vcc-site-df93318f7935fb88ea53 | curated:prologis-trenton-project-mila-campus | Prologis Trenton Project Mila Campus Construction | United States | US | 39.4562 | -84.4597 | Point | campus | representative_point_inside_transformed_exact_developer_parcel | county_response_WKT_EPSG3735_to4326_pyproj3_8_0_then_Shapely2_1_2_representative_point | official_consolidated_parcel_interior_campus_locator | official_source | campus_locator | One point within the exact consolidated parcel R8000060000011 linked by developer filings to Project Mila. It is not a surveyed building position, construction footprint, approved campus boundary or individual hall. The source parcel polygon is not redistributed. |  | County GIS supplies no site-specific positional accuracy; four-metre datum-operation accuracy is not parcel or locator accuracy. | 0048b025-5c07-5f60-82f2-78a73d462260 | under_construction | 2026-08-20 | 54 | authoritative_physical_status_update | a33300f2-4a31-5f6c-afe3-368cf68f396c | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.supremecourt.ohio.gov/pdf_viewer/pdf_viewer.aspx?pdf=1008469.pdf&subdirectory=2026-1035%5CDocketItems&source=DL_Clerk | https://gismaps.bceo.org/server/rest/services/Public/ParcelQuery/FeatureServer/0/query?where=UPPER%28OWNER%29%20LIKE%20%27%25TRENTON%20DATA%20CENTER%25%27&outFields=OBJECTID%2CPIN%2COWNER%2CLOCATION%2CACRES&returnGeometry=true&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-df93318f7935fb88ea53/#project-d6a6d399-4580-54f8-80de-1dc0854e4699 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d6a6d399-4580-54f8-80de-1dc0854e4699.json
d83dc321-220b-5c4c-b5af-ff1f4bc19a5d | curated:iron-mountain-va-9-northern-virginia-data-center:phase-1 | vcc-site-983cd9eec3d1aaa46e69 | curated:iron-mountain-va-9-northern-virginia-data-center | Iron Mountain VA-9 Phase 1 | United States | US | 38.7728 | -77.5429 | Point | campus | official_address_range_geocode | census_single_exact_address_match_then_explicit_nad83_to_wgs84 | official_address_range_interpolation_constituent_campus_locator | official_source | campus_locator | Official Census street-address interpolation for existing VA-1 at 11680 Hayden Road. First-party documents identify VA-1 and VA-9 as constituents of the same 142-acre Manassas campus. Used solely as a campus locator; not the VA-8/VA-9 building, Phase 1/2 work area, campus centroid, parcel boundary or surveyed accuracy. VA-9's 11530 Elevate Drive address was not matched by Census. |  | No source-specific numerical horizontal-accuracy guarantee is published for the selected street-range interpolation. | 375685f2-b4b3-5f21-a1fe-48a1597c9eb2 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 57a8e965-42f2-5089-b1a1-0d3297d572c3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1020569/000102056926000068/q22026srpfinal.htm | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=11680%20Hayden%20Road%20Manassas%20VA%2020109&benchmark=Public_AR_Current&format=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-983cd9eec3d1aaa46e69/#project-d83dc321-220b-5c4c-b5af-ff1f4bc19a5d | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d83dc321-220b-5c4c-b5af-ff1f4bc19a5d.json
d852bc01-c8e9-57c4-b469-9ff3ea1d8a5c | curated:capitaland-dc-chennai-ambattur:current-facility-build | vcc-site-a982e0093e476f44e98f | curated:capitaland-dc-chennai-ambattur | CapitaLand DC Chennai Current Facility Build | India | IN | 13.1115 | 80.1603 | Polygon | campus | source_KML_project_polygon_XY_preserved | PARIVESH_original_CAF128123_2023_active_Project_Site_KML_WGS84_lonlat_no_transform | proponent_submitted_environmental_project_polygon | official_source | campus_locator | Original source polygon vertices, not the conflicting CAF extent labels or an arithmetic midpoint. Government-hosted proponent filing establishes a project-specific campus locator, not cadastral or surveyed boundary accuracy. Exact source decimal tuples are retained with the evidence. The separate display anchor is the planar centroid of this source polygon, independently verified inside it; it is not a publisher point, entrance, surveyed location or replacement geometry. |  | Neither the proponent KML nor the public CAF states a positional-accuracy estimate, survey method, geodetic realization or control points. Decimal count and government hosting do not establish survey accuracy. | 1c75ed75-477d-5d59-9337-803500086218 | under_construction | 2026-07-29 | 76 | authoritative_physical_status_update | 1beede7f-9936-551b-a7b8-13a2d7ac1efa | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.capitaland.com/content/dam/capitaland-newsroom/International/2026/july/clint-1h2026-results/2.%20CLINT%201H%202026%20slides_29%20July%202026.pdf | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=40829&refId=5696080&refType=caf&uuid=963db531-1544-4984-8bef-f68e8a9a0ade&version=1.1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a982e0093e476f44e98f/#project-d852bc01-c8e9-57c4-b469-9ff3ea1d8a5c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d852bc01-c8e9-57c4-b469-9ff3ea1d8a5c.json
d87a919b-df32-53fa-bc01-47b7f6f1dce9 | imported:semiconductor-atlas:core-scientific-muskogee | vcc-site-bf829ea21a9d7386fb5f | imported:semiconductor-atlas:core-scientific-muskogee | Core Scientific Muskogee data center campus | United States | US | 35.7433 | -95.3567 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Core Scientific gives the street address 1525 West 43rd Street South, Muskogee. No geocoder was used, so coordinates are the Muskogee city point from its Wikipedia article, which also names the county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | cfd03805-4a4b-5df9-9505-c6caaf3d7ca5 | partially_operational | 2026-07-28 | 77 | imported_documented_status | 001c0485-1e86-50ad-abbb-53ad2b354d72 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"cfd03805-4a4b-5df9-9505-c6caaf3d7ca5","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-muskogee"},{"evidence_id":"8d1b9b83-a8d1-5ad5-bf76-92a60eb62942","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-muskogee"},{"evidence_id":"3df67d67-97f9-5a91-8efc-a006dd5932b5","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"developer","source_record_id":"core-scientific-muskogee"},{"evidence_id":"cfd03805-4a4b-5df9-9505-c6caaf3d7ca5","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"operator","source_record_id":"core-scientific-muskogee"},{"evidence_id":"371202e2-6a25-5bf2-a53b-57ccfae77647","notes":null,"party":"Core Scientific","relationship_scope":"unknown","role":"operator","source_record_id":"core-scientific-muskogee"},{"evidence_id":"001c0485-1e86-50ad-abbb-53ad2b354d72","notes":"Named as tenant of the roughly 70 MW first building only in the Q2 2026 earnings presentation (s4). The May 2026 release (s3) describes that leased building, designed for the Nvidia GB300 platform, without naming the customer.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-muskogee"},{"evidence_id":"8d1b9b83-a8d1-5ad5-bf76-92a60eb62942","notes":"Named as tenant of the roughly 70 MW first building only in the Q2 2026 earnings presentation (s4). The May 2026 release (s3) describes that leased building, designed for the Nvidia GB300 platform, without naming the customer.","party":"CoreWeave","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-muskogee"},{"evidence_id":"001c0485-1e86-50ad-abbb-53ad2b354d72","notes":"Named for Muskogee only in the Q2 2026 earnings presentation (s4), which lists about 82 MW at this AMD direct site. The Q2 release (s8) gives the 15-year term for about 530 MW across five sites without naming them.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-muskogee"},{"evidence_id":"1d5aaa5f-b165-5194-899b-0e032ebc7701","notes":"Named for Muskogee only in the Q2 2026 earnings presentation (s4), which lists about 82 MW at this AMD direct site. The Q2 release (s8) gives the 15-year term for about 530 MW across five sites without naming them.","party":"AMD","relationship_scope":"unknown","role":"tenant","source_record_id":"core-scientific-muskogee"},{"evidence_id":"371202e2-6a25-5bf2-a53b-57ccfae77647","notes":null,"party":"Oklahoma Gas & Electric","relationship_scope":"unknown","role":"utility","source_record_id":"core-scientific-muskogee"},{"evidence_id":"8d1b9b83-a8d1-5ad5-bf76-92a60eb62942","notes":null,"party":"Oklahoma Gas & Electric","relationship_scope":"unknown","role":"utility","source_record_id":"core-scientific-muskogee"},{"evidence_id":"3df67d67-97f9-5a91-8efc-a006dd5932b5","notes":null,"party":"Oklahoma Gas & Electric","relationship_scope":"unknown","role":"utility","source_record_id":"core-scientific-muskogee"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Core Scientific |  | AMD; CoreWeave |  | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm | https://corescientific.com/high-density-data-centers/muskogee-ok/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Core Scientific Muskogee data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"core-scientific-muskogee"},"record":{"aliases":["Muskogee 1"],"id":"core-scientific-muskogee","last_reviewed":"2026-10-09","location":{"admin1":"Oklahoma","admin2":"Muskogee County","country":"US","lat":35.7433,"locality":"Muskogee","lon":-95.3567,"note":"Core Scientific gives the street address 1525 West 43rd Street South, Muskogee. No geocoder was used, so coordinates are the Muskogee city point from its Wikipedia article, which also names the county.","precision":"locality","source_ids":["s1","s3","s7"]},"metrics":[{"applies_to":"phase","as_of":"2026-03-02","basis":"contracted","metric":"power_capacity","note":"Gross utility power capacity from OG&E listed in the 10-K; the company site page also describes a 100 MW development with a substation able to support more than 500 MW.","phase_label":"Original Muskogee 1 site","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":100},{"applies_to":"phase","as_of":"2026-07-28","basis":"operational","metric":"power_capacity","note":"Leased capacity reported as billing by mid-July 2026. Core Scientific does not say whether the figure is critical IT load.","phase_label":"Building 1 (CoreWeave)","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3","s4"],"unit":"MW","value":70},{"applies_to":"phase","as_of":"2026-07-28","basis":"contracted","metric":"power_capacity","note":"Building under construction since at least May 2026, when it was described as an unleased 82.5 MW building; leased to AMD in July 2026.","phase_label":"Building 2 (AMD)","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3","s4","s5"],"unit":"MW","value":82},{"applies_to":"phase","as_of":"2026-08-14","basis":"operational","metric":"power_capacity","note":"In-service gross grid capacity held by Polaris DS LLC under electric service agreements with OG&E, acquired by Core Scientific to support the expansion.","phase_label":"Polaris DS capacity","power_scope":"grid_connection","qualifier":"approximately","source_ids":["s3","s5"],"unit":"MW","value":440},{"applies_to":"campus","as_of":"2026-08-14","basis":"planned","metric":"power_capacity","note":"Planned gross power from a mix of grid and behind-the-meter supply, which the company equates to about 1.0 GW of leasable power. Gross power is not defined as IT or facility load.","power_scope":"unspecified","qualifier":"approximately","source_ids":["s3","s5","s6"],"unit":"MW","value":1500},{"applies_to":"phase","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"From the undated company site page, accessed 2026-10-09.","phase_label":"Muskogee 1 campus footprint","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":65},{"applies_to":"phase","as_of":"2026-05-06","basis":"reported","metric":"land_area","note":"Described as secured to support the planned expansion; the sources do not say whether it is owned or held under option.","phase_label":"Land secured for planned expansion","qualifier":"approximately","source_ids":["s3","s6"],"unit":"acres","value":250}],"milestones":[{"date":"2026","event":"first_operational","kind":"actual","note":"The 70 MW CoreWeave building was in final testing in May 2026 with delivery targeted for Q2 2026, and was billing by mid-July 2026.","source_ids":["s3","s4"]},{"date":"2026-05-06","event":"expansion_announced","kind":"actual","note":"Plan to scale the campus to about 1.5 GW of gross power and agreement to buy Polaris DS.","source_ids":["s3","s6"]},{"date":"2026-07-28","event":"other","kind":"actual","note":"Core Scientific disclosed AMD leases including about 82 MW at Muskogee.","source_ids":["s4"]},{"date":"2026-08-14","event":"other","kind":"actual","note":"Acquisition of Polaris DS completed for about USD 444 million in cash.","source_ids":["s5"]},{"date":"2027-H2","event":"other","kind":"planned","note":"Target for initial delivery of the roughly 82 MW AMD building; the May 2026 release gave Q4 2027.","source_ids":["s3","s4","s5"]}],"name":"Core Scientific Muskogee data center campus","notes":"Core Scientific's Q2 2026 presentation lists about 917 MW of further power pipeline at Muskogee in two entries without saying how much is grid or behind-the-meter. The AMD agreements are 15-year leases for about 530 MW across five Core Scientific sites; per-site splits come from the company's earnings presentation.","parties":[{"name":"Core Scientific","role":"developer","source_ids":["s1","s3","s5"]},{"name":"Core Scientific","role":"operator","source_ids":["s1","s2"]},{"name":"CoreWeave","note":"Named as tenant of the roughly 70 MW first building only in the Q2 2026 earnings presentation (s4). The May 2026 release (s3) describes that leased building, designed for the Nvidia GB300 platform, without naming the customer.","role":"tenant","source_ids":["s4","s3"]},{"name":"AMD","note":"Named for Muskogee only in the Q2 2026 earnings presentation (s4), which lists about 82 MW at this AMD direct site. The Q2 release (s8) gives the 15-year term for about 530 MW across five sites without naming them.","role":"tenant","source_ids":["s4","s8"]},{"name":"Oklahoma Gas & Electric","role":"utility","source_ids":["s2","s3","s5"]}],"power_sources":[{"description":"Grid power from Oklahoma Gas & Electric, including about 440 MW of in-service capacity under Polaris DS service agreements; load studies for more grid capacity were due to finish in 2026.","source_ids":["s2","s3","s5"],"type":"grid"},{"description":"Core Scientific says it has a plan for a scalable behind-the-meter power solution to supplement grid supply, without naming the fuel or size.","source_ids":["s3"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929001322/https://corescientific.com/high-density-data-centers/muskogee-ok/","id":"s1","published":null,"publisher":"Core Scientific","title":"Muskogee 1 high-density data center","type":"company","url":"https://corescientific.com/high-density-data-centers/muskogee-ok/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260303001537/https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm","id":"s2","published":"2026-03-02","publisher":"Core Scientific, Inc. via SEC EDGAR","title":"Core Scientific, Inc. Form 10-K for the fiscal year ended December 31, 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929001640/https://investors.corescientific.com/news-events/press-releases/detail/135/core-scientific-plans-expansion-to-1-5-gigawatts-of-gross-power-at-muskogee-oklahoma-campus","id":"s3","published":"2026-05-06","publisher":"Core Scientific","title":"Core Scientific plans expansion to 1.5 gigawatts of gross power at Muskogee, Oklahoma campus","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/135/core-scientific-plans-expansion-to-1-5-gigawatts-of-gross-power-at-muskogee-oklahoma-campus"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929002832/https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm","id":"s4","published":"2026-07-28","publisher":"Core Scientific","title":"Core Scientific Q2 2026 earnings presentation (Form 8-K, Exhibit 99.2)","type":"regulatory_filing","url":"https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929001639/https://investors.corescientific.com/news-events/press-releases/detail/142/core-scientific-completes-acquisition-of-polaris-ds-advancing-planned-muskogee-expansion-to-1-5-gw-of-gross-power","id":"s5","published":"2026-08-14","publisher":"Core Scientific","title":"Core Scientific completes acquisition of Polaris DS, advancing planned Muskogee expansion to 1.5 GW of gross power","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/142/core-scientific-completes-acquisition-of-polaris-ds-advancing-planned-muskogee-expansion-to-1-5-gw-of-gross-power"},{"accessed":"2026-10-09","id":"s6","published":"2026-05-07","publisher":"Data Center Knowledge","title":"Core Scientific's Muskogee bet: can crypto-era infrastructure fuel AI?","type":"trade_press","url":"https://www.datacenterknowledge.com/build-design/core-scientific-bets-on-1-5-gw-ai-campus-in-oklahoma"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260930224707/https://en.wikipedia.org/wiki/Muskogee,_Oklahoma","id":"s7","published":null,"publisher":"Wikipedia","title":"Muskogee, Oklahoma","type":"other","url":"https://en.wikipedia.org/wiki/Muskogee,_Oklahoma"},{"accessed":"2026-10-09","id":"s8","published":"2026-07-28","publisher":"Core Scientific","title":"Core Scientific announces second quarter 2026 results","type":"company","url":"https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results"}],"status":"partially_operational","status_as_of":"2026-07-28","status_source_ids":["s4"],"summary":"Core Scientific high-density colocation campus at 1525 West 43rd Street South in Muskogee, Oklahoma, served by Oklahoma Gas & Electric. A 70 MW building designed for Nvidia GB300 systems is leased to CoreWeave and was billing by mid-July 2026, and a second building of about 82 MW, now leased to AMD, is under construction for delivery from the second half of 2027. In May 2026 Core Scientific announced plans to grow the campus to about 1.5 GW of gross power, about 1.0 GW leasable, on about 250 acres, and in August 2026 it closed the purchase of Polaris DS, which holds about 440 MW of in-service OG&E grid capacity.","workloads":["ai_unspecified","hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"cfd03805-4a4b-5df9-9505-c6caaf3d7ca5","s2":"371202e2-6a25-5bf2-a53b-57ccfae77647","s3":"8d1b9b83-a8d1-5ad5-bf76-92a60eb62942","s4":"001c0485-1e86-50ad-abbb-53ad2b354d72","s5":"3df67d67-97f9-5a91-8efc-a006dd5932b5","s6":"01132beb-2c9b-5d8e-8e2c-bf52eb2346d8","s7":"799298e3-b35e-56d4-80df-dbea2dc9fd3f","s8":"1d5aaa5f-b165-5194-899b-0e032ebc7701"},"source_file":"datacenters/projects/core-scientific-muskogee.json","source_record_id":"core-scientific-muskogee","source_record_sha256":"27770cbed3a06baa8115f406673dbf040757ebfc6782e12fbac9b4ef314a02c5","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4ff4d625085967457118e956c79aa03fb78ac1451d63af8873ff9dd0a01cf086"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bf829ea21a9d7386fb5f/#project-d87a919b-df32-53fa-bc01-47b7f6f1dce9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/d87a919b-df32-53fa-bc01-47b7f6f1dce9.json
da9fec8b-b7a1-54cb-afb9-7f534cbab584 | imported:semiconductor-atlas:meta-cheyenne | vcc-site-a51d60551e72a6720e31 | imported:semiconductor-atlas:meta-cheyenne | Meta Cheyenne data center | United States | US | 41.14 | -104.8202 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City point from OpenStreetMap Nominatim; Meta names Cheyenne but gives no site or road. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a544ab6b-cf2e-55b9-9593-f91850151e15 | under_construction | 2026-10-09 | 4 | imported_documented_status | 630c3c0b-7326-5dce-8d23-f0499cd1264b | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a544ab6b-cf2e-55b9-9593-f91850151e15","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-cheyenne"},{"evidence_id":"630c3c0b-7326-5dce-8d23-f0499cd1264b","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-cheyenne"},{"evidence_id":"a544ab6b-cf2e-55b9-9593-f91850151e15","notes":"Meta refers readers to Fortis Construction for construction information.","party":"Fortis Construction","relationship_scope":"unknown","role":"builder","source_record_id":"meta-cheyenne"},{"evidence_id":"a544ab6b-cf2e-55b9-9593-f91850151e15","notes":null,"party":"Black Hills Energy","relationship_scope":"unknown","role":"utility","source_record_id":"meta-cheyenne"},{"evidence_id":"630c3c0b-7326-5dce-8d23-f0499cd1264b","notes":null,"party":"Black Hills Energy","relationship_scope":"unknown","role":"utility","source_record_id":"meta-cheyenne"},{"evidence_id":"630c3c0b-7326-5dce-8d23-f0499cd1264b","notes":"Water and wastewater provider; Meta says it pays the full cost of service.","party":"City of Cheyenne Board of Public Utilities","relationship_scope":"unknown","role":"utility","source_record_id":"meta-cheyenne"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Cheyenne-Data-Center.pdf | https://datacenters.atmeta.com/2024/07/hello-cheyenne/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Cheyenne data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-cheyenne"},"record":{"aliases":["Cheyenne Data Center"],"id":"meta-cheyenne","last_reviewed":"2026-10-09","location":{"admin1":"Wyoming","country":"US","lat":41.14,"locality":"Cheyenne","lon":-104.8202,"note":"City point from OpenStreetMap Nominatim; Meta names Cheyenne but gives no site or road.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2024-07-02","basis":"announced","metric":"investment","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"From Meta's undated fact sheet and location list, read 2026-10-09; labeled as data center investment in Wyoming.","qualifier":"exact","source_ids":["s2","s3"],"unit":"USD","value":1200000000},{"applies_to":"campus","as_of":"2024-07-02","basis":"planned","metric":"floor_area","qualifier":"exact","source_ids":["s1"],"unit":"sq_ft","value":715000},{"applies_to":"campus","as_of":"2024-07-02","basis":"planned","metric":"jobs_construction","qualifier":"more_than","source_ids":["s1","s2","s3"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2024-07-02","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"count","value":100}],"milestones":[{"date":"2024-07-02","event":"announced","kind":"actual","note":"Meta described it as its 21st data center in the U.S. and 25th worldwide.","source_ids":["s1"]},{"date":"2024","event":"construction_started","kind":"actual","note":"Meta's location list gives 2024 as the groundbreaking year.","source_ids":["s3"]}],"name":"Meta Cheyenne data center","notes":"The status rests on two undated Meta pages: the U.S. location list, which gives 2024 as the groundbreaking year, and the fact sheet, which describes the data center in the future tense. status_as_of is therefore the date both were read (2026-10-09). The fact sheet PDF shows no publication date; its embedded file creation date is 2026-09-01.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Fortis Construction","note":"Meta refers readers to Fortis Construction for construction information.","role":"builder","source_ids":["s1"]},{"name":"Black Hills Energy","role":"utility","source_ids":["s1","s2"]},{"name":"City of Cheyenne Board of Public Utilities","note":"Water and wastewater provider; Meta says it pays the full cost of service.","role":"utility","source_ids":["s2"]}],"power_sources":[{"description":"Meta says Black Hills Energy is adding new grid resources, including renewables, and that Meta pays the full cost of the energy used; its fact sheet cites one Wyoming project adding 365 MW of clean energy plus 200 MW of battery storage.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-07-02","publisher":"Meta Platforms","title":"Hello, Cheyenne!","type":"company","url":"https://datacenters.atmeta.com/2024/07/hello-cheyenne/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Meta Platforms","title":"Meta Cheyenne Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Cheyenne-Data-Center.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007122559/https://datacenters.atmeta.com/us-locations/","id":"s3","published":null,"publisher":"Meta Platforms","title":"United States - Meta Data Centers","type":"company","url":"https://datacenters.atmeta.com/us-locations/"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s2","s3"],"summary":"Meta data center campus of 715,000 square feet in Cheyenne, Wyoming, announced in July 2024 as an investment of more than USD 800 million and described as optimized for Meta's AI workloads. Meta's fact sheet and location list now put the investment at USD 1.2 billion, and the list gives 2024 as the groundbreaking year. Black Hills Energy is Meta's energy partner, and Meta refers readers to Fortis Construction for construction information. Meta reports one Wyoming project adding 365 MW of clean energy and 200 MW of battery storage to the grid. No power capacity or opening date for the data center has been published.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a544ab6b-cf2e-55b9-9593-f91850151e15","s2":"630c3c0b-7326-5dce-8d23-f0499cd1264b","s3":"57517a76-9e12-5f01-b5fe-3a0fa1527f43"},"source_file":"datacenters/projects/meta-cheyenne.json","source_record_id":"meta-cheyenne","source_record_sha256":"9aeb323d35f1c5fdef5221869f25597520bf2ececfd001ebb3dae9d4b1f98ca7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"aa8f9f96c934b5e097a08c76fda9bc4c871718f2baadf9ebf6b926473933da82"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a51d60551e72a6720e31/#project-da9fec8b-b7a1-54cb-afb9-7f534cbab584 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/da9fec8b-b7a1-54cb-afb9-7f534cbab584.json
db205e2d-f250-5c0b-861e-1c243f7be933 | imported:semiconductor-atlas:google-meitner-energy-center-texas | vcc-site-7b3778f58b65d557b1f9 | imported:semiconductor-atlas:google-meitner-energy-center-texas | Google Meitner Energy Center data center (Gray and Roberts counties) | United States | US | 35.5363 | -100.9602 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid of Pampa via Nominatim. The project spans Gray and Roberts counties, and Google's location list includes a Pampa, Texas site in development that matches it; no site address or parcel has been published. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 0fa34a95-4233-5fb6-af85-c271b4c81be0 | under_construction | 2026-06-04 | 131 | imported_documented_status | 0fa34a95-4233-5fb6-af85-c271b4c81be0 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"0fa34a95-4233-5fb6-af85-c271b4c81be0","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-meitner-energy-center-texas"},{"evidence_id":"48868792-ea79-5a41-9ada-4c2a26bdcd00","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-meitner-energy-center-texas"},{"evidence_id":"f22f60dd-d9d3-503c-a601-d7550799e10c","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-meitner-energy-center-texas"},{"evidence_id":"48868792-ea79-5a41-9ada-4c2a26bdcd00","notes":"Announced construction of the Meitner Energy Center jointly with Google; Intersect's business is pairing large loads with dedicated generation. Google closed its acquisition of Intersect in March 2026.","party":"Intersect","relationship_scope":"unknown","role":"developer","source_record_id":"google-meitner-energy-center-texas"},{"evidence_id":"f22f60dd-d9d3-503c-a601-d7550799e10c","notes":"Announced construction of the Meitner Energy Center jointly with Google; Intersect's business is pairing large loads with dedicated generation. Google closed its acquisition of Intersect in March 2026.","party":"Intersect","relationship_scope":"unknown","role":"developer","source_record_id":"google-meitner-energy-center-texas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://blog.google/innovation-and-ai/infrastructure-and-cloud/global-network/meitner-energy-center/ | https://blog.google/innovation-and-ai/infrastructure-and-cloud/global-network/meitner-energy-center/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Google Meitner Energy Center data center (Gray and Roberts counties) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"google-meitner-energy-center-texas"},"record":{"aliases":["Meitner Energy Center"],"id":"google-meitner-energy-center-texas","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Gray County","country":"US","lat":35.5363,"locality":"Pampa","lon":-100.9602,"note":"Town centroid of Pampa via Nominatim. The project spans Gray and Roberts counties, and Google's location list includes a Pampa, Texas site in development that matches it; no site address or parcel has been published.","precision":"locality","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-04","basis":"planned","metric":"power_capacity","note":"Combined co-located wind, solar and battery storage capacity; the data center's own load has not been disclosed.","power_scope":"onsite_generation","qualifier":"more_than","source_ids":["s2","s3"],"unit":"MW","value":1000}],"milestones":[{"date":"2026-03","event":"other","kind":"actual","note":"Google (Alphabet) completed its acquisition of Intersect.","source_ids":["s2","s3"]},{"date":"2026-06-04","event":"announced","kind":"actual","source_ids":["s1","s2","s3"]},{"date":"2026-06","event":"construction_started","kind":"actual","note":"The 4 June 2026 announcement launched construction; no exact groundbreaking date was given.","source_ids":["s2","s3"]}],"name":"Google Meitner Energy Center data center (Gray and Roberts counties)","notes":"Google's broader $40 billion Texas investment through 2027 is cited in the Intersect release but is statewide and is not recorded as a campus investment. The more-than-1 GW figure is co-located generation capacity, not the data center's load.","parties":[{"name":"Google","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Intersect","note":"Announced construction of the Meitner Energy Center jointly with Google; Intersect's business is pairing large loads with dedicated generation. Google closed its acquisition of Intersect in March 2026.","role":"developer","source_ids":["s2","s3"]}],"power_sources":[{"description":"Part of more than 1 GW of co-located wind, solar and storage; no per-technology breakdown disclosed.","source_ids":["s2","s3"],"type":"wind"},{"description":"Part of more than 1 GW of co-located wind, solar and storage; no per-technology breakdown disclosed.","source_ids":["s2","s3"],"type":"solar"},{"description":"Part of more than 1 GW of co-located wind, solar and storage; no per-technology breakdown disclosed.","source_ids":["s2","s3"],"type":"battery_storage"},{"description":"On-site gas generation provides firming and meets a minority share of site demand.","source_ids":["s2","s3"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260821141725/https://blog.google/innovation-and-ai/infrastructure-and-cloud/global-network/meitner-energy-center/","id":"s1","published":"2026-06-04","publisher":"Google","title":"We're announcing a new data center and energy investments in Gray and Roberts Counties, Texas","type":"company","url":"https://blog.google/innovation-and-ai/infrastructure-and-cloud/global-network/meitner-energy-center/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260619112227/https://www.intersect.com/news/google-and-intersect-deepen-texas-roots-with-new-data-center-and-energy-investments-in-gray-and-roberts-counties","id":"s2","published":"2026-06-04","publisher":"Intersect","title":"Google and Intersect Deepen Texas Roots with New Data Center and Energy Investments in Gray and Roberts Counties","type":"company","url":"https://www.intersect.com/news/google-and-intersect-deepen-texas-roots-with-new-data-center-and-energy-investments-in-gray-and-roberts-counties"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260824070056/https://www.powermag.com/google-launches-1-gw-plus-co-located-data-center-and-generation-complex-in-texas-panhandle/","id":"s3","published":"2026-06-04","publisher":"POWER Magazine","title":"Google Launches 1-GW-Plus Co-Located Data Center and Generation Complex in Texas Panhandle","type":"trade_press","url":"https://www.powermag.com/google-launches-1-gw-plus-co-located-data-center-and-generation-complex-in-texas-panhandle/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261009093925/https://datacenters.google/locations/","id":"s4","published":null,"publisher":"Google","title":"Locations of Google Data Centers","type":"company","url":"https://datacenters.google/locations/"}],"status":"under_construction","status_as_of":"2026-06-04","status_source_ids":["s1","s2","s3"],"summary":"Google data center being built alongside new dedicated generation at the Meitner Energy Center in Gray and Roberts counties in the Texas Panhandle; Google's location list shows a Pampa site in development. Google and Intersect, the energy developer Google closed on buying in March 2026, announced construction on 4 June 2026. The complex pairs the data center with more than 1 GW of wind, solar and battery storage, and on-site gas firming covers a minority of demand. The data center is designed for air cooling. Google has not disclosed the compute load, cost or opening date. An 800-acre Caprock Workforce Hub in Wheeler County is planned to house up to 3,500 workers.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"0fa34a95-4233-5fb6-af85-c271b4c81be0","s2":"48868792-ea79-5a41-9ada-4c2a26bdcd00","s3":"f22f60dd-d9d3-503c-a601-d7550799e10c","s4":"bbfa5a43-6fe0-5fc0-abdc-35a47bb670d7"},"source_file":"datacenters/projects/google-meitner-energy-center-texas.json","source_record_id":"google-meitner-energy-center-texas","source_record_sha256":"edccc714d49695ab62e24100a017138457b7ffddf49d512a8306190a8acbe1ab","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"6197bfa49b0be6fa6095b27096c5b72f6ed98a335030e50e4428b7b894e78f1f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-7b3778f58b65d557b1f9/#project-db205e2d-f250-5c0b-861e-1c243f7be933 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/db205e2d-f250-5c0b-861e-1c243f7be933.json
db7fc7c1-cc03-5473-80b8-31b36c8224d5 | imported:semiconductor-atlas:airtrunk-jhb4-iskandar-puteri | vcc-site-f8df65a48b8288eac8cb | imported:semiconductor-atlas:airtrunk-jhb4-iskandar-puteri | AirTrunk JHB4 Johor Bahru | Malaysia | MY | 1.4222 | 103.65 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | AirTrunk and W.Media name Iskandar Puteri without an address; the point is the Iskandar Puteri coordinate from its Wikipedia article, so it marks the city rather than the campus. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | c8b886b2-f389-5c16-8c04-57ce8610a2aa | announced | 2026-04-30 | 166 | imported_documented_status | c8b886b2-f389-5c16-8c04-57ce8610a2aa | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"c8b886b2-f389-5c16-8c04-57ce8610a2aa","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb4-iskandar-puteri"},{"evidence_id":"726733f4-b594-56ca-b0e1-a09e4981c6bc","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb4-iskandar-puteri"},{"evidence_id":"43759b4e-7c22-5d73-9971-6aff3b478ea6","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb4-iskandar-puteri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/ | https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AirTrunk JHB4 Johor Bahru as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"airtrunk-jhb4-iskandar-puteri","source_relations":[{"reason":"AirTrunk names separate JHB3 and JHB4 campuses, different site areas and 138/142 MW scopes; shared city centroid is not a shared site.","relationship":"separate_nearby_campuses","source_id":"airtrunk-jhb3-iskandar-puteri"},{"reason":"AirTrunk names separate campuses; shared JHB2 electrical supply does not merge JHB4 physical identity.","relationship":"separate_nearby_campuses","source_id":"airtrunk-jhb2-iskandar-puteri"}]},"record":{"aliases":["AirTrunk JHB4","JHB4 Johor Bahru"],"id":"airtrunk-jhb4-iskandar-puteri","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Johor Bahru District","country":"MY","lat":1.4222,"locality":"Iskandar Puteri","lon":103.65,"note":"AirTrunk and W.Media name Iskandar Puteri without an address; the point is the Iskandar Puteri coordinate from its Wikipedia article, so it marks the city rather than the campus.","precision":"locality","source_ids":["s1","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total capacity on AirTrunk's undated JHB4 page. The April 2026 announcement gives more than 280 MW of IT load for JHB4 and JHB3 together.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s2"],"unit":"MW","value":142},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s2"],"unit":"hectares","value":5.589},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Technical data hall area across eight halls; office and storage space of 3,300 square metres is listed separately.","qualifier":"exact","source_ids":["s2"],"unit":"sq_m","value":11150}],"milestones":[{"date":"2026-04-30","event":"announced","kind":"actual","source_ids":["s1","s3"]}],"name":"AirTrunk JHB4 Johor Bahru","notes":"The more than 280 MW of IT load, the MYR12 billion (USD3 billion) investment and the 3,000-plus construction jobs were announced for JHB4 and JHB3 together, so they are not recorded as metrics for this campus alone. AirTrunk's site page states a total capacity without saying whether it is IT load. No construction start or status update after the announcement was found. Related records: airtrunk-jhb1-johor and airtrunk-jhb2-iskandar-puteri. Wikipedia is cited only for the city coordinate.","parties":[{"name":"AirTrunk","role":"developer","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"Permanent 275 kV dual feed from the neighbouring JHB2 campus, per AirTrunk's site page.","source_ids":["s2"],"type":"grid"}],"related_ids":["airtrunk-jhb3-iskandar-puteri"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001022558/https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/","id":"s1","published":"2026-04-30","publisher":"AirTrunk","title":"AirTrunk doubles down in Malaysia with two new hyperscale campuses in Johor Bahru","type":"company","url":"https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001022558/https://airtrunk.com/location/jhb4-johor-bahru/","id":"s2","published":null,"publisher":"AirTrunk","title":"JHB4 Johor Bahru","type":"company","url":"https://airtrunk.com/location/jhb4-johor-bahru/"},{"accessed":"2026-10-09","id":"s3","published":"2026-04-30","publisher":"W.Media","title":"AirTrunk to invest US$ 3 billion in Johor to build two hyperscale campuses totaling 280MW capacity","type":"trade_press","url":"https://w.media/airtrunk-to-invest-us-3-billion-in-johor-to-build-two-hyperscale-campuses-totaling-280mw-capacity/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Iskandar Puteri","type":"other","url":"https://en.wikipedia.org/wiki/Iskandar_Puteri"}],"status":"announced","status_as_of":"2026-04-30","status_source_ids":["s1","s3"],"summary":"JHB4 is one of two new AirTrunk hyperscale campuses announced on 30 April 2026 in Iskandar Puteri, Johor, next to its JHB1 and JHB2 campuses. AirTrunk lists JHB4 at more than 142 MW across multiple buildings with eight data halls on about 5.589 hectares, fed at 275 kV from JHB2 and cooled with recycled water, aimed at high-density cloud and AI customers. AirTrunk put the combined investment for JHB4 and JHB3 at MYR12 billion (USD3 billion), with more than 3,000 construction jobs; no construction or opening dates were given.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c8b886b2-f389-5c16-8c04-57ce8610a2aa","s2":"726733f4-b594-56ca-b0e1-a09e4981c6bc","s3":"43759b4e-7c22-5d73-9971-6aff3b478ea6","s4":"958ea50b-8567-5d7b-a4a0-a2af3bc5a48c"},"source_file":"datacenters/projects/airtrunk-jhb4-iskandar-puteri.json","source_record_id":"airtrunk-jhb4-iskandar-puteri","source_record_sha256":"07abd8ec3bcc9e2dcff720b03e97ce1aedc9eac5322576de3c6bf12c9f2cda37","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"72508586d108a51e0f5dc5e2fd339c16d5c4aa33110cf6e353ec8f47193054b4"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f8df65a48b8288eac8cb/#project-db7fc7c1-cc03-5473-80b8-31b36c8224d5 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/db7fc7c1-cc03-5473-80b8-31b36c8224d5.json
dc6f83d9-dac5-563a-ba7e-ff18e27ba506 | imported:semiconductor-atlas:aws-salem-township-pennsylvania | vcc-site-b065c16b51237fbb767f | curated:amazon-salem-township-innovation-campus | AWS Salem Township Innovation Campus (Susquehanna) | United States | US | 41.0889 | -76.1489 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Sources place the campus adjacent to the Susquehanna Steam Electric Station but give no address; coordinates are the plant location from its Wikipedia article, so the campus point is approximate. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 08fe1497-9bfa-54ce-94a2-3a8c9ac3dd13 | partially_operational | 2026-10-09 | 4 | imported_documented_status | 0cd43266-a677-5102-a00b-577a5649e5f2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"08fe1497-9bfa-54ce-94a2-3a8c9ac3dd13","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"3cc51408-77e7-5ab2-8cbc-55ff0db95848","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"0cd43266-a677-5102-a00b-577a5649e5f2","notes":null,"party":"Amazon Web Services","relationship_scope":"unknown","role":"developer","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"08fe1497-9bfa-54ce-94a2-3a8c9ac3dd13","notes":"Bought the campus from Talen Energy in March 2024.","party":"Amazon Web Services","relationship_scope":"unknown","role":"owner","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"f19fd718-d740-5ba6-bc39-a2408ca98962","notes":"Bought the campus from Talen Energy in March 2024.","party":"Amazon Web Services","relationship_scope":"unknown","role":"owner","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"08fe1497-9bfa-54ce-94a2-3a8c9ac3dd13","notes":"Original developer of the Cumulus campus and seller to AWS; supplies power from Susquehanna.","party":"Talen Energy","relationship_scope":"unknown","role":"power_supplier","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"f7f0272b-091f-5aa6-a69c-0ed2b4fc1241","notes":"Original developer of the Cumulus campus and seller to AWS; supplies power from Susquehanna.","party":"Talen Energy","relationship_scope":"unknown","role":"power_supplier","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"f8d64fac-ca14-58b0-b778-3c1b4c715099","notes":"Original developer of the Cumulus campus and seller to AWS; supplies power from Susquehanna.","party":"Talen Energy","relationship_scope":"unknown","role":"power_supplier","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"f8d64fac-ca14-58b0-b778-3c1b4c715099","notes":"Handles transmission and delivery once supply moves in front of the meter.","party":"PPL Electric Utilities","relationship_scope":"unknown","role":"utility","source_record_id":"aws-salem-township-pennsylvania"},{"evidence_id":"f19fd718-d740-5ba6-bc39-a2408ca98962","notes":"Approved an industrial zoning district for the project and earlier agreed to a 10-year, 70% tax abatement.","party":"Salem Township","relationship_scope":"unknown","role":"government","source_record_id":"aws-salem-township-pennsylvania"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Amazon Web Services |  |  |  |  | https://www.amazoninnovationinpa.com/salem-township-innovation-campus/ | https://local21news.com/news/local/talen-energy-announces-sale-of-data-center-campus-to-amazon | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["approximate_locator_not_boundary","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same acquired Cumulus/AWS Salem Township campus beside Susquehanna, with shared Amazon campus URL. Source spans the operating campus and long-term buildout; existing record selects active campus construction.","source_record_id":"aws-salem-township-pennsylvania","target_physical_site_stable_key":"curated:amazon-salem-township-innovation-campus"},"record":{"aliases":["Cumulus data center campus","Salem Township Innovation Campus"],"id":"aws-salem-township-pennsylvania","last_reviewed":"2026-10-09","location":{"admin1":"Pennsylvania","admin2":"Luzerne County","country":"US","lat":41.0889,"locality":"Salem Township","lon":-76.1489,"note":"Sources place the campus adjacent to the Susquehanna Steam Electric Station but give no address; coordinates are the plant location from its Wikipedia article, so the campus point is approximate.","precision":"approximate_site","source_ids":["s1","s2","s4"]},"metrics":[{"applies_to":"campus","as_of":"2024-03-04","basis":"planned","metric":"power_capacity","note":"Planned campus size when Talen sold Cumulus to AWS.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s4"],"unit":"MW","value":960},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"Size on Amazon's undated campus page (date accessed); the same site's projects overview gives about 1,062 acres acquired in 2024.","qualifier":"exact","source_ids":["s6"],"unit":"acres","value":1200},{"applies_to":"campus","as_of":"2026-10-09","basis":"acquired","metric":"land_area","note":"Undated project overview page; the date is when it was accessed.","qualifier":"approximately","source_ids":["s7"],"unit":"acres","value":1062},{"applies_to":"campus","as_of":"2024-05-30","basis":"planned","metric":"land_area","note":"Area Amazon sought to rezone in 2024.","qualifier":"approximately","source_ids":["s2"],"unit":"acres","value":1600},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"Count on Amazon's undated campus page (date accessed). In 2024 local reporting described plans for 15 more data center buildings beyond the existing one.","qualifier":"exact","source_ids":["s6","s2"],"unit":"count","value":20},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_permanent","note":"Undated campus page (date accessed); a 2024 Amazon estimate reported up to 600 jobs.","qualifier":"approximately","source_ids":["s6"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2024-05-30","basis":"planned","metric":"jobs_permanent","qualifier":"up_to","source_ids":["s2"],"unit":"count","value":600}],"milestones":[{"date":"2024-03-04","event":"site_acquired","kind":"actual","note":"Talen announced the sale of the Cumulus campus to AWS for $650 million; this is a purchase price, not a build-out budget.","source_ids":["s1"]},{"date":"2024-05","event":"zoning_approved","kind":"actual","note":"Township approved an industrial district enabling the campus.","source_ids":["s2"]},{"date":"2025-06-11","event":"other","kind":"actual","note":"Talen and Amazon signed an expanded nuclear power purchase agreement.","source_ids":["s3","s4"]},{"date":"2025-10","event":"construction_started","kind":"actual","note":"Per the timeline on Amazon's campus project page.","source_ids":["s6"]},{"date":"2026-03","event":"permit_approved","kind":"actual","note":"A news item dated 31 March 2026 on Amazon's campus page reports that an agency approved a data center water permit; the page names neither the agency nor the exact approval date.","source_ids":["s6"]}],"name":"AWS Salem Township Innovation Campus (Susquehanna)","notes":"Status: Amazon's 2024 purchase included an existing data center at the site, and Amazon's campus page says it operates a data center campus there while labelling the site as under active construction; its timeline lists commissioning and operation of the new buildings as to be determined, so the record uses partially operational. Amazon's project pages carry no publication date, so statements from them use the date accessed (2026-10-09). Amazon's at least $20 billion Pennsylvania figure covers several campuses and is not assigned to this site. Amazon and Talen also plan to explore small modular reactors.","parties":[{"name":"Amazon Web Services","role":"developer","source_ids":["s1","s5","s6"]},{"name":"Amazon Web Services","note":"Bought the campus from Talen Energy in March 2024.","role":"owner","source_ids":["s1","s2"]},{"name":"Talen Energy","note":"Original developer of the Cumulus campus and seller to AWS; supplies power from Susquehanna.","role":"power_supplier","source_ids":["s1","s3","s4"]},{"name":"PPL Electric Utilities","note":"Handles transmission and delivery once supply moves in front of the meter.","role":"utility","source_ids":["s4"]},{"name":"Salem Township","note":"Approved an industrial zoning district for the project and earlier agreed to a 10-year, 70% tax abatement.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"Talen agreed in June 2025 to supply 1,920 MW from the Susquehanna nuclear plant through 2042, reaching full volume by 2032 at the latest, for AWS data centers in the region, possibly including other Pennsylvania sites. The earlier co-located arrangement shifts to grid (front-of-the-meter) delivery after transmission work timed for spring 2026. FERC had rejected a bid to raise the load the plant could serve directly.","source_ids":["s3","s4"],"type":"nuclear"},{"description":"After the reconfiguration, Susquehanna output flows to the PJM grid and PPL Electric Utilities delivers power, with Talen as Amazon's retail supplier.","source_ids":["s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20240305032144/https://local21news.com/news/local/talen-energy-announces-sale-of-data-center-campus-to-amazon","id":"s1","published":"2024-03-04","publisher":"local21news (WHP)","title":"Talen Energy announces sale of data center campus to Amazon","type":"news","url":"https://local21news.com/news/local/talen-energy-announces-sale-of-data-center-campus-to-amazon"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260419105326/https://www.phillyvoice.com/amazon-pennsylvania-data-center-salem-luzerne-county/","id":"s2","published":"2024-05-30","publisher":"PhillyVoice","title":"Amazon gets zoning approval for massive data center campus in Luzerne County","type":"news","url":"https://phillyvoice.com/amazon-pennsylvania-data-center-salem-luzerne-county"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260512223622/https://www.publicpower.org/periodical/article/talen-energy-expands-nuclear-energy-relationship-with-amazon","id":"s3","published":"2025-06-11","publisher":"American Public Power Association","title":"Talen Energy expands nuclear energy relationship with Amazon","type":"trade_press","url":"https://www.publicpower.org/periodical/article/talen-energy-expands-nuclear-energy-relationship-with-amazon"},{"accessed":"2026-10-09","id":"s4","published":"2025-06-12","publisher":"World Nuclear News","title":"New supply agreement expands Talen-Amazon partnership","type":"trade_press","url":"https://wnn.world-nuclear.org/articles/new-supply-agreement-expands-talen-amazon-partnership"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Amazon","title":"Amazon plans to invest $20 billion in Pennsylvania to expand cloud computing infrastructure and advance AI innovation","type":"company","url":"https://www.aboutamazon.com/news/aws/amazon-pennsylvania-investment-cloud-infrastructure-ai-innovation"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260829150855/https://www.amazoninnovationinpa.com/salem-township-innovation-campus/","id":"s6","published":null,"publisher":"Amazon Innovation in PA (project website)","title":"Salem Township Innovation Campus","type":"other","url":"https://www.amazoninnovationinpa.com/salem-township-innovation-campus/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260829150902/https://www.amazoninnovationinpa.com/projects-across-pennsylvania/","id":"s7","published":null,"publisher":"Amazon Innovation in PA (project website)","title":"Projects Across Pennsylvania","type":"other","url":"https://www.amazoninnovationinpa.com/projects-across-pennsylvania/"}],"status":"partially_operational","status_as_of":"2026-10-09","status_source_ids":["s6","s2"],"summary":"Amazon Web Services campus next to Talen Energy's Susquehanna nuclear plant in Salem Township, Luzerne County. AWS bought Talen's Cumulus campus, planned at up to 960 MW, in March 2024 and won township rezoning in May 2024. In June 2025 Talen agreed to supply Amazon 1,920 MW from Susquehanna through 2042, moving delivery onto the grid after a spring 2026 reconfiguration. The site was one of the first two named in Amazon's plan to invest at least $20 billion in Pennsylvania. Amazon says it operates a data center campus there and shows active construction since October 2025 toward 20 data centers.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"08fe1497-9bfa-54ce-94a2-3a8c9ac3dd13","s2":"f19fd718-d740-5ba6-bc39-a2408ca98962","s3":"f7f0272b-091f-5aa6-a69c-0ed2b4fc1241","s4":"f8d64fac-ca14-58b0-b778-3c1b4c715099","s5":"3cc51408-77e7-5ab2-8cbc-55ff0db95848","s6":"0cd43266-a677-5102-a00b-577a5649e5f2","s7":"957eb50b-7cbf-5cff-afb0-65812b432532"},"source_file":"datacenters/projects/aws-salem-township-pennsylvania.json","source_record_id":"aws-salem-township-pennsylvania","source_record_sha256":"4dd6dde012f8c93b41327c85112d56db632e692cc634ebdc5e6570285d367043","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"c993320812fc50d933736bb71f6e817a7ac63c5c196656835649e75edb4e0cc4"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b065c16b51237fbb767f/#project-dc6f83d9-dac5-563a-ba7e-ff18e27ba506 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/dc6f83d9-dac5-563a-ba7e-ff18e27ba506.json
dd65fe26-5f6d-52e8-96b6-8709ca040b13 | imported:semiconductor-atlas:mgx-bpifrance-mistral-nvidia-campus | vcc-site-27b404b316b5fece1ef1 | imported:semiconductor-atlas:mgx-bpifrance-mistral-nvidia-campus | Campus AI Fouju | France | FR | 48.5864 | 2.7785 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Nominatim centroid of the commune of Fouju; sources name the commune but not a parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | a82abc73-6eb4-56a6-896f-91d027b975eb | under_construction | 2026-09-01 | 42 | imported_documented_status | 6658457c-af48-5fe0-aa78-c7f6b154b709 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"a82abc73-6eb4-56a6-896f-91d027b975eb","notes":"Joint venture that acquires land, builds high-voltage and shared infrastructure, and co-invests with data center developers; site companies Campus AI SPV1, SPV2 and SPV4 are authorized to operate DC1, DC2 and DC4.","party":"Campus AI","relationship_scope":"unknown","role":"developer","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"6658457c-af48-5fe0-aa78-c7f6b154b709","notes":"Joint venture that acquires land, builds high-voltage and shared infrastructure, and co-invests with data center developers; site companies Campus AI SPV1, SPV2 and SPV4 are authorized to operate DC1, DC2 and DC4.","party":"Campus AI","relationship_scope":"unknown","role":"developer","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"c1df1794-f892-58f1-b497-68bf7532753d","notes":null,"party":"MGX","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"a82abc73-6eb4-56a6-896f-91d027b975eb","notes":null,"party":"MGX","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"c1df1794-f892-58f1-b497-68bf7532753d","notes":null,"party":"Bpifrance","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"a82abc73-6eb4-56a6-896f-91d027b975eb","notes":null,"party":"Bpifrance","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"c1df1794-f892-58f1-b497-68bf7532753d","notes":null,"party":"Mistral AI","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"a82abc73-6eb4-56a6-896f-91d027b975eb","notes":null,"party":"Mistral AI","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"c1df1794-f892-58f1-b497-68bf7532753d","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"a82abc73-6eb4-56a6-896f-91d027b975eb","notes":null,"party":"NVIDIA","relationship_scope":"unknown","role":"investor","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"6658457c-af48-5fe0-aa78-c7f6b154b709","notes":"Described as the founding client, securing up to 200 MW of compute capacity with Campus AI (announced 2026-06-01; the source does not say all of it is at Fouju).","party":"Mistral AI","relationship_scope":"unknown","role":"tenant","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"a82abc73-6eb4-56a6-896f-91d027b975eb","notes":"General contractor (consortium led by Eiffage Énergie Systèmes) for the 400/33 kV substation and shared infrastructure, contract above EUR 120 million.","party":"Eiffage","relationship_scope":"unknown","role":"builder","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"c1df1794-f892-58f1-b497-68bf7532753d","notes":"Signed a fast-track grid connection agreement with Campus AI on 2026-01-26 and was authorized to build a substation at the site.","party":"RTE","relationship_scope":"unknown","role":"utility","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"6658457c-af48-5fe0-aa78-c7f6b154b709","notes":"Signed a fast-track grid connection agreement with Campus AI on 2026-01-26 and was authorized to build a substation at the site.","party":"RTE","relationship_scope":"unknown","role":"utility","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"6658457c-af48-5fe0-aa78-c7f6b154b709","notes":"Issued the environmental authorizations on 2026-07-29.","party":"Préfecture de Seine-et-Marne","relationship_scope":"unknown","role":"government","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},{"evidence_id":"06a5133c-bebf-5bfb-ae62-8ed8e3c29287","notes":"Issued the environmental authorizations on 2026-07-29.","party":"Préfecture de Seine-et-Marne","relationship_scope":"unknown","role":"government","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | Mistral AI |  | https://www.briedesrivieresetchateaux.fr/wp-content/uploads/2026/09/Calendrier_du_projet_Campus_IA_.pdf | https://www.privacy.eiffage.com/files/live/sites/metal/files/publications/PR_Eiffage_Campus%2520AI%2520enters%2520the%2520implementation%2520phase_20260602.pdf | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Campus AI Fouju as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"mgx-bpifrance-mistral-nvidia-campus"},"record":{"aliases":["Campus IA","Campus AI","Campus IA Fouju"],"id":"mgx-bpifrance-mistral-nvidia-campus","last_reviewed":"2026-10-09","location":{"admin1":"Île-de-France","admin2":"Seine-et-Marne","country":"FR","lat":48.5864,"locality":"Fouju","lon":2.7785,"note":"Nominatim centroid of the commune of Fouju; sources name the commune but not a parcel.","precision":"locality","source_ids":["s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-13","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"MW","value":1400},{"applies_to":"campus","as_of":"2026-06-02","basis":"planned","metric":"power_capacity","note":"Final output rating of the 400/33 kV substation Eiffage is building; same headline figure as the campus capacity, not additional.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":1400},{"applies_to":"campus","as_of":"2026-08-13","basis":"reported","metric":"investment","note":"News report attributing the sum to MGX, NVIDIA, Mistral AI and Bpifrance; no company source opened for this figure.","qualifier":"exact","source_ids":["s4"],"unit":"EUR","value":50000000000},{"applies_to":"campus","as_of":"2026-08-13","basis":"planned","metric":"land_area","note":"Of which 73 hectares to be built on.","qualifier":"exact","source_ids":["s4"],"unit":"hectares","value":89},{"applies_to":"campus","as_of":"2026-08-13","basis":"planned","metric":"buildings","note":"Data center buildings; a training center is additional.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":11},{"applies_to":"phase","as_of":"2026-09-01","basis":"planned","metric":"buildings","note":"First three data centers, plus a reception and training building and the substation, due early 2028.","phase_label":"Phase 1","qualifier":"exact","source_ids":["s3"],"unit":"count","value":3}],"milestones":[{"date":"2025-05-19","event":"announced","kind":"actual","note":"Joint venture announced at the Choose France summit for an Île-de-France campus.","source_ids":["s1","s3"]},{"date":"2025-10-13","event":"other","kind":"actual","note":"Start of the voluntary public pre-consultation under the CNDP framework (ran to 2025-11-23).","source_ids":["s3"]},{"date":"2026-01-26","event":"other","kind":"actual","note":"Fast-track grid connection agreement signed with RTE.","source_ids":["s3"]},{"date":"2026-04-30","event":"other","kind":"actual","note":"Single public inquiry opened (to 2026-05-30) covering environmental authorizations, local plan change and building permit.","source_ids":["s3"]},{"date":"2026-06","event":"other","kind":"actual","note":"At Choose France 2026 the joint venture said it plans up to 3 GW in France through a second, not yet named site that will complement the Fouju campus.","source_ids":["s5"]},{"date":"2026-06-02","event":"other","kind":"actual","note":"Eiffage named general contractor for the substation and shared infrastructure.","source_ids":["s2"]},{"date":"2026-07-23","event":"zoning_approved","kind":"actual","note":"Approval of the Fouju local plan (PLU) amendment.","source_ids":["s3"]},{"date":"2026-07-29","event":"permit_approved","kind":"actual","note":"Prefectoral environmental authorizations for data centers and an RTE substation.","source_ids":["s3","s4"]},{"date":"2026-08-28","event":"permit_approved","kind":"actual","note":"Building permit for phase 1.","source_ids":["s3"]},{"date":"2026-09","event":"construction_started","kind":"actual","note":"Start of phase-1 works as listed in the local authority's project timeline; archaeological excavations on 15 hectares were also under way from May 2026.","source_ids":["s3"]},{"date":"2028","event":"first_operational","kind":"planned","note":"Early 2028 delivery of the first phase per the local timeline; the 2025 announcement targeted service by 2028.","source_ids":["s1","s3"]}],"name":"Campus AI Fouju","notes":"Investment figures for the campus vary widely in public reporting; only the EUR 50 billion figure from an opened news source is recorded. A June 2026 announcement raised the joint venture's national target to up to 3 GW with an unnamed second site, which is not part of this record. Opponents (collective Stop IA à Fouju) said they would file an appeal against the authorizations.","parties":[{"name":"Campus AI","note":"Joint venture that acquires land, builds high-voltage and shared infrastructure, and co-invests with data center developers; site companies Campus AI SPV1, SPV2 and SPV4 are authorized to operate DC1, DC2 and DC4.","role":"developer","source_ids":["s2","s3"]},{"name":"MGX","role":"investor","source_ids":["s1","s2"]},{"name":"Bpifrance","role":"investor","source_ids":["s1","s2"]},{"name":"Mistral AI","role":"investor","source_ids":["s1","s2"]},{"name":"NVIDIA","role":"investor","source_ids":["s1","s2"]},{"name":"Mistral AI","note":"Described as the founding client, securing up to 200 MW of compute capacity with Campus AI (announced 2026-06-01; the source does not say all of it is at Fouju).","role":"tenant","source_ids":["s3"]},{"name":"Eiffage","note":"General contractor (consortium led by Eiffage Énergie Systèmes) for the 400/33 kV substation and shared infrastructure, contract above EUR 120 million.","role":"builder","source_ids":["s2"]},{"name":"RTE","note":"Signed a fast-track grid connection agreement with Campus AI on 2026-01-26 and was authorized to build a substation at the site.","role":"utility","source_ids":["s1","s3"]},{"name":"Préfecture de Seine-et-Marne","note":"Issued the environmental authorizations on 2026-07-29.","role":"government","source_ids":["s3","s4"]}],"power_sources":[{"description":"Fast-track connection to the RTE transmission grid through a new 400/33 kV substation rated for 1.4 GW at full build-out.","source_ids":["s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260108033608/https://www.polytechnique.edu/sites/default/files/content/communiques/fichiers/2025-05/Communique%20Presse%20-%20MGX%2C%20Bpifrance%2C%20Mistral%20AI%20et%20NVIDIA%20annoncent%20la%20cre%CC%81ation%20d%E2%80%99une%20JV%20pour%20de%CC%81velopper%20en%20France%20le%20plus%20grand%20campus%20IA%20d'Europe.pdf","id":"s1","published":"2025-05-19","publisher":"MGX, Bpifrance, Mistral AI and NVIDIA (via École polytechnique)","title":"MGX, Bpifrance, Mistral AI et NVIDIA annoncent la création d'une joint-venture pour développer en France le plus grand campus IA d'Europe","type":"company","url":"https://www.polytechnique.edu/sites/default/files/content/communiques/fichiers/2025-05/Communique%20Presse%20-%20MGX%2C%20Bpifrance%2C%20Mistral%20AI%20et%20NVIDIA%20annoncent%20la%20cre%CC%81ation%20d%E2%80%99une%20JV%20pour%20de%CC%81velopper%20en%20France%20le%20plus%20grand%20campus%20IA%20d%27Europe.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2026-06-02","publisher":"Eiffage","title":"Campus AI enters the implementation phase: Eiffage selected for deployment of shared infrastructure on the Fouju Campus","type":"company","url":"https://www.privacy.eiffage.com/files/live/sites/metal/files/publications/PR_Eiffage_Campus%2520AI%2520enters%2520the%2520implementation%2520phase_20260602.pdf"},{"accessed":"2026-10-09","id":"s3","published":"2026-09-01","publisher":"Communauté de communes Brie des Rivières et Châteaux","title":"Calendrier du projet Campus IA","type":"government","url":"https://www.briedesrivieresetchateaux.fr/wp-content/uploads/2026/09/Calendrier_du_projet_Campus_IA_.pdf"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-13","publisher":"Next","title":"La préfecture de Seine-et-Marne autorise l'installation de Campus IA à Fouju","type":"news","url":"https://next.ink/brief-article/la-prefecture-de-seine-et-marne-autorise-linstallation-de-campus-ia-a-fouju/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260610131134/https://www.mac4ever.com/ia/196474-campus-ai-mistral-bpifrance-et-mgx-prevoient-jusqu-a-3-gw-de-puissance-ia-en-france","id":"s5","published":"2026-06-02","publisher":"Mac4Ever","title":"Campus AI : Mistral, Bpifrance et MGX prévoient jusqu'à 3 GW de puissance IA en France","type":"news","url":"https://www.mac4ever.com/ia/196474-campus-ai-mistral-bpifrance-et-mgx-prevoient-jusqu-a-3-gw-de-puissance-ia-en-france"}],"status":"under_construction","status_as_of":"2026-09-01","status_source_ids":["s3","s5"],"summary":"Campus AI, a joint venture of the UAE fund MGX, French public bank Bpifrance, Mistral AI and NVIDIA, is developing a 1.4 GW AI data center campus at Fouju in Seine-et-Marne, about 40 km southeast of Paris. Plans call for roughly eleven data center buildings plus a training building on about 89 hectares, fed by a dedicated 400 kV substation. Environmental authorizations and the phase-one building permit were granted in summer 2026, phase-one works were scheduled from September 2026, and the first three data centers are targeted for early 2028. Local opponents have said they will appeal.","workloads":["ai_training","ai_inference","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"c1df1794-f892-58f1-b497-68bf7532753d","s2":"a82abc73-6eb4-56a6-896f-91d027b975eb","s3":"6658457c-af48-5fe0-aa78-c7f6b154b709","s4":"06a5133c-bebf-5bfb-ae62-8ed8e3c29287","s5":"5d40cf34-3a05-5d7a-a1eb-6e8e73380047"},"source_file":"datacenters/projects/mgx-bpifrance-mistral-nvidia-campus.json","source_record_id":"mgx-bpifrance-mistral-nvidia-campus","source_record_sha256":"0b259aac6c9d22a01d23f16f3ee0a66a849ada132bdcc560ff99ec4cba6639d4","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"37a8693b1b77e0a121c59e3f185ab30784a069428fa03b8dbaf87ea2426957ff"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-27b404b316b5fece1ef1/#project-dd65fe26-5f6d-52e8-96b6-8709ca040b13 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/dd65fe26-5f6d-52e8-96b6-8709ca040b13.json
dd87fe4b-fdb0-5c4e-a906-70fda834e424 | imported:semiconductor-atlas:powerhouse-poe-louisville-camp-ground-road | vcc-site-f7c2acac6f50afd8adde | imported:semiconductor-atlas:powerhouse-poe-louisville-camp-ground-road | PowerHouse Louisville hyperscale campus (Camp Ground Road) | United States | US | 38.2561 | -85.7514 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Local sources place the campus on Camp Ground Road in southern or southwest Louisville without coordinates. The point is the Louisville city coordinate from its Wikipedia article, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 371c4d8b-d919-5614-9c6c-2d8b2976c0af | under_construction | 2026-08-13 | 61 | imported_documented_status | 59461ee2-4f88-55bb-8263-9c2e8168774b | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6d7b5470-faec-5b2e-92c4-f5e7afb58e56","notes":"Joint venture partner; a division of American Real Estate Partners.","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"f67089b5-4755-5edd-bb40-fa6872436fd5","notes":"Joint venture partner; a division of American Real Estate Partners.","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"371c4d8b-d919-5614-9c6c-2d8b2976c0af","notes":"Joint venture partner; a division of American Real Estate Partners.","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"dbc6108f-2dd5-5967-9778-3028f2d9a498","notes":"Joint venture partner; a division of American Real Estate Partners.","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"6d7b5470-faec-5b2e-92c4-f5e7afb58e56","notes":"Louisville-based joint venture partner, described in July 2026 coverage as building the campus.","party":"Poe Companies","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"f67089b5-4755-5edd-bb40-fa6872436fd5","notes":"Louisville-based joint venture partner, described in July 2026 coverage as building the campus.","party":"Poe Companies","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"371c4d8b-d919-5614-9c6c-2d8b2976c0af","notes":"Louisville-based joint venture partner, described in July 2026 coverage as building the campus.","party":"Poe Companies","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"59461ee2-4f88-55bb-8263-9c2e8168774b","notes":"Louisville-based joint venture partner, described in July 2026 coverage as building the campus.","party":"Poe Companies","relationship_scope":"unknown","role":"developer","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"6d7b5470-faec-5b2e-92c4-f5e7afb58e56","notes":"Announced the campus as its first hyperscale data center customer and is building a new switching station.","party":"Louisville Gas and Electric (LG&E)","relationship_scope":"unknown","role":"utility","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"f67089b5-4755-5edd-bb40-fa6872436fd5","notes":"Announced the campus as its first hyperscale data center customer and is building a new switching station.","party":"Louisville Gas and Electric (LG&E)","relationship_scope":"unknown","role":"utility","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},{"evidence_id":"371c4d8b-d919-5614-9c6c-2d8b2976c0af","notes":"Announced the campus as its first hyperscale data center customer and is building a new switching station.","party":"Louisville Gas and Electric (LG&E)","relationship_scope":"unknown","role":"utility","source_record_id":"powerhouse-poe-louisville-camp-ground-road"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.wdrbwave.com/2026/07/18/louisville-data-center-opponents-rally-metro-hall-push-stronger-regulations/ | https://www.wdrbwave.com/2025/01/17/louisville-welcome-kentuckys-first-hyperscale-data-center/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve PowerHouse Louisville hyperscale campus (Camp Ground Road) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"powerhouse-poe-louisville-camp-ground-road"},"record":{"aliases":["PowerHouse Louisville","Camp Ground Road data center","Campground Road data center"],"id":"powerhouse-poe-louisville-camp-ground-road","last_reviewed":"2026-10-09","location":{"admin1":"Kentucky","admin2":"Jefferson County","country":"US","lat":38.2561,"locality":"Louisville","lon":-85.7514,"note":"Local sources place the campus on Camp Ground Road in southern or southwest Louisville without coordinates. The point is the Louisville city coordinate from its Wikipedia article, not the site.","precision":"locality","source_ids":["s3","s5","s6","s7"]},"metrics":[{"applies_to":"campus","as_of":"2025-01-16","basis":"planned","metric":"power_capacity","note":"Campus size given at announcement; scope not stated.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":400},{"applies_to":"campus","as_of":"2025-01-16","basis":"contracted","metric":"power_capacity","note":"Initial utility power capacity secured from LG&E, with near-term expansion to up to 402 MW.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":335},{"applies_to":"phase","as_of":"2025-01-16","basis":"planned","metric":"power_capacity","phase_label":"First power delivery (October 2026)","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":130},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Maximum utility power shown on PowerHouse's undated campus page, accessed 2026-10-09; higher than the 400 MW announced in 2025.","power_scope":"grid_connection","qualifier":"up_to","source_ids":["s4"],"unit":"MW","value":525},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"News reports describe 150 acres (2025) or more than 150 acres (2026).","qualifier":"exact","source_ids":["s4"],"unit":"acres","value":154},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"July 2026 local reporting instead described seven warehouse-sized buildings.","qualifier":"up_to","source_ids":["s4"],"unit":"count","value":6},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Developable floor area listed on the campus page as 1.8M sq ft.","qualifier":"approximately","source_ids":["s4"],"unit":"sq_ft","value":1800000},{"applies_to":"campus","as_of":"2025-01-16","basis":"planned","metric":"jobs_permanent","note":"Operational jobs; hundreds of construction jobs were also expected.","qualifier":"approximately","source_ids":["s3"],"unit":"count","value":200}],"milestones":[{"date":"2025-01-16","event":"announced","kind":"actual","source_ids":["s1","s3"]},{"date":"2025","event":"construction_started","kind":"planned","note":"The January 2025 announcement scheduled construction to begin in 2025 with zoning already in place. Local reporting in July and August 2026 described the campus as under construction; no exact start date was found.","source_ids":["s1","s2","s3","s5","s6"]},{"date":"2026-Q4","event":"first_operational","kind":"planned","note":"First building targeted for Q4 2026 and the first 130 MW for October 2026; the company website, as reported in July 2026, said the first phase could come online as soon as October.","source_ids":["s1","s2","s4","s5"]}],"name":"PowerHouse Louisville hyperscale campus (Camp Ground Road)","notes":"No investment figure was found. The LG&E release names the joint venture but not the street; WAVE's January 2025 report ties it to 150 acres on Camp Ground Road, and the 2026 local reports, which do not mention PowerHouse (one names Poe as the builder), describe the Camp Ground Road campus as under construction. In January 2025 Poe's president said a large technology company would establish a significant presence there without naming it; WAVE suggested Meta or Microsoft as likely, which is unconfirmed. Louisville Metro Council's six-month data center moratorium of August 2026 applies to new proposals. Whether the October 2026 first-phase target was met was not confirmed by 2026-10-09.","parties":[{"name":"PowerHouse Data Centers","note":"Joint venture partner; a division of American Real Estate Partners.","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Poe Companies","note":"Louisville-based joint venture partner, described in July 2026 coverage as building the campus.","role":"developer","source_ids":["s1","s2","s3","s5"]},{"name":"Louisville Gas and Electric (LG&E)","note":"Announced the campus as its first hyperscale data center customer and is building a new switching station.","role":"utility","source_ids":["s1","s2","s3"]}],"power_sources":[{"description":"LG&E supply through a new utility switching station due for completion in September 2026 and a dedicated on-site substation.","source_ids":["s1","s2","s5"],"type":"grid"},{"description":"Backup generators on site, per local reporting; their fuel is not stated.","source_ids":["s5"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-01-16","publisher":"PPL Corporation / Louisville Gas and Electric","title":"LG&E announces first major data center electric customer","type":"utility","url":"https://news.pplweb.com/2025-01-16-LG-E-announces-first-major-data-center-electric-customer"},{"accessed":"2026-10-09","id":"s2","published":"2025-01-27","publisher":"Data Center Frontier","title":"Let's Go Build Some Data Centers: PowerHouse Drives Hyperscale and AI Infrastructure Across North America","type":"trade_press","url":"https://www.datacenterfrontier.com/site-selection/article/55263723/lets-go-build-some-data-centers-powerhouse-drives-hyperscale-and-ai-infrastructure-across-north-america"},{"accessed":"2026-10-09","id":"s3","published":"2025-01-16","publisher":"WAVE","title":"Louisville to welcome Kentucky's first Hyperscale Data Center","type":"news","url":"https://www.wdrbwave.com/2025/01/17/louisville-welcome-kentuckys-first-hyperscale-data-center/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261008172715/https://www.powerhousedata.com/data-center/ph-louisville","id":"s4","published":null,"publisher":"PowerHouse Data Centers","title":"PowerHouse Louisville","type":"company","url":"https://powerhousedata.com/data-center/ph-louisville"},{"accessed":"2026-10-09","id":"s5","published":"2026-07-18","publisher":"WAVE","title":"Louisville data center opponents rally at Metro Hall, push for stronger regulations","type":"news","url":"https://www.wdrbwave.com/2026/07/18/louisville-data-center-opponents-rally-metro-hall-push-stronger-regulations/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260923161021/https://www.lpm.org/news/2026-08-13/louisville-metro-council-approves-data-center-moratorium-as-new-proposal-sparks-controversy","id":"s6","published":"2026-08-13","publisher":"Louisville Public Media","title":"Louisville Metro Council approves data center moratorium as new proposal sparks controversy","type":"news","url":"https://www.lpm.org/news/2026-08-13/louisville-metro-council-approves-data-center-moratorium-as-new-proposal-sparks-controversy"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261006020319/https://en.wikipedia.org/wiki/Louisville,_Kentucky","id":"s7","published":null,"publisher":"Wikipedia","title":"Louisville, Kentucky","type":"other","url":"https://en.wikipedia.org/wiki/Louisville,_Kentucky"}],"status":"under_construction","status_as_of":"2026-08-13","status_source_ids":["s5","s6"],"summary":"Hyperscale data center campus on Camp Ground Road in southwest Louisville, Kentucky, developed by a joint venture of PowerHouse Data Centers and Louisville-based Poe Companies and billed as the state's first hyperscale campus. Announced in January 2025 as a 400 MW campus with 335 MW of initial LG&E power secured and the first 130 MW due in October 2026, it sits on about 150 acres with zoning already in place. PowerHouse's campus page now lists up to 525 MW of utility power and up to six buildings. Local reporting in mid-2026 described seven warehouse-sized buildings under construction, with the first phase expected online as soon as October 2026; no tenant has been named.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6d7b5470-faec-5b2e-92c4-f5e7afb58e56","s2":"f67089b5-4755-5edd-bb40-fa6872436fd5","s3":"371c4d8b-d919-5614-9c6c-2d8b2976c0af","s4":"dbc6108f-2dd5-5967-9778-3028f2d9a498","s5":"59461ee2-4f88-55bb-8263-9c2e8168774b","s6":"97cd85dd-d2e1-5e36-93c2-a8d9ce783e15","s7":"2f03544a-3ea0-59af-bba4-5066d01054f2"},"source_file":"datacenters/projects/powerhouse-poe-louisville-camp-ground-road.json","source_record_id":"powerhouse-poe-louisville-camp-ground-road","source_record_sha256":"37f733b78fae52fff6eec0b5271ca6a26fd3348359f5cf17f00c007fea8c3fd5","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5471b111c6ac92c990b79489fd4ae91e75783ea10c7e4aef405795c3ffdb8b73"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f7c2acac6f50afd8adde/#project-dd87fe4b-fdb0-5c4e-a906-70fda834e424 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/dd87fe4b-fdb0-5c4e-a906-70fda834e424.json
ddaae950-1e47-58e8-b57a-37aeed0eba7a | imported:semiconductor-atlas:koacc-national-ai-computing-center-haenam | vcc-site-af1774a8d4eb3398e76e | imported:semiconductor-atlas:koacc-national-ai-computing-center-haenam | National AI Computing Center, Solaseado (Haenam) | Korea, Republic of | KR | 34.5742 | 126.5975 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Sources place the site in the Solaseado data center park in Sani-myeon, Haenam County, without coordinates; the point is the Haenam County coordinate from its Wikipedia article, so it marks the county, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 4c353195-1c08-58a5-88f0-fc05ceac97af | under_construction | 2026-08-03 | 71 | imported_documented_status | 9e744646-545f-5d48-bfb5-62a2e2aab2b9 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"9e744646-545f-5d48-bfb5-62a2e2aab2b9","notes":"Public-private special purpose company formed in June 2026 to build and operate the center.","party":"Korea AI Computing Center Co., Ltd. (KOACC)","relationship_scope":"unknown","role":"developer","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"6eec6a2f-a48c-5835-a5fe-dd4ca04c5ae8","notes":"Public-private special purpose company formed in June 2026 to build and operate the center.","party":"Korea AI Computing Center Co., Ltd. (KOACC)","relationship_scope":"unknown","role":"developer","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"9e744646-545f-5d48-bfb5-62a2e2aab2b9","notes":null,"party":"Korea AI Computing Center Co., Ltd. (KOACC)","relationship_scope":"unknown","role":"operator","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"6eec6a2f-a48c-5835-a5fe-dd4ca04c5ae8","notes":null,"party":"Korea AI Computing Center Co., Ltd. (KOACC)","relationship_scope":"unknown","role":"operator","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"4c353195-1c08-58a5-88f0-fc05ceac97af","notes":"Leads the nine-member consortium selected as the private partner; consortium members include Naver Cloud, Samsung C&T, Kakao, Samsung Electronics, KT and Clush.","party":"Samsung SDS","relationship_scope":"unknown","role":"developer","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"9e744646-545f-5d48-bfb5-62a2e2aab2b9","notes":"Leads the nine-member consortium selected as the private partner; consortium members include Naver Cloud, Samsung C&T, Kakao, Samsung Electronics, KT and Clush.","party":"Samsung SDS","relationship_scope":"unknown","role":"developer","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"6eec6a2f-a48c-5835-a5fe-dd4ca04c5ae8","notes":"Leads the nine-member consortium selected as the private partner; consortium members include Naver Cloud, Samsung C&T, Kakao, Samsung Electronics, KT and Clush.","party":"Samsung SDS","relationship_scope":"unknown","role":"developer","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"96e477c0-71eb-5525-99a8-72c36988e9c5","notes":"Leads the nine-member consortium selected as the private partner; consortium members include Naver Cloud, Samsung C&T, Kakao, Samsung Electronics, KT and Clush.","party":"Samsung SDS","relationship_scope":"unknown","role":"developer","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"9e744646-545f-5d48-bfb5-62a2e2aab2b9","notes":"Runs the national project and co-founded the joint venture.","party":"Ministry of Science and ICT (South Korea)","relationship_scope":"unknown","role":"government","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"6eec6a2f-a48c-5835-a5fe-dd4ca04c5ae8","notes":"Runs the national project and co-founded the joint venture.","party":"Ministry of Science and ICT (South Korea)","relationship_scope":"unknown","role":"government","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"96e477c0-71eb-5525-99a8-72c36988e9c5","notes":"Runs the national project and co-founded the joint venture.","party":"Ministry of Science and ICT (South Korea)","relationship_scope":"unknown","role":"government","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"6eec6a2f-a48c-5835-a5fe-dd4ca04c5ae8","notes":"Policy fund under the Financial Services Commission that approved an investment and co-founded the joint venture.","party":"People's Growth Fund","relationship_scope":"unknown","role":"investor","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"4c353195-1c08-58a5-88f0-fc05ceac97af","notes":"Consortium member that prepared the site; the province has since become part of the Gwangju-Jeonnam integrated special city.","party":"Jeollanam-do provincial government","relationship_scope":"unknown","role":"government","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"96e477c0-71eb-5525-99a8-72c36988e9c5","notes":"Consortium member that prepared the site; the province has since become part of the Gwangju-Jeonnam integrated special city.","party":"Jeollanam-do provincial government","relationship_scope":"unknown","role":"government","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"9e744646-545f-5d48-bfb5-62a2e2aab2b9","notes":"Electricity supplier to which the joint venture applied for service.","party":"Korea Electric Power Corporation (KEPCO)","relationship_scope":"unknown","role":"utility","source_record_id":"koacc-national-ai-computing-center-haenam"},{"evidence_id":"6eec6a2f-a48c-5835-a5fe-dd4ca04c5ae8","notes":"Electricity supplier to which the joint venture applied for service.","party":"Korea Electric Power Corporation (KEPCO)","relationship_scope":"unknown","role":"utility","source_record_id":"koacc-national-ai-computing-center-haenam"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Korea AI Computing Center Co., Ltd. (KOACC) |  |  |  | https://en.edaily.co.kr/news/eda202608035522/ | https://www.samsungsds.com/en/news/1293056_5252.html | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve National AI Computing Center, Solaseado (Haenam) as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"koacc-national-ai-computing-center-haenam"},"record":{"aliases":["Korea AI Computing Center","KOACC","Solaseado National AI Computing Center"],"id":"koacc-national-ai-computing-center-haenam","last_reviewed":"2026-10-09","location":{"admin1":"South Jeolla (Gwangju-Jeonnam)","admin2":"Haenam County","country":"KR","lat":34.5742,"locality":"Sani-myeon (Solaseado)","lon":126.5975,"note":"Sources place the site in the Solaseado data center park in Sani-myeon, Haenam County, without coordinates; the point is the Haenam County coordinate from its Wikipedia article, so it marks the county, not the site.","precision":"admin2","source_ids":["s1","s2","s3","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-01-12","basis":"announced","metric":"investment","note":"Total budget for the national project from 2026 to 2030, funded by private and government investment and policy loans; the project centres on securing computing resources, so the figure is not the building cost alone.","qualifier":"more_than","source_ids":["s1","s2"],"unit":"KRW","value":2000000000000},{"applies_to":"campus","as_of":"2026-05-13","basis":"reported","metric":"investment","note":"Nocut News figure for the total to be injected by 2030, including 400 billion won of equity.","qualifier":"exact","source_ids":["s4"],"unit":"KRW","value":2406500000000},{"applies_to":"campus","as_of":"2026-08-03","basis":"contracted","metric":"power_capacity","note":"Edaily reports a 40 MW supply confirmed by KEPCO and local governments after a grid review; it does not say whether this is IT or facility power.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":40},{"applies_to":"phase","as_of":"2026-01-12","basis":"planned","metric":"accelerators","note":"Advanced GPUs targeted by 2028 (Samsung SDS says more than 15,000). Edaily says the consortium's plan was based on Nvidia B200 but the chip choice may change.","phase_label":"2028 target","qualifier":"at_least","source_ids":["s1","s2","s3","s4"],"unit":"count","value":15000},{"applies_to":"campus","as_of":"2026-05-13","basis":"planned","metric":"accelerators","note":"GPU target for 2030, reached in stages.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":50000}],"milestones":[{"date":"2025-10","event":"other","kind":"actual","note":"The Samsung SDS consortium submitted the only bid in the government tender.","source_ids":["s1"]},{"date":"2026-05-13","event":"other","kind":"actual","note":"The Samsung SDS consortium was confirmed as the final participant, with Solaseado as the site.","source_ids":["s4"]},{"date":"2026-06","event":"other","kind":"actual","note":"Joint venture Korea AI Computing Center (KOACC) incorporated to build and run the center.","source_ids":["s2","s3"]},{"date":"2026-08-03","event":"construction_started","kind":"actual","note":"Groundbreaking ceremony held by the Ministry of Science and ICT and attended by the science minister. Edaily dates it to the 3rd; Digital Today, publishing the same day, says it took place on Sunday, which would be 2 August.","source_ids":["s2","s3"]},{"date":"2028","event":"fully_operational","kind":"planned","note":"Digital Today says construction is to be completed by 2028 and Nocut News targets full-scale operation in the second half of 2028; Edaily's translated text refers to completion in 2027. Some computing resources are to be offered earlier from a Samsung SDS data center in 2027.","source_ids":["s3","s4"]}],"name":"National AI Computing Center, Solaseado (Haenam)","notes":"Qualifies on investment: the budget of more than 2 trillion won exceeded USD 1 billion at the time. Reported totals vary between 2.0 and 2.5 trillion won across outlets. The site name is romanized several ways (Solaseado, SoLaSeaDo, Solasido). Wikipedia is cited only for the county coordinate. This is separate from the stalled OpenAI and SK data center plan, for which Haenam was one reported candidate site.","parties":[{"name":"Korea AI Computing Center Co., Ltd. (KOACC)","note":"Public-private special purpose company formed in June 2026 to build and operate the center.","role":"developer","source_ids":["s2","s3"]},{"name":"Korea AI Computing Center Co., Ltd. (KOACC)","role":"operator","source_ids":["s2","s3"]},{"name":"Samsung SDS","note":"Leads the nine-member consortium selected as the private partner; consortium members include Naver Cloud, Samsung C&T, Kakao, Samsung Electronics, KT and Clush.","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Ministry of Science and ICT (South Korea)","note":"Runs the national project and co-founded the joint venture.","role":"government","source_ids":["s2","s3","s4"]},{"name":"People's Growth Fund","note":"Policy fund under the Financial Services Commission that approved an investment and co-founded the joint venture.","role":"investor","source_ids":["s3"]},{"name":"Jeollanam-do provincial government","note":"Consortium member that prepared the site; the province has since become part of the Gwangju-Jeonnam integrated special city.","role":"government","source_ids":["s1","s4"]},{"name":"Korea Electric Power Corporation (KEPCO)","note":"Electricity supplier to which the joint venture applied for service.","role":"utility","source_ids":["s2","s3"]}],"power_sources":[{"description":"Power from KEPCO, to which the joint venture applied for service.","source_ids":["s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-01-12","publisher":"Samsung SDS","title":"Samsung SDS Consortium Takes Major Step Forward in National AI Computing Center Project with Its First Official Site Visit","type":"company","url":"https://www.samsungsds.com/en/news/1293056_5252.html"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-03","publisher":"Edaily","title":"South Korea Joins the Global GPU War: Building a 2 Trillion Won AI Outpost in Haenam, South Jeolla Province","type":"news","url":"https://en.edaily.co.kr/news/eda202608035522/"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-03","publisher":"Digital Today","title":"Groundbreaking held for national AI computing center in Haenam, aims for 2028 completion","type":"news","url":"https://www.digitaltoday.co.kr/en/view/88544/groundbreaking-held-for-national-ai-computing-center-in-haenam-aims-for-2028-completion"},{"accessed":"2026-10-09","id":"s4","published":"2026-05-13","publisher":"Nocut News","title":"Jeonnam Province secures national AI Computing Center","type":"news","url":"https://en.nocutnews.co.kr/news/6516549"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Haenam County","type":"other","url":"https://en.wikipedia.org/wiki/Haenam_County"}],"status":"under_construction","status_as_of":"2026-08-03","status_source_ids":["s2","s3"],"summary":"South Korea's government-backed National AI Computing Center is being built in the Solaseado data center park in Haenam County, South Jeolla. A consortium led by Samsung SDS was the only bidder in the 2025 tender and was confirmed as operator in 2026; a public-private joint venture, Korea AI Computing Center (KOACC), formed in June 2026 to build and run it. The project is budgeted at more than 2 trillion won through 2030 and targets at least 15,000 advanced GPUs by 2028 and about 50,000 by 2030. Ground was broken on 3 August 2026, with completion targeted for 2028.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"4c353195-1c08-58a5-88f0-fc05ceac97af","s2":"9e744646-545f-5d48-bfb5-62a2e2aab2b9","s3":"6eec6a2f-a48c-5835-a5fe-dd4ca04c5ae8","s4":"96e477c0-71eb-5525-99a8-72c36988e9c5","s5":"af2bc373-3f1e-5a38-95ad-488c8236c9ea"},"source_file":"datacenters/projects/koacc-national-ai-computing-center-haenam.json","source_record_id":"koacc-national-ai-computing-center-haenam","source_record_sha256":"240e376fa87bff23321da38cdf9a144f3e204cb3be1a16bb0bdb56639a38def3","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a64947cf5b3716010c3735a51d48124215a1957d02f68fc802561f9aed175ce0"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-af1774a8d4eb3398e76e/#project-ddaae950-1e47-58e8-b57a-37aeed0eba7a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ddaae950-1e47-58e8-b57a-37aeed0eba7a.json
def7f329-a075-519e-bc4b-8f8126bc1901 | curated:atnorth-swe02-stockholm-campus:current-development | vcc-site-b25b924e3e107c2cbaf1 | curated:atnorth-swe02-stockholm-campus | atNorth SWE02 Current Development | Sweden | SE | 59.4202 | 17.9191 | Point | project | direct_geometry | official_stockholm_project_map_epsg3011_point_transformed_to_wgs84 | official_municipal_project_map_reference_point | official_source | project_locator | Official municipal project-page point transformed deterministically from EPSG:3011 to EPSG:4326. Decimal precision and sub-nanometre software roundtrip do not imply source survey accuracy. |  | The municipal page publishes projected coordinates but no surveyed reference feature, collection method, or numeric horizontal accuracy. | ad0c7dc7-a25c-56d6-a190-734216237c6a | under_construction | 2026-06-09 | 126 | authoritative_physical_status_update | a9daeede-caae-58b3-8121-7185a3a07a33 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.atnorth.com/news/atnorth-joins-norwegian-data-center-association/ | https://vaxer.stockholm/projekt/akalla/serverhallar-med-atervinning-av-overskottsvarme/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b25b924e3e107c2cbaf1/#project-def7f329-a075-519e-bc4b-8f8126bc1901 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/def7f329-a075-519e-bc4b-8f8126bc1901.json
def89e4b-c93d-5dc8-a955-edd8e51a1058 | imported:semiconductor-atlas:joliet-technology-center | vcc-site-d98cef70ec1688f58e42 | imported:semiconductor-atlas:joliet-technology-center | Joliet Technology Center | United States | US | 41.5297 | -88.0728 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Wikipedia coordinates for Joliet. Neither source gives a street address or parcel; the developers' site describes the location only as away from homes and near distribution uses and a racetrack. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f15c1fc4-df2b-52c9-a0c7-06ff78e68425 | announced | 2026-03-23 | 204 | imported_documented_status | f15c1fc4-df2b-52c9-a0c7-06ff78e68425 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f15c1fc4-df2b-52c9-a0c7-06ff78e68425","notes":null,"party":"Hillwood Investment Properties","relationship_scope":"unknown","role":"developer","source_record_id":"joliet-technology-center"},{"evidence_id":"4811a075-7daa-5f69-949e-01380e12a4af","notes":null,"party":"Hillwood Investment Properties","relationship_scope":"unknown","role":"developer","source_record_id":"joliet-technology-center"},{"evidence_id":"f15c1fc4-df2b-52c9-a0c7-06ff78e68425","notes":"Division of American Real Estate Partners, per the developers' site.","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"joliet-technology-center"},{"evidence_id":"4811a075-7daa-5f69-949e-01380e12a4af","notes":"Division of American Real Estate Partners, per the developers' site.","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"joliet-technology-center"},{"evidence_id":"4811a075-7daa-5f69-949e-01380e12a4af","notes":null,"party":"ComEd","relationship_scope":"unknown","role":"utility","source_record_id":"joliet-technology-center"},{"evidence_id":"f15c1fc4-df2b-52c9-a0c7-06ff78e68425","notes":"City council approved the proposal in March 2026.","party":"City of Joliet","relationship_scope":"unknown","role":"government","source_record_id":"joliet-technology-center"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.bisnow.com/news/chicago/data-center-development/joliet-oks-20b-data-center-as-illinois-seeks-to-make-large-developers-pay-more-for-projects-133777 | https://www.bisnow.com/news/chicago/data-center-development/joliet-oks-20b-data-center-as-illinois-seeks-to-make-large-developers-pay-more-for-projects-133777 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Joliet Technology Center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"joliet-technology-center"},"record":{"aliases":["Hillwood and PowerHouse Joliet data center campus"],"id":"joliet-technology-center","last_reviewed":"2026-10-09","location":{"admin1":"Illinois","admin2":"Will County","country":"US","lat":41.5297,"locality":"Joliet","lon":-88.0728,"note":"Wikipedia coordinates for Joliet. Neither source gives a street address or parcel; the developers' site describes the location only as away from homes and near distribution uses and a racetrack.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-23","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1","s2"],"unit":"USD","value":20000000000},{"applies_to":"campus","as_of":"2026-03-23","basis":"planned","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":795},{"applies_to":"campus","as_of":"2026-03-23","basis":"planned","metric":"buildings","qualifier":"exact","source_ids":["s1"],"unit":"count","value":24},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_construction","note":"Developers' promotional site, undated, as viewed on the access date.","qualifier":"range","source_ids":["s2"],"unit":"count","value":7000,"value_high":10000}],"milestones":[{"date":"2026-03-19","event":"other","kind":"actual","note":"Joliet City Council approved the proposal; Bisnow does not say whether the vote was a rezoning, annexation or agreement. The date is derived: Bisnow's Monday 23 March 2026 article says the vote was on Thursday, late the previous week.","source_ids":["s1"]},{"date":"2026-Q4","event":"construction_started","kind":"planned","note":"Construction expected late in 2026 or early in 2027, with completion taking up to five years.","source_ids":["s1"]}],"name":"Joliet Technology Center","parties":[{"name":"Hillwood Investment Properties","role":"developer","source_ids":["s1","s2"]},{"name":"PowerHouse Data Centers","note":"Division of American Real Estate Partners, per the developers' site.","role":"developer","source_ids":["s1","s2"]},{"name":"ComEd","role":"utility","source_ids":["s2"]},{"name":"City of Joliet","note":"City council approved the proposal in March 2026.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"ComEd service; the developers say the required energy upgrades will not be passed on to other ComEd customers.","source_ids":["s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-03-23","publisher":"Bisnow","title":"Joliet OKs $20B Data Center As Illinois Eyes Higher Developer Costs","type":"trade_press","url":"https://www.bisnow.com/news/chicago/data-center-development/joliet-oks-20b-data-center-as-illinois-seeks-to-make-large-developers-pay-more-for-projects-133777"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260318062032/https://joliettechnologycenter.com/","id":"s2","published":null,"publisher":"Hillwood and PowerHouse Data Centers","title":"Yes to Joliet Jobs","type":"company","url":"https://joliettechnologycenter.com/"}],"status":"announced","status_as_of":"2026-03-23","status_source_ids":["s1"],"summary":"Hillwood Investment Properties and PowerHouse Data Centers, a division of American Real Estate Partners, plan a 24-building data center campus on about 795 acres in Joliet, Illinois. The developers put the investment at USD 20 billion and describe a phased build of five to seven years with 7,000 to 10,000 construction jobs and power from ComEd. Joliet's city council approved the proposal in March 2026, with construction expected to start in late 2026 or early 2027. No tenant is named; Bisnow says the campus is aimed at potential hyperscale users."},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f15c1fc4-df2b-52c9-a0c7-06ff78e68425","s2":"4811a075-7daa-5f69-949e-01380e12a4af"},"source_file":"datacenters/projects/joliet-technology-center.json","source_record_id":"joliet-technology-center","source_record_sha256":"c2b80a0462803a00c5e735ca3bb9ed481670e94077980e72b04d74d6fd4f278b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"3886e89173d173234c8cc643d1c254eadfdbf60c5f2da58b2b6f56093dcfd499"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d98cef70ec1688f58e42/#project-def89e4b-c93d-5dc8-a955-edd8e51a1058 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/def89e4b-c93d-5dc8-a955-edd8e51a1058.json
df2b8f33-9c46-5f6a-9853-b47474606979 | curated:nxdata3-bucharest-ring-road-campus:nxdata3-buh3 | vcc-site-99c848590f717e20510c | curated:nxdata3-bucharest-ring-road-campus | NXDATA-3 / NX-3 / BUH3 | Romania | RO | 44.5387 | 26.1291 | Point | project | source_published_marker_to_point_without_atlas_centroiding | inflect_named_nxdata_bucharest_3_location_marker_as_project_locator | commercial_directory_named_data_center_marker_as_project_locator | community_source | project_locator | Atlas copies the exact page-issued marker and calculates no centroid. Treat it only as a locator for the named NXDATA Bucharest 3 record. It is not an entrance, surveyed point, parcel, building footprint, campus boundary, project footprint, construction extent, or horizontal-accuracy claim. Inflect does not disclose whether its upstream marker was geocoded, manually selected, or otherwise derived. |  | Inflect publishes no collection method, represented feature, datum, or bounded horizontal accuracy for this marker. | b1f159c6-216e-5c92-9a98-9c2e0d27ad3a | under_construction | 2026-06-02 | 133 | authoritative_physical_status_update | f4df0775-4afa-5f48-b9f9-d9098c0be99f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.linkedin.com/posts/nxdata_nxdata-nxdata3-datacenter-activity-7467582788171616256-fwVo | https://inflect.com/building/38-ring-road-tunari/nxdata/datacenter/nxdata-3 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-99c848590f717e20510c/#project-df2b8f33-9c46-5f6a-9853-b47474606979 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/df2b8f33-9c46-5f6a-9853-b47474606979.json
df5ccb0c-2ab0-56fc-a260-71db9387c492 | imported:semiconductor-atlas:adaniconnex-pune | vcc-site-52b1e1c3038357306a39 | curated:adaniconnex-pune-data-center-campus | AdaniConneX Pune data centre campus | India | IN | 18.5211 | 73.8553 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Pune only. Coordinates are the Pune city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 42643fbc-e1c7-5395-9f08-a0b26d79fd1d | partially_operational | 2026-07-29 | 76 | imported_documented_status | 42643fbc-e1c7-5395-9f08-a0b26d79fd1d | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"42643fbc-e1c7-5395-9f08-a0b26d79fd1d","notes":null,"party":"AdaniConneX","relationship_scope":"unknown","role":"developer","source_record_id":"adaniconnex-pune"},{"evidence_id":"6171a3e1-fbf0-57db-b1c6-39747fcf427d","notes":null,"party":"AdaniConneX","relationship_scope":"unknown","role":"developer","source_record_id":"adaniconnex-pune"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.adaniconnex.com/data-centers | https://www.adaniconnex.com/data-centers | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Pune campus context includes operating first and second phases and 250 MW potential; existing record specifically selects PNQ04 current construction. Preserve campus metrics and operating status separately from PNQ04.","source_record_id":"adaniconnex-pune","target_physical_site_stable_key":"curated:adaniconnex-pune-data-center-campus"},"record":{"aliases":[],"id":"adaniconnex-pune","last_reviewed":"2026-10-09","location":{"admin1":"Maharashtra","admin2":"Pune","country":"IN","lat":18.5211,"locality":"Pune","lon":73.8553,"note":"Sources name Pune only. Coordinates are the Pune city coordinates from Wikipedia (Nominatim was rate-limiting requests), not the site.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026","basis":"planned","metric":"power_capacity","note":"Listed by the company as potential capacity in IT load.","power_scope":"it_load","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":250},{"applies_to":"phase","as_of":"2026-07-29","basis":"operational","metric":"power_capacity","phase_label":"Phase II capacity handed over to customer","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":9.6}],"milestones":[{"date":"2025-10","event":"first_operational","kind":"actual","note":"Company lists Phase 1 as live from October 2025, although the same page also describes the Pune facility as soon to be launched.","source_ids":["s1"]}],"name":"AdaniConneX Pune data centre campus","notes":"Microsoft is not listed as a party because the Adani release does not state its role at the Pune campus, and the customer that received the Phase II capacity is not named. The capacity of Phase 1 is not published. The July 2026 results release also gives an operational capacity of 65.4 MW after the handover without saying whether that figure covers Pune alone or all AdaniConneX sites, so it is not recorded.","parties":[{"name":"AdaniConneX","role":"developer","source_ids":["s1","s2"]}],"power_sources":[{"description":"Company states up to 100% renewable energy; the supply arrangement is not described.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"AdaniConneX","title":"Data Centers","type":"company","url":"https://www.adaniconnex.com/data-centers"},{"accessed":"2026-10-09","id":"s2","published":"2026-07-29","publisher":"Adani Group","title":"Adani Enterprises Ltd announces Q1-FY27 results","type":"company","url":"https://www.adani.com/newsroom/media-releases/adani-enterprises-ltd-announces-q1-fy27-results"},{"accessed":"2026-10-09","id":"s3","published":"2026-02-17","publisher":"Adani Group","title":"Adani Commits USD 100 Bn to Sovereign AI Infrastructure","type":"company","url":"https://www.adani.com/newsroom/media-releases/Adani-Commits-USD-100-Bn-to-Sovereign-AI-Infrastructure"}],"status":"partially_operational","status_as_of":"2026-07-29","status_source_ids":["s1","s2"],"summary":"AdaniConneX, the Adani group's data centre business, lists a Pune campus with a potential capacity of 250 MW of IT load and a first phase live from October 2025. Adani reported in July 2026 that 9.6 MW of the campus's second phase had been handed over to a customer. The company says the campus can use up to 100% renewable power, and a February 2026 Adani group release links its Microsoft partnership to the Pune and Hyderabad campuses without describing the terms. The site address has not been published.","workloads":["colocation"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"42643fbc-e1c7-5395-9f08-a0b26d79fd1d","s2":"6171a3e1-fbf0-57db-b1c6-39747fcf427d","s3":"e666c457-e5fe-5f03-a81a-7b7c4b14153a"},"source_file":"datacenters/projects/adaniconnex-pune.json","source_record_id":"adaniconnex-pune","source_record_sha256":"033d7eddbf642d0c4965f4294ae5a51c8130e8723703ed51dbd4a9b76da8d2a9","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1e1befbb85b31275c876195ef6f9e930a3a0b09253f8bedd90d5a4b86a03b86a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-52b1e1c3038357306a39/#project-df5ccb0c-2ab0-56fc-a260-71db9387c492 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/df5ccb0c-2ab0-56fc-a260-71db9387c492.json
e1aeeee2-575c-5873-a96a-528a6c08b387 | curated:goodman-par02-paris-data-centre-campus:phase-1-current-development | vcc-site-40f241ba326fd84eebf1 | curated:goodman-par02-paris-data-centre-campus | Goodman PAR02 Phase 1 Current Development | France | FR | 48.7604 | 2.4472 | Point | campus | official_exact_house_number_geocode | exact_named_address_feature_to_point_without_centroiding | official_address_campus_locator | official_source | campus_locator | The exact house-number point locates the reviewed Goodman campus address, not any specific phase, building, campus boundary or observed-work extent. Multiple buildings on this campus remain one physical site. |  | The service supplies a house-number address point without a numeric horizontal-accuracy statement. Match score is not positional uncertainty. | 15a46a40-3971-5abd-8e45-f6ccadbb5c48 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 420e5a5a-095f-5f13-8af2-98be462dfacf | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | https://data.geopf.fr/geocodage/search?q=34%20Rue%20Louis%20Armand%2094190%20Villeneuve-Saint-Georges&index=address&limit=5 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-40f241ba326fd84eebf1/#project-e1aeeee2-575c-5873-a96a-528a6c08b387 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e1aeeee2-575c-5873-a96a-528a6c08b387.json
e2c7ea58-17cc-594d-8b98-56ca08988c99 | curated:china-mobile-plateau-big-data-center-haidong:phase-2-build | vcc-site-f1171e4b8e247993d773 | curated:china-mobile-plateau-big-data-center-haidong | China Mobile Plateau Big Data Center Phase 2 Build | China | CN | 36.5097 | 102.0073 | Point | project | official_dms_coordinate_to_point | haidong_government_eia_project_center_coordinate | official_environmental_assessment_phase2_stage1_project_point | official_source | project_locator | The point is the official EIA project-center coordinate for Phase 2 Stage 1 and locates the named Phase 2 build. It is not a surveyed entrance, parcel centroid, campus boundary, building footprint, or current-work extent. |  | The EIA reports a project-center coordinate but no bounded horizontal-accuracy or survey-method statement. | e702223c-2730-5dda-90f9-ab59caa40a76 | under_construction | 2026-09-02 | 41 | authoritative_physical_status_update | a5250c40-b79c-5362-b0cb-6a0251069f92 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.qhnews.com/swld/system/2026/09/03/030605257.shtml | https://www.haidong.gov.cn/haidongos/ewebeditor/uploadfile/2025051314534893333.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f1171e4b8e247993d773/#project-e2c7ea58-17cc-594d-8b98-56ca08988c99 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e2c7ea58-17cc-594d-8b98-56ca08988c99.json
e375d86c-75a4-53f3-a80e-31aa6f32b616 | imported:semiconductor-atlas:meta-kuna-idaho | vcc-site-d80966c9e0bc776042e6 | imported:semiconductor-atlas:meta-kuna-idaho | Meta Kuna Data Center | United States | US | 43.4903 | -116.3717 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Kuna city coordinates from its Wikipedia page. Sources name the city and county but give no address or parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 793a4b14-609c-5493-8af9-b9186eaa0d5f | operational | 2026-09-03 | 40 | imported_documented_status | 0449f053-7fad-5be9-a045-a9429c9b9a0a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e82c4d92-a73e-5620-b1a3-6121fc520ef0","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-kuna-idaho"},{"evidence_id":"793a4b14-609c-5493-8af9-b9186eaa0d5f","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-kuna-idaho"},{"evidence_id":"c948c708-4565-526d-9897-096693c80c71","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"meta-kuna-idaho"},{"evidence_id":"0449f053-7fad-5be9-a045-a9429c9b9a0a","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"operator","source_record_id":"meta-kuna-idaho"},{"evidence_id":"e82c4d92-a73e-5620-b1a3-6121fc520ef0","notes":"State regulators expect the data center to become Idaho Power's single largest customer.","party":"Idaho Power","relationship_scope":"unknown","role":"utility","source_record_id":"meta-kuna-idaho"},{"evidence_id":"0449f053-7fad-5be9-a045-a9429c9b9a0a","notes":"State regulators expect the data center to become Idaho Power's single largest customer.","party":"Idaho Power","relationship_scope":"unknown","role":"utility","source_record_id":"meta-kuna-idaho"},{"evidence_id":"e82c4d92-a73e-5620-b1a3-6121fc520ef0","notes":"Owns and operates the water and wastewater treatment system that Meta built and handed over.","party":"City of Kuna","relationship_scope":"unknown","role":"government","source_record_id":"meta-kuna-idaho"},{"evidence_id":"f76c31fd-0a63-5c1c-a894-30b52c97a461","notes":"Owns and operates the water and wastewater treatment system that Meta built and handed over.","party":"City of Kuna","relationship_scope":"unknown","role":"government","source_record_id":"meta-kuna-idaho"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Meta Platforms |  |  |  | https://idahonews.com/news/local/meta-opens-new-ai-data-center-in-kuna-hopes-to-become-water-positive | https://nbc16.com/news/nation-world/facebook-owners-announce-new-data-center-in-kuna | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Kuna Data Center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-kuna-idaho"},"record":{"aliases":["Kuna Data Center"],"id":"meta-kuna-idaho","last_reviewed":"2026-10-09","location":{"admin1":"Idaho","admin2":"Ada County","country":"US","lat":43.4903,"locality":"Kuna","lon":-116.3717,"note":"Coordinates are the Kuna city coordinates from its Wikipedia page. Sources name the city and county but give no address or parcel.","precision":"locality","source_ids":["s2","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2022-02-16","basis":"announced","metric":"investment","qualifier":"approximately","source_ids":["s2","s3"],"unit":"USD","value":800000000},{"applies_to":"campus","as_of":"2026-09-04","basis":"announced","metric":"investment","note":"Meta's fact sheet gives more than USD 1.2 billion; 2026 news reports give USD 1.2 billion.","qualifier":"more_than","source_ids":["s1","s4","s5"],"unit":"USD","value":1200000000},{"applies_to":"campus","as_of":"2022-02-21","basis":"planned","metric":"floor_area","note":"Original 2022 plan, expected by 2025.","qualifier":"more_than","source_ids":["s3","s4"],"unit":"sq_ft","value":960000},{"applies_to":"campus","as_of":"2026-09-03","basis":"operational","metric":"floor_area","qualifier":"more_than","source_ids":["s5"],"unit":"sq_ft","value":750000},{"applies_to":"campus","as_of":"2022-02-16","basis":"planned","metric":"jobs_construction","note":"Expected peak construction workforce at announcement.","qualifier":"more_than","source_ids":["s2"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"jobs_construction","note":"Skilled trade workers on site at peak construction, per Meta's fact sheet.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":1600},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"jobs_permanent","note":"Operational jobs once completed; the 2022 announcement gave the same figure.","qualifier":"approximately","source_ids":["s1","s2"],"unit":"count","value":100}],"milestones":[{"date":"2022-02-16","event":"announced","kind":"actual","source_ids":["s2"]},{"date":"2022","event":"construction_started","kind":"actual","source_ids":["s1","s5"]},{"date":"2026-Q3","event":"first_operational","kind":"actual","note":"Reported in early September 2026 as open and serving traffic, after a construction pause for redesign; in 2022 the campus had been expected by 2025.","source_ids":["s3","s4","s5"]}],"name":"Meta Kuna Data Center","notes":"Reported sizes differ: more than 960,000 sq ft in the 2022 plan versus more than 750,000 sq ft for the finished facility in 2026. Meta's water and wastewater commitment was reported as about USD 50 million in 2022; Meta's 2026 fact sheet puts it at more than USD 100 million. The fact sheet (s1) shows no publication date (embedded file creation date 2026-09-02), so figures that rest on it alone are dated to the access date, 2026-10-09. Meta's investment figures are framed as investment in Idaho; Baxtel's report ties the USD 1.2 billion to the Kuna campus.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Meta Platforms","role":"operator","source_ids":["s4","s5"]},{"name":"Idaho Power","note":"State regulators expect the data center to become Idaho Power's single largest customer.","role":"utility","source_ids":["s1","s5"]},{"name":"City of Kuna","note":"Owns and operates the water and wastewater treatment system that Meta built and handed over.","role":"government","source_ids":["s1","s3"]}],"power_sources":[{"description":"Idaho Power serves the site; at announcement Meta said the campus would be supported by renewable energy through Idaho Power's Clean Energy Your Way program, and Meta says it pays the full cost of the energy it uses.","source_ids":["s1","s2","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260922060110/https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Kuna-Data-Center.pdf","id":"s1","published":null,"publisher":"Meta Platforms","title":"Meta Kuna Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Kuna-Data-Center.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2022-02-16","publisher":"NBC 16","title":"Facebook owners to invest $800 million in new Kuna data center","type":"news","url":"https://nbc16.com/news/nation-world/facebook-owners-announce-new-data-center-in-kuna"},{"accessed":"2026-10-09","id":"s3","published":"2022-02-21","publisher":"Bisnow","title":"Meta Plans $800M Hyperscale Campus In Idaho As It Continues To Explore New Data Center Markets","type":"trade_press","url":"https://www.bisnow.com/news/national/data-center/new-idaho-data-center-part-fits-metas-development-pattern-111978"},{"accessed":"2026-10-09","id":"s4","published":"2026-09-04","publisher":"Baxtel","title":"Meta's $1.2B Data Center In Kuna, Idaho, Goes Live","type":"trade_press","url":"https://baxtel.com/news/meta-s-1-2b-data-center-in-kuna-idaho-goes-live"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-03","publisher":"KBOI 2 (CBS2 Idaho News)","title":"Meta opens new AI data center in Kuna, hopes to become \"water positive\" by 2030","type":"news","url":"https://idahonews.com/news/local/meta-opens-new-ai-data-center-in-kuna-hopes-to-become-water-positive"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Kuna, Idaho","type":"other","url":"https://en.wikipedia.org/wiki/Kuna,_Idaho"}],"status":"operational","status_as_of":"2026-09-03","status_source_ids":["s5"],"summary":"Meta data center in Kuna, Idaho, about 16 miles from downtown Boise. Announced in February 2022 as a USD 800 million campus with more than 960,000 sq ft of data center space expected by 2025, it broke ground in 2022 and was later paused for a redesign to support AI infrastructure and liquid cooling. Meta began serving traffic from it in the third quarter of 2026, citing a USD 1.2 billion investment and a facility of more than 750,000 sq ft. Meta says it planned its energy needs with Idaho Power, and it built a water and wastewater system that it handed to the City of Kuna.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e82c4d92-a73e-5620-b1a3-6121fc520ef0","s2":"793a4b14-609c-5493-8af9-b9186eaa0d5f","s3":"f76c31fd-0a63-5c1c-a894-30b52c97a461","s4":"c948c708-4565-526d-9897-096693c80c71","s5":"0449f053-7fad-5be9-a045-a9429c9b9a0a","s6":"c2fb29a0-b6ad-598c-b4db-fb0a72c3a4ba"},"source_file":"datacenters/projects/meta-kuna-idaho.json","source_record_id":"meta-kuna-idaho","source_record_sha256":"8d1d811407ffc4368350c4dddfc8d4d5342b4e80a906d03d1040c846bd80f215","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"397dff5079f887f8d2b1476159a463e5af374ccd257777bb900b4f7ee5f27e73"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d80966c9e0bc776042e6/#project-e375d86c-75a4-53f3-a80e-31aa6f32b616 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e375d86c-75a4-53f3-a80e-31aa6f32b616.json
e389cd04-b538-5729-85a5-8e0b18e78002 | imported:semiconductor-atlas:terawulf-lake-mariner | vcc-site-88b1acf055e1ab6200e4 | epoch-ai:data-center:dd4bfd7c-adf8-5312-9a4a-f2728f1fe791 | TeraWulf Lake Mariner data campus | United States | US | 43.3275 | -78.5536 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Village coordinates from Wikipedia. The 10-K places the campus on a retired coal-fired plant site in Barker, on about 157 leased acres in Niagara County, but the sources reviewed give no exact site position. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 102ff694-04d2-53be-8f07-919dbe28d2a4 | partially_operational | 2026-08-05 | 69 | imported_documented_status | 7249a75e-6508-5666-a3f8-5c8552019914 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"102ff694-04d2-53be-8f07-919dbe28d2a4","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-lake-mariner"},{"evidence_id":"102ff694-04d2-53be-8f07-919dbe28d2a4","notes":null,"party":"TeraWulf","relationship_scope":"unknown","role":"operator","source_record_id":"terawulf-lake-mariner"},{"evidence_id":"f1b5c0de-d5f2-5205-8350-e7ab0a66a60c","notes":"Leases for about 378 MW of critical IT load entered in August 2025; Google provides credit support for Fluidstack's lease obligations.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-lake-mariner"},{"evidence_id":"178c95ea-e137-5242-ab75-419f303aa009","notes":"Leases for about 378 MW of critical IT load entered in August 2025; Google provides credit support for Fluidstack's lease obligations.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-lake-mariner"},{"evidence_id":"102ff694-04d2-53be-8f07-919dbe28d2a4","notes":"Leases for about 378 MW of critical IT load entered in August 2025; Google provides credit support for Fluidstack's lease obligations.","party":"Fluidstack","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-lake-mariner"},{"evidence_id":"102ff694-04d2-53be-8f07-919dbe28d2a4","notes":"Lease for 60 MW of critical IT load entered in December 2024.","party":"Core42","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-lake-mariner"},{"evidence_id":"40e31fac-4056-5e4c-b91a-8ab84be9a545","notes":"Lease for 60 MW of critical IT load entered in December 2024.","party":"Core42","relationship_scope":"unknown","role":"tenant","source_record_id":"terawulf-lake-mariner"},{"evidence_id":"102ff694-04d2-53be-8f07-919dbe28d2a4","notes":"90 MW allocation under an agreement executed in February 2022, with a ten-year term from NYPA's initial power delivery.","party":"New York Power Authority","relationship_scope":"unknown","role":"power_supplier","source_record_id":"terawulf-lake-mariner"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | TeraWulf |  | Core42; Fluidstack |  | https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results | https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same TeraWulf Barker Lake Mariner campus, confirmed by identical August 2026 issuer results source. Source includes operating mining/HPC, CB-4 and CB-5; existing record is only CB-5 current construction.","source_record_id":"terawulf-lake-mariner","target_physical_site_stable_key":"epoch-ai:data-center:dd4bfd7c-adf8-5312-9a4a-f2728f1fe791"},"record":{"aliases":["Lake Mariner Data Campus"],"id":"terawulf-lake-mariner","last_reviewed":"2026-10-09","location":{"admin1":"New York","admin2":"Niagara County","country":"US","lat":43.3275,"locality":"Barker","lon":-78.5536,"note":"Village coordinates from Wikipedia. The 10-K places the campus on a retired coal-fired plant site in Barker, on about 157 leased acres in Niagara County, but the sources reviewed give no exact site position.","precision":"locality","source_ids":["s4","s7"]},"metrics":[{"applies_to":"phase","as_of":"2025-12-31","basis":"contracted","metric":"power_capacity","phase_label":"Core42 leases","power_scope":"it_load","qualifier":"exact","source_ids":["s4","s5"],"unit":"MW","value":60},{"applies_to":"phase","as_of":"2025-12-31","basis":"contracted","metric":"power_capacity","note":"Per the 10-K; TeraWulf's February 2026 results list Fluidstack at 380 MW.","phase_label":"Fluidstack leases","power_scope":"it_load","qualifier":"exact","source_ids":["s4","s5"],"unit":"MW","value":378},{"applies_to":"campus","as_of":"2026-07","basis":"operational","metric":"power_capacity","note":"Revenue-generating HPC capacity after CB-3 was delivered in early July 2026.","power_scope":"it_load","qualifier":"exact","source_ids":["s6"],"unit":"MW","value":102},{"applies_to":"phase","as_of":"2026-08-05","basis":"under_construction","metric":"power_capacity","phase_label":"CB-4 and CB-5","power_scope":"it_load","qualifier":"exact","source_ids":["s6"],"unit":"MW","value":336},{"applies_to":"campus","as_of":"2025-12-31","basis":"planned","metric":"power_capacity","note":"Near-term gross capacity as described in the 10-K.","power_scope":"facility","qualifier":"approximately","source_ids":["s4"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2025-12-31","basis":"planned","metric":"power_capacity","note":"Potential gross capacity after expansion, subject to further NYISO approvals.","power_scope":"facility","qualifier":"up_to","source_ids":["s4","s5"],"unit":"MW","value":750},{"applies_to":"campus","as_of":"2025-12-31","basis":"operational","metric":"power_capacity","note":"Legacy bitcoin mining capacity at the campus as of December 31, 2025; TeraWulf reported 245 MW of total Lake Mariner capacity in May 2025.","power_scope":"unspecified","qualifier":"exact","source_ids":["s4","s1"],"unit":"MW","value":245}],"milestones":[{"date":"2022-03","event":"first_operational","kind":"actual","note":"Operations at the campus commenced.","source_ids":["s4"]},{"date":"2024-12","event":"other","kind":"actual","note":"Core42 lease for 60 MW of critical IT load entered.","source_ids":["s4"]},{"date":"2025-08-14","event":"other","kind":"actual","note":"Fluidstack signed two 10-year HPC colocation agreements for more than 200 MW of critical IT load, with Google backstopping $1.8 billion of lease obligations.","source_ids":["s2"]},{"date":"2025-08-18","event":"expansion_announced","kind":"actual","note":"A CB-5 lease raised Fluidstack's commitment to about 360 MW of critical IT load; the Google backstop rose to about $3.2 billion.","source_ids":["s3"]},{"date":"2026-07","event":"other","kind":"actual","note":"CB-3 delivered, meeting the conditions for $600 million of Google credit support to take effect.","source_ids":["s6"]},{"date":"2026-H2","event":"other","kind":"planned","note":"Phased delivery and rent commencement for CB-4.","source_ids":["s6"]},{"date":"2027-H1","event":"other","kind":"planned","note":"CB-5 targeted to begin phased delivery in early 2027.","source_ids":["s6"]}],"name":"TeraWulf Lake Mariner data campus","parties":[{"name":"TeraWulf","role":"developer","source_ids":["s4"]},{"name":"TeraWulf","role":"operator","source_ids":["s4"]},{"name":"Fluidstack","note":"Leases for about 378 MW of critical IT load entered in August 2025; Google provides credit support for Fluidstack's lease obligations.","role":"tenant","source_ids":["s2","s3","s4"]},{"name":"Core42","note":"Lease for 60 MW of critical IT load entered in December 2024.","role":"tenant","source_ids":["s4","s5"]},{"name":"New York Power Authority","note":"90 MW allocation under an agreement executed in February 2022, with a ten-year term from NYPA's initial power delivery.","role":"power_supplier","source_ids":["s4"]}],"power_sources":[{"description":"Connection to the NYISO Zone A grid over dual 345 kV lines, with power described as predominantly zero-carbon and a 90 MW New York Power Authority allocation.","source_ids":["s2","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-05-09","publisher":"TeraWulf","title":"TeraWulf Reports First Quarter 2025 Results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/107/terawulf-reports-first-quarter-2025-results"},{"accessed":"2026-10-09","id":"s2","published":"2025-08-14","publisher":"TeraWulf","title":"TeraWulf Signs 200+ MW, 10-Year AI Hosting Agreements with Fluidstack","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/112/terawulf-signs-200-mw-10-year-ai-hosting-agreements-with-fluidstack"},{"accessed":"2026-10-09","id":"s3","published":"2025-08-18","publisher":"TeraWulf","title":"TeraWulf Announces Fluidstack Expansion with 160 MW CB-5 Lease at Lake Mariner","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/114/terawulf-announces-fluidstack-expansion-with-160-mw-cb-5-lease-at-lake-mariner"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260929023534/https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm","id":"s4","published":"2026-02-27","publisher":"U.S. Securities and Exchange Commission (TeraWulf filing)","title":"TeraWulf Inc. Form 10-K for the fiscal year ended December 31, 2025","type":"regulatory_filing","url":"https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm"},{"accessed":"2026-10-09","id":"s5","published":"2026-02-26","publisher":"TeraWulf","title":"TeraWulf Reports Fourth Quarter and Full Year 2025 Results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/132/terawulf-reports-fourth-quarter-and-full-year-2025-results"},{"accessed":"2026-10-09","id":"s6","published":"2026-08-05","publisher":"TeraWulf","title":"TeraWulf Reports Second Quarter 2026 Results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Wikipedia","title":"Barker, Niagara County, New York","type":"other","url":"https://en.wikipedia.org/wiki/Barker,_Niagara_County,_New_York"}],"status":"partially_operational","status_as_of":"2026-08-05","status_source_ids":["s6"],"summary":"TeraWulf campus on the site of a retired coal-fired power plant in Barker, New York, that began operating in 2022, has hosted bitcoin mining and is being expanded for high-performance computing for AI. TeraWulf has leased 60 MW of critical IT load to Core42 and about 378 MW to Fluidstack, whose lease obligations carry Google credit support. About 102 MW of HPC capacity was earning revenue after building CB-3 was delivered in July 2026, while CB-4 and CB-5 (336 MW combined) were under construction. TeraWulf cites about 500 MW of near-term gross capacity and potential to reach about 750 MW.","workloads":["ai_unspecified","hpc","crypto_mining"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"a35762a5-70ae-581a-9e03-552f7ab02a50","s2":"f1b5c0de-d5f2-5205-8350-e7ab0a66a60c","s3":"178c95ea-e137-5242-ab75-419f303aa009","s4":"102ff694-04d2-53be-8f07-919dbe28d2a4","s5":"40e31fac-4056-5e4c-b91a-8ab84be9a545","s6":"7249a75e-6508-5666-a3f8-5c8552019914","s7":"3517cba9-f4a4-5d4f-a880-1c1b1ffe4c0e"},"source_file":"datacenters/projects/terawulf-lake-mariner.json","source_record_id":"terawulf-lake-mariner","source_record_sha256":"081cc26c2e57d03704aae2b9dbe919a2c59626dbb9bf84295aa36cf2d26e6106","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"51a4f406e75d7fb19b3bff1df1781eb0ed72323aecb56d89a58a0a2fe34a4ebe"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88b1acf055e1ab6200e4/#project-e389cd04-b538-5729-85a5-8e0b18e78002 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e389cd04-b538-5729-85a5-8e0b18e78002.json
e39b5191-4a78-5781-8944-24efaf944aa9 | curated:nextdc-ge1-geelong:incremental-in-progress-fit-out | vcc-site-a54941d2855e5bc71a3b | curated:nextdc-ge1-geelong | NEXTDC GE1 Incremental In-Progress Fit-Out | Australia | AU | -38.0561 | 144.3727 | Point | campus | exact_official_primary_virtual_address_point_with_explicit_campus_identity_inference | preserve_Vicmap_PFI215512998_point_response_in_EPSG4326_for_exact_official_Next_DC_Corio_application_address | official_virtual_address_campus_reference_point | official_source | campus_locator | Exact virtual address point for 148-158 O'Brien's Road, Corio; the government Next DC application supplies Lot6 PS615585P. The GE1 code association comes from matching the operator's named Corio facility and is explicit analyst inference for independent review. Not the rejected Geelong city-center marker, Lovely Banks landbank, surveyed entrance, campus boundary or active-work footprint. |  | No feature-specific quantitative positional-accuracy estimate is supplied by the selected point source. Coordinate digits are retained without asserting survey accuracy. | b522ac80-5fe4-592c-b147-223fb992336b | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | c39d71f0-c36f-5942-85a8-d7c235f5ea32 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.nextdc.com/hubfs/Financial%20Reports/FY26/FY26%20Results%20Announcement.pdf | https://services-ap1.arcgis.com/P744lA0wf4LlBZ84/arcgis/rest/services/Vicmap_Address/FeatureServer/0/query?where=pfi%3D%27215512998%27&outFields=*&outSR=4326&returnGeometry=true&f=pjson | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a54941d2855e5bc71a3b/#project-e39b5191-4a78-5781-8944-24efaf944aa9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e39b5191-4a78-5781-8944-24efaf944aa9.json
e3e31b3f-d0db-54ad-849f-126a4eae2868 | imported:semiconductor-atlas:kenya-olkaria-geothermal-campus | vcc-site-e7f4d963829eac6090a7 | imported:semiconductor-atlas:kenya-olkaria-geothermal-campus | G42 and Microsoft Olkaria geothermal data centre campus | Kenya | KE | -0.88574 | 36.27 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name Olkaria only. Coordinates are those given for the Olkaria geothermal area on its Wikipedia page, not a data centre parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | e8aa9f30-dd73-5067-824b-efe66a6d7dcd | announced | 2026-08-24 | 50 | imported_documented_status | e6df56eb-3733-515a-a85b-c146226dc71b | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e8aa9f30-dd73-5067-824b-efe66a6d7dcd","notes":"To design and build the campus with local partners and lead arranging the investment.","party":"G42","relationship_scope":"unknown","role":"developer","source_record_id":"kenya-olkaria-geothermal-campus"},{"evidence_id":"20944103-50c0-59e2-8cdc-724e77c4b54c","notes":"To design and build the campus with local partners and lead arranging the investment.","party":"G42","relationship_scope":"unknown","role":"developer","source_record_id":"kenya-olkaria-geothermal-campus"},{"evidence_id":"e8aa9f30-dd73-5067-824b-efe66a6d7dcd","notes":"Microsoft and G42 were to design and operate a new Azure East Africa cloud region hosted at the campus.","party":"Microsoft","relationship_scope":"unknown","role":"operator","source_record_id":"kenya-olkaria-geothermal-campus"},{"evidence_id":"20944103-50c0-59e2-8cdc-724e77c4b54c","notes":"Microsoft and G42 were to design and operate a new Azure East Africa cloud region hosted at the campus.","party":"Microsoft","relationship_scope":"unknown","role":"operator","source_record_id":"kenya-olkaria-geothermal-campus"},{"evidence_id":"5352a645-2f08-5307-aeb3-5069020e27b9","notes":"Described as a local partner in the G42-led development.","party":"Olkaria EcoCloud Data Centre","relationship_scope":"unknown","role":"developer","source_record_id":"kenya-olkaria-geothermal-campus"},{"evidence_id":"e8aa9f30-dd73-5067-824b-efe66a6d7dcd","notes":"Party to the 2024 letter of intent; the government planned to use the facility for public services.","party":"Kenya Ministry of Information, Communications and the Digital Economy","relationship_scope":"unknown","role":"government","source_record_id":"kenya-olkaria-geothermal-campus"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Microsoft |  |  |  | https://citizen.digital/article/kenyas-1b-microsoft-data-centre-project-in-limbo-over-power-concerns-n383281 | https://news.microsoft.com/2024/05/22/microsoft-and-g42-announce-1-billion-comprehensive-digital-ecosystem-initiative-for-kenya/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve G42 and Microsoft Olkaria geothermal data centre campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"kenya-olkaria-geothermal-campus"},"record":{"aliases":[],"id":"kenya-olkaria-geothermal-campus","last_reviewed":"2026-10-09","location":{"country":"KE","lat":-0.885737,"locality":"Olkaria (near Lake Naivasha)","lon":36.269989,"note":"Sources name Olkaria only. Coordinates are those given for the Olkaria geothermal area on its Wikipedia page, not a data centre parcel.","precision":"locality","source_ids":["s1","s5","s6"]},"metrics":[{"applies_to":"phase","as_of":"2024-05-22","basis":"planned","metric":"power_capacity","phase_label":"First phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s2"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2026-08-24","basis":"planned","metric":"power_capacity","note":"Potential eventual scale, first stated by G42's chief executive in May 2024.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s2","s5"],"unit":"MW","value":1000},{"applies_to":"campus","as_of":"2026-05-23","basis":"reported","metric":"investment","note":"Gulf News, Semafor and Citizen Digital describe a USD 1 billion data centre. Microsoft's announcement and Al Jazeera instead frame USD 1 billion as a wider digital package in which the data centre is one part, so the figure may not be campus-specific.","qualifier":"exact","source_ids":["s2","s3","s4"],"unit":"USD","value":1000000000}],"milestones":[{"date":"2024-05-22","event":"announced","kind":"actual","source_ids":["s1","s2"]},{"date":"2026-05","event":"first_operational","kind":"planned","note":"Original target of operation about two years after the 2024 announcement; it was missed.","source_ids":["s2","s3"]},{"date":"2026-05","event":"other","kind":"actual","note":"Al Jazeera reported that plans stalled in May 2026 over power capacity concerns; Semafor reported that the National Treasury had not approved funding and that ground had not been broken. No formal suspension was reported.","source_ids":["s3","s5"]}],"name":"G42 and Microsoft Olkaria geothermal data centre campus","notes":"Kept at announced: no source reports a formal halt or suspension. Semafor (May 2026) said the project was unlikely to go ahead and the National Treasury had not approved funding; Al Jazeera (August 2026) said plans stalled in May 2026 over power capacity, and KenGen, which operates the Olkaria geothermal complex, said it was still at design stage. Citizen Digital reported the government insisting it had not been abandoned and the technology envoy saying it was not suspended. President Ruto said it would need about 1,000 MW, roughly a third of national capacity. Microsoft presented USD 1 billion as an initial investment in a wider digital initiative.","parties":[{"name":"G42","note":"To design and build the campus with local partners and lead arranging the investment.","role":"developer","source_ids":["s1","s2"]},{"name":"Microsoft","note":"Microsoft and G42 were to design and operate a new Azure East Africa cloud region hosted at the campus.","role":"operator","source_ids":["s1","s2"]},{"name":"Olkaria EcoCloud Data Centre","note":"Described as a local partner in the G42-led development.","role":"developer","source_ids":["s5"]},{"name":"Kenya Ministry of Information, Communications and the Digital Economy","note":"Party to the 2024 letter of intent; the government planned to use the facility for public services.","role":"government","source_ids":["s1"]}],"power_sources":[{"description":"The campus was planned to run entirely on renewable geothermal energy from the Olkaria area.","source_ids":["s1","s2","s5"],"type":"geothermal"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250503035335/https://news.microsoft.com/2024/05/22/microsoft-and-g42-announce-1-billion-comprehensive-digital-ecosystem-initiative-for-kenya/","id":"s1","published":"2024-05-22","publisher":"Microsoft","title":"Microsoft and G42 announce $1 billion comprehensive digital ecosystem initiative for Kenya","type":"company","url":"https://news.microsoft.com/2024/05/22/microsoft-and-g42-announce-1-billion-comprehensive-digital-ecosystem-initiative-for-kenya/"},{"accessed":"2026-10-09","id":"s2","published":"2024-05-22","publisher":"Gulf News","title":"Microsoft, UAE's G42 announce $1 billion geothermal data centre in Kenya","type":"news","url":"https://gulfnews.com/business/markets/microsoft-uaes-g42-announce-1-billion-geothermal-data-centre-in-kenya-1.102753045"},{"accessed":"2026-10-09","id":"s3","published":"2026-05-06","publisher":"Semafor","title":"Energy shortfall 'problem' scuppers Kenya's $1B Microsoft data center","type":"news","url":"https://semafor.com/article/05/06/2026/energy-shortfall-problem-scuppers-kenyas-1b-microsoft-data-center"},{"accessed":"2026-10-09","id":"s4","published":"2026-05-23","publisher":"Citizen Digital","title":"Kenya's $1B Microsoft data centre project in limbo over power concerns","type":"news","url":"https://citizen.digital/article/kenyas-1b-microsoft-data-centre-project-in-limbo-over-power-concerns-n383281"},{"accessed":"2026-10-09","id":"s5","published":"2026-08-24","publisher":"Al Jazeera","title":"Can Kenya's AI ambitions coexist with Naivasha's water needs?","type":"news","url":"https://www.aljazeera.com/economy/2026/8/24/can-kenyas-ai-ambitions-coexist-with-naivashas-water-needs"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Olkaria","type":"other","url":"https://en.wikipedia.org/wiki/Olkaria"}],"status":"announced","status_as_of":"2026-08-24","status_source_ids":["s4","s5"],"summary":"Planned geothermal-powered data centre campus at Olkaria, near Lake Naivasha in Kenya's Rift Valley, announced in May 2024 by G42 and Microsoft with Kenya's ICT ministry. G42 was to build it and it was to host a new Azure East Africa cloud region, with a 100 MW first phase and potential to grow to about 1 GW; press reports call it a USD 1 billion data centre. The May 2026 opening target was missed: in 2026 the project was reported stalled over power supply limits and unapproved funding, with KenGen saying it remained at design stage, while the government said it had not been abandoned.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e8aa9f30-dd73-5067-824b-efe66a6d7dcd","s2":"20944103-50c0-59e2-8cdc-724e77c4b54c","s3":"d4e7493e-a616-5a52-9ee2-2e1fceb684e4","s4":"e6df56eb-3733-515a-a85b-c146226dc71b","s5":"5352a645-2f08-5307-aeb3-5069020e27b9","s6":"3e650804-2ef6-5dcc-8871-ca812b2e9ce0"},"source_file":"datacenters/projects/kenya-olkaria-geothermal-campus.json","source_record_id":"kenya-olkaria-geothermal-campus","source_record_sha256":"1ce7fa93c545d0cc6fd827a397f21b8b1298b234ee8c8c14335f2f9c379cf357","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"11768a9fed052699236b66e6ae89134af107e75d8352c0365721b700cbf034ce"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e7f4d963829eac6090a7/#project-e3e31b3f-d0db-54ad-849f-126a4eae2868 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e3e31b3f-d0db-54ad-849f-126a4eae2868.json
e3f1fc38-bc59-5373-803f-d5c86d817096 | curated:iron-mountain-amsterdam-data-center-campus:ams-2-10mw-expansion | vcc-site-faa101d551da0c45f1c5 | curated:iron-mountain-amsterdam-data-center-campus | Iron Mountain AMS-2 10 MW Expansion | Netherlands | NL | 52.3917 | 4.6647 | Point | campus | official_notice_source_point | EPSG_28992_to_EPSG_4326_always_xy_with_documented_Amersfoort_transform | official_permit_notice_campus_reference_point | official_source | campus_locator | The provincial notice point locates the campus at J.W. Lucasweg 35, Haarlem, not the selected expansion building's footprint. Linking the owner's AMS-2 10 MW description to the SEC AMS-1 Phase 4 row is an analyst identity inference from the same campus, 10 MW scope and Q2 2027 schedule, not an explicit issuer renaming statement. The separate 20 MW held-development row is excluded. Existing and future campus buildings count once. |  | No source-specific numeric horizontal accuracy is published; transform operation accuracy is not site-locator uncertainty. | 583562f6-1d06-596e-81cc-289524fe0c00 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 681761fe-09c6-5f22-b508-1e20945f632d | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1020569/000102056926000068/q22026srpfinal.htm | https://zoek.officielebekendmakingen.nl/prb-2025-5574/metadata.xml | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-faa101d551da0c45f1c5/#project-e3f1fc38-bc59-5373-803f-d5c86d817096 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e3f1fc38-bc59-5373-803f-d5c86d817096.json
e4e51c8d-a98e-50a4-ba16-0795f1f3f63a | curated:stt-jakarta-data-centre-campus:stt-jakarta-6 | vcc-site-57a103a9de718a95ae14 | curated:stt-jakarta-data-centre-campus | STT Jakarta 6 | Indonesia | ID | -6.374 | 107.2011 | Polygon | campus | cross_source_overlay | openstreetmap_exactly_named_stt_jakarta_1_facility_polygon_as_shared_campus_locator | reviewed_openstreetmap_stt_jakarta_1_building_polygon | community_mapped | campus_locator | Contributor-mapped polygon for STT Jakarta 1, used only as one known-building anchor for the shared campus targeted by STT Jakarta 6. It is not the Jakarta 6 location or footprint, the campus boundary, a parcel, a construction extent, or a survey-accuracy claim. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral or survey geometry. | f16b034b-60d8-5826-841a-1acaa849a930 | under_construction | 2026-06-10 | 125 | authoritative_construction_start | a251b3bb-e0bc-56d3-b89a-97914d692f5d | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2026-06-10","base":40.0,"confidence":0.99,"evidence_id":"a251b3bb-e0bc-56d3-b89a-97914d692f5d","high":40.0,"low":40.0,"method":"reported","metric":"critical_it_mw","notes":"Planned critical-IT capacity for STT Jakarta 6 only. The source says the facility is planned to support 40 MW of IT load; this is not current load, gross facility power, grid draw, generation, annual energy, or measured consumption.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.sttelemediagdc.com/newsroom/stt-gdc-accelerates-jakarta-campus-expansion-power-indonesia-ai-and-digital-ambitions | https://www.openstreetmap.org/way/1533569836 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-57a103a9de718a95ae14/#project-e4e51c8d-a98e-50a4-ba16-0795f1f3f63a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e4e51c8d-a98e-50a4-ba16-0795f1f3f63a.json
e542ef62-912c-5edb-982a-8e463179484b | curated:israel-mega-dc-mdcil2-masmiyya-site:phase-a | vcc-site-88781eb659e91e68b6e9 | curated:israel-mega-dc-mdcil2-masmiyya-site | Mega D.C. MDCIL-2 Masmiyya Facility Current Build | Israel | IL | 31.7532 | 34.779 | Polygon | campus | approved_plan_land_use_plot_ring_transformed_EPSG2039_to_WGS84 | Xplan_layer4_plot_query_native_ring_PROJ_Israel1993_to_WGS84_2_round7 | approved_statutory_plan_land_use_plot | official_source | campus_locator | Every native plot vertex is transformed once with the recorded PROJ operation and rounded to seven decimals. Plot 200A of plan 632-0649806 is bound to the campus by the issuer's own plot references; it is a planning plot, not a surveyed cadastral boundary, building footprint or current work extent. The display anchor is the planar shoelace centroid of the transformed ring, verified inside it. |  | The planning service states no positional accuracy and disclaims official status; the 0.5 m datum-operation figure is not a plot accuracy. | 95d0d9b6-a7af-57ce-8b80-2e2714afe61e | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | a6c5d318-fc16-5cdf-a50d-df38b905a568 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://megaor.co.il/wp-content/uploads/2026/08/דוח-רבעון-2-לשנת-2026.pdf | https://ags.iplan.gov.il/arcgisiplan/rest/services/PlanningPublic/Xplan/MapServer/4/query?where=num%3D%27200A%27+AND+pl_number%3D%27632-0649806%27&outFields=*&returnGeometry=true&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-88781eb659e91e68b6e9/#project-e542ef62-912c-5edb-982a-8e463179484b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e542ef62-912c-5edb-982a-8e463179484b.json
e56ff51f-930c-5c5b-bc82-7add264e576e | curated:google-elmina-business-park-data-center:current-campus-build | vcc-site-a9577b8feaea08be317c | wikidata:Q136745002 | Google Elmina Current Campus Construction | Malaysia | MY | 3.2226 | 101.5197 | Point | campus | community_named_entity_source_point | literal_Wikidata_P625_Earth_WGS84_coordinate_no_transform | community_named_campus_reference_point | community_source | campus_locator | Exact numeric point from named community entity Q136745002, used only as a first-campus reference locator. Source precision field is 1e-8 degree and the stored decimals are retained; neither is surveyed accuracy. Not an official point, OSM feature, boundary, entrance, parcel centroid, building footprint or observed-work extent. |  | No positional accuracy or coordinate reference is supplied by the community entity. Its precision parameter describes model resolution only; independent survey accuracy remains unknown. | 2064a4dc-8fc1-50cb-a098-994f6139abe4 | under_construction | 2026-08-15 | 59 | authoritative_physical_status_update | 1d25d015-a527-5efe-a7dc-2791f489ff34 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [{"evidence_id":"237d639b-9ae2-5e9e-aaf1-bbc800f96253","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-elmina-selangor"},{"evidence_id":"8f509788-da86-5e3c-b1e8-3154434aa852","notes":null,"party":"Google","relationship_scope":"unknown","role":"developer","source_record_id":"google-elmina-selangor"},{"evidence_id":"d4a981e6-1245-575e-a6c0-599e16bdfb29","notes":"Google will operate the data center once it is complete.","party":"Google","relationship_scope":"unknown","role":"operator","source_record_id":"google-elmina-selangor"},{"evidence_id":"5cada769-76db-5b81-b958-3393242731d8","notes":"Google will operate the data center once it is complete.","party":"Google","relationship_scope":"unknown","role":"operator","source_record_id":"google-elmina-selangor"},{"evidence_id":"d4a981e6-1245-575e-a6c0-599e16bdfb29","notes":"Sime Darby Property describes a lease arrangement with Google for the facility; the terms are not given.","party":"Google","relationship_scope":"unknown","role":"tenant","source_record_id":"google-elmina-selangor"},{"evidence_id":"d4a981e6-1245-575e-a6c0-599e16bdfb29","notes":"Building the data center to Google's custom specifications inside its Elmina Business Park.","party":"Sime Darby Property Bhd","relationship_scope":"unknown","role":"builder","source_record_id":"google-elmina-selangor"}] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected |  | Google |  | Google |  | https://mediaselangor.com/en/2026/08/390529 | https://www.wikidata.org/wiki/Special:EntityData/Q136745002.json | [{"identity_decision":{"decision":"exact_project","flags":["administrative_locator_not_project_geometry"],"rationale":"Same first Google Malaysia data-center campus in Elmina Business Park developed by Sime Darby Property; both records describe the current campus development.","source_record_id":"google-elmina-selangor","target_project_stable_key":"curated:google-elmina-business-park-data-center:current-campus-build"},"record":{"aliases":["Google Elmina data centre","Google Malaysia cloud region"],"id":"google-elmina-selangor","last_reviewed":"2026-10-09","location":{"admin1":"Selangor","admin2":"Petaling District","country":"MY","lat":3.1992,"locality":"Elmina (Elmina Business Park)","lon":101.5006,"note":"Sources name Elmina Business Park in Selangor without an address; the point is the coordinate of the Elmina township from its Wikipedia article, so it marks the township rather than the parcel.","precision":"locality","source_ids":["s1","s2","s3","s4","s6"]},"metrics":[{"applies_to":"campus","as_of":"2024-05-30","basis":"announced","metric":"investment","note":"Google's announced amount covers both its first Malaysian data center and its first Malaysian cloud region, not the building alone.","qualifier":"exact","source_ids":["s1","s2"],"unit":"USD","value":2000000000}],"milestones":[{"date":"2024-05-30","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2024-10-01","event":"construction_started","kind":"actual","note":"Groundbreaking announced at the Mantap Malaysia Bersama AI event, with the prime minister as guest of honour; EdgeProp reports the ceremony was held in Kuala Lumpur.","source_ids":["s2","s3","s4"]},{"date":"2026-H1","event":"first_operational","kind":"planned","note":"Completion was targeted for early 2026; no confirmation of opening was found, and Google still listed the site as in development in October 2026.","source_ids":["s4"]}],"name":"Google Malaysia data center, Elmina Business Park","notes":"Status rests on Google's undated living locations page, which listed Selangor, Malaysia as in development when accessed on 2026-10-09, so status_as_of is the access date. No power capacity was found in a source that could be opened. Wikipedia is cited only for the township coordinate. Google estimates the investment will support about 26,500 jobs across the economy by 2030; that is not a site job count, so it is not recorded as a metric.","parties":[{"name":"Google","role":"developer","source_ids":["s1","s2"]},{"name":"Google","note":"Google will operate the data center once it is complete.","role":"operator","source_ids":["s3","s4"]},{"name":"Google","note":"Sime Darby Property describes a lease arrangement with Google for the facility; the terms are not given.","role":"tenant","source_ids":["s3"]},{"name":"Sime Darby Property Bhd","note":"Building the data center to Google's custom specifications inside its Elmina Business Park.","role":"builder","source_ids":["s3"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260515051834/https://w.media/google-to-invest-us-2-billion-to-build-its-first-dc-and-cloud-region-in-malaysia/","id":"s1","published":"2024-05-30","publisher":"W.Media","title":"Google to invest US$ 2 Billion to build its first DC and Cloud Region in Malaysia","type":"trade_press","url":"https://w.media/google-to-invest-us-2-billion-to-build-its-first-dc-and-cloud-region-in-malaysia/"},{"accessed":"2026-10-09","id":"s2","published":"2024-10-01","publisher":"Google","title":"Google Breaks Ground on US$2 Billion Malaysia Data Center and Cloud Region, Announces Support for New Sustainability and Skilling Initiatives","type":"company","url":"https://blog.google/intl/ms-my/company-news/inside-google/2024_10_google-breaks-ground-on-us2-billion/"},{"accessed":"2026-10-09","id":"s3","published":"2024-10-02","publisher":"Malaysian Investment Development Authority (MIDA), citing New Straits Times","title":"Google's hyperscale data centre at Elmina Business Park breaks ground","type":"government","url":"https://www.mida.gov.my/mida-news/googles-hyperscale-data-centre-at-elmina-business-park-breaks-ground/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20241003083057/https://www.edgeprop.my/content/1910621/sime-darby-property-commences-construction-malaysia%E2%80%99s-first-google-hyperscale-data-centre-city-elmina","id":"s4","published":"2024-10-02","publisher":"EdgeProp Malaysia","title":"Sime Darby Property commences construction of Malaysia's first Google hyperscale data centre in City of Elmina","type":"news","url":"https://edgeprop.my/content/1910621/sime-darby-property-commences-construction-malaysia%E2%80%99s-first-google-hyperscale-data-centre-city-elmina"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261009093925/https://datacenters.google/locations/","id":"s5","published":null,"publisher":"Google","title":"Discover our data center locations","type":"company","url":"https://datacenters.google/locations/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260507155140/https://en.wikipedia.org/wiki/Elmina,_Malaysia","id":"s6","published":null,"publisher":"Wikipedia","title":"Elmina, Malaysia","type":"other","url":"https://en.wikipedia.org/wiki/Elmina,_Malaysia"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s5"],"summary":"Google's first data center in Malaysia is being built in Sime Darby Property's Elmina Business Park in Selangor, in Greater Kuala Lumpur. Google announced in May 2024 a US$2 billion investment covering this data center and its first Malaysian cloud region, and broke ground in October 2024. Sime Darby Property is building the facility to Google's specifications under a lease arrangement with Google, which will operate it; Google says it will be water-cooled. Completion was targeted for early 2026, but Google's location list still showed the Selangor site as in development in October 2026.","workloads":["cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"237d639b-9ae2-5e9e-aaf1-bbc800f96253","s2":"8f509788-da86-5e3c-b1e8-3154434aa852","s3":"d4a981e6-1245-575e-a6c0-599e16bdfb29","s4":"5cada769-76db-5b81-b958-3393242731d8","s5":"fe75c518-dbb5-59c0-a0b0-74f309d0dc32","s6":"ffbf7680-00c9-5e76-b883-ede1e976f244"},"source_file":"datacenters/projects/google-elmina-selangor.json","source_record_id":"google-elmina-selangor","source_record_sha256":"96e91c84ac98c440c339a464d6075e40626a54ab6c3c3cc05212fbc2c8de6f84","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"e513cad282c7d6e19ea62971b18d671a13f3f11a2c76718cd805fe2b8e2d21bb"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-a9577b8feaea08be317c/#project-e56ff51f-930c-5c5b-bc82-7add264e576e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e56ff51f-930c-5c5b-bc82-7add264e576e.json
e62026de-3394-51f7-8823-44ee0da1801c | curated:capitaland-dc-navi-mumbai-campus:tower-2 | vcc-site-07ef7b0d529815ef1fe5 | curated:capitaland-dc-navi-mumbai-campus | CapitaLand DC Navi Mumbai Tower 2 | India | IN | 19.1758 | 73.0002 | Point | campus | first_party_published_map_pin | source_attribute_decimal_coordinates_to_point_without_centroiding | official_operator_published_campus_reference_point | official_source | campus_locator | The dated results table explicitly places Tower 1 and Tower 2 in CapitaLand DC Navi Mumbai; the operator property page names Mumbai 01 in Airoli and provides the campus point. The current point is not a Tower 2 footprint. No building, phase, construction extent or survey accuracy is asserted. |  | The publisher supplies no numeric horizontal-accuracy statement or surveyed reference feature. | 77dc8de7-b028-5897-b0d6-072bc8a1c922 | under_construction | 2026-07-29 | 76 | authoritative_physical_status_update | bce8fcc5-8779-5852-9c88-28fdd94c9e90 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.capitaland.com/content/dam/capitaland-newsroom/International/2026/july/clint-1h2026-results/2.%20CLINT%201H%202026%20slides_29%20July%202026.pdf | https://www.capitaland.com/en/find-a-property/global-property-listing/data-centres/capitaland-s-datacentrenavimumbai1.html | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-07ef7b0d529815ef1fe5/#project-e62026de-3394-51f7-8823-44ee0da1801c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e62026de-3394-51f7-8823-44ee0da1801c.json
e8a1add0-19fb-5196-ae75-34353e7d580b | curated:firmus-st-leonards-launceston-campus:ai-factory-current-build | vcc-site-d7089d81dd52f365db5b | curated:firmus-st-leonards-launceston-campus | Firmus St Leonards AI Factory Current Construction | Australia | AU | -41.4409 | 147.1766 | Point | campus | Literal Nominatim object-centroid lat/lon fields for native OSM way429540795, reordered to longitude/latitude only; no numerical coordinate transform or map-image extraction. | community_named_constituent_building_centroid | constituent_building_reference_point | community_source | campus_locator | Named Firmus LST01 existing-building reference on the explicitly joined municipal development site. Not a new-hall footprint, demolition extent, complete campus boundary, locality center, headquarters or neighboring substation. |  | Neither the source object nor Nominatim states positional accuracy or original survey provenance. Decimal precision and WGS84 semantics do not establish accuracy. | f6a5780c-e38a-53b2-b296-ce8fcec21a62 | under_construction | 2026-07-02 | 103 | authoritative_physical_status_update | 272cb55a-0283-55d0-a356-53af8aae3872 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.abc.net.au/listen/programs/hobart-mornings/firmus-oliver-curtis-tim-rosenfield-tasmania-data-centres/106868690 | https://nominatim.openstreetmap.org/search?q=23%20Killafaddy%20Road%2C%20St%20Leonards%2C%20Tasmania&format=jsonv2&polygon_geojson=1&addressdetails=1&extratags=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-d7089d81dd52f365db5b/#project-e8a1add0-19fb-5196-ae75-34353e7d580b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e8a1add0-19fb-5196-ae75-34353e7d580b.json
e934864d-423f-5afa-a9a8-09bd05079ee1 | imported:semiconductor-atlas:dayone-chonburi-tech-park | vcc-site-b020cba78b5fa2123866 | imported:semiconductor-atlas:dayone-chonburi-tech-park | DayOne Chonburi Tech Park (CTP) data center campus | Thailand | TH | 13.217 | 101.183 | Point | project | imported_reference_point | imported_reference_point | admin1 | compiled_reference | admin1_context | Sources place the campus in the AMATA City estate in Chonburi province but give no district or address. The point is the province coordinate from the Chonburi province Wikipedia article, so it marks the province, not the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 3ec56c55-c7d6-5540-9496-65bd267bfc8b | under_construction | 2026-04-26 | 170 | imported_documented_status | ca6abec9-ae6a-5497-b726-6454ad5a2b7e | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"3ec56c55-c7d6-5540-9496-65bd267bfc8b","notes":"Singapore-headquartered developer and operator of the campus.","party":"DayOne Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"dayone-chonburi-tech-park"},{"evidence_id":"e90fdf91-30f7-5c84-a3d8-966e73239bfa","notes":"Singapore-headquartered developer and operator of the campus.","party":"DayOne Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"dayone-chonburi-tech-park"},{"evidence_id":"ca6abec9-ae6a-5497-b726-6454ad5a2b7e","notes":"Singapore-headquartered developer and operator of the campus.","party":"DayOne Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"dayone-chonburi-tech-park"},{"evidence_id":"e90fdf91-30f7-5c84-a3d8-966e73239bfa","notes":"Signed a private power purchase agreement to supply floating-solar electricity to the campus.","party":"Amata B.Grimm Renewable Energy (AMBRE)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"dayone-chonburi-tech-park"},{"evidence_id":"d35e58a3-8b6d-5c3d-adff-b52fb1665027","notes":"Signed a private power purchase agreement to supply floating-solar electricity to the campus.","party":"Amata B.Grimm Renewable Energy (AMBRE)","relationship_scope":"unknown","role":"power_supplier","source_record_id":"dayone-chonburi-tech-park"},{"evidence_id":"e90fdf91-30f7-5c84-a3d8-966e73239bfa","notes":"Part of the three-way arrangement that delivers the solar power over its grid.","party":"Provincial Electricity Authority (PEA)","relationship_scope":"unknown","role":"utility","source_record_id":"dayone-chonburi-tech-park"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.aap.com.au/aapreleases/cision20260425ae43618/ | https://www.intelligentcio.com/apac/?p=43549 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve DayOne Chonburi Tech Park (CTP) data center campus as an independent source record; its admin1 locator does not itself establish a surveyed physical site.","source_record_id":"dayone-chonburi-tech-park"},"record":{"aliases":["Chonburi Tech Park","CTP1","CTP2","DayOne Chonburi"],"id":"dayone-chonburi-tech-park","last_reviewed":"2026-10-09","location":{"admin1":"Chonburi","country":"TH","lat":13.217,"locality":"AMATA City Chonburi industrial estate","lon":101.183,"note":"Sources place the campus in the AMATA City estate in Chonburi province but give no district or address. The point is the province coordinate from the Chonburi province Wikipedia article, so it marks the province, not the site.","precision":"admin1","source_ids":["s1","s2","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-03-19","basis":"planned","metric":"power_capacity","note":"Grid capacity of the campus as designed at groundbreaking, to be built in two phases; later raised for CTP1 (see the 300 MW figure).","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":180},{"applies_to":"phase","as_of":"2025-11-10","basis":"planned","metric":"power_capacity","note":"Site power capacity of the first plot after adding adjacent land; the sources do not say whether this is IT or grid capacity.","phase_label":"CTP1 with November 2025 land expansion","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3","s6"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-11-10","basis":"planned","metric":"power_capacity","note":"Target for a combined 1 GW power platform across CTP1 and the future CTP2 plot; CTP2 was covered only by an MoU.","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-04-26","basis":"planned","metric":"power_capacity","note":"IT capacity DayOne expected to bring online during 2026 as part of a multi-phase rollout.","phase_label":"Capacity due to go live in 2026","power_scope":"it_load","qualifier":"more_than","source_ids":["s4"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2025-03-19","basis":"announced","metric":"investment","note":"Intelligent CIO ties a US$1 billion investment, committed over the next few years, to this campus. DayOne's April 2026 release (s4) instead describes US$1 billion as the commitment it made on entering Thailand, without tying it to the campus; the conflict is unresolved.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2025-03-19","basis":"reported","metric":"land_area","note":"Reported as 122,000 square metres for the campus at groundbreaking, before the November 2025 additions.","qualifier":"approximately","source_ids":["s1"],"unit":"hectares","value":12.2},{"applies_to":"phase","as_of":"2025-11-10","basis":"planned","metric":"land_area","note":"Reported as 41.3 rai of adjacent land.","phase_label":"CTP1 adjacent land added in November 2025","qualifier":"approximately","source_ids":["s2","s3"],"unit":"acres","value":16.3}],"milestones":[{"date":"2024-11","event":"announced","kind":"actual","note":"DayOne announced its entry into Thailand.","source_ids":["s6"]},{"date":"2025-03","event":"construction_started","kind":"actual","note":"Groundbreaking reported by Intelligent CIO on 2025-03-19 without a ceremony date; DayOne's April 2026 release gives only the year 2025.","source_ids":["s1","s4"]},{"date":"2025-11-10","event":"expansion_announced","kind":"actual","note":"MoU with Amata for CTP2 and adjacent CTP1 land, lifting CTP1 to 300 MW and targeting a 1 GW platform; solar PPA signed the same day.","source_ids":["s2","s3"]},{"date":"2026","event":"first_operational","kind":"planned","note":"More than 100 MW of IT capacity expected to go live in 2026; DayOne's market page lists a 2026 ready-for-service date.","source_ids":["s4","s6"]},{"date":"2027","event":"other","kind":"planned","note":"Expected commercial operation of the floating-solar plant and start of renewable integration.","source_ids":["s2","s4"]}],"name":"DayOne Chonburi Tech Park (CTP) data center campus","notes":"Amata Corporation signed the November 2025 MoU covering CTP2 and the land added to CTP1 and is called a strategic partner, but no formal ownership or development role is stated, so it is not listed as a party. The US$1 billion rests on one trade-press report (s1); DayOne's April 2026 release frames it as a Thailand-entry commitment. That release describes the campus as under development with capacity due in 2026; no source confirms capacity was live by October 2026. Only Intelligent CIO places the campus in AMATA City; DayOne's pages name Chonburi province. Province coordinates come from Wikipedia (s5), used only for the map point.","parties":[{"name":"DayOne Data Centers","note":"Singapore-headquartered developer and operator of the campus.","role":"developer","source_ids":["s1","s2","s4"]},{"name":"Amata B.Grimm Renewable Energy (AMBRE)","note":"Signed a private power purchase agreement to supply floating-solar electricity to the campus.","role":"power_supplier","source_ids":["s2","s3"]},{"name":"Provincial Electricity Authority (PEA)","note":"Part of the three-way arrangement that delivers the solar power over its grid.","role":"utility","source_ids":["s2"]}],"power_sources":[{"description":"The campus was designed around 180 MW of grid capacity; solar power is delivered through the Provincial Electricity Authority grid.","source_ids":["s1","s2"],"type":"grid"},{"description":"Private power purchase agreement with AMBRE for a 22 kV floating-solar plant in the AMATA City estate, initially 42.5 MWp, expected to start commercial operation in 2027.","source_ids":["s2","s3"],"type":"solar"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-03-19","publisher":"Intelligent CIO APAC","title":"DayOne breaks ground on hyperscale data center pioneering Thailand's digital future","type":"trade_press","url":"https://www.intelligentcio.com/apac/?p=43549"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251213220716/https://dayonedc.com/news/dayone-strengthens-thailands-digital-hub-with-amata-as-chonburi-campus-expands-toward-the-countrys-first-1gw-power-platform/","id":"s2","published":"2025-11-10","publisher":"DayOne Data Centers","title":"DayOne Strengthens Thailand's Digital Hub with Amata as Chonburi Campus Expands Toward the Country's First 1GW Power Platform","type":"company","url":"https://dayonedc.com/news/dayone-strengthens-thailands-digital-hub-with-amata-as-chonburi-campus-expands-toward-the-countrys-first-1gw-power-platform"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-11","publisher":"Bernama","title":"DayOne, Amata In Deal To Build Thailand's First 1GW Power Platform","type":"news","url":"https://www.bernama.com/en/news.php?id=2489483"},{"accessed":"2026-10-09","id":"s4","published":"2026-04-26","publisher":"DayOne Data Centers (via AAP / Cision)","title":"DayOne Launches Inaugural Tech & AI Career Expo in Thailand, Showcasing Commitment to Digital Infrastructure and Talent Development","type":"company","url":"https://www.aap.com.au/aapreleases/cision20260425ae43618/"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Chonburi province","type":"other","url":"https://en.wikipedia.org/wiki/Chonburi_province"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260912081922/https://dayonedc.com/market/greater-bangkok","id":"s6","published":null,"publisher":"DayOne Data Centers","title":"Our markets: Greater Bangkok","type":"company","url":"https://dayonedc.com/market/greater-bangkok"}],"status":"under_construction","status_as_of":"2026-04-26","status_source_ids":["s4"],"summary":"DayOne Data Centers, a Singapore-based operator, is building the Chonburi Tech Park hyperscale campus in the AMATA City area of Chonburi province, southeast of Bangkok. Groundbreaking was reported in March 2025 for a design of 180 MW of grid capacity in two phases, which trade press tied to a US$1 billion multi-year investment. In November 2025 DayOne added adjacent land that lifts the first site (CTP1) to 300 MW and signed an MoU with Amata for a second plot (CTP2) aimed at a 1 GW platform, plus a floating-solar supply deal. In April 2026 DayOne said more than 100 MW of IT capacity was expected to go live during 2026.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"3ec56c55-c7d6-5540-9496-65bd267bfc8b","s2":"e90fdf91-30f7-5c84-a3d8-966e73239bfa","s3":"d35e58a3-8b6d-5c3d-adff-b52fb1665027","s4":"ca6abec9-ae6a-5497-b726-6454ad5a2b7e","s5":"a71b032b-15f0-5f3c-a812-1c3677a46d67","s6":"848fb320-9b1a-5740-b680-9005bc2cf96d"},"source_file":"datacenters/projects/dayone-chonburi-tech-park.json","source_record_id":"dayone-chonburi-tech-park","source_record_sha256":"e68ac067cc3c2366a57d3d17c2100941ffcec5203baeeadbf94f308cc267722c","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"406cbcfb19c7d3619d246ed8413cc9677c7df47c2f64acd4197bb1aa097a8ceb"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b020cba78b5fa2123866/#project-e934864d-423f-5afa-a9a8-09bd05079ee1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e934864d-423f-5afa-a9a8-09bd05079ee1.json
e997ad94-2a62-5c44-90f9-fa27edf77dc2 | curated:lvrtc-pozitrons-kurzeme-data-center:phase-1-current-build | vcc-site-cc86e5f5e64a0438e8c1 | curated:lvrtc-pozitrons-kurzeme-data-center | Pozitrons Phase 1 Current Build | Latvia | LV | 56.9356 | 22.0133 | Point | project | direct_geometry | authoritative_site_plan | parcel_reference_point | official_source | reviewed_site_locator | Government cadastral reference point for the reported 113,200 square metre project parcel; 300 metre stated uncertainty. | 300 |  | a16dbcad-9b13-557e-9b38-46e3305bcc0e | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | aff4b014-b3dd-5ba0-b90b-ad3cde08f30a | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | colocation |  | 9590b8c5-a6cb-5c06-bd54-48063d19de70 | [] | not established by selected evidence | [{"evidence_id":"9590b8c5-a6cb-5c06-bd54-48063d19de70","party":"Valsts akciju sabiedrība “Latvijas Valsts radio un televīzijas centrs”","relationship_scope":"intended","role":"operator"}] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [{"as_of_date":"2026-07-02","base":1.4,"confidence":0.98,"evidence_id":"9590b8c5-a6cb-5c06-bd54-48063d19de70","high":1.4,"low":1.4,"method":"reported","metric":"pue","notes":"Reported project PUE retained as a design value; it is not measured, commissioned, accepted, or operating performance.","stage":"design","target_date":null,"unit":"ratio"}] |  |  | Valsts akciju sabiedrība “Latvijas Valsts radio un televīzijas centrs” |  |  |  | https://www.lvrtc.lv/projekti/datu-centrs-pozitrons/projekta-aktualitate/ | https://grafws.kadastrs.lv/geoserver/cp/wfs?service=WFS&version=2.0.0&request=GetFeature&typeNames=cp%3ACadastralParcel&outputFormat=application%2Fjson&CQL_FILTER=label%3D%2762740010343%27 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-cc86e5f5e64a0438e8c1/#project-e997ad94-2a62-5c44-90f9-fa27edf77dc2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e997ad94-2a62-5c44-90f9-fa27edf77dc2.json
e9f8645b-ff54-5ebb-8f6c-6c04dbc8d5e2 | imported:semiconductor-atlas:stack-berry-hill-pittsylvania-county | vcc-site-e6ad7f75be14475fcc3b | imported:semiconductor-atlas:stack-berry-hill-pittsylvania-county | STACK Infrastructure Berry Hill campus, Pittsylvania County | United States | US | 36.82 | -79.4 | Point | project | imported_reference_point | imported_reference_point | admin2 | compiled_reference | admin2_context | Coordinates are the Wikipedia point for Pittsylvania County (s5); precision is county level. Sources place the campus at the Berry Hill megasite in Pittsylvania County but give no address, and the parcel was not geocoded. The staged record used the Danville city centroid, which lies outside the county. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ded86a8d-470e-5b47-9611-0fdb4ab1f141 | announced | 2026-07-27 | 78 | imported_documented_status | b93b9e0d-ac40-55bb-a104-c151cd6438e9 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"136e7452-1116-5bcc-8846-7412269c17ab","notes":null,"party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"stack-berry-hill-pittsylvania-county"},{"evidence_id":"b93b9e0d-ac40-55bb-a104-c151cd6438e9","notes":null,"party":"STACK Infrastructure","relationship_scope":"unknown","role":"developer","source_record_id":"stack-berry-hill-pittsylvania-county"},{"evidence_id":"ded86a8d-470e-5b47-9611-0fdb4ab1f141","notes":"Approved selling the megasite land and is the county-city partnership through which the project is being developed.","party":"Danville-Pittsylvania Regional Industrial Facility Authority","relationship_scope":"unknown","role":"government","source_record_id":"stack-berry-hill-pittsylvania-county"},{"evidence_id":"b93b9e0d-ac40-55bb-a104-c151cd6438e9","notes":"Approved selling the megasite land and is the county-city partnership through which the project is being developed.","party":"Danville-Pittsylvania Regional Industrial Facility Authority","relationship_scope":"unknown","role":"government","source_record_id":"stack-berry-hill-pittsylvania-county"},{"evidence_id":"298bd1d0-124a-5b3a-bf24-e42dd03fa089","notes":"Approved a resolution supporting the project in July 2026.","party":"Pittsylvania County Board of Supervisors","relationship_scope":"unknown","role":"government","source_record_id":"stack-berry-hill-pittsylvania-county"},{"evidence_id":"136e7452-1116-5bcc-8846-7412269c17ab","notes":"The county moved the megasite from Danville Utilities' service territory to Appalachian Power; a July 2026 report says power will come through AEP.","party":"Appalachian Power","relationship_scope":"unknown","role":"utility","source_record_id":"stack-berry-hill-pittsylvania-county"},{"evidence_id":"b93b9e0d-ac40-55bb-a104-c151cd6438e9","notes":"The county moved the megasite from Danville Utilities' service territory to Appalachian Power; a July 2026 report says power will come through AEP.","party":"Appalachian Power","relationship_scope":"unknown","role":"utility","source_record_id":"stack-berry-hill-pittsylvania-county"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://wset.com/news/local/berry-hill-data-center-expected-to-be-operational-by-july-2027-stack-infrastructure-pittsylvania-county-virginia | https://www.wdbj7.com/2026/03/09/sale-approved-pittsylvania-county-land-data-center-developer/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve STACK Infrastructure Berry Hill campus, Pittsylvania County as an independent source record; its admin2 locator does not itself establish a surveyed physical site.","source_record_id":"stack-berry-hill-pittsylvania-county","source_relations":[{"reason":"Rejected Balico Banister/Chatham plan and STACK Berry Hill megasite have distinct proponent and site descriptions; centroid proximity is not site overlap.","relationship":"separate_named_developments","source_id":"balico-pittsylvania-county"}]},"record":{"aliases":["Berry Hill Data Center","Southern Virginia Megasite at Berry Hill data center"],"id":"stack-berry-hill-pittsylvania-county","last_reviewed":"2026-10-09","location":{"admin1":"Virginia","admin2":"Pittsylvania County","country":"US","lat":36.82,"lon":-79.4,"note":"Coordinates are the Wikipedia point for Pittsylvania County (s5); precision is county level. Sources place the campus at the Berry Hill megasite in Pittsylvania County but give no address, and the parcel was not geocoded. The staged record used the Danville city centroid, which lies outside the county.","precision":"admin2","source_ids":["s1","s2","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-04-30","basis":"reported","metric":"investment","note":"Investment over the next 30 years stated in WDBJ's April 2026 report, without attribution to a speaker.","qualifier":"exact","source_ids":["s2"],"unit":"USD","value":73000000000},{"applies_to":"campus","as_of":"2026-07-21","basis":"reported","metric":"investment","note":"Figure in coverage of the county's July 2026 resolution of support; higher than the April 2026 figure and not reconciled by the sources.","qualifier":"exact","source_ids":["s3"],"unit":"USD","value":100000000000},{"applies_to":"campus","as_of":"2026-04-30","basis":"reported","metric":"land_area","note":"Acreage under the purchase and sale agreement, at USD 238,000 a gross acre.","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":2990},{"applies_to":"campus","as_of":"2026-04-30","basis":"planned","metric":"jobs_permanent","note":"Direct full-time jobs within 20 years.","qualifier":"approximately","source_ids":["s2"],"unit":"count","value":2050},{"applies_to":"campus","as_of":"2026-07-21","basis":"reported","metric":"jobs_permanent","note":"Jobs expected over the next two decades, as reported in July 2026.","qualifier":"approximately","source_ids":["s3"],"unit":"count","value":2500},{"applies_to":"campus","as_of":"2026-04-30","basis":"reported","metric":"jobs_construction","note":"Construction workers expected on site.","qualifier":"range","source_ids":["s2"],"unit":"count","value":2000,"value_high":4000}],"milestones":[{"date":"2026-03-09","event":"other","kind":"actual","note":"The regional industrial authority unanimously approved selling the megasite land; a performance agreement was to be considered separately.","source_ids":["s1"]},{"date":"2026-07-21","event":"other","kind":"actual","note":"County supervisors approved a resolution supporting the campus.","source_ids":["s3"]},{"date":"2027-07","event":"first_operational","kind":"planned","note":"The regional industrial authority's chairman expects the first STACK building to be operating about a year after late July 2026.","source_ids":["s4"]}],"name":"STACK Infrastructure Berry Hill campus, Pittsylvania County","notes":"No MW figure from STACK or local officials was found, so the record qualifies on investment. The March 2026 sale was approved to SAC III Acquisition, which shares an address with STACK; STACK was to take down the land in multiple phases, and no closing was reported in the sources. Officials said the project takes no local tax incentives and that most buildings will be dry-cooled, drawing roughly 10,000 to 20,000 gallons of water a day supplied from Eden through Danville. A resident petition against the project had more than 700 signatures in July 2026. A construction start had not been announced.","parties":[{"name":"STACK Infrastructure","role":"developer","source_ids":["s2","s4"]},{"name":"Danville-Pittsylvania Regional Industrial Facility Authority","note":"Approved selling the megasite land and is the county-city partnership through which the project is being developed.","role":"government","source_ids":["s1","s4"]},{"name":"Pittsylvania County Board of Supervisors","note":"Approved a resolution supporting the project in July 2026.","role":"government","source_ids":["s3"]},{"name":"Appalachian Power","note":"The county moved the megasite from Danville Utilities' service territory to Appalachian Power; a July 2026 report says power will come through AEP.","role":"utility","source_ids":["s2","s4"]}],"power_sources":[{"description":"Appalachian Power (AEP) service; STACK is to pay for all needed transmission and generation improvements, according to the county's economic development director.","source_ids":["s2","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260314002756/https://www.wdbj7.com/2026/03/09/sale-approved-pittsylvania-county-land-data-center-developer/","id":"s1","published":"2026-03-09","publisher":"WDBJ7","title":"Sale approved of Pittsylvania County land to data center developer","type":"news","url":"https://www.wdbj7.com/2026/03/09/sale-approved-pittsylvania-county-land-data-center-developer/"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-30","publisher":"WDBJ7","title":"New details out on massive data center planned in Pittsylvania County","type":"news","url":"https://www.wdbj7.com/2026/04/30/new-details-massive-data-center-planned-pittsylvania-county/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260728041957/https://wset.com/news/local/pittsylvania-county-advances-100b-data-center-campus-proposal-despite-resident-concerns-berry-hill-july-2026","id":"s3","published":"2026-07-21","publisher":"WSET","title":"Pittsylvania supervisors back $100B Berry Hill Data Center project","type":"news","url":"https://wset.com/news/local/pittsylvania-county-advances-100b-data-center-campus-proposal-despite-resident-concerns-berry-hill-july-2026"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260728061244/https://wset.com/news/local/berry-hill-data-center-expected-to-be-operational-by-july-2027-stack-infrastructure-pittsylvania-county-virginia","id":"s4","published":"2026-07-27","publisher":"WSET","title":"Berry Hill Data Center expected to be operational by July 2027","type":"news","url":"https://wset.com/news/local/berry-hill-data-center-expected-to-be-operational-by-july-2027-stack-infrastructure-pittsylvania-county-virginia"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261001021018/https://en.wikipedia.org/wiki/Pittsylvania_County,_Virginia","id":"s5","published":null,"publisher":"Wikipedia","title":"Pittsylvania County, Virginia","type":"other","url":"https://en.wikipedia.org/wiki/Pittsylvania_County,_Virginia"}],"status":"announced","status_as_of":"2026-07-27","status_source_ids":["s4"],"summary":"Hyperscale data center campus planned by STACK Infrastructure on about 2,990 acres of the Southern Virginia Megasite at Berry Hill in Pittsylvania County, Virginia. The Danville-Pittsylvania regional industrial authority approved the land sale in March 2026 at USD 238,000 an acre, about USD 720 million in all. WDBJ reported USD 73 billion of investment over 30 years in April 2026, and county supervisors backed a campus reported at USD 100 billion in July 2026. Appalachian Power will serve the site; the authority's chairman expects the first building to run by about July 2027, and full build-out could take 15 to 30 years.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"ded86a8d-470e-5b47-9611-0fdb4ab1f141","s2":"136e7452-1116-5bcc-8846-7412269c17ab","s3":"298bd1d0-124a-5b3a-bf24-e42dd03fa089","s4":"b93b9e0d-ac40-55bb-a104-c151cd6438e9","s5":"d8be689e-882d-57bb-9cf5-448de562c300"},"source_file":"datacenters/projects/stack-berry-hill-pittsylvania-county.json","source_record_id":"stack-berry-hill-pittsylvania-county","source_record_sha256":"d2020bfa59b7a7adbcb7c333acb3d94bcd1996ebae3d0c2cef21f293d0cbdbff","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"1301e456484de774bba21590e6accbaca516c0d4928ada1480c52c54ea81f28d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-e6ad7f75be14475fcc3b/#project-e9f8645b-ff54-5ebb-8f6c-6c04dbc8d5e2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/e9f8645b-ff54-5ebb-8f6c-6c04dbc8d5e2.json
ea4a0cc5-bb09-5a81-b385-38ae79baf22a | curated:macquarie-ic3-super-west-facility:phase-1-build | vcc-site-bae4ad7e597cccb0da1d | curated:macquarie-ic3-super-west-facility | Macquarie IC3 Super West Phase 1 Build | Australia | AU | -33.781 | 151.127 | Polygon | project | cross_source_geometry | openstreetmap_ic3_super_west_full_development_polygon_as_parent_facility_campus_locator | reviewed_openstreetmap_ic3_super_west_full_development_polygon | community_mapped | campus_locator | Contributor-mapped full-development polygon for Intellicentre 3 Super West, used only to locate the parent IC3 Super West facility/campus. It is not specific to the nested Phase 1 fitted-out scope, and it is not an official planning, cadastral, parcel, building, current-construction, or phase boundary. |  | OpenStreetMap does not state horizontal positional accuracy; community-mapped geometry is not cadastral, planning-authority, or survey geometry. | 7b2675bd-76c0-54b0-82d1-3f5d6cb328b2 | under_construction | 2026-07-17 | 88 | authoritative_physical_status_update | 654559c0-3ba5-519b-8215-80eaaf854f5a | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [{"as_of_date":"2025-12-03","base":6.0,"confidence":0.99,"evidence_id":"10cad266-3d5e-591d-a1c4-8ded1e082c7b","high":6.0,"low":6.0,"method":"reported","metric":"critical_it_mw","notes":"Planned fitted-out IT load within the nested Phase 1 scope. It is included within, and not additive to, the facility's 47 MW planned end state; it is not current load, grid draw, gross-facility demand, generation, annual energy, or measured consumption.","stage":"planned","target_date":null,"unit":"MW"}] |  | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.macquariedatacentres.com/data-centres/sydney/macquarie-park-campus/ic3-super-west/ | https://www.openstreetmap.org/way/1298979790 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bae4ad7e597cccb0da1d/#project-ea4a0cc5-bb09-5a81-b385-38ae79baf22a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ea4a0cc5-bb09-5a81-b385-38ae79baf22a.json
ea847e06-abc6-5935-ad21-a3c0adbec711 | curated:capitaland-dc-itph-hyderabad:current-facility-build | vcc-site-f764d5138ed8928c53bc | curated:capitaland-dc-itph-hyderabad | CapitaLand DC ITPH Hyderabad Current Facility Build | India | IN | 17.4353 | 78.3841 | Point | campus | first_party_published_map_pin | source_attribute_decimal_coordinates_to_point_without_centroiding | official_operator_published_campus_reference_point | official_source | campus_locator | The dated results table names CapitaLand DC ITPH. The operator Hyderabad 01 property page explicitly places the data centre within International Tech Park Hyderabad at Madhapur. Its point locates that shared park/campus, not a surveyed data-centre building. No building, phase, construction extent or survey accuracy is asserted. |  | The publisher supplies no numeric horizontal-accuracy statement or surveyed reference feature. | 786fc8a6-df78-5a81-91bd-ab8f60443243 | under_construction | 2026-07-29 | 76 | authoritative_physical_status_update | 508ac7e6-4bff-5500-b660-0b30b7d4afa3 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.capitaland.com/content/dam/capitaland-newsroom/International/2026/july/clint-1h2026-results/2.%20CLINT%201H%202026%20slides_29%20July%202026.pdf | https://www.capitaland.com/en/find-a-property/global-property-listing/data-centres/capitaland-data-centreitphhyderabad.html | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-f764d5138ed8928c53bc/#project-ea847e06-abc6-5935-ad21-a3c0adbec711 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ea847e06-abc6-5935-ad21-a3c0adbec711.json
eaaa4486-a9d9-5cf1-b196-d03c258f8dc1 | imported:semiconductor-atlas:meta-beaver-dam | vcc-site-fcfc181b3d5d02fb0a65 | imported:semiconductor-atlas:meta-beaver-dam | Meta Beaver Dam data center | United States | US | 43.4578 | -88.8373 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City point from OpenStreetMap Nominatim; Meta names the city but no site or road. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 38a97c43-cfaf-5c4e-8a2a-12611c839cbd | under_construction | 2026-10-09 | 4 | imported_documented_status | f8783628-1fdb-531f-8421-6b9d0edb8596 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"38a97c43-cfaf-5c4e-8a2a-12611c839cbd","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-beaver-dam"},{"evidence_id":"f8783628-1fdb-531f-8421-6b9d0edb8596","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-beaver-dam"},{"evidence_id":"38a97c43-cfaf-5c4e-8a2a-12611c839cbd","notes":"Meta refers readers to Mortenson for construction information and opportunities.","party":"Mortenson","relationship_scope":"unknown","role":"builder","source_record_id":"meta-beaver-dam"},{"evidence_id":"38a97c43-cfaf-5c4e-8a2a-12611c839cbd","notes":"Meta says it planned its energy needs with Alliant Energy.","party":"Alliant Energy","relationship_scope":"unknown","role":"utility","source_record_id":"meta-beaver-dam"},{"evidence_id":"f8783628-1fdb-531f-8421-6b9d0edb8596","notes":"Meta says it planned its energy needs with Alliant Energy.","party":"Alliant Energy","relationship_scope":"unknown","role":"utility","source_record_id":"meta-beaver-dam"},{"evidence_id":"f8783628-1fdb-531f-8421-6b9d0edb8596","notes":"Meta says it pays the city the full cost of water and wastewater service.","party":"City of Beaver Dam","relationship_scope":"unknown","role":"government","source_record_id":"meta-beaver-dam"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Beaver-Dam-Data-Center.pdf | https://datacenters.atmeta.com/2025/11/hello-beaver-dam/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta Beaver Dam data center as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-beaver-dam"},"record":{"aliases":["Beaver Dam Data Center"],"id":"meta-beaver-dam","last_reviewed":"2026-10-09","location":{"admin1":"Wisconsin","country":"US","lat":43.4578,"locality":"Beaver Dam","lon":-88.8373,"note":"City point from OpenStreetMap Nominatim; Meta names the city but no site or road.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2025-11-12","basis":"announced","metric":"investment","note":"Meta's undated fact sheet and location list give USD 1 billion or more.","qualifier":"exact","source_ids":["s1"],"unit":"USD","value":1000000000},{"applies_to":"campus","as_of":"2025-11-12","basis":"planned","metric":"floor_area","qualifier":"more_than","source_ids":["s1"],"unit":"sq_ft","value":700000},{"applies_to":"campus","as_of":"2025-11-12","basis":"planned","metric":"jobs_construction","note":"The fact sheet and location list give more than 1,000 skilled trade workers on site at peak.","qualifier":"approximately","source_ids":["s1"],"unit":"count","value":1000},{"applies_to":"campus","as_of":"2025-11-12","basis":"planned","metric":"jobs_permanent","qualifier":"more_than","source_ids":["s1","s2"],"unit":"count","value":100}],"milestones":[{"date":"2025-11-12","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025","event":"construction_started","kind":"actual","note":"Meta's location list gives 2025 as the groundbreaking year.","source_ids":["s3"]}],"name":"Meta Beaver Dam data center","notes":"The status rests on two undated Meta pages: the U.S. location list, which gives 2025 as the groundbreaking year, and the fact sheet, which describes the data center in the future tense. status_as_of is therefore the date both were read (2026-10-09). The fact sheet PDF shows no publication date; its embedded file creation date is 2026-09-01.","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"Mortenson","note":"Meta refers readers to Mortenson for construction information and opportunities.","role":"builder","source_ids":["s1"]},{"name":"Alliant Energy","note":"Meta says it planned its energy needs with Alliant Energy.","role":"utility","source_ids":["s1","s2"]},{"name":"City of Beaver Dam","note":"Meta says it pays the city the full cost of water and wastewater service.","role":"government","source_ids":["s2"]}],"power_sources":[{"description":"Meta says it planned its energy needs with Alliant Energy, pays the full cost of the energy used and matches the site's use with clean and renewable energy.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-11-12","publisher":"Meta Platforms","title":"Hello, Beaver Dam!","type":"company","url":"https://datacenters.atmeta.com/2025/11/hello-beaver-dam/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Meta Platforms","title":"Meta Beaver Dam Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-Beaver-Dam-Data-Center.pdf"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261007122559/https://datacenters.atmeta.com/us-locations/","id":"s3","published":null,"publisher":"Meta Platforms","title":"United States - Meta Data Centers","type":"company","url":"https://datacenters.atmeta.com/us-locations/"}],"status":"under_construction","status_as_of":"2026-10-09","status_source_ids":["s2","s3"],"summary":"Meta data center campus of more than 700,000 square feet in Beaver Dam, Wisconsin, announced in November 2025 as a USD 1 billion investment and described as optimized for Meta's AI workloads. Meta's fact sheet and location list now give the investment as USD 1 billion or more, and the list gives 2025 as the groundbreaking year. Meta says it planned its energy needs with Alliant Energy and pays the full cost of the power used, and it refers readers to Mortenson for construction information. Meta has not published a power capacity or an opening date.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"38a97c43-cfaf-5c4e-8a2a-12611c839cbd","s2":"f8783628-1fdb-531f-8421-6b9d0edb8596","s3":"5478f1c0-762f-5df3-828c-9fa73a73ecb7"},"source_file":"datacenters/projects/meta-beaver-dam.json","source_record_id":"meta-beaver-dam","source_record_sha256":"f7194a0774189abab934e81dbe4596c5d7a07bf4eb05438362099238e1b91c75","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7eb8591c3b911da58bb84aec866f72b6ea62ec59b6102afaaa0f8df5f6d437e9"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-fcfc181b3d5d02fb0a65/#project-eaaa4486-a9d9-5cf1-b196-d03c258f8dc1 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/eaaa4486-a9d9-5cf1-b196-d03c258f8dc1.json
eaea9fff-9fd3-506f-a490-320f64d86dc3 | curated:cyrusone-yorkville-technology-campus:current-site-work | vcc-site-72215030ee46f7977c35 | curated:cyrusone-yorkville-technology-campus | CyrusOne Yorkville Current Site Work | United States | US | 41.6772 | -88.4822 | Point | campus | official_parcel_centroid_to_point | official_parcel_centroid | largest_identified_owner_parcel_centroid | official_source | campus_locator | Exact county-returned centroid of one 72.52475709-acre C1 YORKVILLE LLC parcel; not the full campus, a building, or active work area. |  | The county service provides a derived parcel centroid but no survey-grade horizontal accuracy. | b5ab4fb4-fff8-580c-8974-9c89f54ed8ec | site_preparation | 2026-07-19 | 86 | authoritative_physical_status_update | 7bba0157-7f22-5a00-b69c-a94cfdffa771 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.cyrusone.com/data-centers/north-america/yorkville-technology-campus | https://maps.co.kendall.il.us/server/rest/services/Hosted/Current_Cadastral_Features/FeatureServer/1/query | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-72215030ee46f7977c35/#project-eaea9fff-9fd3-506f-a490-320f64d86dc3 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/eaea9fff-9fd3-506f-a490-320f64d86dc3.json
eb451867-d1d3-5e41-bce7-d375e861167a | curated:microsoft-lyle-creek-conover-data-center:current-build | vcc-site-9b86fe87cb674e474940 | curated:microsoft-lyle-creek-conover-data-center | Microsoft Conover Lyle Creek Current Build | United States | US | 35.7311 | -81.2054 | Point | project | coordinates_to_point | official_permit_project_coordinate | permit_notice_project_point | official_source | project_locator | Exact USACE-published project coordinate, independently shown inside a current official Catawba parcel; not a parcel boundary, building, or work footprint. The primary capture is an indexed-text extract, not fetched PDF bytes. |  | USACE gives no bounded positional accuracy and the live legacy PDF body is currently unavailable. | 64ff0af6-8438-5865-b01f-3d997ee799b2 | under_construction | 2026-05-31 | 135 | authoritative_physical_status_update | 477ad52f-a618-5140-bd2f-645a05bc2dd4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://local.microsoft.com/blog/lyle-creek-datacenter-construction-update/ | https://saw-reg.usace.army.mil/PN/2023/SAW-2023-00898-PN.pdf | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-9b86fe87cb674e474940/#project-eb451867-d1d3-5e41-bce7-d375e861167a | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/eb451867-d1d3-5e41-bce7-d375e861167a.json
eb75ea0d-8dba-56a1-a956-135227b3d6e6 | imported:semiconductor-atlas:terawulf-chesapeake-morgantown | vcc-site-6a1efb9a8859fd17aa59 | imported:semiconductor-atlas:terawulf-chesapeake-morgantown | TeraWulf Chesapeake Data Campus (Morgantown) | United States | US | 38.3453 | -76.9711 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources name the Morgantown Generating Station in Charles County without an address. Coordinates are the Morgantown community point from its Wikipedia article, which notes the plant's smokestacks; they are not the plant site itself. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 973d660a-dde9-5e62-a89b-8cfea760353c | proposed | 2026-08-05 | 69 | imported_documented_status | 0d31dbb3-2807-5bee-b1e8-d707502791a2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"973d660a-dde9-5e62-a89b-8cfea760353c","notes":"Buyer of the generating station under a February 2026 agreement; the purchase price is confidential.","party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-chesapeake-morgantown"},{"evidence_id":"0d31dbb3-2807-5bee-b1e8-d707502791a2","notes":"Buyer of the generating station under a February 2026 agreement; the purchase price is confidential.","party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-chesapeake-morgantown"},{"evidence_id":"5ada2393-b227-5729-8167-268f7da69cf1","notes":"Buyer of the generating station under a February 2026 agreement; the purchase price is confidential.","party":"TeraWulf","relationship_scope":"unknown","role":"developer","source_record_id":"terawulf-chesapeake-morgantown"},{"evidence_id":"5ada2393-b227-5729-8167-268f7da69cf1","notes":"Current owner and seller of the plant; the sale awaited closing after FERC approval.","party":"GenOn Holdings","relationship_scope":"unknown","role":"owner","source_record_id":"terawulf-chesapeake-morgantown"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | GenOn Holdings |  |  |  |  | https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results | https://investors.terawulf.com/news-events/press-releases/detail/129 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve TeraWulf Chesapeake Data Campus (Morgantown) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"terawulf-chesapeake-morgantown"},"record":{"aliases":["Chesapeake Data Campus","Chesapeake Data","Morgantown Generating Station redevelopment"],"id":"terawulf-chesapeake-morgantown","last_reviewed":"2026-10-09","location":{"admin1":"Maryland","admin2":"Charles County","country":"US","lat":38.3453,"locality":"Morgantown","lon":-76.9711,"note":"Sources name the Morgantown Generating Station in Charles County without an address. Coordinates are the Morgantown community point from its Wikipedia article, which notes the plant's smokestacks; they are not the plant site itself.","precision":"locality","source_ids":["s1","s3","s5"]},"metrics":[{"applies_to":"campus","as_of":"2026-08-05","basis":"planned","metric":"power_capacity","note":"TeraWulf describes expansion to support up to 1 GW of load, and press reports describe 1 GW of gas-fired generation for data centers; the two are not clearly separated.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s2","s3"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-02-02","basis":"planned","metric":"power_capacity","phase_label":"Initial phase","power_scope":"unspecified","qualifier":"approximately","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"phase","as_of":"2026-08-05","basis":"operational","metric":"power_capacity","note":"Existing grid-connected generation at the plant; The Banner puts it at about 220 MW from 1970s-era oil units. This supplies the grid, not a data center.","phase_label":"Existing oil-fired generation","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s1","s2","s3","s4"],"unit":"MW","value":210},{"applies_to":"campus","as_of":"2026-02-02","basis":"planned","metric":"land_area","note":"Buildable acres included in the acquisition.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":250}],"milestones":[{"date":"2026-02-02","event":"announced","kind":"actual","note":"TeraWulf announced the planned acquisition, subject to third-party consents and regulatory approvals including FERC.","source_ids":["s1"]},{"date":"2026-07-29","event":"other","kind":"actual","note":"FERC authorized TeraWulf's acquisition of the Morgantown station; other closing conditions and approvals remained.","source_ids":["s2","s3"]},{"date":"2026-07","event":"other","kind":"actual","note":"Charles County commissioners declined to change zoning to allow data centers and chose to study the issue.","source_ids":["s3"]},{"date":"2030","event":"first_operational","kind":"planned","note":"Initial data center operations contemplated for 2030.","source_ids":["s2"]}],"name":"TeraWulf Chesapeake Data Campus (Morgantown)","notes":"The Q1 2026 release (s4) still listed the acquisition as subject to regulatory approvals including FERC. No source opened confirms that the sale has closed. Data center construction would also need a local zoning path, which Charles County had not provided as of July 2026. TeraWulf's releases describe the site as suited to compute-intensive uses without naming AI. Environmental and consumer groups opposed the sale at FERC over electricity price and grid concerns.","parties":[{"name":"TeraWulf","note":"Buyer of the generating station under a February 2026 agreement; the purchase price is confidential.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"GenOn Holdings","note":"Current owner and seller of the plant; the sale awaited closing after FERC approval.","role":"owner","source_ids":["s3"]}],"power_sources":[{"description":"TeraWulf plans to restart the plant on natural gas to power the data campus. The Banner reports that Maryland's top environmental regulator offered in a December letter to expedite approvals, including pipeline rights-of-way; the governor's office said the letter covered cleanup only.","source_ids":["s3"],"type":"natural_gas_onsite"},{"description":"About 500 MW of battery storage is planned so excess generation can be exported to the grid.","source_ids":["s1","s3"],"type":"battery_storage"},{"description":"The existing plant is grid-connected in the PJM market, and TeraWulf aims for the site to remain a net energy supplier to Maryland.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-02-02","publisher":"TeraWulf","title":"TeraWulf expands digital and power infrastructure portfolio with strategic acquisitions in Kentucky and Maryland","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/129"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261004051013/https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results","id":"s2","published":"2026-08-05","publisher":"TeraWulf","title":"TeraWulf reports second quarter 2026 results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260912050321/https://www.thebanner.com/economy/growth-development/charles-county-coal-data-center-ZHX6HMX5BNDS7HH6X42MKV7A4A/","id":"s3","published":"2026-07-29","publisher":"The Baltimore Banner","title":"Feds approve sale of Potomac River power plant to data center developer","type":"news","url":"https://www.thebanner.com/economy/growth-development/charles-county-coal-data-center-ZHX6HMX5BNDS7HH6X42MKV7A4A/"},{"accessed":"2026-10-09","id":"s4","published":"2026-05-08","publisher":"TeraWulf","title":"TeraWulf reports first quarter 2026 results","type":"company","url":"https://investors.terawulf.com/news-events/press-releases/detail/140/terawulf-reports-first-quarter-2026-results"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Morgantown, Maryland","type":"other","url":"https://en.wikipedia.org/wiki/Morgantown,_Maryland"}],"status":"proposed","status_as_of":"2026-08-05","status_source_ids":["s2","s3"],"summary":"TeraWulf plan to buy the Morgantown Generating Station on the Potomac River in Charles County, Maryland, from GenOn and redevelop it as a data campus with on-site power. The former coal plant, whose coal boilers retired in 2022, now runs about 210 to 220 MW of oil-fired units. TeraWulf proposes restarting it on natural gas and adding battery storage to support up to 1 GW of data center load on about 250 buildable acres, starting with about 500 MW. FERC approved the sale in July 2026 and TeraWulf contemplates first data center operations in 2030, but Charles County zoning does not yet allow data centers.","workloads":["hpc"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"973d660a-dde9-5e62-a89b-8cfea760353c","s2":"0d31dbb3-2807-5bee-b1e8-d707502791a2","s3":"5ada2393-b227-5729-8167-268f7da69cf1","s4":"3f10e818-6cca-560f-ad7d-ad1d2eb9eb5d","s5":"9662c71c-a6af-549b-a563-4bca3894c1b7"},"source_file":"datacenters/projects/terawulf-chesapeake-morgantown.json","source_record_id":"terawulf-chesapeake-morgantown","source_record_sha256":"18df935aca0ec49662ebb793329c8d784f2190244ab66828c6c9d0f1e558aeb6","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"2d88ba12560f6541cc29109fcc38a918b163081507876c2296aab985485d798f"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6a1efb9a8859fd17aa59/#project-eb75ea0d-8dba-56a1-a956-135227b3d6e6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/eb75ea0d-8dba-56a1-a956-135227b3d6e6.json
ebd0b7e7-0ca5-501e-89ff-74f8bf30f59b | imported:semiconductor-atlas:omnia-data-center-pecem | vcc-site-99459620c3cd48c8a82f | curated:omnia-pecem-data-center-campus | Omnia Data Center Pecém | Brazil | BR | -3.5467 | -38.8314 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | The source names the Pecém complex but no parcel. Coordinates are the Port of Pecém reference point (English Wikipedia infobox), in São Gonçalo do Amarante; the data centre's position within the industrial and port complex was not published, so the municipality is left blank. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | fb70795b-1c1b-5f06-86f0-61958cf43fd2 | announced | 2026-05-18 | 148 | imported_documented_status | fb70795b-1c1b-5f06-86f0-61958cf43fd2 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"fb70795b-1c1b-5f06-86f0-61958cf43fd2","notes":"Described as developer, investor and operator of the data centre and a hyperscale platform backed by Pátria Investimentos funds.","party":"Omnia","relationship_scope":"unknown","role":"developer","source_record_id":"omnia-data-center-pecem"},{"evidence_id":"fb70795b-1c1b-5f06-86f0-61958cf43fd2","notes":"Funds it manages back Omnia.","party":"Pátria Investimentos","relationship_scope":"unknown","role":"investor","source_record_id":"omnia-data-center-pecem"},{"evidence_id":"fb70795b-1c1b-5f06-86f0-61958cf43fd2","notes":"Develops, operates and manages the wind generation contracted for the site.","party":"Casa dos Ventos","relationship_scope":"unknown","role":"power_supplier","source_record_id":"omnia-data-center-pecem"},{"evidence_id":"4be52b69-ddf3-549c-8bdf-7717cdf9a8ef","notes":"Reported and unconfirmed: Portuguese Wikipedia, citing a May 2026 Reuters report, says the data centre is intended for ByteDance (the Reuters headline names TikTok). The Reuters article could not be opened, and the Casa dos Ventos announcement names no tenant.","party":"ByteDance","relationship_scope":"unknown","role":"tenant","source_record_id":"omnia-data-center-pecem"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  |  |  | ByteDance |  | https://casadosventos.com.br/cases/case-omnia | https://casadosventos.com.br/cases/case-omnia | [{"identity_decision":{"decision":"same_site_distinct_scope","flags":["administrative_locator_not_project_geometry","campus_and_phase_scopes_must_remain_separate"],"rationale":"Same OMNIA Data Center Pecem campus at the Pecem industrial complex. Source covers campus/PPA context; existing record selects initial construction supported by SEMACE project identity and June 2026 official observation. The port reference point is not the site.","source_record_id":"omnia-data-center-pecem","target_physical_site_stable_key":"curated:omnia-pecem-data-center-campus"},"record":{"aliases":["Data Center Pecém"],"id":"omnia-data-center-pecem","last_reviewed":"2026-10-09","location":{"admin1":"Ceará","country":"BR","lat":-3.5467,"locality":"Pecém","lon":-38.8314,"note":"The source names the Pecém complex but no parcel. Coordinates are the Port of Pecém reference point (English Wikipedia infobox), in São Gonçalo do Amarante; the data centre's position within the industrial and port complex was not published, so the municipality is left blank.","precision":"locality","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2026-05-18","basis":"contracted","metric":"power_capacity","note":"Renewable energy contracted for the data centre, stated in average megawatts (MWm); not a stated IT or facility load.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1"],"unit":"MW","value":300}],"milestones":[{"date":"2026-05-18","event":"other","kind":"actual","note":"Omnia and Casa dos Ventos announced a power purchase agreement of about USD 2 billion for up to 300 average MW of wind energy for the data centre.","source_ids":["s1"]}],"name":"Omnia Data Center Pecém","parties":[{"name":"Omnia","note":"Described as developer, investor and operator of the data centre and a hyperscale platform backed by Pátria Investimentos funds.","role":"developer","source_ids":["s1"]},{"name":"Pátria Investimentos","note":"Funds it manages back Omnia.","role":"investor","source_ids":["s1"]},{"name":"Casa dos Ventos","note":"Develops, operates and manages the wind generation contracted for the site.","role":"power_supplier","source_ids":["s1"]},{"name":"ByteDance","note":"Reported and unconfirmed: Portuguese Wikipedia, citing a May 2026 Reuters report, says the data centre is intended for ByteDance (the Reuters headline names TikTok). The Reuters article could not be opened, and the Casa dos Ventos announcement names no tenant.","role":"tenant","source_ids":["s2"]}],"power_sources":[{"description":"Contracted wind generation from projects in Ceará and Piauí under a self-production arrangement in which Omnia holds equity in the generation assets.","source_ids":["s1"],"type":"wind"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-05-18","publisher":"Casa dos Ventos","title":"Omnia e Casa dos Ventos firmam maior contrato de autoprodução de energia renovável da América Latina para data centers","type":"company","url":"https://casadosventos.com.br/cases/case-omnia"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Wikipedia (Portuguese)","title":"Casa dos Ventos","type":"other","url":"https://pt.wikipedia.org/wiki/Casa_dos_Ventos"}],"status":"announced","status_as_of":"2026-05-18","status_source_ids":["s1"],"summary":"Omnia, a hyperscale data centre platform backed by funds managed by Pátria Investimentos, is developing Data Center Pecém at the Pecém industrial and port complex in Ceará, Brazil, as its first project. In May 2026 Omnia and Casa dos Ventos announced a power purchase agreement valued at about USD 2 billion for an estimated up to 300 average MW of wind energy from projects in Ceará and Piauí, under which Omnia becomes a self-producer with equity in the generation assets. Portuguese Wikipedia, citing Reuters, reports that the facility is intended for ByteDance; the companies' announcement names no tenant, so the link is unconfirmed. No data centre IT capacity or schedule was found.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"fb70795b-1c1b-5f06-86f0-61958cf43fd2","s2":"4be52b69-ddf3-549c-8bdf-7717cdf9a8ef"},"source_file":"datacenters/projects/omnia-data-center-pecem.json","source_record_id":"omnia-data-center-pecem","source_record_sha256":"c9279483257a624b06e9ea785c7a8b5cba7f3d47a5aa69e01b6cf841e9318cec","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"6bb6c50587e24a5e27a2317f1f60adc82bb095190a681a2f1ea0296053362f9c"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-99459620c3cd48c8a82f/#project-ebd0b7e7-0ca5-501e-89ff-74f8bf30f59b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ebd0b7e7-0ca5-501e-89ff-74f8bf30f59b.json
ec871425-75fd-5ee1-9a6f-0e901b2f5837 | imported:semiconductor-atlas:airtrunk-jhb2-iskandar-puteri | vcc-site-3d8ad7e35f76709e9b15 | imported:semiconductor-atlas:airtrunk-jhb2-iskandar-puteri | AirTrunk JHB2 | Malaysia | MY | 1.4523 | 103.6145 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | AirTrunk names Iskandar Puteri without an address; coordinates are the OpenStreetMap Nominatim centroid of Iskandar Puteri. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 09661d28-4b3e-583a-97a6-7e4d2a00a48a | announced | 2026-07-29 | 76 | imported_documented_status | 09661d28-4b3e-583a-97a6-7e4d2a00a48a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"09661d28-4b3e-583a-97a6-7e4d2a00a48a","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb2-iskandar-puteri"},{"evidence_id":"21fc49b4-de9b-50a1-9909-b72c6655ad85","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb2-iskandar-puteri"},{"evidence_id":"f402d2ac-aefa-5ba0-bef7-a81ebb98b358","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb2-iskandar-puteri"},{"evidence_id":"22d00a3f-a2d7-575f-aef5-cf987cce3021","notes":null,"party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-jhb2-iskandar-puteri"},{"evidence_id":"09661d28-4b3e-583a-97a6-7e4d2a00a48a","notes":"Providing the grid connection under its Green Lane Pathway; AirTrunk is providing land for a new TNB substation.","party":"Tenaga Nasional Berhad","relationship_scope":"unknown","role":"utility","source_record_id":"airtrunk-jhb2-iskandar-puteri"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://airtrunk.com/airtrunk-scales-up-in-malaysia-with-announcement-of-second-malaysia-hyperscale-data-centre-jhb2/ | https://airtrunk.com/airtrunk-scales-up-in-malaysia-with-announcement-of-second-malaysia-hyperscale-data-centre-jhb2/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AirTrunk JHB2 as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"airtrunk-jhb2-iskandar-puteri","source_relations":[{"reason":"AirTrunk names separate campuses; shared JHB2 electrical supply does not merge JHB3 physical identity.","relationship":"separate_nearby_campuses","source_id":"airtrunk-jhb3-iskandar-puteri"},{"reason":"AirTrunk names separate campuses; shared JHB2 electrical supply does not merge JHB4 physical identity.","relationship":"separate_nearby_campuses","source_id":"airtrunk-jhb4-iskandar-puteri"}]},"record":{"aliases":["JHB2 Johor"],"id":"airtrunk-jhb2-iskandar-puteri","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Johor Bahru District","country":"MY","lat":1.4523,"locality":"Iskandar Puteri","lon":103.6145,"note":"AirTrunk names Iskandar Puteri without an address; coordinates are the OpenStreetMap Nominatim centroid of Iskandar Puteri.","precision":"locality","source_ids":["s1"]},"metrics":[{"applies_to":"campus","as_of":"2025-02-12","basis":"planned","metric":"power_capacity","note":"AirTrunk's facility page calls this total capacity without saying whether it is IT load. AirTrunk separately gives more than 420 MW of IT load across JHB1 and JHB2 combined.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1","s2"],"unit":"MW","value":270},{"applies_to":"campus","as_of":"2026-10","basis":"reported","metric":"land_area","note":"Undated facility page viewed October 2026.","qualifier":"more_than","source_ids":["s2"],"unit":"hectares","value":11}],"milestones":[{"date":"2025-02-12","event":"announced","kind":"actual","note":"AirTrunk said the announcement brought its Malaysia investment to RM 9.7 billion, without a JHB2-specific figure.","source_ids":["s1"]},{"date":"2026-04-30","event":"other","kind":"actual","note":"AirTrunk said JHB1 and JHB2 were almost 100% contracted.","source_ids":["s3"]},{"date":"2026-07-29","event":"other","kind":"actual","note":"US$2.325 billion (RM 9.5 billion) green project financing from 30 lenders including IFC secured to support JHB2's development.","source_ids":["s4"]}],"name":"AirTrunk JHB2","parties":[{"name":"AirTrunk","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Tenaga Nasional Berhad","note":"Providing the grid connection under its Green Lane Pathway; AirTrunk is providing land for a new TNB substation.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Grid connection from Tenaga Nasional Berhad, targeted on an accelerated 12-month timeframe.","source_ids":["s1"],"type":"grid"}],"related_ids":["airtrunk-jhb1-johor"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-02-12","publisher":"AirTrunk","title":"AirTrunk grows Malaysia platform with second cloud and AI-ready data centre in Johor","type":"company","url":"https://airtrunk.com/airtrunk-scales-up-in-malaysia-with-announcement-of-second-malaysia-hyperscale-data-centre-jhb2/"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"AirTrunk","title":"JHB2 Johor Bahru","type":"company","url":"https://airtrunk.com/data-centres/jhb2/"},{"accessed":"2026-10-09","id":"s3","published":"2026-04-30","publisher":"AirTrunk","title":"AirTrunk doubles down in Malaysia with two new hyperscale campuses in Johor Bahru","type":"company","url":"https://airtrunk.com/airtrunk-doubles-down-in-malaysia-with-two-new-hyperscale-campuses-in-johor-bahru/"},{"accessed":"2026-10-09","id":"s4","published":"2026-07-29","publisher":"AirTrunk","title":"AirTrunk secures US$2.325b green financing to support sustainable digital infrastructure growth in Malaysia","type":"company","url":"https://airtrunk.com/airtrunk-secures-us2-325b-green-financing-to-support-sustainable-digital-infrastructure-growth-in-malaysia/"}],"status":"announced","status_as_of":"2026-07-29","status_source_ids":["s1","s4"],"summary":"JHB2 is AirTrunk's second hyperscale campus in Malaysia, announced in February 2025 in Iskandar Puteri, Johor, and scalable to more than 270 MW on a site of over 11 hectares. It is designed for high-density AI loads with liquid cooling and a grid connection from Tenaga Nasional Berhad on an accelerated schedule, with AirTrunk providing land for a new substation. In April 2026 AirTrunk said JHB1 and JHB2 were almost fully contracted, and in July 2026 it secured US$2.325 billion of green project financing for JHB2. The cited sources give no opening date.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"09661d28-4b3e-583a-97a6-7e4d2a00a48a","s2":"21fc49b4-de9b-50a1-9909-b72c6655ad85","s3":"f402d2ac-aefa-5ba0-bef7-a81ebb98b358","s4":"22d00a3f-a2d7-575f-aef5-cf987cce3021"},"source_file":"datacenters/projects/airtrunk-jhb2-iskandar-puteri.json","source_record_id":"airtrunk-jhb2-iskandar-puteri","source_record_sha256":"05d8cffa147ddb49bdcc4de12a460863f46b072f4ffe4dec45ae38c08852f466","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0b495ab41f673590844d48d51e7e7f81c6ac98fdba1296399f86729ceae7cdd3"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3d8ad7e35f76709e9b15/#project-ec871425-75fd-5ee1-9a6f-0e901b2f5837 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ec871425-75fd-5ee1-9a6f-0e901b2f5837.json
ec8c635b-93db-5c3c-904e-820b7c4f1233 | imported:semiconductor-atlas:microsoft-aragon-villamayor-de-gallego | vcc-site-b74f3c274a5a8c1e01da | imported:semiconductor-atlas:microsoft-aragon-villamayor-de-gallego | Microsoft Villamayor de Gállego datacenter campus (Aragón) | Spain | ES | 41.6857 | -0.774 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Municipality centroid from Nominatim. Sources place the campus on Villamayor de Gállego land associated with the Polígono Malpica, whose named substation (Malpica) serves it; the parcel itself is not identified. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | e35f6456-545d-588b-96a4-06edc7861eec | announced | 2026-09-04 | 39 | imported_documented_status | a7bfbcf3-fda4-58b8-9677-f994e5e6a645 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"e35f6456-545d-588b-96a4-06edc7861eec","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-villamayor-de-gallego"},{"evidence_id":"1fc10052-2e4c-517e-9cea-2e5f1c959a8f","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-villamayor-de-gallego"},{"evidence_id":"14f6f900-635e-5e74-9e8d-d179f4ad51ac","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-villamayor-de-gallego"},{"evidence_id":"3c916b8c-b9e9-572f-b179-e2b2fbb53828","notes":null,"party":"Microsoft","relationship_scope":"unknown","role":"developer","source_record_id":"microsoft-aragon-villamayor-de-gallego"},{"evidence_id":"e35f6456-545d-588b-96a4-06edc7861eec","notes":"Declared the project of regional interest and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-villamayor-de-gallego"},{"evidence_id":"14f6f900-635e-5e74-9e8d-d179f4ad51ac","notes":"Declared the project of regional interest and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-villamayor-de-gallego"},{"evidence_id":"3c916b8c-b9e9-572f-b179-e2b2fbb53828","notes":"Declared the project of regional interest and is processing the PIGA regional plan.","party":"Gobierno de Aragón","relationship_scope":"unknown","role":"government","source_record_id":"microsoft-aragon-villamayor-de-gallego"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.eldiario.es/aragon/politica/zec-presenta-25-alegaciones-plan-microsoft-exige-alcaldesa-zaragoza-paralizar-centro-datos_1_13487405.html | https://www.vozpopuli.com/economia/aragon-centro-datos-microsoft-inversion-2000-millones.html | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Microsoft Villamayor de Gállego datacenter campus (Aragón) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"microsoft-aragon-villamayor-de-gallego","source_relations":[{"reason":"Distinct Azora/Tillion and Microsoft projects; shared Villamayor municipality point is not a parcel or alias.","relationship":"separate_named_developments","source_id":"azora-tillion-villamayor-de-gallego"}]},"record":{"aliases":["Microsoft Malpica campus"],"id":"microsoft-aragon-villamayor-de-gallego","last_reviewed":"2026-10-09","location":{"admin1":"Aragón","admin2":"Zaragoza","country":"ES","lat":41.6857,"locality":"Villamayor de Gállego","lon":-0.774,"note":"Municipality centroid from Nominatim. Sources place the campus on Villamayor de Gállego land associated with the Polígono Malpica, whose named substation (Malpica) serves it; the parcel itself is not identified.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2024-07-03","basis":"announced","metric":"investment","note":"Total cited when the regional interest declaration was made; the Vozpópuli headline rounds it to EUR 2 billion.","qualifier":"exact","source_ids":["s1","s2"],"unit":"EUR","value":2200000000},{"applies_to":"phase","as_of":"2024-07-03","basis":"announced","metric":"investment","phase_label":"Initial construction phase","qualifier":"exact","source_ids":["s1","s2"],"unit":"EUR","value":365300000},{"applies_to":"campus","as_of":"2025-11-14","basis":"reported","metric":"investment","note":"Per-site figure in the November 2025 PIGA as reported by elDiario.es; lower than the 2024 figure, and the sources do not explain the difference.","qualifier":"exact","source_ids":["s3"],"unit":"EUR","value":1733000000},{"applies_to":"phase","as_of":"2025-11-14","basis":"planned","metric":"power_capacity","phase_label":"First phase","power_scope":"unspecified","qualifier":"exact","source_ids":["s3","s4"],"unit":"MW","value":50},{"applies_to":"campus","as_of":"2025-11-14","basis":"planned","metric":"power_capacity","note":"Second-phase aspiration per campus in the PIGA, as reported by elDiario.es; Forbes gives 250-300 MW per campus over about ten years.","power_scope":"unspecified","qualifier":"up_to","source_ids":["s3","s4"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-11-14","basis":"planned","metric":"land_area","qualifier":"exact","source_ids":["s3"],"unit":"hectares","value":81},{"applies_to":"phase","as_of":"2024-07-03","basis":"planned","metric":"jobs_construction","note":"Inspenet describes these as jobs during construction; Vozpópuli says the initial phase will employ 2,000 people.","phase_label":"Initial construction phase","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":2000},{"applies_to":"campus","as_of":"2024-07-03","basis":"planned","metric":"jobs_permanent","qualifier":"approximately","source_ids":["s1","s2"],"unit":"count","value":300}],"milestones":[{"date":"2024-07-03","event":"announced","kind":"actual","note":"Aragón's governing council declared the campus of regional interest.","source_ids":["s1","s2"]},{"date":"2025-11-14","event":"other","kind":"actual","note":"Initial approval of the PIGA Región MSFT plan covering La Muela, Villamayor de Gállego and Zaragoza, opening a public information period.","source_ids":["s3","s4"]},{"date":"2026-07-30","event":"other","kind":"actual","note":"A modification of the PIGA was published in the Boletín Oficial de Aragón for public comment.","source_ids":["s5"]},{"date":"2030","event":"first_operational","kind":"planned","note":"Forbes reported the first phase was expected to operate from 2030.","source_ids":["s4"]}],"name":"Microsoft Villamayor de Gállego datacenter campus (Aragón)","notes":"Investment figures conflict between the 2024 declaration (EUR 2.2 billion) and the 2025 PIGA (about EUR 1.73 billion); both are kept with their dates. In 2024 the sources put Microsoft's investment across its three Aragón sites at EUR 6.6 billion. No government primary source was opened; Boletín Oficial de Aragón entries should be added when available.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Gobierno de Aragón","note":"Declared the project of regional interest and is processing the PIGA regional plan.","role":"government","source_ids":["s1","s3","s4"]}],"power_sources":[{"description":"Grid supply through a new substation (named Malpica) starting at 132 kV with a later upgrade to 220 kV.","source_ids":["s3"],"type":"grid"}],"related_ids":["microsoft-aragon-la-muela","microsoft-aragon-zaragoza-puerto-venecia"],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-07-03","publisher":"Vozpópuli","title":"Aragón da luz verde a un centro de datos de Microsoft con una inversión de 2.000 millones","type":"news","url":"https://www.vozpopuli.com/economia/aragon-centro-datos-microsoft-inversion-2000-millones.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260517054437/https://inspenet.com/noticias/microsoft-abrira-centro-de-datos-en-aragon/","id":"s2","published":"2024-07-04","publisher":"Inspenet","title":"Microsoft abrirá otro centro de datos en Aragón (el tercero)","type":"trade_press","url":"https://inspenet.com/noticias/microsoft-abrira-centro-de-datos-en-aragon/"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-14","publisher":"elDiario.es","title":"Microsoft avanza con su red de centros de datos en Zaragoza, donde proyecta una de sus mayores regiones en Europa","type":"news","url":"https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html"},{"accessed":"2026-10-09","id":"s4","published":"2025-11-14","publisher":"Forbes España","title":"Microsoft obtiene luz verde para su ambicioso proyecto de centros de datos en Aragón","type":"news","url":"https://forbes.es/empresas/828243/microsoft-obtiene-luz-verde-para-su-ambicioso-proyecto-de-centros-de-datos-en-aragon/"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-04","publisher":"elDiario.es","title":"ZeC presenta 25 alegaciones al plan de Microsoft y exige a la alcaldesa de Zaragoza paralizar un centro de datos","type":"news","url":"https://www.eldiario.es/aragon/politica/zec-presenta-25-alegaciones-plan-microsoft-exige-alcaldesa-zaragoza-paralizar-centro-datos_1_13487405.html"}],"status":"announced","status_as_of":"2026-09-04","status_source_ids":["s5"],"summary":"Planned Microsoft datacenter campus on Villamayor de Gállego land at the Malpica industrial estate northeast of Zaragoza, the third Aragón site Microsoft disclosed. The regional government declared it of regional interest in July 2024, citing EUR 2.2 billion of total investment and EUR 365.3 million for an initial phase. The November 2025 regional plan (PIGA Región MSFT) lists 81 hectares and about EUR 1.73 billion, with 50 MW secured for a first phase and up to 300 MW sought later. A modified plan went out for public comment in July 2026, and Forbes reported first operation was expected from 2030.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"e35f6456-545d-588b-96a4-06edc7861eec","s2":"1fc10052-2e4c-517e-9cea-2e5f1c959a8f","s3":"14f6f900-635e-5e74-9e8d-d179f4ad51ac","s4":"3c916b8c-b9e9-572f-b179-e2b2fbb53828","s5":"a7bfbcf3-fda4-58b8-9677-f994e5e6a645"},"source_file":"datacenters/projects/microsoft-aragon-villamayor-de-gallego.json","source_record_id":"microsoft-aragon-villamayor-de-gallego","source_record_sha256":"d2af0f994a460d635bbec1a07ec9c75d3ea424551a637463b05ddc35b2a2a30b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"8eb76b8b42ab11dd1da0f4f4644713db3c5a4e7f7dbea86b60f474218de34810"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-b74f3c274a5a8c1e01da/#project-ec8c635b-93db-5c3c-904e-820b7c4f1233 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ec8c635b-93db-5c3c-904e-820b7c4f1233.json
edaa7f7d-5025-5f95-9870-3ad12478339c | imported:semiconductor-atlas:meta-prometheus-new-albany | vcc-site-66e95eb80a122bb2ee32 | imported:semiconductor-atlas:meta-prometheus-new-albany | Meta New Albany data center campus (Prometheus) | United States | US | 40.0812 | -82.8088 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City point from OpenStreetMap Nominatim; the cited sources name New Albany but give no site address for the data center buildings. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | f777e6f8-5a41-53c1-85a1-8a093d44e70b | partially_operational | 2026-09-16 | 27 | imported_documented_status | 5e95a967-c06e-56c1-b72a-9f09ba8ca132 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"f777e6f8-5a41-53c1-85a1-8a093d44e70b","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"67d9aa6f-0bc0-51be-a5d3-eb574cf5d38d","notes":null,"party":"Meta Platforms","relationship_scope":"unknown","role":"developer","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"f777e6f8-5a41-53c1-85a1-8a093d44e70b","notes":"Meta says it planned its energy needs with AEP.","party":"American Electric Power (AEP)","relationship_scope":"unknown","role":"utility","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"076967b9-e7bd-53d2-a04b-851aa51a63de","notes":"Builds and operates behind-the-meter gas plants in New Albany whose output goes to Sidecat, described as a Meta affiliate.","party":"Will-Power OH","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"097214ae-03ad-505e-9ea1-d45f37b9ccbb","notes":"Builds and operates behind-the-meter gas plants in New Albany whose output goes to Sidecat, described as a Meta affiliate.","party":"Will-Power OH","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"acecc2fb-4230-5483-bac6-2de70661d51a","notes":"Builds and operates behind-the-meter gas plants in New Albany whose output goes to Sidecat, described as a Meta affiliate.","party":"Will-Power OH","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"acecc2fb-4230-5483-bac6-2de70661d51a","notes":"Lists the two 200 MW Socrates gas plants in New Albany as Will-Power projects; its page does not name the customer, but Socrates North is the plant approved to serve the Meta affiliate.","party":"Williams Companies","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"67d9aa6f-0bc0-51be-a5d3-eb574cf5d38d","notes":"20-year nuclear power purchase agreements announced in January 2026 as supporting Prometheus; the plants stay connected to the wider grid.","party":"Vistra","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"67d9aa6f-0bc0-51be-a5d3-eb574cf5d38d","notes":"Agreement to fund new Natrium reactor units, with first delivery as early as 2032; announced alongside the Prometheus deals.","party":"TerraPower","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-prometheus-new-albany"},{"evidence_id":"67d9aa6f-0bc0-51be-a5d3-eb574cf5d38d","notes":"Agreement to help develop a 1.2 GW power campus in Pike County, Ohio, to support Meta's data centers in the region.","party":"Oklo","relationship_scope":"unknown","role":"power_supplier","source_record_id":"meta-prometheus-new-albany"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://blog.synmax.com/vulcan-exclusive/drone-imagery-confirms-metas-prometheus-south-operating-prometheus-north-still-under-construction | https://datacenters.atmeta.com/asset/new-albany-data-center-info-sheet/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Meta New Albany data center campus (Prometheus) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"meta-prometheus-new-albany"},"record":{"aliases":["Prometheus","New Albany Data Center"],"id":"meta-prometheus-new-albany","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","country":"US","lat":40.0812,"locality":"New Albany","lon":-82.8088,"note":"City point from OpenStreetMap Nominatim; the cited sources name New Albany but give no site address for the data center buildings.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Meta's undated fact sheet, read 2026-10-09, describes over 1 GW of compute capacity for the Prometheus cluster; the January 2026 AP report calls it a 1 GW cluster. Neither says whether this is IT or facility load.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1","s2"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-09-16","basis":"planned","metric":"power_capacity","note":"Analyst unit table listing six 80 MW units. IIR Energy, cited for status, lists five of six halls operational; August 2026 imagery showed five halls structurally complete.","phase_label":"Prometheus South","power_scope":"unspecified","qualifier":"exact","source_ids":["s7"],"unit":"MW","value":480},{"applies_to":"phase","as_of":"2026-09-16","basis":"planned","metric":"power_capacity","note":"Analyst unit table listing five 100 MW units. August 2026 drone imagery showed the five shells complete but not energized, although IIR Energy lists them as operational.","phase_label":"Prometheus North","power_scope":"unspecified","qualifier":"exact","source_ids":["s7"],"unit":"MW","value":500},{"applies_to":"phase","as_of":"2025-09-19","basis":"permitted","metric":"power_capacity","note":"Behind-the-meter gas plant approved by the Ohio Power Siting Board for the Meta affiliate Sidecat; Williams lists a matching 200 MW Socrates South plant, for 400 MW combined.","phase_label":"Socrates North gas plant","power_scope":"onsite_generation","qualifier":"exact","source_ids":["s4","s6"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-10-09","basis":"announced","metric":"investment","note":"Meta's cumulative investment figure for the New Albany data center, from its undated fact sheet.","qualifier":"more_than","source_ids":["s1"],"unit":"USD","value":1500000000},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"jobs_construction","note":"Skilled trade workers on site at peak construction, from Meta's undated fact sheet.","qualifier":"exact","source_ids":["s1"],"unit":"count","value":1200},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"jobs_permanent","qualifier":"more_than","source_ids":["s1"],"unit":"count","value":300}],"milestones":[{"date":"2017","event":"construction_started","kind":"actual","note":"Groundbreaking of the original New Albany campus.","source_ids":["s1"]},{"date":"2025-07","event":"expansion_announced","kind":"actual","note":"Meta announced the 1 GW Prometheus cluster spanning multiple buildings.","source_ids":["s2"]},{"date":"2026-06","event":"permit_approved","kind":"actual","note":"In late June the Ohio Power Siting Board approved a further 250 MW behind-the-meter gas plant with 116 MW of batteries (Socrates the Younger) for the Meta affiliate; the report does not name the data center it serves.","source_ids":["s5"]},{"date":"2026-08-31","event":"other","kind":"actual","note":"Drone flight indicated Prometheus South and its gas plant operating; an August 19 flight showed Prometheus North not yet energized.","source_ids":["s7"]},{"date":"2026","event":"other","kind":"planned","note":"Target for the Prometheus cluster to come online, as reported in January 2026.","source_ids":["s2"]}],"name":"Meta New Albany data center campus (Prometheus)","notes":"Meta's fact sheet (s1) is an undated PDF; its embedded file creation date is 2026-09-02. Figures taken only from it carry the date it was read (2026-10-09).","parties":[{"name":"Meta Platforms","role":"developer","source_ids":["s1","s2"]},{"name":"American Electric Power (AEP)","note":"Meta says it planned its energy needs with AEP.","role":"utility","source_ids":["s1"]},{"name":"Will-Power OH","note":"Builds and operates behind-the-meter gas plants in New Albany whose output goes to Sidecat, described as a Meta affiliate.","role":"power_supplier","source_ids":["s4","s5","s6"]},{"name":"Williams Companies","note":"Lists the two 200 MW Socrates gas plants in New Albany as Will-Power projects; its page does not name the customer, but Socrates North is the plant approved to serve the Meta affiliate.","role":"power_supplier","source_ids":["s6"]},{"name":"Vistra","note":"20-year nuclear power purchase agreements announced in January 2026 as supporting Prometheus; the plants stay connected to the wider grid.","role":"power_supplier","source_ids":["s2"]},{"name":"TerraPower","note":"Agreement to fund new Natrium reactor units, with first delivery as early as 2032; announced alongside the Prometheus deals.","role":"power_supplier","source_ids":["s2"]},{"name":"Oklo","note":"Agreement to help develop a 1.2 GW power campus in Pike County, Ohio, to support Meta's data centers in the region.","role":"power_supplier","source_ids":["s2"]}],"power_sources":[{"description":"Meta says it planned the campus's energy needs with AEP and pays the full cost of the energy used.","source_ids":["s1"],"type":"grid"},{"description":"Williams lists two 200 MW Will-Power gas plants in New Albany, Socrates North and South, targeting service in the third and fourth quarters of 2026; Socrates North is approved to run behind the meter for a Meta affiliate, and a further 250 MW plant was approved in June 2026. New Albany's mayor said Meta was building two gas plants on its site. Drone imagery in late August 2026 showed the Prometheus South gas plant running and the Prometheus North plant still under construction.","source_ids":["s3","s4","s5","s6","s7"],"type":"natural_gas_onsite"},{"description":"The 250 MW Socrates the Younger gas plant approved in June 2026 includes 116 MW of battery storage.","source_ids":["s5"],"type":"battery_storage"},{"description":"Nuclear agreements with Vistra (more than 2,600 MW from existing plants and uprates), TerraPower and Oklo were announced in January 2026 in support of Prometheus; the existing plants keep supplying the grid.","source_ids":["s2"],"type":"nuclear"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"Meta Platforms","title":"Meta New Albany Data Center fact sheet","type":"company","url":"https://datacenters.atmeta.com/asset/new-albany-data-center-info-sheet/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260112231829/https://spectrumnews1.com/oh/columbus/news/2026/01/09/meta-lines-up-massive-supply-of-nuclear-power-to-energize-ai-data-centers","id":"s2","published":"2026-01-09","publisher":"Spectrum News 1 (Associated Press)","title":"Meta lines up massive supply of nuclear power to energize AI data centers","type":"news","url":"https://spectrumnews1.com/oh/columbus/news/2026/01/09/meta-lines-up-massive-supply-of-nuclear-power-to-energize-ai-data-centers"},{"accessed":"2026-10-09","id":"s3","published":"2025-11-17","publisher":"Spectrum News 1","title":"Meta's next massive build could become the world's first gigawatt-scale data center","type":"news","url":"https://spectrumnews1.com/oh/columbus/news/2025/11/13/meta-gigawatt-data-center-new-albany-"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20251013031006/https://mountvernonnews.com/stories/675445301-ohio-approves-new-natural-gas-power-plant-for-data-center","id":"s4","published":"2025-09-19","publisher":"Mount Vernon News","title":"Ohio approves new natural gas power plant for data center","type":"news","url":"https://mountvernonnews.com/stories/675445301-ohio-approves-new-natural-gas-power-plant-for-data-center"},{"accessed":"2026-10-09","id":"s5","published":"2026-07-07","publisher":"American Public Power Association","title":"Ohio Power Siting Board Approves Construction of Power Plant to Serve Load of Adjacent Data Center","type":"trade_press","url":"https://www.publicpower.org/node/30607"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Williams Companies","title":"Socrates Power Solution Facilities","type":"company","url":"https://www.williams.com/expansion-project/socrates-power-solution-facilities/"},{"accessed":"2026-10-09","id":"s7","published":"2026-09-16","publisher":"SynMax","title":"Drone Imagery Confirms Meta's Prometheus South Operating, Prometheus North Still Under Construction","type":"analyst","url":"https://blog.synmax.com/vulcan-exclusive/drone-imagery-confirms-metas-prometheus-south-operating-prometheus-north-still-under-construction"}],"status":"partially_operational","status_as_of":"2026-09-16","status_source_ids":["s7"],"summary":"Meta's campus in New Albany, Ohio, where ground was first broken in 2017, is being expanded to host Prometheus, an AI cluster that Meta says delivers more than 1 GW of compute across several buildings. Meta announced Prometheus in July 2025, and it was expected to come online in 2026. Meta planned the campus's energy needs with AEP, behind-the-meter gas plants are being built by Will-Power OH for a Meta affiliate, and Meta signed nuclear power deals in January 2026 tied to the cluster. Drone imagery reported in September 2026 indicated the southern part of the cluster was running while the northern part was not yet energized.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"f777e6f8-5a41-53c1-85a1-8a093d44e70b","s2":"67d9aa6f-0bc0-51be-a5d3-eb574cf5d38d","s3":"af0c2d1b-6a1a-5907-bbd1-8edde88d4101","s4":"076967b9-e7bd-53d2-a04b-851aa51a63de","s5":"097214ae-03ad-505e-9ea1-d45f37b9ccbb","s6":"acecc2fb-4230-5483-bac6-2de70661d51a","s7":"5e95a967-c06e-56c1-b72a-9f09ba8ca132"},"source_file":"datacenters/projects/meta-prometheus-new-albany.json","source_record_id":"meta-prometheus-new-albany","source_record_sha256":"ee389124403f5aa474aca9357c8d9f7c4ca6c72bd75b02efe21419a6421919ee","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"b6f72dafc8710a216c3285bd79b3d24ef810f911becf05924066caf8a62c4716"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-66e95eb80a122bb2ee32/#project-edaa7f7d-5025-5f95-9870-3ad12478339c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/edaa7f7d-5025-5f95-9870-3ad12478339c.json
edf978b4-fbe8-5f8a-9fe0-bd1e9f33e1d2 | curated:microsoft-heath-oh-datacenter:initial-site-preparation | vcc-site-487fd7b91c213d078d2d | curated:microsoft-heath-oh-datacenter | Microsoft Heath Initial Site Preparation | United States | US | 40.0258 | -82.4803 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 2803efb1-75a9-5146-8bbd-483714ab9841 | site_preparation | 2026-07-01 | 104 | authoritative_physical_status_update | 7c13694c-7c87-52e1-a47b-3417bedbc5aa | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://local.microsoft.com/blog/heath-datacenter-construction-updates/ | https://geocoding.geo.census.gov/geocoder/ | [{"identity_decision":{"decision":"multi_site_program","flags":["administrative_locator_not_project_geometry","multiple_sites_no_single_map_point"],"rationale":"Source explicitly describes separate Microsoft campuses in Heath, Hebron and New Albany. Each already has its own release identity and site locator; attach regional context to all three without merging their statuses or capacities. Source statement that no New Albany update was found differs from the release's July 2026 official New Albany observation.","related_project_stable_keys":["curated:microsoft-heath-oh-datacenter:initial-site-preparation","curated:microsoft-hebron-oh-datacenter:initial-site-preparation","curated:microsoft-new-albany-oh-datacenter:initial-site-preparation"],"source_record_id":"microsoft-licking-county-ohio"},"record":{"aliases":["Microsoft Heath datacenter","Microsoft Hebron datacenter","Microsoft New Albany datacenter"],"id":"microsoft-licking-county-ohio","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Licking County","country":"US","lat":40.1318,"lon":-82.4628,"note":"County centroid from Nominatim, because the record covers a three-site program in different municipalities (New Albany, Heath and Hebron). Microsoft's pages place the Heath construction entrance on Thornwood Drive and a temporary Hebron construction entrance on Canyon Road.","precision":"admin2","source_ids":["s1","s2","s6","s7"]},"metrics":[{"applies_to":"campus","as_of":"2024-10-28","basis":"announced","metric":"investment","note":"Initial investment announced for the three campuses together; no per-site split was given, and POWER does not say whether the New Albany USD 420 million is part of it.","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"USD","value":1000000000},{"applies_to":"phase","as_of":"2024-10","basis":"announced","metric":"investment","note":"New Albany's city council approved a 15-year, 100 percent property tax abatement for this building.","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s1","s2"],"unit":"USD","value":420000000},{"applies_to":"phase","as_of":"2025-04-10","basis":"planned","metric":"floor_area","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s2"],"unit":"sq_ft","value":245000},{"applies_to":"phase","as_of":"2025-04-10","basis":"reported","metric":"land_area","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":197}],"milestones":[{"date":"2024-10-28","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-04-07","event":"paused","kind":"actual","note":"Microsoft said it would not move forward at that time, would keep evaluating the sites, would make land at two sites farmable (Heath and Hebron, per ENR), and would still fund road and utility upgrades under its development agreements.","source_ids":["s2","s3","s4"]},{"date":"2026-02-24","event":"construction_started","kind":"actual","note":"Ceremonial groundbreaking at the Heath site off Thornwood Drive; Microsoft's Heath and Hebron pages report mass grading from February 2026 and tree clearing in March 2026.","source_ids":["s5","s6","s7"]},{"date":"2026-11","event":"other","kind":"planned","note":"Target finish of mass grading at Heath and Hebron; Microsoft says early site preparation should be largely done by year-end and has not set a vertical construction timeline.","source_ids":["s6","s7"]}],"name":"Microsoft Licking County three-site datacenter program (New Albany, Heath, Hebron)","notes":"This record groups three sites because the cited sources present them as one program under a single USD 1 billion announcement; split into per-site records if site-level power or investment figures are found. Status reflects site preparation at Heath and Hebron; the New Albany building was on hold as of April 2025 and no later update was found. status_as_of uses the first day of July 2026, the month of the latest entries on Microsoft's month-dated update pages.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2"]},{"name":"Microsoft","note":"ENR and Fox 28 report that Microsoft owns the Licking County sites and will keep the land.","role":"owner","source_ids":["s2","s3"]},{"name":"Ames Construction","note":"Contractor clearing the New Albany site before the 2025 pause (ENR) and main contractor for the Heath and Hebron site work in 2026 (Microsoft).","role":"builder","source_ids":["s2","s6","s7"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-10-28","publisher":"POWER Magazine","title":"Microsoft Announces $1 Billion Investment in Ohio Data Centers as Officials Ponder Power Demands","type":"trade_press","url":"https://www.powermag.com/microsoft-announces-1-billion-investment-in-ohio-data-centers-as-officials-ponder-power-demands"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260516063141/https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio","id":"s2","published":"2025-04-10","publisher":"Engineering News-Record","title":"Microsoft Hits Pause Button on $1B in Data Centers in Ohio","type":"trade_press","url":"https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio"},{"accessed":"2026-10-09","id":"s3","published":"2025-04-08","publisher":"WSYX/WTTE (Fox 28 Columbus)","title":"Microsoft 'not moving forward' with $1B Licking County data center plans right now","type":"news","url":"https://myfox28columbus.com/news/local/microsoft-backs-off-1b-licking-county-data-center-plans"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250410023315/https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/","id":"s4","published":"2025-04-09","publisher":"Associated Press (via News4JAX)","title":"Microsoft says it's 'slowing or pausing' some AI data center projects, including $1B plan for Ohio","type":"news","url":"https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260227140645/https://abc6onyourside.com/news/local/heath-columbus-ohio-break-ground-microsoft-data-center-expected-bring-hundreds-jobs-tech-technology-ai-artificial-intelligence-cloud-computing-digital-services","id":"s5","published":"2026-02-24","publisher":"WSYX ABC 6","title":"Heath breaks ground on Microsoft data center expected to bring hundreds of jobs","type":"news","url":"https://www.abc6onyourside.com/news/local/heath-columbus-ohio-break-ground-microsoft-data-center-expected-bring-hundreds-jobs-tech-technology-ai-artificial-intelligence-cloud-computing-digital-services"},{"accessed":"2026-10-09","id":"s6","published":"2026-07","publisher":"Microsoft Local","title":"Heath datacenter construction updates","type":"company","url":"https://local.microsoft.com/blog/heath-datacenter-construction-updates/"},{"accessed":"2026-10-09","id":"s7","published":"2026-07","publisher":"Microsoft Local","title":"Hebron datacenter construction update","type":"company","url":"https://local.microsoft.com/blog/hebron-datacenter-construction-update/"}],"status":"under_construction","status_as_of":"2026-07-01","status_source_ids":["s5","s6","s7"],"summary":"Three-site Microsoft datacenter program in Licking County, east of Columbus, Ohio, with separate campuses in New Albany, Heath and Hebron. Announced in October 2024 as an initial USD 1 billion investment for Azure cloud capacity, it included a USD 420 million, 245,000 sq ft building on 197 acres in New Albany. In April 2025 Microsoft paused the program, keeping the land and saying two sites would be made farmable. Work resumed in 2026: Heath broke ground in February, and Microsoft's Heath and Hebron pages report tree clearing, mass grading through November 2026 and planned substation work, with no vertical construction timeline. No 2026 update was found for New Albany.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"53a991df-b72c-5ce1-9102-4b2936f3ed84","s2":"3da0d477-2381-54c6-bca3-e3552b21b523","s3":"52512d65-d545-5d59-a6f4-27e8e186eaab","s4":"c9565490-4acd-5d00-97a2-af07b6b2aeae","s5":"c27c9dd5-6622-5355-bd70-7dc3d703241e","s6":"9b8c42cb-65b2-50cc-860d-bd61eed97709","s7":"6591b6d1-867c-59b3-aa1f-ddbe9c167308"},"source_file":"datacenters/projects/microsoft-licking-county-ohio.json","source_record_id":"microsoft-licking-county-ohio","source_record_sha256":"aa63c46124d3685f68abaa56575f892aa7a9a9c91345273642a9a103e42db940","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4efd2bbab8400f3312e0d7e8b453b7bf64695c7208d12e44522b6d32b8cd9cae"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-487fd7b91c213d078d2d/#project-edf978b4-fbe8-5f8a-9fe0-bd1e9f33e1d2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/edf978b4-fbe8-5f8a-9fe0-bd1e9f33e1d2.json
ee6721e5-5463-5350-9b3d-fe2429103a70 | imported:semiconductor-atlas:iozera-tetouan | vcc-site-4b620bcac790d6755738 | imported:semiconductor-atlas:iozera-tetouan | Iozera Tetouan AI data center and hub | Morocco | MA | 35.567 | -5.367 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | City coordinates from the Tétouan Wikipedia article; the opened sources name only the city, not a site within it. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 00756bbb-b1cd-54d5-9350-2a11b661673f | announced | 2026-07-09 | 96 | imported_documented_status | 422abbb5-2c51-55b1-9721-061bc00a27d6 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"00756bbb-b1cd-54d5-9350-2a11b661673f","notes":"The North Africa Post describes it as a US-based technology start-up.","party":"Iozera","relationship_scope":"unknown","role":"developer","source_record_id":"iozera-tetouan"},{"evidence_id":"422abbb5-2c51-55b1-9721-061bc00a27d6","notes":"The North Africa Post describes it as a US-based technology start-up.","party":"Iozera","relationship_scope":"unknown","role":"developer","source_record_id":"iozera-tetouan"},{"evidence_id":"620c4fc4-0519-5e8f-bee6-859aafcd56aa","notes":"The North Africa Post describes it as a US-based technology start-up.","party":"Iozera","relationship_scope":"unknown","role":"developer","source_record_id":"iozera-tetouan"},{"evidence_id":"620c4fc4-0519-5e8f-bee6-859aafcd56aa","notes":"Le360 describes the project as a partnership with the Moroccan state without naming an agency.","party":"Kingdom of Morocco","relationship_scope":"unknown","role":"government","source_record_id":"iozera-tetouan"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://dabafinance.com/en/news/morocco-data-centers-ai-energy-europe | https://northafricapost.com/?p=77106 | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Iozera Tetouan AI data center and hub as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"iozera-tetouan"},"record":{"aliases":[],"id":"iozera-tetouan","last_reviewed":"2026-10-09","location":{"admin1":"Tanger-Tetouan-Al Hoceima","country":"MA","lat":35.567,"locality":"Tetouan","lon":-5.367,"note":"City coordinates from the Tétouan Wikipedia article; the opened sources name only the city, not a site within it.","precision":"locality","source_ids":["s1","s2","s3","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-07-09","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":386},{"applies_to":"campus","as_of":"2024-05-06","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"USD","value":500000000}],"milestones":[{"date":"2024-05","event":"announced","kind":"actual","note":"Announced during a North American roadshow organised by the Moroccan government.","source_ids":["s1","s2"]},{"date":"2026-H2","event":"first_operational","kind":"planned","note":"Commissioning window cited from a BMI (Fitch Solutions) note; no construction progress was reported.","source_ids":["s3"]}],"name":"Iozera Tetouan AI data center and hub","notes":"Daba Finance (January 2026) says Naver's separate 500 MW AI data center plan, unveiled in 2025 with Nvidia, is at the same Tetouan site, whereas Le360 (July 2026) places the Naver Cloud-led 500 MW hub near Casablanca; that project is not covered by this record. Iozera's own website did not mention the Morocco project when checked. Earlier reports of a specific Tetouan site, floor area and an original Q2 2026 opening target come from pages that could not be opened, so they are not recorded.","parties":[{"name":"Iozera","note":"The North Africa Post describes it as a US-based technology start-up.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Kingdom of Morocco","note":"Le360 describes the project as a partnership with the Moroccan state without naming an agency.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"The project is to run on renewable energy; the opened sources do not name the plants or technologies.","source_ids":["s1"],"type":"other"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-05-06","publisher":"The North Africa Post","title":"Artificial Intelligence: U.S. firm Iozera to Invest $500 Mln in Data-center and AI Hub in Morocco","type":"news","url":"https://northafricapost.com/?p=77106"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260501124841/https://dabafinance.com/en/news/morocco-data-centers-ai-energy-europe","id":"s2","published":"2026-01-10","publisher":"Daba Finance","title":"Morocco Attracts Data Center Investments Despite Power, Demand Gaps","type":"news","url":"https://dabafinance.com/en/news/morocco-data-centers-ai-energy-europe"},{"accessed":"2026-10-09","id":"s3","published":"2026-07-09","publisher":"Le360","title":"Data centers au Maroc: une nouvelle vague d'investissements portée par l'IA et la souveraineté numérique","type":"news","url":"https://fr.le360.ma/economie/data-centers-au-maroc-une-nouvelle-vague-dinvestissements-portee-par-lia-et-la-souverainete_5AWWI6OH7FFILPLGYDSUGMU2IA/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Tétouan","type":"other","url":"https://en.wikipedia.org/wiki/Tetouan"}],"status":"announced","status_as_of":"2026-07-09","status_source_ids":["s2","s3"],"summary":"Proposed 386 MW data center and artificial-intelligence hub in Tetouan, northern Morocco, announced in May 2024 by the US start-up Iozera during a Moroccan government roadshow in North America, with a planned investment of about USD 500 million and renewable power. Plans included AI computing, AI training and data-labelling units, conventional data storage and a start-up incubation centre. Reports from January and July 2026 still describe it as announced; a BMI note summarised by Le360 in July 2026 put commissioning in the second half of 2026, but no source found confirms construction.","workloads":["ai_training","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"00756bbb-b1cd-54d5-9350-2a11b661673f","s2":"422abbb5-2c51-55b1-9721-061bc00a27d6","s3":"620c4fc4-0519-5e8f-bee6-859aafcd56aa","s4":"73a0df74-4717-5327-9243-32da3df60a5c"},"source_file":"datacenters/projects/iozera-tetouan.json","source_record_id":"iozera-tetouan","source_record_sha256":"87e6610fa13f99a2575ddb73979b2eef0b94034f528904f24e02bb6e6a3dad23","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d53902702df572eb2238334138cbbf7311864aec2d7e52db268893fe8065768a"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-4b620bcac790d6755738/#project-ee6721e5-5463-5350-9b3d-fe2429103a70 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ee6721e5-5463-5350-9b3d-fe2429103a70.json
eebaf579-8fee-543e-9f06-f7423d642684 | imported:semiconductor-atlas:bridge-my06-sedenak | vcc-site-18b5f6f9e4309fa610af | imported:semiconductor-atlas:bridge-my06-sedenak | Bridge Data Centres MY06, Sedenak Tech Park | Malaysia | MY | 1.7137 | 103.5248 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Sources place the campus in Kidex Sedenak, within the Sedenak Technology Valley (Sedenak Tech Park), without an address; the point is the Sedenak coordinate from its Wikipedia article, so it marks the locality rather than the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 6b6e6695-a936-5100-990b-004dd1051786 | operational | 2026-09-15 | 28 | imported_documented_status | 8c6f8a8d-d739-5d0b-901b-114dc4972f6a | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"6b6e6695-a936-5100-990b-004dd1051786","notes":"Described as a subsidiary of Chindata Group at announcement; later coverage says it is backed by Bain Capital.","party":"Bridge Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-my06-sedenak"},{"evidence_id":"60aca1c5-53ed-5ec0-aef8-b9694a59e152","notes":"Described as a subsidiary of Chindata Group at announcement; later coverage says it is backed by Bain Capital.","party":"Bridge Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-my06-sedenak"},{"evidence_id":"978e36bc-7741-5ae2-84d7-b8da2573d849","notes":"Described as a subsidiary of Chindata Group at announcement; later coverage says it is backed by Bain Capital.","party":"Bridge Data Centres","relationship_scope":"unknown","role":"developer","source_record_id":"bridge-my06-sedenak"},{"evidence_id":"8c6f8a8d-d739-5d0b-901b-114dc4972f6a","notes":null,"party":"Bridge Data Centres","relationship_scope":"unknown","role":"operator","source_record_id":"bridge-my06-sedenak"},{"evidence_id":"a92f4c7b-2d08-5378-b800-708c8fc7192c","notes":null,"party":"Bridge Data Centres","relationship_scope":"unknown","role":"operator","source_record_id":"bridge-my06-sedenak"},{"evidence_id":"60aca1c5-53ed-5ec0-aef8-b9694a59e152","notes":"Named as anchor tenant at the phase 1 opening.","party":"ByteDance System Sdn. Bhd.","relationship_scope":"unknown","role":"tenant","source_record_id":"bridge-my06-sedenak"},{"evidence_id":"60aca1c5-53ed-5ec0-aef8-b9694a59e152","notes":"Backer of Bridge's Southeast Asian hyperscale expansion.","party":"Bain Capital","relationship_scope":"unknown","role":"investor","source_record_id":"bridge-my06-sedenak"},{"evidence_id":"60aca1c5-53ed-5ec0-aef8-b9694a59e152","notes":"Listed among the agencies and utilities supporting the opening.","party":"Tenaga Nasional Berhad","relationship_scope":"unknown","role":"utility","source_record_id":"bridge-my06-sedenak"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. |  | Bridge Data Centres |  | ByteDance System Sdn. Bhd. |  | https://www.bridgedatacentres.com/powering-malaysias-digital-future/ | https://www.mida.gov.my/media-release/bridge-data-centres-announces-construction-of-its-fourth-hyperscale-data-centre-campus-in-johor-malaysia/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Bridge Data Centres MY06, Sedenak Tech Park as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"bridge-my06-sedenak","source_relations":[{"reason":"Bridge MY06 and Vantage JHB1 are separately named campuses in Sedenak Tech Park; identical park/locality coordinates are not evidence of co-location.","relationship":"separate_named_developments","source_id":"vantage-jhb1-sedenak"}]},"record":{"aliases":["BDC MY06","Kidex Sedenak MY06"],"id":"bridge-my06-sedenak","last_reviewed":"2026-10-09","location":{"admin1":"Johor","admin2":"Kulai District","country":"MY","lat":1.7137,"locality":"Sedenak (Sedenak Tech Park)","lon":103.5248,"note":"Sources place the campus in Kidex Sedenak, within the Sedenak Technology Valley (Sedenak Tech Park), without an address; the point is the Sedenak coordinate from its Wikipedia article, so it marks the locality rather than the parcel.","precision":"locality","source_ids":["s1","s2","s3","s6","s7"]},"metrics":[{"applies_to":"campus","as_of":"2021-12-02","basis":"planned","metric":"power_capacity","note":"Original plan for three buildings; the 2022 opening coverage gave 110 MW for the same three-building project.","power_scope":"it_load","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":100},{"applies_to":"campus","as_of":"2022-11-21","basis":"planned","metric":"power_capacity","note":"W.Media gives 110 MW of IT power; The Iskandarian gives 110 MW without a scope.","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":110},{"applies_to":"phase","as_of":"2022-11-21","basis":"operational","metric":"power_capacity","phase_label":"Phase 1 (first building)","power_scope":"unspecified","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":20},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total IT capacity listed for MY06 on Bridge's undated Malaysia locations page; the page does not say how much of it is built.","power_scope":"it_load","qualifier":"exact","source_ids":["s4"],"unit":"MW","value":508},{"applies_to":"campus","as_of":"2021-12-02","basis":"announced","metric":"investment","note":"Estimated investment over five years for the original 100 MW plan.","qualifier":"approximately","source_ids":["s1"],"unit":"MYR","value":2500000000},{"applies_to":"campus","as_of":"2021-12-02","basis":"planned","metric":"buildings","note":"Original plan.","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":3},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"buildings","note":"Campus building count listed on Bridge's locations page; construction status of each building is not given.","qualifier":"exact","source_ids":["s4"],"unit":"count","value":15},{"applies_to":"campus","as_of":"2021-12-02","basis":"reported","metric":"land_area","note":"The Iskandarian gave 38 acres at the 2022 opening.","qualifier":"approximately","source_ids":["s1"],"unit":"acres","value":40}],"milestones":[{"date":"2021-12-02","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2021-11","event":"construction_started","kind":"actual","note":"The Iskandarian dates the groundbreaking to November 2021, with phase 1 finished about 314 days later.","source_ids":["s2"]},{"date":"2022-11","event":"first_operational","kind":"actual","note":"Grand opening of the first building, handed over to the anchor tenant.","source_ids":["s2","s3"]}],"name":"Bridge Data Centres MY06, Sedenak Tech Park","notes":"Status rests on a September 2026 Bridge staff profile describing the Sedenak campus as fully operating; it does not say whether all 15 buildings and 508 MW now listed for MY06 are complete, so the larger figure is recorded as planned. Wikipedia is cited only for the locality coordinate.","parties":[{"name":"Bridge Data Centres","note":"Described as a subsidiary of Chindata Group at announcement; later coverage says it is backed by Bain Capital.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Bridge Data Centres","role":"operator","source_ids":["s5","s6"]},{"name":"ByteDance System Sdn. Bhd.","note":"Named as anchor tenant at the phase 1 opening.","role":"tenant","source_ids":["s2"]},{"name":"Bain Capital","note":"Backer of Bridge's Southeast Asian hyperscale expansion.","role":"investor","source_ids":["s2"]},{"name":"Tenaga Nasional Berhad","note":"Listed among the agencies and utilities supporting the opening.","role":"utility","source_ids":["s2"]}],"power_sources":[{"description":"Bridge lists a 275 kV power intake for MY06; Tenaga Nasional Berhad was among the supporting parties at the opening.","source_ids":["s2","s4"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2021-12-02","publisher":"Malaysian Investment Development Authority (MIDA)","title":"Bridge Data Centres announces construction of its fourth hyperscale data centre campus in Johor, Malaysia","type":"government","url":"https://www.mida.gov.my/media-release/bridge-data-centres-announces-construction-of-its-fourth-hyperscale-data-centre-campus-in-johor-malaysia/"},{"accessed":"2026-10-09","id":"s2","published":"2022-11-09","publisher":"The Iskandarian","title":"The First Phase Hyperscale Data Centre in Johor Malaysia Commenced","type":"news","url":"https://theiskandarian.com/?p=21738"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20221206184338/https://w.media/how-bridges-my06-is-rewriting-the-rules-of-data-centre-construction/","id":"s3","published":"2022-11-21","publisher":"W.Media","title":"How Bridge's MY06 is Rewriting the Rules of Data Centre Construction","type":"trade_press","url":"https://w.media/how-bridges-my06-is-rewriting-the-rules-of-data-centre-construction/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260609083542/https://www.bridgedatacentres.com/locations/malaysia/","id":"s4","published":null,"publisher":"Bridge Data Centres","title":"Malaysia locations","type":"company","url":"https://www.bridgedatacentres.com/locations/malaysia/"},{"accessed":"2026-10-09","id":"s5","published":"2026-09-15","publisher":"Bridge Data Centres","title":"Powering Malaysia's Digital Future","type":"company","url":"https://www.bridgedatacentres.com/powering-malaysias-digital-future/"},{"accessed":"2026-10-09","id":"s6","published":"2026-09-02","publisher":"Bridge Data Centres","title":"Building Malaysia's Digital Future","type":"company","url":"https://www.bridgedatacentres.com/building-malaysias-digital-future/"},{"accessed":"2026-10-09","id":"s7","published":null,"publisher":"Wikipedia","title":"Sedenak","type":"other","url":"https://en.wikipedia.org/wiki/Sedenak"}],"status":"operational","status_as_of":"2026-09-15","status_source_ids":["s5"],"summary":"Bridge Data Centres' MY06 hyperscale campus sits in Kidex Sedenak, part of the Sedenak Tech Park in Kulai District, Johor. Announced in December 2021 as a three-building, 100 MW IT campus on about 40 acres with RM2.5 billion of investment over five years, its first 20 MW building was built with prefabricated modules and opened in November 2022, with ByteDance as anchor tenant. Bridge now lists MY06 at 508 MW of IT capacity across 15 buildings, and in September 2026 described the Sedenak campus as a fully operating hyperscale site.","workloads":["colocation","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"6b6e6695-a936-5100-990b-004dd1051786","s2":"60aca1c5-53ed-5ec0-aef8-b9694a59e152","s3":"978e36bc-7741-5ae2-84d7-b8da2573d849","s4":"61550644-fd6d-5d7c-ba3d-ef317565450b","s5":"8c6f8a8d-d739-5d0b-901b-114dc4972f6a","s6":"a92f4c7b-2d08-5378-b800-708c8fc7192c","s7":"d1bfa237-28ba-5248-9685-e1606fd14f92"},"source_file":"datacenters/projects/bridge-my06-sedenak.json","source_record_id":"bridge-my06-sedenak","source_record_sha256":"9656a81ec781528eef472cf50a28b843344bc3a20a649714fc9247ded59809e7","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"78f13f500d6cc2dafa6bf621af9ae35dbef461ac3bd436f22bfffaec0546fca5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-18b5f6f9e4309fa610af/#project-eebaf579-8fee-543e-9f06-f7423d642684 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/eebaf579-8fee-543e-9f06-f7423d642684.json
f054a923-1869-5cee-aec7-f9673b431f14 | curated:digital-realty-digital-dulles-campus:current-96mw-development | vcc-site-20a2edd7bbbbe47d7c25 | curated:digital-realty-digital-dulles-campus | Digital Realty Digital Dulles Current 96 MW Development | United States | US | 38.961 | -77.4915 | Point | campus | first_party_published_map_pin | operator_decimal_coordinate_attributes_to_point_without_centroiding | official_operator_published_constituent_campus_reference_point | official_source | campus_locator | Operator IAD44/B7 reference point within the county-identified Digital Dulles campus. It is not asserted to locate the unnamed 96 MW active development or Dulles 9 building; no building footprint or accuracy is inferred. |  | No source provides a numeric horizontal-accuracy guarantee or a surveyed campus reference feature. | e9598e01-b9ef-5d87-a239-9d028a3e30c9 | under_construction | 2026-06-29 | 106 | authoritative_physical_status_update | c5e995b6-5ba7-520b-8298-f99f10da5e31 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.digitalrealty.com/about/newsroom/press-releases/30426/digital-realty-announces-purchase-of-blackstone-interest-in-three-northern-virginia-data-centers | https://www.digitalrealty.com/data-centers/americas/northern-virginia/iad44 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-20a2edd7bbbbe47d7c25/#project-f054a923-1869-5cee-aec7-f9673b431f14 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f054a923-1869-5cee-aec7-f9673b431f14.json
f0697b74-aa81-5aca-ab5b-95a2591d7b2c | imported:semiconductor-atlas:brookfield-cambrai | vcc-site-14a570a5f1dfb8b45e8d | imported:semiconductor-atlas:brookfield-cambrai | Data4 Cambrai E-Valley campus | France | FR | 50.22 | 3.1765 | Point | project | imported_reference_point | imported_reference_point | approximate_site | compiled_reference | approximate_site_locator | Nominatim position of the E-Valley information board on Avenue de France, Épinoy, inside the former BA 103 base; sources identify the base and E-Valley but not the data center parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 65504e98-2e99-5c57-9dfd-9b25a7cb6e8e | announced | 2026-06-11 | 124 | imported_documented_status | ec04f464-c888-5e65-bef1-18866a4b0db1 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ec04f464-c888-5e65-bef1-18866a4b0db1","notes":"Named as the project developer (a Brookfield subsidiary) in local news on the prefect-led steering committee; no Data4 release on Cambrai could be opened.","party":"Data4","relationship_scope":"unknown","role":"developer","source_record_id":"brookfield-cambrai"},{"evidence_id":"9f275d73-26cf-5833-8d2f-0185eb616ae4","notes":"Parent of Data4; early reporting (La Tribune Dimanche via TechCrunch) tied part of Brookfield's France pledge to Cambrai.","party":"Brookfield","relationship_scope":"unknown","role":"investor","source_record_id":"brookfield-cambrai"},{"evidence_id":"ec04f464-c888-5e65-bef1-18866a4b0db1","notes":"Parent of Data4; early reporting (La Tribune Dimanche via TechCrunch) tied part of Brookfield's France pledge to Cambrai.","party":"Brookfield","relationship_scope":"unknown","role":"investor","source_record_id":"brookfield-cambrai"},{"evidence_id":"65504e98-2e99-5c57-9dfd-9b25a7cb6e8e","notes":"Distribution operator tendering the medium-voltage connection works for the E-Valley data center site.","party":"Enedis","relationship_scope":"unknown","role":"utility","source_record_id":"brookfield-cambrai"},{"evidence_id":"ec04f464-c888-5e65-bef1-18866a4b0db1","notes":"The prefecture runs the project steering committee: the then sub-prefect chaired the first meeting on 2026-02-03 and the Nord prefect the second on 2026-06-09.","party":"Préfecture du Nord","relationship_scope":"unknown","role":"government","source_record_id":"brookfield-cambrai"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://info.fr/nord-comite-pilotage-data-centers-e-valley-cambrai/ | https://www.marchesonline.com/appels-offres/avis/travaux-d-extension-electrique-hta-pour-le-raccordement/ao-9588877-1 | [{"identity_decision":{"decision":"unique_site","flags":["approximate_locator_not_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Data4 Cambrai E-Valley campus as an independent source record; its approximate_site locator does not itself establish a surveyed physical site.","source_record_id":"brookfield-cambrai"},"record":{"aliases":["E-Valley data center campus","Brookfield Cambrai data center"],"id":"brookfield-cambrai","last_reviewed":"2026-10-09","location":{"admin1":"Hauts-de-France","country":"FR","lat":50.22,"locality":"Épinoy (E-Valley, former Cambrai air base)","lon":3.1765,"note":"Nominatim position of the E-Valley information board on Avenue de France, Épinoy, inside the former BA 103 base; sources identify the base and E-Valley but not the data center parcel.","precision":"approximate_site","source_ids":["s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-11","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"up_to","source_ids":["s1","s3"],"unit":"MW","value":1000},{"applies_to":"phase","as_of":"2026-06-11","basis":"planned","metric":"power_capacity","phase_label":"First tranche","power_scope":"unspecified","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":300},{"applies_to":"campus","as_of":"2025-02-09","basis":"reported","metric":"investment","note":"Media report (La Tribune Dimanche, relayed by TechCrunch); not stated in Brookfield's own release.","qualifier":"approximately","source_ids":["s1"],"unit":"EUR","value":15000000000}],"milestones":[{"date":"2025-02-09","event":"announced","kind":"actual","note":"TechCrunch, relaying La Tribune Dimanche, reported that about EUR 15 billion of Brookfield's EUR 20 billion French pledge would go to a Cambrai data center.","source_ids":["s1"]},{"date":"2026-04-14","event":"other","kind":"actual","note":"Enedis tender for about 29 km of underground HTA cabling to four customer substations, with works scheduled for 2027.","source_ids":["s2"]},{"date":"2026-H2","event":"construction_started","kind":"planned","source_ids":["s3"]},{"date":"2027","event":"first_operational","kind":"planned","note":"First deliveries expected 2027-2028.","source_ids":["s3"]}],"name":"Data4 Cambrai E-Valley campus","notes":"Neither Brookfield nor Data4 published a site-specific release for Cambrai that could be opened; details rest on news reports and the Enedis tender. The info.fr report is labelled as written by an AI editorial agent. It says a significant part of a further EUR 10 billion Brookfield pledge for France is meant for E-Valley; that sum is not a campus figure and is not recorded as a metric. Local officials cite about 4,000 direct and indirect jobs. The 320 hectares often quoted refer to the whole E-Valley site, not the data center plot.","parties":[{"name":"Data4","note":"Named as the project developer (a Brookfield subsidiary) in local news on the prefect-led steering committee; no Data4 release on Cambrai could be opened.","role":"developer","source_ids":["s3"]},{"name":"Brookfield","note":"Parent of Data4; early reporting (La Tribune Dimanche via TechCrunch) tied part of Brookfield's France pledge to Cambrai.","role":"investor","source_ids":["s1","s3"]},{"name":"Enedis","note":"Distribution operator tendering the medium-voltage connection works for the E-Valley data center site.","role":"utility","source_ids":["s2"]},{"name":"Préfecture du Nord","note":"The prefecture runs the project steering committee: the then sub-prefect chaired the first meeting on 2026-02-03 and the Nord prefect the second on 2026-06-09.","role":"government","source_ids":["s3"]}],"power_sources":[{"description":"Medium-voltage feeds from the Haplincourt and Prémy source substations via about 29 km of new underground cable to four customer substations.","source_ids":["s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-02-09","publisher":"TechCrunch","title":"Investments in French AI ecosystem reach $85B as Brookfield commits $20B","type":"news","url":"https://techcrunch.com/2025/02/09/investments-in-french-ai-ecosystem-reach-85b-as-brookfield-commits-20b"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-16","publisher":"Enedis (via Marchés Online)","title":"Travaux d'extension électrique HTA pour le raccordement du site Data Center EVALLEY","type":"utility","url":"https://www.marchesonline.com/appels-offres/avis/travaux-d-extension-electrique-hta-pour-le-raccordement/ao-9588877-1"},{"accessed":"2026-10-09","id":"s3","published":"2026-06-11","publisher":"info.fr","title":"Nord : le comité de pilotage des data centers d'E-Valley réuni mardi sous l'égide du préfet","type":"news","url":"https://info.fr/nord-comite-pilotage-data-centers-e-valley-cambrai/"}],"status":"announced","status_as_of":"2026-06-11","status_source_ids":["s3"],"summary":"Data4, the data center unit of Brookfield, is planning a campus of up to 1 GW at E-Valley on the former Cambrai military air base (BA 103) in northern France. Brookfield's February 2025 France pledge was reported to direct about EUR 15 billion to a Cambrai data center. A June 2026 local report cites a first 300 MW tranche, works from the second half of 2026 and first deliveries in 2027-2028. Enedis tendered about 29 km of medium-voltage cabling in April 2026 to feed four customer substations at the site, with the works set for 2027.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"9f275d73-26cf-5833-8d2f-0185eb616ae4","s2":"65504e98-2e99-5c57-9dfd-9b25a7cb6e8e","s3":"ec04f464-c888-5e65-bef1-18866a4b0db1"},"source_file":"datacenters/projects/brookfield-cambrai.json","source_record_id":"brookfield-cambrai","source_record_sha256":"2891f5a66bae56bd7dc5094bb823fef9c967375463700de3fac489238ce67c84","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"d9e4fe305b4ad667bb9ea27e210e6e6172e41a537eca390f04600fd26b3a208d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-14a570a5f1dfb8b45e8d/#project-f0697b74-aa81-5aca-ab5b-95a2591d7b2c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f0697b74-aa81-5aca-ab5b-95a2591d7b2c.json
f07274ee-deff-5651-b606-da909d7328af | imported:semiconductor-atlas:acs-la-puebla-de-alfinden | vcc-site-5b95b2458a9a5add9fad | imported:semiconductor-atlas:acs-la-puebla-de-alfinden | ACS DC La Puebla data center campus | Spain | ES | 41.634 | -0.748 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Town centroid from the La Puebla de Alfindén Wikipedia article. The regional plan describes the plot but no cited source gives coordinates for it. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 183ff3fc-f33e-5695-a1cd-dd7f80c0d4e3 | announced | 2026-10-05 | 8 | imported_documented_status | 49cd1acb-9749-5fee-9b09-d5fef1ac3c43 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"2749b90c-3a3e-52ea-9636-2dea8c1c4d30","notes":"The regional plan is promoted by the project company ACS DC Infra La Puebla, S.L.","party":"ACS","relationship_scope":"unknown","role":"developer","source_record_id":"acs-la-puebla-de-alfinden"},{"evidence_id":"49cd1acb-9749-5fee-9b09-d5fef1ac3c43","notes":"The regional plan is promoted by the project company ACS DC Infra La Puebla, S.L.","party":"ACS","relationship_scope":"unknown","role":"developer","source_record_id":"acs-la-puebla-de-alfinden"},{"evidence_id":"183ff3fc-f33e-5695-a1cd-dd7f80c0d4e3","notes":"The regional plan is promoted by the project company ACS DC Infra La Puebla, S.L.","party":"ACS","relationship_scope":"unknown","role":"developer","source_record_id":"acs-la-puebla-de-alfinden"},{"evidence_id":"2749b90c-3a3e-52ea-9636-2dea8c1c4d30","notes":"Announced as ACS's partner in the project; its specific role is not described.","party":"Benbros Energy","relationship_scope":"unknown","role":"developer","source_record_id":"acs-la-puebla-de-alfinden"},{"evidence_id":"2749b90c-3a3e-52ea-9636-2dea8c1c4d30","notes":"Guaranteed the 150 MW first-phase connection at the Peñaflor substation; a second 150 MW request is pending.","party":"Red Eléctrica","relationship_scope":"unknown","role":"utility","source_record_id":"acs-la-puebla-de-alfinden"},{"evidence_id":"183ff3fc-f33e-5695-a1cd-dd7f80c0d4e3","notes":"Declared the project of general interest and gave the regional plan initial approval.","party":"Government of Aragon","relationship_scope":"unknown","role":"government","source_record_id":"acs-la-puebla-de-alfinden"},{"evidence_id":"d59b3f76-2fb8-517b-9f06-7547210fea1e","notes":"Declared the project of general interest and gave the regional plan initial approval.","party":"Government of Aragon","relationship_scope":"unknown","role":"government","source_record_id":"acs-la-puebla-de-alfinden"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html | https://www.aragon.es/-/piga-acs-dc-la-puebla | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve ACS DC La Puebla data center campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"acs-la-puebla-de-alfinden"},"record":{"aliases":["ACS DC LA PUEBLA","ACS and Benbros Energy data center, La Puebla de Alfindén"],"id":"acs-la-puebla-de-alfinden","last_reviewed":"2026-10-09","location":{"admin1":"Aragon","admin2":"Zaragoza","country":"ES","lat":41.634,"locality":"La Puebla de Alfindén","lon":-0.748,"note":"Town centroid from the La Puebla de Alfindén Wikipedia article. The regional plan describes the plot but no cited source gives coordinates for it.","precision":"locality","source_ids":["s1","s3","s6"]},"metrics":[{"applies_to":"phase","as_of":"2025-06-27","basis":"planned","metric":"power_capacity","note":"Electrical power secured at the Peñaflor access point; the regional plan describes the project as 150 MW of electrical power.","phase_label":"Phase 1","power_scope":"grid_connection","qualifier":"exact","source_ids":["s3","s1"],"unit":"MW","value":150},{"applies_to":"phase","as_of":"2026-07-06","basis":"planned","metric":"power_capacity","phase_label":"Building 1 (four 10 MW modules)","power_scope":"it_load","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":40},{"applies_to":"phase","as_of":"2026-07-06","basis":"planned","metric":"power_capacity","phase_label":"Building 2 (six 10 MW modules)","power_scope":"it_load","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":60},{"applies_to":"phase","as_of":"2025-06-27","basis":"planned","metric":"power_capacity","note":"Additional capacity the developers had requested; the plot reserves space for a possible second phase.","phase_label":"Phase 2 (pending Red Eléctrica approval)","power_scope":"grid_connection","qualifier":"exact","source_ids":["s3"],"unit":"MW","value":150},{"applies_to":"phase","as_of":"2025-06-27","basis":"announced","metric":"investment","note":"Announced by Aragon's regional president; El Español describes it as committed for the first phase.","phase_label":"Phase 1","qualifier":"exact","source_ids":["s3","s4"],"unit":"EUR","value":1254000000},{"applies_to":"campus","as_of":"2026-07-06","basis":"planned","metric":"land_area","note":"The regional plan covers 255,504.65 square metres of industrial development land.","qualifier":"approximately","source_ids":["s1","s5"],"unit":"hectares","value":25.55},{"applies_to":"phase","as_of":"2026-07-06","basis":"planned","metric":"buildings","phase_label":"Phase 1","qualifier":"exact","source_ids":["s1","s5"],"unit":"count","value":2},{"applies_to":"campus","as_of":"2025-06-27","basis":"planned","metric":"jobs_construction","qualifier":"exact","source_ids":["s3"],"unit":"count","value":1510},{"applies_to":"campus","as_of":"2025-06-27","basis":"planned","metric":"jobs_permanent","note":"Operating jobs; a further 724 induced jobs were also projected.","qualifier":"exact","source_ids":["s3"],"unit":"count","value":540}],"milestones":[{"date":"2025-06-27","event":"announced","kind":"actual","source_ids":["s3"]},{"date":"2025-06-27","event":"other","kind":"actual","note":"Declared an investment of general interest for Aragon; published in the regional gazette on 23 July 2025.","source_ids":["s1","s2"]},{"date":"2025-09-17","event":"other","kind":"actual","note":"Regional plan filed for initial approval.","source_ids":["s1"]},{"date":"2025-12-01","event":"other","kind":"actual","note":"Initial approval of the Plan de Interés General de Aragón (Order FOM/1698/2025), followed by a 30-working-day public information period opened on 9 December 2025.","source_ids":["s1","s2","s4"]},{"date":"2026-07-31","event":"other","kind":"actual","note":"Order VFL/1184/2026 amended the initial approval to add updated 400 kV and 220 kV line and remote substation projects with their environmental studies.","source_ids":["s2"]},{"date":"2027","event":"construction_started","kind":"planned","note":"In March 2026 urbanisation was expected in 2026 and the buildings from early 2027; in October 2026 urbanisation was expected by late 2026 or during 2027.","source_ids":["s4","s5"]}],"name":"ACS DC La Puebla data center campus","notes":"The regional plan pages carry last-updated dates (6 July 2026 and 2 September 2026), used here as their published dates. The two data hall IT figures are recorded per building and not summed. No final approval of the regional plan had been reported by early October 2026.","parties":[{"name":"ACS","note":"The regional plan is promoted by the project company ACS DC Infra La Puebla, S.L.","role":"developer","source_ids":["s3","s4","s1"]},{"name":"Benbros Energy","note":"Announced as ACS's partner in the project; its specific role is not described.","role":"developer","source_ids":["s3"]},{"name":"Red Eléctrica","note":"Guaranteed the 150 MW first-phase connection at the Peñaflor substation; a second 150 MW request is pending.","role":"utility","source_ids":["s3"]},{"name":"Government of Aragon","note":"Declared the project of general interest and gave the regional plan initial approval.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"About 13.5 km of underground line from Red Eléctrica's Peñaflor substation, a new remote 400/220 kV substation next to it, and a substation on the campus plot.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-07-06","publisher":"Gobierno de Aragón","title":"Plan de Interés General de Aragón: Instalación de un centro de datos en el término municipal de La Puebla de Alfindén","type":"government","url":"https://www.aragon.es/-/piga-acs-dc-la-puebla"},{"accessed":"2026-10-09","id":"s2","published":"2026-09-02","publisher":"Gobierno de Aragón","title":"Modificación de la aprobación inicial del PIGA del centro de datos de La Puebla de Alfindén","type":"government","url":"https://www.aragon.es/-/piga-acs-modificacion%201"},{"accessed":"2026-10-09","id":"s3","published":"2025-06-27","publisher":"Hoy Aragón","title":"ACS aterriza con Benbros Energy en Aragón para la construcción de otro centro de datos","type":"news","url":"https://www.hoyaragon.es/articulo/noticias-aragon/acs/20250627135338101330.html"},{"accessed":"2026-10-09","id":"s4","published":"2026-10-05","publisher":"El Español","title":"Cerca de 6.000 millones invertidos en centros de datos en Aragón esperan en la rampa de salida para las obras","type":"news","url":"https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260527095310/https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html","id":"s5","published":"2026-03-22","publisher":"El Español","title":"Aragón se convierte en la capital de los datos y la nube: el calendario de Amazon, Microsoft y todos los proyectos","type":"news","url":"https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20261003063033/https://en.wikipedia.org/wiki/La_Puebla_de_Alfind%C3%A9n","id":"s6","published":null,"publisher":"Wikipedia","title":"La Puebla de Alfindén","type":"other","url":"https://en.wikipedia.org/wiki/La_Puebla_de_Alfind%C3%A9n"}],"status":"announced","status_as_of":"2026-10-05","status_source_ids":["s4","s2"],"summary":"Data center campus planned by ACS with Benbros Energy on about 25.5 hectares of industrial land in La Puebla de Alfindén, Zaragoza province. Announced in June 2025 with EUR 1,254 million for the first phase and 150 MW of grid access at Red Eléctrica's Peñaflor substation; a second phase depends on a further 150 MW the developers have requested. The regional plan describes two data halls of 40 MW and 60 MW of IT load, a new 400/220 kV substation next to Peñaflor and an underground line to the site. The plan won initial approval in December 2025 and was amended in July 2026 to add the power line projects. Urbanisation works were expected from late 2026 or in 2027.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"183ff3fc-f33e-5695-a1cd-dd7f80c0d4e3","s2":"d59b3f76-2fb8-517b-9f06-7547210fea1e","s3":"2749b90c-3a3e-52ea-9636-2dea8c1c4d30","s4":"49cd1acb-9749-5fee-9b09-d5fef1ac3c43","s5":"276bfe3b-499d-5a05-b991-0b57b2cbd91e","s6":"d3a91abc-e752-590c-9c2e-db0922bb10c3"},"source_file":"datacenters/projects/acs-la-puebla-de-alfinden.json","source_record_id":"acs-la-puebla-de-alfinden","source_record_sha256":"4d67e1c342e70c1aab029abca8abac09d6bcba48ba47c042a557ab594cad4c6b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"69e8908bd90e2f014e7389846f8d9d7ba1b72c66e97d81c599cdd97fc5ec0265"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5b95b2458a9a5add9fad/#project-f07274ee-deff-5651-b606-da909d7328af | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f07274ee-deff-5651-b606-da909d7328af.json
f0afff75-0b96-5e18-a8f9-08ac9a4b99ff | imported:semiconductor-atlas:data4-escaudain | vcc-site-3b5d1fe13cf00d04d3f2 | imported:semiconductor-atlas:data4-escaudain | Data4 Escaudain campus | France | FR | 50.3333 | 3.3438 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Nominatim centroid of the commune of Escaudain; the site is the Parc des Soufflantes (former Usinor plant), which could not be geocoded more precisely. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | ac81d24f-1213-55b4-8895-b11b038fa18b | announced | 2026-06-15 | 120 | imported_documented_status | 9715a716-15a7-5f21-ba6a-67aaf679853b | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"ac81d24f-1213-55b4-8895-b11b038fa18b","notes":null,"party":"Data4","relationship_scope":"unknown","role":"developer","source_record_id":"data4-escaudain"},{"evidence_id":"9715a716-15a7-5f21-ba6a-67aaf679853b","notes":null,"party":"Data4","relationship_scope":"unknown","role":"developer","source_record_id":"data4-escaudain"},{"evidence_id":"26ab81d6-a6c2-5f14-983f-4a68a221c851","notes":"Owner of Data4 since April 2023.","party":"Brookfield","relationship_scope":"unknown","role":"investor","source_record_id":"data4-escaudain"},{"evidence_id":"ac81d24f-1213-55b4-8895-b11b038fa18b","notes":"Local authority that selected Data4 as exclusive partner to redevelop the former Usinor site.","party":"Communauté d'Agglomération de La Porte du Hainaut","relationship_scope":"unknown","role":"government","source_record_id":"data4-escaudain"},{"evidence_id":"9715a716-15a7-5f21-ba6a-67aaf679853b","notes":"Local authority that selected Data4 as exclusive partner to redevelop the former Usinor site.","party":"Communauté d'Agglomération de La Porte du Hainaut","relationship_scope":"unknown","role":"government","source_record_id":"data4-escaudain"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.data4group.com/wp-content/uploads/2026/06/Press-release_Data4-launches-a-new-campus-in-France.pdf | https://www.data4group.com/wp-content/uploads/2025/12/CP-FINAL-Data4-Agglomeration-de-La-Porte-du-Hainaut.pdf | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Data4 Escaudain campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"data4-escaudain"},"record":{"aliases":["Parc des Soufflantes data center campus"],"id":"data4-escaudain","last_reviewed":"2026-10-09","location":{"admin1":"Hauts-de-France","admin2":"Nord","country":"FR","lat":50.3333,"locality":"Escaudain","lon":3.3438,"note":"Nominatim centroid of the commune of Escaudain; the site is the Parc des Soufflantes (former Usinor plant), which could not be geocoded more precisely.","precision":"locality","source_ids":["s1","s2"]},"metrics":[{"applies_to":"campus","as_of":"2026-06-12","basis":"planned","metric":"power_capacity","power_scope":"unspecified","qualifier":"exact","source_ids":["s2","s3"],"unit":"MW","value":700},{"applies_to":"campus","as_of":"2026-06-12","basis":"announced","metric":"investment","qualifier":"exact","source_ids":["s2","s3"],"unit":"EUR","value":5000000000},{"applies_to":"campus","as_of":"2026-06-12","basis":"planned","metric":"land_area","note":"The December 2025 selection release described a 38-hectare campus project.","qualifier":"exact","source_ids":["s2"],"unit":"hectares","value":33},{"applies_to":"campus","as_of":"2025-12-15","basis":"planned","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":38},{"applies_to":"campus","as_of":"2026-06-12","basis":"planned","metric":"buildings","note":"Data4 says four data centers will be built to expand the campus; trade press (DCD via BeBeez) described an initial building that could be followed by up to four more.","qualifier":"exact","source_ids":["s2","s3"],"unit":"count","value":4},{"applies_to":"campus","as_of":"2026-06-12","basis":"planned","metric":"jobs_permanent","qualifier":"exact","source_ids":["s2"],"unit":"count","value":2400}],"milestones":[{"date":"2025-12-15","event":"announced","kind":"actual","note":"La Porte du Hainaut selected Data4 and opened a 60-day exclusive negotiation and feasibility phase.","source_ids":["s1"]},{"date":"2026-06-12","event":"other","kind":"actual","note":"Data4 confirmed the EUR 5 billion project after feasibility studies; further studies and preliminary works planned over the next 12 months.","source_ids":["s2","s3"]}],"name":"Data4 Escaudain campus","notes":"No construction start, permit or first-operation date had been published by the companies as of the latest source. Data4 said decontamination of the former Usinor plant would follow once project conditions were met.","parties":[{"name":"Data4","role":"developer","source_ids":["s1","s2"]},{"name":"Brookfield","note":"Owner of Data4 since April 2023.","role":"investor","source_ids":["s3"]},{"name":"Communauté d'Agglomération de La Porte du Hainaut","note":"Local authority that selected Data4 as exclusive partner to redevelop the former Usinor site.","role":"government","source_ids":["s1","s2"]}],"power_sources":[{"description":"Site benefited from the French government and RTE fast-track procedure for ready-to-connect data center sites.","source_ids":["s2","s3"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-12-15","publisher":"Data4","title":"Escaudain : Data4 sélectionné pour le projet de campus numérique de La Porte du Hainaut","type":"company","url":"https://www.data4group.com/wp-content/uploads/2025/12/CP-FINAL-Data4-Agglomeration-de-La-Porte-du-Hainaut.pdf"},{"accessed":"2026-10-09","id":"s2","published":"2026-06-12","publisher":"Data4","title":"Data4 confirms its largest data center project in the North of France","type":"company","url":"https://www.data4group.com/wp-content/uploads/2026/06/Press-release_Data4-launches-a-new-campus-in-France.pdf"},{"accessed":"2026-10-09","id":"s3","published":"2026-06-15","publisher":"BeBeez International (DCD)","title":"Data4 confirms €5bn plan for 700MW AI data center in northern France","type":"trade_press","url":"https://bebeez.eu/2026/06/15/data4-confirms-e5bn-plan-for-700mw-ai-data-center-in-northern-france/"}],"status":"announced","status_as_of":"2026-06-15","status_source_ids":["s2","s3"],"summary":"Data4, the Brookfield-owned European data center developer, plans a EUR 5 billion, 700 MW AI-oriented campus on the Parc des Soufflantes brownfield in Escaudain, northern France, the former Usinor steelworks. The local authority La Porte du Hainaut picked Data4 in December 2025; after feasibility studies Data4 confirmed the project in June 2026, with further studies and preliminary works over the following year and four data center buildings to follow. The site was among the French government and RTE fast-track grid sites.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"ac81d24f-1213-55b4-8895-b11b038fa18b","s2":"9715a716-15a7-5f21-ba6a-67aaf679853b","s3":"26ab81d6-a6c2-5f14-983f-4a68a221c851"},"source_file":"datacenters/projects/data4-escaudain.json","source_record_id":"data4-escaudain","source_record_sha256":"c94ceead57ad73e1cfe6ed4b4d77187261dfce5aff87696917bc35837f0fdea4","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"a84981d51ef8268204daf75b0de64409f5a4063cb3205fca1f692c9212bfbb26"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3b5d1fe13cf00d04d3f2/#project-f0afff75-0b96-5e18-a8f9-08ac9a4b99ff | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f0afff75-0b96-5e18-a8f9-08ac9a4b99ff.json
f0e92e2e-e082-5b7f-9486-fd744b5b68e6 | curated:vantage-zrh1-winterthur-campus:zrh12 | vcc-site-36334bc427db6b226db5 | curated:vantage-zrh1-winterthur-campus | Vantage ZRH12 | Switzerland | CH | 47.5007 | 8.7613 | Point | campus | exact_official_download_record_LV95_easting_northing_to_WGS84_via_official_REFRAME_service | exact_operator_campus_street_house_number_postal_code_city_to_unique_official_address_directory_record | official_building_entrance_address_reference_point | official_source | campus_locator | The selected exact official address record locates the shared ZRH1 campus, not the ZRH12 building, active construction footprint, campus boundary or new access entrance. The CSV gives millimetre-formatted coordinates but no quantitative accuracy for this record. Coordinate decimal places and transformation-service precision do not establish survey accuracy. |  | No quantitative accuracy supplied for individual official address record EGAID 102586517. | 0818330a-60db-531c-ab23-5ac7a6f225c7 | under_construction | 2026-07-30 | 75 | authoritative_physical_status_update | 3893fae6-9768-51d9-b8b0-591f2887e094 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.erne.ch/fr/news/detail/ernenews/in-winterthur-lassen-wir-ein-neues-data-center-wachsen/ | https://data.geo.admin.ch/ch.swisstopo.amtliches-gebaeudeadressverzeichnis/amtliches-gebaeudeadressverzeichnis_ch/amtliches-gebaeudeadressverzeichnis_ch_2056.csv.zip | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-36334bc427db6b226db5/#project-f0e92e2e-e082-5b7f-9486-fd744b5b68e6 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f0e92e2e-e082-5b7f-9486-fd744b5b68e6.json
f166440f-2ab0-57ea-9788-c66d89c8704f | curated:qts-eagle-mountain-slc1-data-center-campus:building-2 | vcc-site-3e65a9f3d78bff82cf77 | curated:qts-eagle-mountain-slc1-data-center-campus | QTS Eagle Mountain SLC1 Building 2 | United States | US | 40.2677 | -112.0333 | Point | campus | official_address_point | official_address_point | campus_address_point | official_source | campus_locator | Exact county-returned point for 550 E Hyperscale Way, capture method Placed on Map (Calc Parcel); broad SLC1 campus locator, not Building 2 footprint or parcel boundary. |  | The county says the point was calculated from a parcel and supplies no bounded positional error. | 646e7f86-8e12-5320-a580-ce00ffedf6ad | under_construction | 2026-07-01 | 104 | authoritative_physical_status_update | 9a7b27f7-7014-5a54-863a-aba6b9ff8e09 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.17 100-site batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://q.com/data-centers/eagle-mountain/ | https://maps.utahcounty.gov/arcgis/rest/services/Parcels/Parcel_AddressPoints/MapServer/0/query | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-3e65a9f3d78bff82cf77/#project-f166440f-2ab0-57ea-9788-c66d89c8704f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f166440f-2ab0-57ea-9788-c66d89c8704f.json
f2b93d1a-7c33-5a9e-be4d-f7d0dadec047 | curated:microsoft-la-porte-indiana-campus:first-phase-current-build | vcc-site-298aaa4c04e0d88160f7 | curated:microsoft-la-porte-indiana-campus | Microsoft La Porte First Phase Current Build | United States | US | 41.5796 | -86.6901 | Polygon | campus | exact_official_constituent_parcel_id_match | Indiana_IGIO_layer0_state_parcel_id_461107326005000058_native_and_output_EPSG4326_no_transform | official_constituent_parcel_campus_locator | official_source | campus_locator | Exact state-published polygon of constituent parcel 461107326005000058 at 360 E Boyd Boulevard, bound to Microsoft LPO campus by the government-hosted application and embedded county record. The application reports 215.361 acres for this parcel; Microsoft describes approximately 500 acres for the initial campus. This is not the whole campus boundary, a specific LPO building, the current grading area or the proposed eastern expansion. No campus count is inferred from buildings or phases. |  | No source-specific numerical horizontal positional accuracy is established for this county-supplied parcel geometry. GIS storage tolerance, decimal precision and a government source do not establish surveyed accuracy. | a2b0611b-2853-50eb-9744-39c6c94b8f69 | under_construction | 2026-06-18 | 117 | authoritative_construction_start | fef30f3e-a280-54a0-af8d-83c759ab90f4 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://local.microsoft.com/blog/microsoft-breaks-ground-on-la-porte-datacenter-project/ | https://gisdata.in.gov/server/rest/services/Hosted/Parcel_Boundaries_of_Indiana_Current/FeatureServer/0/query?where=state_parcel_id%3D%27461107326005000058%27&outFields=*&f=pjson&returnGeometry=true&outSR=4326 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-298aaa4c04e0d88160f7/#project-f2b93d1a-7c33-5a9e-be4d-f7d0dadec047 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f2b93d1a-7c33-5a9e-be4d-f7d0dadec047.json
f3cc5dc7-9547-517f-94aa-89e0769f2bf8 | curated:google-bermuda-hundred-chesterfield-campus:current-development | vcc-site-15afee16348a0ffc414f | curated:google-bermuda-hundred-chesterfield-campus | Google Bermuda Hundred Current Development | United States | US | 37.3463 | -77.3049 | Point | campus | official_service_parcel_centroid | ArcGIS_returnCentroid_true_outSR_4326_exact_property_query | official_parcel_reference_point | official_source | campus_locator | Official source-specific constituent-property centroid used only as a campus locator. Not a surveyed point, full campus boundary, building footprint, entrance, active-work extent or construction stage. Source numerical precision is not positional accuracy. |  | County terms explicitly disclaim numerical positional accuracy and legal/survey use. | 3908b2d8-3494-5c31-93f5-c5d84f368a20 | under_construction | 2026-07-01 | 104 | authoritative_physical_status_update | 3af60f35-2add-56e3-9002-0395731a93ff | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.chesterfield.gov/5989/Data-Centers | https://services3.arcgis.com/TsynfzBSE6sXfoLq/ArcGIS/rest/services/Cadastral_ProdA/FeatureServer/3/query | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-15afee16348a0ffc414f/#project-f3cc5dc7-9547-517f-94aa-89e0769f2bf8 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f3cc5dc7-9547-517f-94aa-89e0769f2bf8.json
f533639a-f574-566d-a780-db81daa4b78c | imported:semiconductor-atlas:terranova-campinas | vcc-site-c2bcc9c77043eec23331 | imported:semiconductor-atlas:terranova-campinas | Terranova Campinas data centre campus | Brazil | BR | -22.8278 | -47.0797 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates of the Barão Geraldo district from its Wikipedia page; the campus is on the Fazenda Pau D'Alho property within the PIDS innovation zone, whose exact boundary was not located. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 41ac3df9-e6e7-5309-b711-87feefee4cf7 | announced | 2026-08-26 | 48 | imported_documented_status | af0dbc2e-dd02-5748-8472-5f70e180f274 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"7c0154f6-387a-5d31-8207-0745baaac3d9","notes":null,"party":"Terranova","relationship_scope":"unknown","role":"developer","source_record_id":"terranova-campinas"},{"evidence_id":"c10c8c8f-57b7-5e17-86e8-c82bf36ab135","notes":null,"party":"Terranova","relationship_scope":"unknown","role":"developer","source_record_id":"terranova-campinas"},{"evidence_id":"41ac3df9-e6e7-5309-b711-87feefee4cf7","notes":null,"party":"Terranova","relationship_scope":"unknown","role":"developer","source_record_id":"terranova-campinas"},{"evidence_id":"af0dbc2e-dd02-5748-8472-5f70e180f274","notes":null,"party":"Terranova","relationship_scope":"unknown","role":"developer","source_record_id":"terranova-campinas"},{"evidence_id":"c10c8c8f-57b7-5e17-86e8-c82bf36ab135","notes":"Sustainable infrastructure investor that launched and backs Terranova.","party":"Actis","relationship_scope":"unknown","role":"investor","source_record_id":"terranova-campinas"},{"evidence_id":"41ac3df9-e6e7-5309-b711-87feefee4cf7","notes":"Sustainable infrastructure investor that launched and backs Terranova.","party":"Actis","relationship_scope":"unknown","role":"investor","source_record_id":"terranova-campinas"},{"evidence_id":"0f9a271a-f42e-57c8-ba53-1c96f463c0dc","notes":"Sustainable infrastructure investor that launched and backs Terranova.","party":"Actis","relationship_scope":"unknown","role":"investor","source_record_id":"terranova-campinas"},{"evidence_id":"41ac3df9-e6e7-5309-b711-87feefee4cf7","notes":"Issued the substation permits and environmental licence and granted 12 years of municipal tax incentives under the PIDS law.","party":"Prefeitura de Campinas","relationship_scope":"unknown","role":"government","source_record_id":"terranova-campinas"},{"evidence_id":"af0dbc2e-dd02-5748-8472-5f70e180f274","notes":"Issued the substation permits and environmental licence and granted 12 years of municipal tax incentives under the PIDS law.","party":"Prefeitura de Campinas","relationship_scope":"unknown","role":"government","source_record_id":"terranova-campinas"},{"evidence_id":"0f9a271a-f42e-57c8-ba53-1c96f463c0dc","notes":"Issued the substation permits and environmental licence and granted 12 years of municipal tax incentives under the PIDS law.","party":"Prefeitura de Campinas","relationship_scope":"unknown","role":"government","source_record_id":"terranova-campinas"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.correiodamanha.com.br/nacional/sao-paulo/campinas/2026/08/312866-campinas-tera-data-center-de-rs-5-bilhoes-voltado-a-inteligencia-artificial.html | https://constructionreviewonline.com/terranova-breaks-ground-on-216-mw-data-centre-in-campinas-sao-paulo/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve Terranova Campinas data centre campus as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"terranova-campinas"},"record":{"aliases":["Terranova Campus Campinas","Campus Campinas"],"id":"terranova-campinas","last_reviewed":"2026-10-09","location":{"admin1":"São Paulo","admin2":"Campinas","country":"BR","lat":-22.82778,"locality":"Barão Geraldo (Fazenda Pau D'Alho)","lon":-47.07972,"note":"Coordinates of the Barão Geraldo district from its Wikipedia page; the campus is on the Fazenda Pau D'Alho property within the PIDS innovation zone, whose exact boundary was not located.","precision":"locality","source_ids":["s3","s4","s5","s6"]},"metrics":[{"applies_to":"phase","as_of":"2026-08-25","basis":"planned","metric":"power_capacity","phase_label":"Phase 1","power_scope":"it_load","qualifier":"exact","source_ids":["s2","s3","s4"],"unit":"MW","value":216},{"applies_to":"campus","as_of":"2026-08-25","basis":"planned","metric":"power_capacity","note":"Expansion using reserved areas of the site.","power_scope":"it_load","qualifier":"up_to","source_ids":["s2","s3","s4"],"unit":"MW","value":386},{"applies_to":"campus","as_of":"2026-02-19","basis":"planned","metric":"power_capacity","note":"Earlier February 2026 report of IT capacity in later phases; August 2026 coverage gives 386 MW instead.","power_scope":"it_load","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2026-08-25","basis":"permitted","metric":"power_capacity","note":"Grid access authorised by the national system operator ONS in December 2025; the dedicated substation starts at 300 MW and could scale to 1 GW.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s3"],"unit":"MW","value":300},{"applies_to":"phase","as_of":"2026-08-20","basis":"announced","metric":"investment","phase_label":"Initial investment","qualifier":"approximately","source_ids":["s4","s5"],"unit":"BRL","value":5000000000},{"applies_to":"campus","as_of":"2026-08-20","basis":"announced","metric":"investment","note":"Potential total across all phases.","qualifier":"up_to","source_ids":["s4","s5"],"unit":"BRL","value":20000000000},{"applies_to":"phase","as_of":"2026-08-25","basis":"reported","metric":"investment","note":"Construction Review gives more than USD 500 million for phase one; W.Media gives an initial USD 500 million, attributed to the Campinas municipal government. Both are below the BRL 5 billion initial figure reported locally.","phase_label":"Phase 1","qualifier":"more_than","source_ids":["s2","s3"],"unit":"USD","value":500000000},{"applies_to":"campus","as_of":"2026-08-24","basis":"reported","metric":"land_area","note":"Other sources give about 944,000 square metres, of which about 115,000 square metres would be built and about 285,000 kept green or transferred to the city.","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":233},{"applies_to":"campus","as_of":"2026-08-25","basis":"planned","metric":"jobs_construction","note":"Direct and indirect jobs at peak construction; local press reported about 3,600 direct and indirect jobs.","qualifier":"up_to","source_ids":["s2","s3"],"unit":"count","value":3000},{"applies_to":"campus","as_of":"2026-08-25","basis":"planned","metric":"jobs_permanent","note":"Permanent roles over five years.","qualifier":"approximately","source_ids":["s2","s3"],"unit":"count","value":650}],"milestones":[{"date":"2025-12","event":"other","kind":"actual","note":"Brazil's grid operator ONS confirmed access to 300 MW at the site.","source_ids":["s1","s3"]},{"date":"2026-04-07","event":"other","kind":"actual","note":"Twelve years of municipal tax benefits for the project company published in the official gazette.","source_ids":["s5"]},{"date":"2026-08-21","event":"permit_approved","kind":"actual","note":"A construction permit was handed over at the 20 August ceremony; approval and execution permits were published on 21 August and, according to the city, cover a power substation. A municipal preliminary and installation environmental licence was issued on 18 August.","source_ids":["s3","s5"]},{"date":"2026-08","event":"other","kind":"actual","note":"Trade press reported that construction had begun after the permit ceremony; the city said the permits issued cover only a power substation and did not confirm wider works.","source_ids":["s2","s3"]},{"date":"2027-12","event":"other","kind":"planned","note":"Target energisation of the 300 MW substation.","source_ids":["s3"]},{"date":"2027","event":"first_operational","kind":"planned","note":"February 2026 report that the campus was expected to open the following year.","source_ids":["s1"]}],"name":"Terranova Campinas data centre campus","notes":"Set to announced as the more conservative reading of conflicting reports. W.Media (citing a city statement) and Construction Review reported construction starting after the 20 August 2026 ceremony, but the city later said the permits published on 21 August covered only a power substation, with land subdivision and the neighbourhood impact study still under review. Tax benefits went to the company Terra Nova 1500 Ltda. February 2026 reporting expected 220 to 230 MW of operational capacity at opening in 2027 and more than 500 MW of IT later. A local lawmaker cited 400 MW of demand rather than 300 MW.","parties":[{"name":"Terranova","role":"developer","source_ids":["s1","s2","s3","s4"]},{"name":"Actis","note":"Sustainable infrastructure investor that launched and backs Terranova.","role":"investor","source_ids":["s2","s3","s5"]},{"name":"Prefeitura de Campinas","note":"Issued the substation permits and environmental licence and granted 12 years of municipal tax incentives under the PIDS law.","role":"government","source_ids":["s3","s4","s5"]}],"power_sources":[{"description":"A dedicated Pau D'Alho substation of 300 MW initially, expandable to 1 GW, is planned by sectioning the 440 kV Replan to Santo Ângelo transmission line.","source_ids":["s3","s5"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2026-02-19","publisher":"TELETIME","title":"Terranova terá megaestruturas e estuda expansão de data centers no Brasil","type":"trade_press","url":"https://teletime.com.br/19/02/2026/terranova-tera-megaestruturas-e-estuda-expansao-de-data-centers-no-brasil/"},{"accessed":"2026-10-09","id":"s2","published":"2026-08-24","publisher":"W.Media","title":"Terranova starts construction on US$ 500 million data center campus in Brazil","type":"trade_press","url":"https://w.media/terranova-starts-construction-on-us-500-million-data-center-campus-in-brazil/"},{"accessed":"2026-10-09","id":"s3","published":"2026-08-25","publisher":"Construction Review Online","title":"Terranova breaks ground on 216 MW Data Centre in Campinas, São Paulo","type":"trade_press","url":"https://constructionreviewonline.com/terranova-breaks-ground-on-216-mw-data-centre-in-campinas-sao-paulo/"},{"accessed":"2026-10-09","id":"s4","published":"2026-08-20","publisher":"Correio da Manhã","title":"Campinas terá data center de R$ 5 bilhões voltado à Inteligência Artificial","type":"news","url":"https://www.correiodamanha.com.br/nacional/sao-paulo/campinas/2026/08/312866-campinas-tera-data-center-de-rs-5-bilhoes-voltado-a-inteligencia-artificial.html"},{"accessed":"2026-10-09","id":"s5","published":"2026-08-26","publisher":"Correio da Manhã","title":"Data center de R$ 5 bilhões em Campinas vira alvo do Ministério Público Federal e Estadual","type":"news","url":"https://www.correiodamanha.com.br/nacional/sao-paulo/campinas/2026/08/314378-data-center-de-rs-5-bi-em-campinas-conti-samia-petta-e-orlando-silva-pedem-suspensao-ao-mpf-e-ao-mp-sp.html"},{"accessed":"2026-10-09","id":"s6","published":null,"publisher":"Wikipedia","title":"Barão Geraldo","type":"other","url":"https://en.wikipedia.org/wiki/Bar%C3%A3o_Geraldo"}],"status":"announced","status_as_of":"2026-08-26","status_source_ids":["s4","s5"],"summary":"Terranova, a Latin American hyperscale platform backed by investor Actis, plans an AI and cloud data centre campus on about 944,000 square metres at Fazenda Pau D'Alho in Barão Geraldo, Campinas, inside the city's PIDS innovation zone. Phase 1 is planned at 216 MW of IT load, expandable to 386 MW, with an initial investment reported locally at about BRL 5 billion that could reach BRL 20 billion. Grid access for 300 MW was authorised in December 2025 and a substation is due to be energised in December 2027. Trade press reported construction starting in August 2026, but the city said the permits issued covered only a substation; local politicians asked prosecutors to review the licensing.","workloads":["ai_unspecified","cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"7c0154f6-387a-5d31-8207-0745baaac3d9","s2":"c10c8c8f-57b7-5e17-86e8-c82bf36ab135","s3":"41ac3df9-e6e7-5309-b711-87feefee4cf7","s4":"af0dbc2e-dd02-5748-8472-5f70e180f274","s5":"0f9a271a-f42e-57c8-ba53-1c96f463c0dc","s6":"8b5aeb85-75f1-576e-94a8-41042d68d94d"},"source_file":"datacenters/projects/terranova-campinas.json","source_record_id":"terranova-campinas","source_record_sha256":"10b10cc37911cb7289232d3966039f336524d3dca8ba5dcec217129518ac0c7b","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"7b53fe541d6e6142c5b7ac2aab833a5e3b6031310cb6798b5dcf48054802e99d"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c2bcc9c77043eec23331/#project-f533639a-f574-566d-a780-db81daa4b78c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f533639a-f574-566d-a780-db81daa4b78c.json
f595ca9f-e584-5dcb-bf76-38b346f6e4aa | curated:cipher-digital-black-pearl-wink-texas-data-center-campus:aws-phase-2-site-preparation | vcc-site-6bedc032f2f6fb914715 | curated:cipher-digital-black-pearl-wink-texas-data-center-campus | Cipher Digital Black Pearl Phase II Current Build | United States | US | 31.6913 | -103.067 | Point | campus | official_9_1_1_address_point_for_exact_primary_site_address | TxGIO_StratMap_address_point_query_by_full_addr_and_county_outSR4326_round7 | official_address_point_for_campus_site_address | official_source | campus_locator | The official statewide 9-1-1 address point for the exact site address named by primary identity sources. It locates the campus address, not a data hall, phase, parcel boundary, footprint or current work extent. Source value rounded to seven decimals. |  | TxGIO states that each authoritative 9-1-1 source applies its own point-placement guideline and policy (rooftop, parcel centroid or street centreline are not fixed) and publishes no positional accuracy for individual points. | eb0bee76-1393-5d0c-ab38-31f685139b3d | under_construction | 2026-08-04 | 70 | authoritative_physical_status_update | 0d9d52ab-0c73-536a-8c47-cd1691698743 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.globenewswire.com/news-release/2026/08/04/3338166/0/en/cipher-digital-provides-second-quarter-2026-business-update.html | https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0/query?where=full_addr%3D%2711786%20COUNTY%20ROAD%20209%27%20AND%20county%3D%27Winkler%27&outFields=*&returnGeometry=true&outSR=4326&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6bedc032f2f6fb914715/#project-f595ca9f-e584-5dcb-bf76-38b346f6e4aa | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f595ca9f-e584-5dcb-bf76-38b346f6e4aa.json
f6d1bce2-6fc7-5fd8-a1fb-55d5fe4cd8e9 | curated:racks-central-johor-ai-campus:rcjm1-first-phase | vcc-site-31ed6c5da19a943535f6 | curated:racks-central-johor-ai-campus | Racks Central RCJM1 Phase A | Malaysia | MY | 1.5324 | 103.9282 | MultiPolygon | host_estate | topological_union_of_two_osm_host_development_way_polygons | osm_iskandar_halal_park_phase_1_v4_phase_2_v3_union_retained_as_host_estate_context_not_campus_locator | community_multi_phase_host_development_polygon_context_only | community_source | host_estate_context | Union of the two named Iskandar Halal Park host-development phases as mapped by OpenStreetMap: way 639973556 version 4 (Phase 1; 16 distinct vertices in a closed way of 17 node references; about 39.76 ha) and way 639973557 version 3 (tagged Phase 2, U/C; 19 distinct vertices in a closed way of 20 node references; about 83.55 ha), two disjoint community polygons about 22 m apart totalling about 123.31 ha (WGS84 geodesic, diagnostic). Racks Central places its RCJM campus only in Iskandar Halal Park, 81700 Pasir Gudang, and reports its first Johor land as a five-acre (about 2.02 ha) plot in the park; no reviewed source places RCJM1, Phase A or that plot at any position within, or confirms containment in, either phase polygon. Host-development locality context only: not an RCJM campus, RCJM1 or Phase A locator, parcel, boundary, footprint or work extent. The display anchor is the planar centroid of the two longitude/latitude rings, kept unchanged only because the row schema requires a point; it lies about 3.3 m outside the Phase 2 ring and about 402 m from the Phase 1 ring, inside neither polygon, and is not an RCJM1 position. |  | RCJM1's position relative to this host-development outline is unknown and no source bounds it; OpenStreetMap states no positional accuracy for either outline. No numeric uncertainty is asserted. | c9c2d9bd-d6b3-5738-9ca0-78a9c351954f | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 6f81ed11-d205-5056-b2d9-d3c014f0bc9a | recent_authoritative_physical_observation_plus_host_estate_context_only | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.16 country-diversity batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.rackscentral.com/news/racks-central-celebrates-milestone-for-southeast-asia-s-first-ai-factory-campus-in-johor | https://api.openstreetmap.org/api/0.6/way/639973556/full.json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-31ed6c5da19a943535f6/#project-f6d1bce2-6fc7-5fd8-a1fb-55d5fe4cd8e9 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f6d1bce2-6fc7-5fd8-a1fb-55d5fe4cd8e9.json
f8377a0f-dc89-5b7a-8257-25f25cdbac43 | curated:microsoft-new-albany-oh-datacenter:initial-site-preparation | vcc-site-c0945d7c74abf8504604 | curated:microsoft-new-albany-oh-datacenter | Microsoft New Albany Initial Site Preparation | United States | US | 40.1038 | -82.7535 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | 35c41e3e-909b-57dd-b9a0-879467ec17cb | site_preparation | 2026-07-01 | 104 | authoritative_physical_status_update | 431690d2-aa37-5626-905e-69ddc5f30a41 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://local.microsoft.com/blog/newalbany-datacenter-construction-update/ | https://geocoding.geo.census.gov/geocoder/ | [{"identity_decision":{"decision":"multi_site_program","flags":["administrative_locator_not_project_geometry","multiple_sites_no_single_map_point"],"rationale":"Source explicitly describes separate Microsoft campuses in Heath, Hebron and New Albany. Each already has its own release identity and site locator; attach regional context to all three without merging their statuses or capacities. Source statement that no New Albany update was found differs from the release's July 2026 official New Albany observation.","related_project_stable_keys":["curated:microsoft-heath-oh-datacenter:initial-site-preparation","curated:microsoft-hebron-oh-datacenter:initial-site-preparation","curated:microsoft-new-albany-oh-datacenter:initial-site-preparation"],"source_record_id":"microsoft-licking-county-ohio"},"record":{"aliases":["Microsoft Heath datacenter","Microsoft Hebron datacenter","Microsoft New Albany datacenter"],"id":"microsoft-licking-county-ohio","last_reviewed":"2026-10-09","location":{"admin1":"Ohio","admin2":"Licking County","country":"US","lat":40.1318,"lon":-82.4628,"note":"County centroid from Nominatim, because the record covers a three-site program in different municipalities (New Albany, Heath and Hebron). Microsoft's pages place the Heath construction entrance on Thornwood Drive and a temporary Hebron construction entrance on Canyon Road.","precision":"admin2","source_ids":["s1","s2","s6","s7"]},"metrics":[{"applies_to":"campus","as_of":"2024-10-28","basis":"announced","metric":"investment","note":"Initial investment announced for the three campuses together; no per-site split was given, and POWER does not say whether the New Albany USD 420 million is part of it.","qualifier":"exact","source_ids":["s1","s2","s4"],"unit":"USD","value":1000000000},{"applies_to":"phase","as_of":"2024-10","basis":"announced","metric":"investment","note":"New Albany's city council approved a 15-year, 100 percent property tax abatement for this building.","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s1","s2"],"unit":"USD","value":420000000},{"applies_to":"phase","as_of":"2025-04-10","basis":"planned","metric":"floor_area","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s2"],"unit":"sq_ft","value":245000},{"applies_to":"phase","as_of":"2025-04-10","basis":"reported","metric":"land_area","phase_label":"New Albany datacenter","qualifier":"exact","source_ids":["s2"],"unit":"acres","value":197}],"milestones":[{"date":"2024-10-28","event":"announced","kind":"actual","source_ids":["s1"]},{"date":"2025-04-07","event":"paused","kind":"actual","note":"Microsoft said it would not move forward at that time, would keep evaluating the sites, would make land at two sites farmable (Heath and Hebron, per ENR), and would still fund road and utility upgrades under its development agreements.","source_ids":["s2","s3","s4"]},{"date":"2026-02-24","event":"construction_started","kind":"actual","note":"Ceremonial groundbreaking at the Heath site off Thornwood Drive; Microsoft's Heath and Hebron pages report mass grading from February 2026 and tree clearing in March 2026.","source_ids":["s5","s6","s7"]},{"date":"2026-11","event":"other","kind":"planned","note":"Target finish of mass grading at Heath and Hebron; Microsoft says early site preparation should be largely done by year-end and has not set a vertical construction timeline.","source_ids":["s6","s7"]}],"name":"Microsoft Licking County three-site datacenter program (New Albany, Heath, Hebron)","notes":"This record groups three sites because the cited sources present them as one program under a single USD 1 billion announcement; split into per-site records if site-level power or investment figures are found. Status reflects site preparation at Heath and Hebron; the New Albany building was on hold as of April 2025 and no later update was found. status_as_of uses the first day of July 2026, the month of the latest entries on Microsoft's month-dated update pages.","parties":[{"name":"Microsoft","role":"developer","source_ids":["s1","s2"]},{"name":"Microsoft","note":"ENR and Fox 28 report that Microsoft owns the Licking County sites and will keep the land.","role":"owner","source_ids":["s2","s3"]},{"name":"Ames Construction","note":"Contractor clearing the New Albany site before the 2025 pause (ENR) and main contractor for the Heath and Hebron site work in 2026 (Microsoft).","role":"builder","source_ids":["s2","s6","s7"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2024-10-28","publisher":"POWER Magazine","title":"Microsoft Announces $1 Billion Investment in Ohio Data Centers as Officials Ponder Power Demands","type":"trade_press","url":"https://www.powermag.com/microsoft-announces-1-billion-investment-in-ohio-data-centers-as-officials-ponder-power-demands"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260516063141/https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio","id":"s2","published":"2025-04-10","publisher":"Engineering News-Record","title":"Microsoft Hits Pause Button on $1B in Data Centers in Ohio","type":"trade_press","url":"https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio"},{"accessed":"2026-10-09","id":"s3","published":"2025-04-08","publisher":"WSYX/WTTE (Fox 28 Columbus)","title":"Microsoft 'not moving forward' with $1B Licking County data center plans right now","type":"news","url":"https://myfox28columbus.com/news/local/microsoft-backs-off-1b-licking-county-data-center-plans"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20250410023315/https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/","id":"s4","published":"2025-04-09","publisher":"Associated Press (via News4JAX)","title":"Microsoft says it's 'slowing or pausing' some AI data center projects, including $1B plan for Ohio","type":"news","url":"https://www.news4jax.com/business/2025/04/09/microsoft-says-its-slowing-or-pausing-some-ai-data-center-projects-including-1b-plan-for-ohio/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260227140645/https://abc6onyourside.com/news/local/heath-columbus-ohio-break-ground-microsoft-data-center-expected-bring-hundreds-jobs-tech-technology-ai-artificial-intelligence-cloud-computing-digital-services","id":"s5","published":"2026-02-24","publisher":"WSYX ABC 6","title":"Heath breaks ground on Microsoft data center expected to bring hundreds of jobs","type":"news","url":"https://www.abc6onyourside.com/news/local/heath-columbus-ohio-break-ground-microsoft-data-center-expected-bring-hundreds-jobs-tech-technology-ai-artificial-intelligence-cloud-computing-digital-services"},{"accessed":"2026-10-09","id":"s6","published":"2026-07","publisher":"Microsoft Local","title":"Heath datacenter construction updates","type":"company","url":"https://local.microsoft.com/blog/heath-datacenter-construction-updates/"},{"accessed":"2026-10-09","id":"s7","published":"2026-07","publisher":"Microsoft Local","title":"Hebron datacenter construction update","type":"company","url":"https://local.microsoft.com/blog/hebron-datacenter-construction-update/"}],"status":"under_construction","status_as_of":"2026-07-01","status_source_ids":["s5","s6","s7"],"summary":"Three-site Microsoft datacenter program in Licking County, east of Columbus, Ohio, with separate campuses in New Albany, Heath and Hebron. Announced in October 2024 as an initial USD 1 billion investment for Azure cloud capacity, it included a USD 420 million, 245,000 sq ft building on 197 acres in New Albany. In April 2025 Microsoft paused the program, keeping the land and saying two sites would be made farmable. Work resumed in 2026: Heath broke ground in February, and Microsoft's Heath and Hebron pages report tree clearing, mass grading through November 2026 and planned substation work, with no vertical construction timeline. No 2026 update was found for New Albany.","workloads":["cloud","ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"53a991df-b72c-5ce1-9102-4b2936f3ed84","s2":"3da0d477-2381-54c6-bca3-e3552b21b523","s3":"52512d65-d545-5d59-a6f4-27e8e186eaab","s4":"c9565490-4acd-5d00-97a2-af07b6b2aeae","s5":"c27c9dd5-6622-5355-bd70-7dc3d703241e","s6":"9b8c42cb-65b2-50cc-860d-bd61eed97709","s7":"6591b6d1-867c-59b3-aa1f-ddbe9c167308"},"source_file":"datacenters/projects/microsoft-licking-county-ohio.json","source_record_id":"microsoft-licking-county-ohio","source_record_sha256":"aa63c46124d3685f68abaa56575f892aa7a9a9c91345273642a9a103e42db940","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"4efd2bbab8400f3312e0d7e8b453b7bf64695c7208d12e44522b6d32b8cd9cae"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-c0945d7c74abf8504604/#project-f8377a0f-dc89-5b7a-8257-25f25cdbac43 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f8377a0f-dc89-5b7a-8257-25f25cdbac43.json
f8900f55-087d-5d51-aef2-820402bcbdc2 | curated:goodman-ams01-amsterdam-data-centre-campus:phase-1-current-development | vcc-site-044046b0ede92919a936 | curated:goodman-ams01-amsterdam-data-centre-campus | Goodman AMS01 Phase 1 Current Development | Netherlands | NL | 52.3794 | 4.7049 | Point | campus | official_notice_published_point_marker | first_published_RD_point_transformed_to_WGS84_without_centroiding | official_project_notice_campus_locator | official_source | campus_locator | The provincial notice marker locates the same named entity/address as the certifier's literal AMS01 record. It does not delineate Building A, Building B, a cadastral property or the June 30 active-work extent. One point represents one campus. |  | The notice gives a location marker but no numeric horizontal-accuracy statement or surveyed reference feature. | fb26fa5c-bb7a-5323-b71e-afa469c7b954 | under_construction | 2026-06-30 | 105 | authoritative_physical_status_update | 06e229c2-36e5-5a0d-a27c-50162d17fe0f | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | https://zoek.officielebekendmakingen.nl/prb-2026-2233/metadata.xml | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-044046b0ede92919a936/#project-f8900f55-087d-5d51-aef2-820402bcbdc2 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f8900f55-087d-5d51-aef2-820402bcbdc2.json
f8a7bd1c-26a2-5b59-8e1b-d657084c4f7c | imported:semiconductor-atlas:airtrunk-hyd1-chandanvelly | vcc-site-2b9d83de9f69d94f5df1 | imported:semiconductor-atlas:airtrunk-hyd1-chandanvelly | AirTrunk HYD1 Hyderabad | India | IN | 17.2327 | 78.1713 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | AirTrunk names Chandanvelly, Hyderabad, without an address; the point is the Chandanvelly village coordinate from its Wikipedia article, so it marks the village rather than the parcel. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 853741ff-31ec-5ba1-b5d2-522cb38c86e5 | announced | 2026-10-09 | 4 | imported_documented_status | 853741ff-31ec-5ba1-b5d2-522cb38c86e5 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"853741ff-31ec-5ba1-b5d2-522cb38c86e5","notes":"Lists HYD1 among its India campuses after acquiring Lumina CloudInfra; the sources do not say whether the site came from Lumina's pipeline.","party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-hyd1-chandanvelly"},{"evidence_id":"a4621440-df63-5fa5-bafc-0bd1c66fec8f","notes":"Lists HYD1 among its India campuses after acquiring Lumina CloudInfra; the sources do not say whether the site came from Lumina's pipeline.","party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-hyd1-chandanvelly"},{"evidence_id":"65c0e6c7-195e-5042-9785-23f68afab5bd","notes":"Lists HYD1 among its India campuses after acquiring Lumina CloudInfra; the sources do not say whether the site came from Lumina's pipeline.","party":"AirTrunk","relationship_scope":"unknown","role":"developer","source_record_id":"airtrunk-hyd1-chandanvelly"},{"evidence_id":"a4621440-df63-5fa5-bafc-0bd1c66fec8f","notes":"Provides long-term capital to AirTrunk's platform alongside CPPIB; not a site-specific investment.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"airtrunk-hyd1-chandanvelly"},{"evidence_id":"65c0e6c7-195e-5042-9785-23f68afab5bd","notes":"Provides long-term capital to AirTrunk's platform alongside CPPIB; not a site-specific investment.","party":"Blackstone","relationship_scope":"unknown","role":"investor","source_record_id":"airtrunk-hyd1-chandanvelly"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://airtrunk.com/location/hyd1-hyderabad/ | https://airtrunk.com/location/hyd1-hyderabad/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve AirTrunk HYD1 Hyderabad as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"airtrunk-hyd1-chandanvelly","source_relations":[{"reason":"Distinct AirTrunk HYD1 and CtrlS campus announcements share only the Chandanvelly locality locator.","relationship":"separate_named_developments","source_id":"ctrls-chandanvelly-hyderabad"}]},"record":{"aliases":["AirTrunk HYD1","HYD1 Hyderabad"],"id":"airtrunk-hyd1-chandanvelly","last_reviewed":"2026-10-09","location":{"admin1":"Telangana","country":"IN","lat":17.2327,"locality":"Chandanvelly","lon":78.1713,"note":"AirTrunk names Chandanvelly, Hyderabad, without an address; the point is the Chandanvelly village coordinate from its Wikipedia article, so it marks the village rather than the parcel.","precision":"locality","source_ids":["s1","s4"]},"metrics":[{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"power_capacity","note":"Total capacity on AirTrunk's undated HYD1 page; the page does not say whether it is IT load or how much is built.","power_scope":"unspecified","qualifier":"more_than","source_ids":["s1"],"unit":"MW","value":243},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1"],"unit":"hectares","value":13.3}],"milestones":[{"date":"2026-04-20","event":"other","kind":"actual","note":"AirTrunk announced its acquisition of Lumina CloudInfra, entering the Mumbai, Chennai and Hyderabad markets with a portfolio of about 600 MW of planned capacity; the announcement does not name HYD1 or Chandanvelly.","source_ids":["s2","s3"]}],"name":"AirTrunk HYD1 Hyderabad","notes":"Thinly sourced: the site name, capacity and land area come only from AirTrunk's undated HYD1 page, read on 2026-10-09, so status_as_of is the access date and the status of announced reflects the absence of any construction report. The page's floor area figure appears garbled and is not recorded. The separate CtrlS campus is also at Chandanvelly. Wikipedia is cited only for the village coordinate.","parties":[{"name":"AirTrunk","note":"Lists HYD1 among its India campuses after acquiring Lumina CloudInfra; the sources do not say whether the site came from Lumina's pipeline.","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Blackstone","note":"Provides long-term capital to AirTrunk's platform alongside CPPIB; not a site-specific investment.","role":"investor","source_ids":["s2","s3"]}],"power_sources":[{"description":"AirTrunk lists a 440/220 kV substation for the campus.","source_ids":["s1"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":null,"publisher":"AirTrunk","title":"HYD1 Hyderabad","type":"company","url":"https://airtrunk.com/location/hyd1-hyderabad/"},{"accessed":"2026-10-09","id":"s2","published":"2026-04-20","publisher":"AirTrunk","title":"AirTrunk Acquires Lumina CloudInfra","type":"company","url":"https://airtrunk.com/?p=16687"},{"accessed":"2026-10-09","id":"s3","published":"2026-04-20","publisher":"W.Media","title":"AirTunk acquires Lumina CloudInfra, makes foray into India","type":"trade_press","url":"https://w.media/airtunk-acquires-lumina-cloudinfra-makes-foray-into-india/"},{"accessed":"2026-10-09","id":"s4","published":null,"publisher":"Wikipedia","title":"Chandanvelly","type":"other","url":"https://en.wikipedia.org/wiki/Chandanvelly"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s1","s2"],"summary":"HYD1 is AirTrunk's Hyderabad campus at Chandanvelly, Telangana, which AirTrunk lists at more than 243 MW on a 13.3-hectare site served by a 440/220 kV substation. AirTrunk entered India in April 2026 by acquiring Blackstone-backed Lumina CloudInfra, whose roughly 600 MW planned pipeline spans Mumbai, Chennai and Hyderabad. AirTrunk's site page gives no construction status or dates, and no other source describing work at the site was found.","workloads":["cloud"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"853741ff-31ec-5ba1-b5d2-522cb38c86e5","s2":"a4621440-df63-5fa5-bafc-0bd1c66fec8f","s3":"65c0e6c7-195e-5042-9785-23f68afab5bd","s4":"c8a65ef5-da7b-5aa8-88c3-d139b4d215a0"},"source_file":"datacenters/projects/airtrunk-hyd1-chandanvelly.json","source_record_id":"airtrunk-hyd1-chandanvelly","source_record_sha256":"8e78b5ba7eee6e390db92f63d08c5efa2bdb25197c8868e097348dfea66d8354","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"27d193e65f9d912a85ab0065cc236870fc7c001c8e7433fe5752dd934220ab08"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-2b9d83de9f69d94f5df1/#project-f8a7bd1c-26a2-5b59-8e1b-d657084c4f7c | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f8a7bd1c-26a2-5b59-8e1b-d657084c4f7c.json
f9e7c64e-3dc3-5d47-a4de-4c72a4284231 | curated:digital-realty-vienna-vie13-vie16-expansion:vie13-phase-1-current-build | vcc-site-137418ccdcd0272f024b | curated:digital-realty-vienna-vie13-vie16-expansion | Digital Realty VIE13 Phase 1 Current Data Center Build | Austria | AT | 48.271 | 16.4241 | Point | project | direct_geometry | first_party_facility_page_next_data_point | first_party_facility_page_reference_point | official_source | project_locator | The source decimal strings are preserved exactly and parsed without coordinate transformation. Their displayed precision does not imply a surveyed reference feature or horizontal accuracy. |  | The page does not identify a geodetic datum, surveyed reference feature, collection method, or numeric horizontal accuracy. | 4bbf6d0c-4fcb-5dd0-9504-4322a80117b8 | under_construction | 2026-06-18 | 117 | authoritative_physical_status_update | 9ef151e3-b5f8-5421-b9df-f5ac0bfca4a6 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | source evidence does not distinguish greenfield, expansion, or retrofit | colocation |  | 7305379e-4152-58ec-9152-c2d7af3d39c1 | [] | not established by selected evidence | [] | [] | no typed project power observation; not estimated | [] | no scoped annual-energy inputs; not estimated | [] | no scoped PUE or WUE observation | [5 empty] | https://www.linkedin.com/posts/digitalrealty_carrier-hub-day-wrapupmp4-activity-7473287475726213120-4j-2 | https://www.digitalrealty.com/data-centers/emea/vienna/vie13 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-137418ccdcd0272f024b/#project-f9e7c64e-3dc3-5d47-a4de-4c72a4284231 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/f9e7c64e-3dc3-5d47-a4de-4c72a4284231.json
fa44cb24-5185-5616-a6a2-3977f190001f | curated:cipher-digital-stingray-andrews-texas-data-center-campus:current-build | vcc-site-bdf4718cb174c2faaaf4 | curated:cipher-digital-stingray-andrews-texas-data-center-campus | Cipher Digital Stingray Data Center Current Build | United States | US | 32.3721 | -102.9824 | Point | campus | official_9_1_1_address_point_for_exact_primary_site_address | TxGIO_StratMap_address_point_query_by_full_addr_and_county_outSR4326_round7 | official_address_point_for_campus_site_address | official_source | campus_locator | The official statewide 9-1-1 address point for the exact site address named by primary identity sources. It locates the campus address, not a data hall, phase, parcel boundary, footprint or current work extent. Source value rounded to seven decimals. |  | TxGIO states that each authoritative 9-1-1 source applies its own point-placement guideline and policy (rooftop, parcel centroid or street centreline are not fixed) and publishes no positional accuracy for individual points. | 1cafca44-f42f-5814-982a-730ce77686e5 | under_construction | 2026-08-04 | 70 | authoritative_physical_status_update | e4070be7-af84-55db-9686-f394b51f2c77 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.globenewswire.com/news-release/2026/08/04/3338166/0/en/cipher-digital-provides-second-quarter-2026-business-update.html | https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0/query?where=full_addr%3D%27110%20SOUTHWEST%209001%27%20AND%20county%3D%27Andrews%27&outFields=*&returnGeometry=true&outSR=4326&f=json | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-bdf4718cb174c2faaaf4/#project-fa44cb24-5185-5616-a6a2-3977f190001f | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/fa44cb24-5185-5616-a6a2-3977f190001f.json
fb943def-5b5b-5192-8bb9-599e4cf616cc | curated:bitdeer-massillon-ohio-campus:2026-fire-damaged-buildings-reconstruction | vcc-site-6524649236861b8342aa | curated:bitdeer-massillon-ohio-campus | Bitdeer Massillon 2026 Fire-Damaged Buildings Reconstruction | United States | US | 40.7804 | -81.5223 | Point | campus | official_address_geocode | census_public_ar_current_street_range_interpolation | official_census_address_locator_point | official_source | campus_locator | Official Census Public_AR_Current address-match point used only to locate the source-linked parent campus. Street-range interpolation can differ from a parcel, building, entrance, or surveyed position. |  | The captured Census match supplies no bounded horizontal-accuracy value, and a street-range interpolation point is not asserted to fall within the campus, parcel, building, or project extent. | fa1a4303-efd0-5426-adb3-2878bca8bb28 | under_construction | 2026-07-21 | 84 | authoritative_physical_status_update | 5e48435e-d49f-5e10-aef3-9b672b64e571 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.14 address-locator batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.sec.gov/Archives/edgar/data/1899123/000121390026079816/ea029852701ex99-1.htm | https://geocoding.geo.census.gov/geocoder/ | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6524649236861b8342aa/#project-fb943def-5b5b-5192-8bb9-599e4cf616cc | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/fb943def-5b5b-5192-8bb9-599e4cf616cc.json
fbbfee97-55a0-5a4e-b000-282ff02a8a39 | imported:semiconductor-atlas:beacon-ai-centers-indus | vcc-site-ef8be5d9da9f69e72683 | imported:semiconductor-atlas:beacon-ai-centers-indus | Beacon AI Centers Indus campus | Canada | CA | 50.9434 | -113.8072 | Point | project | imported_reference_point | imported_reference_point | site | compiled_reference | project_locator | Decimal coordinates given in the proponent's initial project description (legal land description in section 11-23-28-W4M, south of Township Road 232), rounded to four decimals. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 314d2a34-7e3f-5faa-8251-c7eda8caadde | announced | 2026-10-09 | 4 | imported_documented_status | 33790c31-2bee-5340-957a-5ccbe793994e | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"314d2a34-7e3f-5faa-8251-c7eda8caadde","notes":"The filing says Beacon develops the project through the project-specific entity Indus Power.","party":"Beacon AI Centers","relationship_scope":"unknown","role":"developer","source_record_id":"beacon-ai-centers-indus"},{"evidence_id":"314d2a34-7e3f-5faa-8251-c7eda8caadde","notes":"Proponent of the on-site gas plant; its general partner is Northbridge Power GPC Inc.","party":"Indus Power Generation LP","relationship_scope":"unknown","role":"power_supplier","source_record_id":"beacon-ai-centers-indus"},{"evidence_id":"14e5b2e8-3772-50b5-844e-c84bbe7c2bdc","notes":"Proponent of the on-site gas plant; its general partner is Northbridge Power GPC Inc.","party":"Indus Power Generation LP","relationship_scope":"unknown","role":"power_supplier","source_record_id":"beacon-ai-centers-indus"},{"evidence_id":"7224e3fd-627d-5cc7-9901-082062869455","notes":"Proponent of the on-site gas plant; its general partner is Northbridge Power GPC Inc.","party":"Indus Power Generation LP","relationship_scope":"unknown","role":"power_supplier","source_record_id":"beacon-ai-centers-indus"},{"evidence_id":"8ff0872f-8f2a-5986-908a-95d283fc7f39","notes":"Approved the area structure plan and land-use redesignation; participating in the provincial power plant review.","party":"Rocky View County","relationship_scope":"unknown","role":"government","source_record_id":"beacon-ai-centers-indus"},{"evidence_id":"33790c31-2bee-5340-957a-5ccbe793994e","notes":"Approved the area structure plan and land-use redesignation; participating in the provincial power plant review.","party":"Rocky View County","relationship_scope":"unknown","role":"government","source_record_id":"beacon-ai-centers-indus"},{"evidence_id":"f553b03d-c3e6-53e5-9f1a-6455c8f9046e","notes":"Approved the area structure plan and land-use redesignation; participating in the provincial power plant review.","party":"Rocky View County","relationship_scope":"unknown","role":"government","source_record_id":"beacon-ai-centers-indus"},{"evidence_id":"314d2a34-7e3f-5faa-8251-c7eda8caadde","notes":"Owner of the 240 kV line the project proposes to tap, with interconnection at the Langdon 102S substation.","party":"AltaLink","relationship_scope":"unknown","role":"utility","source_record_id":"beacon-ai-centers-indus"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.rockyview.ca/build-plan-and-develop/planning/planning-projects-underway/beacon-ai-hub-area-structure-plan | https://iaac-aeic.gc.ca/050/documents/p90121/164415E.pdf | [{"identity_decision":{"decision":"unique_site","flags":["source_site_point_not_surveyed_boundary"],"rationale":"No matching named development in the 201-project release. Preserve Beacon AI Centers Indus campus as an independent source record; its site locator does not itself establish a surveyed physical site.","source_record_id":"beacon-ai-centers-indus"},"record":{"aliases":["Beacon AI Hub","Beacon AI Centers Indus Project","Beacon AI Centers Indus"],"id":"beacon-ai-centers-indus","last_reviewed":"2026-10-09","location":{"admin1":"Alberta","admin2":"Rocky View County","country":"CA","lat":50.9434,"locality":"Indus","lon":-113.8072,"note":"Decimal coordinates given in the proponent's initial project description (legal land description in section 11-23-28-W4M, south of Township Road 232), rounded to four decimals.","precision":"site","source_ids":["s1","s4"]},"metrics":[{"applies_to":"campus","as_of":"2025-12-29","basis":"planned","metric":"power_capacity","note":"Four data halls with a stated power requirement of 300 MW each; the plant is designed to supply at least this much continuous power to them. The filing does not say whether the figure is IT load or total facility load.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1"],"unit":"MW","value":1200},{"applies_to":"campus","as_of":"2026-01-06","basis":"planned","metric":"power_capacity","note":"Maximum installed capacity: 100 gas reciprocating engines of about 4.6 MW each plus four combined-cycle blocks.","power_scope":"onsite_generation","qualifier":"approximately","source_ids":["s1","s2","s3"],"unit":"MW","value":1494},{"applies_to":"campus","as_of":"2025-12-29","basis":"planned","metric":"land_area","note":"Data centre campus area stated in the federal filing; the power plant footprint is about 45 acres within it.","qualifier":"exact","source_ids":["s1"],"unit":"acres","value":627.2},{"applies_to":"campus","as_of":"2025-09-18","basis":"planned","metric":"land_area","note":"Rocky View County describes the AI hub, and the land it redesignated for data centre use, as about 900 acres; this differs from the 627.2-acre campus in the federal filing.","qualifier":"approximately","source_ids":["s5","s6"],"unit":"acres","value":900},{"applies_to":"campus","as_of":"2025-12-29","basis":"planned","metric":"jobs_construction","qualifier":"up_to","source_ids":["s1"],"unit":"count","value":4500},{"applies_to":"campus","as_of":"2025-12-29","basis":"planned","metric":"jobs_permanent","qualifier":"exact","source_ids":["s1"],"unit":"count","value":300}],"milestones":[{"date":"2025-06-17","event":"zoning_approved","kind":"actual","note":"Council approved the Beacon AI Hub area structure plan; the land was redesignated to a special data centre district.","source_ids":["s4","s5","s6"]},{"date":"2026-01-19","event":"other","kind":"actual","note":"Alberta Utilities Commission posted notice of the gas plant application (proceeding 30524).","source_ids":["s5"]},{"date":"2026-03-10","event":"other","kind":"actual","note":"Impact Assessment Agency of Canada decided no further federal assessment of the power plant was required.","source_ids":["s2"]},{"date":"2026-Q2","event":"construction_started","kind":"planned","note":"Proponent schedule for civil works and foundations, before provincial approval was granted.","source_ids":["s1"]},{"date":"2027-Q3","event":"first_operational","kind":"planned","note":"Target commercial operation date for the plant and data halls.","source_ids":["s1"]}],"name":"Beacon AI Centers Indus campus","notes":"Status rests partly on Rocky View County's undated project page, which shows the gas plant application still under Alberta Utilities Commission review, so status_as_of is the date it was read (2026-10-09). The federal filing gives data centre details for information only; the data centre itself was not part of the federally reviewed power project. In July 2026 county council paused new applications to redesignate land for data centres; the report does not say whether this affects the already rezoned Beacon site.","parties":[{"name":"Beacon AI Centers","note":"The filing says Beacon develops the project through the project-specific entity Indus Power.","role":"developer","source_ids":["s1"]},{"name":"Indus Power Generation LP","note":"Proponent of the on-site gas plant; its general partner is Northbridge Power GPC Inc.","role":"power_supplier","source_ids":["s1","s2","s3"]},{"name":"Rocky View County","note":"Approved the area structure plan and land-use redesignation; participating in the provincial power plant review.","role":"government","source_ids":["s4","s5","s6"]},{"name":"AltaLink","note":"Owner of the 240 kV line the project proposes to tap, with interconnection at the Langdon 102S substation.","role":"utility","source_ids":["s1"]}],"power_sources":[{"description":"Dedicated on-site plant combining gas reciprocating engines and combined-cycle gas turbines; gas supply via NGTL/ATCO or TC Energy options was still being arranged.","source_ids":["s1","s3"],"type":"natural_gas_onsite"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260115230355/https://iaac-aeic.gc.ca/050/documents/p90121/164415E.pdf","id":"s1","published":"2025-12-29","publisher":"Indus Power Generation LP via Impact Assessment Agency of Canada registry","title":"Beacon AI Centers - Indus Project: Initial Project Description","type":"regulatory_filing","url":"https://iaac-aeic.gc.ca/050/documents/p90121/164415E.pdf"},{"accessed":"2026-10-09","id":"s2","published":null,"publisher":"Impact Assessment Agency of Canada","title":"Beacon AI Centers Indus Project (reference 90121)","type":"government","url":"https://iaac-aeic.gc.ca/050/evaluations/proj/90121"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260311013334/https://iaac-aeic.gc.ca/050/evaluations/document/164341","id":"s3","published":"2026-01-06","publisher":"Impact Assessment Agency of Canada","title":"Public notice: Beacon AI Centers Indus Project, comments invited on the summary of the initial project description","type":"government","url":"https://iaac-aeic.gc.ca/050/evaluations/document/164341"},{"accessed":"2026-10-09","id":"s4","published":"2026-02-13","publisher":"Rocky View County","title":"Rocky View County participates in Alberta Utilities Commission review of proposed Beacon AI Hub power plant","type":"government","url":"https://www.rockyview.ca/news-and-events/news/rocky-view-county-participates-alberta-utilities-commission-review-proposed"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Rocky View County","title":"Beacon AI Hub - Thermal Power Plant Application","type":"government","url":"https://www.rockyview.ca/build-plan-and-develop/planning/planning-projects-underway/beacon-ai-hub-area-structure-plan"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260313101503/https://www.rockyview.ca/news-and-events/news/rocky-view-county-affirms-commitment-responsible-ai-data-centre-development","id":"s6","published":"2025-09-18","publisher":"Rocky View County","title":"Rocky View County Affirms Commitment to Responsible AI Data Centre Development","type":"government","url":"https://www.rockyview.ca/news-and-events/news/rocky-view-county-affirms-commitment-responsible-ai-data-centre-development"},{"accessed":"2026-10-09","id":"s7","published":"2026-07-28","publisher":"The Canadian Press via BNN Bloomberg","title":"Councillors in rural county bordering Calgary vote to pause data centres","type":"news","url":"https://www.bnnbloomberg.ca/business/politics/2026/07/28/councillors-in-rural-county-bordering-calgary-vote-to-pause-data-centres/"}],"status":"announced","status_as_of":"2026-10-09","status_source_ids":["s5","s7"],"summary":"Beacon AI Centers plans an AI data centre campus about 3 km east of Calgary and 2 km northwest of the hamlet of Indus in Rocky View County, Alberta. Federal filings describe four data halls needing 300 MW each, supplied by an on-site gas-fired plant of about 1,494 MW built by the project entity Indus Power. The county approved the area structure plan in June 2025; the plant application is before the Alberta Utilities Commission, and the federal agency decided in March 2026 that no further federal assessment was needed. The proponent targeted commercial operation in Q3 2027.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"314d2a34-7e3f-5faa-8251-c7eda8caadde","s2":"14e5b2e8-3772-50b5-844e-c84bbe7c2bdc","s3":"7224e3fd-627d-5cc7-9901-082062869455","s4":"8ff0872f-8f2a-5986-908a-95d283fc7f39","s5":"33790c31-2bee-5340-957a-5ccbe793994e","s6":"f553b03d-c3e6-53e5-9f1a-6455c8f9046e","s7":"fd7cfb8e-cdee-54d7-b337-a945e05ff102"},"source_file":"datacenters/projects/beacon-ai-centers-indus.json","source_record_id":"beacon-ai-centers-indus","source_record_sha256":"31c79930812626de82d850ddcfbca7999819a420e79842f3f49e0e8817661aa2","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"5636ef89c413d8c5dafae870de69a96e134a3db571451a38f452970216f333b5"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-ef8be5d9da9f69e72683/#project-fbbfee97-55a0-5a4e-b000-282ff02a8a39 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/fbbfee97-55a0-5a4e-b000-282ff02a8a39.json
fc6dd688-fca0-5a7f-a6e9-54f9116607c5 | curated:lg-uplus-paju-aidc-campus:building-1 | vcc-site-0fd8442bfe3dc0c487e5 | curated:lg-uplus-paju-aidc-campus | LG Uplus Paju AIDC Building 1 | Korea, Republic of | KR | 37.8141 | 126.7561 | Point | campus | community_named_former_factory_representative_point_bound_to_official_redevelopment_parcel | preserve_Nominatim_source_lat_lon_for_OSM_way_469691383_and_bind_unique_factory_name_through_municipal_registry_and_LG_Uplus_notice | community_former_factory_campus_reference_point | community_source | campus_locator | The source-supplied representative point of former Heesung Electronics industrial building way469691383 locates the exact subsequently redeveloped Paju parcel1239-1. The operator name comes from the city landing page, not from the PDF. This is a historical physical-site locator only: not the current AIDC footprint, factory-survival assertion, entrance, surveyed point, campus boundary, neighboring LG Display1239 complex or June5 active-work extent. |  | Neither the OSM feature nor its Nominatim representative point supplies quantitative positional accuracy. Source coordinate digits are not survey precision. | 5cd22b84-8f94-5761-a01b-df911d39ffff | under_construction | 2026-06-05 | 130 | authoritative_physical_status_update | 49bad016-ecde-51d8-bc29-be1e20237b81 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://news.lguplus.com/?p=21965 | https://nominatim.openstreetmap.org/search?q=%ED%9D%AC%EC%84%B1%EC%A0%84%EC%9E%90&format=jsonv2&polygon_geojson=1 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-0fd8442bfe3dc0c487e5/#project-fc6dd688-fca0-5a7f-a6e9-54f9116607c5 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/fc6dd688-fca0-5a7f-a6e9-54f9116607c5.json
fe6f26cf-4be9-51a3-857e-fca7ee21726b | curated:xtx-markets-kajaani-data-center-campus:second-data-center | vcc-site-780d34f93b2e30c4ae73 | curated:xtx-markets-kajaani-data-center-campus | XTX Markets Kajaani Second Data Center | Finland | FI | 64.2372 | 27.6554 | Polygon | campus | official_coordinate_transform | nls_official_cadastral_parcel_polygon_as_campus_locator | official_cadastral_parcel_as_campus_locator | official_source | campus_locator | Exact reviewed NLS cadastral polygon for parcel 205-7-4-1, used only to locate the XTX Markets Kajaani parent campus and inherited by the Second Data Center project through the explicit project-to-campus link. It is not the DC2 location or footprint, either data-center building footprint, the current work extent, a verified complete campus boundary, a security boundary, or proof every square metre is developed. |  | The cadastral feature is authoritative parcel geometry but the reviewed response publishes no numeric survey-accuracy or horizontal-uncertainty value for this feature; transformed digits do not add accuracy. | 23365ee9-f538-56fe-acec-e41f43182ded | under_construction | 2026-06-25 | 110 | authoritative_physical_status_update | 77e79654-177b-53cf-9db4-8c5ad47c7754 | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by the v0.13 geometry batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed project power observation selected by this batch; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.bravida.se/en/press/press-releases/2026/bravida-finland-awarded-additional-installation-contract-for-xtx-markets-data-center-complex-in-kajaani/ | https://inspire-wfs.maanmittauslaitos.fi/inspire-wfs/cp/ows?service=WFS&version=2.0.0&request=GetFeature&typeNames=cp%3ACadastralParcel&outputFormat=application%2Fjson&CQL_FILTER=nationalCadastralReference%3D%2720500700040001%27 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-780d34f93b2e30c4ae73/#project-fe6f26cf-4be9-51a3-857e-fca7ee21726b | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/fe6f26cf-4be9-51a3-857e-fca7ee21726b.json
fe8ac418-224e-5ac7-b342-11689bcc613e | imported:semiconductor-atlas:provident-powerhouse-grand-prairie | vcc-site-910b8939869a2f993425 | imported:semiconductor-atlas:provident-powerhouse-grand-prairie | PowerHouse Grand Prairie campus (PowerHouse and Provident) | United States | US | 32.5069 | -97.0069 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | Coordinates are the Wikipedia centroid of Midlothian (s5), the mailing city in the state filing for Building 1 at 881 Miller Road (s4). The developers describe the site as just outside Grand Prairie in northern Ellis County. The street address was not geocoded. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 8199ea4f-93f5-5f57-b678-e54dc4cd96c5 | announced | 2026-04-02 | 194 | imported_documented_status | 02c1ae28-3060-58ea-9406-25af14f482bf | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"8199ea4f-93f5-5f57-b678-e54dc4cd96c5","notes":"A division of American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"provident-powerhouse-grand-prairie"},{"evidence_id":"d268be6b-155a-5b1b-afb5-736354789881","notes":"A division of American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"provident-powerhouse-grand-prairie"},{"evidence_id":"becd19ca-3ee2-5c7a-9e6f-61665f690bdb","notes":"A division of American Real Estate Partners (AREP).","party":"PowerHouse Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"provident-powerhouse-grand-prairie"},{"evidence_id":"8199ea4f-93f5-5f57-b678-e54dc4cd96c5","notes":"Dallas-based joint venture partner; this was the first project of the partnership.","party":"Provident Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"provident-powerhouse-grand-prairie"},{"evidence_id":"d268be6b-155a-5b1b-afb5-736354789881","notes":"Dallas-based joint venture partner; this was the first project of the partnership.","party":"Provident Data Centers","relationship_scope":"unknown","role":"developer","source_record_id":"provident-powerhouse-grand-prairie"},{"evidence_id":"02c1ae28-3060-58ea-9406-25af14f482bf","notes":"Owner entity named in the April 2026 state filing for Data Center Building 1.","party":"Prairie Ridge Phase 1 Owner LP","relationship_scope":"unknown","role":"owner","source_record_id":"provident-powerhouse-grand-prairie"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | Prairie Ridge Phase 1 Owner LP |  |  |  |  | https://www.tdlr.texas.gov/TABS/Projects/TABS2026016734 | https://powerhousedata.com/news/powerhouse-and-provident-rewrite-the-data-center-playbook-with-new-texas-hyperscale-campus | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve PowerHouse Grand Prairie campus (PowerHouse and Provident) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"provident-powerhouse-grand-prairie"},"record":{"aliases":["PowerHouse Grand Prairie","AREP Power House Grand Prairie"],"id":"provident-powerhouse-grand-prairie","last_reviewed":"2026-10-09","location":{"admin1":"Texas","admin2":"Ellis County","country":"US","lat":32.5069,"locality":"Midlothian","lon":-97.0069,"note":"Coordinates are the Wikipedia centroid of Midlothian (s5), the mailing city in the state filing for Building 1 at 881 Miller Road (s4). The developers describe the site as just outside Grand Prairie in northern Ellis County. The street address was not geocoded.","precision":"locality","source_ids":["s1","s4","s5"]},"metrics":[{"applies_to":"campus","as_of":"2025-02-25","basis":"planned","metric":"power_capacity","note":"Planned on-site switchyard capacity; the campus page calls it the maximum utility power.","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2","s3"],"unit":"MW","value":1800},{"applies_to":"phase","as_of":"2025-02-25","basis":"planned","metric":"power_capacity","note":"Described as already approved through ERCOT at announcement.","phase_label":"First power tranche","power_scope":"grid_connection","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":500},{"applies_to":"campus","as_of":"2025-02-25","basis":"reported","metric":"land_area","qualifier":"exact","source_ids":["s1","s2"],"unit":"acres","value":768},{"applies_to":"campus","as_of":"2026-10-09","basis":"reported","metric":"land_area","note":"Figure on PowerHouse's undated campus page, which is larger than the 768 acres announced in 2025.","qualifier":"exact","source_ids":["s3"],"unit":"acres","value":810},{"applies_to":"campus","as_of":"2025-02-25","basis":"planned","metric":"buildings","note":"Planned across three phases at announcement. The later campus page instead lists four building phases (10 buildings in each of the first two, 4 in each of the last two).","qualifier":"exact","source_ids":["s1","s2"],"unit":"count","value":24},{"applies_to":"campus","as_of":"2026-10-09","basis":"planned","metric":"floor_area","note":"Developable area stated on the undated campus page.","qualifier":"approximately","source_ids":["s3"],"unit":"sq_ft","value":8500000},{"applies_to":"phase","as_of":"2026-04-02","basis":"planned","metric":"floor_area","phase_label":"Data Center Building 1","qualifier":"exact","source_ids":["s4"],"unit":"sq_ft","value":224152},{"applies_to":"phase","as_of":"2026-04-02","basis":"reported","metric":"investment","note":"Estimated construction cost of the core and shell in a Texas Department of Licensing and Regulation accessibility registration; excludes fit-out and IT equipment.","phase_label":"Data Center Building 1","qualifier":"exact","source_ids":["s4"],"unit":"USD","value":72590278}],"milestones":[{"date":"2025-02-25","event":"announced","kind":"actual","note":"The developers said the site had been rezoned and that all required approvals and permits were in hand.","source_ids":["s1","s2"]},{"date":"2026-04-01","event":"construction_started","kind":"planned","note":"Scheduled start of Building 1 in the state filing, with completion scheduled for 1 April 2028. No report confirming work under way was found.","source_ids":["s4"]},{"date":"2026-05","event":"first_operational","kind":"planned","note":"Original target for energizing the first building, given at announcement.","source_ids":["s1"]},{"date":"2027-Q1","event":"first_operational","kind":"planned","note":"Later target on the campus page, which lists delivery in Q1 2027 alongside power delivery and construction delivery in Q4 2026.","source_ids":["s3"]}],"name":"PowerHouse Grand Prairie campus (PowerHouse and Provident)","notes":"Status is kept at announced because the only 2026 evidence is a state registration with scheduled dates; no report of construction under way, energization or a tenant was found. The campus page is undated (its footer and image file names point to 2025), so its figures carry the access date. Acreage and building counts differ between the 2025 announcement and the campus page.","parties":[{"name":"PowerHouse Data Centers","note":"A division of American Real Estate Partners (AREP).","role":"developer","source_ids":["s1","s2","s3"]},{"name":"Provident Data Centers","note":"Dallas-based joint venture partner; this was the first project of the partnership.","role":"developer","source_ids":["s1","s2"]},{"name":"Prairie Ridge Phase 1 Owner LP","note":"Owner entity named in the April 2026 state filing for Data Center Building 1.","role":"owner","source_ids":["s4"]}],"power_sources":[{"description":"Planned on-site 1.8 GW switchyard on the ERCOT grid, with a first 500 MW tranche approved through ERCOT.","source_ids":["s1","s2"],"type":"grid"}],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","id":"s1","published":"2025-02-25","publisher":"PowerHouse Data Centers","title":"PowerHouse and Provident Rewrite the Data Center Playbook with New Texas Hyperscale Campus","type":"company","url":"https://powerhousedata.com/news/powerhouse-and-provident-rewrite-the-data-center-playbook-with-new-texas-hyperscale-campus"},{"accessed":"2026-10-09","id":"s2","published":"2025-02-25","publisher":"Dallas Innovates","title":"Dallas' Provident Data Centers, Virginia's PowerHouse Partner on 'Hyperscale' North Texas Campus","type":"news","url":"https://dallasinnovates.com/dallas-provident-data-centers-virginias-powerhouse-partner-on-hyperscale-north-texas-campus/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"PowerHouse Data Centers","title":"PowerHouse Grand Prairie","type":"company","url":"https://powerhousedata.com/data-center/powerhouse-grand-prairie"},{"accessed":"2026-10-09","id":"s4","published":"2026-04-02","publisher":"Texas Department of Licensing and Regulation","title":"TABS2026016734: AREP Power House Grand Prairie, Data Center Building 1","type":"regulatory_filing","url":"https://www.tdlr.texas.gov/TABS/Projects/TABS2026016734"},{"accessed":"2026-10-09","id":"s5","published":null,"publisher":"Wikipedia","title":"Midlothian, Texas","type":"other","url":"https://en.wikipedia.org/wiki/Midlothian,_Texas"}],"status":"announced","status_as_of":"2026-04-02","status_source_ids":["s4"],"summary":"Hyperscale data center campus planned by a PowerHouse Data Centers and Provident Data Centers joint venture on 768 to 810 acres just outside Grand Prairie in northern Ellis County, Texas. The partners plan an on-site 1.8 GW switchyard, with a first 500 MW tranche approved through ERCOT, and 24 buildings in three phases at announcement. A state accessibility filing registered in April 2026 covers Data Center Building 1, a two-story 224,152 sq ft core and shell at 881 Miller Road with an estimated cost of about USD 72.6 million and a scheduled April 2026 to April 2028 build window.","workloads":[]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"8199ea4f-93f5-5f57-b678-e54dc4cd96c5","s2":"d268be6b-155a-5b1b-afb5-736354789881","s3":"becd19ca-3ee2-5c7a-9e6f-61665f690bdb","s4":"02c1ae28-3060-58ea-9406-25af14f482bf","s5":"2fef070b-6567-5f52-868a-04c75e9695ba"},"source_file":"datacenters/projects/provident-powerhouse-grand-prairie.json","source_record_id":"provident-powerhouse-grand-prairie","source_record_sha256":"e49a5624d8755cc13c5a33350b318e0f68a8d3fb712e50ccc4ad0996c3573d80","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"0da6c2ea909b84af9206de837090ec74a234cf9464da32e68cd32a53764580db"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-910b8939869a2f993425/#project-fe8ac418-224e-5ac7-b342-11689bcc613e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/fe8ac418-224e-5ac7-b342-11689bcc613e.json
fe92035e-3a00-5a85-b009-34fe9c2c545e | curated:dayone-kiverio-lahti-unnamed-data-center-campus:unnamed-construction-project | vcc-site-5a7d73c964538b72f14d | curated:dayone-kiverio-lahti-unnamed-data-center-campus | DayOne Kiveriö Unnamed Data Center Construction Project | Finland | FI | 60.9908 | 25.7039 | Point | campus | official_cadastral_referencePoint_transformed_to_WGS84 | exact_permit_parcel_address_join_then_NLS_nationalCadastralReference_filter_and_pyproj_3067_to_4326_always_xy | official_parcel_reference_point | official_source | campus_locator | Official provider-supplied reference point for the exact permit-bound cadastral parcel, used only to locate one DayOne Kiveriö campus. Not a calculated centroid, survey, entrance, active-work extent, building footprint or asserted complete campus boundary. The parcel and reference point are not reused from the rejected road, wholesaler or service-area coordinates. |  | No selected source quantifies this reference point's positional accuracy. Transformation-operation accuracy of 1 metre and numeric precision do not establish survey accuracy. | cdc8d295-dbe5-5ec1-98b5-2393692f2f2c | under_construction | 2026-08-11 | 63 | authoritative_physical_status_update | ef9a468b-9c54-53f4-bb18-126423de0d4e | recent_authoritative_physical_observation_plus_reviewed_site_locator | FALSE | not_reviewed_for_core_preview | unknown | not selected by this reviewed draft batch | unknown | not established by selected evidence |  | [] | not established by selected evidence | [] | [] | no typed power observation selected; not estimated | [] | no scoped annual-energy inputs selected; not estimated | [] | no scoped PUE or WUE observation selected | [5 empty] | https://www.srv.fi/srv-yrityksena/tyomaat/2984-lahden-datakeskus/tiedotteet/ | https://inspire-wfs.maanmittauslaitos.fi/inspire-wfs/cp/ows?service=WFS&version=2.0.0&request=GetFeature&typeNames=cp%3ACadastralParcel&outputFormat=application%2Fjson&CQL_FILTER=nationalCadastralReference%3D%2739800509660007%27 | [] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-5a7d73c964538b72f14d/#project-fe92035e-3a00-5a85-b009-34fe9c2c545e | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/fe92035e-3a00-5a85-b009-34fe9c2c545e.json
ffbda424-5468-5619-97e8-3a32b0522e79 | imported:semiconductor-atlas:edgeconnex-kyotanabe-greater-osaka | vcc-site-6fbf2c20aeb106991c61 | imported:semiconductor-atlas:edgeconnex-kyotanabe-greater-osaka | EdgeConneX Greater Osaka campus (Kagoya Tatara Campus, Kyotanabe) | Japan | JP | 34.8144 | 135.7678 | Point | project | imported_reference_point | imported_reference_point | locality | compiled_reference | locality_context | The releases name the Kagoya Tatara Campus and place it in Kyotanabe City through a quote from the city's mayor; no address is given. The point and the prefecture come from the Kyotanabe Wikipedia article, so the point marks the city rather than the site. |  | The source record provides no measured horizontal uncertainty; original coordinate precision and note are preserved. | 604f97e6-9edd-5e9c-b350-035f4b500542 | under_construction | 2026-03-18 | 209 | imported_documented_status | 604f97e6-9edd-5e9c-b350-035f4b500542 | imported_source_record | FALSE | not_reviewed | unknown | Not normalized from imported source record. | unknown | Not normalized from imported source record. |  | [] | Original workload labels are retained in project_details without inventing deployment scope or per-label source support. | [{"evidence_id":"604f97e6-9edd-5e9c-b350-035f4b500542","notes":"Backed by EQT Infrastructure, part of the investment organisation EQT.","party":"EdgeConneX","relationship_scope":"unknown","role":"developer","source_record_id":"edgeconnex-kyotanabe-greater-osaka"},{"evidence_id":"13b65ece-f1a8-5ac6-8475-abb4caf98391","notes":"Backed by EQT Infrastructure, part of the investment organisation EQT.","party":"EdgeConneX","relationship_scope":"unknown","role":"developer","source_record_id":"edgeconnex-kyotanabe-greater-osaka"}] | [] | Original power metrics are retained in project_details with their units, qualifiers, phases and scopes; no unscoped or additive capacity is inferred. | [] | No scoped annual-energy observation selected; not estimated. | [] | No scoped efficiency observation selected; not estimated. | [5 empty] | https://www.edgeconnex.com/news/press-releases/edgeconnex-commences-construction-of-200mw-ai-ready-hyperscale-campus-in-greater-osaka/ | https://www.edgeconnex.com/news/press-releases/edgeconnex-commences-construction-of-200mw-ai-ready-hyperscale-campus-in-greater-osaka/ | [{"identity_decision":{"decision":"unique_site","flags":["administrative_locator_not_project_geometry"],"rationale":"No matching named development in the 201-project release. Preserve EdgeConneX Greater Osaka campus (Kagoya Tatara Campus, Kyotanabe) as an independent source record; its locality locator does not itself establish a surveyed physical site.","source_record_id":"edgeconnex-kyotanabe-greater-osaka"},"record":{"aliases":["ITM01","Kagoya Tatara Campus","EdgeConneX Greater Osaka"],"id":"edgeconnex-kyotanabe-greater-osaka","last_reviewed":"2026-10-09","location":{"admin1":"Kyoto Prefecture","country":"JP","lat":34.81444,"locality":"Kyotanabe","lon":135.76778,"note":"The releases name the Kagoya Tatara Campus and place it in Kyotanabe City through a quote from the city's mayor; no address is given. The point and the prefecture come from the Kyotanabe Wikipedia article, so the point marks the city rather than the site.","precision":"locality","source_ids":["s1","s2","s3"]},"metrics":[{"applies_to":"campus","as_of":"2026-03-17","basis":"planned","metric":"power_capacity","note":"Described as 200 MW of power capacity; neither release says whether this is IT or facility power.","power_scope":"unspecified","qualifier":"exact","source_ids":["s1","s2"],"unit":"MW","value":200},{"applies_to":"campus","as_of":"2026-03-17","basis":"reported","metric":"land_area","note":"The Japanese release gives about 130,000 square metres as the site area; the English release says the campus spans 130,000 square metres.","qualifier":"approximately","source_ids":["s2","s1"],"unit":"hectares","value":13}],"milestones":[{"date":"2026-03","event":"construction_started","kind":"actual","note":"Groundbreaking for the first building, ITM01, reported in releases dated 17 and 18 March 2026.","source_ids":["s1","s2"]},{"date":"2028-Q1","event":"first_operational","kind":"planned","note":"Ready-for-service target for the first phase.","source_ids":["s1","s2"]}],"name":"EdgeConneX Greater Osaka campus (Kagoya Tatara Campus, Kyotanabe)","notes":"Only EdgeConneX's own English and Japanese releases were found for this campus; they carry different dates (17 and 18 March 2026). Kagoya Asset Management is described as EdgeConneX's partner on the project without a stated ownership or development role, and Kyotanabe's mayor is quoted congratulating the parties on the groundbreaking, so neither is listed as a party. The roughly 350 MW Greater Osaka (Kansai) total includes a separate second project and is not a figure for this campus. No investment amount, utility or power arrangement was disclosed. Kyotanabe coordinates and the prefecture come from Wikipedia (s3), used only for the location.","parties":[{"name":"EdgeConneX","note":"Backed by EQT Infrastructure, part of the investment organisation EQT.","role":"developer","source_ids":["s1","s2"]}],"power_sources":[],"schema_version":"1.0","sources":[{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260617074318/https://www.edgeconnex.com/news/press-releases/edgeconnex-commences-construction-of-200mw-ai-ready-hyperscale-campus-in-greater-osaka/","id":"s1","published":"2026-03-17","publisher":"EdgeConneX","title":"EdgeConneX Commences Construction of 200MW AI-Ready Hyperscale Campus in Greater Osaka","type":"company","url":"https://www.edgeconnex.com/news/press-releases/edgeconnex-commences-construction-of-200mw-ai-ready-hyperscale-campus-in-greater-osaka/"},{"accessed":"2026-10-09","archived_url":"https://web.archive.org/web/20260410204401/https://www.edgeconnex.com/news/press-releases/edgeconnex%E3%80%81%E9%96%A2%E8%A5%BF%E3%82%A8%E3%83%AA%E3%82%A2%E3%81%AB200mw%E3%81%AEai%E5%AF%BE%E5%BF%9C%E3%83%8F%E3%82%A4%E3%83%91%E3%83%BC%E3%82%B9%E3%82%B1%E3%83%BC%E3%83%AB%E3%82%AD%E3%83%A3/","id":"s2","published":"2026-03-18","publisher":"EdgeConneX","title":"EdgeConneX、関西エリアに200MWのAI対応ハイパースケールキャンパスの開発に着手","type":"company","url":"https://www.edgeconnex.com/news/press-releases/edgeconnex%e3%80%81%e9%96%a2%e8%a5%bf%e3%82%a8%e3%83%aa%e3%82%a2%e3%81%ab200mw%e3%81%aeai%e5%af%be%e5%bf%9c%e3%83%8f%e3%82%a4%e3%83%91%e3%83%bc%e3%82%b9%e3%82%b1%e3%83%bc%e3%83%ab%e3%82%ad%e3%83%a3/"},{"accessed":"2026-10-09","id":"s3","published":null,"publisher":"Wikipedia","title":"Kyōtanabe","type":"other","url":"https://en.wikipedia.org/wiki/Ky%C5%8Dtanabe"}],"status":"under_construction","status_as_of":"2026-03-18","status_source_ids":["s1","s2"],"summary":"EdgeConneX, a data center developer backed by EQT Infrastructure, began building a 200 MW AI-ready hyperscale campus in March 2026 on a site of about 130,000 square metres at the Kagoya Tatara Campus in Kyotanabe City, roughly 30 km from central Osaka. The company calls it its first data center campus in Japan. It is being developed in partnership with Kagoya Asset Management; the groundbreaking was for a first building named ITM01, and the first phase is targeted to be ready for service in the first quarter of 2028. EdgeConneX said it plans about 350 MW in total across Greater Osaka, including a second project announced in August 2025.","workloads":["ai_unspecified"]},"source_dataset":"semiconductor_atlas","source_evidence_ids":{"s1":"604f97e6-9edd-5e9c-b350-035f4b500542","s2":"13b65ece-f1a8-5ac6-8475-abb4caf98391","s3":"b67cf4a5-884f-5d6e-abde-e0e7a1b7d99a"},"source_file":"datacenters/projects/edgeconnex-kyotanabe-greater-osaka.json","source_record_id":"edgeconnex-kyotanabe-greater-osaka","source_record_sha256":"619d837902d48c8a51fdbfce5f4497b70709e4975695f25a0ed70d39a0659b60","source_repository_commit":"3d1d3434e4799ae8f9cf8ec9e7804ca1826f9c02","source_sha256":"e89b5db4e44d53f27e422e080352cc57c0fa3770c237f7b238dbb10325239fba"}] | https://kiankyars.github.io/datacenter-atlas/sites/vcc-site-6fbf2c20aeb106991c61/#project-ffbda424-5468-5619-97e8-3a32b0522e79 | https://kiankyars.github.io/datacenter-atlas/api/v1/projects/ffbda424-5468-5619-97e8-3a32b0522e79.json

## evidence
evidence_id | roles_json | project_ids_json | kind | title | source_url | publisher | source_family | license | attribution | published_at | retrieved_at | content_hash | publication_date_precision | content_hash_scope | source_record_id | source_local_id | source_record_sha256 | api_url | archive_url
0018bbb4-353b-533f-81ca-d19336a4c0f1 | ["imported:geometry","imported:record","metric:investment","metric:land_area","metric:power_capacity","milestone:announced","milestone:first_operational","power_source:grid","role:developer","role:utility"] | ["39dca169-c304-53a7-b2a6-15a9a914e4d1"] | company_disclosure | Pennsylvania Data Center Partners and PowerHouse Data Centers Launch Joint Venture to Build Next-Gen 1.35 GW Hyperscale Data Center Campus in Carlisle, Pennsylvania | https://powerhousedata.com/news/pennsylvania-data-center-partners-and-powerhouse-data-centers-launch-joint-venture-to-build-next-gen-1-35-gw-hyperscale-data-center-campus-in-carlisle-pennsylvania | PowerHouse Data Centers | powerhousedata.com | source-terms-not-recorded | PowerHouse Data Centers | 2025-07-15 | 2026-10-09 | 4cce16b5f9b795c626ef774ea74f6a004c8ff277db09faf71484031577a29f73 | day | source_record_projection | powerhouse-pennsylvania-digital-i-carlisle | s1 | 0c0cb2497e4d2856da48fa35254909b5de6811fcf8e5589d7ecbcec7bdadded3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0018bbb4-353b-533f-81ca-d19336a4c0f1.json | https://web.archive.org/web/20261009/https://powerhousedata.com/news/pennsylvania-data-center-partners-and-powerhouse-data-centers-launch-joint-venture-to-build-next-gen-1-35-gw-hyperscale-data-center-campus-in-carlisle-pennsylvania
001c0485-1e86-50ad-abbb-53ad2b354d72 | ["imported:record","imported:status","metric:power_capacity","milestone:first_operational","milestone:other","role:tenant"] | ["d87a919b-df32-53fa-bc01-47b7f6f1dce9"] | regulatory_filing | Core Scientific Q2 2026 earnings presentation (Form 8-K, Exhibit 99.2) | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-07-28 | 2026-10-09 | 7679598ab1cebc84c61e67b73e9fa454afe44ca5b45263f83714594f3a8127d0 | day | source_record_projection | core-scientific-muskogee | s4 | 27770cbed3a06baa8115f406673dbf040757ebfc6782e12fbac9b4ef314a02c5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/001c0485-1e86-50ad-abbb-53ad2b354d72.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm
0027957f-dfca-573e-80e3-dc902eddcf2c | ["imported:record","metric:investment","metric:jobs_permanent","milestone:expansion_announced","role:developer","role:government","role:utility"] | [] | government_record | Amazon continues Mississippi expansion, announcing plans to invest a total of $25 billion across the Magnolia State | https://governorreeves.ms.gov/amazon-continues-mississippi-expansion-announcing-plans-to-invest-a-total-of-25-billion-across-the-magnolia-state/ | Office of Governor Tate Reeves | governorreeves.ms.gov | source-terms-not-recorded | Office of Governor Tate Reeves | 2026-04-09 | 2026-10-09 | 028efcc68f72db37bbdb8983bb47fb1a06a2d2009d6013b4a8fccc98a457e8f8 | day | source_record_projection | aws-madison-county-mississippi | s5 | 2a8298712e096fd7bf05fb9d4b56811416a93af6563da82976dc55e2447c5769 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0027957f-dfca-573e-80e3-dc902eddcf2c.json | https://web.archive.org/web/20261009/https://governorreeves.ms.gov/amazon-continues-mississippi-expansion-announcing-plans-to-invest-a-total-of-25-billion-across-the-magnolia-state/
0048b025-5c07-5f60-82f2-78a73d462260 | ["context:site_distinctness","geometry"] | ["d6a6d399-4580-54f8-80de-1dc0854e4699"] | government_record | Butler County Engineer exact Trenton developer parcel geometry | https://gismaps.bceo.org/server/rest/services/Public/ParcelQuery/FeatureServer/0/query?where=UPPER%28OWNER%29%20LIKE%20%27%25TRENTON%20DATA%20CENTER%25%27&outFields=OBJECTID%2CPIN%2COWNER%2CLOCATION%2CACRES&returnGeometry=true&f=json | Butler County Engineer Office | root_round32_trenton | no-open-license-asserted | Butler County Engineer Office |  | 2026-09-10T00:00:52.207Z | 357f548f95aa183d15e6ceb893e2e915e93d7401086cd0a2295521ec7bd1ce46 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0048b025-5c07-5f60-82f2-78a73d462260.json | https://web.archive.org/web/20260910000052/https://gismaps.bceo.org/server/rest/services/Public/ParcelQuery/FeatureServer/0/query?where=UPPER%28OWNER%29%20LIKE%20%27%25TRENTON%20DATA%20CENTER%25%27&outFields=OBJECTID%2CPIN%2COWNER%2CLOCATION%2CACRES&returnGeometry=true&f=json
0058481e-68f2-56d6-b07f-aa9ccb773866 | ["context:geometry_identity","context:site_distinctness"] | ["9fe862f6-ace2-5f5d-9c90-486fa4622982"] | company_disclosure | Nxtra LOS1 project page links its named campus map | https://www.nxtraafrica.com/lagos-eko-atlantic | Nxtra Africa | africa_round7_nxtra | all-rights-reserved | Nxtra Africa |  | 2026-09-08T22:27:54.948Z | 5adc71123795f96370803ca98cdae90fe2c072f8b3cc190c981eb33f0e64db7d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0058481e-68f2-56d6-b07f-aa9ccb773866.json | https://web.archive.org/web/20260908222754/https://www.nxtraafrica.com/lagos-eko-atlantic
00756bbb-b1cd-54d5-9350-2a11b661673f | ["imported:geometry","imported:record","metric:investment","metric:power_capacity","milestone:announced","power_source:other","role:developer"] | ["ee6721e5-5463-5350-9b3d-fe2429103a70"] | news | Artificial Intelligence: U.S. firm Iozera to Invest $500 Mln in Data-center and AI Hub in Morocco | https://northafricapost.com/?p=77106 | The North Africa Post | northafricapost.com | source-terms-not-recorded | The North Africa Post | 2024-05-06 | 2026-10-09 | 6da303cc56cdc764ca6cf6a9a6c51cff134d800b773b1eb10994b28f5cfd4075 | day | source_record_projection | iozera-tetouan | s1 | 87e6610fa13f99a2575ddb73979b2eef0b94034f528904f24e02bb6e6a3dad23 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/00756bbb-b1cd-54d5-9350-2a11b661673f.json | https://web.archive.org/web/20261009/https://northafricapost.com/?p=77106
008ea865-8f97-5b92-ad7a-9b29569aa23a | ["imported:geometry","imported:record"] | ["917342c6-069b-5678-bf52-e27fcf933a5a"] | other | Ennis | https://en.wikipedia.org/wiki/Ennis | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | bd917b8d03b6a0c75d6c751f1a7ee1112e15f7be8bca684abadbe6fd61df3a84 | unknown | source_record_projection | art-data-centres-ennis | s4 | 57f07bb943f4af27c537241facc42eb84e0b74a40b0fa009ae04b4cd34279386 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/008ea865-8f97-5b92-ad7a-9b29569aa23a.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Ennis
00fc7415-5229-515f-8ed4-aa7207226c06 | ["imported:geometry","imported:record","imported:status","metric:jobs_construction","metric:land_area","power_source:natural_gas_onsite","role:developer"] | ["74d6b0be-d450-509d-a406-ddfed7ede756"] | news | Proposed AI data center near Evanston advances as Prometheus courts major tech clients | https://townlift.com/2026/06/proposed-ai-data-center-near-evanston-advances-as-prometheus-courts-major-tech-clients/ | TownLift | townlift.com | source-terms-not-recorded | TownLift | 2026-06-22 | 2026-10-09 | 3dc0d320aaec461c0c148ce7566867c6dd8837e7ccc44bbfa1069baf9ba1f2ea | day | source_record_projection | prometheus-hyperscale-evanston | s2 | 96fae3106ce00d84906fe415cb9a42d8ad8e78e863fa6a9a76f62c1a4430ca5c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/00fc7415-5229-515f-8ed4-aa7207226c06.json | https://web.archive.org/web/20261009/https://townlift.com/2026/06/proposed-ai-data-center-near-evanston-advances-as-prometheus-courts-major-tech-clients/
01132beb-2c9b-5d8e-8e2c-bf52eb2346d8 | ["imported:record","metric:land_area","metric:power_capacity","milestone:expansion_announced"] | ["d87a919b-df32-53fa-bc01-47b7f6f1dce9"] | trade_press | Core Scientific's Muskogee bet: can crypto-era infrastructure fuel AI? | https://www.datacenterknowledge.com/build-design/core-scientific-bets-on-1-5-gw-ai-campus-in-oklahoma | Data Center Knowledge | www.datacenterknowledge.com | source-terms-not-recorded | Data Center Knowledge | 2026-05-07 | 2026-10-09 | c172d899d588a3e2d848fd8d400d54fff19511baaa18c7e84d2f07021911ae94 | day | source_record_projection | core-scientific-muskogee | s6 | 27770cbed3a06baa8115f406673dbf040757ebfc6782e12fbac9b4ef314a02c5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/01132beb-2c9b-5d8e-8e2c-bf52eb2346d8.json | https://web.archive.org/web/20261009/https://www.datacenterknowledge.com/build-design/core-scientific-bets-on-1-5-gw-ai-campus-in-oklahoma
01200511-2e49-573b-bd74-ab830c2253b5 | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:investment","metric:jobs_permanent","milestone:construction_started","milestone:fully_operational","milestone:zoning_approved","role:developer","role:government"] | ["8d08b021-e457-5102-9ef2-33528ad786d1"] | news | 'We want transparency before approvals happen': Residents oppose proposed $11 billion Amazon data center | https://fox32chicago.com/news/hobart-approves-11b-amazon-data-center-details-still-unclear | FOX 32 Chicago | fox32chicago.com | source-terms-not-recorded | FOX 32 Chicago | 2026-02-05 | 2026-10-09 | e59aaf3f29a20f5a7e17367f8ea4cf1487d28672d863f2a0a32476ec162f5f05 | day | source_record_projection | aws-hobart-indiana | s3 | 51fd6e547d8fd5c8eaa8837b69b75043041b5ae8f9bec2a94b1b95328b7c679b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/01200511-2e49-573b-bd74-ab830c2253b5.json | https://web.archive.org/web/20261009/https://fox32chicago.com/news/hobart-approves-11b-amazon-data-center-details-still-unclear
0138ff1f-f3bd-5214-a41a-c9f9d7e01ed2 | ["context:site_distinctness"] | ["e8a1add0-19fb-5196-ae75-34353e7d580b"] | company_disclosure | Firmus September 8 portfolio: operating-site caveat, not new-hall completion | https://firmus.co/newsroom/firmus-surpasses-900-mw-contracted-capacity-adds-openai-as-anchor-customer-and-expands-into-malaysia | Firmus Technologies | europe_round31_firmus_st_leonards | no-open-license-asserted | Firmus Technologies | 2026-09-08 | 2026-09-09T23:35:02.848Z | e7b2a3b2039b7e2d8bd1ff6cdafabb8f4c9adbf2e0d8974595098e81c448ae40 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0138ff1f-f3bd-5214-a41a-c9f9d7e01ed2.json | https://web.archive.org/web/20260909233502/https://firmus.co/newsroom/firmus-surpasses-900-mw-contracted-capacity-adds-openai-as-anchor-customer-and-expands-into-malaysia
0176052f-124b-5bf9-b361-a5c97cb98b62 | ["physical_status"] | ["8f8c241d-ee6b-5182-8a76-ebb101a3f4c2"] | company_disclosure | Verne begins construction of the first 70 MW on its data center campus in Mäntsälä | https://www.verne.co/news/news-verne-begins-construction-of-the-first-70-mw-on-its-data-center-campus-in-m%C3%A4nts%C3%A4l%C3%A4 | Verne | verne_news | all-rights-reserved | Verne | 2026-06-17 | 2026-07-21T00:05:01Z | 2ec376832ffe1fb1c1313375cebc197834b657cec18beec6df37dc2152795ebc | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0176052f-124b-5bf9-b361-a5c97cb98b62.json | https://web.archive.org/web/20260721000501/https://www.verne.co/news/news-verne-begins-construction-of-the-first-70-mw-on-its-data-center-campus-in-m%C3%A4nts%C3%A4l%C3%A4
01789a58-fb70-56f6-bfe2-532d7aadf6fc | ["context:site_distinctness"] | ["c789668b-ecf3-53b2-b23c-44151e199317"] | openstreetmap | The exact 25 Indwe Street address query returns house node12419413360 at the northern edge of the named M3 campus feature | https://nominatim.openstreetmap.org/search?q=25%20Indwe%20Street%20West%20Footscray&format=jsonv2&polygon_geojson=1 | OpenStreetMap contributors / Nominatim | nextdc_m3_independent_locator_review | ODbL-1.0 | OpenStreetMap contributors / Nominatim |  | 2026-09-08T21:10:13Z | fc15564e341087352debcc3eff493e822255c7e21e2e76444d6430f74eeb9546 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/01789a58-fb70-56f6-bfe2-532d7aadf6fc.json | https://web.archive.org/web/20260908211013/https://nominatim.openstreetmap.org/search?q=25%20Indwe%20Street%20West%20Footscray&format=jsonv2&polygon_geojson=1
01b458cf-d4e4-5032-bd65-3afdc46856b8 | ["imported:geometry","imported:record","imported:status","metric:investment","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:government","role:utility"] | ["9dbfd718-7b41-58b1-bb46-0138b96aeca8"] | company_disclosure | Kentucky PSC Approves 482 MW Power Agreement for TeraWulf's Justified Data Campus | https://investors.terawulf.com/news-events/press-releases/detail/145/kentucky-psc-approves-482-mw-power-agreement-for-terawulfs-justified-data-campus | TeraWulf | investors.terawulf.com | source-terms-not-recorded | TeraWulf | 2026-08-24 | 2026-10-09 | 3d07d65f0b1f48a1dd73eec327d3c1a80aabf310eca034d6425f9f7621978db5 | day | source_record_projection | terawulf-justified-data-hawesville | s4 | 7db40d44894208f4e792a562ea9403ac682100e2515b0c7715e1d07e0ca4a4e7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/01b458cf-d4e4-5032-bd65-3afdc46856b8.json | https://web.archive.org/web/20261009/https://investors.terawulf.com/news-events/press-releases/detail/145/kentucky-psc-approves-482-mw-power-agreement-for-terawulfs-justified-data-campus
01d2faf8-1fe2-5401-9411-3486a52fa477 | ["context:site_distinctness","geometry"] | ["8dbc82d0-1a4d-5d8e-955e-c5e4973ea19e"] | government_record | Census public-use statement and geographic-product citation guidance | https://www.census.gov/about/policies/citation.html | U.S. Census Bureau | americas_round11_flexential_parker | no-open-redistribution-license-asserted | U.S. Census Bureau |  | 2026-09-09T00:30:24.125Z | cdd8cb1cb40f643b2e8bc201673ef8e2cf1d0c50bb5cc8e8a4a29042fac2eb27 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/01d2faf8-1fe2-5401-9411-3486a52fa477.json | https://web.archive.org/web/20260909003024/https://www.census.gov/about/policies/citation.html
020ae58c-6caf-51af-ba92-3ec539c5f030 | ["imported:geometry","imported:record","imported:status","metric:power_capacity","milestone:construction_started","milestone:first_operational","power_source:other","role:developer"] | ["016877e7-a475-5ebe-9219-0ac699cfff53"] | company_disclosure | HUMAIN partners with DataVolt to jointly develop 100MW of a 360MW AI data center project in NEOM | https://www.neom.com/en-us/newsroom/HUMAIN-and-DataVolt-to-develop-AI-data-center-in-NEOM | NEOM | www.neom.com | source-terms-not-recorded | NEOM | 2026-08-31 | 2026-10-09 | 9571fe0f86cd8013d9e0a1846b267dfa4f9aa2a0ba1a7579c2905417f8bf5b16 | day | source_record_projection | datavolt-oxagon | s2 | 55133dd6d75ca52eb0ee78922496756fb284d18ccf52ac00be1955a870a6a561 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/020ae58c-6caf-51af-ba92-3ec539c5f030.json | https://web.archive.org/web/20261009/https://www.neom.com/en-us/newsroom/HUMAIN-and-DataVolt-to-develop-AI-data-center-in-NEOM
02397198-c326-5ccf-af85-e38655c99fab | ["imported:record","metric:power_capacity","milestone:construction_started","milestone:first_operational","role:owner","role:tenant"] | ["0f5f4fcc-53c4-53d0-9795-2a387d195364"] | analyst_report | Microsoft Fairwater Wisconsin | https://epoch.ai/data/ai-data-centers/directory/microsoft-fairwater-wisconsin | Epoch AI | epoch.ai | source-terms-not-recorded | Epoch AI | 2026-10-05 | 2026-10-09 | 53f02c11078e39dd9e0f9d16de910ec01cab184f84061fce6e4f0154622ef50b | day | source_record_projection | microsoft-fairwater-mount-pleasant | s8 | 24656e656bf4cdff0af525c80e7f73c6f32adc9cbc3eecf6bacf0ff2abf770fa | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/02397198-c326-5ccf-af85-e38655c99fab.json | https://web.archive.org/web/20261009/https://epoch.ai/data/ai-data-centers/directory/microsoft-fairwater-wisconsin
029f0c50-dc53-50c2-a0bd-44f17b527093 | ["imported:record","imported:status","milestone:other","role:government"] | ["5d11dbb6-e8aa-5602-9c7c-8997b1c620c1"] | news | EU Commission approves Khazna–ENI joint venture, says it does “not raise competition concerns” | https://www.eunews.it/en/2026/08/10/eu-commission-approves-khazna-eni-joint-venture-says-it-does-not-raise-competition-concerns/ | Eunews | www.eunews.it | source-terms-not-recorded | Eunews | 2026-08-10 | 2026-10-09 | bff1f288e495deeb21f303e2c0108348c73de88ce7c2469bf694bc27f131603e | day | source_record_projection | eni-khazna-ferrera-erbognone | s4 | a0cb3643305f3a5a888c331dde151b57fce4ada563e49634d96a348a6f0ea568 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/029f0c50-dc53-50c2-a0bd-44f17b527093.json | https://web.archive.org/web/20261009/https://www.eunews.it/en/2026/08/10/eu-commission-approves-khazna-eni-joint-venture-says-it-does-not-raise-competition-concerns/
02c1ae28-3060-58ea-9406-25af14f482bf | ["imported:geometry","imported:record","imported:status","metric:floor_area","metric:investment","milestone:construction_started","role:owner"] | ["fe8ac418-224e-5ac7-b342-11689bcc613e"] | regulatory_filing | TABS2026016734: AREP Power House Grand Prairie, Data Center Building 1 | https://www.tdlr.texas.gov/TABS/Projects/TABS2026016734 | Texas Department of Licensing and Regulation | www.tdlr.texas.gov | source-terms-not-recorded | Texas Department of Licensing and Regulation | 2026-04-02 | 2026-10-09 | 28a939c1aff8fa36fd1e0e71d902fead1f3611751ed9184628aaa3e5437102fe | day | source_record_projection | provident-powerhouse-grand-prairie | s4 | e49a5624d8755cc13c5a33350b318e0f68a8d3fb712e50ccc4ad0996c3573d80 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/02c1ae28-3060-58ea-9406-25af14f482bf.json | https://web.archive.org/web/20261009/https://www.tdlr.texas.gov/TABS/Projects/TABS2026016734
0319c9a2-0161-5f88-ad38-3fd3aa0e3ea3 | ["physical_status"] | ["38033ec9-dbd8-56bb-8a35-0fa91dd284e2"] | company_disclosure | Ten Brinke Data Center Spata current-project page | https://www.tenbrinke.com/en/projects/current-projects/current-projects-details/data-center-spata-26-1052-gr.html | Ten Brinke Group | ten_brinke_current_project_pages | all-rights-reserved | Ten Brinke Group |  | 2026-07-21T17:05:00Z | 9ef57bbcb1517843d3e2e0f399d645147433f9896b1ece41f062cff8c5273c1a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0319c9a2-0161-5f88-ad38-3fd3aa0e3ea3.json | https://web.archive.org/web/20260721170500/https://www.tenbrinke.com/en/projects/current-projects/current-projects-details/data-center-spata-26-1052-gr.html
0328fcce-2c60-5546-ac42-9f861ed8f9e1 | ["imported:geometry","imported:record"] | ["94562977-e3af-5f59-bee1-896ee8db20f6"] | other | Pantex Plant | https://en.wikipedia.org/wiki/Pantex_Plant | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 181cb64863654d0a3c741d608198a5aeb5323c71aecbb0ad0b224217d383bba4 | unknown | source_record_projection | fermi-america-hypergrid-amarillo | s5 | 2784250e9a1dd9f679638c54fd185e63aec4254906feee0f129ab485698ebe1c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0328fcce-2c60-5546-ac42-9f861ed8f9e1.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Pantex_Plant
0348bc9b-365d-5081-95c5-5c40abc26114 | ["imported:record","imported:status","metric:investment","metric:land_area","milestone:announced","role:developer","role:owner"] | ["3641032c-9acd-5840-b94b-beab26a1ce0d"] | trade_press | Amazon earmarks $6b for third data center campus in northwest Louisiana | https://irei.com/news/amazon-earmarks-6b-for-third-data-center-campus-in-northwest-louisiana/ | Institutional Real Estate, Inc. | irei.com | source-terms-not-recorded | Institutional Real Estate, Inc. | 2026-08-27 | 2026-10-09 | 7d35ca7e1590a359210b7619e4d69450db2ecdf4905bcfe6162c5c34f9da6478 | day | source_record_projection | stack-amazon-resilient-technology-park-shreveport | s5 | 2237bb64e77771c65a9e25a502b027659ad4492ebb5afaf66d9e21861ce63b15 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0348bc9b-365d-5081-95c5-5c40abc26114.json | https://web.archive.org/web/20261009/https://irei.com/news/amazon-earmarks-6b-for-third-data-center-campus-in-northwest-louisiana/
0348daa4-b3cf-562b-97d3-9a49949647d2 | ["context:site_distinctness","geometry"] | ["c9b6bff7-09a3-599b-9c8c-49243461c0fb"] | openstreetmap | Named new Technologiezentrum Laufenburg community locator | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bnwr%5B%22name%22~%22FlexBase%7CTechnologiezentrum%7CSwissgrid%22%2Ci%5D%2847.52%2C8.03%2C47.59%2C8.1%29%3Bout%20meta%20center%3B | OpenStreetMap contributors via Overpass | europe_round5_flexbase | ODbL-1.0 | OpenStreetMap contributors via Overpass |  | 2026-09-08T21:56:53Z | 285142b0fcf5f2e5040c09d3629a1143343083162db89afe589b785c0a6f3bd1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0348daa4-b3cf-562b-97d3-9a49949647d2.json | https://web.archive.org/web/20260908215653/https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bnwr%5B%22name%22~%22FlexBase%7CTechnologiezentrum%7CSwissgrid%22%2Ci%5D%2847.52%2C8.03%2C47.59%2C8.1%29%3Bout%20meta%20center%3B
0357dcf6-dd2c-51fe-b107-8c9b253f17ec | ["context:site_distinctness","geometry"] | ["1404f5cd-04ee-57ea-8f73-91992fea0552"] | openstreetmap | Exact named Meta Richland Parish Data Center Nominatim point | https://nominatim.openstreetmap.org/search?q=Meta%20Richland%20Parish&countrycodes=us&format=jsonv2&polygon_geojson=1 | OpenStreetMap contributors via Nominatim | meta_round10_independent_review | ODbL-1.0 | OpenStreetMap contributors via Nominatim |  | 2026-09-08T23:44:16Z | 619548b627d084a63f05a776ea734cd1c360f4f686b6f58f56feed7d59cc6243 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0357dcf6-dd2c-51fe-b107-8c9b253f17ec.json | https://web.archive.org/web/20260908234416/https://nominatim.openstreetmap.org/search?q=Meta%20Richland%20Parish&countrycodes=us&format=jsonv2&polygon_geojson=1
035cc4b0-57d1-5e19-8842-07ccc8b6f5ea | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","role:builder","role:developer"] | ["4f8a32cf-b64b-51b4-8758-368320eb441d"] | news | Al Yamama takes the infrastructure contract for Humain's 6 GW Riyadh AI campus | https://enterpriseam.com/ksa/2026/09/27/al-yamama-takes-the-infrastructure-contract-for-humains-6-gw-riyadh-ai-campus/ | Enterprise AM | enterpriseam.com | source-terms-not-recorded | Enterprise AM | 2026-09-27 | 2026-10-09 | df48d41eadb9388020ba5b06aa249a82fd2e98c65c311f108746cca85eb816c5 | day | source_record_projection | humain-al-saad-riyadh | s3 | 96bc082928e663285a75443429bde24b04b1e06b6936ea2388084e9d91203d90 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/035cc4b0-57d1-5e19-8842-07ccc8b6f5ea.json | https://web.archive.org/web/20261009/https://enterpriseam.com/ksa/2026/09/27/al-yamama-takes-the-infrastructure-contract-for-humains-6-gw-riyadh-ai-campus/
03627a5f-061f-575a-8f9f-a0431558c660 | ["context:site_distinctness","geometry"] | ["8dbc82d0-1a4d-5d8e-955e-c5e4973ea19e"] | government_record | Census exact match for Flexential Parker's official postal address | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=15255%20Compark%20Blvd%2C%20Englewood%2C%20CO%2080112&benchmark=Public_AR_Current&format=json | U.S. Census Bureau | americas_round11_flexential_parker | no-open-redistribution-license-asserted | U.S. Census Bureau |  | 2026-09-09T00:26:55.764Z | 7ed8e9c0c7bc92cd70d8d260f8da628caf4c11273363f20a3df08e232e019df9 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/03627a5f-061f-575a-8f9f-a0431558c660.json | https://web.archive.org/web/20260909002655/https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=15255%20Compark%20Blvd%2C%20Englewood%2C%20CO%2080112&benchmark=Public_AR_Current&format=json
0368978b-07f1-5d7b-b5e8-3c25ccf751a8 | ["imported:record","imported:status","metric:power_capacity","milestone:first_operational","milestone:other","role:developer","role:tenant"] | ["8ce04eb2-b1ed-5375-a685-122f79fc2ee6"] | regulatory_filing | Core Scientific Q2 2026 earnings presentation (Form 8-K, Exhibit 99.2) | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-07-28 | 2026-10-09 | b7c850c632833f1b2f81974e679136079b442d95d94aab89afd1e5d6d74fb504 | day | source_record_projection | core-scientific-pecos | s4 | ab37ccfdcc0bc48d95f588d7a62361846b812822a0cd61b3d36fc6ae2dea2784 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0368978b-07f1-5d7b-b5e8-3c25ccf751a8.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm
036fc2ba-eaa4-573c-90ba-1d7351a1e086 | ["imported:record","imported:status","metric:power_capacity","milestone:first_operational","milestone:other"] | ["384a401d-cc7f-52e4-9ae3-218a378995b9"] | trade_press | Khazna breaks ground on new UAE data centre projects | https://guest.meed.com/?p=12676 | MEED | guest.meed.com | source-terms-not-recorded | MEED | 2025-04-22 | 2026-10-09 | 3702a4e1cf33de3d74459a4a9013e7cab56d20763c592da11fa51c957b29d9b3 | day | source_record_projection | khazna-ajman | s3 | 92a643d476e98c5addb8185cc1322ba283996fcbede435884f9449965f68ea71 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/036fc2ba-eaa4-573c-90ba-1d7351a1e086.json | https://web.archive.org/web/20261009/https://guest.meed.com/?p=12676
037f649a-0355-578e-b423-6ce6f1d6d63c | ["imported:record","milestone:other","role:government"] | ["bb1b28fd-610b-5739-b928-e44f21cb6f1b"] | government_record | Standing Decision: Sturgeon Lake Cree Nation v Designated Director under the Water Act, re: Municipal District of Greenview No. 16, 2026 ABEAB 9 | https://www.eab.gov.ab.ca/media/r2slqi1d/eab-25-014-md-of-greenview-final.pdf | Alberta Environmental Appeals Board | www.eab.gov.ab.ca | source-terms-not-recorded | Alberta Environmental Appeals Board | 2026-04-17 | 2026-10-09 | 4322415ee998e476fffe7d5017d2d436fac74cc18af62440464323e3bf2d15e7 | day | source_record_projection | wonder-valley-alberta | s6 | 8362b04814249174419268d40122ca73605913dfcf84412d960be5265857e94c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/037f649a-0355-578e-b423-6ce6f1d6d63c.json | https://web.archive.org/web/20261009/https://www.eab.gov.ab.ca/media/r2slqi1d/eab-25-014-md-of-greenview-final.pdf
03b9ee73-7cf3-53a7-9660-81544f5ee935 | ["context:site_distinctness","geometry"] | ["546bf83f-2bb4-5539-b576-6b7100981420"] | government_record | County web-map public access and absent license terms | https://maps.co.ellis.tx.us/portal/sharing/rest/content/items/699ad5fa2c004d0d972f22f416747072?f=json | Ellis County, Texas GIS | americas_round29_databank_red_oak | no-open-license-asserted | Ellis County, Texas GIS |  | 2026-09-09T11:22:04.203Z | 43d67520f6185653093115ed2e706a829d3d4bd129a8cf30b57bf3354f1b40f8 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/03b9ee73-7cf3-53a7-9660-81544f5ee935.json | https://web.archive.org/web/20260909112204/https://maps.co.ellis.tx.us/portal/sharing/rest/content/items/699ad5fa2c004d0d972f22f416747072?f=json
03d2d93d-6216-5214-a952-7c6399432079 | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:owner"] | ["b02620fe-58af-53a3-91fc-855e2454512c"] | regulatory_filing | Bitdeer Reports Unaudited Financial Results for the Second Quarter of 2026 (Form 6-K exhibit 99.1) | https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm | Bitdeer Technologies Group via SEC EDGAR | www.sec.gov | source-terms-not-recorded | Bitdeer Technologies Group via SEC EDGAR | 2026-08-10 | 2026-10-09 | 210af551f11c37804318c05eb71dd90774716ef4ffe65c5cc0b910e616135c14 | day | source_record_projection | bitdeer-weathersfield-ohio | s3 | 6873998ecf110e750fa0194050d1a7f43fadc62158d613faef7b8fe7d3b8dc9b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/03d2d93d-6216-5214-a952-7c6399432079.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm
043916cc-e7ce-5a3d-a8a7-d3dc7bd28038 | ["context:site_distinctness","geometry"] | ["100cf064-1cae-5dba-a4d9-6c4ae35152ec"] | government_record | Ministry of Justice cadastral data custom terms | https://www.geospatial.jp/ckan/dataset/fc3b0593-ce9e-40d1-aa33-94382d5f0da1/resource/47871bf1-4c85-48f7-a8fe-b27c6643c1c5/download/license.pdf | Ministry of Justice, Japan | aigid_moj_cadastral_reference | MOJ-map-data-custom-terms-2023-01-23 | Ministry of Justice, Japan; AIGID conversion; Data Center Atlas selection and display-anchor derivation |  | 2026-09-08T21:44:42.457Z | 275914c735b19cc7a274a13aac22e0c08378269d9d80f26f6b285aca32367b99 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/043916cc-e7ce-5a3d-a8a7-d3dc7bd28038.json | https://web.archive.org/web/20260908214442/https://www.geospatial.jp/ckan/dataset/fc3b0593-ce9e-40d1-aa33-94382d5f0da1/resource/47871bf1-4c85-48f7-a8fe-b27c6643c1c5/download/license.pdf
043bbd43-bda2-54d9-97f7-697c718363a4 | ["imported:geometry","imported:record","imported:status","metric:investment","metric:jobs_permanent","metric:land_area","milestone:announced","milestone:construction_started","milestone:zoning_approved","power_source:other","role:developer","role:government","role:owner"] | ["1369aebb-7496-56a6-9260-159cd3a37283"] | trade_press | Meta ultima en Talavera un centro de datos de 1.000 M€ que se abastecerá de agua del Tajo por la red municipal | https://www.iagua.es/noticias/redaccion-iagua/meta-ultima-en-talavera-un-centro-de-datos-de-1-000-me-que-se-abastecera-de-agua-del-tajo-por-la-red-municipal | iAgua | www.iagua.es | source-terms-not-recorded | iAgua | 2026-08-28 | 2026-10-09 | 887cc1f2d98dc6fcc90a57b2b78ba11131653e6111c84cf43ce1d067add27687 | day | source_record_projection | meta-talavera-de-la-reina | s1 | d9ae0a11c63a4d533b2e1fb63d37634e7e84f2e088f00911d1e92b36506c02f5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/043bbd43-bda2-54d9-97f7-697c718363a4.json | https://web.archive.org/web/20261009/https://www.iagua.es/noticias/redaccion-iagua/meta-ultima-en-talavera-un-centro-de-datos-de-1-000-me-que-se-abastecera-de-agua-del-tajo-por-la-red-municipal
0449f053-7fad-5be9-a045-a9429c9b9a0a | ["imported:record","imported:status","metric:floor_area","metric:investment","milestone:construction_started","milestone:first_operational","power_source:grid","role:operator","role:utility"] | ["e375d86c-75a4-53f3-a80e-31aa6f32b616"] | news | Meta opens new AI data center in Kuna, hopes to become "water positive" by 2030 | https://idahonews.com/news/local/meta-opens-new-ai-data-center-in-kuna-hopes-to-become-water-positive | KBOI 2 (CBS2 Idaho News) | idahonews.com | source-terms-not-recorded | KBOI 2 (CBS2 Idaho News) | 2026-09-03 | 2026-10-09 | 4239f9f3796acbb708230d939eac4f4ab2eedef0732f34591a3440c0a62eb9f3 | day | source_record_projection | meta-kuna-idaho | s5 | 8d1d811407ffc4368350c4dddfc8d4d5342b4e80a906d03d1040c846bd80f215 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0449f053-7fad-5be9-a045-a9429c9b9a0a.json | https://web.archive.org/web/20261009/https://idahonews.com/news/local/meta-opens-new-ai-data-center-in-kuna-hopes-to-become-water-positive
0479f072-9b63-51b5-bdf7-80d627d47394 | ["imported:record","imported:status","metric:buildings","metric:power_capacity","milestone:construction_started","milestone:first_operational","role:tenant"] | ["304e9b81-f1b5-5a80-8ad5-6f46e12f5a85"] | analyst_report | EcoDataCenter 2 (AI data center directory) | https://epoch.ai/data/ai-data-centers/directory/ecodatacenter-2 | Epoch AI | epoch.ai | source-terms-not-recorded | Epoch AI | 2026-10-05 | 2026-10-09 | 3a6d44e23f59d37cbae5973101800db3eb2c9cdb26991b341e3b47069c157183 | day | source_record_projection | ecodatacenter-borlange | s5 | 553c6701161532f38f3aefda2f0854ee4f3382deb968866b9e6120abf75060c7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0479f072-9b63-51b5-bdf7-80d627d47394.json | https://web.archive.org/web/20261009/https://epoch.ai/data/ai-data-centers/directory/ecodatacenter-2
047b4c1b-72aa-5de6-b677-d5ba01d3a2a3 | ["context:site_distinctness","geometry"] | ["337ace90-652d-52fe-a856-fe9b04b5966f"] | openstreetmap | Exact named Meta El Paso Data Center Nominatim point | https://nominatim.openstreetmap.org/search?q=Meta%20El%20Paso&countrycodes=us&format=jsonv2&polygon_geojson=1 | OpenStreetMap contributors via Nominatim | meta_round10_independent_review | ODbL-1.0 | OpenStreetMap contributors via Nominatim |  | 2026-09-08T23:44:15Z | ca177512cb6cc28ac6c912853387d38829e10c0899c8cd3eeeeab4ec2fb505c5 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/047b4c1b-72aa-5de6-b677-d5ba01d3a2a3.json | https://web.archive.org/web/20260908234415/https://nominatim.openstreetmap.org/search?q=Meta%20El%20Paso&countrycodes=us&format=jsonv2&polygon_geojson=1
04a7d918-5856-59fd-bbaf-8712a56bbc52 | ["imported:record","metric:buildings","metric:floor_area","metric:investment","metric:land_area","milestone:construction_started","milestone:first_operational","milestone:fully_operational","role:developer","role:tenant"] | ["126f2c37-cadc-5f20-9e3c-e544d70b5c37"] | trade_press | Vantage Data Centers breaks ground on data center campus in Texas | https://w.media/vantage-data-centers-breaks-ground-on-data-center-campus-in-texas/ | W.Media | w.media | source-terms-not-recorded | W.Media | 2025-12-16 | 2026-10-09 | 5dcabfd26b2a156774cd9cdab01c6f52fc927f8f60fe10f374c5dc9bc0e8a0e6 | day | source_record_projection | openai-stargate-shackelford-county | s3 | d7f00a3af4692eb8b87a8fe8ff934e44ef3d783701c67872ad62cb1f21703743 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/04a7d918-5856-59fd-bbaf-8712a56bbc52.json | https://web.archive.org/web/20261009/https://w.media/vantage-data-centers-breaks-ground-on-data-center-campus-in-texas/
04bdf086-bc27-5e07-917a-c52bd1c94e28 | ["imported:record","metric:power_capacity"] | ["32b98d7e-1d0f-5c16-af18-3f469f3b662b"] | company_disclosure | Applied Digital Announces Pricing of $1.59 Billion of Senior Secured Notes to fund the Fourth Building at Polaris Forge 1 | https://ir.applieddigital.com/_assets/_f6377ac165e571402492e7df82cea1ee/appliedblockchaininc/news/2026-06-09_Applied_Digital_Announces_Pricing_of_1_59_Billion__156.pdf | Applied Digital | ir.applieddigital.com | source-terms-not-recorded | Applied Digital | 2026-06-09 | 2026-10-09 | 6777765f5ab9b1b5b705fdde0b32bc5cb58737cd76f58e1ff62b5c6d2b752b36 | day | source_record_projection | applied-digital-polaris-forge-1 | s5 | 02039c7978eb5ad0982cb959c5731f70118c004f1fe48428a14ffb1b20797de1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/04bdf086-bc27-5e07-917a-c52bd1c94e28.json | https://web.archive.org/web/20261009/https://ir.applieddigital.com/_assets/_f6377ac165e571402492e7df82cea1ee/appliedblockchaininc/news/2026-06-09_Applied_Digital_Announces_Pricing_of_1_59_Billion__156.pdf
04c12ac4-c0e4-5912-9150-44d384663222 | ["imported:record","metric:investment","metric:power_capacity","milestone:site_acquired","role:owner","role:tenant"] | ["75596cc6-0434-596d-be35-53be39de9c0a"] | news | SoftBank buys $676M old Sharp plant for its OpenAI collab in Japan | https://techcrunch.com/2025/03/14/softbank-buys-676m-old-sharp-plant-for-its-openai-collab-in-japan | TechCrunch | techcrunch.com | source-terms-not-recorded | TechCrunch | 2025-03-14 | 2026-10-09 | 27b7828bbc67c7556285b7045ae7d81e56dc7a8792d1be0d0f57f90dfa9f8def | day | source_record_projection | softbank-sakai | s4 | 03bed245e3fd6adfb416da230450efa6ff1009a2f6cdecf8a5e45419a5e1039d | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/04c12ac4-c0e4-5912-9150-44d384663222.json | https://web.archive.org/web/20261009/https://techcrunch.com/2025/03/14/softbank-buys-676m-old-sharp-plant-for-its-openai-collab-in-japan
04cdcd08-1dfc-59dc-9133-d6052c0175fa | ["imported:geometry","imported:record"] | ["39b97d53-5af7-55ea-bfc4-6f2f08f32e74"] | other | Kiowa, Oklahoma | https://en.wikipedia.org/wiki/Kiowa,_Oklahoma | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | db19c81b8523e14ff6e1870b6895fe97abfca24a60a16a094301a21d6fa4aec2 | unknown | source_record_projection | iren-kiowa-oklahoma | s7 | 7a82fb1816b60ae0736e58a3073374185644fa92a93e57f59148f6d5c023d4fb | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/04cdcd08-1dfc-59dc-9133-d6052c0175fa.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Kiowa,_Oklahoma
04eb4e29-b035-5d4f-b6dc-ababe98ba94e | ["geometry"] | ["bb8ba3ad-d563-5f84-a543-079a10264640"] | government_record | City of Gosnells IntraMaps property result, Lot 500 / 582 Bickley Road | https://maps.gosnells.wa.gov.au/intramaps22A/?project=Gosnells | City of Gosnells | city_of_gosnells_intramaps_property | rights-status-uncertain-fact-extraction-only | City of Gosnells |  | 2026-08-23 | 40dbab2d5aa393d92f1f60e27c366d72336764d0a15ba650a6518074f09863d6 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/04eb4e29-b035-5d4f-b6dc-ababe98ba94e.json | https://web.archive.org/web/20260823/https://maps.gosnells.wa.gov.au/intramaps22A/?project=Gosnells
04fa5bd4-ae37-536c-abab-4c6c98747cf3 | ["imported:geometry","imported:record","imported:status","power_source:natural_gas_onsite","role:operator"] | ["94562977-e3af-5f59-bee1-896ee8db20f6"] | company_disclosure | Fermi Selects NAES to Operate Project Matador's Natural Gas Fleet | https://fermiamerica.com/fermi-selects-naes-to-operate-project-matadors-natural-gas-fleet/ | Fermi America | fermiamerica.com | source-terms-not-recorded | Fermi America | 2026-09-28 | 2026-10-09 | 68e1953a07f459c769d03d60231f9dce40bc9ae2af14a537a8856fb3fd09fe77 | day | source_record_projection | fermi-america-hypergrid-amarillo | s4 | 2784250e9a1dd9f679638c54fd185e63aec4254906feee0f129ab485698ebe1c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/04fa5bd4-ae37-536c-abab-4c6c98747cf3.json | https://web.archive.org/web/20261009/https://fermiamerica.com/fermi-selects-naes-to-operate-project-matadors-natural-gas-fleet/
0573a8b5-aea9-50f4-8ac3-b2cbe830d5df | ["imported:record","imported:status","metric:investment","metric:power_capacity","milestone:construction_started","milestone:other","role:developer"] | ["4a2a09d1-1ace-5ff8-a80f-89996cda5799"] | company_disclosure | Rowan Closes $3B Green Financing for Turnkey Hyperscale Campus in High-Growth Texas Market | https://rowan.com/rowan-closes-3b-green-financing-for-turnkey-hyperscale-campus-in-high-growth-texas-market/ | Rowan Digital Infrastructure | rowan.com | source-terms-not-recorded | Rowan Digital Infrastructure | 2026-05-27 | 2026-10-09 | 5e0d89ce451bfd0c2a88dd2a4a045158689d41d64f50309a4d6c3993bbfd6916 | day | source_record_projection | rowan-project-temple | s2 | ac6a9ba056d88fd802fe69828988dcb7d1f1434be4bf4235730b1b47e5aeeacb | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0573a8b5-aea9-50f4-8ac3-b2cbe830d5df.json | https://web.archive.org/web/20261009/https://rowan.com/rowan-closes-3b-green-financing-for-turnkey-hyperscale-campus-in-high-growth-texas-market/
05a43522-dea2-5e51-a479-742c80d8477c | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:power_capacity","milestone:expansion_announced","milestone:first_operational","role:builder"] | ["8d1ed9d7-795d-55a8-b8cf-41e51579dd27"] | company_disclosure | HENT, a subsidiary of Sentia, has signed a contract for the expansion of Nscale's data center in the Narvik region | https://www.inderes.se/releases/hent-a-subsidiary-of-sentia-has-signed-a-contract-for-the-expansion-of-nscales-data-center-in-the-narvik-region | Sentia (via Inderes) | www.inderes.se | source-terms-not-recorded | Sentia (via Inderes) | 2026-09-02 | 2026-10-09 | 962b23d1839e520372b6a12573318d7ddc65124cf0404e951f49189b62539a5f | day | source_record_projection | nscale-kvandal-narvik | s9 | b6e0ecf7f879e1a240a2261292267e94077cb03a765ee2aa5afb2c430537adf1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/05a43522-dea2-5e51-a479-742c80d8477c.json | https://web.archive.org/web/20261009/https://www.inderes.se/releases/hent-a-subsidiary-of-sentia-has-signed-a-contract-for-the-expansion-of-nscales-data-center-in-the-narvik-region
05ae0c36-233c-5df1-a141-9576a0cb36ba | ["context:site_distinctness","geometry"] | ["5e0d1954-690d-51cb-816a-88cec595f51a"] | government_record | LGL-BW INSPIRE address Einsteinallee 14 in the advertised ETRS89 geographic CRS (EPSG:4258): cross-check | https://owsproxy.lgl-bw.de/owsproxy/wfs/WFS_INSP_BW_Adr_Hauskoord_ALKIS?SERVICE=WFS&VERSION=2.0.0&REQUEST=GetFeature&TYPENAMES=ad:Address&SRSNAME=urn:ogc:def:crs:EPSG::4258&BBOX=48.36210,7.81680,48.36240,7.81720,urn:ogc:def:crs:EPSG::4258&COUNT=100 | Landesamt für Geoinformation und Landentwicklung Baden-Württemberg (LGL-BW) | lgl_bw_inspire_addresses_house_coordinates_alkis | dl-de/by-2-0 | LGL-BW (2026) Datenlizenz Deutschland – Namensnennung – Version 2.0, www.lgl-bw.de |  | 2026-10-09T11:06:06.847Z | 1ab7eb600431b7b3b2193d69e405268e21c8e529772dfefb5da2b2482f901f12 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/05ae0c36-233c-5df1-a141-9576a0cb36ba.json | https://web.archive.org/web/20261009110606/https://owsproxy.lgl-bw.de/owsproxy/wfs/WFS_INSP_BW_Adr_Hauskoord_ALKIS?SERVICE=WFS&VERSION=2.0.0&REQUEST=GetFeature&TYPENAMES=ad:Address&SRSNAME=urn:ogc:def:crs:EPSG::4258&BBOX=48.36210,7.81680,48.36240,7.81720,urn:ogc:def:crs:EPSG::4258&COUNT=100
05b0646a-d1a4-519d-8665-d227d9de98de | ["context:site_distinctness","geometry"] | ["b4ff75a2-9d55-54ad-bf27-4c60b096eb0f"] | government_record | TxGIO address-layer schema and native CRS | https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0?f=pjson | Texas Geographic Information Office | americas_round30_riot_rockdale | no-open-license-asserted | Texas Geographic Information Office |  | 2026-09-09T11:46:57.727Z | f3585317c3d32f3f057b47c57927319649e39521b1ed03a73fc4d0f4195cff46 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/05b0646a-d1a4-519d-8665-d227d9de98de.json | https://web.archive.org/web/20260909114657/https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0?f=pjson
05cb13bf-4df5-5b3c-8ecc-a2a16b1ced59 | ["context:site_distinctness","geometry"] | ["d5b84301-4f54-5958-a0d1-fd2c5a72cc5b"] | government_record | City map-service provenance and catalogue binding | https://gis.palmcoast.gov/hosting/rest/services/External/FlaglerCountyParcels/MapServer?f=pjson | City of Palm Coast; Flagler Property Appraiser | americas_round28_palm_coast | no-open-license-asserted | City of Palm Coast; Flagler Property Appraiser |  | 2026-09-09T10:37:18.101Z | ed0e0c6cef2aca99131fe3027e79c60360bc8f3d5ffc628b0b18c2856386f9f6 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/05cb13bf-4df5-5b3c-8ecc-a2a16b1ced59.json | https://web.archive.org/web/20260909103718/https://gis.palmcoast.gov/hosting/rest/services/External/FlaglerCountyParcels/MapServer?f=pjson
05fc7a75-5568-56e7-95cd-90eaeb278a67 | ["context:site_distinctness","geometry"] | ["6b11de63-a6b0-5513-87a1-b77ff3b71bfb"] | government_record | Census FAQ identifies source datum and interpolation semantics | https://www2.census.gov/geo/pdfs/maps-data/data/FAQ_for_Census_Bureau_Public_Geocoder.pdf | U.S. Census Bureau | americas_round15_lake_mariner | no-open-redistribution-license-asserted | U.S. Census Bureau |  | 2026-09-09T03:42:13.438Z | 13a8ca9f7395daf53e0c06344dd2f1ed28bc6806ab0625b3410eba7e280db169 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/05fc7a75-5568-56e7-95cd-90eaeb278a67.json | https://web.archive.org/web/20260909034213/https://www2.census.gov/geo/pdfs/maps-data/data/FAQ_for_Census_Bureau_Public_Geocoder.pdf
062565fb-46a0-5b50-a40e-6b8979219535 | ["context:geometry_identity","context:site_distinctness"] | ["8a5fbd17-48b6-5484-8c37-ce406068bf3e","ad5f9b2b-80bf-5580-92f2-0f53473c882d","c789668b-ecf3-53b2-b23c-44151e199317"] | company_disclosure | NEXTDC official contact page: M2, M3 and S3 campus addresses | https://www.nextdc.com/contact | NEXTDC Limited | nextdc_official_campus_locator | all-rights-reserved | NEXTDC Limited |  | 2026-09-08T20:46:45Z | a0f41425492c1b34f30399d2e6192ea6b59f0031f3b0e503a2210a7df7673893 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/062565fb-46a0-5b50-a40e-6b8979219535.json | https://web.archive.org/web/20260908204645/https://www.nextdc.com/contact
06401c9f-9251-5d21-af37-495cc1759f3e | ["imported:geometry","imported:record"] | ["79276528-66df-572a-8baf-0afce2bb01e4"] | other | Bosque County, Texas | https://en.wikipedia.org/wiki/Bosque_County,_Texas | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 3d35812efdf6bf0b0c532b77c730e17369daf46795b4307321878c1e6e6f4a5d | unknown | source_record_projection | cyrusone-bosque-county | s5 | 083700c73d0cef1c843251f67ac8c9c1039c441b433603e8408a84f4d522909a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/06401c9f-9251-5d21-af37-495cc1759f3e.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Bosque_County,_Texas
066affc1-b93b-502b-92b6-a030a9f63198 | ["imported:record","metric:investment","milestone:other","role:government"] | ["bc344b80-1656-5a9a-a788-a5f7cb59131e"] | news | Page residents push back on $10B data center proposal near Horseshoe Bend | https://www.azfamily.com/2025/12/18/page-residents-push-back-10b-data-center-proposal-near-horseshoe-bend/ | Arizona's Family (KTVK/KPHO) | www.azfamily.com | source-terms-not-recorded | Arizona's Family (KTVK/KPHO) | 2025-12-17 | 2026-10-09 | c4e6e513725a9583378a3f01cfe212ff9cbd816ab97a98aa847cd72ad1f24e7e | day | source_record_projection | huntley-page-arizona | s2 | 97f36630761d76604a66ebb99d8f270114cf82e816eff5b78d0570cacf0af6d6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/066affc1-b93b-502b-92b6-a030a9f63198.json | https://web.archive.org/web/20261009/https://www.azfamily.com/2025/12/18/page-residents-push-back-10b-data-center-proposal-near-horseshoe-bend/
06a5133c-bebf-5bfb-ae62-8ed8e3c29287 | ["imported:geometry","imported:record","metric:buildings","metric:investment","metric:land_area","metric:power_capacity","milestone:permit_approved","role:government"] | ["dd65fe26-5f6d-52e8-96b6-8709ca040b13"] | news | La préfecture de Seine-et-Marne autorise l'installation de Campus IA à Fouju | https://next.ink/brief-article/la-prefecture-de-seine-et-marne-autorise-linstallation-de-campus-ia-a-fouju/ | Next | next.ink | source-terms-not-recorded | Next | 2026-08-13 | 2026-10-09 | ce1506ba0cfea309ba1229078f795a389f0b1053121b1598b1f51979155373b7 | day | source_record_projection | mgx-bpifrance-mistral-nvidia-campus | s4 | 0b259aac6c9d22a01d23f16f3ee0a66a849ada132bdcc560ff99ec4cba6639d4 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/06a5133c-bebf-5bfb-ae62-8ed8e3c29287.json | https://web.archive.org/web/20261009/https://next.ink/brief-article/la-prefecture-de-seine-et-marne-autorise-linstallation-de-campus-ia-a-fouju/
06c0bcf8-7abe-5ced-aad8-d754a6a570ba | ["imported:record","milestone:construction_started","milestone:first_operational","power_source:geothermal","role:developer","role:government"] | ["bb1b28fd-610b-5739-b928-e44f21cb6f1b"] | news | The truth about Wonder Valley, Kevin O'Leary's data-centre dream | https://www.geothermalcanada.org/news/2025/12/17/the-truth-about-wonder-valley | The Logic (republished by Geothermal Canada) | www.geothermalcanada.org | source-terms-not-recorded | The Logic (republished by Geothermal Canada) | 2025-12-10 | 2026-10-09 | 21dc36740e3a1bae3267923d13595224becb266ab824ea678dfc51212af87e06 | day | source_record_projection | wonder-valley-alberta | s5 | 8362b04814249174419268d40122ca73605913dfcf84412d960be5265857e94c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/06c0bcf8-7abe-5ced-aad8-d754a6a570ba.json | https://web.archive.org/web/20261009/https://www.geothermalcanada.org/news/2025/12/17/the-truth-about-wonder-valley
06de5624-4429-5d56-a4eb-d9e3f87ca265 | ["imported:geometry","imported:record","metric:buildings","milestone:fully_operational","milestone:other","power_source:grid","role:developer","role:power_supplier"] | ["79276528-66df-572a-8baf-0afce2bb01e4"] | company_disclosure | Bosque County Data Center | https://www.cyrusone.com/data-centers/north-america/bosque-county-tx | CyrusOne | www.cyrusone.com | source-terms-not-recorded | CyrusOne |  | 2026-10-09 | e391d51c500143affc6ec230f4a9738c071da3822d6450d857bab9434e80f9b1 | unknown | source_record_projection | cyrusone-bosque-county | s3 | 083700c73d0cef1c843251f67ac8c9c1039c441b433603e8408a84f4d522909a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/06de5624-4429-5d56-a4eb-d9e3f87ca265.json | https://web.archive.org/web/20261009/https://www.cyrusone.com/data-centers/north-america/bosque-county-tx
06e229c2-36e5-5a0d-a27c-50162d17fe0f | ["physical_status"] | ["f8900f55-087d-5d51-aef2-820402bcbdc2"] | company_disclosure | Goodman FY26 Results - AMS01 current development | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | Goodman Group | goodman_group_investor_presentations | all-rights-reserved | Goodman Group | 2026-08-19 | 2026-09-08T18:38:25Z | 892c9d069276912a13d2ff100ff3260b1c2d26874693d644e0d34dce3a7d809d | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/06e229c2-36e5-5a0d-a27c-50162d17fe0f.json | https://web.archive.org/web/20260908183825/https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1
06f448bb-2a9b-5e8d-8fbd-4b23952bea58 | ["imported:geometry","imported:record","imported:status","milestone:announced","role:government"] | [] | news | Amazon plans $11 billion data center expansion in Georgia | https://www.ajc.com/news/amazon-plans-11-billion-data-center-expansion-in-georgia/4L34LL7RM5DTPBX67KUD5PCJUI/ | The Atlanta Journal-Constitution | www.ajc.com | source-terms-not-recorded | The Atlanta Journal-Constitution | 2025-01-08 | 2026-10-09 | 3dc958d057204261c06c19546d5f9ad31cb045bcc8307206cee4c5a1e9e7a737 | day | source_record_projection | aws-douglas-county-georgia | s2 | a7bccffb503d4373ef898ca74489eb2b68a093f878680cef90e2cab6bf61bfbd | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/06f448bb-2a9b-5e8d-8fbd-4b23952bea58.json | https://web.archive.org/web/20261009/https://www.ajc.com/news/amazon-plans-11-billion-data-center-expansion-in-georgia/4L34LL7RM5DTPBX67KUD5PCJUI/
0702ec92-61c9-595f-a8dc-bb25e0186aa1 | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:announced","power_source:grid","role:builder","role:developer","role:power_supplier","role:utility"] | ["d1538d73-e301-5203-9e49-924b20051374"] | company_disclosure | Hello, Sturgeon County! | https://datacenters.atmeta.com/2026/07/hello-sturgeon-county/ | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms | 2026-07-08 | 2026-10-09 | 00d71212749998bc5d4f6c6f82a31ce5ff8d84585c08a4b84c6db60840c1676d | day | source_record_projection | meta-sturgeon-county | s2 | b5f2331db09e9949bd4b7edfc68469145bbe29ee0ecd55917d535b96345275e1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0702ec92-61c9-595f-a8dc-bb25e0186aa1.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/2026/07/hello-sturgeon-county/
0760610d-7367-5c5f-ba60-ecabca22a5e4 | ["imported:record","milestone:other"] | ["d654ea2a-ea8e-564e-a1df-67f35d52ebbc"] | news | Tucson rejects Amazon-linked data center amid water, energy concerns | https://www.azfamily.com/2025/08/09/tucson-rejects-amazon-linked-data-center-amid-water-energy-concerns/ | Arizona's Family (KTVK/KPHO) | www.azfamily.com | source-terms-not-recorded | Arizona's Family (KTVK/KPHO) | 2025-08-08 | 2026-10-09 | 17d4d54ad205b56ace926b3258c87c97c044d6541180c8990b8bcc6ec11b7197 | day | source_record_projection | project-blue-tucson | s3 | 36e90bd020e0cf912c30f63d71e0c1efd8ce8bbc328218d5e7860d7c1996c304 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0760610d-7367-5c5f-ba60-ecabca22a5e4.json | https://web.archive.org/web/20261009/https://www.azfamily.com/2025/08/09/tucson-rejects-amazon-linked-data-center-amid-water-energy-concerns/
076967b9-e7bd-53d2-a04b-851aa51a63de | ["imported:record","metric:power_capacity","power_source:natural_gas_onsite","role:power_supplier"] | ["edaa7f7d-5025-5f95-9870-3ad12478339c"] | news | Ohio approves new natural gas power plant for data center | https://mountvernonnews.com/stories/675445301-ohio-approves-new-natural-gas-power-plant-for-data-center | Mount Vernon News | mountvernonnews.com | source-terms-not-recorded | Mount Vernon News | 2025-09-19 | 2026-10-09 | 923a238255fe4b832d7dd3cb69901e303f6d6c8920db48e8e62e356ee9f89c2c | day | source_record_projection | meta-prometheus-new-albany | s4 | ee389124403f5aa474aca9357c8d9f7c4ca6c72bd75b02efe21419a6421919ee | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/076967b9-e7bd-53d2-a04b-851aa51a63de.json | https://web.archive.org/web/20261009/https://mountvernonnews.com/stories/675445301-ohio-approves-new-natural-gas-power-plant-for-data-center
077a6629-8396-549b-92c0-cdec324067f3 | ["physical_status"] | ["9ddf0df3-e40c-515f-9468-ed78f063513b"] | company_disclosure | Time-Lapse Video - TX4 Garland, TX | https://www.linkedin.com/posts/ntt-global-data-centers_time-lapse-video-tx4-garland-tx-activity-7473147125938147328-uZsM | NTT Global Data Centers | ntt_global_data_centers_linkedin | all-rights-reserved | NTT Global Data Centers via LinkedIn | 2026-06-17T22:58:39.165Z | 2026-07-20T05:41:07Z | aad2ec60df3f58a87d98d5656f58da9305c701276083920aa939b0510c554dad | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/077a6629-8396-549b-92c0-cdec324067f3.json | https://web.archive.org/web/20260720054107/https://www.linkedin.com/posts/ntt-global-data-centers_time-lapse-video-tx4-garland-tx-activity-7473147125938147328-uZsM
078ea19d-9af1-51c4-938d-74a15d90c5e2 | ["imported:record","imported:status","milestone:other","role:government"] | ["46434a5c-4980-5f79-ac83-000783b60566"] | news | La explosión de los centros de datos en Aragón: entre la opacidad, el choque institucional y el riesgo de colapso | https://www.eldiario.es/aragon/politica/explosion-centros-datos-aragon-opacidad-choque-institucional-riesgo-colapso_1_12559021.amp.html | elDiario.es | www.eldiario.es | source-terms-not-recorded | elDiario.es | 2025-08-27 | 2026-10-09 | e34407249b0c908201fe9fcd4e1bfd82f6aad85305bf4f1a5d2b80bb096d093b | day | source_record_projection | blackstone-calatorao | s4 | 6afcb1fbc59cf3659ffc3e2d0aa618b2fd646f74ecfb8cd734af34d6d752dadf | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/078ea19d-9af1-51c4-938d-74a15d90c5e2.json | https://web.archive.org/web/20261009/https://www.eldiario.es/aragon/politica/explosion-centros-datos-aragon-opacidad-choque-institucional-riesgo-colapso_1_12559021.amp.html
0795bcb6-d4ac-58b7-81dc-8f90bf417f20 | ["context:site_distinctness","geometry"] | ["1f430ea1-a0e6-5a91-b3e7-3f002b331cf6"] | government_record | DNR official DoWORC provenance and point semantics | https://secure.in.gov/dnr/water/online-research-center/ | Indiana Department of Natural Resources, Division of Water | americas_round4_meta_lebanon | no-open-redistribution-license-asserted | Indiana Department of Natural Resources, Division of Water |  | 2026-09-08T21:08:44Z | 6841cbaf70b542ae2e56d6129d8bb27fbe3269d96a258ae17a2ad9a5c7ce6dab | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0795bcb6-d4ac-58b7-81dc-8f90bf417f20.json | https://web.archive.org/web/20260908210844/https://secure.in.gov/dnr/water/online-research-center/
07ea32f1-85b6-5285-8219-504b14f65e60 | ["context:geometry_identity","context:site_distinctness","geometry"] | ["3761e59a-fe39-523d-83a6-9fbfa9feec85"] | government_record | NSW Planning Portal: NEXTDC S4 named project and GeoJSON marker | https://www.planningportal.nsw.gov.au/major-projects/projects/nextdc-s4-data-centre-horsley-park | NSW Department of Planning, Housing and Infrastructure | nsw_major_projects_public_record | CC-BY-4.0-Department-material-scope | © State of New South Wales and Department of Planning, Housing and Infrastructure 2026 |  | 2026-09-08T20:47:57Z | c1b431e00b3af4d6c550cac7f92ab5aecca5742f7d021816ec269c1bb100108c | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/07ea32f1-85b6-5285-8219-504b14f65e60.json | https://web.archive.org/web/20260908204757/https://www.planningportal.nsw.gov.au/major-projects/projects/nextdc-s4-data-centre-horsley-park
07eeb2a7-7bc4-59bf-953c-00879a92180d | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:first_operational","milestone:other","role:developer","role:government"] | ["81d20134-d073-5e0c-ad1c-7f8a97f2dadb"] | trade_press | Application filed for data center campus near QTS' site in Northumberland, UK | https://bebeez.eu/2026/08/18/application-filed-for-data-center-campus-near-qts-site-in-northumberland-uk/ | BeBeez International (republishing DatacenterDynamics) | bebeez.eu | source-terms-not-recorded | BeBeez International (republishing DatacenterDynamics) | 2026-08-18 | 2026-10-09 | e9fd93a7d329322d65417879ad9fce04d66f9d146d2b50bfdf93e0cbe88e6f5e | day | source_record_projection | tbc-partners-cambois | s2 | 1ed67826272efcc8bff6bd33ef12dcbc0ab7f5e8ee6f3b1cac4e60aa1808b7e4 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/07eeb2a7-7bc4-59bf-953c-00879a92180d.json | https://web.archive.org/web/20261009/https://bebeez.eu/2026/08/18/application-filed-for-data-center-campus-near-qts-site-in-northumberland-uk/
07efc002-2951-51bc-bae2-76b8e0f7c949 | ["imported:record","milestone:other","role:tenant"] | ["40abc164-3033-5172-b386-52422d1513b9"] | company_disclosure | Core Scientific announces second quarter 2026 results | https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-07-28 | 2026-10-09 | b97d99a2a3a4796490ac273fc28ec2d0522f582db609eb202f0e0ebada245bd7 | day | source_record_projection | core-scientific-hunt-county | s4 | f3d8655922984d28b63705187f2e9186750a7799301fc3ba8ed58403f4c0acd3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/07efc002-2951-51bc-bae2-76b8e0f7c949.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results
0818330a-60db-531c-ab23-5ac7a6f225c7 | ["context:site_distinctness","geometry"] | ["f0e92e2e-e082-5b7f-9486-fd744b5b68e6"] | government_record | Official downloadable Swiss building-address directory exact Winterthur record | https://data.geo.admin.ch/ch.swisstopo.amtliches-gebaeudeadressverzeichnis/amtliches-gebaeudeadressverzeichnis_ch/amtliches-gebaeudeadressverzeichnis_ch_2056.csv.zip | Federal Office of Topography swisstopo | europe_mena_round9_expansion_asia | swisstopo-free-geodata-terms-2021-03-01 | © swisstopo |  | 2026-09-08T23:14:47.769Z | 94f414fd80a8a9b500b8d5977ce765bab66ff8136fa52f4a01a9da3688639c9f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0818330a-60db-531c-ab23-5ac7a6f225c7.json | https://web.archive.org/web/20260908231447/https://data.geo.admin.ch/ch.swisstopo.amtliches-gebaeudeadressverzeichnis/amtliches-gebaeudeadressverzeichnis_ch/amtliches-gebaeudeadressverzeichnis_ch_2056.csv.zip
08279736-b463-5ac5-a3f2-832e17b4474c | ["context:geometry_identity","context:site_distinctness"] | ["20ee1eea-91bf-52aa-a464-c4a38d436f9e"] | company_disclosure | Applied Digital PF1 phase delivery and Ellendale identity | https://ir.applieddigital.com/news-events/press-releases/detail/157/applied-digital-delivers-second-building-at-polaris-forge-1 | Applied Digital Corporation | americas_round5 | no-open-redistribution-license-asserted | Applied Digital Corporation | 2026-07-01 | 2026-09-08T21:38:05Z | c3bc3fb2cf33f34890f94ed0712e3544fadcb5b20aa4da1f58e12cd10e8d0d45 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/08279736-b463-5ac5-a3f2-832e17b4474c.json | https://web.archive.org/web/20260908213805/https://ir.applieddigital.com/news-events/press-releases/detail/157/applied-digital-delivers-second-building-at-polaris-forge-1
08c1fde3-35eb-5cf1-a141-822cfefed1f4 | ["imported:geometry","imported:record","metric:land_area","metric:power_capacity","milestone:first_operational","milestone:permit_approved","power_source:grid","power_source:natural_gas_onsite","role:developer"] | ["7d6333d2-26e6-548c-979a-324c7113281b"] | news | To Feed Data Centers, Pennsylvania Faces a New Fracking Surge | https://e360.yale.edu/features/pennsylvania-data-centers-natural-gas | Yale Environment 360 | e360.yale.edu | source-terms-not-recorded | Yale Environment 360 | 2025-12-11 | 2026-10-09 | 6d68bbe6a00b5bf1e19713eec1a11d909c0c98de301162e05f6ee85516020f90 | day | source_record_projection | homer-city-redevelopment | s4 | df51c430e2602ca76bfc730c4a832dc4378f8c2783e5e0d87db5fa2704e614db | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/08c1fde3-35eb-5cf1-a141-822cfefed1f4.json | https://web.archive.org/web/20261009/https://e360.yale.edu/features/pennsylvania-data-centers-natural-gas
08fe1497-9bfa-54ce-94a2-3a8c9ac3dd13 | ["imported:geometry","imported:record","metric:power_capacity","milestone:site_acquired","role:developer","role:owner","role:power_supplier"] | ["dc6f83d9-dac5-563a-ba7e-ff18e27ba506"] | news | Talen Energy announces sale of data center campus to Amazon | https://local21news.com/news/local/talen-energy-announces-sale-of-data-center-campus-to-amazon | local21news (WHP) | local21news.com | source-terms-not-recorded | local21news (WHP) | 2024-03-04 | 2026-10-09 | df67b926a01c3d6ff6a7c6c021dfba17ff2493e23d6e39b277afe39eefed8ecc | day | source_record_projection | aws-salem-township-pennsylvania | s1 | 4dd6dde012f8c93b41327c85112d56db632e692cc634ebdc5e6570285d367043 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/08fe1497-9bfa-54ce-94a2-3a8c9ac3dd13.json | https://web.archive.org/web/20261009/https://local21news.com/news/local/talen-energy-announces-sale-of-data-center-campus-to-amazon
09530596-5c39-5d1c-881f-6993227a10d1 | ["typed_metric:critical_it_mw"] | ["aa93c84a-17d6-5092-bf57-686f7e1ab4a4"] | company_disclosure | STT Jakarta 3 Factsheet | https://assets.sttelemediagdc.com/sttgdc/global_en/public/2026-07/STT_Jakarta_3_Factsheet-vJul2026.pdf | ST Telemedia Global Data Centres | stt_gdc_facility_factsheets | all-rights-reserved | ST Telemedia Global Data Centres | 2026-07-16 | 2026-07-19T19:09:17Z | 79219de45833e9cdb149c37a1cfbc644ac805b2e7be7fbdbfcad6de90347a240 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/09530596-5c39-5d1c-881f-6993227a10d1.json | https://web.archive.org/web/20260719190917/https://assets.sttelemediagdc.com/sttgdc/global_en/public/2026-07/STT_Jakarta_3_Factsheet-vJul2026.pdf
095b495d-4219-576d-a976-579e7afcc8be | ["imported:geometry","imported:record","metric:investment","metric:land_area","metric:power_capacity","milestone:announced","milestone:site_acquired","power_source:grid","role:developer","role:owner","role:tenant"] | ["298d7152-0985-535e-a701-60b689a3cd00"] | regulatory_filing | Riot announces fee simple acquisition of land and first data center lease with AMD at the Rockdale Site (Form 8-K, Exhibit 99.1) | https://www.sec.gov/Archives/edgar/data/1167419/000110465926004551/riot-20260116xex99d1.htm | Riot Platforms, Inc. via SEC EDGAR | www.sec.gov | source-terms-not-recorded | Riot Platforms, Inc. via SEC EDGAR | 2026-01-16 | 2026-10-09 | 7a50bb738a7c161724b7ab1fc560137bbca6ffd55932dfde5c6fdcb30a22bd5f | day | source_record_projection | riot-rockdale | s1 | f94008953bdaca0278e91a5f93b52917878d68e759e2df3a39593ff1e55cb0e8 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/095b495d-4219-576d-a976-579e7afcc8be.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1167419/000110465926004551/riot-20260116xex99d1.htm
09661d28-4b3e-583a-97a6-7e4d2a00a48a | ["imported:geometry","imported:record","imported:status","metric:power_capacity","milestone:announced","power_source:grid","role:developer","role:utility"] | ["ec871425-75fd-5ee1-9a6f-0e901b2f5837"] | company_disclosure | AirTrunk grows Malaysia platform with second cloud and AI-ready data centre in Johor | https://airtrunk.com/airtrunk-scales-up-in-malaysia-with-announcement-of-second-malaysia-hyperscale-data-centre-jhb2/ | AirTrunk | airtrunk.com | source-terms-not-recorded | AirTrunk | 2025-02-12 | 2026-10-09 | f874af89c0b0cdb6a23b862e47c99d426dcb423ce7a3e9a6977f6e09b5ed2025 | day | source_record_projection | airtrunk-jhb2-iskandar-puteri | s1 | 05d8cffa147ddb49bdcc4de12a460863f46b072f4ffe4dec45ae38c08852f466 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/09661d28-4b3e-583a-97a6-7e4d2a00a48a.json | https://web.archive.org/web/20261009/https://airtrunk.com/airtrunk-scales-up-in-malaysia-with-announcement-of-second-malaysia-hyperscale-data-centre-jhb2/
0966d5c7-8856-5c81-94e5-503a5bee322d | ["context:site_distinctness","geometry"] | ["546bf83f-2bb4-5539-b576-6b7100981420"] | government_record | County public web map binds its displayed Addresses service | https://maps.co.ellis.tx.us/portal/sharing/rest/content/items/699ad5fa2c004d0d972f22f416747072/data?f=json | Ellis County, Texas GIS | americas_round29_databank_red_oak | no-open-license-asserted | Ellis County, Texas GIS |  | 2026-09-09T11:18:32.562Z | ec6ad6f3b325062562d91e9a1fd62d459aa1a69710cd7044a29e072bb5bbb223 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0966d5c7-8856-5c81-94e5-503a5bee322d.json | https://web.archive.org/web/20260909111832/https://maps.co.ellis.tx.us/portal/sharing/rest/content/items/699ad5fa2c004d0d972f22f416747072/data?f=json
097214ae-03ad-505e-9ea1-d45f37b9ccbb | ["imported:record","milestone:permit_approved","power_source:battery_storage","power_source:natural_gas_onsite","role:power_supplier"] | ["edaa7f7d-5025-5f95-9870-3ad12478339c"] | trade_press | Ohio Power Siting Board Approves Construction of Power Plant to Serve Load of Adjacent Data Center | https://www.publicpower.org/node/30607 | American Public Power Association | www.publicpower.org | source-terms-not-recorded | American Public Power Association | 2026-07-07 | 2026-10-09 | ffbbcea90ff427ecdcd7f37d3aeaae32a9511cd2258e84d2c2b0411836fba2a7 | day | source_record_projection | meta-prometheus-new-albany | s5 | ee389124403f5aa474aca9357c8d9f7c4ca6c72bd75b02efe21419a6421919ee | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/097214ae-03ad-505e-9ea1-d45f37b9ccbb.json | https://web.archive.org/web/20261009/https://www.publicpower.org/node/30607
09b2d5a9-29d7-512d-84e2-65e09c2bfd97 | ["imported:record","milestone:other","role:power_supplier"] | ["9002afae-5b81-5c8c-a6f9-4504c91e8624"] | other | Groups appeal air permit for xAI's personal power plant in North Mississippi | https://www.selc.org/press-release/groups-appeal-air-permit-for-xais-personal-power-plant/ | Southern Environmental Law Center | www.selc.org | source-terms-not-recorded | Southern Environmental Law Center | 2026-04-09 | 2026-10-09 | 4bbee8b8734e96260e81e88b08e4d69ca25e0dfe3ac6287ff370acce903c80cf | day | source_record_projection | xai-colossus-2-memphis | s5 | a96b3341db0b72f4eeb487d50474903219c98fa2d20b32ec4e3af47c0c0a03d7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/09b2d5a9-29d7-512d-84e2-65e09c2bfd97.json | https://web.archive.org/web/20261009/https://www.selc.org/press-release/groups-appeal-air-permit-for-xais-personal-power-plant/
09cc5d95-2cf4-5691-9cf6-122f40731133 | ["context:site_distinctness"] | ["aa2dc8a4-52d8-5519-b23a-2ff0313db9e3"] | company_disclosure | MERLIN July27: GetafeII work continues | https://ir.merlinproperties.com/en/merlin-increases-total-revenues-and-ebitda-by-11-7-thanks-to-the-data-centers-division-which-reaches-160-mw-leased/ | MERLIN Properties | expansion_round5_primary_sources | all-rights-reserved | MERLIN Properties | 2026-07-27T23:20:41Z | 2026-09-08T20:47:28Z | 5babae5e721089512f4f4efc0ccecfc608538460c351c03dccc714ea651f63d0 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/09cc5d95-2cf4-5691-9cf6-122f40731133.json | https://web.archive.org/web/20260908204728/https://ir.merlinproperties.com/en/merlin-increases-total-revenues-and-ebitda-by-11-7-thanks-to-the-data-centers-division-which-reaches-160-mw-leased/
09fd54b2-c42d-5a6e-bfe0-9b30a1c87a00 | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","milestone:announced","power_source:grid","role:developer","role:utility"] | ["3315c754-ca0d-5702-8071-44b22787215a"] | company_disclosure | Hello, Kansas City! | https://datacenters.atmeta.com/2022/03/hello-kansas-city/ | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms | 2022-03-24 | 2026-10-09 | 6242867633f1907c43c803dff32f0864af2e810a675f2bebc2f96b3ee8976f79 | day | source_record_projection | meta-kansas-city | s1 | d5a16739885c6faee38a87b2fcc8bd21b6a278e697cf56b52e86e13524ae7479 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/09fd54b2-c42d-5a6e-bfe0-9b30a1c87a00.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/2022/03/hello-kansas-city/
0a66a7cc-d742-528e-91a8-06a6fd1f84e6 | ["context:source_location_identity"] | ["c71872a1-fc95-5d5b-8ee8-6b5082e974df"] | government_record | LINZ NZ Primary Parcels - four Datagrid Makarewa core-campus parcels | https://services.arcgis.com/xdsHIIxuCWByZiCB/ArcGIS/rest/services/LINZ_NZ_Primary_Parcels/FeatureServer/0/query?where=appellation+IN+%28%27Lot+1+DP+595572%27%2c%27Lot+2+DP+595572%27%2c%27Lot+3+DP+595572%27%2c%27Lot+2+DP+526953%27%29&outFields=OBJECTID%2cid%2cappellation%2cparcel_intent%2ctopology_type%2cland_district%2ctitles%2csurvey_area%2ccalc_area%2cShape__Area%2cShape__Length&returnGeometry=true&outSR=4326&orderByFields=appellation+ASC&f=geojson | Land Information New Zealand | linz_nz_primary_parcels | CC-BY-4.0 | Crown copyright - Land Information New Zealand |  | 2026-09-07T02:26:38Z | e8823967334879161cf139277879260228bea45bd079647ec71467f5718a6059 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0a66a7cc-d742-528e-91a8-06a6fd1f84e6.json | https://web.archive.org/web/20260907022638/https://services.arcgis.com/xdsHIIxuCWByZiCB/ArcGIS/rest/services/LINZ_NZ_Primary_Parcels/FeatureServer/0/query?where=appellation+IN+%28%27Lot+1+DP+595572%27%2c%27Lot+2+DP+595572%27%2c%27Lot+3+DP+595572%27%2c%27Lot+2+DP+526953%27%29&outFields=OBJECTID%2cid%2cappellation%2cparcel_intent%2ctopology_type%2cland_district%2ctitles%2csurvey_area%2ccalc_area%2cShape__Area%2cShape__Length&returnGeometry=true&outSR=4326&orderByFields=appellation+ASC&f=geojson
0a7a2121-3c55-5126-b58b-7cadf9f45d72 | ["imported:record","milestone:other","power_source:natural_gas_onsite"] | ["2a418e82-60a0-52bf-ac57-8e0e3d3eabdb"] | other | Campaigners appeal Herbata Data Centre decision in Naas | https://www.friendsoftheearth.ie/news/campaigners-appeal-herbata-data-centre-decision-in-naas/ | Friends of the Earth Ireland | www.friendsoftheearth.ie | source-terms-not-recorded | Friends of the Earth Ireland | 2025-09-25 | 2026-10-09 | 94672723e0b03d4acee8656cbc1a1fddfe420a4beb39ed16e5e6932afcbac25d | day | source_record_projection | herbata-naas | s3 | 29b656bc7d083a6924175ee16b7bfaa8b3a4ca4c4859a471e7907432dc262ac6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0a7a2121-3c55-5126-b58b-7cadf9f45d72.json | https://web.archive.org/web/20261009/https://www.friendsoftheearth.ie/news/campaigners-appeal-herbata-data-centre-decision-in-naas/
0a8ec5bd-7966-524b-9806-092f0d43fe3f | ["context:geometry_identity","context:site_distinctness"] | ["9fe862f6-ace2-5f5d-9c90-486fa4622982"] | company_disclosure | Airtel first Nigeria data-centre historical announcement | https://cdn-webportal.airtelstream.net/website/investor/main/pdf/H1-2023/Airtel_Africa_commences_construction_of_Nxtra_by_Airtel_first_data_centre_in_Nigeria_1.pdf | Airtel Africa | africa_round7_nxtra | all-rights-reserved | Airtel Africa | 2024-03-13 | 2026-09-08T22:28:39.668Z | a5b665f23205c0aa50fb23f2b12cbfbefa06e86bcfb62de9bd26944dce4c53a1 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0a8ec5bd-7966-524b-9806-092f0d43fe3f.json | https://web.archive.org/web/20260908222839/https://cdn-webportal.airtelstream.net/website/investor/main/pdf/H1-2023/Airtel_Africa_commences_construction_of_Nxtra_by_Airtel_first_data_centre_in_Nigeria_1.pdf
0a91dfb2-a658-54cd-8294-e917690855b7 | ["context:geometry_identity","context:site_distinctness"] | ["e3f1fc38-bc59-5373-803f-d5c86d817096"] | company_disclosure | Amsterdam Data Center campus 3D rendering: Powering the future with AMS-2 | https://resources.ironmountain.com/videos-and-webinars/d/data-centers-inside-the-amsterdam-data-center-campus-3d-rendering | Iron Mountain Data Centers | iron_mountain_resources | all-rights-reserved | Iron Mountain Data Centers | 2026-06-12T18:03:57Z | 2026-07-20T04:22:16Z | cf3624ab97b5d5e8b372655cecd2f9c98df3406fa2a2678eea8d5ecba25391de | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0a91dfb2-a658-54cd-8294-e917690855b7.json | https://web.archive.org/web/20260720042216/https://resources.ironmountain.com/videos-and-webinars/d/data-centers-inside-the-amsterdam-data-center-campus-3d-rendering
0aa0b898-0cb3-5e6e-9b6d-6c7d0501c090 | ["context:site_distinctness"] | ["60485ece-bd7e-5f82-9f1b-6e271b8dcf45"] | government_record | PARIVESH compliance listing for proposal 477127: May 30 upload and December 2025 predecessor | https://parivesh.nic.in/compliance/data/previousCompliance?proposal_no=SIA%2FMH%2FINFRA2%2F477127%2F2024 | Ministry of Environment, Forest and Climate Change, India (PARIVESH portal) | india_parivesh_public_environmental_proposals | no-open-license-asserted | Ministry of Environment, Forest and Climate Change, India (PARIVESH portal) |  | 2026-09-25T22:22:40.656Z | ae51d65fd32c81e7c111c8b5c469279429439101c36d92a0d39d14b94e9eee04 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0aa0b898-0cb3-5e6e-9b6d-6c7d0501c090.json | https://web.archive.org/web/20260925222240/https://parivesh.nic.in/compliance/data/previousCompliance?proposal_no=SIA%2FMH%2FINFRA2%2F477127%2F2024
0acf5c00-bb2a-5bb7-b417-ea36a5bb07d2 | ["imported:geometry","imported:record","imported:status","metric:buildings","milestone:other","power_source:grid","role:developer","role:government","role:utility"] | ["2a273a46-2f4f-5ccb-9d10-6f2bfeb5e5f5"] | government_record | Plan de Interés General de Aragón Tillion Aragón | https://www.aragon.es/-/piga-tillion-aragon | Gobierno de Aragón | www.aragon.es | source-terms-not-recorded | Gobierno de Aragón | 2026-07-07 | 2026-10-09 | 21e8c71062a037c99b918f82edfe7e7d9a8b2485fa7e937fee30c18c1e126b0a | day | source_record_projection | azora-tillion-villamayor-de-gallego | s2 | d1aa0d3a5fca4ebf39c3e2a7b90748b3b6d7ece4bb0331301d392f040c29ec3a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0acf5c00-bb2a-5bb7-b417-ea36a5bb07d2.json | https://web.archive.org/web/20261009/https://www.aragon.es/-/piga-tillion-aragon
0ad1d56c-aa25-535d-82b8-275d8a38b87c | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","milestone:construction_started","power_source:grid","role:developer","role:government","role:utility"] | ["d3694f4b-3497-5f87-88aa-de8e9449c754"] | company_disclosure | Meta DeKalb Data Center fact sheet | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-DeKalb-Data-Center.pdf | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms |  | 2026-10-09 | 6a3beb91f080ac2dfc9a8a256caa30a17fcd5ef3e5fe795603dbb5e06e24d498 | unknown | source_record_projection | meta-dekalb-illinois | s1 | 83f6ef171748fe2d9828ddcc471e268a595f3828207a358113ba59290c39dc6e | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ad1d56c-aa25-535d-82b8-275d8a38b87c.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/wp-content/uploads/2026/09/Meta_s-DeKalb-Data-Center.pdf
0b1a18c3-44a1-57e1-99a9-670ed7f91769 | ["context:geometry_identity","context:site_distinctness"] | ["e56ff51f-930c-5c5b-bc82-7add264e576e"] | company_disclosure | Google terms preserve content rights and legal-use limitations | https://policies.google.com/terms?hl=en | Google | asia_round30_google_elmina | no-open-license-asserted | Google |  | 2026-09-09T11:50:41.023Z | 1b0b1d1ce21ea20e8679835eb9bb8d3b6214709687b3dc62d29cf9c21e83f50c | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0b1a18c3-44a1-57e1-99a9-670ed7f91769.json | https://web.archive.org/web/20260909115041/https://policies.google.com/terms?hl=en
0b89abc2-dbd0-5721-9607-fb26c955d09c | ["imported:geometry","imported:record"] | ["5c691ba6-a630-5ab4-a45d-4d676e3e4d53"] | other | Harwood, North Dakota | https://en.wikipedia.org/wiki/Harwood,_North_Dakota | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 246d346ed598debe54050a2aebeba77a53ff9f4fa16b8d55d2556311f662c736 | unknown | source_record_projection | applied-digital-polaris-forge-2 | s6 | c28d9e66605af454a76ac320e9b833d6efe8fe36b481ef4868d8867964ae7278 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0b89abc2-dbd0-5721-9607-fb26c955d09c.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Harwood,_North_Dakota
0ba37f72-6f9b-5d8f-8b8e-8b66e03dbb11 | ["context:project_context"] | ["ea4a0cc5-bb09-5a81-b385-38ae79baf22a"] | company_disclosure | IC3 Super West Facility - Macquarie Park Data Centre Campus | https://www.macquariedatacentres.com/wp-content/uploads/sites/5/2023/09/Data-Centres-Data-Sheet-IC3-Super-West-Specs-230923.pdf | Macquarie Data Centres | macquarie_data_centres_specifications | all-rights-reserved | Macquarie Data Centres |  | 2026-07-20T00:53:38Z | bc455a2fa3310e76108b15e8459292aea83dea36beb0fafbc91d2e17ec04e6ce | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ba37f72-6f9b-5d8f-8b8e-8b66e03dbb11.json | https://web.archive.org/web/20260720005338/https://www.macquariedatacentres.com/wp-content/uploads/sites/5/2023/09/Data-Centres-Data-Sheet-IC3-Super-West-Specs-230923.pdf
0ba7bc30-e024-58f4-96d3-dbe3da8693cd | ["imported:geometry","imported:record","metric:investment","metric:jobs_permanent","role:developer"] | ["3e853975-e7a4-52ba-bc38-6b3d09bfdaf0"] | company_disclosure | Amazon plans to invest $10 billion in North Carolina to expand cloud computing infrastructure and advance AI innovation | https://www.aboutamazon.com/news/aws/aws-investment-north-carolina-ai-cloud-infrastructure | Amazon | www.aboutamazon.com | source-terms-not-recorded | Amazon |  | 2026-10-09 | a2edf3ca03876a5bef67f1cbf19e40dc9ac76499c0e60c73402693afa86c257e | unknown | source_record_projection | aws-richmond-county-north-carolina | s3 | 95811ce2b80c82e38fd95f89c057fbe796eb89e70f4ca39334c33a0ff1cb9e09 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ba7bc30-e024-58f4-96d3-dbe3da8693cd.json | https://web.archive.org/web/20261009/https://www.aboutamazon.com/news/aws/aws-investment-north-carolina-ai-cloud-infrastructure
0bb03983-3d2f-5ed5-b740-e635c891bf53 | ["context:site_distinctness"] | ["5ace12f8-658e-5956-9173-d78e625d4df9"] | government_record | Vineland 2026-08-06 equipment-specific stop-construction order | https://woodburywarbler.com/wp-content/uploads/2026/08/20206.0806-Stop-Work-Order-LNG-Tank.jpg | City of Vineland construction official; scan hosted by The Woodbury Warbler | us_round23_dataone_vineland | no-open-license-asserted | City of Vineland construction official; scan hosted by The Woodbury Warbler | 2026-08-06 | 2026-09-09T07:50:41Z | 41bdc4b86f693381b2fc912239c0d5cfe40e92583909d7f04ec5f9b453ad0118 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0bb03983-3d2f-5ed5-b740-e635c891bf53.json | https://web.archive.org/web/20260909075041/https://woodburywarbler.com/wp-content/uploads/2026/08/20206.0806-Stop-Work-Order-LNG-Tank.jpg
0bb1b8a1-24a2-5e40-818e-29621e6017d1 | ["physical_status"] | ["08d881e7-8a1c-50da-81a5-d2ef49f22a7a"] | company_disclosure | Paris 2 Data Centre ¦ Data Centres in Paris ¦ Colt DCS | https://www.coltdatacentres.net/en-GB/our-locations/data-centre-locations-europe/paris-2 | Colt Data Centre Services | colt_data_centre_location_pages | all-rights-reserved | Colt Data Centre Services | 2025-05-14T12:57:10Z | 2026-07-19T17:42:54Z | 14f8f9373d8662b145bf72c62f4f8d2410ba9f8a9e451b0c22951252d81efd20 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0bb1b8a1-24a2-5e40-818e-29621e6017d1.json | https://web.archive.org/web/20260719174254/https://www.coltdatacentres.net/en-GB/our-locations/data-centre-locations-europe/paris-2
0c2462c8-8407-550b-8c6a-a49848f1c879 | ["imported:geometry","imported:record"] | ["8d3985c2-7777-5c6b-9a7f-fcab6c9b6a4f"] | other | Mesa, Arizona | https://en.wikipedia.org/wiki/Mesa,_Arizona | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 1e9742c3285ff879bc6c36994eae7d57d386905de7432d34f12918d5ee27b7bf | unknown | source_record_projection | meta-mesa-arizona | s6 | 690a5d65866311037933f9ddd4b78f9f474ed7fab8310573de902132c5585030 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0c2462c8-8407-550b-8c6a-a49848f1c879.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Mesa,_Arizona
0cabe4a2-5a81-55b7-ad0b-bdd36a74e213 | ["context:geometry_identity","context:site_distinctness"] | ["762397cd-ffc7-55c2-936e-af38cb8d4d0c"] | government_record | Public notice binds WVR113311 to Monarch Cloud Campus LLC | https://apps.dep.wv.gov/ListServ/api.cfc?method=viewMessage | West Virginia Department of Environmental Protection | americas_round16_monarch | no-open-license-asserted | West Virginia Department of Environmental Protection | 2026-03-20T21:55:17Z | 2026-09-09T04:27:54.025Z | 11c94f9a8a2cae6c2a03b38bc5f8d86af9e67e1592574b37532d55f0b9220a70 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0cabe4a2-5a81-55b7-ad0b-bdd36a74e213.json | https://web.archive.org/web/20260909042754/https://apps.dep.wv.gov/ListServ/api.cfc?method=viewMessage
0cad69d1-3151-5073-af8e-73f8401bf2cb | ["geometry"] | ["6f0acd88-cd04-5f3f-915c-48a71fd51f39"] | openstreetmap | OpenStreetMap way 1476734418: Project Jupiter | https://www.openstreetmap.org/way/1476734418 | OpenStreetMap contributors | openstreetmap | ODbL-1.0 | © OpenStreetMap contributors | 2026-06-20T12:23:52Z | 2026-07-18T18:15:02.152575Z | 5b2cf1fffa8582fc7302db34ab8d69dab067ab61a98be479f70e6404b469dcb7 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0cad69d1-3151-5073-af8e-73f8401bf2cb.json | https://web.archive.org/web/20260718181502/https://www.openstreetmap.org/way/1476734418
0cb2d25c-611d-5bdf-9af0-71547a3b740e | ["imported:record","imported:status","metric:investment","metric:jobs_construction","metric:jobs_permanent","milestone:first_operational","role:developer"] | ["a7a29c6e-70aa-5f7b-b172-d1abe208715e"] | news | New data centres: CloudHQ invests USD 4.8 billion in Mexico | https://heise.de/-10678892 | heise online | heise.de | source-terms-not-recorded | heise online | 2025-09-29 | 2026-10-09 | 6ba763960174235cd32a44599b773f910f73759fc6e01a90c22d90ad39d59f33 | day | source_record_projection | cloudhq-queretaro | s4 | e5fc1c4b95552e1f066ffad711ea763302ef3b9f31617b210adb0554fb9d29f9 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0cb2d25c-611d-5bdf-9af0-71547a3b740e.json | https://web.archive.org/web/20261009/https://heise.de/-10678892
0cd43266-a677-5102-a00b-577a5649e5f2 | ["imported:record","imported:status","metric:buildings","metric:jobs_permanent","metric:land_area","milestone:construction_started","milestone:permit_approved","role:developer"] | ["dc6f83d9-dac5-563a-ba7e-ff18e27ba506"] | other | Salem Township Innovation Campus | https://www.amazoninnovationinpa.com/salem-township-innovation-campus/ | Amazon Innovation in PA (project website) | www.amazoninnovationinpa.com | source-terms-not-recorded | Amazon Innovation in PA (project website) |  | 2026-10-09 | 048b0e07e3098f75e83e96b9e2c94a403cd4a0b33b714f22324fe50a92ff1894 | unknown | source_record_projection | aws-salem-township-pennsylvania | s6 | 4dd6dde012f8c93b41327c85112d56db632e692cc634ebdc5e6570285d367043 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0cd43266-a677-5102-a00b-577a5649e5f2.json | https://web.archive.org/web/20261009/https://www.amazoninnovationinpa.com/salem-township-innovation-campus/
0cd7c212-77b6-569f-9b56-0f107bec6d3c | ["imported:geometry","imported:record","imported:status","metric:investment","milestone:permit_approved","power_source:other","role:developer","role:government"] | ["2a418e82-60a0-52bf-ac57-8e0e3d3eabdb"] | news | 'We just don't want them': Hundreds gather in a Kildare town over data centre plans | https://www.irishtimes.com/ireland/2026/09/04/naas-has-a-message-for-the-bond-villains-we-dont-want-your-data-centres/ | The Irish Times | www.irishtimes.com | source-terms-not-recorded | The Irish Times | 2026-09-04 | 2026-10-09 | 651dd49137940ea806faa36e6331a36b203ac04eb20a40da02d0f27733a1e24c | day | source_record_projection | herbata-naas | s5 | 29b656bc7d083a6924175ee16b7bfaa8b3a4ca4c4859a471e7907432dc262ac6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0cd7c212-77b6-569f-9b56-0f107bec6d3c.json | https://web.archive.org/web/20261009/https://www.irishtimes.com/ireland/2026/09/04/naas-has-a-message-for-the-bond-villains-we-dont-want-your-data-centres/
0ce3803d-4613-5202-9599-9ce610e3bd1f | ["context:geometry_identity","context:site_distinctness"] | ["d6a6d399-4580-54f8-80de-1dc0854e4699"] | government_record | Butler County Auditor exact developer former-parcel set | https://maps.butlercountyauditor.org/arcgis/rest/services/basemap_wgs84/MapServer/1/query?where=UPPER%28OWNER%29%20LIKE%20%27%25TRENTON%20DATA%20CENTER%25%27&outFields=OBJECTID%2CPIN%2CPARID%2COWNER%2CACRES%2CLOCATION%2CLEGAL1%2CLEGAL2%2CLEGAL3&returnGeometry=true&f=json | Butler County Auditor; source attribution Butler County Engineer | root_round32_trenton | no-open-license-asserted | Butler County Auditor; source attribution Butler County Engineer |  | 2026-09-10T00:00:48.138Z | f216acd32e92e2061ea5a70a8368ffab6a15d1b7f488b2228b13b1a814b6fca1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ce3803d-4613-5202-9599-9ce610e3bd1f.json | https://web.archive.org/web/20260910000048/https://maps.butlercountyauditor.org/arcgis/rest/services/basemap_wgs84/MapServer/1/query?where=UPPER%28OWNER%29%20LIKE%20%27%25TRENTON%20DATA%20CENTER%25%27&outFields=OBJECTID%2CPIN%2CPARID%2COWNER%2CACRES%2CLOCATION%2CLEGAL1%2CLEGAL2%2CLEGAL3&returnGeometry=true&f=json
0ceb23a4-a4de-5d14-8ae4-328ee9bf3212 | ["imported:geometry","imported:record","imported:status","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:construction_started","milestone:first_operational","power_source:grid","power_source:natural_gas_onsite","role:developer"] | ["602d4e58-abef-54a7-b8f6-894a714e7174"] | company_disclosure | Bitdeer breaks ground on new energy and digital infrastructure facility in Alberta, Canada | https://www.bnnbloomberg.ca/press-releases/2026/06/02/bitdeer-breaks-ground-on-new-energy-and-digital-infrastructure-facility-in-alberta-canada/ | Bitdeer Technologies Group (press release via BNN Bloomberg) | www.bnnbloomberg.ca | source-terms-not-recorded | Bitdeer Technologies Group (press release via BNN Bloomberg) | 2026-06-02 | 2026-10-09 | 80f1fc0bca32b71370ae08b21a7526bdd1973ee05c3a4128148a6c7718f71dfe | day | source_record_projection | bitdeer-fox-creek | s2 | f745c0fc027e66d0a064cde500d844a27c571e80ddd2d7fad377deefd0e77fe1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ceb23a4-a4de-5d14-8ae4-328ee9bf3212.json | https://web.archive.org/web/20261009/https://www.bnnbloomberg.ca/press-releases/2026/06/02/bitdeer-breaks-ground-on-new-energy-and-digital-infrastructure-facility-in-alberta-canada/
0ceea970-6b27-5b46-945e-0e9dd038f9e3 | ["context:site_distinctness","geometry"] | ["e8a1add0-19fb-5196-ae75-34353e7d580b"] | openstreetmap | OSM node documentation: WGS84 geographic coordinates | https://wiki.openstreetmap.org/wiki/Node | OpenStreetMap contributors | europe_round31_firmus_st_leonards | CC-BY-SA-2.0 | OpenStreetMap contributors |  | 2026-09-09T23:35:07.659Z | fb320036a9c16ec2bcbda65297ab47572d429f17b1572a98d9bf76078f9a0b24 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ceea970-6b27-5b46-945e-0e9dd038f9e3.json | https://web.archive.org/web/20260909233507/https://wiki.openstreetmap.org/wiki/Node
0d151e84-b2af-5d9b-b996-2fe97116bb58 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["546bf83f-2bb4-5539-b576-6b7100981420"] | company_disclosure | DataBank reports current construction across its Red Oak first phase | https://www.databank.com/resources/news/inside-databanks-multibillion-dollar-red-oak-data-center-campus/ | DataBank | americas_round29_databank_red_oak | no-open-license-asserted | DataBank | 2026-07-26 | 2026-09-09T11:09:13.201Z | d77fa7a5d2dc2c39a71133ec0c0260b3de94b529cac7c6ba0294cc4adfb800c7 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0d151e84-b2af-5d9b-b996-2fe97116bb58.json | https://web.archive.org/web/20260909110913/https://www.databank.com/resources/news/inside-databanks-multibillion-dollar-red-oak-data-center-campus/
0d31dbb3-2807-5bee-b1e8-d707502791a2 | ["imported:record","imported:status","metric:power_capacity","milestone:first_operational","milestone:other","role:developer"] | ["eb75ea0d-8dba-56a1-a956-135227b3d6e6"] | company_disclosure | TeraWulf reports second quarter 2026 results | https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results | TeraWulf | investors.terawulf.com | source-terms-not-recorded | TeraWulf | 2026-08-05 | 2026-10-09 | 59749fea849ef437f7576699b9da982577ad7b4fd15f1ba2ccf544fac3159800 | day | source_record_projection | terawulf-chesapeake-morgantown | s2 | 18df935aca0ec49662ebb793329c8d784f2190244ab66828c6c9d0f1e558aeb6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0d31dbb3-2807-5bee-b1e8-d707502791a2.json | https://web.archive.org/web/20261009/https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results
0d9d52ab-0c73-536a-8c47-cd1691698743 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["f595ca9f-e584-5dcb-bf76-38b346f6e4aa"] | company_disclosure | Cipher August 4 business update: Black Pearl Phase II foundations, steel and underground electrical in progress | https://www.globenewswire.com/news-release/2026/08/04/3338166/0/en/cipher-digital-provides-second-quarter-2026-business-update.html | Cipher Digital Inc. | cipher_digital_official_releases | all-rights-reserved | Cipher Digital Inc., via GlobeNewswire | 2026-08-04T11:00:00Z | 2026-09-25T22:15:22.263Z | e11b4a4092c3d7844d87a421aa1129dd1b18fd4fec50590a8630205a730a05bc | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0d9d52ab-0c73-536a-8c47-cd1691698743.json | https://web.archive.org/web/20260925221522/https://www.globenewswire.com/news-release/2026/08/04/3338166/0/en/cipher-digital-provides-second-quarter-2026-business-update.html
0dd3dc39-1457-5bc3-b7d2-7ff44183aed3 | ["context:geometry_identity"] | ["15e0ef92-6408-5517-b0d4-a6b8707745f4"] | company_disclosure | ENKA EDS IST 01 TUZLA identity listing | https://www.enka.com/what-we-do/ | ENKA İnşaat ve Sanayi A.Ş. | enka_corporate_asset_listings | all-rights-reserved | ENKA İnşaat ve Sanayi A.Ş. |  | 2026-07-21T16:52:10Z | 7bc183370fd9f9139ded516fc8895c6f65c3692e03163df6dea38b8695a5b7bf | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0dd3dc39-1457-5bc3-b7d2-7ff44183aed3.json | https://web.archive.org/web/20260721165210/https://www.enka.com/what-we-do/
0dd7a6bd-41cb-5875-a335-cd3a5bf7fc2f | ["imported:geometry","imported:record","imported:status","metric:jobs_construction","milestone:first_operational","power_source:grid","role:tenant"] | ["8aa8e9f5-915e-51f6-bc08-463822cf16f9"] | news | First Look: West Feliciana's data center | https://www.wafb.com/2026/10/05/first-look-west-felicianas-data-center/ | WAFB | www.wafb.com | source-terms-not-recorded | WAFB | 2026-10-05 | 2026-10-09 | 860502fddd7fbb6b04e926d3d4b788aaa41448bbf993dc2704e2c56391ce28b7 | day | source_record_projection | hut8-river-bend-louisiana | s7 | fb7eeaf52bb6e7789effaf24b3ee0bb7e31922a38047e56ede8f20f89e9b204a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0dd7a6bd-41cb-5875-a335-cd3a5bf7fc2f.json | https://web.archive.org/web/20261009/https://www.wafb.com/2026/10/05/first-look-west-felicianas-data-center/
0e272cde-13f1-5c9e-91d4-877af3058c04 | ["imported:geometry","imported:record","role:developer"] | ["c01f2073-5c23-511c-9d85-80ad9345987a"] | company_disclosure | Nebius x Vineland, NJ fact sheet | https://assets.nebius.com/assets/729154ac-8d55-459f-9dd6-8f85a40da15b/NEW%20Vineland%20NJ%20Fact%20Sheet_7.10.26.pdf?cache-buster=2026-07-10T18:45:11.445Z | Nebius | assets.nebius.com | source-terms-not-recorded | Nebius | 2026-07-10 | 2026-10-09 | b7c5eda4bd0fbc84cda9095272bcefbddc78f3e241a319325986ad84e2a5b4cd | day | source_record_projection | nebius-birmingham-alabama | s2 | 0aab4bda32e1c1b74b9110271f1466bebe21f707042341167cb2d486459c1505 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0e272cde-13f1-5c9e-91d4-877af3058c04.json | https://web.archive.org/web/20261009/https://assets.nebius.com/assets/729154ac-8d55-459f-9dd6-8f85a40da15b/NEW%20Vineland%20NJ%20Fact%20Sheet_7.10.26.pdf?cache-buster=2026-07-10T18:45:11.445Z
0e2ea4ee-748a-5425-ba47-816efc6112b4 | ["imported:record","metric:floor_area","metric:power_capacity","milestone:announced","power_source:natural_gas_onsite"] | ["bb1b28fd-610b-5739-b928-e44f21cb6f1b"] | trade_press | VC unveils plan for 7.5 GW data centre in Alberta | https://www.naturalgasworld.com/vc-unveils-plan-for-7.5-gw-data-centre-in-alberta-118787 | Natural Gas World | www.naturalgasworld.com | source-terms-not-recorded | Natural Gas World | 2024-12-09 | 2026-10-09 | 7204f39b7034a321da093e2068dbfe1d050e80c1f93d472de734c65319ff6e5d | day | source_record_projection | wonder-valley-alberta | s2 | 8362b04814249174419268d40122ca73605913dfcf84412d960be5265857e94c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0e2ea4ee-748a-5425-ba47-816efc6112b4.json | https://web.archive.org/web/20261009/https://www.naturalgasworld.com/vc-unveils-plan-for-7.5-gw-data-centre-in-alberta-118787
0e2edc42-b2dd-5f2e-be91-bbb3e5a2abad | ["imported:geometry","imported:record","imported:status","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","role:government","role:utility"] | ["39b97d53-5af7-55ea-bfc4-6f2f08f32e74"] | news | What to know: Kiowa data center planned for Pittsburg County | https://www.newson6.com/data-centers-in-oklahoma/what-to-know-kiowa-data-center-planned-for-pittsburg-county | News On 6 | www.newson6.com | source-terms-not-recorded | News On 6 | 2026-09-08 | 2026-10-09 | 4e5f448ee0d9c631059617372dfe6486adbd9eaf4b0dc162590f28ae1410135f | day | source_record_projection | iren-kiowa-oklahoma | s4 | 7a82fb1816b60ae0736e58a3073374185644fa92a93e57f59148f6d5c023d4fb | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0e2edc42-b2dd-5f2e-be91-bbb3e5a2abad.json | https://web.archive.org/web/20261009/https://www.newson6.com/data-centers-in-oklahoma/what-to-know-kiowa-data-center-planned-for-pittsburg-county
0e3f5300-2d80-546c-86ee-7e8cb231b86a | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:other","role:developer"] | ["bb1b28fd-610b-5739-b928-e44f21cb6f1b"] | company_disclosure | Wonder Valley FAQ | https://www.olearydigital.ai/faq | O'Leary Digital | www.olearydigital.ai | source-terms-not-recorded | O'Leary Digital |  | 2026-10-09 | 17810dc6f48352266e504e44bc5366659531e103dbabe127a541d45f58ef9c6f | unknown | source_record_projection | wonder-valley-alberta | s8 | 8362b04814249174419268d40122ca73605913dfcf84412d960be5265857e94c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0e3f5300-2d80-546c-86ee-7e8cb231b86a.json | https://web.archive.org/web/20261009/https://www.olearydigital.ai/faq
0e479646-8e7b-5f02-ac23-985229195800 | ["context:geometry_identity","context:site_distinctness"] | ["898b0895-99d6-545b-8053-79813ae63ffa"] | company_disclosure | envia TEL LeipzigII event: exact physical venue | https://www.enviatel.de/presse-events/events/envia-tel-reseller-treffen | envia TEL | europe_round28_envia_leipzig | no-open-license-asserted | envia TEL |  | 2026-09-09T10:45:05.671Z | ad270674babade597ad2a4ae93a1bc0fc2294cbd197c8501dcb1fd38e449941f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0e479646-8e7b-5f02-ac23-985229195800.json | https://web.archive.org/web/20260909104505/https://www.enviatel.de/presse-events/events/envia-tel-reseller-treffen
0eb488ab-3c0c-5223-86d8-2b47a96e7476 | ["context:campus_address_identity","physical_status"] | ["b75695b9-38e3-58ec-baf2-039179ab353a"] | company_disclosure | Chirisa Technology Parks data center locations | https://chirisatechnologyparks.com/ | Chirisa Technology Parks | chirisa_technology_parks_locations | all-rights-reserved | Chirisa Technology Parks |  | 2026-07-22T01:27:58Z | 6217db82caf16b110532ddd7ef4a4888f1803a8d590d4920289394b29392cdf3 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0eb488ab-3c0c-5223-86d8-2b47a96e7476.json | https://web.archive.org/web/20260722012758/https://chirisatechnologyparks.com/
0eda5c21-7b89-54f5-92a8-531e280f0d17 | ["imported:geometry","imported:record","metric:jobs_permanent","milestone:announced","milestone:construction_started","power_source:grid","role:developer","role:government"] | ["8d08b021-e457-5102-9ef2-33528ad786d1"] | news | Hobart reaches agreement with Amazon for next-gen data center | https://www.21alivenews.com/2025/11/25/hobart-reaches-agreement-with-amazon-next-gen-data-center/ | 21Alive News (WPTA), from Inside INdiana Business | www.21alivenews.com | source-terms-not-recorded | 21Alive News (WPTA), from Inside INdiana Business | 2025-11-25 | 2026-10-09 | a0a7a8e8b26e0dbc7b9108bd32edf297c904ae8b0393135a0c62fad64cab868b | day | source_record_projection | aws-hobart-indiana | s2 | 51fd6e547d8fd5c8eaa8837b69b75043041b5ae8f9bec2a94b1b95328b7c679b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0eda5c21-7b89-54f5-92a8-531e280f0d17.json | https://web.archive.org/web/20261009/https://www.21alivenews.com/2025/11/25/hobart-reaches-agreement-with-amazon-next-gen-data-center/
0ef731b5-5de7-5370-8051-699baa7ff44e | ["context:geometry_identity","context:site_distinctness"] | ["f595ca9f-e584-5dcb-bf76-38b346f6e4aa"] | government_record | TCEQ Central Registry RN112175997 'BLACK PEARL DATA CENTER' at 11786 CR 209, Wink | https://www15.tceq.texas.gov/crpub/index.cfm?fuseaction=regent.showSingleRN&re_id=313640032025078 | Texas Commission on Environmental Quality | tceq_central_registry | public-record-as-is | Texas Commission on Environmental Quality |  | 2026-09-25T22:21:08.376Z | 6a51d87ad394c48377b1911ad3b17f7d53b2503a08f2b308b83b444ba16e302f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ef731b5-5de7-5370-8051-699baa7ff44e.json | https://web.archive.org/web/20260925222108/https://www15.tceq.texas.gov/crpub/index.cfm?fuseaction=regent.showSingleRN&re_id=313640032025078
0efd0f29-b8d7-5a51-9714-1ed7cb45140d | ["imported:geometry","imported:record","metric:floor_area","metric:investment","metric:land_area","metric:power_capacity","milestone:first_operational","milestone:site_acquired","role:developer","role:owner"] | ["75596cc6-0434-596d-be35-53be39de9c0a"] | company_disclosure | AIデータセンターの構築に向けて、シャープ堺工場の土地や建物の取得に関する契約を締結 | https://www.softbank.jp/corp/news/press/sbkk/2025/20250314_01 | SoftBank Corp. | www.softbank.jp | source-terms-not-recorded | SoftBank Corp. | 2025-03-14 | 2026-10-09 | db7f177db0c20804081c18bffa152fb94b4b147e962181a086ec85ab89e3d834 | day | source_record_projection | softbank-sakai | s3 | 03bed245e3fd6adfb416da230450efa6ff1009a2f6cdecf8a5e45419a5e1039d | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0efd0f29-b8d7-5a51-9714-1ed7cb45140d.json | https://web.archive.org/web/20261009/https://www.softbank.jp/corp/news/press/sbkk/2025/20250314_01
0f6a6cde-f89b-55f8-9fec-f74f96737f10 | ["context:site_distinctness","geometry"] | ["709cd37b-7f3a-5313-b3e2-a18ddc0885ec"] | openstreetmap | Exact relation tags bind1851FM2119 to Core Scientific Pecos | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Brel(20669718)%3Bout%20meta%20geom%3B | © OpenStreetMap contributors | pecos_round15_primary_review | ODbL-1.0 | © OpenStreetMap contributors |  | 2026-09-09T03:14:20.555Z | 6aac6cd5e88caa07f91bd5e14df7982410b788bfe2fcab228dc2ea83eb462fe1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0f6a6cde-f89b-55f8-9fec-f74f96737f10.json | https://web.archive.org/web/20260909031420/https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Brel(20669718)%3Bout%20meta%20geom%3B
0f8bcc15-68a6-5c0c-93be-7c34bddd54a5 | ["imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","milestone:construction_started","role:developer","role:government"] | ["2fc433ea-05de-5b3a-b4a1-bd9d544f8ae3"] | company_disclosure | Meta Temple Data Center fact sheet | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Metas-Temple-Data-Center.pdf | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms |  | 2026-10-09 | c167b2399b799d1717b56fe1bdb09b1cd3e2327ff491d516d251a23c37c5bead | unknown | source_record_projection | meta-temple-texas | s1 | 6558a5072429b8e64f5a5654423c0025443d77b5adf5c9f2228113f65f8fef5c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0f8bcc15-68a6-5c0c-93be-7c34bddd54a5.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/wp-content/uploads/2026/09/Metas-Temple-Data-Center.pdf
0f9a271a-f42e-57c8-ba53-1c96f463c0dc | ["imported:geometry","imported:record","imported:status","metric:investment","milestone:other","milestone:permit_approved","power_source:grid","role:government","role:investor"] | ["f533639a-f574-566d-a780-db81daa4b78c"] | news | Data center de R$ 5 bilhões em Campinas vira alvo do Ministério Público Federal e Estadual | https://www.correiodamanha.com.br/nacional/sao-paulo/campinas/2026/08/314378-data-center-de-rs-5-bi-em-campinas-conti-samia-petta-e-orlando-silva-pedem-suspensao-ao-mpf-e-ao-mp-sp.html | Correio da Manhã | www.correiodamanha.com.br | source-terms-not-recorded | Correio da Manhã | 2026-08-26 | 2026-10-09 | fae6e43cc5a5b550438e5c8cf1732e68fc87e92941b3ba6051cebc4e6538291f | day | source_record_projection | terranova-campinas | s5 | 10b10cc37911cb7289232d3966039f336524d3dca8ba5dcec217129518ac0c7b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0f9a271a-f42e-57c8-ba53-1c96f463c0dc.json | https://web.archive.org/web/20261009/https://www.correiodamanha.com.br/nacional/sao-paulo/campinas/2026/08/314378-data-center-de-rs-5-bi-em-campinas-conti-samia-petta-e-orlando-silva-pedem-suspensao-ao-mpf-e-ao-mp-sp.html
0fa34a95-4233-5fb6-af85-c271b4c81be0 | ["imported:geometry","imported:record","imported:status","milestone:announced","role:developer"] | ["db205e2d-f250-5c0b-861e-1c243f7be933"] | company_disclosure | We're announcing a new data center and energy investments in Gray and Roberts Counties, Texas | https://blog.google/innovation-and-ai/infrastructure-and-cloud/global-network/meitner-energy-center/ | Google | blog.google | source-terms-not-recorded | Google | 2026-06-04 | 2026-10-09 | 3f4dba8431c788eac9372918c400d9ef64578eb0731bab91468869b481fa3629 | day | source_record_projection | google-meitner-energy-center-texas | s1 | edccc714d49695ab62e24100a017138457b7ffddf49d512a8306190a8acbe1ab | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0fa34a95-4233-5fb6-af85-c271b4c81be0.json | https://web.archive.org/web/20261009/https://blog.google/innovation-and-ai/infrastructure-and-cloud/global-network/meitner-energy-center/
0ff34972-d808-5d05-8f04-291c5f48f7ae | ["imported:geometry","imported:record","metric:investment","metric:land_area","metric:power_capacity","role:investor"] | ["46434a5c-4980-5f79-ac83-000783b60566"] | trade_press | Blackstone to make $8.2bn data centre investment in Spain | https://www.investmentmonitor.ai/news/blackstone-to-make-8-2bn-data-centre-investment-in-spain | Investment Monitor | www.investmentmonitor.ai | source-terms-not-recorded | Investment Monitor | 2024-10-16 | 2026-10-09 | 1d5b05f5eddbb80a9414e1f0ce366722769f9148f6bd85a759f1f8f2b3aa53ef | day | source_record_projection | blackstone-calatorao | s2 | 6afcb1fbc59cf3659ffc3e2d0aa618b2fd646f74ecfb8cd734af34d6d752dadf | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0ff34972-d808-5d05-8f04-291c5f48f7ae.json | https://web.archive.org/web/20261009/https://www.investmentmonitor.ai/news/blackstone-to-make-8-2bn-data-centre-investment-in-spain
0fff6073-2536-58db-b16e-b82141605ef5 | ["geometry"] | ["85cb6e56-ec73-5685-82e7-15e4ef96106b"] | government_record | Pottawattamie County address point 2313 College Road | https://gis.pottcounty-ia.gov/arcgis/rest/services/OpenData/MapServer/9/query | Pottawattamie County GIS | pottawattamie_county_open_data_address_points | county-open-data-no-explicit-license | Pottawattamie County GIS |  | 2026-09-07T02:58:43Z | af7fc312e0055acebbbf5bd866219a3d7fd48fc1536c65e1ca5378c979ea8cd1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/0fff6073-2536-58db-b16e-b82141605ef5.json | https://web.archive.org/web/20260907025843/https://gis.pottcounty-ia.gov/arcgis/rest/services/OpenData/MapServer/9/query
100ab544-05a4-5194-a4af-64a391377239 | ["context:site_distinctness","geometry"] | ["546bf83f-2bb4-5539-b576-6b7100981420"] | government_record | Ellis County exact DFW10 site-address reference point | https://maps.co.ellis.tx.us/arcgis/rest/services/Elections/External_Elections_Web_Map/MapServer/888/query?objectIds=70622&outFields=OBJECTID,Address,AddressLong,LandmkName,Placement,Parcel_ID,Source,DateUpdate,Post_Comm,Post_Code&returnGeometry=true&outSR=2276&f=json | Ellis County, Texas GIS | americas_round29_databank_red_oak | no-open-license-asserted | Ellis County, Texas GIS |  | 2026-09-09T11:20:34.448Z | 1caacda18e102d24ec51eeb568cee6f571d0259d4c988919e0ee95abef71b6d0 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/100ab544-05a4-5194-a4af-64a391377239.json | https://web.archive.org/web/20260909112034/https://maps.co.ellis.tx.us/arcgis/rest/services/Elections/External_Elections_Web_Map/MapServer/888/query?objectIds=70622&outFields=OBJECTID,Address,AddressLong,LandmkName,Placement,Parcel_ID,Source,DateUpdate,Post_Comm,Post_Code&returnGeometry=true&outSR=2276&f=json
102ff694-04d2-53be-8f07-919dbe28d2a4 | ["imported:geometry","imported:record","metric:power_capacity","milestone:first_operational","milestone:other","power_source:grid","role:developer","role:operator","role:power_supplier","role:tenant"] | ["e389cd04-b538-5729-85a5-8e0b18e78002"] | regulatory_filing | TeraWulf Inc. Form 10-K for the fiscal year ended December 31, 2025 | https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm | U.S. Securities and Exchange Commission (TeraWulf filing) | www.sec.gov | source-terms-not-recorded | U.S. Securities and Exchange Commission (TeraWulf filing) | 2026-02-27 | 2026-10-09 | e334cb93b63e7a8a284a828109f8b1c4c2d5ba6224accc92ae4068b1d1a9c18c | day | source_record_projection | terawulf-lake-mariner | s4 | 081cc26c2e57d03704aae2b9dbe919a2c59626dbb9bf84295aa36cf2d26e6106 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/102ff694-04d2-53be-8f07-919dbe28d2a4.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm
103edd8f-a15e-54f0-802f-cd68c47df0ea | ["context:site_distinctness","geometry"] | ["d5b84301-4f54-5958-a0d1-fd2c5a72cc5b"] | government_record | Exact public parcel-service item rights and accuracy limitations | https://gis.palmcoast.gov/portal/sharing/rest/content/items/14e7221cb8224211b02185fdb1a76863?f=json | City of Palm Coast; Flagler Property Appraiser | americas_round28_palm_coast | no-open-license-asserted | City of Palm Coast; Flagler Property Appraiser |  | 2026-09-09T10:38:53.690Z | 9be564e35c63d22649e0c86af1f09b686fae859e1d4424e9d8fb3b81b395d412 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/103edd8f-a15e-54f0-802f-cd68c47df0ea.json | https://web.archive.org/web/20260909103853/https://gis.palmcoast.gov/portal/sharing/rest/content/items/14e7221cb8224211b02185fdb1a76863?f=json
10ba1957-5dd6-5ad0-aad7-d2437baa1e5e | ["imported:geometry","imported:record"] | ["3fc18374-cbc2-5a11-9356-ab751ac3820c"] | other | Praia Grande | https://en.wikipedia.org/wiki/Praia_Grande | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | a883cbd4e203d472d924de56494ff92434af66d97b1ea376f5e847352012e21b | unknown | source_record_projection | terranova-praia-grande | s3 | 5c9ae8c619cac9aebd8c46a9f663565f736bbff88406ff9954317ab8129db32a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/10ba1957-5dd6-5ad0-aad7-d2437baa1e5e.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Praia_Grande
10cad266-3d5e-591d-a1c4-8ded1e082c7b | ["typed_metric:critical_it_mw"] | ["ea4a0cc5-bb09-5a81-b385-38ae79baf22a"] | company_disclosure | Treasurer Tops Out Macquarie Data Centres' Newest 47MW AI and Cloud Data Centre | https://www.macquariedatacentres.com/blog/treasurer-tops-out-macquarie-data-centres-newest-47mw-ai-and-cloud-data-centre/ | Macquarie Data Centres | macquarie_data_centres_newsroom | all-rights-reserved | Macquarie Data Centres | 2025-12-03T03:23:55+00:00 | 2026-07-20T00:53:38Z | f8f86d1d3f36d46c81f9fe23edce1416f11193e7a16fc32014f98acd96f053e3 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/10cad266-3d5e-591d-a1c4-8ded1e082c7b.json | https://web.archive.org/web/20260720005338/https://www.macquariedatacentres.com/blog/treasurer-tops-out-macquarie-data-centres-newest-47mw-ai-and-cloud-data-centre/
11086c9d-4b87-5828-8aa8-8bc8dce80f2c | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["c7eebc15-358c-5985-9a48-16f53bdd4726"] | company_disclosure | Indonet June 2026 financial statements: EDGE2 phase-3 construction in progress | https://indonet.id/wp-content/uploads/2026/08/FS-Indonet-30-June-2026.pdf | PT Indointernet Tbk | indonet_consolidated_financial_statements | all-rights-reserved | PT Indointernet Tbk |  | 2026-09-10T17:55:59.095Z | 9f1480b169d2df05a37977879ecb81f77ccadccf8cf619e830f4878beb64b6c0 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/11086c9d-4b87-5828-8aa8-8bc8dce80f2c.json | https://web.archive.org/web/20260910175559/https://indonet.id/wp-content/uploads/2026/08/FS-Indonet-30-June-2026.pdf
111e4ef0-d1c4-5b87-8c40-be427705300f | ["context:site_distinctness","geometry"] | ["3e074273-f5f7-5785-ab10-232a5ebd5c6b","9563b94b-4d68-5f38-b2b2-ce63346ebbe8"] | company_disclosure | Hut 8 frontend named marker derivation | https://www.hut8.com/_nuxt/D5nZ9oDL.js | Hut 8 Corp. | americas_round9_hut8 | all-rights-reserved | Hut 8 Corp. |  | 2026-09-08T23:16:24.414Z | 832b2a3b34eb077b91faeb7bd5d3575f884ab65d1544dfa8d741bd78f29a4d8e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/111e4ef0-d1c4-5b87-8c40-be427705300f.json | https://web.archive.org/web/20260908231624/https://www.hut8.com/_nuxt/D5nZ9oDL.js
117a516b-4901-56d6-8322-ad8efe5b2ddd | ["imported:geometry","imported:record","imported:status","metric:buildings","milestone:other","power_source:grid","role:developer","role:government"] | ["15360f72-acfa-572f-aac9-eb117ae9fc0d"] | government_record | Plan de Interés General de Aragón Green It Aragón | https://www.aragon.es/-/piga-green-it | Gobierno de Aragón | www.aragon.es | source-terms-not-recorded | Gobierno de Aragón | 2026-07-07 | 2026-10-09 | e10a12fc396671e2961207e08fd3326b7441caee16e0cdd4286cea7f503437d8 | day | source_record_projection | samca-green-it-aragon-luceni | s1 | e8260b20d552deefda45a4ad13f6c0fb3681dc3da63f5e6e3901bc4240b50619 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/117a516b-4901-56d6-8322-ad8efe5b2ddd.json | https://web.archive.org/web/20261009/https://www.aragon.es/-/piga-green-it
118332ce-15bf-5316-893a-cf74ce75462d | ["context:geometry_identity","context:site_distinctness"] | ["709cd37b-7f3a-5313-b3e2-a18ddc0885ec"] | company_disclosure | Issuer leadership links exact CEO author profile | https://corescientific.com/about/leadership/ | Core Scientific, Inc. | pecos_round15_primary_review | no-open-redistribution-license-asserted | Core Scientific, Inc.; Adam Sullivan |  | 2026-09-09T03:39:56Z | ef597233cae85670cc50fb02236afab66decf109658eb9cbb7be7a65e5c5466f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/118332ce-15bf-5316-893a-cf74ce75462d.json | https://web.archive.org/web/20260909033956/https://corescientific.com/about/leadership/
11e06062-9188-5c5b-8df8-8f557f27c7e6 | ["physical_status"] | ["b0be5071-aff0-5470-a041-a0be3cc8385a"] | company_disclosure | Goodman FY26 Results - MAD01 current development | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | Goodman Group | goodman_group_investor_presentations | all-rights-reserved | Goodman Group | 2026-08-19 | 2026-09-08T18:38:25Z | 892c9d069276912a13d2ff100ff3260b1c2d26874693d644e0d34dce3a7d809d | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/11e06062-9188-5c5b-8df8-8f557f27c7e6.json | https://web.archive.org/web/20260908183825/https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1
1201b25d-ce3a-519c-b327-3e27c110d04c | ["context:site_distinctness"] | ["5ace12f8-658e-5956-9173-d78e625d4df9"] | company_disclosure | DataOne Vineland undated construction and delivery context | https://askvineland.dataone.eu/ | DataOne | us_round23_dataone_vineland | no-open-license-asserted | DataOne |  | 2026-09-09T07:48:29Z | 6542c20e3d641b48261990d6073e2346540d386e1e8795caa91f61312bb28aec | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1201b25d-ce3a-519c-b327-3e27c110d04c.json | https://web.archive.org/web/20260909074829/https://askvineland.dataone.eu/
12061b36-621f-5896-9816-570fc1e6d37f | ["imported:geometry","imported:record","imported:status","metric:power_capacity","milestone:announced","milestone:first_operational","power_source:other","role:builder","role:developer","role:operator","role:power_supplier","role:tenant"] | ["987638c1-43b0-5075-a91a-f02ac2f007cc"] | company_disclosure | Reliance and Meta to Develop AI-Enabled Data Centre in Jamnagar, Gujarat | https://www.ril.com/sites/default/files/2026-06/10062026_MR_Reliance_and_Meta_to_Develop_AI-Enabled_Data_Centre_in_Jamnagar_Gujarat.pdf | Reliance Industries Limited | www.ril.com | source-terms-not-recorded | Reliance Industries Limited | 2026-06-10 | 2026-10-09 | 752f9018a7b2c3121ddfc8ac71209b487f6d24e5772f105c3c3172eba7fa34a8 | day | source_record_projection | reliance-jamnagar-ai-data-center | s1 | 8728624624506889a917efa504539545fa6de92360d5f39b83f3ac96b202431e | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/12061b36-621f-5896-9816-570fc1e6d37f.json | https://web.archive.org/web/20261009/https://www.ril.com/sites/default/files/2026-06/10062026_MR_Reliance_and_Meta_to_Develop_AI-Enabled_Data_Centre_in_Jamnagar_Gujarat.pdf
123278b3-cec1-5c38-b035-facda8b70f25 | ["context:site_distinctness","geometry"] | ["c1016e49-7b45-52ff-8938-0bd01e78a7ad"] | openstreetmap | Named DVZ data-center campus community locator | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bnwr%5B%22name%22~%22DVZ%7CDatenverarbeitungszentrum%22%2Ci%5D%2853.6%2C11.3%2C53.7%2C11.45%29%3Bout%20meta%20center%3B | OpenStreetMap contributors via Overpass | europe_round5_dvz_schwerin | ODbL-1.0 | OpenStreetMap contributors via Overpass |  | 2026-09-08T22:03:03Z | b14676d43662227726f397ec88aa8f438f0853fc8e5485c11bb9c6cd1a98b5c6 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/123278b3-cec1-5c38-b035-facda8b70f25.json | https://web.archive.org/web/20260908220303/https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bnwr%5B%22name%22~%22DVZ%7CDatenverarbeitungszentrum%22%2Ci%5D%2853.6%2C11.3%2C53.7%2C11.45%29%3Bout%20meta%20center%3B
1259e6c5-d7bd-5b59-bd22-95b2f92da07c | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:floor_area","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","milestone:construction_started","milestone:zoning_approved","role:government"] | ["ca9b7a8f-2f71-5996-8ef1-66d4a2bfe2fa"] | trade_press | Go-ahead for Microsoft's £4bn Leeds data hub push | https://www.constructionenquirer.com/2026/04/27/go-ahead-for-microsofts-4bn-leeds-data-hub-push/ | Construction Enquirer | www.constructionenquirer.com | source-terms-not-recorded | Construction Enquirer | 2026-04-27 | 2026-10-09 | 1af8d885bb576067453c6e54ff1e434f20214d370d243388ec872204f201e534 | day | source_record_projection | microsoft-skelton-grange-leeds | s3 | 9060bb11a242aa6d4b736bffada87ddb9a23ac1c4462581a4aa1aea25874a7b5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1259e6c5-d7bd-5b59-bd22-95b2f92da07c.json | https://web.archive.org/web/20261009/https://www.constructionenquirer.com/2026/04/27/go-ahead-for-microsofts-4bn-leeds-data-hub-push/
12674abe-1b54-563d-adbe-b2b32893468c | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:land_area","metric:power_capacity","milestone:cancelled","role:developer","role:government"] | ["908ba9ce-1e84-567b-926f-8d47d4d2a7ed"] | news | Pittsylvania rejects data center project that has dominated county conversation for 6 months | https://cardinalnews.org/2025/04/16/pittsylvania-rejects-data-center-project-that-has-dominated-county-conversation-for-6-months/ | Cardinal News | cardinalnews.org | source-terms-not-recorded | Cardinal News | 2025-04-16 | 2026-10-09 | f94270d524a0e21d4ba41f3b6c9e58cccc5544024566e3208e8daec3a9831561 | day | source_record_projection | balico-pittsylvania-county | s4 | 9169c30b464bb8fd99931fce532ae356b7455ba9eb4e67c4c9c205374c151b21 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/12674abe-1b54-563d-adbe-b2b32893468c.json | https://web.archive.org/web/20261009/https://cardinalnews.org/2025/04/16/pittsylvania-rejects-data-center-project-that-has-dominated-county-conversation-for-6-months/
1293fc76-3f6d-560f-9cb3-7ea2a0751450 | ["context:site_distinctness","geometry"] | ["5bfb4ad8-a8f4-5937-9242-a96f9292c385"] | openstreetmap | Nominatim identifies the named CSC building at Tehdaskatu 15 | https://nominatim.openstreetmap.org/search?q=CSC%20Kajaani&format=jsonv2&addressdetails=1 | OpenStreetMap contributors / Nominatim | europe_round15_csc_lumi_ai | ODbL-1.0 | © OpenStreetMap contributors |  | 2026-09-09T03:38:46Z | 0130bbda2be1d73efbf6e3dd5ecd3fa5bd389d1768ec2ef2d652799346468172 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1293fc76-3f6d-560f-9cb3-7ea2a0751450.json | https://web.archive.org/web/20260909033846/https://nominatim.openstreetmap.org/search?q=CSC%20Kajaani&format=jsonv2&addressdetails=1
12be03bb-d41e-5223-a7e2-201289a9d236 | ["context:geometry_identity","context:site_distinctness"] | ["0fd5e6a4-6421-5a23-b51c-e490e4a79cd9"] | government_record | SEMACE same-company licensing records, public page 2 | https://servicos.semace.ce.gov.br/SemaceMobileWS/webService/consultaProcesso/processos | Superintendência Estadual do Meio Ambiente do Ceará (SEMACE) | americas_round26_omnia_pecem | no-open-license-asserted | Superintendência Estadual do Meio Ambiente do Ceará (SEMACE) |  | 2026-09-09T09:45:45.148297Z | 1dbf0e3835293ededa1f32b17aec09b0e142b36d7c2d89d10bcb493ae66b485e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/12be03bb-d41e-5223-a7e2-201289a9d236.json | https://web.archive.org/web/20260909094545/https://servicos.semace.ce.gov.br/SemaceMobileWS/webService/consultaProcesso/processos
12f5d89c-ebd5-501c-8f98-62e845710d8c | ["geometry"] | ["0a075c8d-2733-5aba-b19a-4b53e51fd8f8"] | government_cadastral_api | Kartverket matrikkelteig union 1121-46/316, 1121-46/317 and 1121-46/319 | https://api.kartverket.no/eiendom/v1 | Kartverket | kartverket_open_property_api | CC-BY-4.0 | © Kartverket |  | 2026-08-20T19:49:51Z | 6bcd905d036ecde8e55ef4933bf1502f58a58701e5784583fdc3bccc5c6edd1f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/12f5d89c-ebd5-501c-8f98-62e845710d8c.json | https://web.archive.org/web/20260820194951/https://api.kartverket.no/eiendom/v1
131dc75e-a3a4-5ae0-a7fb-ff8b0104bed8 | ["context:geometry_identity","context:site_distinctness"] | ["c23fe40c-0685-5cee-8fab-9c08575e6b27"] | government_record | City document index explicitly names QTS DEN1 DC2 at1140 Gun Club | https://coaapps.auroragov.org/publicdocuments/publicrecordsearch.aspx?locationkey=227490 | City of Aurora, Colorado | americas_round24_qts_aurora | no-open-license-asserted | City of Aurora, Colorado |  | 2026-09-09T07:49:37.833480+00:00 | ff9a7b4efd31c5ea0ac21885784d270cf48edb5e8698cfd430c37d1e260c541d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/131dc75e-a3a4-5ae0-a7fb-ff8b0104bed8.json | https://web.archive.org/web/20260909074937/https://coaapps.auroragov.org/publicdocuments/publicrecordsearch.aspx?locationkey=227490
1337f6ef-1e09-5b6e-a1e0-55fbdcf95bf3 | ["operating_model","role:operator"] | ["44130f9f-95af-5f19-9fcf-47aabd3a5c8b"] | company_disclosure | About Akashi | https://akashi.cloud/about/ | Akashi Data Center | akashi_data_center_project_pages | all-rights-reserved | Akashi Data Center |  | 2026-07-21T12:22:07Z | 01e105af2a09a3e96987bccde8d7c7cc68cf6add95ab48c6d9286e4dca5ce774 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1337f6ef-1e09-5b6e-a1e0-55fbdcf95bf3.json | https://web.archive.org/web/20260721122207/https://akashi.cloud/about/
136e7452-1116-5bcc-8846-7412269c17ab | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","power_source:grid","role:developer","role:utility"] | ["e9f8645b-ff54-5ebb-8f6c-6c04dbc8d5e2"] | news | New details out on massive data center planned in Pittsylvania County | https://www.wdbj7.com/2026/04/30/new-details-massive-data-center-planned-pittsylvania-county/ | WDBJ7 | www.wdbj7.com | source-terms-not-recorded | WDBJ7 | 2026-04-30 | 2026-10-09 | cf226367e3d0fe16ce1754dbea90791b9bd84e8ef3992f16b8843e5c1f7b4f2d | day | source_record_projection | stack-berry-hill-pittsylvania-county | s2 | d2020bfa59b7a7adbcb7c333acb3d94bcd1996ebae3d0c2cef21f293d0cbdbff | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/136e7452-1116-5bcc-8846-7412269c17ab.json | https://web.archive.org/web/20261009/https://www.wdbj7.com/2026/04/30/new-details-massive-data-center-planned-pittsylvania-county/
1375d1b3-7de9-5b6a-8109-6c33626a675e | ["imported:record","imported:status","milestone:construction_started","role:operator"] | ["7c9397d2-971c-5d1e-ad58-210d19777a37"] | company_disclosure | Indiana - Google Data Center Location | https://datacenters.google/locations/indiana/ | Google | datacenters.google | source-terms-not-recorded | Google |  | 2026-10-09 | bb619c7a1c177ef05be651415013d6c0fcf1d6507dbf9f27379aa9fc1c458bd2 | unknown | source_record_projection | google-fort-wayne-indiana | s2 | 140e615990e16bd1d60c983ff139345118f93e72fd9ebd3a99658c8db663db69 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1375d1b3-7de9-5b6a-8109-6c33626a675e.json | https://web.archive.org/web/20261009/https://datacenters.google/locations/indiana/
1396cf0e-0de1-5c51-ab78-5e027fd4a6e8 | ["context:site_distinctness","geometry"] | ["b9ccc1e7-c2da-5822-82bc-b20be7d43dfe"] | government_record | City service transforms exact address point into EPSG4326 | https://kartta.lappeenranta.fi/IMS/fi/Transform?north=6771752&east=28515420&targetSystem=EPSG%3A4326&decimalCount=8 | City of Lappeenranta via Trimble IMS | europe_round5_exact_locators | no-open-license-asserted | City of Lappeenranta via Trimble IMS |  | 2026-09-08T21:48:12Z | 29017038745012c333210dd11624040ad854ac33c0986e6c902317c09b6d7cb1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1396cf0e-0de1-5c51-ab78-5e027fd4a6e8.json | https://web.archive.org/web/20260908214812/https://kartta.lappeenranta.fi/IMS/fi/Transform?north=6771752&east=28515420&targetSystem=EPSG%3A4326&decimalCount=8
13a65a07-1b3a-58a3-9ca7-b98723686f7c | ["geometry"] | ["c73ac912-e44d-5477-84f5-c5beb4813518"] | openstreetmap | OpenStreetMap way 1334234458: Amazon AWS PHL | https://www.openstreetmap.org/way/1334234458 | OpenStreetMap contributors | openstreetmap | ODbL-1.0 | © OpenStreetMap contributors | 2026-04-20T12:38:41Z | 2026-07-18T18:15:02.152575Z | c54668987cf45c4196dbc111ea2b12451f5b68d5513661a1f0333f2fadc12945 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/13a65a07-1b3a-58a3-9ca7-b98723686f7c.json | https://web.archive.org/web/20260718181502/https://www.openstreetmap.org/way/1334234458
13b41dff-6c36-562b-a775-d58b65d98d2e | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:construction_started","milestone:first_operational","power_source:grid","role:developer","role:government","role:utility"] | ["4a2a09d1-1ace-5ff8-a80f-89996cda5799"] | company_disclosure | Rowan Powers Texas Growth as Construction Begins on 300 MW Temple Data Center | https://rowan.com/rowan-powers-texas-growth-as-construction-begins-on-300-mw-temple-data-center/ | Rowan Digital Infrastructure | rowan.com | source-terms-not-recorded | Rowan Digital Infrastructure | 2026-01-05 | 2026-10-09 | 15923c01ef84b9eaab53749df6bd1abaa8083bad7efce523bf70d4b77e66f86d | day | source_record_projection | rowan-project-temple | s1 | ac6a9ba056d88fd802fe69828988dcb7d1f1434be4bf4235730b1b47e5aeeacb | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/13b41dff-6c36-562b-a775-d58b65d98d2e.json | https://web.archive.org/web/20261009/https://rowan.com/rowan-powers-texas-growth-as-construction-begins-on-300-mw-temple-data-center/
13b65ece-f1a8-5ac6-8475-abb4caf98391 | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:construction_started","milestone:first_operational","role:developer"] | ["ffbda424-5468-5619-97e8-3a32b0522e79"] | company_disclosure | EdgeConneX、関西エリアに200MWのAI対応ハイパースケールキャンパスの開発に着手 | https://www.edgeconnex.com/news/press-releases/edgeconnex%e3%80%81%e9%96%a2%e8%a5%bf%e3%82%a8%e3%83%aa%e3%82%a2%e3%81%ab200mw%e3%81%aeai%e5%af%be%e5%bf%9c%e3%83%8f%e3%82%a4%e3%83%91%e3%83%bc%e3%82%b9%e3%82%b1%e3%83%bc%e3%83%ab%e3%82%ad%e3%83%a3/ | EdgeConneX | www.edgeconnex.com | source-terms-not-recorded | EdgeConneX | 2026-03-18 | 2026-10-09 | 7de0786b54342483859a17da7d0accb61588a52704cda8d036b3e648ab634227 | day | source_record_projection | edgeconnex-kyotanabe-greater-osaka | s2 | 619d837902d48c8a51fdbfce5f4497b70709e4975695f25a0ed70d39a0659b60 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/13b65ece-f1a8-5ac6-8475-abb4caf98391.json | https://web.archive.org/web/20261009/https://www.edgeconnex.com/news/press-releases/edgeconnex%e3%80%81%e9%96%a2%e8%a5%bf%e3%82%a8%e3%83%aa%e3%82%a2%e3%81%ab200mw%e3%81%aeai%e5%af%be%e5%bf%9c%e3%83%8f%e3%82%a4%e3%83%91%e3%83%bc%e3%82%b9%e3%82%b1%e3%83%bc%e3%83%ab%e3%82%ad%e3%83%a3/
13c130cf-a2a7-51db-9d24-6b6aef94d717 | ["imported:geometry","imported:record","imported:status","metric:power_capacity","milestone:other","role:developer"] | ["352e29e6-cabf-5acb-bd20-619157576502"] | trade_press | KIO Plans US$1.3 Billion Data Center in Queretaro | https://mexicobusiness.news/trade-and-investment/news/kio-plans-us13-billion-data-center-queretaro | Mexico Business News | mexicobusiness.news | source-terms-not-recorded | Mexico Business News | 2026-08-14 | 2026-10-09 | 73bdfb906685bd78e9c09e22ea6770527c3593b6577889aa0b258d36ed4df783 | day | source_record_projection | kio-qro3-queretaro | s1 | 3fcbdddd0394a4007cbb1d1f2f5f6b03be006d2c4278b477af1a718d233745c9 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/13c130cf-a2a7-51db-9d24-6b6aef94d717.json | https://web.archive.org/web/20261009/https://mexicobusiness.news/trade-and-investment/news/kio-plans-us13-billion-data-center-queretaro
13d05dfa-7a3e-5ac5-a544-1fd5420dad90 | ["context:site_distinctness"] | ["cbe074bd-68d8-59cb-aaf7-e21fa82b193f"] | company_disclosure | Amazon's August 18 update: Bossier retained in northwest Louisiana campus plans | https://www.aboutamazon.com/news/company-news/amazon-data-center-louisiana-new-jobs | Amazon | amazon_official_company_news | all-rights-reserved | Amazon | 2026-02-23 | 2026-09-10T18:37:08.831Z | bcf9d33c6d1308c1d19ebd9699d135b47d4b1d537d6632f0b890087a10950f47 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/13d05dfa-7a3e-5ac5-a544-1fd5420dad90.json | https://web.archive.org/web/20260910183708/https://www.aboutamazon.com/news/company-news/amazon-data-center-louisiana-new-jobs
13dc86ac-4e90-5c6e-8540-de0c7893690f | ["geometry"] | ["257f3255-46fe-585e-bdf5-9689b34edbdc"] | open_map_geometry | OpenStreetMap way 554352050 — Ex Postal Market | https://api.openstreetmap.org/api/0.6/way/554352050/full.json | OpenStreetMap contributors | openstreetmap_api | ODbL-1.0 | © OpenStreetMap contributors | 2022-07-19T17:15:33Z | 2026-08-20T21:06:03Z | 56e6716b49448de12f7737546875328459688b563c3f0d98e3b4e9212e05552f | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/13dc86ac-4e90-5c6e-8540-de0c7893690f.json | https://web.archive.org/web/20260820210603/https://api.openstreetmap.org/api/0.6/way/554352050/full.json
13fd9433-c937-5d15-83df-0615d0f5d23e | ["imported:record","metric:power_capacity"] | ["d31725a8-2753-5d70-963d-320d4f6fbb61"] | company_disclosure | Data centre | https://www.sifytechnologies.com/europe/data-centre/ | Sify Technologies | www.sifytechnologies.com | source-terms-not-recorded | Sify Technologies |  | 2026-10-09 | 103b2115aa1cd32b753732773272587a67803943e68d102b39a7117617a52565 | unknown | source_record_projection | sify-noida-02 | s2 | de2cd649d7b533c3c76ce23f61f0aafb9a8f5ea874df5d8d2c5d72dce0096611 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/13fd9433-c937-5d15-83df-0615d0f5d23e.json | https://web.archive.org/web/20261009/https://www.sifytechnologies.com/europe/data-centre/
14226399-1fd3-570b-a457-48adc247ccf4 | ["context:site_distinctness","geometry"] | ["898b0895-99d6-545b-8053-79813ae63ffa"] | openstreetmap | Nominatim response documentation: object centroid fields | https://nominatim.org/release-docs/latest/api/Output/ | Nominatim documentation | europe_round28_envia_leipzig | no-open-license-asserted | Nominatim documentation |  | 2026-09-09T10:46:21.013Z | 2b22abff55df61794873a6648149a09a46262c4f409578cb8d6823de3d6b5f7e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/14226399-1fd3-570b-a457-48adc247ccf4.json | https://web.archive.org/web/20260909104621/https://nominatim.org/release-docs/latest/api/Output/
14234414-a555-5760-9bf2-fb50561e5fc2 | ["imported:geometry","imported:record","role:government"] | ["337ace90-652d-52fe-a856-fe9b04b5966f"] | news | El Paso leaders get update on Meta data center project, city cites enforceable agreements | https://kfoxtv.com/news/local/el-paso-leaders-get-update-on-meta-data-center-project-city-cites-enforceable-agreements | KFOX14 | kfoxtv.com | source-terms-not-recorded | KFOX14 | 2026-04-13 | 2026-10-09 | 22762adf8c89e4471439705f414bae037cf7063c160abe9402240a202e705619 | day | source_record_projection | meta-el-paso | s4 | be1879b543b0ada955c7ab4a7ecebeb6d0d63a8bc5b4b2467644b09395dfd1dc | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/14234414-a555-5760-9bf2-fb50561e5fc2.json | https://web.archive.org/web/20261009/https://kfoxtv.com/news/local/el-paso-leaders-get-update-on-meta-data-center-project-city-cites-enforceable-agreements
142ec0fd-0dbf-5254-a749-9111129a6f73 | ["imported:geometry","imported:record"] | ["c01f2073-5c23-511c-9d85-80ad9345987a"] | other | Birmingham, Alabama | https://en.wikipedia.org/wiki/Birmingham,_Alabama | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 2091c053841e08539b59ea376ecfbf0058b2bf6e94d3019a71dcd81ab4a2b21a | unknown | source_record_projection | nebius-birmingham-alabama | s3 | 0aab4bda32e1c1b74b9110271f1466bebe21f707042341167cb2d486459c1505 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/142ec0fd-0dbf-5254-a749-9111129a6f73.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Birmingham,_Alabama
1434c1dc-df1e-5f02-a1b2-371520fc95c5 | ["context:geometry_identity","context:site_distinctness","geometry"] | ["cbe9c330-13a3-5d1f-a9ba-c981c31585a7"] | company_disclosure | Cloud4Y public frontend: data-center card to map marker binding | https://www.cloud4y.ru/bitrix/cache/js/s1/2019/template_5c75325715617cdba326d6a89c8251cf/template_5c75325715617cdba326d6a89c8251cf_v1.js?1787322416381485 | Cloud4Y | europe_round26_cloud4y_marfino | no-open-license-asserted | Cloud4Y |  | 2026-09-09T09:41:20Z | 72068c1a91c292da5d2406f45e334c16ce01b277d0a0bbd66575fc2dffae7099 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1434c1dc-df1e-5f02-a1b2-371520fc95c5.json | https://web.archive.org/web/20260909094120/https://www.cloud4y.ru/bitrix/cache/js/s1/2019/template_5c75325715617cdba326d6a89c8251cf/template_5c75325715617cdba326d6a89c8251cf_v1.js?1787322416381485
14729585-bde5-5c16-96e9-f008242638d7 | ["imported:geometry","imported:record","metric:power_capacity","milestone:permit_approved","power_source:battery_storage","power_source:natural_gas_onsite"] | ["d2db6863-886a-5c16-b819-7f2cd95cd87e"] | analyst_report | Colossus 1 & 2 ¦ Behind-the-Meter Data Centers | https://cleanview.co/reports/behind-the-meter-data-centers/full-report/colossus | Cleanview | cleanview.co | source-terms-not-recorded | Cleanview |  | 2026-10-09 | fff5195966282311725631fc6ef5fe462ea7a0fcf4022d06606d7feedd887811 | unknown | source_record_projection | xai-colossus-memphis | s7 | dfb2757770260ccf50149a6e04c556018f960324cd194a80d5c5cf347be8f974 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/14729585-bde5-5c16-96e9-f008242638d7.json | https://web.archive.org/web/20261009/https://cleanview.co/reports/behind-the-meter-data-centers/full-report/colossus
14a5995c-d88f-58cc-90f1-32f1639dd609 | ["physical_status"] | ["6f0acd88-cd04-5f3f-915c-48a71fd51f39"] | company_disclosure | Project Jupiter statement on construction permitting | https://www.oracle.com/news/announcement/project-jupiter-statement-on-construction-permitting-2026-09-14/ | Oracle | oracle_news | all-rights-reserved | Oracle | 2026-09-14 | 2026-10-13T09:54:20.636452+00:00 | d0df3007f3e0c14d128c5d296e7bb47df62e00f9d0411683f77a40b3d7d4642d | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/14a5995c-d88f-58cc-90f1-32f1639dd609.json | https://web.archive.org/web/20261013095420/https://www.oracle.com/news/announcement/project-jupiter-statement-on-construction-permitting-2026-09-14/
14da81a2-b755-5b3f-b124-3de0daf223f4 | ["context:geometry_identity","context:site_distinctness"] | ["f0e92e2e-e082-5b7f-9486-fd744b5b68e6"] | company_disclosure | Vantage Zurich I campus exact address | https://vantage-dc.com/data-center-locations/emea/zurich-i-switzerland/ | Vantage Data Centers | europe_mena_round9_expansion_asia | no-open-license-asserted | Vantage Data Centers |  | 2026-09-08T23:11:32.902Z | 083800b6a92a163df0b24b3271d16bc1cf44460b2a0e627e56d711f947dc09e9 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/14da81a2-b755-5b3f-b124-3de0daf223f4.json | https://web.archive.org/web/20260908231132/https://vantage-dc.com/data-center-locations/emea/zurich-i-switzerland/
14e5b2e8-3772-50b5-844e-c84bbe7c2bdc | ["imported:record","metric:power_capacity","milestone:other","role:power_supplier"] | ["fbbfee97-55a0-5a4e-b000-282ff02a8a39"] | government_record | Beacon AI Centers Indus Project (reference 90121) | https://iaac-aeic.gc.ca/050/evaluations/proj/90121 | Impact Assessment Agency of Canada | iaac-aeic.gc.ca | source-terms-not-recorded | Impact Assessment Agency of Canada |  | 2026-10-09 | a8164606a6195bd3696459ba84574e5b3a50bdbe6971f11dc6f891ad8eee027f | unknown | source_record_projection | beacon-ai-centers-indus | s2 | 31c79930812626de82d850ddcfbca7999819a420e79842f3f49e0e8817661aa2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/14e5b2e8-3772-50b5-844e-c84bbe7c2bdc.json | https://web.archive.org/web/20261009/https://iaac-aeic.gc.ca/050/evaluations/proj/90121
14f6f900-635e-5e74-9e8d-d179f4ad51ac | ["imported:geometry","imported:record","metric:investment","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:government"] | ["ec8c635b-93db-5c3c-904e-820b7c4f1233"] | news | Microsoft avanza con su red de centros de datos en Zaragoza, donde proyecta una de sus mayores regiones en Europa | https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html | elDiario.es | www.eldiario.es | source-terms-not-recorded | elDiario.es | 2025-11-14 | 2026-10-09 | 56457d526fcfc7a719fa128725dbe7a57b8399f404281d3914ddc70f685dc990 | day | source_record_projection | microsoft-aragon-villamayor-de-gallego | s3 | d2af0f994a460d635bbec1a07ec9c75d3ea424551a637463b05ddc35b2a2a30b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/14f6f900-635e-5e74-9e8d-d179f4ad51ac.json | https://web.archive.org/web/20261009/https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html
1503cf45-fa45-5d59-a7fc-7ce360a11a88 | ["imported:geometry","imported:record","metric:investment","metric:land_area","milestone:announced","milestone:other","role:government","role:investor"] | ["46434a5c-4980-5f79-ac83-000783b60566"] | trade_press | Blackstone invertirá hasta 7.500 millones en un data center en Aragón | https://brainsre.news/blackstone-7500-millones-data-center-aragon/ | Brainsre.news | brainsre.news | source-terms-not-recorded | Brainsre.news | 2024-10-14 | 2026-10-09 | 512ccaab5844e5f631756c99eee4584b808c9293061728b19c3b49f117ead5a5 | day | source_record_projection | blackstone-calatorao | s1 | 6afcb1fbc59cf3659ffc3e2d0aa618b2fd646f74ecfb8cd734af34d6d752dadf | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1503cf45-fa45-5d59-a7fc-7ce360a11a88.json | https://web.archive.org/web/20261009/https://brainsre.news/blackstone-7500-millones-data-center-aragon/
15245591-7c39-5b0f-ba74-f5156f3bf425 | ["imported:geometry","imported:record","metric:land_area","metric:power_capacity","milestone:other"] | ["297b1705-767f-5434-af46-c08932afceb9"] | news | atNorth data center to supply district heating | https://www.atnorth.com/in-the-news/atnorths-data-center-to-supply-district-heating/ | JydskeVestkysten (republished by atNorth) | www.atnorth.com | source-terms-not-recorded | JydskeVestkysten (republished by atNorth) | 2025-11-13 | 2026-10-09 | e33d482d1ad00abab43603bfa36b7665f2023809fbfeaeab4df71f44ee5468aa | day | source_record_projection | atnorth-varde-den02 | s2 | 2e602936e413676100564b4bf9d804be7256f23bd1dc65bd77af500406096f07 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/15245591-7c39-5b0f-ba74-f5156f3bf425.json | https://web.archive.org/web/20261009/https://www.atnorth.com/in-the-news/atnorths-data-center-to-supply-district-heating/
15a46a40-3971-5abd-8e45-f6ccadbb5c48 | ["context:site_distinctness","geometry"] | ["e1aeeee2-575c-5873-a96a-528a6c08b387"] | government_record | Official address point - 34 rue Louis Armand, Villeneuve-Saint-Georges | https://data.geopf.fr/geocodage/search?q=34%20Rue%20Louis%20Armand%2094190%20Villeneuve-Saint-Georges&index=address&limit=5 | IGN Geoplateforme / Base Adresse Nationale | france_ign_ban_address_geocoding | no-open-redistribution-license-asserted | IGN Geoplateforme / Base Adresse Nationale |  | 2026-09-08T19:27:02Z | 24a1fba2a5f5adf64cc85e9af539726a8a7b98833cb0645484a16c37543b7068 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/15a46a40-3971-5abd-8e45-f6ccadbb5c48.json | https://web.archive.org/web/20260908192702/https://data.geopf.fr/geocodage/search?q=34%20Rue%20Louis%20Armand%2094190%20Villeneuve-Saint-Georges&index=address&limit=5
15bf3257-b23b-5081-8705-5882f10baedb | ["imported:record","role:developer"] | ["d2db6863-886a-5c16-b819-7f2cd95cd87e"] | news | xAI raises billions of dollars for expansion amid rapid growth in Memphis metro | https://www.actionnews5.com/2026/01/07/xai-raises-billions-dollars-expansion-amid-rapid-growth-memphis-metro | WMC Action News 5 | www.actionnews5.com | source-terms-not-recorded | WMC Action News 5 | 2026-01-07 | 2026-10-09 | c330ce2a7b47a4c7d30a2a2c94e9c7ae588715edb1b11d49adb0f30a5947f8d2 | day | source_record_projection | xai-colossus-memphis | s4 | dfb2757770260ccf50149a6e04c556018f960324cd194a80d5c5cf347be8f974 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/15bf3257-b23b-5081-8705-5882f10baedb.json | https://web.archive.org/web/20261009/https://www.actionnews5.com/2026/01/07/xai-raises-billions-dollars-expansion-amid-rapid-growth-memphis-metro
15c1ff4e-32e7-53f5-a6bf-9ec0b270f046 | ["imported:record","milestone:announced","role:developer"] | ["93e5705d-3c86-524c-8089-0868d13bbd0d"] | company_disclosure | Google's investments run deep in the heart of Texas | https://blog.google/inside-google/company-announcements/google-american-innovation-texas/ | Google | blog.google | source-terms-not-recorded | Google | 2025-11-14 | 2026-10-09 | 6b3d111e190b944038d22508e5f5271f3f66f6aff6ed8774889784aeb50cc85c | day | source_record_projection | google-journey-haskell-county-texas | s1 | 72e5be79448d9c10c235e6e58f736780f1941773120215f3afa2cd445bf665d7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/15c1ff4e-32e7-53f5-a6bf-9ec0b270f046.json | https://web.archive.org/web/20261009/https://blog.google/inside-google/company-announcements/google-american-innovation-texas/
15cc2b08-69b2-5325-9550-89f870c78575 | ["imported:record","milestone:other","role:tenant"] | ["126f2c37-cadc-5f20-9e3c-e544d70b5c37"] | company_disclosure | OpenAI, Oracle, and SoftBank expand Stargate with five new AI data center sites | https://group.softbank/en/news/press/20250924 | SoftBank Group Corp. | group.softbank | source-terms-not-recorded | SoftBank Group Corp. | 2025-09-24 | 2026-10-09 | 77e86241ed68d61e9e04fd3f44ba4e1cd85eeab82a5118fb40fc21d1b34b07be | day | source_record_projection | openai-stargate-shackelford-county | s2 | d7f00a3af4692eb8b87a8fe8ff934e44ef3d783701c67872ad62cb1f21703743 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/15cc2b08-69b2-5325-9550-89f870c78575.json | https://web.archive.org/web/20261009/https://group.softbank/en/news/press/20250924
15e1fc03-9d97-5c6a-8ea4-ac692cba90af | ["imported:geometry","imported:record","imported:status","metric:investment","metric:jobs_permanent","metric:land_area","milestone:construction_started","milestone:other","power_source:grid","role:developer","role:operator","role:utility"] | ["0a4a2c40-bdf2-5f56-aa09-ecfa54431d3c"] | trade_press | Google ID'd as Operator of Tulsa Area Data Center | https://news.constructconnect.com/google-idd-as-operator-of-tulsa-area-data-center | ConstructConnect | news.constructconnect.com | source-terms-not-recorded | ConstructConnect | 2026-08-21 | 2026-10-09 | c986d4c7c0d1fc7840f5a069113939a3e58348637087f0d90dddeb8419694db2 | day | source_record_projection | google-owasso-project-clydesdale | s4 | a97c56693be5922a0e0efe7d6461c0d87a07a5d861231215bf2d8e48f2ff4ef6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/15e1fc03-9d97-5c6a-8ea4-ac692cba90af.json | https://web.archive.org/web/20261009/https://news.constructconnect.com/google-idd-as-operator-of-tulsa-area-data-center
165fbb6a-eef4-52fe-a01f-1ea31fee2c23 | ["context:geometry_identity","context:site_distinctness"] | ["e542ef62-912c-5edb-982a-8e463179484b"] | company_disclosure | Mega Or FY2025 annual report: plot 200A (block 2604 parcel 12) data-centre building under construction | https://megaor.co.il/wp-content/uploads/2026/05/%D7%93%D7%95%D7%97-%D7%AA%D7%A7%D7%95%D7%A4%D7%AA%D7%97-%D7%95%D7%A9%D7%A0%D7%AA%D7%99-%D7%9C%D7%A9%D7%A0%D7%AA-2025.pdf | Mega Or Holdings Ltd | mega_or_holdings_periodic_reports | all-rights-reserved | Mega Or Holdings Ltd |  | 2026-09-25T22:16:14.705Z | 32da29360469f3ca2d13c5679fbff9bdbb2d5c2b423997c2f65a0522ecd4b5e2 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/165fbb6a-eef4-52fe-a01f-1ea31fee2c23.json | https://web.archive.org/web/20260925221614/https://megaor.co.il/wp-content/uploads/2026/05/%D7%93%D7%95%D7%97-%D7%AA%D7%A7%D7%95%D7%A4%D7%AA%D7%97-%D7%95%D7%A9%D7%A0%D7%AA%D7%99-%D7%9C%D7%A9%D7%A0%D7%AA-2025.pdf
166840f7-6620-5ddb-ae24-c2b8a1f011de | ["imported:geometry","imported:record"] | ["c7671f1b-16fb-5d22-b002-93f28cea5585"] | company_disclosure | PDG Acquires 240 MW of Powered Land in Jakarta, Advancing Its Rapid Expansion Across Asia | https://princetondg.com/press-releases/pdg-acquires-240-mw-of-powered-land-in-jakarta-advancing-its-rapid-expansion-across-asia/ | Princeton Digital Group | princetondg.com | source-terms-not-recorded | Princeton Digital Group | 2026-04-30 | 2026-10-09 | 2df14d3f3abf87f00673c8f40fb6a4e8346e7e514bb67269fd8a1a1ea451871b | day | source_record_projection | pdg-jc3-bekasi | s3 | fb1513fb62dcd655204b9379590ede9da417a35626575c38b1e116e557e866f4 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/166840f7-6620-5ddb-ae24-c2b8a1f011de.json | https://web.archive.org/web/20261009/https://princetondg.com/press-releases/pdg-acquires-240-mw-of-powered-land-in-jakarta-advancing-its-rapid-expansion-across-asia/
166e9d97-3a08-5dd1-8de8-57935faa410f | ["context:geometry_identity","context:site_distinctness"] | ["726d6e35-8381-58ae-8dcd-eeb9ae23583a"] | government_record | 31st Considerate Contractors Site Award Scheme, Non-Public RMAA Works winners: Project Galaxy at Goodman Texaco Centre, Section A of Lot No. 472 in D.D. 443 | https://www.safetyweek.hk/web/files.php?id=7670&scode=3c5d51c4aebb67a615e742d56d29e47d | Development Bureau and Construction Industry Council, Hong Kong (Construction Safety Week) | hk_devb_cic_considerate_contractors_awards | no-open-license-asserted | Development Bureau and Construction Industry Council, Hong Kong |  | 2026-10-09T11:13:20.481Z | e5aa01249d848fa43d84153302d05ad8f3fdf9f1c95e52a90adb744dadd1914e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/166e9d97-3a08-5dd1-8de8-57935faa410f.json | https://web.archive.org/web/20261009111320/https://www.safetyweek.hk/web/files.php?id=7670&scode=3c5d51c4aebb67a615e742d56d29e47d
167e54b8-a831-5dd8-8bb7-c78931101544 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["20a32e9d-3c57-520d-aeb8-ad999d43fee3"] | company_disclosure | HIVE Form10-Q: ongoing Yguazú substation expansion | https://www.hivedigitaltechnologies.com/static/hivesite/filings/000106299326004434/form10q.htm | HIVE Digital Technologies Ltd. | hive_issuer_disclosures | no-open-license-asserted | HIVE Digital Technologies Ltd. | 2026-08-14 | 2026-09-10T01:31:35.129Z | 2c1fda383f064fdfaca0784188b009bfec7854ed5700b657a8c58338b44f50a0 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/167e54b8-a831-5dd8-8bb7-c78931101544.json | https://web.archive.org/web/20260910013135/https://www.hivedigitaltechnologies.com/static/hivesite/filings/000106299326004434/form10q.htm
16bd796f-400b-51f9-be5b-59149c0107cc | ["imported:record","metric:power_capacity","milestone:first_operational","milestone:other","role:developer","role:government"] | ["a9ca22ae-d872-5122-a052-e5c9ec410abd"] | news | Microsoft obtiene luz verde para su ambicioso proyecto de centros de datos en Aragón | https://forbes.es/empresas/828243/microsoft-obtiene-luz-verde-para-su-ambicioso-proyecto-de-centros-de-datos-en-aragon/ | Forbes España | forbes.es | source-terms-not-recorded | Forbes España | 2025-11-14 | 2026-10-09 | 0c2b25a0eff692b960c8edef2b22f3b0ed17fc7c1dfa7f3667c491ec379861ce | day | source_record_projection | microsoft-aragon-la-muela | s3 | 6b52e7ee1fc0d0bf161b9378e47ebccbfedbc6afc0fbcb18c225c7fcc32a53b3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/16bd796f-400b-51f9-be5b-59149c0107cc.json | https://web.archive.org/web/20261009/https://forbes.es/empresas/828243/microsoft-obtiene-luz-verde-para-su-ambicioso-proyecto-de-centros-de-datos-en-aragon/
16c9db8a-3405-5535-8a99-032f92fc323e | ["imported:record","metric:investment","milestone:other","role:investor"] | ["2bd78b04-9314-5aa8-ac32-ef30e111bc2e"] | government_record | US-UK pact will boost advances in drug discovery, create tens of thousands of jobs and transform lives | https://www.gov.uk/government/news/us-uk-pact-will-boost-advances-in-drug-discovery-create-tens-of-thousands-of-jobs-and-transform-lives | UK Government | www.gov.uk | source-terms-not-recorded | UK Government | 2025-09-16 | 2026-10-09 | e9d37d5b18d2b40cfd7e6766493d0002169e44a01fd75f24f01489f345764d9c | day | source_record_projection | qts-cambois-blyth | s3 | 0b723f64ffa9d6efd917b3e9c656e1369d367d1a946f7568d998ed9ce8cd7927 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/16c9db8a-3405-5535-8a99-032f92fc323e.json | https://web.archive.org/web/20261009/https://www.gov.uk/government/news/us-uk-pact-will-boost-advances-in-drug-discovery-create-tens-of-thousands-of-jobs-and-transform-lives
16df3c45-da29-54dc-8ddd-5db6caea30ac | ["context:site_distinctness","geometry"] | ["8c926b8f-0190-533b-aa7e-3223971b9e23","ad57807a-f6b6-55f9-b26f-acd194e12880"] | openstreetmap | OSM copyright page binds open-data licence and attribution | https://www.openstreetmap.org/copyright | OpenStreetMap Foundation / OpenStreetMap contributors | americas_round11_flexential_hillsboro5 | ODbL-1.0 | OpenStreetMap Foundation / OpenStreetMap contributors |  | 2026-09-09T00:40:45.230Z | 7571bb36f52530c83bd30428463dd04d549831479240579a303d73f10abe6c39 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/16df3c45-da29-54dc-8ddd-5db6caea30ac.json | https://web.archive.org/web/20260909004045/https://www.openstreetmap.org/copyright
16e36e46-4aa0-575e-b78d-bf6521024466 | ["imported:record","metric:buildings","metric:floor_area","metric:investment","milestone:fully_operational","role:builder"] | ["8d3985c2-7777-5c6b-9a7f-fcab6c9b6a4f"] | trade_press | Meta selects DPR for $1B Arizona data center | https://www.constructiondive.com/news/meta-dpr-arizona-data-center-mesa-phoenix/701776/ | Construction Dive | www.constructiondive.com | source-terms-not-recorded | Construction Dive | 2023-12-06 | 2026-10-09 | a49828a572bb2edaab83b39dc6efbe49eb130fb89e45ce92d9186461099a3e0e | day | source_record_projection | meta-mesa-arizona | s3 | 690a5d65866311037933f9ddd4b78f9f474ed7fab8310573de902132c5585030 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/16e36e46-4aa0-575e-b78d-bf6521024466.json | https://web.archive.org/web/20261009/https://www.constructiondive.com/news/meta-dpr-arizona-data-center-mesa-phoenix/701776/
17414c26-e568-5e54-ae88-13ac8e17f591 | ["imported:record","imported:status","metric:buildings","milestone:zoning_approved","role:government"] | ["96848e3f-da64-53c8-be33-bf5c9cd2109a"] | news | Mount Pleasant village board approves Microsoft data center expansion | https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval | Spectrum News 1 | spectrumnews1.com | source-terms-not-recorded | Spectrum News 1 | 2026-01-27 | 2026-10-09 | c9e5ab699903ee4f4c258c03a79ae4359110c1ceab118e746fe2682a669f7845 | day | source_record_projection | microsoft-mount-pleasant-international-drive | s4 | 2fc9140e0cc603e7e8d9d9b804a94e384834e7381c41e9a315d5d9adc4fd1354 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/17414c26-e568-5e54-ae88-13ac8e17f591.json | https://web.archive.org/web/20261009/https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval
177d1598-ed7b-59f6-bc0f-941cf1a828b0 | ["imported:geometry","imported:record"] | ["715ba9aa-f36a-5afb-b266-caeb7681b54e"] | other | Childress, Texas | https://en.wikipedia.org/wiki/Childress,_Texas | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | df9fd2e0a6114639f7f056b13aa084d8b47144f910e562d2a8eac83ee1774524 | unknown | source_record_projection | crusoe-lancium-childress-texas | s3 | a80783e043af94acc3d310b6b23c3ec5da45db230e987b2ba158e15964808b6a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/177d1598-ed7b-59f6-bc0f-941cf1a828b0.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Childress,_Texas
178c95ea-e137-5242-ab75-419f303aa009 | ["imported:record","milestone:expansion_announced","role:tenant"] | ["e389cd04-b538-5729-85a5-8e0b18e78002"] | company_disclosure | TeraWulf Announces Fluidstack Expansion with 160 MW CB-5 Lease at Lake Mariner | https://investors.terawulf.com/news-events/press-releases/detail/114/terawulf-announces-fluidstack-expansion-with-160-mw-cb-5-lease-at-lake-mariner | TeraWulf | investors.terawulf.com | source-terms-not-recorded | TeraWulf | 2025-08-18 | 2026-10-09 | 8b49ecbfc17a39b9eba4d7c41f77783dc32787105df0d495155227770c13af52 | day | source_record_projection | terawulf-lake-mariner | s3 | 081cc26c2e57d03704aae2b9dbe919a2c59626dbb9bf84295aa36cf2d26e6106 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/178c95ea-e137-5242-ab75-419f303aa009.json | https://web.archive.org/web/20261009/https://investors.terawulf.com/news-events/press-releases/detail/114/terawulf-announces-fluidstack-expansion-with-160-mw-cb-5-lease-at-lake-mariner
17a1d516-33f6-5108-9c04-806f94890963 | ["context:site_distinctness","geometry"] | ["be6d721d-f632-5c86-a057-78774604bc6c"] | government_record | Official address point - 13 rue Charles Cros, Tremblay-en-France | https://data.geopf.fr/geocodage/search?q=13%20Rue%20Charles%20Cros%2093290%20Tremblay-en-France&index=address&limit=5 | IGN Geoplateforme / Base Adresse Nationale | france_ign_ban_address_geocoding | no-open-redistribution-license-asserted | IGN Geoplateforme / Base Adresse Nationale |  | 2026-09-08T19:27:02Z | 5376cb7cc9bd84e13a67d92e8c2c604699ea5be093b4c5180de900059584ca51 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/17a1d516-33f6-5108-9c04-806f94890963.json | https://web.archive.org/web/20260908192702/https://data.geopf.fr/geocodage/search?q=13%20Rue%20Charles%20Cros%2093290%20Tremblay-en-France&index=address&limit=5
17a317b4-d4a3-5fc0-b852-09cdfaf3de99 | ["context:site_distinctness","geometry"] | ["100cf064-1cae-5dba-a4d9-6c4ae35152ec"] | third_party_dataset | AIGID MOJ-derived Tomakomai 2026 cadastral polygon: Kashiwabara 32-17 | https://gsic-opendata.s3.ap-northeast-1.amazonaws.com/aigid/aigid-moj/2026/01/aigid-moj-01213/01213_%E8%8B%AB%E5%B0%8F%E7%89%A7%E5%B8%82_%E5%85%AC%E5%85%B1%E5%BA%A7%E6%A8%9912%E7%B3%BB_%E7%AD%86R_2026.geojson | Association for Promotion of Infrastructure Geospatial Information Distribution (AIGID) | aigid_moj_cadastral_reference | CC-BY-version-unspecified; underlying MOJ-map-data-custom-terms-2023-01-23 | Ministry of Justice, Japan; AIGID conversion; Data Center Atlas selection and display-anchor derivation |  | 2026-09-08T21:42:59.229Z | 0b62da38a45a5da642d35338c3a43ca765ad46875dae2e97f7bfed6ad56223c7 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/17a317b4-d4a3-5fc0-b852-09cdfaf3de99.json | https://web.archive.org/web/20260908214259/https://gsic-opendata.s3.ap-northeast-1.amazonaws.com/aigid/aigid-moj/2026/01/aigid-moj-01213/01213_%E8%8B%AB%E5%B0%8F%E7%89%A7%E5%B8%82_%E5%85%AC%E5%85%B1%E5%BA%A7%E6%A8%9912%E7%B3%BB_%E7%AD%86R_2026.geojson
17da0c46-2546-5d53-b910-108e95100470 | ["imported:geometry","imported:record","metric:land_area","metric:power_capacity","milestone:announced","power_source:battery_storage","power_source:solar","role:developer","role:owner"] | ["2e14f098-9798-567b-ae40-a7d552f9be18"] | company_disclosure | TeraWulf secures long-term ground lease at Cayuga site to expand high-performance computing infrastructure | https://investors.terawulf.com/news-events/press-releases/detail/113 | TeraWulf | investors.terawulf.com | source-terms-not-recorded | TeraWulf | 2025-08-14 | 2026-10-09 | 2ce15f6d78da5339c09aa98fca59df3c59c5b8a5198bed3be5bfd4679760ec1f | day | source_record_projection | terawulf-lake-hawkeye | s1 | d8d535edbd465f66e5e0963a5691de97b492f14002691ea654db6ada9c90efd8 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/17da0c46-2546-5d53-b910-108e95100470.json | https://web.archive.org/web/20261009/https://investors.terawulf.com/news-events/press-releases/detail/113
17ee56c4-bb04-50b4-a94b-d1550ac3f2a5 | ["context:site_distinctness","geometry"] | ["96d7988b-a1e7-517c-9218-462524058a80"] | government_record | Israel Planning Administration Xplan plan record 625-0866855 | https://ags.iplan.gov.il/arcgisiplan/rest/services/PlanningPublic/Xplan/MapServer/1/query?where=pl_number%3D%27625-0866855%27&outFields=pl_number,pl_name,jurstiction_area_name,ja_concat,district_name,station_desc,pl_objectives,pl_url,pl_area_dunam,pl_date_8&returnGeometry=false&f=json | Israel Planning Administration | israel_planning_administration_xplan | no-open-license-asserted | Israel Planning Administration (iplan.gov.il) |  | 2026-09-25T22:29:43.844Z | d9401655e139b7abe0011de21b46351457c2ab25c84e93254d3f4f2caaf6e4c7 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/17ee56c4-bb04-50b4-a94b-d1550ac3f2a5.json | https://web.archive.org/web/20260925222943/https://ags.iplan.gov.il/arcgisiplan/rest/services/PlanningPublic/Xplan/MapServer/1/query?where=pl_number%3D%27625-0866855%27&outFields=pl_number,pl_name,jurstiction_area_name,ja_concat,district_name,station_desc,pl_objectives,pl_url,pl_area_dunam,pl_date_8&returnGeometry=false&f=json
1803578b-9a35-5a2f-a022-63de34cf79d9 | ["imported:geometry","imported:record"] | ["8ce04eb2-b1ed-5375-a685-122f79fc2ee6"] | other | Pecos, Texas | https://en.wikipedia.org/wiki/Pecos,_Texas | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 3621c50a6d85ed4ef02bf5c8834c82081e0653a135363b8d398eb6fea70f09c7 | unknown | source_record_projection | core-scientific-pecos | s7 | ab37ccfdcc0bc48d95f588d7a62361846b812822a0cd61b3d36fc6ae2dea2784 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1803578b-9a35-5a2f-a022-63de34cf79d9.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Pecos,_Texas
1839db3d-9273-53fc-8afb-de73b478e26d | ["context:site_distinctness","geometry"] | ["cbe074bd-68d8-59cb-aaf7-e21fa82b193f"] | other | Adobe PDF 1.7 ExtensionLevel 3: GEO registration, underlying geographic CRS and WKT semantics | https://web.archive.org/web/20200621050243/https://www.adobe.com/content/dam/acom/en/devnet/acrobat/pdfs/adobe_supplement_iso32000.pdf | Adobe Systems Incorporated; historical original document preserved by Internet Archive | adobe_pdf_1_7_extensionlevel_3_specification | all-rights-reserved | Adobe Systems Incorporated, Adobe Supplement to ISO 32000, BaseVersion 1.7, ExtensionLevel 3, June 2008 |  | 2026-09-10T18:54:54.923Z | 638f531b57ceb50b4f0b86a6740a57438ccecb0e434e32f0209d9c8200ecc44b | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1839db3d-9273-53fc-8afb-de73b478e26d.json | https://web.archive.org/web/20260910185454/https://web.archive.org/web/20200621050243/https://www.adobe.com/content/dam/acom/en/devnet/acrobat/pdfs/adobe_supplement_iso32000.pdf
183ba80f-eeac-5e5f-a13d-f1640eb9e217 | ["imported:record","metric:investment","milestone:other","role:developer"] | ["b9f9191a-1f90-551d-a8b9-44e6f8833e96"] | company_disclosure | QScale Accelerates Its Expansion and Growth | https://www.qscale.com/news/qscale-accelerates-its-expansion-and-growth | QScale | www.qscale.com | source-terms-not-recorded | QScale | 2022-09-21 | 2026-10-09 | c8bffa01762068af6a8ceebb09b101b41bd5f1298373b43e6af1814e8a66afe9 | day | source_record_projection | qscale-q01-levis | s2 | 88ec25d50c62b593691517ad815b73e1bc3d81f12e4e437b5e05f6b866166882 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/183ba80f-eeac-5e5f-a13d-f1640eb9e217.json | https://web.archive.org/web/20261009/https://www.qscale.com/news/qscale-accelerates-its-expansion-and-growth
183ff3fc-f33e-5695-a1cd-dd7f80c0d4e3 | ["imported:geometry","imported:record","metric:buildings","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:government"] | ["f07274ee-deff-5651-b606-da909d7328af"] | government_record | Plan de Interés General de Aragón: Instalación de un centro de datos en el término municipal de La Puebla de Alfindén | https://www.aragon.es/-/piga-acs-dc-la-puebla | Gobierno de Aragón | www.aragon.es | source-terms-not-recorded | Gobierno de Aragón | 2026-07-06 | 2026-10-09 | 1ca2288d3e357208b7f88fd345bef4139005fe43886f929689c5ff607e0ed31e | day | source_record_projection | acs-la-puebla-de-alfinden | s1 | 4d67e1c342e70c1aab029abca8abac09d6bcba48ba47c042a557ab594cad4c6b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/183ff3fc-f33e-5695-a1cd-dd7f80c0d4e3.json | https://web.archive.org/web/20261009/https://www.aragon.es/-/piga-acs-dc-la-puebla
185d2429-b370-5243-a85b-26e02465e160 | ["context:geometry_identity","context:site_distinctness"] | ["e39b5191-4a78-5781-8944-24efaf944aa9"] | company_disclosure | Kapitol GE1 project: matching NEXTDC Corio identity | https://www.kapitol.com/our-projects/industrial/nextdc-ge1-geelong | Kapitol | expansion_round5_primary_sources | all-rights-reserved | Kapitol |  | 2026-09-08T21:34:12Z | 477c4dca8f974b868c34092504e5c156589ead84bcf51a620820855abced91f1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/185d2429-b370-5243-a85b-26e02465e160.json | https://web.archive.org/web/20260908213412/https://www.kapitol.com/our-projects/industrial/nextdc-ge1-geelong
185ef1c7-2599-5b98-b3cb-e32b54ed5282 | ["imported:geometry","imported:record","imported:status","metric:accelerators","metric:investment","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:hardware_supplier","role:operator","role:tenant","role:utility"] | ["3a54ff50-0fd6-5767-86f2-c6818a515bb2"] | company_disclosure | SINES Data Campus | https://www.startcampus.pt/ | Start Campus | www.startcampus.pt | source-terms-not-recorded | Start Campus |  | 2026-10-09 | a9d1fb41fd712e09ea213786a4577012a898d927360a96f5bec4ca8f16fe0312 | unknown | source_record_projection | start-campus-sines | s1 | e191e9241fa8bdf6141fcf892c29124043391e1435e8be79ed7237aed12f6426 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/185ef1c7-2599-5b98-b3cb-e32b54ed5282.json | https://web.archive.org/web/20261009/https://www.startcampus.pt/
1861a22f-c317-598a-bf68-77573715e3d0 | ["imported:record","imported:status","metric:investment","milestone:other","milestone:zoning_approved","role:government"] | ["1369aebb-7496-56a6-9260-159cd3a37283"] | news | Page anuncia la llegada “definitiva” del centro de datos de Meta a Talavera de la Reina | https://www.eldiario.es/castilla-la-mancha/provincias/toledo/page-anuncia-llegada-definitiva-centro-datos-meta-talavera-reina_1_13416975.amp.html | elDiario.es | www.eldiario.es | source-terms-not-recorded | elDiario.es | 2026-07-30 | 2026-10-09 | 8284a82a5e78773e6cf53e14921734631170bcaffb69ab19f7b5822f537084b1 | day | source_record_projection | meta-talavera-de-la-reina | s2 | d9ae0a11c63a4d533b2e1fb63d37634e7e84f2e088f00911d1e92b36506c02f5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1861a22f-c317-598a-bf68-77573715e3d0.json | https://web.archive.org/web/20261009/https://www.eldiario.es/castilla-la-mancha/provincias/toledo/page-anuncia-llegada-definitiva-centro-datos-meta-talavera-reina_1_13416975.amp.html
18d75187-fb81-5222-af61-f0ad9e97c3fb | ["imported:record","imported:status","metric:buildings","metric:power_capacity","milestone:cancelled","power_source:battery_storage","power_source:grid","power_source:natural_gas_onsite","role:developer","role:government"] | ["18844ee0-7ce9-5a0b-9a50-1d9ed0769266"] | news | Pinal County rejects massive La Osa data center. Residents want more rules for future projects | https://www.kjzz.org/politics/2026-08-26/pinal-county-rejects-massive-la-osa-data-center-residents-want-more-rules-for-future-projects | KJZZ | www.kjzz.org | source-terms-not-recorded | KJZZ | 2026-08-26 | 2026-10-09 | 79202289368a4caeca2fdd1c1e43ea5d649c4052eb0e42f2624b1cd94a159d00 | day | source_record_projection | vermaland-la-osa-pinal-county | s5 | 5fb12121ee713957a5e0413a435f1746010f7893d018b06a01b1c498a8d8f9b6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/18d75187-fb81-5222-af61-f0ad9e97c3fb.json | https://web.archive.org/web/20261009/https://www.kjzz.org/politics/2026-08-26/pinal-county-rejects-massive-la-osa-data-center-residents-want-more-rules-for-future-projects
18e55c05-989b-581b-b412-470a89fff1c3 | ["context:site_distinctness","geometry"] | ["0b67b532-d779-5784-bd6d-d7ee124844aa","f3cc5dc7-9547-517f-94aa-89e0769f2bf8"] | government_record | County catalogue query binds its parcel item to exact current service | https://www.arcgis.com/sharing/rest/search | Chesterfield County GIS | chesterfield_round14 | CC0-1.0 | Data retrieved from Chesterfield County GIS Data Catalog. |  | 2026-09-09T03:07:04Z | 3aaf85ca0486660b98b9b1fce750b0069dffaf16de687cd168775373a6f0ea88 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/18e55c05-989b-581b-b412-470a89fff1c3.json | https://web.archive.org/web/20260909030704/https://www.arcgis.com/sharing/rest/search
18f23330-9877-5e2d-997f-50e05615ad76 | ["context:geometry_identity","context:site_distinctness"] | ["20a32e9d-3c57-520d-aeb8-ad999d43fee3"] | government_record | MADES resolution 3769/2026: Zunz exact parcel and project infrastructure | https://apps.mades.gov.py/siam/portal/dashboard-proyecto/declaracion/83461 | Ministerio del Ambiente y Desarrollo Sostenible, Paraguay | paraguay_mades_siam_public_register | no-open-license-asserted | Ministerio del Ambiente y Desarrollo Sostenible, Paraguay | 2026-07-22 | 2026-09-10T01:28:50.152Z | a14195053c2c631226cff3e5f4b9b215e85f30c55eb6beaf7fa0c494cc90be96 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/18f23330-9877-5e2d-997f-50e05615ad76.json | https://web.archive.org/web/20260910012850/https://apps.mades.gov.py/siam/portal/dashboard-proyecto/declaracion/83461
194a47cc-c9ee-5c10-91ad-b408ea61d7b9 | ["imported:record","imported:status","milestone:cancelled","role:developer"] | ["4ac7a0d0-0faf-50c0-bed8-08d54e0bc62b"] | trade_press | Blackstone's QTS Abandons Digital Gateway Project, Ends Legal Fight | https://www.bisnow.com/news/washington-dc/data-center-development/blackstones-qts-abandons-digital-gateway-project-ends-lawsuit-135295 | Bisnow | www.bisnow.com | source-terms-not-recorded | Bisnow | 2026-07-03 | 2026-10-09 | add175fa426e292c118cffa80a69b4dcced3f5eab1e7f3734fca1b198d91cc50 | day | source_record_projection | pw-digital-gateway | s5 | bc280c373c02f7c258ed949cb09b655406e267bf48cb43edcd6d084ccc9e6fa5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/194a47cc-c9ee-5c10-91ad-b408ea61d7b9.json | https://web.archive.org/web/20261009/https://www.bisnow.com/news/washington-dc/data-center-development/blackstones-qts-abandons-digital-gateway-project-ends-lawsuit-135295
194b0923-7bbf-5769-b6ec-24d034caa47e | ["context:site_distinctness","geometry"] | ["5e0d1954-690d-51cb-816a-88cec595f51a"] | government_record | LGL-BW INSPIRE ThoroughfareName 0831706583002: Einsteinallee | https://owsproxy.lgl-bw.de/owsproxy/wfs/WFS_INSP_BW_Adr_Hauskoord_ALKIS?SERVICE=WFS&VERSION=2.0.0&REQUEST=GetFeature&STOREDQUERY_ID=urn:ogc:def:query:OGC-WFS::GetFeatureById&ID=ThoroughfareName.0831706583002 | Landesamt für Geoinformation und Landentwicklung Baden-Württemberg (LGL-BW) | lgl_bw_inspire_addresses_house_coordinates_alkis | dl-de/by-2-0 | LGL-BW (2026) Datenlizenz Deutschland – Namensnennung – Version 2.0, www.lgl-bw.de |  | 2026-10-09T11:06:07.160Z | 21d9d6a5a746d74e58b9655c3e4bc4fce0a8718010a20a7bb237c67d7c897b7e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/194b0923-7bbf-5769-b6ec-24d034caa47e.json | https://web.archive.org/web/20261009110607/https://owsproxy.lgl-bw.de/owsproxy/wfs/WFS_INSP_BW_Adr_Hauskoord_ALKIS?SERVICE=WFS&VERSION=2.0.0&REQUEST=GetFeature&STOREDQUERY_ID=urn:ogc:def:query:OGC-WFS::GetFeatureById&ID=ThoroughfareName.0831706583002
19577687-e5d9-5814-be67-9003fa0455da | ["context:geometry_identity","context:site_distinctness"] | ["9fe862f6-ace2-5f5d-9c90-486fa4622982"] | company_disclosure | Airtel data-centre portfolio identifies first Nigerian hyperscale site | https://www.airtel.africa/data-centers | Airtel Africa | africa_round7_nxtra | all-rights-reserved | Airtel Africa |  | 2026-09-08T22:27:54.542Z | 35424019e571704b2b6bed73039fa197b5077587dbd53d4d7fae185a5cd20b1f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/19577687-e5d9-5814-be67-9003fa0455da.json | https://web.archive.org/web/20260908222754/https://www.airtel.africa/data-centers
195bbfbf-9214-5087-ad56-e9c5c31c307c | ["imported:geometry","imported:record","metric:buildings","metric:land_area","role:developer","role:owner"] | ["9ed96427-8138-552b-9f88-3b1fbeaa341b"] | news | Shalersville weighs zoning changes to block data center | https://theportager.com/shalersville-holds-off-on-zoning-changes-to-allow-a-data-center | The Portager | theportager.com | source-terms-not-recorded | The Portager | 2026-08-14 | 2026-10-09 | 2cfc54b347553b38748b377197ff8d9e9bf3b4599b80191e0e102d45f0e56560 | day | source_record_projection | bitdeer-shalersville-portage-county | s4 | 3bf4ed692033cd5d7788a796df21f16156be296573a4b008414791a303564b37 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/195bbfbf-9214-5087-ad56-e9c5c31c307c.json | https://web.archive.org/web/20261009/https://theportager.com/shalersville-holds-off-on-zoning-changes-to-allow-a-data-center
196e3b19-08a7-5753-99cc-0b0c3e5d7f0b | ["context:geometry_identity","context:site_distinctness"] | ["7ac977cb-cbe2-5dfd-b058-f26707f86b6c"] | company_disclosure | MERLIN Bilbao-Arasur campus address and published location link | https://www.merlinproperties.com/en/assets/data-center-bilbao-arasur/ | MERLIN Properties | merlin_edged_official_round4 | all-rights-reserved | MERLIN Properties | 2022-06-08T16:23:08Z | 2026-09-08T20:44:08Z | 5d414cbd78b5f7e45b6503e5719a1acd0630af7091c447defcd8286daac3cc38 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/196e3b19-08a7-5753-99cc-0b0c3e5d7f0b.json | https://web.archive.org/web/20260908204408/https://www.merlinproperties.com/en/assets/data-center-bilbao-arasur/
1973e08d-0c30-5b25-a128-58ccfb617a19 | ["context:site_distinctness","geometry"] | ["5ace12f8-658e-5956-9173-d78e625d4df9"] | government_record | Vineland exact parcel with explicitly requested WGS84 transformation | https://gisportal.vinelandcity.org/arcgis/rest/services/Cadastre/Parcel_Public_Viewer/MapServer/0/query?f=pjson&where=BLOCK%3D%277503%27%20AND%20LOT%3D%2735.01%27&outFields=OBJECTID_1,MUN,BLOCK,LOT,UNIQUEID,ParcelAddr,Owner&returnGeometry=true&outSR=4326&datumTransformation=1188 | City of Vineland | vineland_public_gis_round23 | no-open-license-asserted | City of Vineland GIS / Engineering |  | 2026-09-09T07:50:40Z | 0f7ac063ce8ded83310ce701af988f9576190db5fa82be88a8d5efd385501452 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1973e08d-0c30-5b25-a128-58ccfb617a19.json | https://web.archive.org/web/20260909075040/https://gisportal.vinelandcity.org/arcgis/rest/services/Cadastre/Parcel_Public_Viewer/MapServer/0/query?f=pjson&where=BLOCK%3D%277503%27%20AND%20LOT%3D%2735.01%27&outFields=OBJECTID_1,MUN,BLOCK,LOT,UNIQUEID,ParcelAddr,Owner&returnGeometry=true&outSR=4326&datumTransformation=1188
198c88a9-e654-5181-8c63-320728601fe3 | ["geometry"] | ["1cae5b48-c630-5f16-9fe2-5d77571cafe9"] | open_map_record | OpenStreetMap way 1485385261 Telia duomenų centras | https://api.openstreetmap.org/api/0.6/way/1485385261/full.json | OpenStreetMap contributors | openstreetmap_way_full_api | ODbL-1.0 | Contains information from OpenStreetMap, which is made available under the Open Database License (ODbL). | 2026-03-04T14:01:01Z | 2026-08-23 | cd1a7bc1a2c7d9837f81b4c635e70d7e3103630a99d479586e6fee049f605b00 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/198c88a9-e654-5181-8c63-320728601fe3.json | https://web.archive.org/web/20260823/https://api.openstreetmap.org/api/0.6/way/1485385261/full.json
198d5f9c-13f9-5091-b407-6e7b0a5b0ecb | ["context:geometry_identity","context:site_distinctness"] | ["0a4a2c40-bdf2-5f56-aa09-ecfa54431d3c"] | company_disclosure | Beale Tulsa County campus identity and planned completion context | https://bealeinfra.com/location/tulsa-county/ | Beale Infrastructure | root_round33_clydesdale | no-open-license-asserted | Beale Infrastructure |  | 2026-09-10T00:29:10.062Z | c452104a712f53bde8f2630b98965cb6f222e77e2c5645e598ba48e36b767174 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/198d5f9c-13f9-5091-b407-6e7b0a5b0ecb.json | https://web.archive.org/web/20260910002910/https://bealeinfra.com/location/tulsa-county/
19c00ba6-d671-5c9a-811d-d7911af9b674 | ["imported:geometry","imported:record"] | ["a31a1552-7be0-58e9-8097-4083d11175dd"] | other | Cyberjaya | https://en.wikipedia.org/wiki/Cyberjaya | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | de6ff702d4f06ff817cc0c44660dc59445a219c9ee04e5783b7c32ef14e5a4b3 | unknown | source_record_projection | vantage-kul2-cyberjaya | s4 | a5368f23664126d38af865d9bb7fb6cf59a1e4af284c3d0160de0ca0ed90aae8 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/19c00ba6-d671-5c9a-811d-d7911af9b674.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Cyberjaya
1a242c9b-8fb0-5db5-a662-bf137da65f36 | ["imported:geometry","imported:record","metric:investment","role:owner"] | ["126f2c37-cadc-5f20-9e3c-e544d70b5c37"] | regulatory_filing | TABS2026024112: Vantage DC Abilene - TX3 - Project Frontier, building TX310 | https://www.tdlr.texas.gov/TABS/Search/Project/TABS2026024112 | Texas Department of Licensing and Regulation | www.tdlr.texas.gov | source-terms-not-recorded | Texas Department of Licensing and Regulation | 2026-06-30 | 2026-10-09 | c1d2fe390e53caf0fe773c151852a3a5ef29e4fe3a4506fc8a57e9d1819415a4 | day | source_record_projection | openai-stargate-shackelford-county | s5 | d7f00a3af4692eb8b87a8fe8ff934e44ef3d783701c67872ad62cb1f21703743 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1a242c9b-8fb0-5db5-a662-bf137da65f36.json | https://web.archive.org/web/20261009/https://www.tdlr.texas.gov/TABS/Search/Project/TABS2026024112
1a38543f-df6d-5aed-8878-b4bd2cf46893 | ["announcement"] | ["bb2a6c51-4439-5bda-aa65-a5f7f9e14e98"] | government_record | Shaoguan city records September 21 Shaotang project commencement event | https://www.sg.gov.cn/smsg/sgqmshggn/content/post_2883361.html | Shaoguan Municipal Government / Shaoguan Daily | cn-shaotang | all-rights-reserved | Shaoguan Municipal Government / Shaoguan Daily | 2026-09-22 | 2026-10-13T17:18:54.522614+00:00 | 97a84f3f4da119f90d695253507b0573850f13129c2069a1f1e4862c1527893c | day | sha256_exact_content_decoded_response_bytes |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1a38543f-df6d-5aed-8878-b4bd2cf46893.json | https://web.archive.org/web/20261013171854/https://www.sg.gov.cn/smsg/sgqmshggn/content/post_2883361.html
1a572902-495e-5d09-85d2-f9148814a902 | ["imported:record","milestone:other","role:owner"] | ["b9f9191a-1f90-551d-a8b9-44e6f8833e96"] | company_disclosure | Goldman Sachs Alternatives to Acquire QScale, a Leading Canadian Data Center Platform | https://www.qscale.com/news/goldman-sachs-alternatives-to-acquire-qscale | QScale | www.qscale.com | source-terms-not-recorded | QScale | 2026-05-13 | 2026-10-09 | 465e6d62f72139e93c755900473aa286022ca28991920d94c96ca07ef06fdedb | day | source_record_projection | qscale-q01-levis | s5 | 88ec25d50c62b593691517ad815b73e1bc3d81f12e4e437b5e05f6b866166882 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1a572902-495e-5d09-85d2-f9148814a902.json | https://web.archive.org/web/20261009/https://www.qscale.com/news/goldman-sachs-alternatives-to-acquire-qscale
1a606443-bf19-54d8-8025-8c1e1102c25e | ["context:geometry_identity"] | ["c30aeadf-c2f6-58a5-a8b1-227868f477c1"] | regulatory_filing | Bitzero exhibit 99.80 - Annual information form | https://www.sec.gov/Archives/edgar/data/2100457/000175392626000899/g085467_ex99-80.htm | Bitzero Holdings Inc. via SEC EDGAR | bitzero_sec_filings | all-rights-reserved-fact-extraction-only | Bitzero Holdings Inc.; U.S. Securities and Exchange Commission EDGAR | 2026-05-11 | 2026-08-23 | 459f619d5ad1586a6e12214d7f9892d4ee3423eb3b2beca378e7d19395e5683c | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1a606443-bf19-54d8-8025-8c1e1102c25e.json | https://web.archive.org/web/20260823/https://www.sec.gov/Archives/edgar/data/2100457/000175392626000899/g085467_ex99-80.htm
1a63393b-38dd-5e83-b13b-1b8e4256c63c | ["context:site_distinctness","geometry"] | ["e8a1add0-19fb-5196-ae75-34353e7d580b"] | openstreetmap | OSM copyright: database attribution and share-alike | https://www.openstreetmap.org/copyright | OpenStreetMap Foundation and contributors | europe_round31_firmus_st_leonards | ODbL-1.0 | OpenStreetMap Foundation and contributors |  | 2026-09-09T23:35:07.967Z | f8a8fa47e66155a588de62b7f9d19b581038e2599a90666e051c7ce631f5384d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1a63393b-38dd-5e83-b13b-1b8e4256c63c.json | https://web.archive.org/web/20260909233507/https://www.openstreetmap.org/copyright
1a835559-f037-5b0a-a38e-3b9ed4315099 | ["imported:record","metric:power_capacity"] | ["40a718e2-038a-5edf-a495-ba05e3f76560"] | news | Morocco's Data Center Boom Raises a Power Question | https://northafricapost.com/?p=99949 | The North Africa Post | northafricapost.com | source-terms-not-recorded | The North Africa Post | 2026-09 | 2026-10-09 | 47dd3f06e26635e439c43681097a85001810b258e1df7b6da1ab350d4fd8171e | month | source_record_projection | igoudar-dakhla | s3 | ecc303cf1bc6f0b2f56d8961bee667f83a9912a2a4f1b0a7c40a40887109dfcd | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1a835559-f037-5b0a-a38e-3b9ed4315099.json | https://web.archive.org/web/20261009/https://northafricapost.com/?p=99949
1aac3d2d-a83f-5684-8b27-b556173ac168 | ["context:geometry_identity","context:site_distinctness"] | ["64289119-458d-5fc9-bf51-5af6097220eb"] | company_disclosure | Microsoft Kirkkonummi project - owner, contractor and address | https://local.microsoft.com/blog/microsoft-aikoo-rakentaa-uuden-datakeskusalueen-etela-suomeen/ | Microsoft | microsoft_local_project_updates | all-rights-reserved | Microsoft |  | 2026-09-08T19:09:10Z | 606578acd763fc683775888ec7beeb6252fed3b3e5eaeb049ad4a7323532870b | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1aac3d2d-a83f-5684-8b27-b556173ac168.json | https://web.archive.org/web/20260908190910/https://local.microsoft.com/blog/microsoft-aikoo-rakentaa-uuden-datakeskusalueen-etela-suomeen/
1ad44bfe-736f-511c-91ea-89c64e5f5970 | ["context:source_location_identity","physical_status"] | ["99fa93f5-9f63-5576-b036-2ee8086032a3"] | company_disclosure | Goodman SYD01, 2-8 Lanceley Place, Artarmon | https://au.goodman.com/en/our-properties/properties-for-lease/goodman-syd01 | Goodman Group | goodman_australia_property_pages | all-rights-reserved | Goodman Group |  | 2026-07-20T09:18:30Z | c02900e0abb8cd5a3aabdca24a8dec28b9e4fb111b59b1731be83c6aae95a45b | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1ad44bfe-736f-511c-91ea-89c64e5f5970.json | https://web.archive.org/web/20260720091830/https://au.goodman.com/en/our-properties/properties-for-lease/goodman-syd01
1ae19b56-f226-5eb6-b673-041e0d86c005 | ["imported:geometry","imported:record","metric:land_area","milestone:other"] | ["a5b2cd4f-b857-573e-82b8-6edc1e776eec"] | news | First look at Amazon's New Carlisle data center's administration building, campus | https://wsbt.com/news/local/first-look-at-amazons-new-carlisle-data-centers-administration-building-campus-11-billion-dollar-investment-recruit-workers-technical-careers-multiple-buildings | WSBT | wsbt.com | source-terms-not-recorded | WSBT | 2026-06-03 | 2026-10-09 | 078ef8289f07ca216869579fee20db6facdf1a42c555f3548b1635761c852f7b | day | source_record_projection | aws-project-rainier-new-carlisle | s5 | 9e019ae4b414feaed73344d8d3bddbdaf009ce19c6a6d17e8cf32708910e178a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1ae19b56-f226-5eb6-b673-041e0d86c005.json | https://web.archive.org/web/20261009/https://wsbt.com/news/local/first-look-at-amazons-new-carlisle-data-centers-administration-building-campus-11-billion-dollar-investment-recruit-workers-technical-careers-multiple-buildings
1b01daad-275d-5d85-8065-33576847e484 | ["imported:geometry","imported:record","imported:status","metric:power_capacity","milestone:construction_started","role:developer"] | ["a2de1edb-c874-5d78-902a-e174a5ecd03e"] | government_record | Mihta Askiy Data Centre | https://majorprojects.alberta.ca/details/Mihta-Askiy-Data-Centre/12097 | Government of Alberta, Major Projects | majorprojects.alberta.ca | source-terms-not-recorded | Government of Alberta, Major Projects |  | 2026-10-09 | 7036f5aadf7f3224127a4584f6867b27d3e115b1cd30b4d39eb96705aef517f2 | unknown | source_record_projection | mihta-askiy-data-centre-peace-river | s4 | 472b8f227e3fd0409f1e131ff9a41c0886bdf5f70ed37d3c1a38e42c34cb2913 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1b01daad-275d-5d85-8065-33576847e484.json | https://web.archive.org/web/20261009/https://majorprojects.alberta.ca/details/Mihta-Askiy-Data-Centre/12097
1b1ec251-1aa7-5b40-8ba7-290c3b9cbfe9 | ["context:geometry_identity","context:site_distinctness"] | ["5bfb4ad8-a8f4-5937-9242-a96f9292c385"] | company_disclosure | CSC contact information: Kajaani data center directions | https://csc.fi/en/about-us/contact-information/ | CSC – IT Center for Science Ltd. | europe_round15_csc_lumi_ai | no-open-license-asserted | CSC – IT Center for Science Ltd. |  | 2026-09-09T03:39:23Z | 00abe5f81f2a1b8c0edbe591fa58999a8e82baa31db36176ae5caf8ffc428757 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1b1ec251-1aa7-5b40-8ba7-290c3b9cbfe9.json | https://web.archive.org/web/20260909033923/https://csc.fi/en/about-us/contact-information/
1b7988e6-fae3-537c-8a4a-7702622c0195 | ["imported:geometry","imported:record"] | ["d31725a8-2753-5d70-963d-320d4f6fbb61"] | other | Noida | https://en.wikipedia.org/wiki/Noida | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 82b560b3391e78ae15eda1c2e38fb9d824b4fde4642a60f1170501ffe6361fae | unknown | source_record_projection | sify-noida-02 | s5 | de2cd649d7b533c3c76ce23f61f0aafb9a8f5ea874df5d8d2c5d72dce0096611 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1b7988e6-fae3-537c-8a4a-7702622c0195.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Noida
1bbd948f-24ff-5798-8133-456f2209cf86 | ["context:site_distinctness"] | ["43ded2e8-5dcf-5174-b553-a4a04aaeebe3","7ac977cb-cbe2-5dfd-b058-f26707f86b6c"] | company_disclosure | MERLIN source rights restrictions | https://www.merlinproperties.com/en/legal-notice/ | MERLIN Properties | merlin_edged_official_round4 | all-rights-reserved | MERLIN Properties |  | 2026-09-08T20:50:34Z | d6a457fce4e95c8c55b352a418d6df0f664a860f92110b23db6342cbfb67e354 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1bbd948f-24ff-5798-8133-456f2209cf86.json | https://web.archive.org/web/20260908205034/https://www.merlinproperties.com/en/legal-notice/
1beede7f-9936-551b-a7b8-13a2d7ac1efa | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["d852bc01-c8e9-57c4-b469-9ff3ea1d8a5c"] | company_disclosure | CapitaLand India Trust 1H 2026 results: Chennai current physical works | https://www.capitaland.com/content/dam/capitaland-newsroom/International/2026/july/clint-1h2026-results/2.%20CLINT%201H%202026%20slides_29%20July%202026.pdf | CapitaLand India Trust | capitaland_india_trust_financial_results | all-rights-reserved | CapitaLand India Trust | 2026-07-29 | 2026-09-10T17:52:01.185Z | 5ce78c489021757c8e3f7978039ee3efc256cc58a569625c6f0fc446ea9321af | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1beede7f-9936-551b-a7b8-13a2d7ac1efa.json | https://web.archive.org/web/20260910175201/https://www.capitaland.com/content/dam/capitaland-newsroom/International/2026/july/clint-1h2026-results/2.%20CLINT%201H%202026%20slides_29%20July%202026.pdf
1bf21fc1-2ca5-5f90-b1da-4cb3ca6f4e77 | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:land_area","metric:power_capacity","milestone:first_operational","power_source:wind","role:developer"] | ["b6d175dc-d92a-56ca-a1a7-85306c9de22a"] | company_disclosure | Berlin Data Centres ¦ Wustermark Campus | https://virtusdatacentres.com/locations/germany/berlin-data-centres-wustermark-campus | VIRTUS Data Centres | virtusdatacentres.com | source-terms-not-recorded | VIRTUS Data Centres |  | 2026-10-09 | ae23787dc7a4e55b08d4b327ae4a165922af2172c37af0be52909a1117590011 | unknown | source_record_projection | virtus-wustermark | s3 | 2280f1936acf26cd5cb763e4d09d8dc103abd5d9fcfa88388580dffb2d4a5649 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1bf21fc1-2ca5-5f90-b1da-4cb3ca6f4e77.json | https://web.archive.org/web/20261009/https://virtusdatacentres.com/locations/germany/berlin-data-centres-wustermark-campus
1bf3f4be-636b-5f44-88bd-072d6d3a526f | ["imported:record","metric:jobs_permanent","milestone:announced"] | ["077a5970-0684-5ef0-8320-65efbf78c960"] | news | Amazon to Build $3B AI Data Center in Vicksburg, as Gov. Reeves Proclaims Arrival of the 'Digital Delta' | https://www.mississippifreepress.org/amazon-to-build-3b-ai-data-center-in-vicksburg-as-gov-reeves-proclaims-arrival-of-the-digital-delta/ | Mississippi Free Press | www.mississippifreepress.org | source-terms-not-recorded | Mississippi Free Press | 2025-11-20 | 2026-10-09 | 293ca8c6048dd8d8d6d8718932846bbf7c6cb99bd5f72d2f44165323ecaff686 | day | source_record_projection | aws-vicksburg-warren-county-mississippi | s3 | e1ddd3d99fd07c52d39a039e17ead8347cc72830b536cfe7e1b763cbc216a041 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1bf3f4be-636b-5f44-88bd-072d6d3a526f.json | https://web.archive.org/web/20261009/https://www.mississippifreepress.org/amazon-to-build-3b-ai-data-center-in-vicksburg-as-gov-reeves-proclaims-arrival-of-the-digital-delta/
1c0a3b0c-6e89-5bf2-aaca-bed6426d2b2f | ["context:site_distinctness","geometry"] | ["100cf064-1cae-5dba-a4d9-6c4ae35152ec"] | third_party_dataset | AIGID exact 2026 Tomakomai GeoJSON resource: endpoint and license label | https://www.geospatial.jp/ckan/dataset/aigid-moj-01213/resource/2ead1043-214c-4a4f-b458-ce589d133e4a | Association for Promotion of Infrastructure Geospatial Information Distribution (AIGID) | aigid_moj_cadastral_reference | CC-BY-version-unspecified; underlying MOJ-map-data-custom-terms-2023-01-23 | Ministry of Justice, Japan; AIGID conversion; Data Center Atlas selection and display-anchor derivation |  | 2026-09-08T21:43:46.421Z | 80df0de4c926efd7dafad615282bbdf5e56de7da6455a82d42c6467961966939 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1c0a3b0c-6e89-5bf2-aaca-bed6426d2b2f.json | https://web.archive.org/web/20260908214346/https://www.geospatial.jp/ckan/dataset/aigid-moj-01213/resource/2ead1043-214c-4a4f-b458-ce589d133e4a
1c2e246b-2818-533c-93e6-ca5c3dee5644 | ["context:source_location_identity"] | ["bb8ba3ad-d563-5f84-a543-079a10264640"] | company_disclosure | CDC Maddington current campus page | https://cdc.com.au/locations/perth/ | CDC Data Centres | cdc_current_location_pages | all-rights-reserved | CDC Data Centres |  | 2026-07-21T17:12:46Z | 9628085823f3434144b66048b965c5b4babac113a5041c8191ca954706356c5c | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1c2e246b-2818-533c-93e6-ca5c3dee5644.json | https://web.archive.org/web/20260721171246/https://cdc.com.au/locations/perth/
1c3bcbbc-7232-5a74-a3c0-c9c32a460a20 | ["imported:record","imported:status","metric:power_capacity","milestone:other","role:developer","role:operator"] | ["3fe8297a-147b-56fe-a5a6-6ae165798506"] | company_disclosure | AirTrunk secures largest financing for a data centre in Japan with US$1.2 billion green loan | https://airtrunk.com/airtrunk-secures-largest-financing-for-a-data-centre-in-japan-with-us1-2-billion-green-loan-for-its-flagship-tokyo-campus/ | AirTrunk | airtrunk.com | source-terms-not-recorded | AirTrunk | 2026-03-10 | 2026-10-09 | bb0a2b703bd9534a205a82fd3e42aac7bfcc3436228fc618b233bb85323b0797 | day | source_record_projection | airtrunk-tok1-inzai | s4 | 4c28605b649ccf51780503b5829856089f31072a900b71c243bb8f4e88762814 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1c3bcbbc-7232-5a74-a3c0-c9c32a460a20.json | https://web.archive.org/web/20261009/https://airtrunk.com/airtrunk-secures-largest-financing-for-a-data-centre-in-japan-with-us1-2-billion-green-loan-for-its-flagship-tokyo-campus/
1c75ed75-477d-5d59-9337-803500086218 | ["context:site_distinctness","geometry"] | ["d852bc01-c8e9-57c4-b469-9ff3ea1d8a5c"] | government_record | Minerva Chennai Project Site KML: source-specific project polygon | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=40829&refId=5696080&refType=caf&uuid=963db531-1544-4984-8bef-f68e8a9a0ade&version=1.1 | Minerva Veritas Data Centre Private Limited, proponent; PARIVESH, Government of India, host | india_parivesh_public_environmental_proposals | no-open-license-asserted | Minerva Veritas Data Centre Private Limited, proponent; PARIVESH, Government of India, host |  | 2026-09-10T17:47:49.338Z | d81e269d9496bee594ba88fd2bcd218f9af430e15118e580b31ba20e6c3e8d4e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1c75ed75-477d-5d59-9337-803500086218.json | https://web.archive.org/web/20260910174749/https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=40829&refId=5696080&refType=caf&uuid=963db531-1544-4984-8bef-f68e8a9a0ade&version=1.1
1c80fcc9-5d29-5196-9ecf-9ed583c6f1f4 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["aa2dc8a4-52d8-5519-b23a-2ff0313db9e3"] | company_disclosure | MERLIN 6M26: project-bound Getafe II demolition underway | https://ir.merlinproperties.com/wp-content/uploads/2026/07/RI-6M26-MERLIN-Properties_eng.pdf | MERLIN Properties | expansion_round5_primary_sources | all-rights-reserved | MERLIN Properties | 2026-07-27 | 2026-09-08T20:44:38Z | 6b782137a240bdb3195249f1029b24b71e71f3f206e60ec9ebd2c450b7538dc6 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1c80fcc9-5d29-5196-9ecf-9ed583c6f1f4.json | https://web.archive.org/web/20260908204438/https://ir.merlinproperties.com/wp-content/uploads/2026/07/RI-6M26-MERLIN-Properties_eng.pdf
1c941f06-0df3-5b78-b123-f307d1dfbe10 | ["context:site_distinctness"] | ["14a67880-da37-5f59-a2cf-2322bbf778d7"] | company_disclosure | DigiCo August 21 operator report separates completed upgrade and next expansion | https://www.hmccapital.com.au/investment-strategies/digital-infrastructure/digico-infrastructure-reit/asx-announcements/fy26-results-presentation/ | DigiCo Infrastructure REIT / HMC Capital | digico_official_public_reporting | all-rights-reserved | DigiCo Infrastructure REIT / HMC Capital |  | 2026-09-09T08:55:53.950Z | 3ace8c99e510efd4217e7cd72767298a4ef9382addc335d200b2030cc449ca17 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1c941f06-0df3-5b78-b123-f307d1dfbe10.json | https://web.archive.org/web/20260909085553/https://www.hmccapital.com.au/investment-strategies/digital-infrastructure/digico-infrastructure-reit/asx-announcements/fy26-results-presentation/
1caa8d44-b6d4-5345-b24c-76b1cbaa5026 | ["imported:record","metric:power_capacity","milestone:other","role:developer"] | ["4a0d8f6f-b848-5650-a479-4f0caee97fa1"] | news | Alberta regulator rejects proposal for massive data centre in Olds over deficient application | https://thelogic.co/briefing/alberta-regulator-rejects-proposal-for-massive-data-centre-in-olds-over-deficient-application/ | The Logic | thelogic.co | source-terms-not-recorded | The Logic | 2026-03-09 | 2026-10-09 | 64a4f72006a0e402ba98c72d169075b35b4da18596be24c1cb089f63a03bbd86 | day | source_record_projection | synapse-olds | s3 | 14fc93e0f111163a184e77ec2774f5d985878a5d18f5faf2fad82a140bde792d | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1caa8d44-b6d4-5345-b24c-76b1cbaa5026.json | https://web.archive.org/web/20261009/https://thelogic.co/briefing/alberta-regulator-rejects-proposal-for-massive-data-centre-in-olds-over-deficient-application/
1cafca44-f42f-5814-982a-730ce77686e5 | ["context:site_distinctness","geometry"] | ["fa44cb24-5185-5616-a6a2-3977f190001f"] | government_record | TxGIO StratMap 9-1-1 address point: 110 SOUTHWEST 9001, Andrews County | https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0/query?where=full_addr%3D%27110%20SOUTHWEST%209001%27%20AND%20county%3D%27Andrews%27&outFields=*&returnGeometry=true&outSR=4326&f=json | Texas Geographic Information Office (TxGIO), Texas Water Development Board | txgio_stratmap_address_points | public-use-as-is | Texas Geographic Information Office, StratMap Address Points; 9-1-1 source authority CSEC |  | 2026-09-25T22:36:27.650Z | 68e69efc1e3b2f4bbc1b72609a9c349def79d38c279f09d23fc91ab33ea7c6de | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1cafca44-f42f-5814-982a-730ce77686e5.json | https://web.archive.org/web/20260925223627/https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0/query?where=full_addr%3D%27110%20SOUTHWEST%209001%27%20AND%20county%3D%27Andrews%27&outFields=*&returnGeometry=true&outSR=4326&f=json
1cf26270-52c3-5e65-b4bb-92c10a00d4f9 | ["imported:record","imported:status","metric:buildings","metric:floor_area","metric:land_area","metric:power_capacity","milestone:other","role:builder","role:developer","role:owner"] | ["a490f00a-8b75-5547-b0e9-5fb3b6e5f616"] | trade_press | Aligned Tops out New Maryland Data Center | https://baxtel.com/news/aligned-tops-out-new-maryland-data-center | Baxtel | baxtel.com | source-terms-not-recorded | Baxtel | 2026-03-12 | 2026-10-09 | 223fbd4f532812bb1e60c7e8c774624a16f4c5c7c8771c05a2ad953513a6fa45 | day | source_record_projection | quantum-frederick | s4 | 98a19a570fec7492c5695c7b8bfda0e04f30819df89668cd9a89dcebba4c7f12 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1cf26270-52c3-5e65-b4bb-92c10a00d4f9.json | https://web.archive.org/web/20261009/https://baxtel.com/news/aligned-tops-out-new-maryland-data-center
1d0890d8-0e46-53db-b916-42fd2742e4b3 | ["context:geometry_identity","context:site_distinctness"] | ["fc6dd688-fca0-5a7f-a6e9-54f9116607c5"] | government_record | Paju factory register2018Q1 - publication and attachment linkage | https://www.paju.go.kr/user/board/BD_board.view.do?bbsCd=2003&seq=20180406090751845 | City of Paju | paju_city_historical_factory_registers | all-rights-reserved | City of Paju | 2018-04-06 | 2026-09-08T20:09:39Z | 46bfa8a7150a618c36ae7cbbaccb5c9302b796b298d7975e7e532425f44989f1 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d0890d8-0e46-53db-b916-42fd2742e4b3.json | https://web.archive.org/web/20260908200939/https://www.paju.go.kr/user/board/BD_board.view.do?bbsCd=2003&seq=20180406090751845
1d1c1313-e4ef-5c51-89f4-bdca74e11a2e | ["context:geometry_identity","context:site_distinctness"] | ["6a3cb870-eb89-5d4b-a486-44eb7d10f8b0"] | government_record | Hong Kong ITIB March 2 tender result: Sandy Ridge Data Facility Cluster, Lot 953 in DD 89 | https://www.info.gov.hk/gia/general/202603/02/P2026030200249.htm | Innovation, Technology and Industry Bureau, Government of the Hong Kong SAR | hksar_government_press_releases | no-open-license-asserted | Government of the Hong Kong SAR (info.gov.hk) | 2026-03-02 | 2026-09-25T22:31:35.131Z | 3c32ca732a499ca4755257d79ed412c09213615a0b93c9c93fe11a43b5fbca19 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d1c1313-e4ef-5c51-89f4-bdca74e11a2e.json | https://web.archive.org/web/20260925223135/https://www.info.gov.hk/gia/general/202603/02/P2026030200249.htm
1d25d015-a527-5efe-a7dc-2791f489ff34 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["e56ff51f-930c-5c5b-bc82-7add264e576e"] | company_disclosure | Google infrastructure principal reports continuing Elmina construction in dated interview | https://mediaselangor.com/en/2026/08/390529 | Media Selangor; first-hand interview with Google infrastructure principal Ken Siah | asia_round30_google_elmina | no-open-license-asserted | Media Selangor; first-hand interview with Google infrastructure principal Ken Siah | 2026-08-20 | 2026-09-09T11:45:11.253Z | db3ee6d2e644cda4ca13cf1a613b9c2feac73a75ace65c4c6449562343fa60ee | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d25d015-a527-5efe-a7dc-2791f489ff34.json | https://web.archive.org/web/20260909114511/https://mediaselangor.com/en/2026/08/390529
1d43f3d5-ca96-50d2-aadc-660f30981b8c | ["imported:record","metric:buildings","metric:power_capacity","milestone:construction_started","milestone:first_operational","milestone:other","power_source:fuel_cell","power_source:natural_gas_onsite","power_source:other","role:developer","role:power_supplier","role:tenant"] | ["6f0acd88-cd04-5f3f-915c-48a71fd51f39"] | analyst_report | Behind-the-meter data centers: Stargate Project Jupiter | https://cleanview.co/reports/behind-the-meter-data-centers/full-report/stargate-jupiter | Cleanview | cleanview.co | source-terms-not-recorded | Cleanview |  | 2026-10-09 | e17c8e6b4de0e77f2361123dce54369948c2606aff0a8e91eea6b22a4ed9d52b | unknown | source_record_projection | openai-stargate-dona-ana-county | s4 | 8e31c0a50f8ac2a25edc79eb491092d84a4d788513541c7270cf128763c98146 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d43f3d5-ca96-50d2-aadc-660f30981b8c.json | https://web.archive.org/web/20261009/https://cleanview.co/reports/behind-the-meter-data-centers/full-report/stargate-jupiter
1d5aaa5f-b165-5194-899b-0e032ebc7701 | ["imported:record","role:tenant"] | ["d87a919b-df32-53fa-bc01-47b7f6f1dce9"] | company_disclosure | Core Scientific announces second quarter 2026 results | https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-07-28 | 2026-10-09 | b70ec1a285588315094bb4c9fa71ad598c095bae8feb80f667d38aa11d7f73d3 | day | source_record_projection | core-scientific-muskogee | s8 | 27770cbed3a06baa8115f406673dbf040757ebfc6782e12fbac9b4ef314a02c5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d5aaa5f-b165-5194-899b-0e032ebc7701.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results
1d6cc958-8ca3-5a8c-ab4b-a07cf5a45b32 | ["physical_status"] | ["2e2b9d40-5024-5e6d-bbb2-56a8b16b9c16"] | company_disclosure | CDC Eastern Creek EC5 current status | https://cdc.com.au/locations/sydney/ | CDC Data Centres | cdc_current_location_pages | all-rights-reserved | CDC Data Centres |  | 2026-07-21T17:12:46Z | 66d6de9440d4496482af80159cbe361afdb8e36bdebd5edf81ac1c65f1337620 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d6cc958-8ca3-5a8c-ab4b-a07cf5a45b32.json | https://web.archive.org/web/20260721171246/https://cdc.com.au/locations/sydney/
1d917775-0af3-5219-98e1-39146778e43a | ["imported:geometry","imported:record","metric:power_capacity","milestone:announced","power_source:grid","role:developer","role:power_supplier"] | ["a5618437-38a6-5fd0-a340-56ab10f1e97b"] | company_disclosure | Constellation and CyrusOne Announce Agreement to Support New Data Center Facility at Freestone Energy Center in Texas | https://www.cyrusone.com/resources/press-releases/constellation-and-cyrusone-announce-agreement-to-support-new-data-center-facility-at-freestone-energy-center-in-texas | CyrusOne | www.cyrusone.com | source-terms-not-recorded | CyrusOne | 2026-02-09 | 2026-10-09 | 712bc5d565a21b6af25175ee3ac35d2bf515ea19b44ff7b516d27eaa6b537291 | day | source_record_projection | cyrusone-freestone-county | s1 | 6a4ceb3cac6ddc4faecfc7a89809b4861740596566c42b6a9ceaee9af91a1642 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d917775-0af3-5219-98e1-39146778e43a.json | https://web.archive.org/web/20261009/https://www.cyrusone.com/resources/press-releases/constellation-and-cyrusone-announce-agreement-to-support-new-data-center-facility-at-freestone-energy-center-in-texas
1d9f465e-6826-5ca7-8f71-903dc85cf877 | ["imported:record","imported:status","metric:power_capacity","milestone:first_operational","milestone:other","role:tenant"] | ["40abc164-3033-5172-b386-52422d1513b9"] | regulatory_filing | Core Scientific Q2 2026 earnings presentation (Form 8-K, Exhibit 99.2) | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-07-28 | 2026-10-09 | 2979ca9805a0120ce59a068aaa14add9820a62c714bd19b78ecf364571f3376f | day | source_record_projection | core-scientific-hunt-county | s3 | f3d8655922984d28b63705187f2e9186750a7799301fc3ba8ed58403f4c0acd3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1d9f465e-6826-5ca7-8f71-903dc85cf877.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000012/q2fy26earningsdeck728am.htm
1da49023-dd86-5890-ad4c-a83551c3d516 | ["imported:record","imported:status","metric:power_capacity","milestone:first_operational","role:developer"] | ["2e14f098-9798-567b-ae40-a7d552f9be18"] | company_disclosure | TeraWulf reports second quarter 2026 results | https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results | TeraWulf | investors.terawulf.com | source-terms-not-recorded | TeraWulf | 2026-08-05 | 2026-10-09 | 332c91af6595bbec0f5d3422590e459075b8ea3382432b88052b40d1d7f227dc | day | source_record_projection | terawulf-lake-hawkeye | s3 | d8d535edbd465f66e5e0963a5691de97b492f14002691ea654db6ada9c90efd8 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1da49023-dd86-5890-ad4c-a83551c3d516.json | https://web.archive.org/web/20261009/https://investors.terawulf.com/news-events/press-releases/detail/144/terawulf-reports-second-quarter-2026-results
1da75167-6f75-52a8-8d5c-81dfd3d4b7bf | ["imported:record","imported:status","metric:investment","metric:power_capacity","milestone:fully_operational","role:builder","role:developer"] | ["912a1942-9e25-5d1f-b3ce-7f39f60ca845"] | trade_press | SDAIA Hexagon Data Centre (project profile) | https://ognnews.com/ArticleOGN/461988/sdaia-hexagon-data-centre | Oil & Gas News | ognnews.com | source-terms-not-recorded | Oil & Gas News | 2026-05-01 | 2026-10-09 | 69a5ee4855530623d960fea98c254f8750036b67b46369e2d1dc71668f2247c3 | day | source_record_projection | sdaia-hexagon-riyadh | s3 | 5a355aa9d4df550b443d510babcc5ebcbe3c271cec99a7f31673680ead44846b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1da75167-6f75-52a8-8d5c-81dfd3d4b7bf.json | https://web.archive.org/web/20261009/https://ognnews.com/ArticleOGN/461988/sdaia-hexagon-data-centre
1ddc9461-bcfb-5df4-bb52-ef88c2d1b13c | ["context:geometry_identity","context:site_distinctness"] | ["867d91cb-7a17-59db-a92e-4a50a499f54f","b3656b35-f3ad-5119-8918-ac5237bf2a7f"] | company_disclosure | Microsoft L’Ancienne-Lorette scope and bounded successor context | https://local.microsoft.com/blog/lancienne-lorette-datacentre-construction-update/ | Microsoft | americas_round30_microsoft_quebec | no-open-license-asserted | Microsoft |  | 2026-09-09T11:54:41.394Z | 55bb263d4d52d0ddb4d62c540bb8faacab068fad8667253cc9cfe3d7117e0e86 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1ddc9461-bcfb-5df4-bb52-ef88c2d1b13c.json | https://web.archive.org/web/20260909115441/https://local.microsoft.com/blog/lancienne-lorette-datacentre-construction-update/
1de91fed-9b38-5c47-886d-5fa766be2aa0 | ["geometry"] | ["86bcbcd1-702d-5afa-aeb8-1cb145224b97"] | government_record | Census Public_AR_Current match for 323 North High Street | https://geocoding.geo.census.gov/geocoder/ | United States Census Bureau | us_census_geocoder | public-domain-us-government | United States Census Bureau |  | 2026-08-23 | 70c9ee69586590257deb71dc27cb0878d8d205b8c16be886dc909e8e00b37833 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1de91fed-9b38-5c47-886d-5fa766be2aa0.json | https://web.archive.org/web/20260823/https://geocoding.geo.census.gov/geocoder/
1deeba50-c61e-5703-a5eb-a4b870f9a9ea | ["context:site_distinctness","geometry"] | ["b0588082-53ae-577a-b989-667b8f9f171d"] | company_disclosure | Digital Realty current runtime resolves the reviewed map component versions | https://www.digitalrealty.com/_next/static/chunks/webpack-b78081d3905b684e.js | Digital Realty | europe_round24_fechenheim | no-open-license-asserted | Digital Realty |  | 2026-09-09T08:23:58Z | b5c78e9a291f9c082f921a6ab6d32539bbff06d5f4daf5a32dde7cac162ae15d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1deeba50-c61e-5703-a5eb-a4b870f9a9ea.json | https://web.archive.org/web/20260909082358/https://www.digitalrealty.com/_next/static/chunks/webpack-b78081d3905b684e.js
1df077b4-ffa3-5938-a5fe-88d5b4028ad4 | ["context:geometry_identity"] | ["b3b98301-a692-5790-88e7-656d77e8fb69"] | openstreetmap | OpenStreetMap address-object containment proof for NTT Frankfurt 1 | https://www.openstreetmap.org/way/697501723 | OpenStreetMap contributors | openstreetmap | ODbL-1.0 | © OpenStreetMap contributors |  | 2026-08-20T23:57:12Z | c63c5411afcf91dc35a0e16a7c27e4d8234e4810810a9feb97a568ac7920d582 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1df077b4-ffa3-5938-a5fe-88d5b4028ad4.json | https://web.archive.org/web/20260820235712/https://www.openstreetmap.org/way/697501723
1e2a7ea7-9439-5415-810a-75656b9f2b31 | ["imported:record","imported:status","metric:investment","metric:power_capacity","milestone:construction_started","milestone:first_operational","role:owner"] | ["27c38b34-579b-5542-b04b-44d6d5747bff"] | analyst_report | Google Cedar Rapids ¦ AI data centers | https://epoch.ai/data/ai-data-centers/directory/google-cedar-rapids | Epoch AI | epoch.ai | source-terms-not-recorded | Epoch AI | 2026-10-05 | 2026-10-09 | 40318f4886cd6191b7615dbd1aa47bda8c3d131e631dcee4e846e214afb675a2 | day | source_record_projection | google-cedar-rapids-iowa | s4 | df53e48c7006c49a303c8441490dbef432e4f568bd62589405eab64482984a16 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1e2a7ea7-9439-5415-810a-75656b9f2b31.json | https://web.archive.org/web/20261009/https://epoch.ai/data/ai-data-centers/directory/google-cedar-rapids
1e2e5d54-724b-5882-8b4b-8dbd2350b253 | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:first_operational","power_source:grid","role:developer"] | ["b10fbc1b-2689-5864-989c-b36b13abb9ad"] | news | A $1.3B power plant and data centre is in the works northwest of Edmonton | https://dailyhive.com/edmonton/power-plant-data-centre-swan-hills | Daily Hive | dailyhive.com | source-terms-not-recorded | Daily Hive | 2026-09-23 | 2026-10-09 | 09e578f5e3258b8b2bf49827a90929064167d6f50fa100bf6cec7e872d02dc1b | day | source_record_projection | teton-digital-black-bear-swan-hills | s4 | d01e8fafc2f8a182ec3539b2223aeaa9076b7c425026e60538d9904df7100d82 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1e2e5d54-724b-5882-8b4b-8dbd2350b253.json | https://web.archive.org/web/20261009/https://dailyhive.com/edmonton/power-plant-data-centre-swan-hills
1e532437-06f5-5fc8-8a2f-9d239405abc1 | ["context:geometry_identity","context:site_distinctness","geometry"] | ["b0be5071-aff0-5470-a041-a0be3cc8385a"] | company_disclosure | Goodman MAD01 - exact address and map link | https://es.goodman.com/-/media/project/goodman/spain/files/property/properties-for-lease/mad01/es_mad-01_data-centre_digibrochure_en.pdf | Goodman Group | goodman_mad01_brochure | all-rights-reserved | Goodman Group |  | 2026-09-08T19:52:55Z | 74413f12d58eae05977028ea20fe06299cc83fb88524d86d60442d31b709a266 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1e532437-06f5-5fc8-8a2f-9d239405abc1.json | https://web.archive.org/web/20260908195255/https://es.goodman.com/-/media/project/goodman/spain/files/property/properties-for-lease/mad01/es_mad-01_data-centre_digibrochure_en.pdf
1e5b63b2-b334-52e0-94a1-f78d02457964 | ["geometry"] | ["3941c42e-216d-52fa-b0d8-d7555b441a1a"] | company_disclosure | maincubes Factsheet BER02 | https://www.maincubes.com/wp-content/uploads/2026/02/maincubes_factsheet_ber02_en.pdf | maincubes | maincubes_data_center_factsheets | all-rights-reserved | maincubes |  | 2026-07-19T20:43:30Z | 32e7ca51d69ebf49621a17a97f7fb7db4a5d948ec4a88886b6a020e3da4cf43a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1e5b63b2-b334-52e0-94a1-f78d02457964.json | https://web.archive.org/web/20260719204330/https://www.maincubes.com/wp-content/uploads/2026/02/maincubes_factsheet_ber02_en.pdf
1e7d82eb-791b-578e-b8b8-6c9312497731 | ["context:site_distinctness","geometry"] | ["12407b2e-a44d-5c8d-aa62-c7b64045e20f"] | government_record | Exact Cass County APLD FAR-01 parcel | https://gisweb.casscountynd.gov/arcgis/rest/services/OpenData/OpenData/FeatureServer/7/query?where=GISPIN%3D%2775000000120020%27&outFields=OBJECTID,GISPIN,DASHPIN,Name,PropertyAddress,ACRES,Section,LandCity,LandSt,LandZip&returnGeometry=true&outSR=4326&f=pjson | Cass County North Dakota | americas_round5 | public-domain-per-Cass-County-item-policy | Cass County North Dakota |  | 2026-09-08T21:45:14Z | 14aa4e3e568e41c7457aa744301e11a0002f23d2ef4256ff6989d64eb330de4f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1e7d82eb-791b-578e-b8b8-6c9312497731.json | https://web.archive.org/web/20260908214514/https://gisweb.casscountynd.gov/arcgis/rest/services/OpenData/OpenData/FeatureServer/7/query?where=GISPIN%3D%2775000000120020%27&outFields=OBJECTID,GISPIN,DASHPIN,Name,PropertyAddress,ACRES,Section,LandCity,LandSt,LandZip&returnGeometry=true&outSR=4326&f=pjson
1eb33017-9a24-53cd-ad7e-0f707ac74c02 | ["context:geometry_identity","context:site_distinctness"] | ["a1390e66-5b95-568b-869b-b9413c56f8ce"] | other | Industry award organizer identifies NBG6 BA3 as modular 400-square-metre expansion of Nürnberg Süd | https://www.eco.de/?p=274354&post_type=page | eco - Association of the Internet Industry | europe_mena_round12_expansion_asia | no-open-license-asserted | eco - Association of the Internet Industry |  | 2026-09-09T03:13:44Z | 4f40aa8730885e6aaa735008be9b42c4d296f1babcc43a1d589784f13bad04ba | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1eb33017-9a24-53cd-ad7e-0f707ac74c02.json | https://web.archive.org/web/20260909031344/https://www.eco.de/?p=274354&post_type=page
1ec15cfd-6343-5e8d-bdfd-cc9b07fdf514 | ["context:site_distinctness","geometry"] | ["9217888a-3e78-5b75-ac86-bd32ef026084"] | openstreetmap | Nominatim documents latitude and longitude as object-centroid fields | https://nominatim.org/release-docs/latest/api/Output/ | Nominatim project | europe_mena_round10_expansion_asia | no-open-license-asserted | Nominatim project |  | 2026-09-08T23:48:45.688Z | 2b22abff55df61794873a6648149a09a46262c4f409578cb8d6823de3d6b5f7e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1ec15cfd-6343-5e8d-bdfd-cc9b07fdf514.json | https://web.archive.org/web/20260908234845/https://nominatim.org/release-docs/latest/api/Output/
1ee6b991-a57e-562f-992e-34e4bb6015b8 | ["context:geometry_identity","context:site_distinctness"] | ["14a67880-da37-5f59-a2cf-2322bbf778d7"] | company_disclosure | SHAPE FY26 annual report identifies Peter Marix-Evans as CEO | https://app.sharelinktechnologies.com/announcement/asx/b6662ed032c0a7e523bb950bbf61b403 | SHAPE Australia Corporation Limited | shape_official_results | all-rights-reserved | SHAPE Australia Corporation Limited |  | 2026-09-09T08:53:39.283Z | 672fb50f89f148bf90d1ca924cfdddd8d92f4f3723dcc0a3c9277fa36421564d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1ee6b991-a57e-562f-992e-34e4bb6015b8.json | https://web.archive.org/web/20260909085339/https://app.sharelinktechnologies.com/announcement/asx/b6662ed032c0a7e523bb950bbf61b403
1f1fdaa4-75e0-53d1-9e81-65fdbc1c09bb | ["imported:record","metric:power_capacity","milestone:other","role:developer"] | ["384a401d-cc7f-52e4-9ae3-218a378995b9"] | trade_press | Khazna Awarded Uptime Tier III Certification of Design Documents for Ajman, UAE Facility, Largest in Company's Portfolio | https://itweb.africa/article/khazna-awarded-uptime-tier-iii-certification-of-design-documents-for-ajman-uae-facility-largest-in-companys-portfolio/lLn147mQVWz7J6Aa | ITWeb Africa (Uptime Institute release via Business Wire) | itweb.africa | source-terms-not-recorded | ITWeb Africa (Uptime Institute release via Business Wire) | 2026-02-25 | 2026-10-09 | 29e9c90cd57dd961c0dd6a4de99076edc0000835f0a075811658144e920b6ab6 | day | source_record_projection | khazna-ajman | s6 | 92a643d476e98c5addb8185cc1322ba283996fcbede435884f9449965f68ea71 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f1fdaa4-75e0-53d1-9e81-65fdbc1c09bb.json | https://web.archive.org/web/20261009/https://itweb.africa/article/khazna-awarded-uptime-tier-iii-certification-of-design-documents-for-ajman-uae-facility-largest-in-companys-portfolio/lLn147mQVWz7J6Aa
1f2cd24b-81fb-5075-a1a7-dc959ca421ba | ["context:site_distinctness","geometry"] | ["867d91cb-7a17-59db-a92e-4a50a499f54f","b3656b35-f3ad-5119-8918-ac5237bf2a7f"] | government_record | RQA address-layer schema and native NAD83(CSRS) | https://servicescarto.mern.gouv.qc.ca/pes/rest/services/Territoire/RQA_WMS/MapServer/0?f=pjson | Québec Ministère des Ressources naturelles et des Forêts | americas_round30_microsoft_quebec | CC-BY-4.0 | Québec Ministère des Ressources naturelles et des Forêts |  | 2026-09-09T11:51:23.008Z | c146b02bc3e33a5d64a448893a88138782da12c11b9ff663ce26bbdc9b3fc18f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f2cd24b-81fb-5075-a1a7-dc959ca421ba.json | https://web.archive.org/web/20260909115123/https://servicescarto.mern.gouv.qc.ca/pes/rest/services/Territoire/RQA_WMS/MapServer/0?f=pjson
1f3e196a-da54-548c-8d11-d91607c3cae3 | ["imported:geometry","imported:record","imported:status","metric:power_capacity","milestone:first_operational","power_source:grid","role:developer","role:owner","role:tenant"] | ["b6f0ed21-2ab2-51e2-971e-4e9512279101"] | regulatory_filing | TeraWulf Inc. Form 10-K for the fiscal year ended December 31, 2025 | https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm | U.S. Securities and Exchange Commission (TeraWulf filing) | www.sec.gov | source-terms-not-recorded | U.S. Securities and Exchange Commission (TeraWulf filing) | 2026-02-27 | 2026-10-09 | d3e84b1907c41fae5cd053f8ba06ce4f9642a3ecc7f97f30f40568646b3ab8c9 | day | source_record_projection | terawulf-fluidstack-abernathy | s3 | c78e69781f5e1182302f758390b03e4b52f85cc85c10d9fbb82d5c157135f5a3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f3e196a-da54-548c-8d11-d91607c3cae3.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1083301/000108330126000031/wulf-20251231.htm
1f3f4582-48b8-5490-9d67-31ac283d00c1 | ["imported:record","metric:buildings","metric:power_capacity","milestone:other","role:tenant"] | ["32b98d7e-1d0f-5c16-af18-3f469f3b662b"] | company_disclosure | Applied Digital Completes Phase II Ready for Service at Polaris Forge 1, Fully Energizing First 100 MW Building | https://ir.applieddigital.com/news-events/press-releases/detail/137/applied-digital-completes-phase-ii-ready-for-service-at | Applied Digital | ir.applieddigital.com | source-terms-not-recorded | Applied Digital | 2025-11-24 | 2026-10-09 | ff72d167f0c96c7af4c07de6908c3628c674b513fedd6fef9f009710f4753225 | day | source_record_projection | applied-digital-polaris-forge-1 | s3 | 02039c7978eb5ad0982cb959c5731f70118c004f1fe48428a14ffb1b20797de1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f3f4582-48b8-5490-9d67-31ac283d00c1.json | https://web.archive.org/web/20261009/https://ir.applieddigital.com/news-events/press-releases/detail/137/applied-digital-completes-phase-ii-ready-for-service-at
1f444679-4f9d-5dc3-952f-64a062473389 | ["imported:geometry","imported:record","imported:status","metric:floor_area","metric:investment","milestone:construction_started","milestone:other","role:owner"] | ["93e5705d-3c86-524c-8089-0868d13bbd0d"] | regulatory_filing | TABS project TABS2026023821: Journey 1A (JNR1A) | https://www.tdlr.texas.gov/TABS/Search/Print/TABS2026023821 | Texas Department of Licensing and Regulation | www.tdlr.texas.gov | source-terms-not-recorded | Texas Department of Licensing and Regulation | 2026-06-25 | 2026-10-09 | acff34c0bfe8009e666877cfc2bd07cfb76aa78623c35b236a3ba93c732367af | day | source_record_projection | google-journey-haskell-county-texas | s4 | 72e5be79448d9c10c235e6e58f736780f1941773120215f3afa2cd445bf665d7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f444679-4f9d-5dc3-952f-64a062473389.json | https://web.archive.org/web/20261009/https://www.tdlr.texas.gov/TABS/Search/Print/TABS2026023821
1f5b7d3a-f4d6-5215-8d66-ac2de4a9cb41 | ["imported:geometry","imported:record","imported:status","metric:land_area","milestone:other","power_source:other","role:developer","role:government"] | ["8e72e640-c0e0-5e58-8a76-e53c011dcf92"] | news | Taylor City Council approves deal to clear the way for a nearby data center and power plant | https://www.kut.org/energy-environment/2026-10-09/taylor-tx-annex-data-center-power-plant | KUT News | www.kut.org | source-terms-not-recorded | KUT News | 2026-10-09 | 2026-10-09 | 77f4fa9de1b603d06fb63c88b117a15e8afccf9f8aa3a458d63c20801e29c315 | day | source_record_projection | powerhouse-big-watt-taylor | s3 | fdd4764a33b08456c9173f8afbfd7ea9a7fc8a466505b3f720f9157bcfcccc1c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f5b7d3a-f4d6-5215-8d66-ac2de4a9cb41.json | https://web.archive.org/web/20261009/https://www.kut.org/energy-environment/2026-10-09/taylor-tx-annex-data-center-power-plant
1f776e1f-3f79-53d1-880c-e90b0fd8b958 | ["workload","workload_scope:intended"] | ["37e33657-b788-57e6-98f2-b78834cdecda"] | company_disclosure | AVAIO Digital Breaks Ground on $6 Billion Brandon Data Center Campus; Leading Mississippi Contractor Begins Site Work | https://www.avaiodigital.com/updates/avaio-digital-breaks-ground-on-6-billion-brandon-data-center-campus-leading-mississippi-contractor-begins-site-work | AVAIO Digital Partners | avaio_digital_updates | all-rights-reserved | AVAIO Digital Partners | 2025-09-10 | 2026-07-20T05:42:11Z | 6a079899544c4c251df2c9c2fe959df702f4695ced5acc1a3bf570f3704acf81 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f776e1f-3f79-53d1-880c-e90b0fd8b958.json | https://web.archive.org/web/20260720054211/https://www.avaiodigital.com/updates/avaio-digital-breaks-ground-on-6-billion-brandon-data-center-campus-leading-mississippi-contractor-begins-site-work
1f8cb4b3-cb47-5293-875f-d9e50d2d0482 | ["context:geometry_identity","context:site_distinctness"] | ["95b33a98-a85e-57af-b18d-6811a7fd3b20"] | company_disclosure | NEXTDC KL1 official contact entry: Petaling Jaya address | https://www.nextdc.com/contact | NEXTDC Limited | nextdc_official_campus_locator | all-rights-reserved | NEXTDC Limited |  | 2026-09-08T20:46:45Z | a0f41425492c1b34f30399d2e6192ea6b59f0031f3b0e503a2210a7df7673893 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1f8cb4b3-cb47-5293-875f-d9e50d2d0482.json | https://web.archive.org/web/20260908204645/https://www.nextdc.com/contact
1fc10052-2e4c-517e-9cea-2e5f1c959a8f | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","milestone:announced","role:developer"] | ["ec8c635b-93db-5c3c-904e-820b7c4f1233"] | trade_press | Microsoft abrirá otro centro de datos en Aragón (el tercero) | https://inspenet.com/noticias/microsoft-abrira-centro-de-datos-en-aragon/ | Inspenet | inspenet.com | source-terms-not-recorded | Inspenet | 2024-07-04 | 2026-10-09 | f6d870174f663042c654502145b660201ec7e58925c6fd82867b8eab965a9199 | day | source_record_projection | microsoft-aragon-villamayor-de-gallego | s2 | d2af0f994a460d635bbec1a07ec9c75d3ea424551a637463b05ddc35b2a2a30b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1fc10052-2e4c-517e-9cea-2e5f1c959a8f.json | https://web.archive.org/web/20261009/https://inspenet.com/noticias/microsoft-abrira-centro-de-datos-en-aragon/
1fdde38e-79d4-5d65-83e5-f686e75392a1 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["5443b4c1-09dc-5f14-a9a3-ec32c05602fb"] | company_disclosure | dataR July17: current construction and later operations | https://www.datar.de/zwei-neue-kollegen-ein-gemeinsamer-start/ | dataR GmbH | europe_round30_datar_rellingen | no-open-license-asserted | dataR GmbH | 2026-07-17 | 2026-09-09T11:52:14.991Z | d05d5a0ae9553afffaf723bb0448b832bf1a614fba9f7d412b82ed38ac027836 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1fdde38e-79d4-5d65-83e5-f686e75392a1.json | https://web.archive.org/web/20260909115214/https://www.datar.de/zwei-neue-kollegen-ein-gemeinsamer-start/
1ff2edcd-d460-5832-b947-1bdd6e7b5409 | ["context:geometry_identity","context:site_distinctness"] | ["c1016e49-7b45-52ff-8938-0bd01e78a7ad"] | government_record | Public procurement notice binds new build to exact campus address | https://ted.europa.eu/en/notice/304486-2023/pdf | TED / DVZ M-V GmbH | europe_round5_dvz_schwerin | no-open-license-asserted | TED / DVZ M-V GmbH | 2023-05-22 | 2026-09-08T22:03:03Z | 28b38640a41e7deb29591a72dd7281728fd1b2c42ba9ba7c9309566704f99fb0 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/1ff2edcd-d460-5832-b947-1bdd6e7b5409.json | https://web.archive.org/web/20260908220303/https://ted.europa.eu/en/notice/304486-2023/pdf
20040910-3ae7-5291-981e-139492623469 | ["imported:record","metric:buildings","metric:land_area","metric:power_capacity","role:developer"] | ["cb66229f-70db-5cfc-95b3-f5a05a3e73bc"] | news | Kasi Set to Launch Hyperscale AI-ready Data Centres in Lagos | https://www.thisdaylive.com/2026/05/18/kasi-set-to-launch-hyperscale-ai-ready-data-centres-in-lagos/ | ThisDay | www.thisdaylive.com | source-terms-not-recorded | ThisDay | 2026-05-18 | 2026-10-09 | 5c737bbd4b4372234cb304c6f73b30616169f35a1e075b0d654c91d64c52e98e | day | source_record_projection | kasi-cloud-lekki | s2 | f28323f52114c0517e3c60722514b6397a3c39996bc56c6cdaaf9597fa545f91 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/20040910-3ae7-5291-981e-139492623469.json | https://web.archive.org/web/20261009/https://www.thisdaylive.com/2026/05/18/kasi-set-to-launch-hyperscale-ai-ready-data-centres-in-lagos/
2064a4dc-8fc1-50cb-a098-994f6139abe4 | ["context:site_distinctness","geometry"] | ["e56ff51f-930c-5c5b-bc82-7add264e576e"] | third_party_dataset | Named Elmina Google data-center Wikidata coordinate | https://www.wikidata.org/wiki/Special:EntityData/Q136745002.json | Wikidata contributors | asia_round30_google_elmina | CC0-1.0 | Wikidata contributors |  | 2026-09-09T11:48:57.869Z | 2b691341a52237a1ac222a854f383f3de68a7d2e5cf8dfa591b76a55824e147c | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2064a4dc-8fc1-50cb-a098-994f6139abe4.json | https://web.archive.org/web/20260909114857/https://www.wikidata.org/wiki/Special:EntityData/Q136745002.json
206aff59-d746-56e5-af7e-4ce594a6af30 | ["imported:geometry","imported:record","metric:power_capacity","milestone:site_acquired","role:developer","role:utility"] | ["9002afae-5b81-5c8c-a6f9-4504c91e8624"] | utility_disclosure | MLGW update regarding utility support for xAI | https://www.mlgw.com/images/content/files/pdf/new/5-5-25%20xAI%20Update.pdf | Memphis Light, Gas and Water | www.mlgw.com | source-terms-not-recorded | Memphis Light, Gas and Water | 2025-05-05 | 2026-10-09 | 03d7778bdef17b1605ed72bc8f6e0c28a4478255275c6b4aab50a35d8092cb03 | day | source_record_projection | xai-colossus-2-memphis | s2 | a96b3341db0b72f4eeb487d50474903219c98fa2d20b32ec4e3af47c0c0a03d7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/206aff59-d746-56e5-af7e-4ce594a6af30.json | https://web.archive.org/web/20261009/https://www.mlgw.com/images/content/files/pdf/new/5-5-25%20xAI%20Update.pdf
20944103-50c0-59e2-8cdc-724e77c4b54c | ["imported:record","metric:investment","metric:power_capacity","milestone:announced","milestone:first_operational","power_source:geothermal","role:developer","role:operator"] | ["e3e31b3f-d0db-54ad-849f-126a4eae2868"] | news | Microsoft, UAE's G42 announce $1 billion geothermal data centre in Kenya | https://gulfnews.com/business/markets/microsoft-uaes-g42-announce-1-billion-geothermal-data-centre-in-kenya-1.102753045 | Gulf News | gulfnews.com | source-terms-not-recorded | Gulf News | 2024-05-22 | 2026-10-09 | 148d2cf13ca5baf892bf0584f5e7f401c51ec0f1b14ff2287a3a37d6188a2444 | day | source_record_projection | kenya-olkaria-geothermal-campus | s2 | 1ce7fa93c545d0cc6fd827a397f21b8b1298b234ee8c8c14335f2f9c379cf357 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/20944103-50c0-59e2-8cdc-724e77c4b54c.json | https://web.archive.org/web/20261009/https://gulfnews.com/business/markets/microsoft-uaes-g42-announce-1-billion-geothermal-data-centre-in-kenya-1.102753045
2099b779-9d76-5a88-a84f-0c239664a1e0 | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:investment","metric:jobs_construction","metric:land_area","milestone:construction_started","milestone:other","milestone:site_acquired","role:developer","role:government","role:utility"] | ["a1696719-0fe3-52ce-ad37-43e6d2215f4f"] | company_disclosure | Compass Kicks Off Development Of Its First Hyperscale Data Center Campus in Illinois | https://www.compassdatacenters.com/news/compass-kicks-off-development-of-its-first-hyperscale-campus-in-illinois/ | Compass Datacenters | www.compassdatacenters.com | source-terms-not-recorded | Compass Datacenters | 2024-06-13 | 2026-10-09 | f3f854ece2d2963217626165298266fe6fb1c4ca98f59956a216f82fb361e0bd | day | source_record_projection | compass-hoffman-estates | s1 | 919e4cab350dccba044b29137ae2d07da2c687d60d24fff80a509beb085c84d2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2099b779-9d76-5a88-a84f-0c239664a1e0.json | https://web.archive.org/web/20261009/https://www.compassdatacenters.com/news/compass-kicks-off-development-of-its-first-hyperscale-campus-in-illinois/
209c7f3e-18eb-533c-bb99-0b302fc22d7b | ["context:campus_address_identity","physical_status"] | ["ba5ddf33-10ec-5fb8-b880-98a04df096b8"] | company_disclosure | TRG Data Center Campus — HOU2 Brochure | https://www.trgdatacenters.com/wp-content/uploads/2026/01/TRG-Campus-HOU2-Brochure.pdf | TRG Datacenters | trg_datacenters_official_brochures | all-rights-reserved | TRG Datacenters |  | 2026-07-20T17:32:09Z | 5864de217fc954c10498ada7c05978ea634077106de20aae26c5bebb02ded605 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/209c7f3e-18eb-533c-bb99-0b302fc22d7b.json | https://web.archive.org/web/20260720173209/https://www.trgdatacenters.com/wp-content/uploads/2026/01/TRG-Campus-HOU2-Brochure.pdf
20bca9c3-7ad1-5ecb-b2f3-0f993680faf7 | ["imported:geometry","imported:record"] | ["8e72e640-c0e0-5e58-8a76-e53c011dcf92"] | other | Taylor, Texas | https://en.wikipedia.org/wiki/Taylor,_Texas | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | d2131b3910821a36e87fc608831a23a74c8310d1cc10c597b4b09a23f77cfb9f | unknown | source_record_projection | powerhouse-big-watt-taylor | s4 | fdd4764a33b08456c9173f8afbfd7ea9a7fc8a466505b3f720f9157bcfcccc1c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/20bca9c3-7ad1-5ecb-b2f3-0f993680faf7.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Taylor,_Texas
20f56b6a-7a02-5d6a-8594-62c37963dc46 | ["context:site_distinctness","geometry"] | ["b4349487-1879-5b90-9064-d1b86cb49850"] | openstreetmap | OSM copyright and ODbL attribution policy | https://www.openstreetmap.org/copyright | OpenStreetMap Foundation | europe_round18_greenergy_huuru | no-open-license-asserted | OpenStreetMap Foundation |  | 2026-09-09T04:58:22.794Z | 97c8da4341cb2ae34e913cb3c483c16d028996d3c0f65db957f0a46576a0c20d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/20f56b6a-7a02-5d6a-8594-62c37963dc46.json | https://web.archive.org/web/20260909045822/https://www.openstreetmap.org/copyright
20fee728-51c4-598d-b3e8-3cf49887dbe3 | ["imported:geometry","imported:record","metric:buildings","metric:floor_area","metric:investment","metric:land_area","milestone:announced","milestone:site_acquired","role:developer","role:government","role:owner"] | ["96848e3f-da64-53c8-be33-bf5c9cd2109a"] | news | Microsoft wants to build 15 more data centers in Mount Pleasant | https://www.wpr.org/news/microsoft-15-more-data-centers-mount-pleasant | Wisconsin Public Radio | www.wpr.org | source-terms-not-recorded | Wisconsin Public Radio | 2026-01-20 | 2026-10-09 | f5c07ee2d16d30d338ec6b0749836f4293ad6b42aa12d1c2039d40ab6aa1c402 | day | source_record_projection | microsoft-mount-pleasant-international-drive | s1 | 2fc9140e0cc603e7e8d9d9b804a94e384834e7381c41e9a315d5d9adc4fd1354 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/20fee728-51c4-598d-b3e8-3cf49887dbe3.json | https://web.archive.org/web/20261009/https://www.wpr.org/news/microsoft-15-more-data-centers-mount-pleasant
2143d0c4-d059-55ca-8019-5785af3e2ed2 | ["physical_status"] | ["6b62c459-dc75-5f31-87d4-d6dbf47de8b0"] | company_disclosure | Yesterday, EdgeCore celebrated the topping out of our AS02 data center in Ashburn, VA! | https://www.linkedin.com/posts/edgecore-digital-infrastructure_yesterday-edgecore-celebrated-the-topping-activity-7478135212778938368-t979 | EdgeCore Digital Infrastructure | edgecore_digital_infrastructure_linkedin | all-rights-reserved | EdgeCore Digital Infrastructure via LinkedIn | 2026-07-01T17:19:31.744Z | 2026-07-20T06:04:09Z | e2e7be3885f8fb982770cc0655622db43906982977de0f4af519f1495f9407cf | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2143d0c4-d059-55ca-8019-5785af3e2ed2.json | https://web.archive.org/web/20260720060409/https://www.linkedin.com/posts/edgecore-digital-infrastructure_yesterday-edgecore-celebrated-the-topping-activity-7478135212778938368-t979
2157a790-74df-5026-b2b6-58b1bb82519d | ["geometry"] | ["08d881e7-8a1c-50da-81a5-d2ef49f22a7a"] | government_cadastral_open_data | Cadastre Etalab parcel 91661000AP0008 | https://cadastre.data.gouv.fr/data/etalab-cadastre/latest/geojson/communes/91/91661/cadastre-91661-parcelles.json.gz | Direction générale des Finances publiques (DGFiP) / data.gouv.fr | etalab_dgfip_cadastre_geojson | etalab-2.0 | Direction générale des Finances publiques (DGFiP), Cadastre Etalab, millésime 1 June 2026 |  | 2026-08-20T21:44:03Z | f779721f25089d9e94057a3cb6094542ac97eb88a49cb9566bb3e28a2c94462a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2157a790-74df-5026-b2b6-58b1bb82519d.json | https://web.archive.org/web/20260820214403/https://cadastre.data.gouv.fr/data/etalab-cadastre/latest/geojson/communes/91/91661/cadastre-91661-parcelles.json.gz
2180537b-28c6-58b2-828b-653522117316 | ["imported:geometry","imported:record","metric:accelerators","metric:investment","metric:land_area","metric:power_capacity","milestone:announced","milestone:construction_started","power_source:other","power_source:solar","role:developer","role:operator"] | ["8f5c2434-0b2d-547e-ac2c-e25ddeefe1b7"] | trade_press | Schwarz Digits investiert 11 Milliarden Euro in digitale Souveränität | https://www.startbase.com/news/schwarz-digits-investiert-11-milliarden-euro-in-digitale-souveraenitaet/ | Startbase | www.startbase.com | source-terms-not-recorded | Startbase | 2025-11-18 | 2026-10-09 | 149b5f0563210980f858b0885e6d51849f161fbb395b714158c42d3a56535233 | day | source_record_projection | schwarz-digits-luebbenau | s2 | 9de167e8b0193e174395c2d0ff0f822919f334b7d7d9e2bc4b4bb25ec6ea9ab6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2180537b-28c6-58b2-828b-653522117316.json | https://web.archive.org/web/20261009/https://www.startbase.com/news/schwarz-digits-investiert-11-milliarden-euro-in-digitale-souveraenitaet/
2184bacc-e338-5f73-bb78-327e08fc392a | ["geometry"] | ["2cac8eb7-dff6-50bc-be49-b45f6e353982"] | company_disclosure | Ascenty Campus Vinhedo factsheet | https://ascenty.com/wp-content/uploads/2025/02/EN-Campus-Vinhedo_compressed.pdf | Ascenty | ascenty_campus_factsheets | all-rights-reserved-fact-extraction-only | Ascenty |  | 2026-09-07T02:50:21Z | c30210635d897e4545605e8f035a1678a7e0449d950f206fd4f27cb782c66e3a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2184bacc-e338-5f73-bb78-327e08fc392a.json | https://web.archive.org/web/20260907025021/https://ascenty.com/wp-content/uploads/2025/02/EN-Campus-Vinhedo_compressed.pdf
21a7143e-0bd4-5c77-9527-9029d461b655 | ["context:site_distinctness","geometry"] | ["e56ff51f-930c-5c5b-bc82-7add264e576e"] | third_party_dataset | Wikidata structured-data reuse license | https://www.wikidata.org/wiki/Wikidata:Data_access | Wikidata contributors | asia_round30_google_elmina | CC-BY-SA-4.0 | Wikidata contributors |  | 2026-09-09T11:49:35.262Z | 216df4a86930e79921bac342e55a07cf5b5d6ed53d52bc7dcb8766037fb3b947 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/21a7143e-0bd4-5c77-9527-9029d461b655.json | https://web.archive.org/web/20260909114935/https://www.wikidata.org/wiki/Wikidata:Data_access
21aa3998-cc7d-5a18-be05-a691da505426 | ["imported:record","milestone:other","power_source:wind"] | ["632aad8a-8c12-5a02-bd17-1138e6b03b6c"] | analyst_report | OpenAI Stargate: where the US sites stand | https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand | Epoch AI | epoch.ai | source-terms-not-recorded | Epoch AI | 2026-04-17 | 2026-10-09 | 1d7f94716c08389e4419997f927952fbdf1a3fecb3b0d5b39c4c01ca2fdda8bc | day | source_record_projection | openai-stargate-abilene | s5 | 066c9529d28eb79b7fc21ed2ed0dd80e325c61e382e4ef4017df6b302effa713 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/21aa3998-cc7d-5a18-be05-a691da505426.json | https://web.archive.org/web/20261009/https://epoch.ai/blog/openai-stargate-where-the-us-sites-stand
21c517a3-29b5-5a54-afef-3d0dbc922188 | ["context:geometry_identity","context:site_distinctness"] | ["d6a6d399-4580-54f8-80de-1dc0854e4699"] | government_record | Project Mila zoning certificate: applicant, parcel and street | https://ci.trenton.oh.us/DocumentCenter/View/2388 | City of Trenton, Ohio | root_round32_trenton | no-open-license-asserted | City of Trenton, Ohio | 2025-12-16 | 2026-09-09T23:55:46.248Z | 7d5243ddb8575106bcfc5bbfce9d1d6e5c4db62fac171167965e57984320ffa6 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/21c517a3-29b5-5a54-afef-3d0dbc922188.json | https://web.archive.org/web/20260909235546/https://ci.trenton.oh.us/DocumentCenter/View/2388
21e4e740-9c6e-5115-996c-3aa378a2f590 | ["context:site_distinctness","geometry"] | ["8715738f-39ac-5058-a01a-b62758b49831","e39b5191-4a78-5781-8944-24efaf944aa9"] | government_record | Vicmap Address layer: point schema and storage spatial reference | https://services-ap1.arcgis.com/P744lA0wf4LlBZ84/arcgis/rest/services/Vicmap_Address/FeatureServer/0?f=pjson | Victoria Department of Transport and Planning / Vicmap | vicmap_official_address_service | CC-BY-4.0 | © State of Victoria, Department of Transport and Planning, Vicmap |  | 2026-09-08T21:07:49Z | 95dec67863ee5c5ecb00924e1f74725efc226c9fd3b3ff7aa5eaf0560fc04afa | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/21e4e740-9c6e-5115-996c-3aa378a2f590.json | https://web.archive.org/web/20260908210749/https://services-ap1.arcgis.com/P744lA0wf4LlBZ84/arcgis/rest/services/Vicmap_Address/FeatureServer/0?f=pjson
21e72855-0ef7-570f-85cd-49291f6c0f6d | ["context:geometry_identity","context:site_distinctness","geometry"] | ["5443b4c1-09dc-5f14-a9a3-ec32c05602fb"] | openstreetmap | OSM exact-address result: dataR construction-site node | https://nominatim.openstreetmap.org/search?q=Kellerstra%C3%9Fe%2068%2C%2025462%20Rellingen&format=jsonv2&polygon_geojson=1&addressdetails=1&extratags=1 | OpenStreetMap contributors via Nominatim | europe_round30_datar_rellingen | ODbL-1.0 | OpenStreetMap contributors via Nominatim |  | 2026-09-09T11:56:45.444Z | f70278817432e332fb57c6b14737111c9f4940c2563879f68cfcfc2c5a2d0070 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/21e72855-0ef7-570f-85cd-49291f6c0f6d.json | https://web.archive.org/web/20260909115645/https://nominatim.openstreetmap.org/search?q=Kellerstra%C3%9Fe%2068%2C%2025462%20Rellingen&format=jsonv2&polygon_geojson=1&addressdetails=1&extratags=1
21f09e98-2096-55c8-a0a7-41be03842204 | ["physical_status"] | ["c71872a1-fc95-5d5b-8ee8-6b5082e974df"] | company_disclosure | Horizontal works begin on Datagrid's AI data centre campus in Makarewa | https://www.datagrid.nz/pr1-rc/horizontal-works-begin-on-datagrids-ai-data-centre-campus-in-makarewa | Datagrid New Zealand | datagrid_new_zealand_project_updates | all-rights-reserved | Datagrid New Zealand | 2026-08-19T16:07:34+12:00 | 2026-09-06T13:58:47Z | 38a918e1f7afb8c263364efa16e4b1845a59fdb2668e90e462666abb42723500 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/21f09e98-2096-55c8-a0a7-41be03842204.json | https://web.archive.org/web/20260906135847/https://www.datagrid.nz/pr1-rc/horizontal-works-begin-on-datagrids-ai-data-centre-campus-in-makarewa
21fc49b4-de9b-50a1-9909-b72c6655ad85 | ["imported:record","metric:land_area","metric:power_capacity","role:developer"] | ["ec871425-75fd-5ee1-9a6f-0e901b2f5837"] | company_disclosure | JHB2 Johor Bahru | https://airtrunk.com/data-centres/jhb2/ | AirTrunk | airtrunk.com | source-terms-not-recorded | AirTrunk |  | 2026-10-09 | bca85cff43f66fdd23a25abe92d5dc904e751f82b7e0623cc2c5c7ccf6be2421 | unknown | source_record_projection | airtrunk-jhb2-iskandar-puteri | s2 | 05d8cffa147ddb49bdcc4de12a460863f46b072f4ffe4dec45ae38c08852f466 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/21fc49b4-de9b-50a1-9909-b72c6655ad85.json | https://web.archive.org/web/20261009/https://airtrunk.com/data-centres/jhb2/
224ed1fd-1f35-59ea-a767-96481a580872 | ["imported:record","metric:buildings","milestone:zoning_approved","role:government"] | ["7c5eed16-f5f1-515a-b9ee-b7c30754fc10"] | news | Mount Pleasant village board approves Microsoft data center expansion | https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval | Spectrum News 1 | spectrumnews1.com | source-terms-not-recorded | Spectrum News 1 | 2026-01-27 | 2026-10-09 | 2796e50595c810e50f729d1f609429cfbfe70a8a7b8efdba970ca2072c305071 | day | source_record_projection | microsoft-mount-pleasant-durand-avenue | s4 | d8ced53f6564dffee42db2b1d9fcde39cfad69294d3e5cab7cc9b1a817f79650 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/224ed1fd-1f35-59ea-a767-96481a580872.json | https://web.archive.org/web/20261009/https://spectrumnews1.com/wi/milwaukee/news/2026/01/27/mount-pleasant--microsoft--data-center-expansion--approval
226ef5c8-b1ef-5507-b15d-bafaf52315fd | ["context:geometry_identity","context:site_distinctness"] | ["d2e988cd-e878-5061-817e-0c1cda87f372"] | government_record | Danish environmental register identifies Bulk DK01 at its campus address | https://dma.mst.dk/vis-virksomhed/4199d44b-5404-4907-ad78-799090d60e16 | Miljøstyrelsen / Digital MiljøAdministration | europe_round22_bulk | no-open-license-asserted | Miljøstyrelsen / Digital MiljøAdministration |  | 2026-09-09T07:11:25Z | 7d86271d86eaf41f5d45b144083d6f80a7d49d05c9a15cd79486d8fd2411317a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/226ef5c8-b1ef-5507-b15d-bafaf52315fd.json | https://web.archive.org/web/20260909071125/https://dma.mst.dk/vis-virksomhed/4199d44b-5404-4907-ad78-799090d60e16
22c3b82d-1a57-5d67-aecc-52234ce7a7de | ["imported:geometry","imported:record","imported:status","milestone:first_operational","milestone:fully_operational","milestone:other","role:developer","role:tenant"] | ["8fc14c03-d70a-5634-81e4-883a2fd6eec9"] | company_disclosure | Cipher Digital Expands Barber Lake Lease Term to 20 Years, Increasing Revenue to Over $9 Billion (Form 8-K Exhibit 99.1) | https://www.sec.gov/Archives/edgar/data/1819989/000181998926000043/barberlakeleaseamendmentpr.htm | Cipher Digital | www.sec.gov | source-terms-not-recorded | Cipher Digital | 2026-09-25 | 2026-10-09 | c99d88618bc49c3da0069d67f890fd35193c3b8664ba650c2aeffd25f46aa2f9 | day | source_record_projection | cipher-barber-lake | s4 | d3ec6727593ff92e05524c4162ede0f1fc5ba4db9109696c94c4021d888ba151 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/22c3b82d-1a57-5d67-aecc-52234ce7a7de.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1819989/000181998926000043/barberlakeleaseamendmentpr.htm
22d00a3f-a2d7-575f-aef5-cf987cce3021 | ["imported:record","imported:status","milestone:other","role:developer"] | ["ec871425-75fd-5ee1-9a6f-0e901b2f5837"] | company_disclosure | AirTrunk secures US$2.325b green financing to support sustainable digital infrastructure growth in Malaysia | https://airtrunk.com/airtrunk-secures-us2-325b-green-financing-to-support-sustainable-digital-infrastructure-growth-in-malaysia/ | AirTrunk | airtrunk.com | source-terms-not-recorded | AirTrunk | 2026-07-29 | 2026-10-09 | 0a9149e404a9e4e44dbf0eb1e5340f6e27579de637e3fc4e16eccbdf66433fd5 | day | source_record_projection | airtrunk-jhb2-iskandar-puteri | s4 | 05d8cffa147ddb49bdcc4de12a460863f46b072f4ffe4dec45ae38c08852f466 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/22d00a3f-a2d7-575f-aef5-cf987cce3021.json | https://web.archive.org/web/20261009/https://airtrunk.com/airtrunk-secures-us2-325b-green-financing-to-support-sustainable-digital-infrastructure-growth-in-malaysia/
22df2f28-4402-57a9-9de9-45919481329d | ["context:site_distinctness","geometry"] | ["b91d994d-0f59-5ed8-ad74-20e4ba2251f3"] | openstreetmap | OpenStreetMap data licence and attribution requirements | https://www.openstreetmap.org/copyright | OpenStreetMap Foundation | americas_round21_procergs | no-open-license-asserted | OpenStreetMap Foundation |  | 2026-09-09T06:36:58Z | 8b25e999a8c6feb9cedbac09ede068b55cf703ed4b9de8afa54e462f315ce2a3 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/22df2f28-4402-57a9-9de9-45919481329d.json | https://web.archive.org/web/20260909063658/https://www.openstreetmap.org/copyright
22e3e100-6fac-50ab-ac5c-44d1960cfbf1 | ["imported:geometry","imported:record","metric:land_area","metric:power_capacity","milestone:site_acquired","role:developer","role:owner"] | ["688df4a2-dc56-5cde-901a-87c87a08137e"] | company_disclosure | NEXTDC Announces Massive Expansion Plans with Acquisition of S7 Data Centre Site in Sydney | https://www.nextdc.com/news/nextdc-acquires-new-sydney-data-centre-s7 | NEXTDC | www.nextdc.com | source-terms-not-recorded | NEXTDC | 2024-10-17 | 2026-10-09 | 0e600b1765421eb9cf36b2a978312fda75124f75a23e88bd575c4ae5a1cc4925 | day | source_record_projection | nextdc-s7-eastern-creek | s1 | 9785caf78f3771cd71892e9d6971b50ee7bad038bc1e48b3298d25779be39e15 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/22e3e100-6fac-50ab-ac5c-44d1960cfbf1.json | https://web.archive.org/web/20261009/https://www.nextdc.com/news/nextdc-acquires-new-sydney-data-centre-s7
22eac0e1-71fa-59dd-a6d7-4378a663ab9d | ["context:site_distinctness","geometry"] | ["8a5fbd17-48b6-5484-8c37-ce406068bf3e"] | openstreetmap | NEXTDC S3: exact-address community representative point | https://nominatim.openstreetmap.org/search?q=NEXTDC%20S3&format=jsonv2&polygon_geojson=1 | OpenStreetMap contributors / Nominatim | openstreetmap_nominatim | ODbL-1.0 | © OpenStreetMap contributors |  | 2026-09-08T20:48:13Z | ea9cc22642809ccd97ee33ab1519678cf13ec4fbfc5570cc5d256eec0b17b358 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/22eac0e1-71fa-59dd-a6d7-4378a663ab9d.json | https://web.archive.org/web/20260908204813/https://nominatim.openstreetmap.org/search?q=NEXTDC%20S3&format=jsonv2&polygon_geojson=1
22f02ca2-f634-5d40-8cff-d36809be3432 | ["context:site_distinctness","geometry"] | ["f0e92e2e-e082-5b7f-9486-fd744b5b68e6"] | government_record | REFRAME manual defines exact LV95 input and longitude/latitude output | https://www.swisstopo.admin.ch/dam/fr/sd-web/3xmcWvfxgG6X/Report16-03.pdf | Federal Office of Topography swisstopo | europe_mena_round9_expansion_asia | swisstopo-report-A-public-domain | © swisstopo |  | 2026-09-08T23:20:09.277Z | 3caf0be28399229b6d06988eb9150d07c7ad140d0459dbd6494a05ecaa1ca89d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/22f02ca2-f634-5d40-8cff-d36809be3432.json | https://web.archive.org/web/20260908232009/https://www.swisstopo.admin.ch/dam/fr/sd-web/3xmcWvfxgG6X/Report16-03.pdf
2330aefe-fa95-51f7-a1f8-cc6eb56e317a | ["context:geometry_identity","context:site_distinctness"] | ["709cd37b-7f3a-5313-b3e2-a18ddc0885ec"] | company_disclosure | Operator identifies Pecos as Cottonwood 1 and 2 on FM2119 | https://corescientific.com/high-density-data-centers/pecos-tx/ | Core Scientific, Inc. | pecos_round15_primary_review | all-rights-reserved | Core Scientific, Inc. |  | 2026-09-09T03:10:48.300Z | 6738cc95622c4668a4bbd56bca8c18c665f702a98e3a8154e413fa38fcc564a1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2330aefe-fa95-51f7-a1f8-cc6eb56e317a.json | https://web.archive.org/web/20260909031048/https://corescientific.com/high-density-data-centers/pecos-tx/
23365ee9-f538-56fe-acec-e41f43182ded | ["geometry"] | ["fe6f26cf-4be9-51a3-857e-fca7ee21726b"] | government_record | NLS INSPIRE Cadastral Parcels feature 205-7-4-1 | https://inspire-wfs.maanmittauslaitos.fi/inspire-wfs/cp/ows?service=WFS&version=2.0.0&request=GetFeature&typeNames=cp%3ACadastralParcel&outputFormat=application%2Fjson&CQL_FILTER=nationalCadastralReference%3D%2720500700040001%27 | National Land Survey of Finland (NLS) | nls_inspire_cadastral_parcels_wfs | CC-BY-4.0 | Contains data from the National Land Survey of Finland INSPIRE Cadastral Parcels (CP) WFS, licensed under the National Land Survey open data Attribution CC 4.0 licence; retrieved 2026-08-23. |  | 2026-08-23T22:43:14.877Z | 2f83cf299f5258c92fd4c61306c5a5aed91bd20a56c48dae51b94c99714164af | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/23365ee9-f538-56fe-acec-e41f43182ded.json | https://web.archive.org/web/20260823224314/https://inspire-wfs.maanmittauslaitos.fi/inspire-wfs/cp/ows?service=WFS&version=2.0.0&request=GetFeature&typeNames=cp%3ACadastralParcel&outputFormat=application%2Fjson&CQL_FILTER=nationalCadastralReference%3D%2720500700040001%27
23498602-d954-533f-bdcc-e9bb8a865749 | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:power_capacity","milestone:announced","milestone:first_operational","power_source:grid","role:developer"] | ["511bfd88-0355-5080-b5ef-5a39ec51dfd8"] | company_disclosure | 国内最大級、千葉県印西・白井エリアで約250メガワット（MW）のデータセンターキャンパス開発を始動 | https://www.nttdata.com/global/ja/news/release/2026/041700/ | NTT DATA Group / NTT Global Data Centers | www.nttdata.com | source-terms-not-recorded | NTT DATA Group / NTT Global Data Centers | 2026-04-17 | 2026-10-09 | f8c174680a9236dfed387b898946d8dbb2320a57604c08ccef4707c51b1c3f7f | day | source_record_projection | ntt-gdc-tokyo-tky12-shiroi | s1 | c52af1d01450703ae6fda9d5f4203a03ded8ba51f550658201e77e57c9ca559c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/23498602-d954-533f-bdcc-e9bb8a865749.json | https://web.archive.org/web/20261009/https://www.nttdata.com/global/ja/news/release/2026/041700/
235d8722-38d3-5f6d-849c-675e6c0dea42 | ["imported:record","metric:buildings","metric:investment","metric:land_area","role:builder","role:developer"] | ["09904943-69d4-51d7-aef7-4ff880e47332"] | trade_press | Google linked to US$10bn data centre campus in US | https://www.constructionbriefing.com/news/google-linked-to-us10bn-data-centre-campus-in-us/8062290.article | Construction Briefing | www.constructionbriefing.com | source-terms-not-recorded | Construction Briefing | 2025-05-30 | 2026-10-09 | b92722a345400782dfe2e83f3f72df01b0fb4de06024acfc42edd226bcd8d76e | day | source_record_projection | google-west-memphis-arkansas | s5 | affe666039075290c2511ab766a40b580f546f594dfcdc4b58bfb59341573b09 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/235d8722-38d3-5f6d-849c-675e6c0dea42.json | https://web.archive.org/web/20261009/https://www.constructionbriefing.com/news/google-linked-to-us10bn-data-centre-campus-in-us/8062290.article
237d639b-9ae2-5e9e-aaf1-bbc800f96253 | ["imported:geometry","imported:record","metric:investment","milestone:announced","role:developer"] | ["e56ff51f-930c-5c5b-bc82-7add264e576e"] | trade_press | Google to invest US$ 2 Billion to build its first DC and Cloud Region in Malaysia | https://w.media/google-to-invest-us-2-billion-to-build-its-first-dc-and-cloud-region-in-malaysia/ | W.Media | w.media | source-terms-not-recorded | W.Media | 2024-05-30 | 2026-10-09 | e1af947a1db3d2025bf0c97e3fc863898d5b01653f3dce9a2d164f85ab403e0a | day | source_record_projection | google-elmina-selangor | s1 | 96e91c84ac98c440c339a464d6075e40626a54ab6c3c3cc05212fbc2c8de6f84 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/237d639b-9ae2-5e9e-aaf1-bbc800f96253.json | https://web.archive.org/web/20261009/https://w.media/google-to-invest-us-2-billion-to-build-its-first-dc-and-cloud-region-in-malaysia/
23891a1e-e8d2-5b57-afb7-c97a6aa838d7 | ["imported:record","metric:investment","metric:land_area","metric:power_capacity","milestone:first_operational","role:developer","role:tenant"] | ["8f5c2434-0b2d-547e-ac2c-e25ddeefe1b7"] | trade_press | Lidl and Kaufland owner advances $12 billion data centre project amid EU AI infrastructure talks | https://thetechcapital.com/lidl-and-kaufland-owner-advances-12-billion-data-centre-project-amid-eu-ai-infrastructure-talks/ | The Tech Capital | thetechcapital.com | source-terms-not-recorded | The Tech Capital | 2026-01-12 | 2026-10-09 | acbfb1cf09c86aad5fb6780b8c1446092559866647145f30ab75590d0bd0556f | day | source_record_projection | schwarz-digits-luebbenau | s3 | 9de167e8b0193e174395c2d0ff0f822919f334b7d7d9e2bc4b4bb25ec6ea9ab6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/23891a1e-e8d2-5b57-afb7-c97a6aa838d7.json | https://web.archive.org/web/20261009/https://thetechcapital.com/lidl-and-kaufland-owner-advances-12-billion-data-centre-project-amid-eu-ai-infrastructure-talks/
23d44bfc-7613-5581-8585-2f23cd7c0f75 | ["imported:geometry","imported:record","metric:buildings","metric:investment","metric:jobs_construction","metric:power_capacity","milestone:construction_started","milestone:fully_operational","milestone:other","power_source:wind","role:developer","role:investor"] | ["632aad8a-8c12-5a02-bd17-1138e6b03b6c"] | company_disclosure | Crusoe, Blue Owl Capital and Primary Digital Infrastructure Enter Second Phase of $15 Billion Joint Venture | https://www.crusoe.ai/resources/newsroom/crusoe-blue-owl-capital-and-primary-digital-infrastructure-enter-joint-venture | Crusoe | www.crusoe.ai | source-terms-not-recorded | Crusoe | 2025-05-21 | 2026-10-09 | 8c251fe134b7418f25079e2217cb13a273f19d5a6f1966cdcc22352a2a0e483b | day | source_record_projection | openai-stargate-abilene | s1 | 066c9529d28eb79b7fc21ed2ed0dd80e325c61e382e4ef4017df6b302effa713 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/23d44bfc-7613-5581-8585-2f23cd7c0f75.json | https://web.archive.org/web/20261009/https://www.crusoe.ai/resources/newsroom/crusoe-blue-owl-capital-and-primary-digital-infrastructure-enter-joint-venture
23d45bff-b0d4-5d24-8dfb-b83cb4977a49 | ["context:geometry_identity","context:site_distinctness"] | ["f8900f55-087d-5d51-aef2-820402bcbdc2"] | company_disclosure | AMS01 Goodman Mona Logistics Netherlands B.V. - project address | https://www.usgbc.org/projects/ams01-goodman-mona-logistics-netherlands-bv | U.S. Green Building Council | usgbc_public_project_records | all-rights-reserved | U.S. Green Building Council |  | 2026-09-08T19:25:38Z | 995128c382216f4648fe8242a251ad15eff7bdd9a95572d8530a811b9ab7fa8a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/23d45bff-b0d4-5d24-8dfb-b83cb4977a49.json | https://web.archive.org/web/20260908192538/https://www.usgbc.org/projects/ams01-goodman-mona-logistics-netherlands-bv
23df5ccc-860a-557c-a60c-11a7a4c08fea | ["imported:geometry","imported:record","imported:status","metric:investment","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:other","power_source:natural_gas_onsite","role:developer","role:government"] | ["c400f10b-b4a6-5824-987b-3ff8657fb0d3"] | trade_press | Houston-Area County Rejects Tax Break For $3.5B Data Center Project | https://www.bisnow.com/houston/news/data-center-development/houston-area-county-rejects-tax-abatement-for-35b-data-center-development-133616 | Bisnow | www.bisnow.com | source-terms-not-recorded | Bisnow | 2026-03-11 | 2026-10-09 | 85bc4afa057588f34a437ed57077a93e74f0dbe2cb853ca091e8d93e096adf9c | day | source_record_projection | nightpeak-old-ocean | s2 | 5878487ce27a64c97206ce1a137a67a4ba60cd6bf2884d1aa54a1f4fe3d80f15 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/23df5ccc-860a-557c-a60c-11a7a4c08fea.json | https://web.archive.org/web/20261009/https://www.bisnow.com/houston/news/data-center-development/houston-area-county-rejects-tax-abatement-for-35b-data-center-development-133616
23f9086f-59d8-5e91-ac49-a0f6ab331d31 | ["context:geometry_identity","context:site_distinctness"] | ["8715738f-39ac-5058-a01a-b62758b49831"] | company_disclosure | NEXTDC M4 announcement: exact 127 Todd Road campus identity | https://www.nextdc.com/news/nextdc-announces-2-billion-ai-factory-and-technology-campus-at-fishermans-bend | NEXTDC Limited | nextdc_official_campus_identity | all-rights-reserved | NEXTDC Limited | 2025-06-12 | 2026-09-08T21:01:51Z | f5fa90cc6d137d7db524c79ae61524491e78e3cde2ba6356e9232ce093527896 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/23f9086f-59d8-5e91-ac49-a0f6ab331d31.json | https://web.archive.org/web/20260908210151/https://www.nextdc.com/news/nextdc-announces-2-billion-ai-factory-and-technology-campus-at-fishermans-bend
240ff090-6815-5cab-942c-af184e725d45 | ["imported:record","imported:status","metric:buildings","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:first_operational","role:developer"] | ["a7a29c6e-70aa-5f7b-b172-d1abe208715e"] | trade_press | CloudHQ to Build Mexico's Largest Hyperscale Data Hub in Querétaro | https://www.telecomreviewamericas.com/articles/wholesale-and-capacity/cloudhq-to-build-mexicos-largest-hyperscale-data-hub-in-queretaro/ | Telecom Review Americas | www.telecomreviewamericas.com | source-terms-not-recorded | Telecom Review Americas | 2025-09-30 | 2026-10-09 | e61f9f53932f8cb683ec013ff8fff0a67d6b53ac57e489f429db681fde2f1c7b | day | source_record_projection | cloudhq-queretaro | s3 | e5fc1c4b95552e1f066ffad711ea763302ef3b9f31617b210adb0554fb9d29f9 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/240ff090-6815-5cab-942c-af184e725d45.json | https://web.archive.org/web/20261009/https://www.telecomreviewamericas.com/articles/wholesale-and-capacity/cloudhq-to-build-mexicos-largest-hyperscale-data-hub-in-queretaro/
242c3019-1f53-551c-a0be-de57b4e4352f | ["imported:geometry","imported:record","metric:buildings","metric:land_area","metric:power_capacity","milestone:construction_started","power_source:grid","role:developer","role:operator","role:owner"] | ["164033cb-411d-5ffb-ab5d-b04bdecfa1ac"] | company_disclosure | CDC Data Centres Breaks Ground on New State-of-the-Art Data Centre Development in Marsden Park Industrial Precinct | https://cdc.com/resources/news/cdc-data-centres-breaks-ground-on-new-state-of-the-art-data-centre-development-in-marsden-park-industrial-precinct/ | CDC Data Centres | cdc.com | source-terms-not-recorded | CDC Data Centres | 2024-10-25 | 2026-10-09 | 1b47260f3da54b9ec87a8cfb18e97d9ded2e844e1513ef6896cdff9a92e30bc0 | day | source_record_projection | cdc-marsden-park | s1 | 7f5328a6e8a50cf869cf98075451fd843a9f85bd3c5f6c8f2ec96b1a664b20b4 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/242c3019-1f53-551c-a0be-de57b4e4352f.json | https://web.archive.org/web/20261009/https://cdc.com/resources/news/cdc-data-centres-breaks-ground-on-new-state-of-the-art-data-centre-development-in-marsden-park-industrial-precinct/
2435d594-4bb5-5062-9ac2-4564e08dc119 | ["imported:record","imported:status","metric:investment","milestone:construction_started","milestone:other","role:developer","role:government"] | ["2a273a46-2f4f-5ccb-9d10-6f2bfeb5e5f5"] | news | Cerca de 6.000 millones invertidos en centros de datos en Aragón esperan en la rampa de salida para las obras | https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html | El Español | www.elespanol.com | source-terms-not-recorded | El Español | 2026-10-05 | 2026-10-09 | 2de00c1ea5531e9199d811695e6ab8022330e70d91351006d00418ded20b65e9 | day | source_record_projection | azora-tillion-villamayor-de-gallego | s3 | d1aa0d3a5fca4ebf39c3e2a7b90748b3b6d7ece4bb0331301d392f040c29ec3a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2435d594-4bb5-5062-9ac2-4564e08dc119.json | https://web.archive.org/web/20261009/https://www.elespanol.com/aragon/actualidad/20261005/cerca-millones-invertidos-centros-datos-aragon-esperan-rampa-salida-obras/1003744406849_0.html
24883aba-24d8-587f-b4e2-c84ea6bdd083 | ["imported:geometry","imported:record","metric:floor_area","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","milestone:announced","milestone:construction_started","role:developer","role:government"] | ["2fc433ea-05de-5b3a-b4a1-bd9d544f8ae3"] | news | Facebook parent company to invest $800 million in Central Texas | https://www.kwtx.com/2022/03/31/facebook-parent-company-invest-800-million-central-texas/ | KWTX | www.kwtx.com | source-terms-not-recorded | KWTX | 2022-03-31 | 2026-10-09 | 5c5e9e263727239e2efb8e18cd27874eaa4c3c35b3f3414f6679fdf294a5dc21 | day | source_record_projection | meta-temple-texas | s2 | 6558a5072429b8e64f5a5654423c0025443d77b5adf5c9f2228113f65f8fef5c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/24883aba-24d8-587f-b4e2-c84ea6bdd083.json | https://web.archive.org/web/20261009/https://www.kwtx.com/2022/03/31/facebook-parent-company-invest-800-million-central-texas/
24e8b46a-f7f4-57b5-a278-3a6cd588c244 | ["context:site_distinctness","geometry"] | ["cf028790-cea6-555d-a3bb-48e08ff78f3b"] | government_record | Census defines geocoder datum and address interpolation | https://www2.census.gov/geo/pdfs/maps-data/data/FAQ_for_Census_Bureau_Public_Geocoder.pdf | U.S. Census Bureau | americas_round31_cyrusone_aurora | no-open-license-asserted | U.S. Census Bureau |  | 2026-09-09T23:35:05.176Z | 13a8ca9f7395daf53e0c06344dd2f1ed28bc6806ab0625b3410eba7e280db169 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/24e8b46a-f7f4-57b5-a278-3a6cd588c244.json | https://web.archive.org/web/20260909233505/https://www2.census.gov/geo/pdfs/maps-data/data/FAQ_for_Census_Bureau_Public_Geocoder.pdf
2584dc11-92bc-5311-b669-832d0c1daec9 | ["imported:geometry","imported:record"] | ["b7744ad5-aa48-5977-a70e-3d6a588f468d"] | other | Boyce, Louisiana | https://en.wikipedia.org/wiki/Boyce,_Louisiana | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 05472822eeb801376179df807c703a196fe17061281bf8eb8823cb423c47a87e | unknown | source_record_projection | applied-digital-delta-forge-1 | s5 | 10214256785a9b6414201e99b67e33b4d86cc025f37ec2646022215dc0d7c5f7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2584dc11-92bc-5311-b669-832d0c1daec9.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Boyce,_Louisiana
25d019c0-b422-52a0-9fdc-f6d87e295150 | ["context:site_distinctness"] | ["5ace12f8-658e-5956-9173-d78e625d4df9"] | government_record | City legal-notice index dates the exact DataOne PDF | https://www.vinelandcity.org/legal-notices/ | City of Vineland | us_round23_dataone_vineland | no-open-license-asserted | City of Vineland | 2026-08-07 | 2026-09-09T07:47:37Z | 1c6b9cf088b844218693ad4883fcb4687af08e196af3007fe696c7af532643e3 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/25d019c0-b422-52a0-9fdc-f6d87e295150.json | https://web.archive.org/web/20260909074737/https://www.vinelandcity.org/legal-notices/
25d30d41-6ee8-521c-a8d5-5fc372370ebb | ["context:source_location_identity","physical_status"] | ["c794c146-24e6-5cb8-8cd9-a12a266bba83"] | company_disclosure | Digi Power X Provides Operations and Financial Update | https://thankful-miracle-1ed8bdfdaf.media.strapiapp.com/Digi_Power_X_Provides_Operations_and_Financial_Update_4a179c433b.pdf | Digi Power X Inc. | digipowerx_press_releases | all-rights-reserved | Digi Power X Inc. | 2026-07-07 | 2026-07-20T08:30:56Z | ebcddc3bc3e8d35325e56fe7b81803a90a3a69938d1451401051f8eea135f734 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/25d30d41-6ee8-521c-a8d5-5fc372370ebb.json | https://web.archive.org/web/20260720083056/https://thankful-miracle-1ed8bdfdaf.media.strapiapp.com/Digi_Power_X_Provides_Operations_and_Financial_Update_4a179c433b.pdf
25d95be5-0754-59ec-a7bb-b8a2d6c1c330 | ["imported:geometry","imported:record","imported:status","milestone:other","power_source:natural_gas_onsite","role:hardware_supplier"] | ["94562977-e3af-5f59-bee1-896ee8db20f6"] | company_disclosure | First Power Generation Assets Arrive at Project Matador | https://fermiamerica.com/first-power-generation-assets-arrive-at-project-matador/ | Fermi America | fermiamerica.com | source-terms-not-recorded | Fermi America | 2026-09-18 | 2026-10-09 | 531253599adfcaf9e8335b2e34e47168751a78b9c94428cef5e61305aa12f7db | day | source_record_projection | fermi-america-hypergrid-amarillo | s3 | 2784250e9a1dd9f679638c54fd185e63aec4254906feee0f129ab485698ebe1c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/25d95be5-0754-59ec-a7bb-b8a2d6c1c330.json | https://web.archive.org/web/20261009/https://fermiamerica.com/first-power-generation-assets-arrive-at-project-matador/
25e20e63-5e98-5bda-9722-480996fbd354 | ["imported:geometry","imported:record","metric:floor_area","milestone:other","role:government"] | ["7c43c342-562c-5d46-b793-39a4dd2a8cc0"] | news | Fayetteville approves development agreement for 612-acre QTS Data Center on Hwy. 54 West | https://thecitizen.com/?p=109827 | The Citizen (Fayette County) | thecitizen.com | source-terms-not-recorded | The Citizen (Fayette County) | 2023-06-19 | 2026-10-09 | cb98cb8797cacb50c752e533961414a5870c7429fb66e32f168b001c603be722 | day | source_record_projection | qts-fayetteville-georgia | s4 | ea566795916692c88310a339616e1dea6edc33a46d1339e5b0ef908029aae32f | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/25e20e63-5e98-5bda-9722-480996fbd354.json | https://web.archive.org/web/20261009/https://thecitizen.com/?p=109827
25e8d6e9-275e-55fb-ad03-97523dd3b542 | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:other","power_source:battery_storage","power_source:grid","power_source:solar","power_source:wind","role:developer","role:government","role:utility"] | ["a8c0727c-ed59-5641-8856-e4eac08a5cf0"] | news | Vantage levantará un centro de datos de hiperescala en Aragón con 3.200 millones de inversión | https://www.libertaddigital.com/espana/2025-09-12/azcon-anuncia-una-inversion-de-3-200-millones-para-un-centro-de-datos-de-vantage-en-aragon-7294927/ | Libertad Digital | www.libertaddigital.com | source-terms-not-recorded | Libertad Digital | 2025-09-12 | 2026-10-09 | 4eeea91a96c1d858a7d7d00670479c9887541a5469b5a0c6b8c3e3c6e3a1c4c2 | day | source_record_projection | vantage-villanueva-de-gallego | s2 | 0e2845a71c98adb1675b74a6066bea2e001875aea020628c790e01910e33e9b7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/25e8d6e9-275e-55fb-ad03-97523dd3b542.json | https://web.archive.org/web/20261009/https://www.libertaddigital.com/espana/2025-09-12/azcon-anuncia-una-inversion-de-3-200-millones-para-un-centro-de-datos-de-vantage-en-aragon-7294927/
25f87a88-356b-5d9a-9919-130dc6c119b6 | ["context:identity"] | ["c2ec8d08-3436-5bbc-af4e-4eb553297fe2"] | government_record | Official masterportal registers EPSG25832 and named projection definitions. | https://geoportal.frankfurt.de/karte/config.js | Stadt Frankfurt am Main | frankfurt_municipal_geoportal | public-record-source-terms | Stadt Frankfurt am Main |  | 2026-10-13T13:49:37.664311+00:00 | b1e44812e388cd6ce7da6a4179b9b50dd2562f74328465a0dc03b371d6b4e7cc | unknown | sha256_exact_content_decoded_response_bytes |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/25f87a88-356b-5d9a-9919-130dc6c119b6.json | https://web.archive.org/web/20261013134937/https://geoportal.frankfurt.de/karte/config.js
26ab81d6-a6c2-5f14-983f-4a68a221c851 | ["imported:record","imported:status","metric:buildings","metric:investment","metric:power_capacity","milestone:other","power_source:grid","role:investor"] | ["f0afff75-0b96-5e18-a8f9-08ac9a4b99ff"] | trade_press | Data4 confirms €5bn plan for 700MW AI data center in northern France | https://bebeez.eu/2026/06/15/data4-confirms-e5bn-plan-for-700mw-ai-data-center-in-northern-france/ | BeBeez International (DCD) | bebeez.eu | source-terms-not-recorded | BeBeez International (DCD) | 2026-06-15 | 2026-10-09 | 835f1969e553fb1b7fd4e82fbab201e66158d13b157e78065932cee623701df4 | day | source_record_projection | data4-escaudain | s3 | c94ceead57ad73e1cfe6ed4b4d77187261dfce5aff87696917bc35837f0fdea4 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/26ab81d6-a6c2-5f14-983f-4a68a221c851.json | https://web.archive.org/web/20261009/https://bebeez.eu/2026/06/15/data4-confirms-e5bn-plan-for-700mw-ai-data-center-in-northern-france/
26af7c65-ad08-51a8-89d1-19668ed0a6a3 | ["context:site_distinctness"] | ["5ace12f8-658e-5956-9173-d78e625d4df9"] | government_record | Vineland 2026-08-10 equipment-specific stop-construction order | https://woodburywarbler.com/wp-content/uploads/2026/08/2026.0810-Stop-Work-Order-Bloom-Energy-Cells-826x1024.jpg | City of Vineland construction official; scan hosted by The Woodbury Warbler | us_round23_dataone_vineland | no-open-license-asserted | City of Vineland construction official; scan hosted by The Woodbury Warbler | 2026-08-10 | 2026-09-09T07:50:41Z | 10c5d1a4d5e9bba0cad84145499f3d5a31b1fb17f9d38a0de00064d6220b4135 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/26af7c65-ad08-51a8-89d1-19668ed0a6a3.json | https://web.archive.org/web/20260909075041/https://woodburywarbler.com/wp-content/uploads/2026/08/2026.0810-Stop-Work-Order-Bloom-Energy-Cells-826x1024.jpg
26d88bed-8fc2-5e71-8683-68d3b9bb1ee3 | ["geometry"] | ["94c0f50d-843b-57cd-bfcd-4bd3b7b9d9f0"] | government_record | APA AIA 3633 drawing 22045-EP-AMB-DES-001-01-A | https://siaia.apambiente.pt/AIADOC/AIA3633/22045-ep-amb-des-001-01-a202382212930.pdf | Agência Portuguesa do Ambiente (APA) | apa_siaia_aia_3633_project_drawings | rights-status-uncertain-fact-extraction-only | Agência Portuguesa do Ambiente; Start Campus / TPF project drawing | 2023-06 | 2026-08-23 | db4ba67fd29a7ef8037d3a53e13940e772b58867e1ebf212dd27b4773f09adb6 | month | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/26d88bed-8fc2-5e71-8683-68d3b9bb1ee3.json | https://web.archive.org/web/20260823/https://siaia.apambiente.pt/AIADOC/AIA3633/22045-ep-amb-des-001-01-a202382212930.pdf
26e820ae-0d05-593e-9d5f-794caa26f215 | ["imported:geometry","imported:record","metric:floor_area","metric:investment","metric:jobs_construction","milestone:announced","role:builder","role:developer"] | ["c0f8dadf-2c3d-5176-b649-85363c06e1fa"] | company_disclosure | Hello, Montgomery! | https://datacenters.atmeta.com/2024/05/hello-montgomery/ | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms | 2024-05-02 | 2026-10-09 | 62a171c03b4d75226937b310d4fe665fd9e33d7d476a86a8d1775234f612b9bc | day | source_record_projection | meta-montgomery | s1 | ca356acb7d71bb8501b5d2bfa601c1dcc4bce58c72de4e9ab7349dd3af9a18e1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/26e820ae-0d05-593e-9d5f-794caa26f215.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/2024/05/hello-montgomery/
2705a04d-8e88-5b06-9cd5-30fc83cc4328 | ["context:site_distinctness","geometry"] | ["b9ccc1e7-c2da-5822-82bc-b20be7d43dfe"] | government_record | City exact Pajarilanväylä 24 address result | https://kartta.lappeenranta.fi/IMS/fi/Search?Op=all&Name=Pajarilanv%C3%A4yl%C3%A4%2024 | City of Lappeenranta via Trimble IMS | europe_round5_exact_locators | no-open-license-asserted | City of Lappeenranta via Trimble IMS |  | 2026-09-08T21:45:53Z | 0308eb155e73b832cf05b377844d29d518cf8f4cd33fcf2f465bbb5880d525d4 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2705a04d-8e88-5b06-9cd5-30fc83cc4328.json | https://web.archive.org/web/20260908214553/https://kartta.lappeenranta.fi/IMS/fi/Search?Op=all&Name=Pajarilanv%C3%A4yl%C3%A4%2024
271d4ec7-9ffe-5ee5-9b50-fbf025df7212 | ["context:geometry_identity","context:site_distinctness"] | ["b4349487-1879-5b90-9064-d1b86cb49850"] | company_disclosure | Caverion Finnish parallel release retains narrower employment wording | https://www.caverion.fi/media/tiedotteet/2026/caverion-toteuttaa-paaurakoitsijana-50-miljoonan-euron-datakeskushankkeen-mcf-group-estonialle-baltian-suurin-korkean-turvallisuusstandardin-datakeskus-laajenee/ | Caverion | europe_round18_greenergy_huuru | no-open-license-asserted | Caverion | 2026-07-31 | 2026-09-09T04:59:01.006Z | 0f7d92aa916827989a61811d99abd7f6a02dd7c57c9d1a50dc527ade34d04790 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/271d4ec7-9ffe-5ee5-9b50-fbf025df7212.json | https://web.archive.org/web/20260909045901/https://www.caverion.fi/media/tiedotteet/2026/caverion-toteuttaa-paaurakoitsijana-50-miljoonan-euron-datakeskushankkeen-mcf-group-estonialle-baltian-suurin-korkean-turvallisuusstandardin-datakeskus-laajenee/
272cb55a-0283-55d0-a356-53af8aae3872 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["e8a1add0-19fb-5196-ae75-34353e7d580b"] | company_disclosure | ABC original July 2 interview: Firmus current St Leonards construction | https://www.abc.net.au/listen/programs/hobart-mornings/firmus-oliver-curtis-tim-rosenfield-tasmania-data-centres/106868690 | Australian Broadcasting Corporation | europe_round31_firmus_st_leonards | no-open-license-asserted | Australian Broadcasting Corporation | 2026-07-02 | 2026-09-09T23:35:02.471Z | 04e9f0b4260963b1ea9f441a63a3f5a6767db55c6078d355ce559a5b6e0f02e7 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/272cb55a-0283-55d0-a356-53af8aae3872.json | https://web.archive.org/web/20260909233502/https://www.abc.net.au/listen/programs/hobart-mornings/firmus-oliver-curtis-tim-rosenfield-tasmania-data-centres/106868690
2749b90c-3a3e-52ea-9636-2dea8c1c4d30 | ["imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:announced","role:developer","role:utility"] | ["f07274ee-deff-5651-b606-da909d7328af"] | news | ACS aterriza con Benbros Energy en Aragón para la construcción de otro centro de datos | https://www.hoyaragon.es/articulo/noticias-aragon/acs/20250627135338101330.html | Hoy Aragón | www.hoyaragon.es | source-terms-not-recorded | Hoy Aragón | 2025-06-27 | 2026-10-09 | 29b4536b1f970f6571d3d4d2cbe07aed56b1eaf3b4efbb3946f8342429e2259b | day | source_record_projection | acs-la-puebla-de-alfinden | s3 | 4d67e1c342e70c1aab029abca8abac09d6bcba48ba47c042a557ab594cad4c6b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2749b90c-3a3e-52ea-9636-2dea8c1c4d30.json | https://web.archive.org/web/20261009/https://www.hoyaragon.es/articulo/noticias-aragon/acs/20250627135338101330.html
275a19af-0f87-5309-a7b4-a466dea142d5 | ["context:geometry_identity"] | ["d024514a-30a3-514d-b65e-2743133f6800"] | government_record | Loviisa building permit 2025-157 | https://loviisa.oncloudos.com/fi/kokous/20251258-4-67458.PDF | City of Loviisa | loviisa_building_control_decisions | rights-status-uncertain-fact-extraction-only | City of Loviisa |  | 2026-08-23 | 1694e8038e5f30d2996103a7f27478530c088f19b2d4e64f0870d78a2ba6c42f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/275a19af-0f87-5309-a7b4-a466dea142d5.json | https://web.archive.org/web/20260823/https://loviisa.oncloudos.com/fi/kokous/20251258-4-67458.PDF
276230cb-6f75-55ca-9fe4-81acaf55bb82 | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:construction_started","milestone:other","milestone:site_acquired","power_source:diesel_backup","power_source:grid","power_source:other","role:builder","role:developer","role:government","role:owner","role:utility"] | ["c01906b8-f76a-5afe-ae86-ea56184443f3"] | company_disclosure | Nebius in Independence, Missouri project page | https://nebius.com/independencemo | Nebius | nebius.com | source-terms-not-recorded | Nebius |  | 2026-10-09 | 3268e94e18a2b0885fa7f885db4a92a9514d66aea176c1e3bfdfd71202877c47 | unknown | source_record_projection | nebius-independence-missouri | s2 | 520960b450397b2cfae36eb12989945f7e799ceb6836cefd2f9542e954ffef16 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/276230cb-6f75-55ca-9fe4-81acaf55bb82.json | https://web.archive.org/web/20261009/https://nebius.com/independencemo
2765ea35-4037-5771-8cab-3cbd7f180977 | ["imported:geometry","imported:record","metric:investment","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:government"] | ["6788c655-d9ed-520c-8012-56d246d29a0c"] | news | Microsoft avanza con su red de centros de datos en Zaragoza, donde proyecta una de sus mayores regiones en Europa | https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html | elDiario.es | www.eldiario.es | source-terms-not-recorded | elDiario.es | 2025-11-14 | 2026-10-09 | 3699cf5f4141b4c85001d9fda3e500a5fda85755bd4d53c322c730c8e8ed62fa | day | source_record_projection | microsoft-aragon-zaragoza-puerto-venecia | s1 | 4d1630963fc53925a1148c968d421f54888d88d4da82a9f12a33249ea81824f7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2765ea35-4037-5771-8cab-3cbd7f180977.json | https://web.archive.org/web/20261009/https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html
276847d4-183f-5995-ab80-90d4636b467b | ["role:operator"] | ["65e8849e-2ebe-5d58-be63-299cbbcf8d23"] | company_disclosure | CoreSite DE3 - Denver Data Center | https://www.coresite.com/data-center/de3-denver-co | CoreSite | coresite_official_website | all-rights-reserved | CoreSite |  | 2026-07-20T10:42:21Z | 99720e18665fabb5cb2d09308b60326c9bcb226dd1ff2648fa95ba3b21fdb894 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/276847d4-183f-5995-ab80-90d4636b467b.json | https://web.archive.org/web/20260720104221/https://www.coresite.com/data-center/de3-denver-co
276bfe3b-499d-5a05-b991-0b57b2cbd91e | ["imported:record","metric:buildings","metric:land_area","milestone:construction_started"] | ["f07274ee-deff-5651-b606-da909d7328af"] | news | Aragón se convierte en la capital de los datos y la nube: el calendario de Amazon, Microsoft y todos los proyectos | https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html | El Español | www.elespanol.com | source-terms-not-recorded | El Español | 2026-03-22 | 2026-10-09 | 207dd0fcaae6c0765d41910f5aca8db2687ef5cae368b5f4874833c3b0c4fb64 | day | source_record_projection | acs-la-puebla-de-alfinden | s5 | 4d67e1c342e70c1aab029abca8abac09d6bcba48ba47c042a557ab594cad4c6b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/276bfe3b-499d-5a05-b991-0b57b2cbd91e.json | https://web.archive.org/web/20261009/https://www.elespanol.com/aragon/economia/20260322/aragon-convierte-capital-datos-nube-calendario-amazon-microsoft-proyectos/1003744178360_0.html
2777bf28-902c-5287-9929-cee958f099b3 | ["imported:geometry","imported:record"] | ["0a4a2c40-bdf2-5f56-aa09-ecfa54431d3c"] | other | Owasso, Oklahoma | https://en.wikipedia.org/wiki/Owasso,_Oklahoma | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 541d533adc6b9855ff6e8e7873f713a9e1ba3d119b1a55f42256f3237f3f4c08 | unknown | source_record_projection | google-owasso-project-clydesdale | s6 | a97c56693be5922a0e0efe7d6461c0d87a07a5d861231215bf2d8e48f2ff4ef6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2777bf28-902c-5287-9929-cee958f099b3.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Owasso,_Oklahoma
27cd40f2-5183-5f51-a749-737dcb1e93a5 | ["imported:geometry","imported:record","metric:buildings","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","milestone:first_operational","milestone:site_acquired","role:developer","role:government","role:owner"] | ["d654ea2a-ea8e-564e-a1df-67f35d52ebbc"] | government_record | Project Blue FAQ | https://www.pima.gov/3552/Project-Blue-FAQ | Pima County | www.pima.gov | source-terms-not-recorded | Pima County |  | 2026-10-09 | 97295c55ce08a7f561d7807aaacecd876b8ac5a4c6b8980324e1385c76ac172a | unknown | source_record_projection | project-blue-tucson | s1 | 36e90bd020e0cf912c30f63d71e0c1efd8ce8bbc328218d5e7860d7c1996c304 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/27cd40f2-5183-5f51-a749-737dcb1e93a5.json | https://web.archive.org/web/20261009/https://www.pima.gov/3552/Project-Blue-FAQ
27ef5292-9eef-504b-97ab-5d854f237d7f | ["imported:geometry","imported:record","imported:status","metric:power_capacity","role:developer","role:government"] | ["53a18106-0c3f-5249-8717-107230729abc"] | company_disclosure | SoftBank Group and Sesterce to Develop 1 GW AI Data Center in Bosquel, France | https://www.sesterce.com/newsroom/softbank-group-sesterce-1gw-ai-data-center-bosquel-france | Sesterce | www.sesterce.com | source-terms-not-recorded | Sesterce | 2026-06-01 | 2026-10-09 | dfca3a61b82e61e2d64f964d43821062ca39c6e11d68aaac1411d9278af573ad | day | source_record_projection | softbank-sesterce-bosquel | s2 | eb3ff773b740b83fac744a336f55d4b004403fa67da697dbc4c4340bb3aa23dd | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/27ef5292-9eef-504b-97ab-5d854f237d7f.json | https://web.archive.org/web/20261009/https://www.sesterce.com/newsroom/softbank-group-sesterce-1gw-ai-data-center-bosquel-france
2803efb1-75a9-5146-8bbd-483714ab9841 | ["geometry"] | ["edf978b4-fbe8-5f8a-9fe0-bd1e9f33e1d2"] | government_record | Census Public_AR_Current match for 975 Thornwood Drive | https://geocoding.geo.census.gov/geocoder/ | United States Census Bureau | us_census_geocoder | public-domain-us-government | United States Census Bureau |  | 2026-08-23 | 75521d137c83d066a96548ad00594813dc9a22e7c1c57170d6ecf66191bd14da | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2803efb1-75a9-5146-8bbd-483714ab9841.json | https://web.archive.org/web/20260823/https://geocoding.geo.census.gov/geocoder/
28169906-b467-58d6-8829-997e48787111 | ["context:geometry_identity","context:site_distinctness"] | ["1f430ea1-a0e6-5a91-b3e7-3f002b331cf6"] | government_record | DNR FW-33468-0 public notice - Orla data-center campus identity | https://www.in.gov/dnr/calendar/files/wa-102925.pdf | Indiana Department of Natural Resources, Division of Water | americas_round4_meta_lebanon | no-open-redistribution-license-asserted | Indiana Department of Natural Resources, Division of Water |  | 2026-09-08T21:08:43Z | 83eae39dfc8a43dc95474b3b0f2f7a70ef00ecdb55b28060d41d82cc953546f4 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/28169906-b467-58d6-8829-997e48787111.json | https://web.archive.org/web/20260908210843/https://www.in.gov/dnr/calendar/files/wa-102925.pdf
284323d5-84bc-54e0-94fc-3d8edeafda75 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["118053c0-38ee-5fc1-9c4d-f4875cc3c32e"] | government_record | Raiden Infotech's August 3 EC compliance letter for the Turbhe MIDC data centre: under construction phase | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=1544616&refId=1237477223&refType=COMPLIANCE&uuid=448f19a4-30c8-4bdd-8381-d845615e1f8d&version=1.1 | Raiden Infotech India Private Limited, proponent; Ministry of Environment, Forest and Climate Change, India (PARIVESH portal), host | india_parivesh_public_environmental_proposals | no-open-license-asserted | Raiden Infotech India Private Limited, proponent; Ministry of Environment, Forest and Climate Change, India (PARIVESH portal) | 2026-08-05 | 2026-10-09T10:59:29.429Z | 520b8b2e07c5ab755dc91bbe373a7c056c4c0ee17988fe58e664e020218c8668 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/284323d5-84bc-54e0-94fc-3d8edeafda75.json | https://web.archive.org/web/20261009105929/https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=1544616&refId=1237477223&refType=COMPLIANCE&uuid=448f19a4-30c8-4bdd-8381-d845615e1f8d&version=1.1
2845fdef-aa69-5234-99c2-694474e06566 | ["imported:record","imported:status","milestone:other"] | ["9a4afe64-8789-5cee-8947-61a12f8966a8"] | government_record | Notice of Early Decision with Reasons: Beacon AI Centers Heartland Project | https://iaac-aeic.gc.ca/050/evaluations/document/165326?culture=en-CA | Impact Assessment Agency of Canada | iaac-aeic.gc.ca | source-terms-not-recorded | Impact Assessment Agency of Canada | 2026-03-10 | 2026-10-09 | 1c08b7fe116f4b02a1f927408b14c4010f9fbf3d4a411933e6eee3bec42698d6 | day | source_record_projection | beacon-ai-centers-heartland | s3 | 3fa20de3718e9272491cd51627f812d8541cc3638c62724375f137b02b6e33f9 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2845fdef-aa69-5234-99c2-694474e06566.json | https://web.archive.org/web/20261009/https://iaac-aeic.gc.ca/050/evaluations/document/165326?culture=en-CA
284caabe-4de1-56e5-af68-2dad3ffdba21 | ["imported:geometry","imported:record","metric:buildings","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:announced","power_source:grid","role:developer","role:government","role:utility"] | ["a7a29c6e-70aa-5f7b-b172-d1abe208715e"] | news | Inversión millonaria en Querétaro: CloudHQ construirá 6 centros de datos de hiperescala para potenciar la Inteligencia Artificial | https://www.xataka.com.mx/servicios/inversion-millonaria-queretaro-cloudhq-construira-6-centros-datos-hiperescala-para-potenciar-inteligencia-artificial | Xataka México | www.xataka.com.mx | source-terms-not-recorded | Xataka México | 2025-09-26 | 2026-10-09 | b3a989c548cda88e8c190758cfd334461ff624aa9e70a9eff6fc572a89be1296 | day | source_record_projection | cloudhq-queretaro | s2 | e5fc1c4b95552e1f066ffad711ea763302ef3b9f31617b210adb0554fb9d29f9 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/284caabe-4de1-56e5-af68-2dad3ffdba21.json | https://web.archive.org/web/20261009/https://www.xataka.com.mx/servicios/inversion-millonaria-queretaro-cloudhq-construira-6-centros-datos-hiperescala-para-potenciar-inteligencia-artificial
2853444c-d991-5aa9-82a6-31b621178535 | ["imported:geometry","imported:record","metric:buildings","metric:floor_area","metric:investment","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","power_source:solar","role:developer","role:utility"] | ["3b636397-fbb2-5564-a352-fa1382a218b5"] | news | Vantage chief calls complex large even by its standards | https://ozaukeepress.com/content/vantage-chief-calls-complex-large-even-its-standards | Ozaukee Press | ozaukeepress.com | source-terms-not-recorded | Ozaukee Press | 2025-08-20 | 2026-10-09 | ff1710f2aeb5f871c1fbde22d4ea04d79faaabe3b687730f295b46eb567260ce | day | source_record_projection | oracle-vantage-port-washington | s1 | d9322bd7e03400684eb1de18b401871dbb56eee1f83f17ea7546f26ce30e37c7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2853444c-d991-5aa9-82a6-31b621178535.json | https://web.archive.org/web/20261009/https://ozaukeepress.com/content/vantage-chief-calls-complex-large-even-its-standards
285df9c4-2bcd-53b6-b852-c3c1d5c66025 | ["imported:geometry","imported:record","imported:status","milestone:first_operational","role:developer"] | ["55a2bfbb-45b2-5d51-bc40-4cc74d88ccfd"] | trade_press | How Humain plans to use US chips in new Saudi Arabia AI data centres | https://capacityglobal.com/news/humain-data-centre-construction-saudi-arabia/ | Capacity | capacityglobal.com | source-terms-not-recorded | Capacity | 2025-08-26 | 2026-10-09 | 8696fee14fa787135225f2f6d371e456e2fa3886a257a6a18ad35c0faa34398f | day | source_record_projection | humain-dammam | s2 | 9aef373592e1bca1eb175c6a68277e31943df1b2bc543a48f2af8a73ada08d22 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/285df9c4-2bcd-53b6-b852-c3c1d5c66025.json | https://web.archive.org/web/20261009/https://capacityglobal.com/news/humain-data-centre-construction-saudi-arabia/
2866835f-9449-50ee-85cf-3109159fd5a7 | ["context:geometry_identity","context:site_distinctness"] | ["057826b7-3798-5e94-9628-e76e45647c61"] | company_disclosure | Daou issuer service page links the Daou IDC operator domain | https://www.daou.co.kr/ko/service/idc | Daou Technology Inc. | daou_official_public_reporting_and_site_identity | all-rights-reserved | Daou Technology Inc. |  | 2026-09-09T08:21:47.704Z | 730eed5b30fcd564391d5e5091e2d247d98f363bbe2b73fdfa432d5c34a1e573 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2866835f-9449-50ee-85cf-3109159fd5a7.json | https://web.archive.org/web/20260909082147/https://www.daou.co.kr/ko/service/idc
2866b764-c7b1-5435-8585-2f4a496a00f3 | ["imported:geometry","imported:record","metric:buildings","metric:floor_area","metric:land_area","milestone:announced","role:developer","role:utility"] | ["4a2847d7-f84f-5f89-a4c2-ee832e1f6cad"] | other | Coweta County Project Sail Data Center FAQ | https://chattahoochee.org/wp-content/uploads/2026/03/Project-Sail-Fact-Sheet-March-2026.pdf | Chattahoochee Riverkeeper | chattahoochee.org | source-terms-not-recorded | Chattahoochee Riverkeeper | 2026-03-26 | 2026-10-09 | f26f71a16d875c2e8028e7c6c8dfbdc5900f125dcbe68acc9b2a680c350c9875 | day | source_record_projection | project-sail-coweta-county | s1 | 83972926247b9a72f27b4efd57a7891fdbfa7bef75f39efc5ace7d7bd6f0157a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2866b764-c7b1-5435-8585-2f4a496a00f3.json | https://web.archive.org/web/20261009/https://chattahoochee.org/wp-content/uploads/2026/03/Project-Sail-Fact-Sheet-March-2026.pdf
28743ca1-9778-595d-974c-94ff2c3c980a | ["imported:geometry","imported:record","metric:buildings","metric:investment","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:operator"] | ["4ea35229-9824-5086-8441-310876ea8911"] | company_disclosure | Scala Data Centers inaugurates Phase 2 of Tamboré Campus with Governor Tarcísio de Freitas present, committing $1.13 billion | https://www.prnewswire.com/news-releases/scala-data-centers-inaugurates-phase-2-of-tambore-campus-with-governor-tarcisio-de-freitas-present-committing-1-13-billion-302224370.html | Scala Data Centers via PR Newswire | www.prnewswire.com | source-terms-not-recorded | Scala Data Centers via PR Newswire | 2024-08-16 | 2026-10-09 | 0bc5af4c3fe1cc34ae77e4288928021475dcba1863eaf8a60d4bcb845dafe170 | day | source_record_projection | scala-tambore-barueri | s1 | c955f764189fbe4105e203e5a35a47ec6a8ec43c417b4e88dc026f109542be57 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/28743ca1-9778-595d-974c-94ff2c3c980a.json | https://web.archive.org/web/20261009/https://www.prnewswire.com/news-releases/scala-data-centers-inaugurates-phase-2-of-tambore-campus-with-governor-tarcisio-de-freitas-present-committing-1-13-billion-302224370.html
289b100b-96a4-5c57-9235-a36c407be5f3 | ["context:site_distinctness","geometry"] | ["c4ffa53e-bb43-5af1-9e07-aa5045ea480b"] | government_record | Toronto dataset page: OAR licence binding | https://open.toronto.ca/dataset/address-points-municipal-toronto-one-address-repository/ | City of Toronto | americas_africa_round10_etobicoke | Open Government Licence - Toronto | City of Toronto |  | 2026-09-08T23:52:45.293Z | 7a2a8ac2d9cd54aafd86fe393632f9ca7a84607ab4d1c0a0353cfb8a4050b2c2 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/289b100b-96a4-5c57-9235-a36c407be5f3.json | https://web.archive.org/web/20260908235245/https://open.toronto.ca/dataset/address-points-municipal-toronto-one-address-repository/
28c33ea5-e84c-5d84-aa08-9603a4d56df3 | ["imported:record","imported:status","metric:investment","metric:power_capacity","milestone:first_operational"] | ["016877e7-a475-5ebe-9219-0ac699cfff53"] | news | Saudi Arabian data center firm races to export compute from NEOM | https://www.semafor.com/article/09/07/2026/saudi-arabian-data-center-firm-races-to-export-compute-from-neom | Semafor | www.semafor.com | source-terms-not-recorded | Semafor | 2026-09-07 | 2026-10-09 | 0db919c0cbe7e010bdc73cbc73ee39fcf53f9903825c1daf80cba0ba8dd4e615 | day | source_record_projection | datavolt-oxagon | s4 | 55133dd6d75ca52eb0ee78922496756fb284d18ccf52ac00be1955a870a6a561 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/28c33ea5-e84c-5d84-aa08-9603a4d56df3.json | https://web.archive.org/web/20261009/https://www.semafor.com/article/09/07/2026/saudi-arabian-data-center-firm-races-to-export-compute-from-neom
28e75c9f-ba0c-5a0e-adab-3460af89efcc | ["imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","milestone:construction_started","power_source:grid","role:utility"] | ["3315c754-ca0d-5702-8071-44b22787215a"] | company_disclosure | Meta Kansas City Data Center fact sheet | https://datacenters.atmeta.com/wp-content/uploads/2026/09/Metas-Kansas-City-Data-Center.pdf | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms |  | 2026-10-09 | a57871aed2fb1bd369bea0e5a0020fffbfa96c38b29ae3e1f464ccf9faa55b05 | unknown | source_record_projection | meta-kansas-city | s3 | d5a16739885c6faee38a87b2fcc8bd21b6a278e697cf56b52e86e13524ae7479 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/28e75c9f-ba0c-5a0e-adab-3460af89efcc.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/wp-content/uploads/2026/09/Metas-Kansas-City-Data-Center.pdf
28e90c7d-c059-5cbb-a53d-9d6a9913e7f3 | ["physical_status"] | ["3941c42e-216d-52fa-b0d8-d7555b441a1a"] | company_disclosure | Next-level data center Berlin BER02 | https://www.maincubes.com/en/data-centers/berlin-cloud-ai-provider-campus-ber02/ | maincubes | maincubes_data_center_pages | all-rights-reserved | maincubes |  | 2026-07-19T20:43:30Z | cbf094f1a609a272739054b5c5f2f33f5663c9b2d9eee7a0dfa1a5d295f80efb | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/28e90c7d-c059-5cbb-a53d-9d6a9913e7f3.json | https://web.archive.org/web/20260719204330/https://www.maincubes.com/en/data-centers/berlin-cloud-ai-provider-campus-ber02/
28f7a83e-130e-5334-b341-8165c439b288 | ["imported:geometry","imported:record","metric:floor_area","metric:investment","metric:jobs_construction","metric:land_area","milestone:other","milestone:permit_approved","role:government"] | ["d2bf7339-8e09-50df-8229-96ad3f8fa358"] | news | Applied Digital confirms $3.2 billion data center campus in Brookwood | https://www.fox10tv.com/2026/09/25/applied-digital-confirms-32-billion-data-center-campus-brookwood/ | FOX10 News | www.fox10tv.com | source-terms-not-recorded | FOX10 News | 2026-09-24 | 2026-10-09 | f961ada363fe686f6f65897cece4baefd040a9678144482edfdea4ab554fc467 | day | source_record_projection | applied-digital-delta-forge-2 | s4 | 3f77543f5729096edee3c5ffc6f3c7c95c63e56ffc896f2abb25148735d8af6c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/28f7a83e-130e-5334-b341-8165c439b288.json | https://web.archive.org/web/20261009/https://www.fox10tv.com/2026/09/25/applied-digital-confirms-32-billion-data-center-campus-brookwood/
29445792-c8cc-5589-894d-d8094d059dbf | ["context:campus_address_identity"] | ["9ddf0df3-e40c-515f-9468-ed78f063513b"] | company_disclosure | Dallas TX4 Data Center | https://services.global.ntt/en-us/services-and-products/global-data-centers/global-locations/americas/dallas-tx-4-data-center | NTT DATA, Inc. | ntt_global_data_center_location_pages | all-rights-reserved | NTT DATA, Inc. |  | 2026-07-20T05:41:07Z | 8477b8e75e9f30ee2c38136b7001042a18d16aafabf66725cd56e5b15115787f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/29445792-c8cc-5589-894d-d8094d059dbf.json | https://web.archive.org/web/20260720054107/https://services.global.ntt/en-us/services-and-products/global-data-centers/global-locations/americas/dallas-tx-4-data-center
2945aeae-a31b-575f-84f0-0f296eb15f29 | ["imported:record","metric:floor_area","metric:jobs_construction","role:builder"] | ["302bc1de-8d94-5ca1-a94e-ceb9facdcc1e"] | company_disclosure | Tulsa Data Center | https://tulsaokdatacenter.com/ | Tulsa Data Center project website | tulsaokdatacenter.com | source-terms-not-recorded | Tulsa Data Center project website |  | 2026-10-09 | dda499a14382d51f654bbaff5abafb50672826bb41a5fa3c3aa06f9ea235ebeb | unknown | source_record_projection | meta-tulsa | s4 | 1133f6138b97e58b44c5175d758532514cfa710f665fe1387b3ac86f5d43bc21 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2945aeae-a31b-575f-84f0-0f296eb15f29.json | https://web.archive.org/web/20261009/https://tulsaokdatacenter.com/
29483830-227d-5f2c-9552-ea7a8e4a2018 | ["imported:record","imported:status","metric:investment","metric:power_capacity","milestone:first_operational","milestone:other","power_source:grid","role:developer","role:operator"] | ["cb66229f-70db-5cfc-95b3-f5a05a3e73bc"] | news | Kasi Cloud Commissions First Phase Of 100MW AI-Ready Hyperscale Data Centre In Lagos | https://brandspurng.com/?p=191649 | Brand Spur Nigeria | brandspurng.com | source-terms-not-recorded | Brand Spur Nigeria | 2026-05-19 | 2026-10-09 | 187597c18262c794fa0a61ab56a3c1fca9f3bb77500fb7b4f59353f496313429 | day | source_record_projection | kasi-cloud-lekki | s3 | f28323f52114c0517e3c60722514b6397a3c39996bc56c6cdaaf9597fa545f91 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/29483830-227d-5f2c-9552-ea7a8e4a2018.json | https://web.archive.org/web/20261009/https://brandspurng.com/?p=191649
295b555a-ca97-5752-b525-24ab75f62a71 | ["geometry"] | ["b5625b8f-5e00-5fbe-b313-ba7adb980583"] | government_record | Fortaleza municipal SFORPF01 surveyed site plan | https://urbanismoemeioambiente.fortaleza.ce.gov.br/images/urbanismo-e-meio-ambiente/infocidade/cppd/PROJETO_ARQUITETONICO_FL01-02.pdf | Prefeitura de Fortaleza - SEUMA | fortaleza_cppd_project_plans | all-rights-reserved | Prefeitura de Fortaleza - SEUMA; Scala Data Centers |  | 2026-07-21T09:27:36Z | 039df7d2426a28c602fcdb2bafee8cb9bb2ce72ca3d3d2d55d1d44442c2d8b24 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/295b555a-ca97-5752-b525-24ab75f62a71.json | https://web.archive.org/web/20260721092736/https://urbanismoemeioambiente.fortaleza.ce.gov.br/images/urbanismo-e-meio-ambiente/infocidade/cppd/PROJETO_ARQUITETONICO_FL01-02.pdf
298bd1d0-124a-5b3a-bf24-e42dd03fa089 | ["imported:record","metric:investment","metric:jobs_permanent","milestone:other","role:government"] | ["e9f8645b-ff54-5ebb-8f6c-6c04dbc8d5e2"] | news | Pittsylvania supervisors back $100B Berry Hill Data Center project | https://wset.com/news/local/pittsylvania-county-advances-100b-data-center-campus-proposal-despite-resident-concerns-berry-hill-july-2026 | WSET | wset.com | source-terms-not-recorded | WSET | 2026-07-21 | 2026-10-09 | 5438aadf49acd237f49889a253710ae0ce7e4c8fd80ebaaafd9fabdeab9a3749 | day | source_record_projection | stack-berry-hill-pittsylvania-county | s3 | d2020bfa59b7a7adbcb7c333acb3d94bcd1996ebae3d0c2cef21f293d0cbdbff | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/298bd1d0-124a-5b3a-bf24-e42dd03fa089.json | https://web.archive.org/web/20261009/https://wset.com/news/local/pittsylvania-county-advances-100b-data-center-campus-proposal-despite-resident-concerns-berry-hill-july-2026
2990174e-9cc5-5129-9c06-7fd46477a9b0 | ["context:site_distinctness","geometry"] | ["cbe074bd-68d8-59cb-aaf7-e21fa82b193f"] | government_record | USACE MVK-2025-00855: named Highway 3 Technology Park Project Site and embedded map georeference | https://www.mvk.usace.army.mil/Portals/58/docs/regulatory/publicnotices/Public%20Notice%20MVK-2025-00855%20WP%20Signed.pdf?ver=D2NPrQzn2XfolicLUj62YA%3D%3D | U.S. Army Corps of Engineers, Vicksburg District; applicant mapping by Headwaters for Bohler Engineering | usace_vicksburg_public_notice_mvk_2025_00855 | no-open-redistribution-license-asserted-for-applicant-map | U.S. Army Corps of Engineers, Vicksburg District; Headwaters / Bohler Engineering applicant map | 2026-04-16 | 2026-09-10T18:35:45.565Z | 5b1ba57fa706c41a28920d3cd6e06c87f7dd38a744df56decf4d49b0919f8f8d | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2990174e-9cc5-5129-9c06-7fd46477a9b0.json | https://web.archive.org/web/20260910183545/https://www.mvk.usace.army.mil/Portals/58/docs/regulatory/publicnotices/Public%20Notice%20MVK-2025-00855%20WP%20Signed.pdf?ver=D2NPrQzn2XfolicLUj62YA%3D%3D
29917174-7529-531b-9498-1ccd315ddb92 | ["context:site_distinctness","geometry"] | ["d5b84301-4f54-5958-a0d1-fd2c5a72cc5b"] | government_record | Official Address Numbers layer semantics | https://gis.palmcoast.gov/hosting/rest/services/External/FlaglerCountyParcels/MapServer/0?f=pjson | City of Palm Coast | americas_round28_palm_coast | no-open-license-asserted | City of Palm Coast |  | 2026-09-09T10:40:01.835Z | 36787e4c75e88880554f70408f687da05e6c66989503f96f10e89dc9d3f77bd2 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/29917174-7529-531b-9498-1ccd315ddb92.json | https://web.archive.org/web/20260909104001/https://gis.palmcoast.gov/hosting/rest/services/External/FlaglerCountyParcels/MapServer/0?f=pjson
299ff180-d01b-5474-b229-12fed55b6f7c | ["context:source_location_identity","physical_status"] | ["9283d3fe-3789-54c7-abf4-8bb757e29835"] | government_record | Jefferson Lab breaks ground on new building to power next-generation scientific discovery | https://www.jlab.org/news/releases/jefferson-lab-breaks-ground-new-building-power-next-generation-scientific-discovery | Thomas Jefferson National Accelerator Facility | jefferson_lab_news_releases | all-rights-reserved | Thomas Jefferson National Accelerator Facility | 2026-06-12 | 2026-07-21T00:05:02Z | 1c9034ba0e4bd2c0d210dc7a3dfe74f9a98c25913b57284661165f9c6bb01f48 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/299ff180-d01b-5474-b229-12fed55b6f7c.json | https://web.archive.org/web/20260721000502/https://www.jlab.org/news/releases/jefferson-lab-breaks-ground-new-building-power-next-generation-scientific-discovery
29bdb34b-54f1-5e00-b28e-877efbf2e828 | ["geometry"] | ["4eeb97fa-8e1d-53de-ae86-eebc40e97d6f"] | government_record | Energieatlas Rheinland-Pfalz project 149 | https://www.energieatlas.rlp.de/geoserver/earp/ows?service=WFS&version=1.0.0&request=GetFeature&typeName=earp%3Apraxisbeispiele&srsName=EPSG%3A4326&outputFormat=application%2Fjson&cql_filter=id%3D149%20AND%20typ%3D%27unternehmen%27 | Energieagentur Rheinland-Pfalz | energieatlas_rlp_praxisbeispiele_wfs | all-rights-reserved-fact-extraction-only | Energieagentur Rheinland-Pfalz |  | 2026-08-23 | 0ce08cddbf9abfd8377c390c2f7def9ba1df95ee6447a0400ae8d2a00ebacbde | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/29bdb34b-54f1-5e00-b28e-877efbf2e828.json | https://web.archive.org/web/20260823/https://www.energieatlas.rlp.de/geoserver/earp/ows?service=WFS&version=1.0.0&request=GetFeature&typeName=earp%3Apraxisbeispiele&srsName=EPSG%3A4326&outputFormat=application%2Fjson&cql_filter=id%3D149%20AND%20typ%3D%27unternehmen%27
2a3a54fe-bcf3-5e51-ac21-8791ecef42ae | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["ad57807a-f6b6-55f9-b26f-acd194e12880"] | company_disclosure | Flexential reports a Hillsboro facility currently under construction | https://www.prnewswire.com/news-releases/flexential-secures-800-million-to-fund-data-center-development-across-four-high-growth-markets-302853453.html | Flexential, distributed by PR Newswire | americas_round11_flexential_hillsboro5 | all-rights-reserved | Flexential, distributed by PR Newswire | 2026-08-18T13:04:00Z | 2026-09-09T00:23:28.443Z | 9ebff6124ed797e5d92ac20c409d391c2f2bdf2b165243a16314f44f562eb4d2 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2a3a54fe-bcf3-5e51-ac21-8791ecef42ae.json | https://web.archive.org/web/20260909002328/https://www.prnewswire.com/news-releases/flexential-secures-800-million-to-fund-data-center-development-across-four-high-growth-markets-302853453.html
2a51650c-1b90-5cd4-9448-8601d200965e | ["imported:geometry","imported:record","metric:floor_area","metric:investment","milestone:other","role:developer","role:power_supplier"] | ["09904943-69d4-51d7-aef7-4ff880e47332"] | news | Google confirms West Memphis data center | https://dailymemphian.com/section/businessreal-estate/article/54862/google-west-memphis-data-center-entergy-arkansas-groot | The Daily Memphian | dailymemphian.com | source-terms-not-recorded | The Daily Memphian | 2025-09-05 | 2026-10-09 | 3e84462ee169684176df0c9de0cacf8861688276ff06cd02832f75e0b69dab60 | day | source_record_projection | google-west-memphis-arkansas | s4 | affe666039075290c2511ab766a40b580f546f594dfcdc4b58bfb59341573b09 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2a51650c-1b90-5cd4-9448-8601d200965e.json | https://web.archive.org/web/20261009/https://dailymemphian.com/section/businessreal-estate/article/54862/google-west-memphis-data-center-entergy-arkansas-groot
2a532c35-28a5-5706-9606-e1d4ccf2c03c | ["imported:record","metric:buildings","metric:floor_area","metric:land_area","milestone:announced","role:developer"] | ["3f13d78d-ac2f-533b-8e04-01009bd9d17b"] | trade_press | Tract announces new gigawatt-scale data center park in Phoenix, Arizona | https://baxtel.com/news/tract-announces-new-gigawatt-scale-data-center-park-in-phoenix-arizona | Baxtel | baxtel.com | source-terms-not-recorded | Baxtel | 2024-08-31 | 2026-10-09 | 96824ea7befbc04c7ec87a65ac08a69b2d35ac660f43176f7e2de093fc7c8db5 | day | source_record_projection | tract-buckeye | s3 | 310f1982a3fe50db0f439de7a123a0ed3dbd700b5d8471ba9b368d8d683560ee | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2a532c35-28a5-5706-9606-e1d4ccf2c03c.json | https://web.archive.org/web/20261009/https://baxtel.com/news/tract-announces-new-gigawatt-scale-data-center-park-in-phoenix-arizona
2a8a3d06-a59f-570b-82cf-2dfa6b118607 | ["imported:record","imported:status","milestone:other","role:tenant"] | ["8ce04eb2-b1ed-5375-a685-122f79fc2ee6"] | company_disclosure | Core Scientific announces second quarter 2026 results | https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-07-28 | 2026-10-09 | 476124874189569bce65e88cad0e1bfd86ffc092c87a0ab4c891e95b10c3987b | day | source_record_projection | core-scientific-pecos | s5 | ab37ccfdcc0bc48d95f588d7a62361846b812822a0cd61b3d36fc6ae2dea2784 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2a8a3d06-a59f-570b-82cf-2dfa6b118607.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/news-events/press-releases/detail/139/core-scientific-announces-second-quarter-2026-results
2aa9849b-9467-53dd-ba43-e1fdbb2e2641 | ["imported:geometry","imported:record"] | ["0eb54c2e-ed0f-58e9-85cc-bf616b723139"] | other | Center, North Dakota | https://en.wikipedia.org/wiki/Center,_North_Dakota | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 468ebe615643bd1f40b9ca035548576dbc936b0c3e7de5ced281e9f4081610e4 | unknown | source_record_projection | applied-digital-polaris-forge-3 | s4 | bf8ae2da16a9750a0827601c845afcadcb3388756142390227e81be26b2fc1a2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2aa9849b-9467-53dd-ba43-e1fdbb2e2641.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Center,_North_Dakota
2b138f72-e7f8-560c-8f63-0cbe196b245e | ["context:source_location_identity","physical_status"] | ["2cac8eb7-dff6-50bc-be49-b45f6e353982"] | company_disclosure | Ascenty Secures 150 Megawatts of New AI Contracts with Leading Global Hyperscalers | https://ascenty.com/en/blog/news-ascenty-en/ascenty-ai-contracts/ | Ascenty | ascenty_newsroom | all-rights-reserved | Ascenty | 2026-05-28T12:05:17+00:00 | 2026-07-20T18:06:07Z | 966870f4e9dc712246aaa91720f200ebb422da97c408f2ddedb8b9b1daa0e132 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2b138f72-e7f8-560c-8f63-0cbe196b245e.json | https://web.archive.org/web/20260720180607/https://ascenty.com/en/blog/news-ascenty-en/ascenty-ai-contracts/
2b179a35-b28d-57c4-86d4-e1ab5a58e8e7 | ["imported:record","metric:buildings","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:announced","milestone:fully_operational","role:developer","role:tenant"] | ["3b636397-fbb2-5564-a352-fa1382a218b5"] | trade_press | OpenAI, Oracle and Vantage Data Centers announce Stargate data center site in Wisconsin | https://w.media/openai-oracle-and-vantage-data-centers-announce-stargate-data-center-site-in-wisconsin/ | W.Media | w.media | source-terms-not-recorded | W.Media | 2025-10-23 | 2026-10-09 | ff502a263e64f1b06af6ba795f6d0eecb34208746bd2ab3de60f27fd0fdf0db7 | day | source_record_projection | oracle-vantage-port-washington | s2 | d9322bd7e03400684eb1de18b401871dbb56eee1f83f17ea7546f26ce30e37c7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2b179a35-b28d-57c4-86d4-e1ab5a58e8e7.json | https://web.archive.org/web/20261009/https://w.media/openai-oracle-and-vantage-data-centers-announce-stargate-data-center-site-in-wisconsin/
2b33b1a7-ba8e-5f00-b45d-7a0a55ee8850 | ["context:geometry_identity","context:site_distinctness"] | ["b4ff75a2-9d55-54ad-bf27-4c60b096eb0f"] | company_disclosure | Operator distinguishes existing Rockdale infrastructure from expansion | https://www.riotplatforms.com/locations/rockdale/ | Riot Platforms, Inc. | americas_round30_riot_rockdale | no-open-license-asserted | Riot Platforms, Inc. |  | 2026-09-09T11:44:29.804Z | e7e2de36f19756e49845ef8e1b7bd0d5c744074154ad2012114cbaf813b019eb | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2b33b1a7-ba8e-5f00-b45d-7a0a55ee8850.json | https://web.archive.org/web/20260909114429/https://www.riotplatforms.com/locations/rockdale/
2b3603ad-d2a2-504e-9c31-dbbb21a8b08d | ["imported:geometry","imported:record","metric:power_capacity","milestone:announced","power_source:grid","role:developer","role:utility"] | ["384a401d-cc7f-52e4-9ae3-218a378995b9"] | trade_press | Khazna announces construction of 100 MW AI optimised Data Center in Ajman | https://w.media/khazna-announces-construction-of-100-mw-ai-optimised-data-center-in-ajman/ | W.Media | w.media | source-terms-not-recorded | W.Media | 2024-10-15 | 2026-10-09 | f4945a5fc12173736d1c6cfbbec2d37e09da86a4ba33c911e0d2a0b90b912624 | day | source_record_projection | khazna-ajman | s1 | 92a643d476e98c5addb8185cc1322ba283996fcbede435884f9449965f68ea71 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2b3603ad-d2a2-504e-9c31-dbbb21a8b08d.json | https://web.archive.org/web/20261009/https://w.media/khazna-announces-construction-of-100-mw-ai-optimised-data-center-in-ajman/
2b620414-745c-5b05-9ddb-a65fa6fe757a | ["imported:geometry","imported:record","metric:buildings","metric:land_area","metric:power_capacity","power_source:natural_gas_onsite","role:developer"] | ["908ba9ce-1e84-567b-926f-8d47d4d2a7ed"] | news | Company withdraws data center proposal, residents express skepticism | https://www.wdbj7.com/2025/04/14/company-withdraws-data-center-proposal-residents-express-skepticism/ | WDBJ7 | www.wdbj7.com | source-terms-not-recorded | WDBJ7 | 2025-04-14 | 2026-10-09 | 51b14f724e6c968ce90ade978582e6e34fe091a57be96f5c2f293f2c583d45cd | day | source_record_projection | balico-pittsylvania-county | s3 | 9169c30b464bb8fd99931fce532ae356b7455ba9eb4e67c4c9c205374c151b21 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2b620414-745c-5b05-9ddb-a65fa6fe757a.json | https://web.archive.org/web/20261009/https://www.wdbj7.com/2025/04/14/company-withdraws-data-center-proposal-residents-express-skepticism/
2b7eb369-a205-5ca1-93c4-3a6a2058b8a7 | ["imported:geometry","imported:record","imported:status","metric:floor_area","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:expansion_announced","power_source:battery_storage","power_source:grid","power_source:nuclear","power_source:solar","role:developer","role:government","role:utility"] | ["803e9da5-cd1e-5849-813c-fe7c5b5f126b"] | government_record | Meta Commits More Than $50 Billion for North Louisiana Project, Becoming One of the Largest Data Centers in History | https://www.opportunitylouisiana.gov/news/meta-commits-more-than-50-billion-for-north-louisiana-project-becoming-one-of-the-largest-data-centers-in-history | Louisiana Economic Development | www.opportunitylouisiana.gov | source-terms-not-recorded | Louisiana Economic Development | 2026-07-13 | 2026-10-09 | 87ec24f1852b0b90601a8255f00c1af828218d6e00b7f2f542944d1930bda3d8 | day | source_record_projection | meta-hyperion-richland-parish | s4 | 32572f3cc36c74b52139674363a64f8dc1cb863db825b2f7c38e412c404e5ebe | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2b7eb369-a205-5ca1-93c4-3a6a2058b8a7.json | https://web.archive.org/web/20261009/https://www.opportunitylouisiana.gov/news/meta-commits-more-than-50-billion-for-north-louisiana-project-becoming-one-of-the-largest-data-centers-in-history
2ba6b299-460e-5bf7-b44f-bae30608c150 | ["context:geometry_identity","context:site_distinctness"] | ["709cd37b-7f3a-5313-b3e2-a18ddc0885ec"] | company_disclosure | Issuer-hosted indenture identifies Core Scientific property at1851FM2119 | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001193125-24-008966/d527548dex99t3c1.htm | Core Scientific, Inc. | pecos_round15_primary_review | all-rights-reserved | Core Scientific, Inc. | 2024-01-17 | 2026-09-09T03:14:16.469Z | f7d00a9de368a74cc6ca2718d531e8dc3f54d0dc36a95fb69a86ab5079be2ec1 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2ba6b299-460e-5bf7-b44f-bae30608c150.json | https://web.archive.org/web/20260909031416/https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001193125-24-008966/d527548dex99t3c1.htm
2bd6997a-8723-5dfc-a591-49bb888061d9 | ["imported:geometry","imported:record","metric:land_area","metric:power_capacity","milestone:site_acquired","power_source:grid","role:developer","role:investor"] | ["48d82a4f-46ea-5641-a650-b6e147b30ae6"] | trade_press | PowerHouse Data Centers announces purchase of 145 acres in Spotsylvania, Va. for PowerHouse 95 campus | https://www.lightwaveonline.com/data-center/article/14304356/powerhouse-data-centers-announces-purchase-of-145-acres-in-spotsylvania-va-for-powerhouse-95-campus | Lightwave | www.lightwaveonline.com | source-terms-not-recorded | Lightwave | 2024-01-30 | 2026-10-09 | a326f425c37e519adba01d0b071adf37fe17265c2a75cc9e9800256639ce97be | day | source_record_projection | powerhouse-95-spotsylvania | s2 | f0b18d16b3585dbcbd5b508f44acc06b6752ef0ee16c2c6b445248f02291d9c6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2bd6997a-8723-5dfc-a591-49bb888061d9.json | https://web.archive.org/web/20261009/https://www.lightwaveonline.com/data-center/article/14304356/powerhouse-data-centers-announces-purchase-of-145-acres-in-spotsylvania-va-for-powerhouse-95-campus
2bd9d01f-b34d-5ac0-94b8-8dd17c9543cf | ["context:site_distinctness","geometry"] | ["aa2dc8a4-52d8-5519-b23a-2ff0313db9e3"] | company_disclosure | Edged MAD02: literal campus coordinates | https://cdn.prod.website-files.com/612d5118cc3229538b508294/68bf2b6a1186eb51f6c433e8_MAD02_Spec%20Sheet_250730_Digital.pdf | Edged | expansion_round5_primary_sources | all-rights-reserved | Edged |  | 2026-09-08T21:23:00Z | d2171b5dc409ad7f1c2f8ccb26198d2a7051a70ddc2a331e313204b5b463cedd | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2bd9d01f-b34d-5ac0-94b8-8dd17c9543cf.json | https://web.archive.org/web/20260908212300/https://cdn.prod.website-files.com/612d5118cc3229538b508294/68bf2b6a1186eb51f6c433e8_MAD02_Spec%20Sheet_250730_Digital.pdf
2bf376f5-d22b-52d3-8103-8830be48bafc | ["context:geometry_identity","context:site_distinctness"] | ["8c926b8f-0190-533b-aa7e-3223971b9e23"] | company_disclosure | Owner exact D2 street address and identity | https://www.prnewswire.com/news-releases/flexential-secures-strategic-real-estate-control-in-atlanta-with-acquisition-of-two-facilities-302452014.html | Flexential, distributed by PR Newswire | flexential_douglasville2_round12 | no-open-redistribution-license-asserted | Flexential, distributed by PR Newswire | 2025-05-12T13:00:00Z | 2026-09-09T00:24:07.026Z | a5a25c4f40c8afdce86726d1c9e69ac9705966a6c440086f400cc192cbf2f9d9 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2bf376f5-d22b-52d3-8103-8830be48bafc.json | https://web.archive.org/web/20260909002407/https://www.prnewswire.com/news-releases/flexential-secures-strategic-real-estate-control-in-atlanta-with-acquisition-of-two-facilities-302452014.html
2c0bc98f-0caf-5723-971e-4cacbedf9e34 | ["imported:geometry","imported:record","metric:buildings","metric:investment","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:announced","milestone:construction_started","power_source:grid","role:developer","role:utility"] | ["5c691ba6-a630-5ab4-a45d-4d676e3e4d53"] | company_disclosure | Applied Digital to Break Ground on $3 Billion Polaris Forge 2 Campus in September 2025 | https://ir.applieddigital.com/news-events/press-releases/detail/127/applied-digital-to-break-ground-on-3-billion-polaris-forge | Applied Digital | ir.applieddigital.com | source-terms-not-recorded | Applied Digital | 2025-08-18 | 2026-10-09 | aaa9641b76e94d7f23e7bfe59b3b2d49c344c9f1b195d7b2b0cda67820307503 | day | source_record_projection | applied-digital-polaris-forge-2 | s1 | c28d9e66605af454a76ac320e9b833d6efe8fe36b481ef4868d8867964ae7278 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2c0bc98f-0caf-5723-971e-4cacbedf9e34.json | https://web.archive.org/web/20261009/https://ir.applieddigital.com/news-events/press-releases/detail/127/applied-digital-to-break-ground-on-3-billion-polaris-forge
2c1a0857-1368-581b-adfa-96bf72cc9c16 | ["geometry"] | ["7d936c4e-29f2-592f-984b-61f5d6367fc8"] | openstreetmap | OpenStreetMap way 1528327802: The Barn Data Center | https://www.openstreetmap.org/way/1528327802 | OpenStreetMap contributors | openstreetmap | ODbL-1.0 | © OpenStreetMap contributors | 2026-06-11T00:48:00Z | 2026-07-18T18:15:02.152575Z | 04f03a496617fcc7159f1762127d29f861002822d76203c2cceda97689a309e7 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2c1a0857-1368-581b-adfa-96bf72cc9c16.json | https://web.archive.org/web/20260718181502/https://www.openstreetmap.org/way/1528327802
2c1ca24e-7649-5551-85f5-511271e7c8c4 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["1f430ea1-a0e6-5a91-b3e7-3f002b331cf6"] | government_record | Lebanon July 6 minutes - Meta/Orla campus under construction | https://lebanon.in.gov/wp-content/uploads/2026/01/07.06.2026-Board-of-Zoning-Appeals-Mtg-Minutes.pdf | City of Lebanon Board of Zoning Appeals | americas_round4_meta_lebanon | no-open-redistribution-license-asserted | City of Lebanon Board of Zoning Appeals |  | 2026-09-08T21:05:44Z | 02bd41d816ba6e5fb6fc478161a60743ae32931e4c42d35a5317c2fcaf14ff3d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2c1ca24e-7649-5551-85f5-511271e7c8c4.json | https://web.archive.org/web/20260908210544/https://lebanon.in.gov/wp-content/uploads/2026/01/07.06.2026-Board-of-Zoning-Appeals-Mtg-Minutes.pdf
2c3a3f9f-e178-5fec-8935-ad6d17201359 | ["context:identity"] | ["510a8216-64d9-5626-992a-3ca10f40fb90","7b86e3a5-3492-5bb1-b47c-2010427939cd"] | company_disclosure | TECROWD digital-infrastructure progress report index | https://tecrowd.jp/column/construction-report/digital-infrastructure/ | TECRA / TECROWD | tecra_official | all-rights-reserved | TECRA / TECROWD |  | 2026-10-13T17:12:22.196185+00:00 | 7fced8b9c4db040e77198d9bcbbf9b5a2d9996114817faf61b3002cb48d36d99 | unknown | sha256_exact_content_decoded_response_bytes |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2c3a3f9f-e178-5fec-8935-ad6d17201359.json | https://web.archive.org/web/20261013171222/https://tecrowd.jp/column/construction-report/digital-infrastructure/
2c514e1e-08fd-5e9d-b21d-14694ef236cc | ["imported:record","metric:investment","metric:land_area","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:government"] | ["a9ca22ae-d872-5122-a052-e5c9ec410abd"] | news | Microsoft avanza con su red de centros de datos en Zaragoza, donde proyecta una de sus mayores regiones en Europa | https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html | elDiario.es | www.eldiario.es | source-terms-not-recorded | elDiario.es | 2025-11-14 | 2026-10-09 | 501a1f66e7ce05f58750a3ecdadafb5faa555140208c27bd7324657de1852354 | day | source_record_projection | microsoft-aragon-la-muela | s2 | 6b52e7ee1fc0d0bf161b9378e47ebccbfedbc6afc0fbcb18c225c7fcc32a53b3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2c514e1e-08fd-5e9d-b21d-14694ef236cc.json | https://web.archive.org/web/20261009/https://www.eldiario.es/aragon/sociedad/microsoft-avanza-red-centros-datos-zaragoza-proyecta-mayores-regiones-europa_1_12768636.html
2c88a108-743f-55a6-98df-271b27933fdd | ["imported:record","milestone:expansion_announced","power_source:other","role:developer","role:government"] | ["0b37ac4d-93f2-559b-a6ec-f5a12938681a"] | company_disclosure | Bell AI Fabric to expand nation-building project in Saskatchewan with up to 900 MW of additional power | https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-to-expand-nation-building-project-in-saskatchewan-with-up-to-900-mw-of-additional-power | BCE Inc. | www.bce.ca | source-terms-not-recorded | BCE Inc. | 2026-09-14 | 2026-10-09 | 426fb43b5ba2695cb86b9ce9aae2d94a4559d57bf33564740ad7e6045de628d6 | day | source_record_projection | bell-ai-fabric-sherwood-saskatchewan | s1 | 16c96149f34f8e8f77b8c0c17353148d280b27c5336b316bd6a5419437e7acef | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2c88a108-743f-55a6-98df-271b27933fdd.json | https://web.archive.org/web/20261009/https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-to-expand-nation-building-project-in-saskatchewan-with-up-to-900-mw-of-additional-power
2cad566b-10a1-597e-9398-4502d4fbce10 | ["context:geometry_identity","context:site_distinctness"] | ["b7744ad5-aa48-5977-a70e-3d6a588f468d"] | company_disclosure | Applied Digital disclaimer and source copyright notice | https://ir.applieddigital.com/disclaimer | Applied Digital Corporation | americas_round5_df1_followup | no-open-redistribution-license-asserted | Applied Digital Corporation |  | 2026-09-08T22:10:37Z | 07c7f278a1dc8bfe3410349faa46230f615bc7d10f0731525f3e698398366eba | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2cad566b-10a1-597e-9398-4502d4fbce10.json | https://web.archive.org/web/20260908221037/https://ir.applieddigital.com/disclaimer
2cd48493-bff6-5366-9b52-98b724d14f7c | ["imported:record","metric:power_capacity","milestone:announced","role:developer"] | ["81d20134-d073-5e0c-ad1c-7f8a97f2dadb"] | company_disclosure | TBC Partners | https://www.tbcpartners.co.uk/ | TBC Partners | www.tbcpartners.co.uk | source-terms-not-recorded | TBC Partners |  | 2026-10-09 | ed4345078dbc0b3443553b69aed973a94a4689dafbe8c9ab542c6e2df1014f66 | unknown | source_record_projection | tbc-partners-cambois | s1 | 1ed67826272efcc8bff6bd33ef12dcbc0ab7f5e8ee6f3b1cac4e60aa1808b7e4 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2cd48493-bff6-5366-9b52-98b724d14f7c.json | https://web.archive.org/web/20261009/https://www.tbcpartners.co.uk/
2ce6c8b6-53a4-51a5-b633-c84753eb096e | ["imported:geometry","imported:record","metric:power_capacity","milestone:announced","role:developer"] | ["304e9b81-f1b5-5a80-8ad5-6f46e12f5a85"] | trade_press | EcoDataCenter announces plans for mega campus in Sweden | https://datacentrereview.com/?p=81016 | Data Centre Review | datacentrereview.com | source-terms-not-recorded | Data Centre Review | 2024-09-06 | 2026-10-09 | 654c04d82d5b4ec00e55f343cef47fd07f736fbec7ddbd6e66f62461a69cae0e | day | source_record_projection | ecodatacenter-borlange | s2 | 553c6701161532f38f3aefda2f0854ee4f3382deb968866b9e6120abf75060c7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2ce6c8b6-53a4-51a5-b633-c84753eb096e.json | https://web.archive.org/web/20261009/https://datacentrereview.com/?p=81016
2d022ff4-45fb-5337-adb2-b49bfa3546d9 | ["context:source_location_identity","physical_status"] | ["e2c7ea58-17cc-594d-8b98-56ca08988c99"] | government_record | Haidong mayor visits computing-industry construction sites | https://www.huzhu.gov.cn/info/1007/85926.htm | Huzhu County People's Government | haidong_government_project_updates | all-rights-reserved | Huzhu County People's Government | 2026-06-24 | 2026-07-21T15:55:09Z | 0c6f983f91c9f2804287c2cbd8420c6006af2f500cb2b265aebb1d1a4bb2c9ba | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2d022ff4-45fb-5337-adb2-b49bfa3546d9.json | https://web.archive.org/web/20260721155509/https://www.huzhu.gov.cn/info/1007/85926.htm
2d52158b-57ba-559c-8ffa-acde0ff95458 | ["context:site_distinctness","geometry"] | ["c23fe40c-0685-5cee-8fab-9c08575e6b27"] | government_record | Public permit map exposes exact official address and permit layers | https://AuroraCo.maps.arcgis.com/sharing/rest/content/items/3bb0ce685ce442129077c9b1d37081fc/data?f=json | City of Aurora, Colorado | americas_round24_qts_aurora | no-open-license-asserted | City of Aurora, Colorado |  | 2026-09-09T07:47:51.297520+00:00 | 41a307046ff16c7779fecfaf1e8bd1c94ca61f880f5e2a133d41753170a6784c | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2d52158b-57ba-559c-8ffa-acde0ff95458.json | https://web.archive.org/web/20260909074751/https://AuroraCo.maps.arcgis.com/sharing/rest/content/items/3bb0ce685ce442129077c9b1d37081fc/data?f=json
2d5bc456-aeed-594a-ab5b-cd46d905c58e | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:investment","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:government","role:operator"] | ["4ea35229-9824-5086-8441-310876ea8911"] | company_disclosure | Scala Data Centers celebrates historic milestone with approval of the master plan for its Tamboré Campus in São Paulo, the largest and most advanced in Latin America with 600 MW of capacity | https://www.prnewswire.com/news-releases/scala-data-centers-celebrates-historic-milestone-with-approval-of-the-master-plan-for-its-tambore-campus-in-sao-paulo---the-largest-and-most-advanced-in-latin-america-with-600-mw-of-capacity-302599995.html | Scala Data Centers via PR Newswire | www.prnewswire.com | source-terms-not-recorded | Scala Data Centers via PR Newswire | 2025-10-30 | 2026-10-09 | 498d12c994f367cc16a2941b790f5b024578912970876350147025ba8f101871 | day | source_record_projection | scala-tambore-barueri | s2 | c955f764189fbe4105e203e5a35a47ec6a8ec43c417b4e88dc026f109542be57 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2d5bc456-aeed-594a-ab5b-cd46d905c58e.json | https://web.archive.org/web/20261009/https://www.prnewswire.com/news-releases/scala-data-centers-celebrates-historic-milestone-with-approval-of-the-master-plan-for-its-tambore-campus-in-sao-paulo---the-largest-and-most-advanced-in-latin-america-with-600-mw-of-capacity-302599995.html
2d648f1e-7c80-5940-a12f-d4773dea2219 | ["imported:geometry","imported:record"] | ["2c24f89f-37e6-5164-a240-e1e3d2fca176"] | other | Ulu Tiram | https://en.wikipedia.org/wiki/Ulu_Tiram | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 783cd90c2a2affa6cc333b9cc2947a1b2326b4935e738bef1f1cc48d0a1a9676 | unknown | source_record_projection | bridge-my07-ulu-tiram | s5 | fda31697d9ade5ca3619d910cdecda07562b9dd09cef4c65a48d67a3aa1b507c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2d648f1e-7c80-5940-a12f-d4773dea2219.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Ulu_Tiram
2dae533a-a76f-54ec-a85e-7612134d111e | ["imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:announced","role:developer"] | ["337ace90-652d-52fe-a856-fe9b04b5966f"] | news | Meta to spend $1.5 billion on AI data center in Texas | https://www.fox26houston.com/news/meta-ai-data-center-texas-el-paso | FOX 26 Houston | www.fox26houston.com | source-terms-not-recorded | FOX 26 Houston | 2025-10-15 | 2026-10-09 | fa7f27f31c462389807d72863f180d2ba1782896b98315cda7b9fb986fe866b1 | day | source_record_projection | meta-el-paso | s1 | be1879b543b0ada955c7ab4a7ecebeb6d0d63a8bc5b4b2467644b09395dfd1dc | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2dae533a-a76f-54ec-a85e-7612134d111e.json | https://web.archive.org/web/20261009/https://www.fox26houston.com/news/meta-ai-data-center-texas-el-paso
2ddfa1d8-0a27-58a7-bc6a-1086d024ffa7 | ["context:multi_site_program","imported:geometry","imported:record","imported:status","metric:floor_area","metric:investment","milestone:construction_started","milestone:other","power_source:grid","power_source:other","role:developer","role:tenant","role:utility"] | ["b75695b9-38e3-58ec-baf2-039179ab353a"] | news | Data center's second phase expected to cost up to $2.5 billion in Lancaster County | https://www.witf.org/2025/10/19/data-centers-second-phase-expected-to-cost-up-to-2-5-billion-in-lancaster-county/ | WITF (LNP ¦ LancasterOnline) | www.witf.org | source-terms-not-recorded | WITF (LNP ¦ LancasterOnline) | 2025-10-19 | 2026-10-09 | ec2509437e139b284b0e32f312afdddfeefe5ab9157ec4183b0855eca61a934b | day | source_record_projection | coreweave-lancaster-pennsylvania | s4 | 3da7b985dea6aab54b6d7610b08c127892b84b6825d60e166f63e4d3b65a78de | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2ddfa1d8-0a27-58a7-bc6a-1086d024ffa7.json | https://web.archive.org/web/20261009/https://www.witf.org/2025/10/19/data-centers-second-phase-expected-to-cost-up-to-2-5-billion-in-lancaster-county/
2e09b450-ac25-5670-a9cf-3a4e0a434bc5 | ["imported:geometry","imported:record","metric:land_area","metric:power_capacity","milestone:construction_started","milestone:site_acquired","role:developer","role:investor"] | ["c53b72b6-ff87-58eb-b74f-7082b159a513"] | trade_press | Data4 breaks ground on data center project in Hanau, Germany | https://bebeez.eu/en/news/data4-breaks-ground-on-data-center-project-in-hanau-germany/ | BeBeez International (republishing DCD) | bebeez.eu | source-terms-not-recorded | BeBeez International (republishing DCD) | 2025-09-17 | 2026-10-09 | 225e61c0241de29a56a3a5fc1d45b302ac707096f33615180a48e2a4e72ab17a | day | source_record_projection | data4-hanau | s2 | 0ded64a8f2c490b254e02fe884f19b185b57310e137175a2ae8a3af63ce99372 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2e09b450-ac25-5670-a9cf-3a4e0a434bc5.json | https://web.archive.org/web/20261009/https://bebeez.eu/en/news/data4-breaks-ground-on-data-center-project-in-hanau-germany/
2e1d8fdc-f473-5df8-9053-04a2a58431d3 | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:land_area","milestone:first_operational","milestone:fully_operational","milestone:site_acquired","role:operator"] | ["8d3985c2-7777-5c6b-9a7f-fcab6c9b6a4f"] | news | First phase of Meta's Mesa data center project open; more under construction | https://ktar.com/arizona-news/mesa-data-center-mesa | KTAR News | ktar.com | source-terms-not-recorded | KTAR News | 2025-01-31 | 2026-10-09 | b4ddaee95726a15b394d36df32272b9c62c805c45a4771aacace536e66426ab8 | day | source_record_projection | meta-mesa-arizona | s5 | 690a5d65866311037933f9ddd4b78f9f474ed7fab8310573de902132c5585030 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2e1d8fdc-f473-5df8-9053-04a2a58431d3.json | https://web.archive.org/web/20261009/https://ktar.com/arizona-news/mesa-data-center-mesa
2e36f168-e466-556c-a835-1214c23e679a | ["context:source_location_identity"] | ["df2b8f33-9c46-5f6a-9853-b47474606979"] | company_disclosure | NXDATA-3 Bucharest Data Center | https://nxdata3.com/ | NXDATA SRL | nxdata3_project_pages | all-rights-reserved | NXDATA SRL | 2025-06-26T11:02:06Z | 2026-07-22T04:32:17Z | 26c2e1cc1fb21ad42575e0cf022cff148da4a13ef396abc216223385ed6827fd | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2e36f168-e466-556c-a835-1214c23e679a.json | https://web.archive.org/web/20260722043217/https://nxdata3.com/
2e44a0cd-e620-53d7-afa6-1e7a4e88411c | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:floor_area","metric:jobs_construction","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:construction_started","milestone:first_operational","milestone:other","power_source:grid","role:developer","role:government","role:utility"] | ["b19d5d3a-c2cc-5cea-9698-fe07ac125c8e"] | news | Il primo data center della città si svela | https://primamonza.it/attualita/il-primo-data-center-della-citta-si-svela/ | Prima Monza | primamonza.it | source-terms-not-recorded | Prima Monza | 2026-07-12 | 2026-10-09 | 6b037ce29aea112da6d7a6265ba3551b06d551d4923942dfeeee65e1c11eec5f | day | source_record_projection | qts-vimercate | s2 | 2eab43957ef241c6d48d076e0bf4c83579582967c2f8daf95df70b38410c03dd | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2e44a0cd-e620-53d7-afa6-1e7a4e88411c.json | https://web.archive.org/web/20261009/https://primamonza.it/attualita/il-primo-data-center-della-citta-si-svela/
2e4f8736-4982-55ba-80ce-2c981c7b4b5e | ["context:geometry_identity","context:site_distinctness"] | ["cbe9c330-13a3-5d1f-a9ba-c981c31585a7"] | company_disclosure | Cloud4Y corporate Habr original project account: DC4Y.1 Marfino / TerraBit | https://habr.com/ru/companies/cloud4y/articles/862426/ | Cloud4Y corporate blog on Habr, currently displayed as Cloud4U | europe_round26_cloud4y_marfino | no-open-license-asserted | Cloud4Y corporate blog on Habr, currently displayed as Cloud4U | 2024-12-12 | 2026-09-09T09:42:59Z | dce325440c3c5c54bb7782ae297cd01fd56c5d02c3a4f267dd2b6c77a78891c0 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2e4f8736-4982-55ba-80ce-2c981c7b4b5e.json | https://web.archive.org/web/20260909094259/https://habr.com/ru/companies/cloud4y/articles/862426/
2e7e6bb8-ba6f-5df9-8212-a0e1b93471ca | ["imported:record","milestone:first_operational","power_source:grid","role:power_supplier"] | ["8d1ed9d7-795d-55a8-b8cf-41e51579dd27"] | trade_press | Nscale signs PPA with Vattenfall for Kvandal data center Norway | https://www.datacenter-forum.com/nscale/nscale-signs-ppa-with-vattenfall-for-kvandal-data-center-norway | Datacenter Forum | www.datacenter-forum.com | source-terms-not-recorded | Datacenter Forum | 2026-06 | 2026-10-09 | 74945f429841180038e8da11359ba7f370818fbe483852edea9a51967ad74727 | month | source_record_projection | nscale-kvandal-narvik | s7 | b6e0ecf7f879e1a240a2261292267e94077cb03a765ee2aa5afb2c430537adf1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2e7e6bb8-ba6f-5df9-8212-a0e1b93471ca.json | https://web.archive.org/web/20261009/https://www.datacenter-forum.com/nscale/nscale-signs-ppa-with-vattenfall-for-kvandal-data-center-norway
2eb43ea9-9af0-573a-80a9-aa67d7210065 | ["imported:geometry","imported:record","metric:buildings","metric:power_capacity","milestone:announced","milestone:construction_started","milestone:first_operational","power_source:battery_storage","power_source:other","role:developer","role:tenant"] | ["31ee01b0-a72b-5f4a-bcc1-a13a53732efc"] | company_disclosure | Crusoe announces new 900 MW AI factory campus in Abilene, Texas to support Microsoft AI infrastructure | https://www.crusoe.ai/resources/newsroom/crusoe-announces-new-900-mw-ai-factory-campus-in-abilene-texas-to-support-microsoft-ai-infrastructure | Crusoe | www.crusoe.ai | source-terms-not-recorded | Crusoe | 2026-03-27 | 2026-10-09 | 11a79aaa38ddd15a6c449a5c37e2c9bc641419f26c7bbab3796b8c41f10a0467 | day | source_record_projection | crusoe-abilene-microsoft | s1 | b34d49d30f04664484e776e86777c3772a827321f238830f24821bcdc168ab5c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2eb43ea9-9af0-573a-80a9-aa67d7210065.json | https://web.archive.org/web/20261009/https://www.crusoe.ai/resources/newsroom/crusoe-announces-new-900-mw-ai-factory-campus-in-abilene-texas-to-support-microsoft-ai-infrastructure
2eb72a73-6d23-5336-8fa8-a86ba4aede5d | ["context:geometry_identity","context:site_distinctness"] | ["f0e92e2e-e082-5b7f-9486-fd744b5b68e6"] | company_disclosure | DPR explicitly names ERNE as ZRH12 trade partner | https://www.linkedin.com/posts/dpr-construction-inc_datacenter-vantagedatacenters-projectmilestone-activity-7417373744987426816-REKH | DPR Construction | europe_mena_round9_expansion_asia | no-open-license-asserted | DPR Construction | 2026-01-15 | 2026-09-08T23:13:15.934Z | 9835485fca3d77e7a9a92062deb728413fe7a6ee6aa300fd0a531f709ed4dfa0 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2eb72a73-6d23-5336-8fa8-a86ba4aede5d.json | https://web.archive.org/web/20260908231315/https://www.linkedin.com/posts/dpr-construction-inc_datacenter-vantagedatacenters-projectmilestone-activity-7417373744987426816-REKH
2ebacc55-15b9-5a33-b96e-3c51676e39c8 | ["context:site_distinctness","geometry"] | ["8715738f-39ac-5058-a01a-b62758b49831","e39b5191-4a78-5781-8944-24efaf944aa9"] | government_record | Australian government catalogue: official Vicmap Address endpoint | https://data.gov.au/data/api/3/action/resource_show?id=eb3cd08e-762b-4b1c-ba57-6dca4e4059f4 | Victoria Department of Transport and Planning / Vicmap | vicmap_official_address_service | CC-BY-4.0 | © State of Victoria, Department of Transport and Planning, Vicmap |  | 2026-09-08T21:12:04Z | 1c376e0ae2aea9918a6e12640db46d0afdc0819eac0355f02a375f3d3b0f8f52 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2ebacc55-15b9-5a33-b96e-3c51676e39c8.json | https://web.archive.org/web/20260908211204/https://data.gov.au/data/api/3/action/resource_show?id=eb3cd08e-762b-4b1c-ba57-6dca4e4059f4
2ec0a78b-0ec9-5148-8f48-34c62e140fb9 | ["imported:record","imported:status","metric:power_capacity","role:operator"] | ["27338e9f-68b5-58be-b981-a8a13c391bd6"] | regulatory_filing | Riot Platforms, Inc. quarterly report on Form 10-Q for the period ended June 30, 2026 | https://www.sec.gov/Archives/edgar/data/1167419/000110465926093448/riot-20260630x10q.htm | Riot Platforms, Inc. via SEC EDGAR | www.sec.gov | source-terms-not-recorded | Riot Platforms, Inc. via SEC EDGAR | 2026-08-10 | 2026-10-09 | 95f43fcc7b54ee5c8d95aea324b084e4b1e2312950895b48e9c73be64e497333 | day | source_record_projection | riot-corsicana | s5 | fd7de4e5a6744fb57de2a86a81e2ee5777f7ea63817e188b66af01f7259fc006 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2ec0a78b-0ec9-5148-8f48-34c62e140fb9.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1167419/000110465926093448/riot-20260630x10q.htm
2f03544a-3ea0-59af-bba4-5066d01054f2 | ["imported:geometry","imported:record"] | ["dd87fe4b-fdb0-5c4e-a906-70fda834e424"] | other | Louisville, Kentucky | https://en.wikipedia.org/wiki/Louisville,_Kentucky | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | d83ca0baba2bbf667db792586d232bf3dba561e3189374a01dfb0a13979548c3 | unknown | source_record_projection | powerhouse-poe-louisville-camp-ground-road | s7 | 37f733b78fae52fff6eec0b5271ca6a26fd3348359f5cf17f00c007fea8c3fd5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f03544a-3ea0-59af-bba4-5066d01054f2.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Louisville,_Kentucky
2f076364-097b-50d9-a0fe-8b96fe3d404d | ["context:site_distinctness","geometry"] | ["118053c0-38ee-5fc1-9c4d-f4875cc3c32e"] | other | OGC KML 2.2 normative coordinate reference system | https://docs.ogc.org/is/07-147r2/07-147r2.pdf | Open Geospatial Consortium | ogc_kml_coordinate_standard | no-open-license-asserted | Open Geospatial Consortium | 2008-04-14 | 2026-10-09T11:08:48.834Z | fcad423c7700c13e4a25bcf1c305ee241d8470e94128b7185c377c47d6b82b77 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f076364-097b-50d9-a0fe-8b96fe3d404d.json | https://web.archive.org/web/20261009110848/https://docs.ogc.org/is/07-147r2/07-147r2.pdf
2f20d843-ded1-5a00-a865-11fe3f8c9c66 | ["imported:record","role:developer","role:investor","role:operator"] | ["46434a5c-4980-5f79-ac83-000783b60566"] | company_disclosure | Campus de centros de datos de Calatorao | https://q.com/data-centers/calatorao/ | QTS Data Centers | q.com | source-terms-not-recorded | QTS Data Centers |  | 2026-10-09 | 37f890869b1119e3a64e55b3ccde618ba9b8a2334308f01ef3ffc6123efc2134 | unknown | source_record_projection | blackstone-calatorao | s6 | 6afcb1fbc59cf3659ffc3e2d0aa618b2fd646f74ecfb8cd734af34d6d752dadf | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f20d843-ded1-5a00-a865-11fe3f8c9c66.json | https://web.archive.org/web/20261009/https://q.com/data-centers/calatorao/
2f4528c3-705c-5b59-95c2-1b4a37661ccf | ["geometry"] | ["a072994f-1b7d-5cc8-98b7-bc79c666c6c3"] | government_record | PDOK BAG address Plimsollweg 3, Amsterdam | https://api.pdok.nl/bzk/locatieserver/search/v3_1/lookup?id=adr-26c03da8f403dfbe0de863d7b9cff485&fl=%2A | PDOK / Netherlands Cadastre, Land Registry and Mapping Agency | pdok_bag_location_server | Public-Domain-Mark-1.0 | BAG address data via PDOK; Public Domain Mark 1.0 |  | 2026-08-23 | e1bdb1cd3c3b8fbf48d8a38c7343f6794514f844e261600809edf94d66aff9e5 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f4528c3-705c-5b59-95c2-1b4a37661ccf.json | https://web.archive.org/web/20260823/https://api.pdok.nl/bzk/locatieserver/search/v3_1/lookup?id=adr-26c03da8f403dfbe0de863d7b9cff485&fl=%2A
2f63a682-a415-5963-81ef-ad0f0b71cfdd | ["context:site_distinctness","geometry"] | ["cf028790-cea6-555d-a3bb-48e08ff78f3b"] | government_record | Census public-use and geographic attribution guidance | https://www.census.gov/about/policies/citation.html | U.S. Census Bureau | americas_round31_cyrusone_aurora | no-open-license-asserted | U.S. Census Bureau |  | 2026-09-09T23:35:05.779Z | 8c27beb51562c17affb3a491b27aa5ff52fe71af46ec9cc9503332b5266d3967 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f63a682-a415-5963-81ef-ad0f0b71cfdd.json | https://web.archive.org/web/20260909233505/https://www.census.gov/about/policies/citation.html
2f78833c-a01d-51fb-9395-3b52350e1505 | ["context:site_distinctness","geometry"] | ["5e0d1954-690d-51cb-816a-88cec595f51a"] | government_record | LGL-BW INSPIRE AdminUnitName 08317065: municipality Lahr/Schwarzwald | https://owsproxy.lgl-bw.de/owsproxy/wfs/WFS_INSP_BW_Adr_Hauskoord_ALKIS?SERVICE=WFS&VERSION=2.0.0&REQUEST=GetFeature&STOREDQUERY_ID=urn:ogc:def:query:OGC-WFS::GetFeatureById&ID=AdminUnitName.08317065 | Landesamt für Geoinformation und Landentwicklung Baden-Württemberg (LGL-BW) | lgl_bw_inspire_addresses_house_coordinates_alkis | dl-de/by-2-0 | LGL-BW (2026) Datenlizenz Deutschland – Namensnennung – Version 2.0, www.lgl-bw.de |  | 2026-10-09T11:06:07.774Z | 14ee0b478dc7f031d7f43e21db5e72b8a8dc3dcbfb857eea6cf4f5d57605c366 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f78833c-a01d-51fb-9395-3b52350e1505.json | https://web.archive.org/web/20261009110607/https://owsproxy.lgl-bw.de/owsproxy/wfs/WFS_INSP_BW_Adr_Hauskoord_ALKIS?SERVICE=WFS&VERSION=2.0.0&REQUEST=GetFeature&STOREDQUERY_ID=urn:ogc:def:query:OGC-WFS::GetFeatureById&ID=AdminUnitName.08317065
2f92b229-80ee-5009-9e0b-becd1fe7b293 | ["imported:record","metric:buildings","milestone:other","power_source:natural_gas_onsite","role:developer","role:government"] | ["908ba9ce-1e84-567b-926f-8d47d4d2a7ed"] | news | Balico withdraws application to build data centers in Pittsylvania County | https://www.wvtf.org/news/2025-04-14/balico-withdraws-application-to-build-data-centers-in-pittsylvania-county | Radio IQ (WVTF) | www.wvtf.org | source-terms-not-recorded | Radio IQ (WVTF) | 2025-04-14 | 2026-10-09 | 13c272253cf001e9f5eebd912171a863edf76fcda45fc5dd183c90d7e85b87fa | day | source_record_projection | balico-pittsylvania-county | s2 | 9169c30b464bb8fd99931fce532ae356b7455ba9eb4e67c4c9c205374c151b21 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f92b229-80ee-5009-9e0b-becd1fe7b293.json | https://web.archive.org/web/20261009/https://www.wvtf.org/news/2025-04-14/balico-withdraws-application-to-build-data-centers-in-pittsylvania-county
2f975102-6fc9-5fb4-8634-9b787db77ac8 | ["imported:geometry","imported:record","metric:buildings","metric:land_area","milestone:construction_started","milestone:other","power_source:other","role:developer"] | ["55df6642-2ef8-5b72-a965-996a28bdfb24"] | company_disclosure | Information market 3 December 2025: new datacentre development in Middenmeer | https://local.microsoft.com/wp-content/uploads/2026/01/Information-market-3-december-2025.pdf | Microsoft | local.microsoft.com | source-terms-not-recorded | Microsoft | 2025-12 | 2026-10-09 | 9913c80dc544a6dfd41d3b9f59f6f6ffacd86a3554e47c51ae73082461657a5b | month | source_record_projection | microsoft-middenmeer-campus-west | s2 | bb6c8959847a730e9c12e50d71fd7ff9b9bee6a5b5f421c55bca81ca920154d7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2f975102-6fc9-5fb4-8634-9b787db77ac8.json | https://web.archive.org/web/20261009/https://local.microsoft.com/wp-content/uploads/2026/01/Information-market-3-december-2025.pdf
2fca3e43-9324-59c0-bde1-f38ea5ca4910 | ["imported:geometry","imported:record"] | ["39dca169-c304-53a7-b2a6-15a9a914e4d1"] | other | Middlesex Township, Cumberland County, Pennsylvania | https://en.wikipedia.org/wiki/Middlesex_Township,_Cumberland_County,_Pennsylvania | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 1b7ba250598a26b9123a7eea36009b00d1b3f1e9ea4601f712db1dd14bd22bf1 | unknown | source_record_projection | powerhouse-pennsylvania-digital-i-carlisle | s4 | 0c0cb2497e4d2856da48fa35254909b5de6811fcf8e5589d7ecbcec7bdadded3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2fca3e43-9324-59c0-bde1-f38ea5ca4910.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Middlesex_Township,_Cumberland_County,_Pennsylvania
2fce484d-a8d3-5fb3-be18-3cb4c685c302 | ["imported:geometry","imported:record","metric:power_capacity","milestone:site_acquired","power_source:grid","role:developer"] | ["40abc164-3033-5172-b386-52422d1513b9"] | company_disclosure | Core Scientific announces first quarter fiscal year 2026 results | https://investors.corescientific.com/news-events/press-releases/detail/136/core-scientific-announces-first-quarter-fiscal-year-2026-results | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-05-06 | 2026-10-09 | 42ef3d1263fc2f39182e6f9ac03c2db8de3fd2f8d9862b6082429b74baee581d | day | source_record_projection | core-scientific-hunt-county | s1 | f3d8655922984d28b63705187f2e9186750a7799301fc3ba8ed58403f4c0acd3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2fce484d-a8d3-5fb3-be18-3cb4c685c302.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/news-events/press-releases/detail/136/core-scientific-announces-first-quarter-fiscal-year-2026-results
2fcf925a-b3d0-5027-a685-797bf2096c0c | ["context:identity","role:owner"] | ["52b09d3a-44ac-5836-9724-7df5c69687bf"] | company_disclosure | CR4 supercomputer preparation project | https://estates.ed.ac.uk/campus-development/easter-bush/cr4-supercomputer-preparation-project | University of Edinburgh Estates | university_edinburgh_acf | all-rights-reserved | University of Edinburgh Estates | 2026-07-13 | 2026-10-13T09:53:18.039056+00:00 | 41a13c364e590a1b8abd7c75d1f67e270359a2906668650c1d65c4e625338012 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2fcf925a-b3d0-5027-a685-797bf2096c0c.json | https://web.archive.org/web/20261013095318/https://estates.ed.ac.uk/campus-development/easter-bush/cr4-supercomputer-preparation-project
2fda39d7-1494-5a7f-9b17-10910c94ee51 | ["imported:record","imported:status","milestone:other"] | ["27338e9f-68b5-58be-b981-a8a13c391bd6"] | regulatory_filing | Riot Platforms Form 8-K: second quarter 2026 results and Corsicana letter of intent | https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810x8k.htm | Riot Platforms, Inc. via SEC EDGAR | www.sec.gov | source-terms-not-recorded | Riot Platforms, Inc. via SEC EDGAR | 2026-08-10 | 2026-10-09 | 8ec7d3fea5d371fbf0a1b74e2543a624fef988480ed2f09a9cb3177e6f376831 | day | source_record_projection | riot-corsicana | s3 | fd7de4e5a6744fb57de2a86a81e2ee5777f7ea63817e188b66af01f7259fc006 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2fda39d7-1494-5a7f-9b17-10910c94ee51.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1167419/000110465926093406/riot-20260810x8k.htm
2fef070b-6567-5f52-868a-04c75e9695ba | ["imported:geometry","imported:record"] | ["fe8ac418-224e-5ac7-b342-11689bcc613e"] | other | Midlothian, Texas | https://en.wikipedia.org/wiki/Midlothian,_Texas | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 262784da66f9ba25764017cb0fcbbdee5cb3613641c9f7420ecc2c8117d49520 | unknown | source_record_projection | provident-powerhouse-grand-prairie | s5 | e49a5624d8755cc13c5a33350b318e0f68a8d3fb712e50ccc4ad0996c3573d80 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/2fef070b-6567-5f52-868a-04c75e9695ba.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Midlothian,_Texas
30404c19-2608-5791-98f7-8411cde80c3c | ["context:site_distinctness","geometry"] | ["82f20665-aa7b-51d5-b303-ddf63792d77b"] | government_record | Israel Planning Administration Xplan land-use plot 62, plan 420-1456037 | https://ags.iplan.gov.il/arcgisiplan/rest/services/PlanningPublic/Xplan/MapServer/4/query?where=num%3D%2762%27+AND+pl_number%3D%27420-1456037%27&outFields=*&returnGeometry=true&f=json | Israel Planning Administration | israel_planning_administration_xplan | no-open-license-asserted | Israel Planning Administration (iplan.gov.il) |  | 2026-09-25T22:29:06.228Z | ad9bb5dc15852f3f1e6fba356ac7c17a912b0420990ad7834138f3a8f6f6c6db | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/30404c19-2608-5791-98f7-8411cde80c3c.json | https://web.archive.org/web/20260925222906/https://ags.iplan.gov.il/arcgisiplan/rest/services/PlanningPublic/Xplan/MapServer/4/query?where=num%3D%2762%27+AND+pl_number%3D%27420-1456037%27&outFields=*&returnGeometry=true&f=json
3055e2e6-d496-5e2a-9537-aa0e26047f25 | ["context:multi_site_program","imported:record","metric:investment"] | ["b75695b9-38e3-58ec-baf2-039179ab353a"] | company_disclosure | CoreWeave Announces Multi-Billion Dollar Commitment to AI Infrastructure in Pennsylvania | https://investors.coreweave.com/news/news-details/2025/CoreWeave-Announces-Multi-Billion-Dollar-Commitment-to-AI-Infrastructure-in-Pennsylvania/default.aspx | CoreWeave | investors.coreweave.com | source-terms-not-recorded | CoreWeave | 2025-07-15 | 2026-10-09 | 193bd3bbbc77a9e72fafc48c2bd628cf4de8e3fcf39ffd47700de7e67b743ca6 | day | source_record_projection | coreweave-lancaster-pennsylvania | s6 | 3da7b985dea6aab54b6d7610b08c127892b84b6825d60e166f63e4d3b65a78de | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3055e2e6-d496-5e2a-9537-aa0e26047f25.json | https://web.archive.org/web/20261009/https://investors.coreweave.com/news/news-details/2025/CoreWeave-Announces-Multi-Billion-Dollar-Commitment-to-AI-Infrastructure-in-Pennsylvania/default.aspx
306c783a-a273-51e4-a2c2-9c40e2912596 | ["announcement"] | ["02a9ee88-08e5-58fd-b715-488b3ee903a3"] | company_disclosure | JERA, Dell and RHAELM announce first AI infrastructure project at Chiba Thermal Power Station | https://www.jera.co.jp/news/information/20261001_2535 | JERA | jera_official | all-rights-reserved | JERA | 2026-10-01 | 2026-10-13T17:14:10.758503+00:00 | bdef802fc144c1e7fd6582b2aee2a5cbdfd40461aa2ae1fd71beaff3e9afd29f | day | sha256_exact_content_decoded_response_bytes |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/306c783a-a273-51e4-a2c2-9c40e2912596.json | https://web.archive.org/web/20261013171410/https://www.jera.co.jp/news/information/20261001_2535
306ee880-6ae1-5119-8eed-6b728cca33c0 | ["context:site_distinctness","geometry"] | ["26ebe837-0ec5-5973-a729-656b1b4ce011"] | government_record | County web map binds the public Parcels_View service | https://www.arcgis.com/sharing/rest/content/items/b6f6de3d2902468093e60cd0d28c2908/data?f=pjson | Coshocton County GIS | americas_round20_conesville | no-open-license-asserted | Coshocton County GIS |  | 2026-09-09T06:01:19.142Z | de5378f0747448a329823eb867302cd004c5e11e770d428e0317f83372d2029d | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/306ee880-6ae1-5119-8eed-6b728cca33c0.json | https://web.archive.org/web/20260909060119/https://www.arcgis.com/sharing/rest/content/items/b6f6de3d2902468093e60cd0d28c2908/data?f=pjson
30a8faac-6bf4-5f82-80b3-159eed56720e | ["imported:geometry","imported:record","metric:land_area","milestone:site_acquired","power_source:grid","role:developer","role:owner"] | ["9dbfd718-7b41-58b1-bb46-0138b96aeca8"] | company_disclosure | TeraWulf Expands Digital and Power Infrastructure Portfolio with Strategic Acquisitions in Kentucky and Maryland | https://investors.terawulf.com/news-events/press-releases/detail/129/terawulf-expands-digital-and-power-infrastructure-portfolio-with-strategic-acquisitions-in-kentucky-and-maryland | TeraWulf | investors.terawulf.com | source-terms-not-recorded | TeraWulf | 2026-02-02 | 2026-10-09 | 794aa7ac7eee14a2147b480adfd8d58d37b6c2820061b4b72a658a708fa7064d | day | source_record_projection | terawulf-justified-data-hawesville | s1 | 7db40d44894208f4e792a562ea9403ac682100e2515b0c7715e1d07e0ca4a4e7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/30a8faac-6bf4-5f82-80b3-159eed56720e.json | https://web.archive.org/web/20261009/https://investors.terawulf.com/news-events/press-releases/detail/129/terawulf-expands-digital-and-power-infrastructure-portfolio-with-strategic-acquisitions-in-kentucky-and-maryland
31000e3f-77ed-5366-8b43-521bfa77331d | ["context:geometry_identity","context:site_distinctness"] | ["b9ccc1e7-c2da-5822-82bc-b20be7d43dfe"] | government_record | City Fira data-center piling notice fixes exact parcel and address | https://www.lappeenranta.fi/MFiles/MFFiles/Open?fileId=169510&objectId=123121&objectTypeId=0 | City of Lappeenranta | europe_round5_nebius_pajarila | no-open-license-asserted | City of Lappeenranta | 2026-08-12 | 2026-09-08T21:37:00Z | b2a4fce8fb20137c8ad3d35269aadfd436c6debbc356abb2050b1a7db39c79e2 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/31000e3f-77ed-5366-8b43-521bfa77331d.json | https://web.archive.org/web/20260908213700/https://www.lappeenranta.fi/MFiles/MFFiles/Open?fileId=169510&objectId=123121&objectTypeId=0
3106fe02-8768-5ca1-a84c-a17e6f304086 | ["context:geometry_identity","context:site_distinctness"] | ["c9b6bff7-09a3-599b-9c8c-49243461c0fb"] | company_disclosure | Project participant corroborates actual foundation milestone | https://www.amperio.ch/de/technologiezentrum-laufenburg-ki-rechenzentrum/ | Amperio | europe_round5_flexbase | no-open-license-asserted | Amperio | 2026-06-04T13:54:45Z | 2026-09-08T21:57:24Z | 962c4c6dc5187cb49b7d7002bb5442a9455b6fe29735b2b22e1b8b1b2157cd66 | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3106fe02-8768-5ca1-a84c-a17e6f304086.json | https://web.archive.org/web/20260908215724/https://www.amperio.ch/de/technologiezentrum-laufenburg-ki-rechenzentrum/
3142d580-0924-5470-ac67-7096693a897e | ["context:geometry_identity","context:site_distinctness"] | ["8dbc82d0-1a4d-5d8e-955e-c5e4973ea19e"] | government_record | Town of Parker permit row binds Flexential DEN12 to 15255 Compark Boulevard | https://www.parkerco.gov/Archive/ViewFile/Item/7258 | Town of Parker | americas_round11_flexential_parker | no-open-redistribution-license-asserted | Town of Parker |  | 2026-09-09T00:27:17.702Z | c7f65a3d9148133c80402ffde8cfc3ca45f9f5358ce4204306c8dc006e0a3095 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3142d580-0924-5470-ac67-7096693a897e.json | https://web.archive.org/web/20260909002717/https://www.parkerco.gov/Archive/ViewFile/Item/7258
3144acd5-1519-555c-941d-ba0e49895219 | ["imported:record","metric:power_capacity","milestone:other","role:developer"] | ["3fe8297a-147b-56fe-a5a6-6ae165798506"] | company_disclosure | AirTrunk breaks ground on 40+MW phase of TOK1, Japan's largest hyperscale data centre campus. | https://airtrunk.com/airtrunk-breaks-ground-on-40mw-phase-of-tok1-japans-largest-hyperscale-data-centre-campus/ | AirTrunk | airtrunk.com | source-terms-not-recorded | AirTrunk | 2025-06-19 | 2026-10-09 | 64b01f11061b6de2f05d85ac1c73b5662c5be94f770c61cc8d5248c416675317 | day | source_record_projection | airtrunk-tok1-inzai | s3 | 4c28605b649ccf51780503b5829856089f31072a900b71c243bb8f4e88762814 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3144acd5-1519-555c-941d-ba0e49895219.json | https://web.archive.org/web/20261009/https://airtrunk.com/airtrunk-breaks-ground-on-40mw-phase-of-tok1-japans-largest-hyperscale-data-centre-campus/
31471ce2-024f-586a-9689-ede2521339fd | ["imported:geometry","imported:record"] | ["a95db60b-fb99-5f16-ad4a-c763e4714041"] | other | Kansas City, Missouri | https://en.wikipedia.org/wiki/Kansas_City,_Missouri | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 0be267d63abfe787f09af8f04b84571a3b0163dabe7fe14c5aab41dfb4f688cb | unknown | source_record_projection | lambda-kansas-city | s2 | 06a230bf76ea131b0cc128f6fbd6ab1c196fffdbc6c4dafe3e65d10695f74a6f | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/31471ce2-024f-586a-9689-ede2521339fd.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Kansas_City,_Missouri
314d2a34-7e3f-5faa-8251-c7eda8caadde | ["imported:geometry","imported:record","metric:jobs_construction","metric:jobs_permanent","metric:land_area","metric:power_capacity","milestone:construction_started","milestone:first_operational","power_source:natural_gas_onsite","role:developer","role:power_supplier","role:utility"] | ["fbbfee97-55a0-5a4e-b000-282ff02a8a39"] | regulatory_filing | Beacon AI Centers - Indus Project: Initial Project Description | https://iaac-aeic.gc.ca/050/documents/p90121/164415E.pdf | Indus Power Generation LP via Impact Assessment Agency of Canada registry | iaac-aeic.gc.ca | source-terms-not-recorded | Indus Power Generation LP via Impact Assessment Agency of Canada registry | 2025-12-29 | 2026-10-09 | 85eb073f3143231f9c7f48b60cfce959e8bfb4730d9b1e6dca2bedeb0d60b065 | day | source_record_projection | beacon-ai-centers-indus | s1 | 31c79930812626de82d850ddcfbca7999819a420e79842f3f49e0e8817661aa2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/314d2a34-7e3f-5faa-8251-c7eda8caadde.json | https://web.archive.org/web/20261009/https://iaac-aeic.gc.ca/050/documents/p90121/164415E.pdf
315dce68-5452-5a14-aa7c-4ea81b393779 | ["context:geometry_identity","context:site_distinctness"] | ["867d91cb-7a17-59db-a92e-4a50a499f54f","b3656b35-f3ad-5119-8918-ac5237bf2a7f"] | company_disclosure | Microsoft Lévis Charny project identity and scope | https://local.microsoft.com/blog/levis-datacenter-project-updates/ | Microsoft | americas_round30_microsoft_quebec | no-open-license-asserted | Microsoft |  | 2026-09-09T11:54:41.972Z | 55d7b7c536ff1aa6d5f02a15c0adec5c70992543af06b3a588b0096a38cb091c | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/315dce68-5452-5a14-aa7c-4ea81b393779.json | https://web.archive.org/web/20260909115441/https://local.microsoft.com/blog/levis-datacenter-project-updates/
31cbba68-5623-5192-9250-ed5fa4e62c21 | ["context:site_distinctness","geometry"] | ["d5b84301-4f54-5958-a0d1-fd2c5a72cc5b"] | government_record | Official exact address query delivered in the map service's NAD83 CRS | https://gis.palmcoast.gov/hosting/rest/services/External/FlaglerCountyParcels/MapServer/0/query?f=json&where=ADDRESS%20%3D%20%271109%20TOWN%20CENTER%20BLVD%27&outFields=OBJECTID%2CPT_ID%2CADDRESS%2CADDR_NUM%2CST_NAME%2CST_TYPE%2CPO_CITY%2CSTATE%2CZIPCODE%2CPARCEL_ID%2CCONF%2CStatus&returnGeometry=true&outSR=2236 | City of Palm Coast | americas_round28_palm_coast | no-open-license-asserted | City of Palm Coast |  | 2026-09-09T10:40:15.877Z | 65468e0a8aa283bf78edfdac52871d9f875c8fe1fd4fdcff59ce84c281c5761b | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/31cbba68-5623-5192-9250-ed5fa4e62c21.json | https://web.archive.org/web/20260909104015/https://gis.palmcoast.gov/hosting/rest/services/External/FlaglerCountyParcels/MapServer/0/query?f=json&where=ADDRESS%20%3D%20%271109%20TOWN%20CENTER%20BLVD%27&outFields=OBJECTID%2CPT_ID%2CADDRESS%2CADDR_NUM%2CST_NAME%2CST_TYPE%2CPO_CITY%2CSTATE%2CZIPCODE%2CPARCEL_ID%2CCONF%2CStatus&returnGeometry=true&outSR=2236
31feb8fa-3920-5576-aa53-b7ac0b67e434 | ["physical_status"] | ["c160d8d5-7572-53c2-8051-cd7990b1f771"] | company_disclosure | ODATA DC SP04 Phase 2 site mobilization | https://www.linkedin.com/embed/feed/update/urn:li:activity:7473377620018077696 | ODATA - An Aligned Data Centers Company | odata_linkedin_company_posts | all-rights-reserved | ODATA - An Aligned Data Centers Company | 2026-06-18 | 2026-07-21T19:42:31Z | fb73fcb98ed6b67d10bc52d27795e4d444ab10def6d00eeccf74349aaf723458 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/31feb8fa-3920-5576-aa53-b7ac0b67e434.json | https://web.archive.org/web/20260721194231/https://www.linkedin.com/embed/feed/update/urn:li:activity:7473377620018077696
32183336-78be-55f3-9961-9c0095ff0135 | ["context:geometry_identity","context:site_distinctness"] | ["c23fe40c-0685-5cee-8fab-9c08575e6b27"] | government_record | Later DC2 fit-out inspections retained only as successor context | https://amandacommerce.auroragov.org/BuildingPlanReviewPub/MyProjects/Inspections.aspx | City of Aurora, Colorado | americas_round24_qts_aurora | no-open-license-asserted | City of Aurora, Colorado |  | 2026-09-09T08:20:48.532634Z | fa062e1c19024718f3fe0d878b3abee3a6e6daf33c71689f813ef3159f7cfbaf | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/32183336-78be-55f3-9961-9c0095ff0135.json | https://web.archive.org/web/20260909082048/https://amandacommerce.auroragov.org/BuildingPlanReviewPub/MyProjects/Inspections.aspx
322acf52-c4b4-5ba6-9083-b2bb02a7ab87 | ["context:site_distinctness","geometry"] | ["f595ca9f-e584-5dcb-bf76-38b346f6e4aa"] | government_record | TxGIO StratMap address point in native Web Mercator: 11786 COUNTY ROAD 209 | https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0/query?where=full_addr%3D%2711786%20COUNTY%20ROAD%20209%27%20AND%20county%3D%27Winkler%27&outFields=*&returnGeometry=true&f=json | Texas Geographic Information Office (TxGIO), Texas Water Development Board | txgio_stratmap_address_points | public-use-as-is | Texas Geographic Information Office, StratMap Address Points; 9-1-1 source authority CSEC |  | 2026-09-25T22:36:30.399Z | 9d4af87af48e3fe87275465e74ba89d2b2f062086f756823805ce3f7861c34be | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/322acf52-c4b4-5ba6-9083-b2bb02a7ab87.json | https://web.archive.org/web/20260925223630/https://feature.geographic.texas.gov/arcgis/rest/services/Address_Points/stratmap_address_points_48_most_recent/MapServer/0/query?where=full_addr%3D%2711786%20COUNTY%20ROAD%20209%27%20AND%20county%3D%27Winkler%27&outFields=*&returnGeometry=true&f=json
326814ae-f382-57c4-8230-0b68e73f75f0 | ["context:geometry_identity","context:site_distinctness"] | ["43ded2e8-5dcf-5174-b553-a4a04aaeebe3"] | company_disclosure | MERLIN Lisbon campus identity | https://www.merlinproperties.com/en/assets/data-center-lisboa/ | MERLIN Properties | merlin_edged_official_round4 | all-rights-reserved | MERLIN Properties | 2022-06-09T07:05:45Z | 2026-09-08T20:44:09Z | 3673e320465c84f00fb7d97ddf462308d86f531a06a3d88f86f8f33fff4fdf1d | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/326814ae-f382-57c4-8230-0b68e73f75f0.json | https://web.archive.org/web/20260908204409/https://www.merlinproperties.com/en/assets/data-center-lisboa/
3285e666-f6bb-575c-9571-01ed3c5bcf8f | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["726d6e35-8381-58ae-8dcd-eeb9ae23583a"] | company_disclosure | Goodman FY26 results: HKG10 Tsuen Wan industrial-building conversion in the data-centre WIP cohort at 30 June 2026 | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | Goodman Group | goodman_group_investor_presentations | all-rights-reserved | Goodman Group | 2026-08-19 | 2026-10-09T11:19:16.843Z | 892c9d069276912a13d2ff100ff3260b1c2d26874693d644e0d34dce3a7d809d | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3285e666-f6bb-575c-9571-01ed3c5bcf8f.json | https://web.archive.org/web/20261009111916/https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1
328eac52-bc7d-5b77-bba6-282860b8b49a | ["context:geometry_identity","context:site_distinctness"] | ["cf028790-cea6-555d-a3bb-48e08ff78f3b"] | company_disclosure | CyrusOne identifies CHI1-CHI3 as one Aurora campus | https://www.cyrusone.com/data-centers/north-america/aurora-il | CyrusOne | americas_round31_cyrusone_aurora | no-open-license-asserted | CyrusOne |  | 2026-09-09T23:35:03.180Z | e0ff993efc3351b7d681c7ff18f038fc3b6eeca52b2ccac04d2cf8e31ab0d06c | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/328eac52-bc7d-5b77-bba6-282860b8b49a.json | https://web.archive.org/web/20260909233503/https://www.cyrusone.com/data-centers/north-america/aurora-il
32ac4772-10ce-539c-88d9-4d419bff74ef | ["imported:record","metric:buildings","metric:floor_area","metric:land_area","metric:power_capacity","milestone:first_operational","milestone:fully_operational"] | ["2bd78b04-9314-5aa8-ac32-ef30e111bc2e"] | company_disclosure | QTS Data Center Campus Cambois | https://www.corgan.com/projects/qts-data-center-campus-cambois | Corgan | www.corgan.com | source-terms-not-recorded | Corgan |  | 2026-10-09 | 0475b3983f63af7f6156d5cd7c8e0997815b9b8602d65575a96dedf5e229f36e | unknown | source_record_projection | qts-cambois-blyth | s5 | 0b723f64ffa9d6efd917b3e9c656e1369d367d1a946f7568d998ed9ce8cd7927 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/32ac4772-10ce-539c-88d9-4d419bff74ef.json | https://web.archive.org/web/20261009/https://www.corgan.com/projects/qts-data-center-campus-cambois
32ac65f1-30f1-5995-a23c-95d956f6cd35 | ["context:geometry_identity","context:site_distinctness"] | ["e8a1add0-19fb-5196-ae75-34353e7d580b"] | company_disclosure | Firmus Tasmania community hub: one current Launceston site and two prospective sites | https://firmus.co/tasmaniancommunity | Firmus Technologies | europe_round31_firmus_st_leonards | no-open-license-asserted | Firmus Technologies |  | 2026-09-09T23:35:02.605Z | dc3ebe9acac83ece704f9afac75836db9d2577bd258d374b3596ca20de8c929f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/32ac65f1-30f1-5995-a23c-95d956f6cd35.json | https://web.archive.org/web/20260909233502/https://firmus.co/tasmaniancommunity
33149068-8232-51ab-9404-1ce6278b8750 | ["imported:record","imported:status","metric:jobs_construction","metric:jobs_permanent","milestone:other","role:developer","role:investor","role:tenant"] | ["d63cbbf2-d501-5bf8-83d4-befc76c4bb39"] | company_disclosure | DataVita secures £300 million for data centre rollout in Scotland's AI Growth Zone, with backing from National Wealth Fund and major lenders | https://blog.datavita.co.uk/blog/datavita-secures-funding-data-centre-expansion | DataVita | blog.datavita.co.uk | source-terms-not-recorded | DataVita | 2026-08-18 | 2026-10-09 | 6d7d4cc9061019d48e28e49b7c1a33133105bfc33887a53d7ae3ea42738d9700 | day | source_record_projection | datavita-lanarkshire-ai-growth-zone | s4 | e50f7a7877930b30a9f0bf4dd7d58e55b956794c069b49ab3b9dd7d0aece56cb | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/33149068-8232-51ab-9404-1ce6278b8750.json | https://web.archive.org/web/20261009/https://blog.datavita.co.uk/blog/datavita-secures-funding-data-centre-expansion
331ffac3-a2e5-5120-b0f7-a7fac2e79d12 | ["imported:geometry","imported:record","imported:status","metric:power_capacity","power_source:grid","role:developer"] | ["6799aac4-c4f8-5902-b8ae-2fffb6fa893d"] | regulatory_filing | Bitdeer reports unaudited financial results for the second quarter of 2026 (Form 6-K, Exhibit 99.1) | https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm | Bitdeer Technologies Group via SEC EDGAR | www.sec.gov | source-terms-not-recorded | Bitdeer Technologies Group via SEC EDGAR | 2026-08-10 | 2026-10-09 | c31770395350de001348390de07d937b25b68d66ab78bc541b894f62a65c8c3f | day | source_record_projection | bitdeer-clarington-ohio | s4 | 10a76766bcfe1bdddcc1859f59d9d9215325db951e58914f679613022357efa3 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/331ffac3-a2e5-5120-b0f7-a7fac2e79d12.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1899123/000121390026086938/ea030131301ex99-1.htm
3325e1c3-aaa7-5316-9737-22d7b08edb1a | ["context:site_distinctness","geometry"] | ["c23fe40c-0685-5cee-8fab-9c08575e6b27"] | government_record | Native DC2 address geometry and separate DC1 occupancy context | https://ags.auroragov.org/aurora/rest/services/OpenData/MapServer/9/query?f=json&where=ADDRESS+IN+%28%271160+N+GUN+CLUB+RD%27%2C%271140+N+GUN+CLUB+RD%27%2C%271100+N+GUN+CLUB+RD%27%29&outFields=OBJECTID%2CADDRESS%2CADDRESS_TYPE%2CADDRESS_STATUS%2CADDRESS_ID%2CPROPERTYRSN%2CCO_DATE%2CCO_ISSUED%2CSUBDIVISION_NAME%2CSUBDIVISION_CASE_NUMBER%2CLOT%2CBLOCK%2CHYPERLINK%2CPOINT_X%2CPOINT_Y%2CLATITUDE%2CLONGITUDE&returnGeometry=true | City of Aurora, Colorado | americas_round24_qts_aurora | no-open-license-asserted | City of Aurora, Colorado |  | 2026-09-09T07:49:02.337722+00:00 | 976d9d3b7def40245b3538ed1edb63ecf9f6625a01506501b5407e4609e99fc5 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3325e1c3-aaa7-5316-9737-22d7b08edb1a.json | https://web.archive.org/web/20260909074902/https://ags.auroragov.org/aurora/rest/services/OpenData/MapServer/9/query?f=json&where=ADDRESS+IN+%28%271160+N+GUN+CLUB+RD%27%2C%271140+N+GUN+CLUB+RD%27%2C%271100+N+GUN+CLUB+RD%27%29&outFields=OBJECTID%2CADDRESS%2CADDRESS_TYPE%2CADDRESS_STATUS%2CADDRESS_ID%2CPROPERTYRSN%2CCO_DATE%2CCO_ISSUED%2CSUBDIVISION_NAME%2CSUBDIVISION_CASE_NUMBER%2CLOT%2CBLOCK%2CHYPERLINK%2CPOINT_X%2CPOINT_Y%2CLATITUDE%2CLONGITUDE&returnGeometry=true
3373b0d6-8b9e-501a-b14a-17562f635a14 | ["imported:record","imported:status","metric:power_capacity","milestone:other","role:developer"] | ["4278fea3-2c31-5512-87d1-d713170569e2"] | company_disclosure | G42 Provides Update on Construction of Stargate UAE AI Infrastructure Cluster | https://www.prnewswire.com/news-releases/g42-provides-update-on-construction-of-stargate-uae-ai-infrastructure-cluster-302586430.html | G42 via PR Newswire | www.prnewswire.com | source-terms-not-recorded | G42 via PR Newswire | 2025-10-16 | 2026-10-09 | 3da1d44e52141a056d13769b8a8f1adb6704c1186210efcd0d1f48e1af6a54b4 | day | source_record_projection | stargate-uae | s3 | fe5de8dd0f71cb9deccf394cd387a6f464e3e2b89be722d08e474a78600b11cf | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3373b0d6-8b9e-501a-b14a-17562f635a14.json | https://web.archive.org/web/20261009/https://www.prnewswire.com/news-releases/g42-provides-update-on-construction-of-stargate-uae-ai-infrastructure-cluster-302586430.html
33790c31-2bee-5340-957a-5ccbe793994e | ["imported:record","imported:status","metric:land_area","milestone:other","milestone:zoning_approved","role:government"] | ["fbbfee97-55a0-5a4e-b000-282ff02a8a39"] | government_record | Beacon AI Hub - Thermal Power Plant Application | https://www.rockyview.ca/build-plan-and-develop/planning/planning-projects-underway/beacon-ai-hub-area-structure-plan | Rocky View County | www.rockyview.ca | source-terms-not-recorded | Rocky View County |  | 2026-10-09 | c3129e00a44cb415c27f2a89ee7e2dbd433dbed336386231cc2d7923a742d33d | unknown | source_record_projection | beacon-ai-centers-indus | s5 | 31c79930812626de82d850ddcfbca7999819a420e79842f3f49e0e8817661aa2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/33790c31-2bee-5340-957a-5ccbe793994e.json | https://web.archive.org/web/20261009/https://www.rockyview.ca/build-plan-and-develop/planning/planning-projects-underway/beacon-ai-hub-area-structure-plan
33a59a67-e62e-5348-8fbb-5fc44302a000 | ["imported:geometry","imported:record","imported:status","metric:floor_area","metric:investment","metric:land_area","metric:power_capacity","milestone:first_operational","milestone:zoning_approved","role:developer"] | ["4a2a09d1-1ace-5ff8-a80f-89996cda5799"] | trade_press | Colorado Developer Secures $3B For Data Center Campus North Of Austin | https://www.bisnow.com/news/austin-san-antonio/data-center/sustainable-developer-bringing-data-center-campus-to-temple-134759 | Bisnow | www.bisnow.com | source-terms-not-recorded | Bisnow | 2026-05-29 | 2026-10-09 | 671bcb3cc48d54a9e7c870aa4aa6cbe554e46c166170b7945c15572ab2442383 | day | source_record_projection | rowan-project-temple | s4 | ac6a9ba056d88fd802fe69828988dcb7d1f1434be4bf4235730b1b47e5aeeacb | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/33a59a67-e62e-5348-8fbb-5fc44302a000.json | https://web.archive.org/web/20261009/https://www.bisnow.com/news/austin-san-antonio/data-center/sustainable-developer-bringing-data-center-campus-to-temple-134759
33d8c10b-d2f7-59d5-b1de-bb27cd65ffc4 | ["context:site_distinctness","geometry"] | ["d6a6d399-4580-54f8-80de-1dc0854e4699"] | government_record | Butler County Auditor GIS map request disclaimer | https://cms3.revize.com/revize/butlercountyauditor/Documents/Real%20Estate/GIS%20Maps/2024_GISMap_Request_Form_p.pdf | Butler County Auditor Office | root_round32_trenton | no-open-license-asserted | Butler County Auditor Office |  | 2026-09-10T00:06:00.157Z | 083ac55f10112e74f9c243af659b2d166105490c69bedfb9265cd935ab77aded | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/33d8c10b-d2f7-59d5-b1de-bb27cd65ffc4.json | https://web.archive.org/web/20260910000600/https://cms3.revize.com/revize/butlercountyauditor/Documents/Real%20Estate/GIS%20Maps/2024_GISMap_Request_Form_p.pdf
34034aa1-f108-544c-8a94-2dd5f9244826 | ["context:site_distinctness","geometry"] | ["118053c0-38ee-5fc1-9c4d-f4875cc3c32e"] | government_record | 'raiden kml.kml' attached to CAF/226849/2025: Raiden Plot Boundary polygon, Turbhe MIDC | https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=40829&refId=123711148&refType=caf&uuid=82bd367c-609c-46be-ab68-0d537b8e1d8e&version=1.0 | Raiden Infotech India Private Limited, proponent; Ministry of Environment, Forest and Climate Change, India (PARIVESH portal), host | india_parivesh_public_environmental_proposals | no-open-license-asserted | Raiden Infotech India Private Limited, proponent; Ministry of Environment, Forest and Climate Change, India (PARIVESH portal), host |  | 2026-10-09T10:59:32.242Z | 67fb2d78e7362381946524b7aacd2b494099756aae73bb6981a29cdb29d8d42e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34034aa1-f108-544c-8a94-2dd5f9244826.json | https://web.archive.org/web/20261009105932/https://parivesh.nic.in/dms/okm/downloadDocument?docTypemappingId=40829&refId=123711148&refType=caf&uuid=82bd367c-609c-46be-ab68-0d537b8e1d8e&version=1.0
345b448f-5907-513d-a752-69d014e7aa34 | ["imported:geometry","imported:record","metric:land_area","milestone:announced","milestone:other","power_source:grid","role:developer","role:government","role:investor","role:utility"] | ["8560b48f-07cb-54c8-8b8d-163dc196caee"] | trade_press | New $17B Project Continues Data Center Surge In Small Virginia County | https://www.bisnow.com/news/national/data-center/17b-campus-continues-data-center-surge-in-small-virginia-county-129918 | Bisnow | www.bisnow.com | source-terms-not-recorded | Bisnow | 2025-06-25 | 2026-10-09 | eac6f0202e09635efcdf0d74bbb6a20b1ae22ddb71b0e772ee7c0080cb37639e | day | source_record_projection | edgecore-louisa-county | s3 | 4818450653b73fabd55a50a76634714a88cddcb9cc5097779c29293d08ddf993 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/345b448f-5907-513d-a752-69d014e7aa34.json | https://web.archive.org/web/20261009/https://www.bisnow.com/news/national/data-center/17b-campus-continues-data-center-surge-in-small-virginia-county-129918
3464cc5f-4960-5039-a630-b4fdca2f4fed | ["imported:geometry","imported:record","imported:status","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:hardware_supplier","role:operator","role:owner","role:tenant"] | ["b74385b8-0724-5b4d-b192-4aa5a1c45885"] | regulatory_filing | IREN Ltd Form 10-K for the fiscal year ended June 30, 2026 | https://www.sec.gov/Archives/edgar/data/1878848/000187884826000052/iren-20260630.htm | U.S. Securities and Exchange Commission (IREN filing) | www.sec.gov | source-terms-not-recorded | U.S. Securities and Exchange Commission (IREN filing) | 2026-08-27 | 2026-10-09 | dbb1cee13c74605a53df298963ae9ce0216eccb165d9c1af49ba8c0ac428281c | day | source_record_projection | iren-childress | s2 | 2e84178afc0deb7b62de37b97e373907adbcd669801951165b008127658131de | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3464cc5f-4960-5039-a630-b4fdca2f4fed.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1878848/000187884826000052/iren-20260630.htm
34892ffa-c4fb-555f-844d-cc3736146fc2 | ["imported:record","metric:investment","metric:power_capacity","milestone:construction_started","power_source:other","role:builder","role:developer","role:government","role:investor","role:power_supplier"] | ["64f6ec20-7a91-530a-85f2-7748b0e320f8"] | trade_press | Under the hood of SKT's Ulsan AI datacentre | https://www.telecomtv.com/content/ai/under-the-hood-of-skt-s-ulsan-ai-datacentre-53720/ | TelecomTV | www.telecomtv.com | source-terms-not-recorded | TelecomTV | 2025-08-29 | 2026-10-09 | 37db69c75399659fc842cac33ab31fd8436e5a4e41abe509f02916a9f4a05994 | day | source_record_projection | sk-aws-ulsan-ai-data-center | s4 | efedefcd9b321f667a41f68c35a639ab91f3254b2e9d1437d44ee3298e289fd6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34892ffa-c4fb-555f-844d-cc3736146fc2.json | https://web.archive.org/web/20261009/https://www.telecomtv.com/content/ai/under-the-hood-of-skt-s-ulsan-ai-datacentre-53720/
34a0d6a4-02e3-57e3-8b39-6c7e64363b3a | ["geometry"] | ["9283d3fe-3789-54c7-abf4-8bb757e29835"] | government_record | Census Public_AR_Current match for 12000 Jefferson Avenue | https://geocoding.geo.census.gov/geocoder/ | United States Census Bureau | us_census_geocoder | public-domain-us-government | United States Census Bureau |  | 2026-08-23 | b1b7f05939322797233febc86f63dd51296c13424a3d2f32d13fdbee4087b2a6 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34a0d6a4-02e3-57e3-8b39-6c7e64363b3a.json | https://web.archive.org/web/20260823/https://geocoding.geo.census.gov/geocoder/
34abf7af-e181-5f64-a9ec-6701337d4344 | ["context:site_distinctness","geometry"] | ["14a67880-da37-5f59-a2cf-2322bbf778d7"] | company_disclosure | Google Maps JavaScript coordinate semantics: WGS84 | https://developers.google.com/maps/documentation/javascript/coordinates | Google | google_maps_javascript_documentation | CC-BY-4.0 | Google |  | 2026-09-09T08:58:34.729Z | e521e224a05644311c45f5762d23f943a9bceed25cbbc25ba1b6776bbb1d96f6 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34abf7af-e181-5f64-a9ec-6701337d4344.json | https://web.archive.org/web/20260909085834/https://developers.google.com/maps/documentation/javascript/coordinates
34c18a94-daee-58ac-a05d-5e7953ceeffb | ["imported:record","metric:power_capacity","milestone:announced","role:developer"] | ["8aa8e9f5-915e-51f6-bc08-463822cf16f9"] | company_disclosure | Hut 8 Signs 15-Year, 245 MW AI Data Center Lease at River Bend Campus with Total Contract Value of $7.0 Billion | https://www.hut8.com/news-insights/press-releases/hut-8-signs-15-year-245-mw-ai-data-center-lease-at-river-bend-campus-with-total-contract-value | Hut 8 | www.hut8.com | source-terms-not-recorded | Hut 8 | 2025-12-17 | 2026-10-09 | c876fc1fb02d7cc5c17fa5313806a921e77c266c13bcd9c851b0afca221bb7fc | day | source_record_projection | hut8-river-bend-louisiana | s1 | fb7eeaf52bb6e7789effaf24b3ee0bb7e31922a38047e56ede8f20f89e9b204a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34c18a94-daee-58ac-a05d-5e7953ceeffb.json | https://web.archive.org/web/20261009/https://www.hut8.com/news-insights/press-releases/hut-8-signs-15-year-245-mw-ai-data-center-lease-at-river-bend-campus-with-total-contract-value
34de5b68-3131-58d5-b992-614a9da691b0 | ["imported:geometry","imported:record","metric:floor_area","metric:investment","milestone:announced","power_source:grid","role:builder","role:developer","role:power_supplier","role:utility"] | ["1f430ea1-a0e6-5a91-b3e7-3f002b331cf6"] | company_disclosure | Hello, Lebanon! | https://datacenters.atmeta.com/2026/02/hello-lebanon/ | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms | 2026-02-11 | 2026-10-09 | df42fe12ee38ec944ee5be9a29da22b449dc504212011c47560d4823c7ddfb80 | day | source_record_projection | meta-lebanon-indiana | s2 | 03e9051a50c26f3cef0e0f42bff8b4b98654c271a046060ae67fac417f04952b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34de5b68-3131-58d5-b992-614a9da691b0.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/2026/02/hello-lebanon/
34f3ebce-3c8f-5366-ba0d-990f25bda04e | ["imported:geometry","imported:record","imported:status","metric:investment","metric:power_capacity"] | ["7d936c4e-29f2-592f-984b-61f5d6367fc8"] | news | PHOTOS: Construction continues on Related Digital's Saline Township data center | https://spectrumlocalnews.com/mi/michigan/news/2026/08/02/related-digital-saline-township-data-center-construction-progress | Spectrum News | spectrumlocalnews.com | source-terms-not-recorded | Spectrum News | 2026-08-02 | 2026-10-09 | 3161c6b160e251c938240be8b48c27ffd0ace84e40abadda8ae9e0ac4e0a2524 | day | source_record_projection | openai-stargate-saline-township | s4 | 94ad5442cd8eb9d4cd6dc401ca97cd335b9bce574ef89935df559b03d300316f | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34f3ebce-3c8f-5366-ba0d-990f25bda04e.json | https://web.archive.org/web/20261009/https://spectrumlocalnews.com/mi/michigan/news/2026/08/02/related-digital-saline-township-data-center-construction-progress
34f860f9-9746-5f72-9b8f-9cb414f9cb9c | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:jobs_construction","metric:power_capacity","milestone:first_operational","power_source:grid","role:builder","role:developer","role:government"] | ["0b37ac4d-93f2-559b-a6ec-f5a12938681a"] | company_disclosure | Bell AI Fabric provides construction update in Saskatchewan, announces $1 million mental health commitment | https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-provides-construction-update-in-saskatchewan-announces-1-million-mental-health-commitment | BCE Inc. | www.bce.ca | source-terms-not-recorded | BCE Inc. | 2026-10-01 | 2026-10-09 | 7c2c6720e34101b3d39a54537c1a816432b2eab6bcd2507edf681ad0c2df5277 | day | source_record_projection | bell-ai-fabric-sherwood-saskatchewan | s2 | 16c96149f34f8e8f77b8c0c17353148d280b27c5336b316bd6a5419437e7acef | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/34f860f9-9746-5f72-9b8f-9cb414f9cb9c.json | https://web.archive.org/web/20261009/https://www.bce.ca/news-and-media/newsroom?article=bell-ai-fabric-provides-construction-update-in-saskatchewan-announces-1-million-mental-health-commitment
35039ae0-f0db-5291-9008-a188022fead7 | ["context:source_location_identity"] | ["6b62c459-dc75-5f31-87d4-d6dbf47de8b0"] | company_disclosure | Ashburn Data Centers | https://edgecore.com/locations/ashburn-data-center | EdgeCore Digital Infrastructure | edgecore_location_pages | all-rights-reserved | EdgeCore Digital Infrastructure |  | 2026-07-20T06:04:09Z | e02d1a93ee961d6f0961fc924575b33781e1c026f87f18035f964b4bd02ca160 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/35039ae0-f0db-5291-9008-a188022fead7.json | https://web.archive.org/web/20260720060409/https://edgecore.com/locations/ashburn-data-center
3505d3bd-8d12-50ee-bad8-99fad58dde8e | ["context:geometry_identity","context:site_distinctness"] | ["c1016e49-7b45-52ff-8938-0bd01e78a7ad"] | company_disclosure | DVZ news index dates the exact issue announcement July31 | https://www.dvz-mv.de/news | DVZ M-V GmbH | europe_round5_dvz_schwerin | no-open-license-asserted | DVZ M-V GmbH | 2026-07-31 | 2026-09-08T21:56:20Z | 01a832564e0a7deae6ba717f66ad949b579b9cebf8caf39f479063f1bc9ea37a | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3505d3bd-8d12-50ee-bad8-99fad58dde8e.json | https://web.archive.org/web/20260908215620/https://www.dvz-mv.de/news
3517cba9-f4a4-5d4f-a880-1c1b1ffe4c0e | ["imported:geometry","imported:record"] | ["e389cd04-b538-5729-85a5-8e0b18e78002"] | other | Barker, Niagara County, New York | https://en.wikipedia.org/wiki/Barker,_Niagara_County,_New_York | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 44613d91803e705fc4a9b21e1b0721ffe11c74f36a87854c544fe7080e1cb198 | unknown | source_record_projection | terawulf-lake-mariner | s7 | 081cc26c2e57d03704aae2b9dbe919a2c59626dbb9bf84295aa36cf2d26e6106 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3517cba9-f4a4-5d4f-a880-1c1b1ffe4c0e.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Barker,_Niagara_County,_New_York
3530db1f-8c5d-541a-bf50-146038fd3aaa | ["context:site_distinctness","geometry"] | ["20a32e9d-3c57-520d-aeb8-ad999d43fee3"] | government_record | MADES GeoJSON locator for Zunz environmental project 83461 | https://apps.mades.gov.py/siam/poligono-siam?expediente=6240&gestion=2026&punto=true | Ministerio del Ambiente y Desarrollo Sostenible, Paraguay | root34_hive_yguazu_locator_contract | no-open-license-asserted | Ministerio del Ambiente y Desarrollo Sostenible, Paraguay |  | 2026-09-10T01:54:26.521Z | 7634de9d86da7a53d2bb14ed2a9a25b2046fdb16edccddc3b17a9579ecf2f89a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3530db1f-8c5d-541a-bf50-146038fd3aaa.json | https://web.archive.org/web/20260910015426/https://apps.mades.gov.py/siam/poligono-siam?expediente=6240&gestion=2026&punto=true
3532813c-b4a1-5d46-8164-c9c929b18eb7 | ["imported:geometry","imported:record","imported:status","metric:land_area","role:developer","role:investor","role:operator"] | ["46434a5c-4980-5f79-ac83-000783b60566"] | company_disclosure | Calatorao data centre campus | https://q.com/data-centers/calatorao-en/ | QTS Data Centers | q.com | source-terms-not-recorded | QTS Data Centers |  | 2026-10-09 | 63885ea623d5e050b5bc8150d851787bb0c638549d2bc10c60bc8393a295c56e | unknown | source_record_projection | blackstone-calatorao | s5 | 6afcb1fbc59cf3659ffc3e2d0aa618b2fd646f74ecfb8cd734af34d6d752dadf | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3532813c-b4a1-5d46-8164-c9c929b18eb7.json | https://web.archive.org/web/20261009/https://q.com/data-centers/calatorao-en/
35570395-4998-5b2a-95de-be3e67915aad | ["context:site_distinctness"] | ["f2b93d1a-7c33-5a9e-be4d-f7d0dadec047"] | company_disclosure | Microsoft La Porte July-labelled grading update | https://local.microsoft.com/blog/la-porte-public-meeting-recap/ | Microsoft | americas_round4_microsoft_la_porte | no-open-redistribution-license-asserted | Microsoft | 2026-04-22T21:16:49+00:00 | 2026-09-08T20:46:08Z | bc52b5bd8525a8d574cf0a45437ae9e4b15424dab9de55b3a10e463aa6ec7a2f | datetime | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/35570395-4998-5b2a-95de-be3e67915aad.json | https://web.archive.org/web/20260908204608/https://local.microsoft.com/blog/la-porte-public-meeting-recap/
3567866f-3d2f-567b-936c-899c42e352db | ["context:geometry_identity","context:site_distinctness"] | ["2c3a5bbe-3573-5abe-98dc-8d8312b0a586"] | openstreetmap | OpenStreetMap data rights and attribution | https://www.openstreetmap.org/copyright | OpenStreetMap Foundation | europe_round22_bulk | no-open-license-asserted | OpenStreetMap Foundation |  | 2026-09-09T07:12:48Z | 4604615ef29f0d34751058f5505d6b00985b791827ae473b0e2533c4f0c34194 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3567866f-3d2f-567b-936c-899c42e352db.json | https://web.archive.org/web/20260909071248/https://www.openstreetmap.org/copyright
356a7f87-aa3b-5287-9253-2c4577ff03b9 | ["context:geometry_identity","context:site_distinctness"] | ["b4349487-1879-5b90-9064-d1b86cb49850"] | company_disclosure | Caverion July 31 Greenergy data-hall expansion and on-site workforce | https://www.caverion.com/newsroom/releases/2026/mcf-group-estonia-chooses-caverion-as-main-contractor-for-a-eur-50-million-project-the-largest-high-security-data-centre-in-the-baltics-is-expanding/ | Caverion | europe_round18_greenergy_huuru | no-open-license-asserted | Caverion | 2026-07-31 | 2026-09-09T04:58:22.922Z | bae47a62882058d6b713f106c0a06069c8c3bcee80143dead533431bab8a03fc | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/356a7f87-aa3b-5287-9253-2c4577ff03b9.json | https://web.archive.org/web/20260909045822/https://www.caverion.com/newsroom/releases/2026/mcf-group-estonia-chooses-caverion-as-main-contractor-for-a-eur-50-million-project-the-largest-high-security-data-centre-in-the-baltics-is-expanding/
357f0fbd-6b6b-59a3-ba37-9cae594560e5 | ["context:geometry_identity","context:site_distinctness"] | ["20a32e9d-3c57-520d-aeb8-ad999d43fee3"] | company_disclosure | Share purchase agreement: Zunz ownership of the Yguazú data-center site | https://www.sec.gov/Archives/edgar/data/1812477/000121390025053195/ea024522901ex99-1_bitfarms.htm | Bitfarms Ltd.; HIVE Digital Technologies Ltd. | bitfarms_hive_sec_acquisition | no-open-license-asserted | Bitfarms Ltd.; HIVE Digital Technologies Ltd. |  | 2026-09-10T01:23:35.312Z | 0cab6ab8df6115cf53fda4b583f1d7c707f50855e8c9fc3b3b44bbda1735a8c3 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/357f0fbd-6b6b-59a3-ba37-9cae594560e5.json | https://web.archive.org/web/20260910012335/https://www.sec.gov/Archives/edgar/data/1812477/000121390025053195/ea024522901ex99-1_bitfarms.htm
35b4997b-e1c8-5437-8d10-b716e4012f8f | ["imported:record","imported:status","milestone:other"] | ["a2de1edb-c874-5d78-902a-e174a5ecd03e"] | government_record | Notice of early decision with reasons: Mihta Askiy Data Center Project | https://iaac-aeic.gc.ca/050/evaluations/document/165286?culture=en-CA | Impact Assessment Agency of Canada | iaac-aeic.gc.ca | source-terms-not-recorded | Impact Assessment Agency of Canada | 2026-03-04 | 2026-10-09 | 41ae4e4c1284652a1ec0d6673e601e1342172a1ae31510b56e5f0c7666aeca91 | day | source_record_projection | mihta-askiy-data-centre-peace-river | s3 | 472b8f227e3fd0409f1e131ff9a41c0886bdf5f70ed37d3c1a38e42c34cb2913 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/35b4997b-e1c8-5437-8d10-b716e4012f8f.json | https://web.archive.org/web/20261009/https://iaac-aeic.gc.ca/050/evaluations/document/165286?culture=en-CA
35c41e3e-909b-57dd-b9a0-879467ec17cb | ["geometry"] | ["f8377a0f-dc89-5b7a-8257-25f25cdbac43"] | government_record | Census Public_AR_Current match for 3287 Beech Road | https://geocoding.geo.census.gov/geocoder/ | United States Census Bureau | us_census_geocoder | public-domain-us-government | United States Census Bureau |  | 2026-08-23 | 639b956e41113b6ebc44c5c7e9da794248c1222203fd287c250cbdbbbc99c025 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/35c41e3e-909b-57dd-b9a0-879467ec17cb.json | https://web.archive.org/web/20260823/https://geocoding.geo.census.gov/geocoder/
35d502eb-803a-5c40-8dc1-f0825babb831 | ["context:project_and_campus_identity","typed_metric:grid_connection_mw"] | ["1f33fed8-b0f9-50e2-8fac-56d135325c27"] | company_disclosure | IIJ Announces Plans for Phase 3 Server Building Construction, Expanding the Shiroi Data Center Campus to Meet Growing Demand for IIJ Services | https://www.iij.ad.jp/en/news/pressrelease/2025/0508.html | Internet Initiative Japan Inc. | iij_press_releases | all-rights-reserved | Internet Initiative Japan Inc. | 2025-05-08 | 2026-07-20T01:03:36Z | 7c9f965f4d6c229f0aaab2ecd4584d9943c6d6fca13ed6c528316c72956d18b8 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/35d502eb-803a-5c40-8dc1-f0825babb831.json | https://web.archive.org/web/20260720010336/https://www.iij.ad.jp/en/news/pressrelease/2025/0508.html
362131d4-48db-5185-a5db-a5d237c876db | ["context:site_distinctness","geometry"] | ["fc6dd688-fca0-5a7f-a6e9-54f9116607c5"] | openstreetmap | OpenStreetMap way469691383 - Heesung industrial building | https://api.openstreetmap.org/api/0.6/way/469691383/full.json | OpenStreetMap contributors | openstreetmap_api | ODbL-1.0 | © OpenStreetMap contributors |  | 2026-09-08T19:43:13Z | 7ab33bbc0699911ea919942e43f6dbbd26c99215d68637d60dc03b67b4169885 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/362131d4-48db-5185-a5db-a5d237c876db.json | https://web.archive.org/web/20260908194313/https://api.openstreetmap.org/api/0.6/way/469691383/full.json
3649b928-3853-593a-a281-372f7d012c60 | ["context:geometry_identity","context:site_distinctness"] | ["05033935-bf13-5754-a9af-25c96ea1b473"] | company_disclosure | Company-authored FRA1 foundation and address statement | https://www.technologiebox.de/2026/06/11/noris-network-legt-grundstein-fr-frankfurter-rechenzentrum/ | noris network AG via TechnologieBox | europe_round5_noris_schwalbach | no-open-license-asserted | noris network AG via TechnologieBox | 2026-06-11 | 2026-09-08T21:46:17Z | 2e696f27e662d72eb4eb0e0845e78baf40de86751249e311d5dcb486074645a1 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3649b928-3853-593a-a281-372f7d012c60.json | https://web.archive.org/web/20260908214617/https://www.technologiebox.de/2026/06/11/noris-network-legt-grundstein-fr-frankfurter-rechenzentrum/
3672a27a-eb15-5769-a38d-02c8f32d4991 | ["imported:record","metric:buildings","metric:floor_area","metric:investment","metric:land_area","milestone:expansion_announced"] | ["0f5f4fcc-53c4-53d0-9795-2a387d195364"] | trade_press | Microsoft unveils its largest AI data center yet; to spend US$ 7 billion on Wisconsin facility | https://w.media/microsoft-unveils-its-largest-ai-data-center-yet-to-spend-us-7-billion-on-wisconsin-facility/ | W.Media | w.media | source-terms-not-recorded | W.Media | 2025-09-22 | 2026-10-09 | d83bb0ea6ebff1454101e9cba8eb57b1e9b0259d1b8cd2e592818f62cbdca87e | day | source_record_projection | microsoft-fairwater-mount-pleasant | s9 | 24656e656bf4cdff0af525c80e7f73c6f32adc9cbc3eecf6bacf0ff2abf770fa | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3672a27a-eb15-5769-a38d-02c8f32d4991.json | https://web.archive.org/web/20261009/https://w.media/microsoft-unveils-its-largest-ai-data-center-yet-to-spend-us-7-billion-on-wisconsin-facility/
369e264a-0712-5253-9b8a-730f235d5a69 | ["context:geometry_identity","context:site_distinctness"] | ["fa44cb24-5185-5616-a6a2-3977f190001f"] | company_disclosure | Cipher June 15 Form 8-K indenture: Stingray Datacenter Facility Site at 110 SW 9001, Andrews | https://investors.cipherdigital.com/static-files/83b35945-a986-4510-9a32-bcdb2945fbb0 | Cipher Digital Inc. | cipher_digital_sec_filings_investor_mirror | public-sec-filing | Cipher Digital Inc. Form 8-K, as mirrored on its investor-relations site | 2026-06-15 | 2026-09-25T22:21:06.512Z | 66048f0dd3ee963440976d0c265f2691379880a445958d1d5b585a26c389813b | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/369e264a-0712-5253-9b8a-730f235d5a69.json | https://web.archive.org/web/20260925222106/https://investors.cipherdigital.com/static-files/83b35945-a986-4510-9a32-bcdb2945fbb0
36b66e9e-70fc-5150-850b-6a65e9646e55 | ["context:site_distinctness","geometry"] | ["b7744ad5-aa48-5977-a70e-3d6a588f468d"] | open_dataset | OSM changeset187658622 construction-fence provenance | https://api.openstreetmap.org/api/0.6/changeset/187658622?include_discussion=true | OpenStreetMap contributors | americas_round5_df1_followup | ODbL-1.0 | OpenStreetMap contributors | 2026-08-18 | 2026-09-08T22:10:02Z | 99dc39607070ea06357a6277cf3eb70c2b1d4ae782eca945329fc735519256b2 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/36b66e9e-70fc-5150-850b-6a65e9646e55.json | https://web.archive.org/web/20260908221002/https://api.openstreetmap.org/api/0.6/changeset/187658622?include_discussion=true
36c2c165-107c-5b62-b856-6fa2c4b83cb4 | ["imported:geometry","imported:record","imported:status","metric:land_area","milestone:other","role:builder"] | ["4f8a32cf-b64b-51b4-8758-368320eb441d"] | trade_press | Al-Yamama Wins Infrastructure Contract for 6GW Humain AI Data Center Campus in Riyadh | https://constructionreviewonline.com/al-yamama-wins-infrastructure-contract-for-6gw-humain-ai-data-center-campus-in-riyadh/ | Construction Review Online | constructionreviewonline.com | source-terms-not-recorded | Construction Review Online | 2026-09-24 | 2026-10-09 | 9bb62147fa8eaf09bce4e0175a4162e6e8627ea207dad81ade2f1495b8e7d494 | day | source_record_projection | humain-al-saad-riyadh | s4 | 96bc082928e663285a75443429bde24b04b1e06b6936ea2388084e9d91203d90 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/36c2c165-107c-5b62-b856-6fa2c4b83cb4.json | https://web.archive.org/web/20261009/https://constructionreviewonline.com/al-yamama-wins-infrastructure-contract-for-6gw-humain-ai-data-center-campus-in-riyadh/
36e3d518-b1a0-5bb8-891e-8e2031731430 | ["imported:record","metric:buildings","metric:power_capacity","milestone:announced","milestone:construction_started","milestone:first_operational","power_source:other","role:tenant"] | ["31ee01b0-a72b-5f4a-bcc1-a13a53732efc"] | news | Microsoft takes up residence next to OpenAI, Oracle at Crusoe's 900 MW Texas datacenter expansion | https://www.theregister.com/2026/03/27/microsoft_ai_crusoe/ | The Register | www.theregister.com | source-terms-not-recorded | The Register | 2026-03-27 | 2026-10-09 | 8cea85a73caee51bb46b84d70aa2c595a1e7c14ecebac42407121526e77691a3 | day | source_record_projection | crusoe-abilene-microsoft | s2 | b34d49d30f04664484e776e86777c3772a827321f238830f24821bcdc168ab5c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/36e3d518-b1a0-5bb8-891e-8e2031731430.json | https://web.archive.org/web/20261009/https://www.theregister.com/2026/03/27/microsoft_ai_crusoe/
37013ce5-a12c-59d4-beb5-6ae9011daed7 | ["context:site_distinctness","geometry"] | ["447b19d9-b89b-59a6-9931-824aa1781fb0"] | government_record | Los Angeles County Assessor - 3094 E Vernon Avenue parcel reference point | https://public.gis.lacounty.gov/public/rest/services/LACounty_Cache/LACounty_Parcel/MapServer/0/query?where=SitusHouseNo%3D'3094'%20AND%20SitusStreet%20LIKE%20'%25VERNON%25'&outFields=AIN%2CAPN%2CSitusHouseNo%2CSitusDirection%2CSitusStreet%2CSitusAddress%2CSitusCity%2CSitusZIP%2CCENTER_LAT%2CCENTER_LON&returnGeometry=true&outSR=4326&f=json | Los Angeles County Office of the Assessor | los_angeles_county_assessor_parcel_service | no-open-redistribution-license-asserted | Los Angeles County Office of the Assessor |  | 2026-09-08T18:45:13Z | 017ae60d3c75089af984307002a4751da7b16bbcc45f1dcdc280352cfe3e368f | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/37013ce5-a12c-59d4-beb5-6ae9011daed7.json | https://web.archive.org/web/20260908184513/https://public.gis.lacounty.gov/public/rest/services/LACounty_Cache/LACounty_Parcel/MapServer/0/query?where=SitusHouseNo%3D'3094'%20AND%20SitusStreet%20LIKE%20'%25VERNON%25'&outFields=AIN%2CAPN%2CSitusHouseNo%2CSitusDirection%2CSitusStreet%2CSitusAddress%2CSitusCity%2CSitusZIP%2CCENTER_LAT%2CCENTER_LON&returnGeometry=true&outSR=4326&f=json
371202e2-6a25-5bf2-a53b-57ccfae77647 | ["imported:record","metric:power_capacity","power_source:grid","role:operator","role:utility"] | ["d87a919b-df32-53fa-bc01-47b7f6f1dce9"] | regulatory_filing | Core Scientific, Inc. Form 10-K for the fiscal year ended December 31, 2025 | https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm | Core Scientific, Inc. via SEC EDGAR | www.sec.gov | source-terms-not-recorded | Core Scientific, Inc. via SEC EDGAR | 2026-03-02 | 2026-10-09 | a75005b81dcd522ad3f042c7f25ce3807c03b796bea0edf597ff3035d32c7e5d | day | source_record_projection | core-scientific-muskogee | s2 | 27770cbed3a06baa8115f406673dbf040757ebfc6782e12fbac9b4ef314a02c5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/371202e2-6a25-5bf2-a53b-57ccfae77647.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm
371c4d8b-d919-5614-9c6c-2d8b2976c0af | ["imported:geometry","imported:record","metric:jobs_permanent","milestone:announced","milestone:construction_started","role:developer","role:utility"] | ["dd87fe4b-fdb0-5c4e-a906-70fda834e424"] | news | Louisville to welcome Kentucky's first Hyperscale Data Center | https://www.wdrbwave.com/2025/01/17/louisville-welcome-kentuckys-first-hyperscale-data-center/ | WAVE | www.wdrbwave.com | source-terms-not-recorded | WAVE | 2025-01-16 | 2026-10-09 | 31f0ed519d8e2696eb2edee36b2f44a3a4c53ff2d2d584ad80bed0252425a821 | day | source_record_projection | powerhouse-poe-louisville-camp-ground-road | s3 | 37f733b78fae52fff6eec0b5271ca6a26fd3348359f5cf17f00c007fea8c3fd5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/371c4d8b-d919-5614-9c6c-2d8b2976c0af.json | https://web.archive.org/web/20261009/https://www.wdrbwave.com/2025/01/17/louisville-welcome-kentuckys-first-hyperscale-data-center/
375685f2-b4b3-5f21-a1fe-48a1597c9eb2 | ["context:site_distinctness","geometry"] | ["d83dc321-220b-5c4c-b5af-ff1f4bc19a5d"] | government_record | US Census geocoder - 11680 HAYDEN RD, MANASSAS, VA, 20109 | https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=11680%20Hayden%20Road%20Manassas%20VA%2020109&benchmark=Public_AR_Current&format=json | U.S. Census Bureau | iron_mountain_us_q2_locator_review | no-open-redistribution-license-asserted | U.S. Census Bureau |  | 2026-09-08T20:08:08Z | 41f920d31036ca788e2d52d4c5d7f17924ebde3378c6caf8548ac3ad4c375f84 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/375685f2-b4b3-5f21-a1fe-48a1597c9eb2.json | https://web.archive.org/web/20260908200808/https://geocoding.geo.census.gov/geocoder/locations/onelineaddress?address=11680%20Hayden%20Road%20Manassas%20VA%2020109&benchmark=Public_AR_Current&format=json
37a32cc5-39a0-5b1b-910b-3ebd913fa3c5 | ["imported:geometry","imported:record"] | ["b74385b8-0724-5b4d-b192-4aa5a1c45885"] | other | Childress, Texas | https://en.wikipedia.org/wiki/Childress,_Texas | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 9e83a5c1838e907f9bed2040ed0c5736cb8a7adf2d512bb09b64eb5cab301bc3 | unknown | source_record_projection | iren-childress | s6 | 2e84178afc0deb7b62de37b97e373907adbcd669801951165b008127658131de | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/37a32cc5-39a0-5b1b-910b-3ebd913fa3c5.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Childress,_Texas
37a8ffc7-4e5e-5503-9fee-9d738613bcef | ["imported:geometry","imported:record","metric:buildings","metric:floor_area","metric:land_area","metric:power_capacity","role:developer"] | ["441174d1-4dab-5b80-bfb2-76062cf675aa"] | company_disclosure | Phoenix data center campus | https://edgecore.com/locations/phoenix-data-center | EdgeCore Digital Infrastructure | edgecore.com | source-terms-not-recorded | EdgeCore Digital Infrastructure |  | 2026-10-09 | 3409245d898b380fbec9363aee2417210d0946f1fee9d786ba99b90487f86d81 | unknown | source_record_projection | edgecore-mesa | s3 | 11108ce31c1e8198f200d4be4681d069335589ece0fb1c2199fee548a18090d2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/37a8ffc7-4e5e-5503-9fee-9d738613bcef.json | https://web.archive.org/web/20261009/https://edgecore.com/locations/phoenix-data-center
382c3879-d33c-54d1-bdaf-beabe809b5ab | ["imported:record","metric:power_capacity","milestone:announced","milestone:first_operational","power_source:grid","role:developer"] | ["0eb54c2e-ed0f-58e9-85cc-bf616b723139"] | company_disclosure | Applied Digital Reaches Significant Milestone, Surpassing 1 GW of Contracted Capacity with U.S. Based High Investment-Grade Hyperscaler Lease at Fourth Campus, Polaris Forge 3 | https://ir.applieddigital.com/news-events/press-releases/detail/152/applied-digital-reaches-significant-milestone-surpassing-1 | Applied Digital | ir.applieddigital.com | source-terms-not-recorded | Applied Digital | 2026-05-20 | 2026-10-09 | 9877d156ca494f6fae7059125afa0c1b734b897032777efc189f76b0e000907b | day | source_record_projection | applied-digital-polaris-forge-3 | s1 | bf8ae2da16a9750a0827601c845afcadcb3388756142390227e81be26b2fc1a2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/382c3879-d33c-54d1-bdaf-beabe809b5ab.json | https://web.archive.org/web/20261009/https://ir.applieddigital.com/news-events/press-releases/detail/152/applied-digital-reaches-significant-milestone-surpassing-1
3834817e-f9ca-5455-9e36-b9830864246c | ["context:site_distinctness"] | ["aa2dc8a4-52d8-5519-b23a-2ff0313db9e3"] | company_disclosure | Edged Getafe1: distinct Fundidores40 campus | https://www.edged.es/madrid-getafe | Edged | expansion_round5_primary_sources | all-rights-reserved | Edged |  | 2026-09-08T21:23:01Z | 275ae20c0500ecccc5e9784e55336c0063df9d3e1fd54caebac97d5c4ec80905 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3834817e-f9ca-5455-9e36-b9830864246c.json | https://web.archive.org/web/20260908212301/https://www.edged.es/madrid-getafe
3877ce56-44bc-5417-b82c-46b731aa3cf8 | ["imported:geometry","imported:record","metric:power_capacity","power_source:grid","role:operator","role:utility"] | ["c62aed61-a87f-57ab-b1a4-76d1867f73b9"] | regulatory_filing | Core Scientific, Inc. Form 10-K for the fiscal year ended December 31, 2025 | https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm | U.S. Securities and Exchange Commission (Core Scientific filing) | www.sec.gov | source-terms-not-recorded | U.S. Securities and Exchange Commission (Core Scientific filing) | 2026-03-02 | 2026-10-09 | 69dad069c47a25cf010398ad150e928e231eebc8847e514a282b9f0c439d04d1 | day | source_record_projection | core-scientific-denton | s2 | 91a53158a43d538f9b348f473ca1b8746bd8d181d2d3a8473af455cd7ea27b0b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3877ce56-44bc-5417-b82c-46b731aa3cf8.json | https://web.archive.org/web/20261009/https://www.sec.gov/Archives/edgar/data/1839341/000162828026013305/core-20251231.htm
388f30b8-8e1e-537c-a590-14a13c4a4e0b | ["physical_status"] | ["be6d721d-f632-5c86-a057-78774604bc6c"] | company_disclosure | Goodman FY26 Results - PAR01 current development | https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1 | Goodman Group | goodman_group_investor_presentations | all-rights-reserved | Goodman Group | 2026-08-19 | 2026-09-08T18:38:25Z | 892c9d069276912a13d2ff100ff3260b1c2d26874693d644e0d34dce3a7d809d | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/388f30b8-8e1e-537c-a590-14a13c4a4e0b.json | https://web.archive.org/web/20260908183825/https://www.goodman.com/-/media/project/goodman/global/files/investor-centre/gmg-goodman-group/announcements/asx-announcements/2026/4-full-year-results-presentation-5.pdf?rev=ac56d4e1f3444d309bbefa27304c7da1
3893fae6-9768-51d9-b8b0-591f2887e094 | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["f0e92e2e-e082-5b7f-9486-fd744b5b68e6"] | company_disclosure | ERNE reports ongoing finishing works at Vantage Winterthur | https://www.erne.ch/fr/news/detail/ernenews/in-winterthur-lassen-wir-ein-neues-data-center-wachsen/ | ERNE AG Bauunternehmung | europe_mena_round9_expansion_asia | no-open-license-asserted | ERNE AG Bauunternehmung | 2026-07-30 | 2026-09-08T23:11:30.039Z | 76b4d530f0480fbe0624ca11721781e90c4727bc2a1f22db2d92a880718c0a9c | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3893fae6-9768-51d9-b8b0-591f2887e094.json | https://web.archive.org/web/20260908231130/https://www.erne.ch/fr/news/detail/ernenews/in-winterthur-lassen-wir-ein-neues-data-center-wachsen/
38a97c43-cfaf-5c4e-8a2a-12611c839cbd | ["imported:geometry","imported:record","metric:floor_area","metric:investment","metric:jobs_construction","metric:jobs_permanent","milestone:announced","power_source:grid","role:builder","role:developer","role:utility"] | ["eaaa4486-a9d9-5cf1-b196-d03c258f8dc1"] | company_disclosure | Hello, Beaver Dam! | https://datacenters.atmeta.com/2025/11/hello-beaver-dam/ | Meta Platforms | datacenters.atmeta.com | source-terms-not-recorded | Meta Platforms | 2025-11-12 | 2026-10-09 | f3b47bfcf5e71a2d22746a45cb47cc11a68df037ba58c28399124bfd184594cc | day | source_record_projection | meta-beaver-dam | s1 | f7194a0774189abab934e81dbe4596c5d7a07bf4eb05438362099238e1b91c75 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/38a97c43-cfaf-5c4e-8a2a-12611c839cbd.json | https://web.archive.org/web/20261009/https://datacenters.atmeta.com/2025/11/hello-beaver-dam/
38ba8adb-7b5d-5a1f-9482-a94654fc485d | ["context:site_distinctness","geometry"] | ["5bfb4ad8-a8f4-5937-9242-a96f9292c385"] | openstreetmap | OSM names the same industrial hall CSC and LUMI | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bway(705545655)%3Bout%20body%20geom%3B | OpenStreetMap contributors / Overpass API | europe_round15_csc_lumi_ai | ODbL-1.0 | © OpenStreetMap contributors |  | 2026-09-09T03:39:20Z | c61cdd2216ebf210e5fef246888cf6ae03308fb4ecfdea47e1a5f7b594ff8d5b | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/38ba8adb-7b5d-5a1f-9482-a94654fc485d.json | https://web.archive.org/web/20260909033920/https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bway(705545655)%3Bout%20body%20geom%3B
3908b2d8-3494-5c31-93f5-c5d84f368a20 | ["context:site_distinctness","geometry"] | ["f3cc5dc7-9547-517f-94aa-89e0769f2bf8"] | government_record | County-generated centroid of exact Peanut parcel | https://services3.arcgis.com/TsynfzBSE6sXfoLq/ArcGIS/rest/services/Cadastral_ProdA/FeatureServer/3/query | Chesterfield County GIS | chesterfield_round14 | CC0-1.0 | Data retrieved from Chesterfield County GIS Data Catalog. |  | 2026-09-09T03:05:03Z | dc5b7572e4faa9385e314c0a5dfbb48d94288ba0c926d60ccf509aa2f77419f4 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3908b2d8-3494-5c31-93f5-c5d84f368a20.json | https://web.archive.org/web/20260909030503/https://services3.arcgis.com/TsynfzBSE6sXfoLq/ArcGIS/rest/services/Cadastral_ProdA/FeatureServer/3/query
391bac0c-4bc6-5c67-88fe-be1eac2d1abe | ["context:geometry_identity","context:site_distinctness"] | ["e39b5191-4a78-5781-8944-24efaf944aa9"] | government_record | Next DC Corio officer report: O'Brien's Road address and Lot 6 | https://sftpbspomppprod01.blob.core.windows.net/applicationfiles/ac08c0c4-2a7f-f011-b4cc-00224811ea6c_PA2503895%20REDACTED_148-158%20OBRIENS%20ROAD%20CORIO%20-%20Officer%20Report.pdf | Victoria Department of Transport and Planning | victoria_ministerial_permit_officer_report | all-rights-reserved | Victoria Department of Transport and Planning |  | 2026-09-08T21:09:44Z | 49793d4191d10f88cffe4fd90b67fa6ee2ae55a72c11100637e6590a78717999 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/391bac0c-4bc6-5c67-88fe-be1eac2d1abe.json | https://web.archive.org/web/20260908210944/https://sftpbspomppprod01.blob.core.windows.net/applicationfiles/ac08c0c4-2a7f-f011-b4cc-00224811ea6c_PA2503895%20REDACTED_148-158%20OBRIENS%20ROAD%20CORIO%20-%20Officer%20Report.pdf
39230453-beab-5905-a11b-852730385ea6 | ["context:geometry_identity","context:site_distinctness"] | ["b7744ad5-aa48-5977-a70e-3d6a588f468d"] | government_record | Official LDEQ public notice AI250709 | https://www.deq.louisiana.gov/public-notices?q=250709 | Louisiana Department of Environmental Quality | americas_round5_df1_followup | no-open-redistribution-license-asserted | Louisiana Department of Environmental Quality | 2026-07-29 | 2026-09-08T22:02:57Z | 10a8bbe4c886f1c4203b7cd5399c90febbcd9745e9527b038269eea3371bc6ab | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/39230453-beab-5905-a11b-852730385ea6.json | https://web.archive.org/web/20260908220257/https://www.deq.louisiana.gov/public-notices?q=250709
3935b984-1fc9-538b-aa2e-c2431e85553a | ["context:site_distinctness","geometry"] | ["f3cc5dc7-9547-517f-94aa-89e0769f2bf8"] | government_record | Exact Peanut parcel query crosscheck | https://services3.arcgis.com/TsynfzBSE6sXfoLq/ArcGIS/rest/services/Cadastral_ProdA/FeatureServer/3/query | Chesterfield County GIS | chesterfield_round14 | CC0-1.0 | Chesterfield County GIS |  | 2026-09-09T00:30:01.403Z | 4527279f720e25e56bdefa0eb2efec9045b5d6f1d0cc23e3937fb96e739407b1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3935b984-1fc9-538b-aa2e-c2431e85553a.json | https://web.archive.org/web/20260909003001/https://services3.arcgis.com/TsynfzBSE6sXfoLq/ArcGIS/rest/services/Cadastral_ProdA/FeatureServer/3/query
394f235e-1d3c-51f7-8c30-388921536a8d | ["imported:geometry","imported:record","role:developer"] | ["9ed96427-8138-552b-9f88-3b1fbeaa341b"] | news | Asian crypto mining company and Geis partner to bring data center to Shalersville | https://theportager.com/asian-crypto-mining-company-and-geis-partner-to-bring-data-center-to-shalersville | The Portager | theportager.com | source-terms-not-recorded | The Portager | 2026-06-05 | 2026-10-09 | 622bf74cbf8b07572fa40da7977914ef71d57b53a381a9821843a371c3a6e1e0 | day | source_record_projection | bitdeer-shalersville-portage-county | s2 | 3bf4ed692033cd5d7788a796df21f16156be296573a4b008414791a303564b37 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/394f235e-1d3c-51f7-8c30-388921536a8d.json | https://web.archive.org/web/20261009/https://theportager.com/asian-crypto-mining-company-and-geis-partner-to-bring-data-center-to-shalersville
3954fec5-a497-5881-b6df-94f7331ccb47 | ["context:site_distinctness","geometry"] | ["5e0d1954-690d-51cb-816a-88cec595f51a"] | other | INSPIRE code list GeometrySpecificationValue: building | https://inspire.ec.europa.eu/codelist/GeometrySpecificationValue/building/building.en.json | European Commission, INSPIRE registry | inspire_registry_code_lists | no-open-license-asserted | European Commission, INSPIRE registry |  | 2026-10-09T11:10:01.741Z | d74b4950a59aafea1706eb7b9c5f72eb594e6ed649293fbbbc90f26382eaa230 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3954fec5-a497-5881-b6df-94f7331ccb47.json | https://web.archive.org/web/20261009111001/https://inspire.ec.europa.eu/codelist/GeometrySpecificationValue/building/building.en.json
3984266e-da0e-556b-b18b-5db9ee87f1d6 | ["imported:geometry","imported:record"] | ["31ee01b0-a72b-5f4a-bcc1-a13a53732efc"] | other | Abilene, Texas | https://en.wikipedia.org/wiki/Abilene,_Texas | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 1335f68509546dc007e77b287c8242e9833f9fb1415bc3ed75f335b5379e5904 | unknown | source_record_projection | crusoe-abilene-microsoft | s5 | b34d49d30f04664484e776e86777c3772a827321f238830f24821bcdc168ab5c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3984266e-da0e-556b-b18b-5db9ee87f1d6.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Abilene,_Texas
398fc453-b238-5308-9e7a-703789024d93 | ["context:geometry_identity","context:site_distinctness"] | ["f8900f55-087d-5d51-aef2-820402bcbdc2"] | government_record | Datacenter permit amendment - Hybrideweg 105, Vijfhuizen | https://zoek.officielebekendmakingen.nl/prb-2026-2233.html | Province of Noord-Holland | netherlands_official_provincial_notices | no-open-redistribution-license-asserted | Province of Noord-Holland | 2026-02-10 | 2026-09-08T19:27:02Z | d29002362b47cb7aca4048e080e2c4c94f3fb3d47feb4ecabdb73ed90f7b5531 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/398fc453-b238-5308-9e7a-703789024d93.json | https://web.archive.org/web/20260908192702/https://zoek.officielebekendmakingen.nl/prb-2026-2233.html
39b564fe-6296-50b9-9ef8-4718b4e12f97 | ["imported:record","imported:status","power_source:grid"] | ["8d08b021-e457-5102-9ef2-33528ad786d1"] | news | Indiana power outage raises concerns about data centers | https://www.wbur.org/hereandnow/2026/08/25/indiana-power-data-centers | WBUR (Here & Now) | www.wbur.org | source-terms-not-recorded | WBUR (Here & Now) | 2026-08-25 | 2026-10-09 | a9d410f4e3b4c7eebe38897254b14184522bd07b164f47bc1e2217b390a38204 | day | source_record_projection | aws-hobart-indiana | s5 | 51fd6e547d8fd5c8eaa8837b69b75043041b5ae8f9bec2a94b1b95328b7c679b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/39b564fe-6296-50b9-9ef8-4718b4e12f97.json | https://web.archive.org/web/20261009/https://www.wbur.org/hereandnow/2026/08/25/indiana-power-data-centers
39ca2ddf-3a1e-5d9c-983e-4a30ae537dc7 | ["typed_metric:critical_it_mw"] | ["65e8849e-2ebe-5d58-be63-299cbbcf8d23"] | company_disclosure | Denver DE3 Facility Specification | https://www.coresite.com/hubfs/-website-documents/facility-specifications/sp-CoreSite-Denver-DE3-Spec-Sheet.pdf | CoreSite | coresite_official_website | all-rights-reserved | CoreSite |  | 2026-07-20T10:42:21Z | 3883645e759b91f59887b225c46b5bdfb98f6168bacd0057bbf0780162cff2d1 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/39ca2ddf-3a1e-5d9c-983e-4a30ae537dc7.json | https://web.archive.org/web/20260720104221/https://www.coresite.com/hubfs/-website-documents/facility-specifications/sp-CoreSite-Denver-DE3-Spec-Sheet.pdf
39cdd4b0-60f0-5d50-9a38-59d72c0a9d53 | ["context:geometry_identity"] | ["01baa3bb-ea56-5f41-8c67-82dd84f87d51"] | government_record | City of Chicago Building Footprints row BLDG_ID 871169 | https://data.cityofchicago.org/resource/syp8-uezg.json?bldg_id=871169 | City of Chicago | city_of_chicago_building_footprints | SEE_TERMS_OF_USE | City of Chicago |  | 2026-08-20T23:30:13Z | 9d9838b72d74b3be5db4c5c0cbad94a866ad31c2af0ed623bdef68e2e2b5feaa | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/39cdd4b0-60f0-5d50-9a38-59d72c0a9d53.json | https://web.archive.org/web/20260820233013/https://data.cityofchicago.org/resource/syp8-uezg.json?bldg_id=871169
39e38bb3-a3ec-5d6b-bb7a-a5b3a354380c | ["context:geometry_identity","context:site_distinctness"] | ["d83dc321-220b-5c4c-b5af-ff1f4bc19a5d"] | company_disclosure | Iron Mountain government-solutions page - Manassas campus addresses | https://datacenter.ironmountain.com/government-data-centers | Iron Mountain Data Centers | iron_mountain_us_q2_locator_review | no-open-redistribution-license-asserted | Iron Mountain Data Centers |  | 2026-09-08T20:06:32Z | a629bf95e4d71ccce245c7f542981ec447bb3a5ad1c3e7a0e9c57037cdc7712a | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/39e38bb3-a3ec-5d6b-bb7a-a5b3a354380c.json | https://web.archive.org/web/20260908200632/https://datacenter.ironmountain.com/government-data-centers
3a1470e0-70e9-542b-8e57-545ea6b11011 | ["imported:record","metric:land_area","milestone:construction_started","power_source:grid","role:developer"] | ["a490f00a-8b75-5547-b0e9-5fb3b6e5f616"] | trade_press | Quantum Loophole begins construction on massive Frederick, Md. data center campus | https://www.cablinginstall.com/data-center/article/14279126/quantum-loophole-begins-construction-on-massive-frederick-md-data-center-campus | Cabling Installation & Maintenance | www.cablinginstall.com | source-terms-not-recorded | Cabling Installation & Maintenance | 2022-07-05 | 2026-10-09 | 50c966319329a8886e0b8acea354d2e1394ff93b57435018fe6a96dc70d99323 | day | source_record_projection | quantum-frederick | s2 | 98a19a570fec7492c5695c7b8bfda0e04f30819df89668cd9a89dcebba4c7f12 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3a1470e0-70e9-542b-8e57-545ea6b11011.json | https://web.archive.org/web/20261009/https://www.cablinginstall.com/data-center/article/14279126/quantum-loophole-begins-construction-on-massive-frederick-md-data-center-campus
3a24f856-066d-5c00-9451-e88d2b2e59da | ["imported:geometry","imported:record"] | ["602d4e58-abef-54a7-b8f6-894a714e7174"] | other | Fox Creek, Alberta | https://en.wikipedia.org/wiki/Fox_Creek,_Alberta | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 794f57f51a6e4c3fd6006992509a575d41d910e9202789c769b8fc613d0f56eb | unknown | source_record_projection | bitdeer-fox-creek | s4 | f745c0fc027e66d0a064cde500d844a27c571e80ddd2d7fad377deefd0e77fe1 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3a24f856-066d-5c00-9451-e88d2b2e59da.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Fox_Creek,_Alberta
3a3271fa-be5b-57bd-a878-6c5de4e7860c | ["context:geometry_identity","context:site_distinctness"] | ["337ace90-652d-52fe-a856-fe9b04b5966f"] | government_record | El Paso municipal Meta and Wurldwide campus identity | https://www.elpasotexas.gov/data-centers | City of El Paso | meta_round10_independent_review | all-rights-reserved | City of El Paso |  | 2026-09-08T23:45:08Z | 0953bb349d8fe57516316f3230fb2abc5a3365b685394f6634703590f3e3a3b5 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3a3271fa-be5b-57bd-a878-6c5de4e7860c.json | https://web.archive.org/web/20260908234508/https://www.elpasotexas.gov/data-centers
3a5551fb-11b1-5245-b4b0-6611bca52342 | ["context:site_distinctness","geometry"] | ["5bfb4ad8-a8f4-5937-9242-a96f9292c385"] | openstreetmap | OpenStreetMap specifies ODbL reuse and attribution obligations | https://www.openstreetmap.org/copyright | OpenStreetMap Foundation | europe_round15_csc_lumi_ai | no-open-license-asserted | OpenStreetMap Foundation |  | 2026-09-09T03:14:02Z | c8055488347fce8abf6b4fb31178c7212b062c5d914f7501588069233718b914 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3a5551fb-11b1-5245-b4b0-6611bca52342.json | https://web.archive.org/web/20260909031402/https://www.openstreetmap.org/copyright
3a625ff7-d3f3-5a72-bdb7-713ce15a8145 | ["imported:record","metric:power_capacity","role:tenant"] | ["8aa8e9f5-915e-51f6-bc08-463822cf16f9"] | company_disclosure | Hut 8 Reports Second Quarter 2026 Results | https://www.hut8.com/news-insights/press-releases/hut-8-reports-second-quarter-2026-results | Hut 8 | www.hut8.com | source-terms-not-recorded | Hut 8 | 2026-08-04 | 2026-10-09 | f45ef6f66258b70bf676285c3dec2478a1ae555c5ea3dac72d705a5a6e64eb22 | day | source_record_projection | hut8-river-bend-louisiana | s6 | fb7eeaf52bb6e7789effaf24b3ee0bb7e31922a38047e56ede8f20f89e9b204a | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3a625ff7-d3f3-5a72-bdb7-713ce15a8145.json | https://web.archive.org/web/20261009/https://www.hut8.com/news-insights/press-releases/hut-8-reports-second-quarter-2026-results
3a993ad5-1b04-5754-9adb-eac65e528c2b | ["imported:geometry","imported:record","milestone:other","power_source:grid","power_source:nuclear","role:tenant","role:utility"] | ["3b636397-fbb2-5564-a352-fa1382a218b5"] | news | We Energies strikes deal to power Oracle data center with nuclear energy | https://wisconsinwatch.org/2026/10/wisconsin-we-energies-deal-oracle-data-center-nuclear-energy-power-point-beach-plant/ | Wisconsin Watch | wisconsinwatch.org | source-terms-not-recorded | Wisconsin Watch | 2026-10-02 | 2026-10-09 | e5d7433e92a84d2de46a8b5530b9cc1da6c374ac6dfc7d9370219c78aad99a31 | day | source_record_projection | oracle-vantage-port-washington | s8 | d9322bd7e03400684eb1de18b401871dbb56eee1f83f17ea7546f26ce30e37c7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3a993ad5-1b04-5754-9adb-eac65e528c2b.json | https://web.archive.org/web/20261009/https://wisconsinwatch.org/2026/10/wisconsin-we-energies-deal-oracle-data-center-nuclear-energy-power-point-beach-plant/
3ac3ad9e-8831-5419-8130-9e60d24342e6 | ["imported:geometry","imported:record","metric:investment","metric:jobs_permanent","milestone:announced","milestone:construction_started","power_source:grid","role:developer","role:government","role:utility"] | ["7c9397d2-971c-5d1e-ad58-210d19777a37"] | government_record | Gov. Holcomb announces Google is building a $2B Data Center in Northeast Indiana | https://iedc.in.gov/events/news/details/2024/04/26/gov.-holcomb-announces-google-is-building-a-2b-data-center-in-northeast-indiana | Indiana Economic Development Corporation | iedc.in.gov | source-terms-not-recorded | Indiana Economic Development Corporation | 2024-04-26 | 2026-10-09 | 9125d90d11f34c3c599b652b0392f28f9a8975a91328e10e917c3b35cda673db | day | source_record_projection | google-fort-wayne-indiana | s1 | 140e615990e16bd1d60c983ff139345118f93e72fd9ebd3a99658c8db663db69 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3ac3ad9e-8831-5419-8130-9e60d24342e6.json | https://web.archive.org/web/20261009/https://iedc.in.gov/events/news/details/2024/04/26/gov.-holcomb-announces-google-is-building-a-2b-data-center-in-northeast-indiana
3ae304e7-a74f-522e-8b9b-df93664fbd17 | ["context:identity","role:operator"] | ["c2ec8d08-3436-5bbc-af4e-4eb553297fe2"] | company_disclosure | NorthC Frankfurt1 official facility address | https://www.northcdatacenters.com/de/frankfurt-1/ | NorthC Datacenters | northc_official | all-rights-reserved | NorthC Datacenters |  | 2026-10-13T13:48:48.097079+00:00 | 72265758c4266ef3a3667db841f58810b6287f3b72c7ccdd387de144834eb1ae | unknown | sha256_exact_content_decoded_response_bytes |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3ae304e7-a74f-522e-8b9b-df93664fbd17.json | https://web.archive.org/web/20261013134848/https://www.northcdatacenters.com/de/frankfurt-1/
3af60f35-2add-56e3-9002-0395731a93ff | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["f3cc5dc7-9547-517f-94aa-89e0769f2bf8"] | government_record | Google Bermuda Hundred Current Development - July 2026 county status | https://www.chesterfield.gov/5989/Data-Centers | Chesterfield County | chesterfield_round14 | no-open-redistribution-license-asserted | Chesterfield County, Virginia |  | 2026-09-09T00:19:01Z | ab850d526998b565b7a834a1730b074f695721830577ac1ca0b7f78477561ddc | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3af60f35-2add-56e3-9002-0395731a93ff.json | https://web.archive.org/web/20260909001901/https://www.chesterfield.gov/5989/Data-Centers
3b0268bc-5706-536f-b8be-bc6e7eb102ac | ["imported:geometry","imported:record"] | ["6aa46e28-dd40-513b-8722-f514b6503b02"] | other | Strängnäs | https://en.wikipedia.org/wiki/Str%C3%A4ngn%C3%A4s | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | 5bc71f29deeda10e0086ddb9daa613e7d424db81b09e3912a94f1452bd464a56 | unknown | source_record_projection | brookfield-strangnas | s3 | 8c82afafd59fa623fa44dc63c720db2bc356d54172b0ba49e5439118f88a9364 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b0268bc-5706-536f-b8be-bc6e7eb102ac.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Str%C3%A4ngn%C3%A4s
3b11e0f1-1a48-542b-9b5c-c681ae6ed732 | ["imported:geometry","imported:record","metric:buildings","metric:investment","metric:power_capacity","milestone:announced","power_source:grid","role:developer","role:government","role:utility"] | ["2b520cfa-8aea-5212-9b60-8ff417ee6578"] | company_disclosure | Compass project generates $10 billion investment in Lauderdale County | https://www.compassdatacenters.com/news/compass-10b-investment-lauderdale-county-mississippi/ | Compass Datacenters | www.compassdatacenters.com | source-terms-not-recorded | Compass Datacenters | 2025-01-09 | 2026-10-09 | aa5ed441ec23a4b997c2cb874662ba23b9f06e58f2b3b6eb77a30e6fcf8be60b | day | source_record_projection | compass-meridian-mississippi | s1 | a18df3f46fbdb7b6bbbba380d6ce88046afae5e7f7409b3cc456fe2a94fdb4c6 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b11e0f1-1a48-542b-9b5c-c681ae6ed732.json | https://web.archive.org/web/20261009/https://www.compassdatacenters.com/news/compass-10b-investment-lauderdale-county-mississippi/
3b23c6b7-ae38-589a-bc7f-c53ddade961d | ["imported:geometry","imported:record","imported:status","metric:investment","metric:land_area","metric:power_capacity","milestone:announced","milestone:first_operational","role:developer","role:government","role:investor"] | ["0d75be4c-1fff-5854-895c-71aef25eff11"] | news | TCS HyperVault to Build Rs 70,000 Cr AI Data Centre in Hyderabad | https://startupfeed.in/?p=11607 | StartupFeed | startupfeed.in | source-terms-not-recorded | StartupFeed | 2026-09-09 | 2026-10-09 | 55dc7251d9b40eadd9c0d9f200ea7191c1073e8a9da9c7a75d649dbb71ca3ce1 | day | source_record_projection | tcs-hypervault-hyderabad | s2 | 7ab430f2d4c7241fbcba9a1d98ff235e0e05dbfb82b29311d12b2af980637444 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b23c6b7-ae38-589a-bc7f-c53ddade961d.json | https://web.archive.org/web/20261009/https://startupfeed.in/?p=11607
3b39030f-c2a8-583b-8198-cab46caaabcf | ["imported:geometry","imported:record"] | ["908ba9ce-1e84-567b-926f-8d47d4d2a7ed"] | other | Chatham, Virginia | https://en.wikipedia.org/wiki/Chatham,_Virginia | Wikipedia | en.wikipedia.org | source-terms-not-recorded | Wikipedia |  | 2026-10-09 | b1e1e3a3c0bf73aeec3cab43106d718206f974e9372dd472ae8b85463c1c3d93 | unknown | source_record_projection | balico-pittsylvania-county | s5 | 9169c30b464bb8fd99931fce532ae356b7455ba9eb4e67c4c9c205374c151b21 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b39030f-c2a8-583b-8198-cab46caaabcf.json | https://web.archive.org/web/20261009/https://en.wikipedia.org/wiki/Chatham,_Virginia
3b4d4ed2-ae2c-5c50-97b6-3f7e70b1338e | ["imported:geometry","imported:record","imported:status","metric:accelerators","metric:investment","metric:power_capacity","milestone:construction_started","milestone:first_operational","role:operator"] | ["54782d37-d21e-5ddf-990b-a578130ac9d0"] | trade_press | Telekom data center to boost German AI performance by half | https://heise.de/-11165327 | heise online | heise.de | source-terms-not-recorded | heise online | 2026-02-04 | 2026-10-09 | db1b2ec99ef757e0ec16200dc9a78ac8107c3566c247767585c3980d2a25dc76 | day | source_record_projection | deutsche-telekom-nvidia-munich | s3 | 4bcdf47b4a9cad5a44cc8dbea515091ace6e23bf69ea7cc718e42e346f184cfa | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b4d4ed2-ae2c-5c50-97b6-3f7e70b1338e.json | https://web.archive.org/web/20261009/https://heise.de/-11165327
3b796d81-9046-5662-b53e-4a7363bb50f3 | ["context:site_distinctness","geometry"] | ["05033935-bf13-5754-a9af-25c96ea1b473"] | openstreetmap | Named noris FRA1 community campus locator | https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bway%28313208490%29%3Bout%20meta%20center%3B | OpenStreetMap contributors via Overpass | europe_round5_exact_locators | ODbL-1.0 | OpenStreetMap contributors via Overpass |  | 2026-09-08T21:37:49Z | 68907f60d504b0aa48d5184ee46747e45736fbd3ef2838f9c12154145dc3df37 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b796d81-9046-5662-b53e-4a7363bb50f3.json | https://web.archive.org/web/20260908213749/https://overpass-api.de/api/interpreter?data=%5Bout%3Ajson%5D%3Bway%28313208490%29%3Bout%20meta%20center%3B
3b847726-3c79-5d0b-8e80-70c0498fd745 | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:announced","milestone:cancelled","role:developer","role:government"] | ["03207f8c-1d9d-577f-9d8c-af881144fb86"] | trade_press | Apex Data Center Scrapped | https://www.bisnow.com/news/raleigh-durham/data-center/massive-raleigh-area-data-center-scrapped-133584 | Bisnow | www.bisnow.com | source-terms-not-recorded | Bisnow | 2026-03-10 | 2026-10-09 | 5980ec4eadb91aeb00110e51afc03db24a349325da1e6ab89c9697459339b16d | day | source_record_projection | natelli-new-hill-digital-campus | s1 | ce0a61a3c0650b4f20901871383b33a499a2f44ec25ff5f8d350a43483c5f70c | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b847726-3c79-5d0b-8e80-70c0498fd745.json | https://web.archive.org/web/20261009/https://www.bisnow.com/news/raleigh-durham/data-center/massive-raleigh-area-data-center-scrapped-133584
3b92e884-db33-5b13-be1e-bcb97a3e4344 | ["imported:geometry","imported:record","imported:status","metric:land_area","metric:power_capacity","milestone:expansion_announced","milestone:other","power_source:grid","role:developer","role:utility"] | ["441174d1-4dab-5b80-bfb2-76062cf675aa"] | company_disclosure | EdgeCore Digital Infrastructure Announces Expansion of Its Metro Phoenix Data Center Market to Over 450 MW | https://edgecore.com/edgecore-digital-infrastructure-announces-expansion-of-its-metro-phoenix-data-center-market-to-over-450-mw/ | EdgeCore Digital Infrastructure | edgecore.com | source-terms-not-recorded | EdgeCore Digital Infrastructure | 2025-05-20 | 2026-10-09 | 9b0b658c498ca92acc465a0ffeb1a794d9afede12ac4f95fd4a4b8f094caa3d6 | day | source_record_projection | edgecore-mesa | s1 | 11108ce31c1e8198f200d4be4681d069335589ece0fb1c2199fee548a18090d2 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3b92e884-db33-5b13-be1e-bcb97a3e4344.json | https://web.archive.org/web/20261009/https://edgecore.com/edgecore-digital-infrastructure-announces-expansion-of-its-metro-phoenix-data-center-market-to-over-450-mw/
3ba6fbeb-a1db-5021-bc92-bd16ef1bc36e | ["context:site_distinctness"] | ["5ace12f8-658e-5956-9173-d78e625d4df9"] | company_disclosure | Nebius Vineland undated construction context | https://nebius.com/vinelandnj | Nebius | us_round23_dataone_vineland | no-open-license-asserted | Nebius |  | 2026-09-09T07:50:20Z | f0e17b17f4ac56d04157d75776033ce5d0522031ba4e75d8269fb36807ea319e | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3ba6fbeb-a1db-5021-bc92-bd16ef1bc36e.json | https://web.archive.org/web/20260909075020/https://nebius.com/vinelandnj
3bb1bb6d-c4d0-57ac-9eb0-dc81963e6429 | ["imported:geometry","imported:record","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:announced","power_source:natural_gas_onsite","role:developer"] | ["4a0d8f6f-b848-5650-a479-4f0caee97fa1"] | company_disclosure | Synapse Data Center Project Information Package | https://www.olds.ca/media/y3cp0anv/synapse-data-center-project-information-package.pdf | Synapse Real Estate Corp. (hosted by the Town of Olds) | www.olds.ca | source-terms-not-recorded | Synapse Real Estate Corp. (hosted by the Town of Olds) | 2026-01-27 | 2026-10-09 | c385cacde5ba759dfc55e7ed5b997f8a12c2ba5091970db5617e952e13531c08 | day | source_record_projection | synapse-olds | s1 | 14fc93e0f111163a184e77ec2774f5d985878a5d18f5faf2fad82a140bde792d | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3bb1bb6d-c4d0-57ac-9eb0-dc81963e6429.json | https://web.archive.org/web/20261009/https://www.olds.ca/media/y3cp0anv/synapse-data-center-project-information-package.pdf
3c85c95a-5036-5cf2-b9b8-c15070c6aaea | ["context:source_location_identity","physical_status"] | ["c30aeadf-c2f6-58a5-a8b1-227868f477c1"] | company_disclosure | Bitzero Nordic infrastructure update | https://www.newsfilecorp.com/release/301582 | Bitzero Holdings Inc. | bitzero_newsfile_releases | all-rights-reserved | Bitzero Holdings Inc. | 2026-06-15 | 2026-07-22T03:29:10Z | 402e9589e0cf82c663020a5d98352545e6b1ca582e5e835cd5f8f55ccd4be852 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3c85c95a-5036-5cf2-b9b8-c15070c6aaea.json | https://web.archive.org/web/20260722032910/https://www.newsfilecorp.com/release/301582
3c916b8c-b9e9-572f-b179-e2b2fbb53828 | ["imported:record","metric:power_capacity","milestone:first_operational","milestone:other","role:developer","role:government"] | ["ec8c635b-93db-5c3c-904e-820b7c4f1233"] | news | Microsoft obtiene luz verde para su ambicioso proyecto de centros de datos en Aragón | https://forbes.es/empresas/828243/microsoft-obtiene-luz-verde-para-su-ambicioso-proyecto-de-centros-de-datos-en-aragon/ | Forbes España | forbes.es | source-terms-not-recorded | Forbes España | 2025-11-14 | 2026-10-09 | 925ed1313fbda1781670d1935ccfe139098e7d3757cc6d39954b86782c4ba9c4 | day | source_record_projection | microsoft-aragon-villamayor-de-gallego | s4 | d2af0f994a460d635bbec1a07ec9c75d3ea424551a637463b05ddc35b2a2a30b | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3c916b8c-b9e9-572f-b179-e2b2fbb53828.json | https://web.archive.org/web/20261009/https://forbes.es/empresas/828243/microsoft-obtiene-luz-verde-para-su-ambicioso-proyecto-de-centros-de-datos-en-aragon/
3ca04bf3-2438-554c-8f7a-ac8c8167e22c | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:power_capacity","milestone:other","power_source:grid","power_source:solar","power_source:wind","role:operator"] | ["c52dcc98-dfd2-5012-8703-5d9e24de51b2"] | company_disclosure | Mumbai data center | https://www.sifytechnologies.com/data-center/mumbai-data-center/ | Sify Technologies | www.sifytechnologies.com | source-terms-not-recorded | Sify Technologies |  | 2026-10-09 | dd5f16d9d02aa25cabc1a100d539005aa49a1b87c735733276288042313ebc07 | unknown | source_record_projection | sify-rabale-navi-mumbai | s2 | f90080b82ee86a1325331b42b98916e8af2adb26691fc1b4b755ddf2a1092cd7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3ca04bf3-2438-554c-8f7a-ac8c8167e22c.json | https://web.archive.org/web/20261009/https://www.sifytechnologies.com/data-center/mumbai-data-center/
3cb5d028-a110-558f-b9c3-69f22e0c699a | ["context:source_location_identity","physical_status"] | ["acf9eda7-3b44-5e9b-8c40-62783a7e0aa0"] | company_disclosure | CRA reports active execution at the Prague Gateway DC site | https://www.linkedin.com/embed/feed/update/urn:li:activity:7496145983718969344 | CRA | cra_linkedin_company_posts | all-rights-reserved | CRA | 2026-08-20 | 2026-09-07T02:18:47Z | 2fd6c4a5b292384b2ee76ed9841171ccaaf791d51cf9631634c10a46243703a4 | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3cb5d028-a110-558f-b9c3-69f22e0c699a.json | https://web.archive.org/web/20260907021847/https://www.linkedin.com/embed/feed/update/urn:li:activity:7496145983718969344
3cc51408-77e7-5ab2-8cbc-55ff0db95848 | ["imported:record","role:developer"] | ["dc6f83d9-dac5-563a-ba7e-ff18e27ba506"] | company_disclosure | Amazon plans to invest $20 billion in Pennsylvania to expand cloud computing infrastructure and advance AI innovation | https://www.aboutamazon.com/news/aws/amazon-pennsylvania-investment-cloud-infrastructure-ai-innovation | Amazon | www.aboutamazon.com | source-terms-not-recorded | Amazon |  | 2026-10-09 | c3b6635a91d03e769aca8ca0f07d2c6b66b0e0d22ea08b80661728309bbd88ea | unknown | source_record_projection | aws-salem-township-pennsylvania | s5 | 4dd6dde012f8c93b41327c85112d56db632e692cc634ebdc5e6570285d367043 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3cc51408-77e7-5ab2-8cbc-55ff0db95848.json | https://web.archive.org/web/20261009/https://www.aboutamazon.com/news/aws/amazon-pennsylvania-investment-cloud-infrastructure-ai-innovation
3cdab590-3e47-5972-8a2a-f164a6a59916 | ["physical_status"] | ["c04bedc0-51b3-5d4d-996c-1d1e56de96c0"] | company_disclosure | Goodman advances HKG09 data centre to meet growing demand for digital infrastructure in Hong Kong | https://hk.goodman.com/en/about-goodman/media-centre/news/2026/20260716-goodman-advances-hkg09-groundbreaking | Goodman Group | goodman_hong_kong_news | all-rights-reserved | Goodman Group | 2026-07-15 | 2026-07-20T09:18:30Z | 20e2094f5d2af2bec605bf094444e909a6598cbcb3b85f4e9ac6610f013ef51e | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3cdab590-3e47-5972-8a2a-f164a6a59916.json | https://web.archive.org/web/20260720091830/https://hk.goodman.com/en/about-goodman/media-centre/news/2026/20260716-goodman-advances-hkg09-groundbreaking
3ced538d-64d2-56f9-982d-6e46504192d5 | ["context:site_distinctness","geometry"] | ["867d91cb-7a17-59db-a92e-4a50a499f54f","b3656b35-f3ad-5119-8918-ac5237bf2a7f"] | openstreetmap | OSM attribution and ODbL licence | https://www.openstreetmap.org/copyright | OpenStreetMap Foundation | americas_round30_microsoft_quebec | ODbL-1.0 | OpenStreetMap Foundation |  | 2026-09-09T11:56:34.797Z | e137b7c7edfa01ef2d2245654155001d82b10e6bee8aaa1618fa2ee148bca4d3 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3ced538d-64d2-56f9-982d-6e46504192d5.json | https://web.archive.org/web/20260909115634/https://www.openstreetmap.org/copyright
3cef948d-9ec8-5287-a23c-f3d70d2a7bdd | ["context:site_distinctness","geometry"] | ["c4ffa53e-bb43-5af1-9e07-aa5045ea480b"] | government_record | Toronto address point 30029368: explicit EPSG4326 service response | https://gis.toronto.ca/arcgis/rest/services/cot_geospatial27/FeatureServer/101/query?where=ADDRESS_POINT_ID%3D30029368&outFields=ADDRESS_POINT_ID,ADDRESS_ID,ADDRESS_NUMBER,LINEAR_NAME_FULL,MAINT_STAGE,ADDRESS_CLASS,ADDRESS_CLASS_DESC,ADDRESS_FULL,LONGITUDE,LATITUDE&returnGeometry=true&outSR=4326&f=pjson | City of Toronto | americas_africa_round10_etobicoke | Open Government Licence - Toronto | City of Toronto |  | 2026-09-08T23:54:51.001Z | bc22c55cababccd35d8157a79139855be83b519db738d288c13c3a6ec1521185 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3cef948d-9ec8-5287-a23c-f3d70d2a7bdd.json | https://web.archive.org/web/20260908235451/https://gis.toronto.ca/arcgis/rest/services/cot_geospatial27/FeatureServer/101/query?where=ADDRESS_POINT_ID%3D30029368&outFields=ADDRESS_POINT_ID,ADDRESS_ID,ADDRESS_NUMBER,LINEAR_NAME_FULL,MAINT_STAGE,ADDRESS_CLASS,ADDRESS_CLASS_DESC,ADDRESS_FULL,LONGITUDE,LATITUDE&returnGeometry=true&outSR=4326&f=pjson
3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a | ["imported:record","imported:status","metric:power_capacity","milestone:other","power_source:other","role:developer","role:government","role:power_supplier"] | ["5d11dbb6-e8aa-5602-9c7c-8997b1c620c1"] | news | Data centres: EU gives the green light to the Eni-Khazna joint venture. Lombardy hub set to accelerate | https://en.ilsole24ore.com/art/data-centre-eu-gives-green-light-to-eni-khazna-joint-venture-lombardy-hub-to-be-accelerated-AJl2Zcj | Il Sole 24 Ore | en.ilsole24ore.com | source-terms-not-recorded | Il Sole 24 Ore | 2026-08-10 | 2026-10-09 | 3db0d30135348bfcf27a9600a0a72a6d7e2c52e0df680e3fe8a6e537d4c4c7af | day | source_record_projection | eni-khazna-ferrera-erbognone | s3 | a0cb3643305f3a5a888c331dde151b57fce4ada563e49634d96a348a6f0ea568 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3d3ba2e4-8795-5efc-b13e-9d6eacf95b5a.json | https://web.archive.org/web/20261009/https://en.ilsole24ore.com/art/data-centre-eu-gives-green-light-to-eni-khazna-joint-venture-lombardy-hub-to-be-accelerated-AJl2Zcj
3d7442c7-1c78-5134-8b9c-12581486464e | ["context:geometry_identity"] | ["1861d9fb-3980-5a16-baa1-c32762e244c1"] | government_record | City of San Jose Major Private Development record for CP23-016 | https://geo.sanjoseca.gov/server/rest/services/OPN/OPN_OpenDataService/MapServer/455 | City of San Jose | city_of_san_jose_major_private_developments | rights-status-disclaimer-fact-extraction-only | City of San Jose |  | 2026-08-23 | 7ce046444d2a1ee327d8994d17d2d13a2016367b8c43c2aef047eab52ec1da08 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3d7442c7-1c78-5134-8b9c-12581486464e.json | https://web.archive.org/web/20260823/https://geo.sanjoseca.gov/server/rest/services/OPN/OPN_OpenDataService/MapServer/455
3d8d0c3d-24da-5903-a27e-3ace4ec4925f | ["context:multi_site_program","imported:geometry","imported:record","metric:investment","metric:jobs_construction","metric:jobs_permanent","metric:power_capacity","milestone:announced","role:developer","role:tenant"] | ["b75695b9-38e3-58ec-baf2-039179ab353a"] | company_disclosure | CoreWeave Announces Multi-Billion Dollar Commitment to AI Infrastructure in Pennsylvania | https://coreweave.com/news/coreweave-announces-multi-billion-dollar-commitment-to-ai-infrastructure-in-pennsylvania | CoreWeave | coreweave.com | source-terms-not-recorded | CoreWeave | 2025-07-15 | 2026-10-09 | 3be2df33a24bd0edd66b48c068023e3c3d894e8f35b6d4fb76b41e7b722fb0d7 | day | source_record_projection | coreweave-lancaster-pennsylvania | s1 | 3da7b985dea6aab54b6d7610b08c127892b84b6825d60e166f63e4d3b65a78de | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3d8d0c3d-24da-5903-a27e-3ace4ec4925f.json | https://web.archive.org/web/20261009/https://coreweave.com/news/coreweave-announces-multi-billion-dollar-commitment-to-ai-infrastructure-in-pennsylvania
3d965061-2afb-5201-b178-6690a45d1f18 | ["imported:geometry","imported:record","imported:status","metric:buildings","metric:land_area","milestone:first_operational"] | ["d654ea2a-ea8e-564e-a1df-67f35d52ebbc"] | news | Construction begins on first hyper-scale data center in Pima County | https://www.kold.com/2026/04/25/construction-begins-first-hyper-scale-data-center-pima-county/ | KOLD News 13 | www.kold.com | source-terms-not-recorded | KOLD News 13 | 2026-04-24 | 2026-10-09 | b59904404725f2515cae9af8a5b36b7ccd27fedeb02c9b91c18cedaab3923cb4 | day | source_record_projection | project-blue-tucson | s6 | 36e90bd020e0cf912c30f63d71e0c1efd8ce8bbc328218d5e7860d7c1996c304 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3d965061-2afb-5201-b178-6690a45d1f18.json | https://web.archive.org/web/20261009/https://www.kold.com/2026/04/25/construction-begins-first-hyper-scale-data-center-pima-county/
3da0d477-2381-54c6-bca3-e3552b21b523 | ["context:multi_site_program","imported:geometry","imported:record","metric:floor_area","metric:investment","metric:land_area","milestone:paused","role:builder","role:developer","role:owner"] | ["86bcbcd1-702d-5afa-aeb8-1cb145224b97","edf978b4-fbe8-5f8a-9fe0-bd1e9f33e1d2","f8377a0f-dc89-5b7a-8257-25f25cdbac43"] | trade_press | Microsoft Hits Pause Button on $1B in Data Centers in Ohio | https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio | Engineering News-Record | www.enr.com | source-terms-not-recorded | Engineering News-Record | 2025-04-10 | 2026-10-09 | f2935b45398d6e2da10846e47bae4d560dad4d40e39592f313a08c14bcdd22c0 | day | source_record_projection | microsoft-licking-county-ohio | s2 | aa63c46124d3685f68abaa56575f892aa7a9a9c91345273642a9a103e42db940 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3da0d477-2381-54c6-bca3-e3552b21b523.json | https://web.archive.org/web/20261009/https://www.enr.com/articles/60572-microsoft-hits-pause-button-on-1b-in-data-centers-in-ohio
3dd97b1c-26ad-5403-99cb-2ed24b8f815f | ["imported:record","milestone:other","role:power_supplier"] | ["9002afae-5b81-5c8c-a6f9-4504c91e8624"] | news | xAI buys Southaven property | https://desotocountynews.com/desoto-county-news/xai-buys-southaven-property/ | DeSoto County News | desotocountynews.com | source-terms-not-recorded | DeSoto County News | 2025-07-18 | 2026-10-09 | bebdb6473f466af30ee853f276b731af59e64bccea7581ce29e22ced62b8bb81 | day | source_record_projection | xai-colossus-2-memphis | s3 | a96b3341db0b72f4eeb487d50474903219c98fa2d20b32ec4e3af47c0c0a03d7 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3dd97b1c-26ad-5403-99cb-2ed24b8f815f.json | https://web.archive.org/web/20261009/https://desotocountynews.com/desoto-county-news/xai-buys-southaven-property/
3df67d67-97f9-5a91-8efc-a006dd5932b5 | ["imported:record","metric:power_capacity","milestone:other","power_source:grid","role:developer","role:utility"] | ["d87a919b-df32-53fa-bc01-47b7f6f1dce9"] | company_disclosure | Core Scientific completes acquisition of Polaris DS, advancing planned Muskogee expansion to 1.5 GW of gross power | https://investors.corescientific.com/news-events/press-releases/detail/142/core-scientific-completes-acquisition-of-polaris-ds-advancing-planned-muskogee-expansion-to-1-5-gw-of-gross-power | Core Scientific | investors.corescientific.com | source-terms-not-recorded | Core Scientific | 2026-08-14 | 2026-10-09 | 9d5b5910345d55f30d58a56f885a0a85fadbb437462648b444972c0568ad3737 | day | source_record_projection | core-scientific-muskogee | s5 | 27770cbed3a06baa8115f406673dbf040757ebfc6782e12fbac9b4ef314a02c5 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3df67d67-97f9-5a91-8efc-a006dd5932b5.json | https://web.archive.org/web/20261009/https://investors.corescientific.com/news-events/press-releases/detail/142/core-scientific-completes-acquisition-of-polaris-ds-advancing-planned-muskogee-expansion-to-1-5-gw-of-gross-power
3e139db5-f1a0-566e-9f40-383df947e1ea | ["imported:geometry","imported:record","imported:status","milestone:announced","role:developer"] | ["baa5ddbb-3439-5e4f-a03f-265b844b4460"] | trade_press | AirTrunk to invest US$ 3 billion in Johor to build two hyperscale campuses totaling 280MW capacity | https://w.media/airtrunk-to-invest-us-3-billion-in-johor-to-build-two-hyperscale-campuses-totaling-280mw-capacity/ | W.Media | w.media | source-terms-not-recorded | W.Media | 2026-04-30 | 2026-10-09 | 5f80b028324dfe000c7677861c29c26febe73498e7549f807fe19a22e94d147f | day | source_record_projection | airtrunk-jhb3-iskandar-puteri | s3 | 53ca2c2a255790080b0498d64eaaeb2494166033ef54efda8388e43fd03a5744 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3e139db5-f1a0-566e-9f40-383df947e1ea.json | https://web.archive.org/web/20261009/https://w.media/airtrunk-to-invest-us-3-billion-in-johor-to-build-two-hyperscale-campuses-totaling-280mw-capacity/
3e2be26d-bcc7-5313-a9d8-9886d2157402 | ["context:site_distinctness","geometry"] | ["9217888a-3e78-5b75-ac86-bd32ef026084"] | openstreetmap | Exact-address Nominatim building point for Marsstraße 5 | https://nominatim.openstreetmap.org/search?q=Marsstrasse%205%20Kirchheim%20bei%20Munchen&format=jsonv2&addressdetails=1 | OpenStreetMap contributors / Nominatim | europe_mena_round10_expansion_asia | ODbL-1.0 | © OpenStreetMap contributors |  | 2026-09-08T23:44:55.164Z | ba7202d49745af085b316f09e5479630516441074db138dea755bdf4ca6c1026 | unknown | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3e2be26d-bcc7-5313-a9d8-9886d2157402.json | https://web.archive.org/web/20260908234455/https://nominatim.openstreetmap.org/search?q=Marsstrasse%205%20Kirchheim%20bei%20Munchen&format=jsonv2&addressdetails=1
3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c | ["imported:geometry","imported:record","imported:status","metric:jobs_construction","metric:jobs_permanent","metric:land_area","milestone:construction_started","role:builder","role:developer"] | ["c01906b8-f76a-5afe-ae86-ea56184443f3"] | company_disclosure | Nebius breaks ground on gigawatt-scale AI factory in Independence, Missouri | https://nebius.com/newsroom/nebius-breaks-ground-on-gigawatt-scale-ai-factory-in-independence-missouri | Nebius | nebius.com | source-terms-not-recorded | Nebius | 2026-05-12 | 2026-10-09 | c75e19780ed649661b298c710d655a50d63d865f13a9e3f0aa6ba455849d8294 | day | source_record_projection | nebius-independence-missouri | s1 | 520960b450397b2cfae36eb12989945f7e799ceb6836cefd2f9542e954ffef16 | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3e2c6a6a-dcb8-5d1c-9e01-9b943b94671c.json | https://web.archive.org/web/20261009/https://nebius.com/newsroom/nebius-breaks-ground-on-gigawatt-scale-ai-factory-in-independence-missouri
3e31f188-1822-59b3-a3ae-ffd7f298725c | ["context:geometry_identity","context:site_distinctness","physical_status"] | ["1404f5cd-04ee-57ea-8f73-91992fea0552"] | company_disclosure | Turner July 16 Richland Parish interior buildout observation | https://www.turnerconstruction.com/insights/expanded-meta-data-center-creates-more-jobs-and-opportunity-in-richland-parish-louisiana | Turner Construction Company | meta_round10_independent_review | all-rights-reserved | Turner Construction Company | 2026-07-16 | 2026-09-08T23:44:14Z | f9536829eedf4c5226ef71cec78fb4979a3cf05d3368d98cd79b3d52dad569cb | day | inherited_unspecified |  |  |  | https://kiankyars.github.io/datacenter-atlas/api/v1/evidence/3e31f188-1822-59b3-a3ae-ffd7f298725c.json | https://web.archive.org/web/20260908234414/https://www.turnerconstruction.com/insights/expanded-meta-data-center-creates-more-jobs-and-opportunity-in-richland-parish-louisiana